|  |  |  |  |
| --- | --- | --- | --- |
| **Scope:** Partition Walls | **ITP Document No.:** 1 | **Revision No.** A | **Date of Revision:** 24/03/2023 |
| **Project Name:** Melbourne Quarter Tower – Medibank Fitout | | **Organization Name:** Lendlease | |
| **Project Address:** 699 Collins Street, Docklands VIC 3008 | | | |
| **Prepared by** | | | |
| **Name:** Austin Han | **Position:** Contract Administrator | **Signature:** | **Date:** |
| **Approved by** | | | |
| **Name:** Greg Edwards | **Position:** Construction Manager | **Signature:** | **Date:** |

|  |  |
| --- | --- |
| **Level:** | **Room No./Area:** |

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| W = Witness, HP = Hold Point, S = Surveillance, R = Review | | | | | | | | |
| **Item** | **Activity** | **Reference Documents** | **Acceptance Criteria** | **Frequency** | **Verification Records/Comments** | **Inspection By** | | |
| **Subcontractor** | **Lendlease** | **Client** |
| 1 | Set out walls | Architect drawings (MQT\_ID series)  Architect Specification (MQT\_IS\_SPE\_1) | Partition Plan and Partition Wall Details approved by Lendlease.  Architectural Specification – 0522 Partitions And Linings  Australian Standard: AS/NZS 4600:2005 , AS/NS 1170:2002 | Each location | Visual  Checklist | S | S |  |
| 2 | Furring channel to walls | Architect drawings (MQT\_ID series)  Architect Specification (MQT\_IS\_SPE\_1) | Partition Plan and Partition Wall Details approved by Lendlease.  Architectural Specification – 0522 Partitions And Linings  Studco Wall design & installation manual Volume 3.2  Australian Standard: AS/NZS 4600:2005 , AS/NS 1170:2002 | Each location | Visual  Checklist | S | S |  |
| 3 | Metal stud wall frame | Architect drawings (MQT\_ID series)  Architect Specification (MQT\_IS\_SPE\_1)  Refer to Lendlease CiDD for All Alerts and Guidelines for Smoke doors and Baffle | Partition Plan and Partition Wall Details approved by Lendlease.  Architectural Specification – 0522 Partitions And Linings  Studco Wall design & installation manual Volume 3.2  Australian Standard: AS/NZS 4600:2005 , AS/NS 1170:2002 | Each location | Visual  Checklist | S | S |  |
| 4 | Noggins |  | As per scope of work.  Studco Wall design & installation manual Volume 3.2  Architectural Specification – 0522 Partitions And Linings  Australian Standard: AS/NZS 4600:2005 , AS/NS 1170:2002 | Each location | Visual  Checklist | S | S |  |
| 5 | Check no screws in deflection head |  | No screws in deflection head | Each location | Visual  Checklist | S | S |  |
| 6 | Service Check for pre-installation of sheets | Service Sign-off checklist | All service checklists are signed off by relevant trades | Each location | Visual  Checklist | S | HP |  |
| 7 | Sheet all walls | Architect drawings (MQT\_ID series)  Architect Specification (MQT\_IS\_SPE\_1)  Refer to Lendlease CiDD for All Alerts and Guidelines for Fibre Cement and Smoke doors and Baffle | Partition Plan and Partition Wall Details approved by Lendlease.  Check wall types before installation (F/R, Acoustic, Wet Area, PBD etc).  Architectural Specification – 0522 Partitions And Linings  Boral installation manual revision 2016. Batts insulation installation guide.  Australian Standard: AS/NZS 2589.1:1997 | Each location | Visual  Checklist | S | S |  |
| 8 | Caulking |  | Boral installation manual revision 2016  Australian Standard: AS 1530.4-2014, AS4072.1-2005, AS1157-1972 | Each location | Visual  Checklist | S | S |  |
| 9 | Check insulation in walls | Architect drawings (MQT\_ID series)  Architect Specification (MQT\_IS\_SPE\_1) | Partition Plan and Partition Wall Details approved by Lendlease.  Batts Insulation Installation Guidelines  Architectural Specification – 0819 Insulation and Barriers  Australian Standard: AS/NZS 4859:1 – 2018, AS/NZS 1530.3 : 1999, AS/NZS1530 Part 1: 1994 | Each location | Visual  Checklist | S | S |  |
| 10 | Stopping to walls | Refer to Lendlease CiDD - Alerts and Guidelines for Setting Compounds for Plasterboard | Boral installation manual revision 2016.  Australian Standard: AS/NZS 2589.1:1997 | Each location | Visual  Checklist | S | S |  |
| 11 | Sanding to walls |  | Boral installation manual revision 2016.  Australian Standard: AS/NZS 2589.1:1997 | Each location | Visual  Checklist | S | S |  |
| 12 | Clean up |  | Waste all cleaned. Tools and materials placed well. | Each location | Visual  Checklist |  | R |  |
| 13 | Check walls for patching | Architect drawings (MQT\_ID series)  Architect Specification (MQT\_IS\_SPE\_1) | Partition Plan and Partition Wall Details approved by Lendlease. | Each location | Visual  Checklist | S | S |  |

|  |  |
| --- | --- |
| Comments: | |
| Date of Inspection: | Carried out by: |

\*This document will be provided to evidence compliance to applicable works