|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | | | | | | | | | | **nightshift** | | | | |
| Design to be confirmed | | | | |
| **EBOP NOC AC PROGRAMME** | | | | | | | | | | **New Program Sites** | | | | |
| **Completed** | | | | |
| **To be completed by others** | | | | |
| **Delivery start date** | **Delivery end date** | **Job Number** | **Site Name** | **Site Location** | **SH-RS** | **RP** | **Lanes** | **Surface Type** | **Original Area Programmed (m2)** | **Thickness (mm)** | **Tonnes programmed** | **Original deeplift area** | **Deeplift depth** | **Deeplift Tonnages** |
| 30/09/2024 | 11/10/2024 |  | Sala street | Data type icon Rotorua | 030-0144 | 1830-2000 | All | AC14 | 2040 | 50 | 245 | 2040 | 170 | 832 |
| 13/10/2024 | 14/10/2024 | GT0524 | Puarenga Bridge East - D | Data type icon Rotorua | 030-0147-D | 270-410 | R2 | AC14 | 424 | 50 | 51 | 0 | 0 | 0 |
| 13/10/2024 | 14/10/2024 | GT0524 | Puarenga bridge east - D | Data type icon Rotorua | 030-147 | 410-479 | R1,R2 | SMA? | 483 | 50 | 68 | 483 | 170? | 197 |
| 15/10/2024 | 16/10/2024 | GT0524 | Puarenga Bridge - I | Data type icon Rotorua | 030-0147-I | 380-464 | L2 | AC14 | 487 | 50 | 58 | 84 | 100 | 20 |
| 17/10/2024 | 22/10/2024 | GT0524 | Hamiora place D and I | Data type icon Rotorua | 030-147 | 479-530 | R1, R2, L1,L2 | SMA? | 1284 | 50 | 180 | 1284 | 170? | 524 |
| 23/10/2024 | 23/10/2024 | GT0524 | Ngapuna - I | Data type icon Rotorua | 030-0147-I | 516-810 | L2 | AC14 | 1177 | 50 | 141 | 0 | 0 | 0 |
| 24/10/2024 | 25/10/2024 | GT0524 | Ngapuna - I | Data type icon Rotorua | 030-0147-I | 516-573 | L1 | AC14 | 324 | 50 | 39 | 0 | 0 | 0 |
| 3/11/2024 | 6/11/2024 | GT0522 | Tarawera to Tennyson | Data type icon Rotorua | 030-0147/01.11 | 1300-1760 | R1 | AC14 | 2497 | 50 | 300 | 1628 | 100 | 391 |
| 7/11/2024 | 11/11/2024 | GT0466 | Eruera street | Data type icon Rotorua | 30A-0000 | 0-85 | R1,R2 | SMA11-Melt; AC20(hi-Mod) | 796 | 45 | 111 | 796 | 170 | 325 |
| 12/11/2024 | 13/11/2024 | GT0521 | Cochrane St Pedestrian Xing | Data type icon Rotorua | 005-0045/01.95-I | 3108-3173 | L1 | SMA11-Melt | 425 | 50 | 51 | 189 | 100 | 45 |
| 14/11/2024 | 17/11/2024 | GT0520 | Rainbow Farm to Cochrane | Data type icon Rotorua | 005-0045/01.95-D | 2470-2541 | R1 | SMA11-Melt | 586 | 50 | 70 | 415 | 100 | 99 |
| 25/11/2024 | 25/11/2024 | GT0528 | Dunn Rd Intersection I | Data type icon Kaingaroa Forest | 038-0000 | 17477-17500 | All | SMA12.5 (60/70); AC20(PMB) | 472 | 50 | 57 | 95 | 100 | 23 |
| 26/11/2024 | 26/11/2024 | GT0528 | Dunn Rd Intersection I | Data type icon Kaingaroa Forest | 038-0017 | 0-16 | All | SMA12.5 (60/70); AC20(PMB) | 374 | 50 | 45 | 62 | 100 | 15 |
| 27/11/2024 | 27/11/2024 | GT0527 | Goudies Rd Intersection | Data type icon Kaingaroa Forest | 038-0000 | 17167-17200 | All | SMA12.5 PMB | 1133 | 50 | 136 | 0 | 0 | 0 |
| 10/02/2025 | 13/02/2025 | GT0519 | Fishermans bend | Waioeka Gorge | 002-0334 | 5880-6130 | All | SMA11-Melt | 2700 | 50 | 324 | 0 | 0 | 0 |
| 14/02/2025 | 19/02/2025 | GT0518 | Balls Bluff Waterfall | Waioeka Gorge | 002-0334 | 2669-3016 | All | SMA11-Melt | 2849 | 45 | 399 | 299 | 100 | 72 |
| 20/02/2025 | 24/02/2025 | GT0525 | St John Rab | Data type icon Ōpōtiki | 035-0000 | 873-940 | All | SMA | 1497 | 50 | 180 | 160 | 130 | 50 |
| 25/02/2025 | 28/02/2025 | GT0478 | Gauging station corner | law Glade/waimana | 002-0258 | 8451-8661 | All | SMA11-Melt | 1890 | 45 | 265 | 1197 | 100 | 287 |
| 3/03/2025 | 5/03/2025 | GT0475 | Reids Road I | Data type icon Tāneatua | 002-0258 | 1352-1437 | All | SMA11-Melt | 1221 | 45 | 171 | 223 | 150 | 80 |