## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Precast Grouting - |  |  |  |  | Yes | QA - Precast Grouting Checklist (V1) | 083737f9-e514-4e87-abc0-30ee882af864
checkpoint-status |  |  | checkpoint | Grouting Details
text | f8594738-facd-4b12-a7d0-554989445e46 |  | textbox | Subcontractor/Supplier:
text | 4408521a-1281-4dfc-be17-786de0033469 |  | textbox | Trade:
text | 6e50d3db-f828-448b-88ac-32de4da9e082 |  | textbox | Trade Supervisor:
text | 90dc246d-ce55-4a1c-99fe-f50d4b566246 |  | textbox | Contract Drawings: Please list drawing no’s
text | 5077e7d4-f110-4f46-8c76-ef79c1d047c5 |  | textbox | Area / Location: Please specify area of works
checkpoint-status |  |  | checkpoint | Preparation
label | 179a82aa-8391-4768-8fdd-ab3c3dc22e9b |  | note | Work area clear
label | 6fc03fae-b87f-45d7-892b-916990404d58 |  | note | Power available
label | bc835f63-faaa-4862-bf42-e53336517cbd |  | note | Access scaffold in place
label | 43f3e0c4-5b34-4cd6-8309-a7fc2d793e81 |  | note | Weather conditions favourable
label | ad49922a-3573-46f9-8574-66205c562784 |  | note | Disposal for waste arranged
label | d0787777-edbf-4618-a1fd-06b29fed3081 |  | note | Access clear
label | 3dd185f1-2a16-4f82-86dd-9ece8753a267 |  | note | Water available
checkpoint-status |  |  | checkpoint | Safety Requirements
label | 58f47e5f-150c-4c8a-858a-22fb099d8994 |  | note | Task planning/task analysis completed
label | ae07d140-a533-41f3-bac9-bc6b7081de76 |  | note | Hazards identified and controls in place
checkpoint-status |  |  | checkpoint | HOLDPOINT - All preliminaries and planning in place and approved
checkpoint-status |  |  | checkpoint | Prepare & amp; Drill
text | ea2fa517-e12f-498f-9591-33c2951f152e |  | textbox | Determine hole size - Specify in mm
label | 85ff531a-07f5-496a-8b37-c13d760e29d2 |  | note | Set out checked
label | 201c0c81-be7d-4f37-82c0-ba00970024a6 |  | note | Blow out
label | 8a084dec-fac5-49d2-b178-3d75ce55189e |  | note | Check depth
checkpoint-status |  |  | checkpoint | Grout
label | 5fd458d7-406f-488c-b268-35bd0f5a9b39 |  | note | Grout type as specified
label | 23d381a4-677b-47a9-a65c-079cd34bd9f0 |  | note | Mixed as manufacturers recommendations
text | 7ccbc447-4e29-4631-81b4-5bc31ce2e600 |  | textbox | Mixing time:
label | 549fd937-02c3-45aa-8875-f701b8917a51 |  | note | Flow consistency
label | b9e764f6-04a0-49d6-a347-5d43f1e7418d |  | note | Water meter checked
checkpoint-status |  |  | checkpoint | HOLDPOINT - Inspected by engineer/client rep/ ABL
checkpoint-status |  |  | checkpoint | Grout to holes
label | 5fd22b2b-ee20-489d-95c4-af55c2aa384d |  | note | Holes grout filled
label | ca1ace6e-07ad-4f02-86bd-4b9c80e18e87 |  | note | Bars installed
label | 356a9955-5a5a-4a7c-a71b-ab685d927491 |  | note | Grout test taken
label | 85e58388-a2b0-4cea-addb-d64c6d1e636e |  | note | Top up as required
checkpoint-status |  |  | checkpoint | Completion
text | 9f236918-f976-4187-8fa5-f959505f4583 |  | textbox | Curing time: Specify in Days
label | dca7340d-a855-45fd-b73f-d2550a78abc9 |  | note | Area cleaned up
checkpoint-status |  |  | checkpoint | Consultants
label | eca966e7-258a-4857-87e5-346c4c3706f7 |  | note | If Yes put down the reason:
label | 6fe34e8c-5561-48dd-a5b0-ffc3054cc4b9 |  | note | Council required for inspection: Yes /No
label | 0ff6d26c-a06e-4c8e-a49c-2d5f624431a3 |  | note | Client required for inspection: Yes/No
label | 15d89eb9-4396-455d-bf4b-f130d6a6aa75 |  | note | Engineer required for inspection: Yes/ No
label | ceb4e0b3-c7c1-4275-8f9d-82a6e4c87b1f |  | note | Notified Council/Client/Consultant 48 hours prior :Yes/No
label | 34f592cb-4378-498a-91a7-961fdce35760 |  | note | Photo evidence required by Council/Client/Consultant: Yes/No
label | 9d99427d-e9a0-4406-a8f3-8d98e66c9fc0 |  | note | Inspection not required Yes/No
text | a8fb655d-f3cf-4284-a083-9053b69f8d11 |  | textbox | For those that are "YES" explain here
checkpoint-status |  |  | checkpoint | As completed by the Subcontractor
text | 7d53a0d6-ecfe-4d81-87b7-895a970bdc29 |  | textbox | Name
text | af566dfe-815f-4084-ad16-f7a9db61074f |  | textbox | Date
label | 70eb5b4e-b62c-41a0-995d-9388ffc11deb |  | note | Signed (click the paperclip)
checkpoint-status |  |  | checkpoint | As checked by Amalgamated Builders Ltd
text | 9c46ee8a-02fe-46a7-b560-8da731ad0712 |  | textbox | Name
text | b52008fa-839f-44d7-900c-2a6639e23ebb |  | textbox | Date
label | 852ae61b-9b86-4982-ac2d-341c908ee940 |  | note | Signed (click the paperclip)
checklist-sectioned |  |  | checklist | Piling QA - |  |  |  |  | Yes | QA - Piling Checklist | 0bbf8c11-fa70-45b3-bccc-6c9a53ebfa2c
checkpoint-group |  |  | section | Pre commencement - Setout, Establishment and Observations
checkpoint-status |  |  | checkpoint | Piles setout, surveyed and clearly marked
checkpoint-status |  |  | checkpoint | Accurate RL confirmed for piling reference
checkpoint-status |  |  | checkpoint | Acceptable site conditions and access for piling rig
checkpoint-status |  |  | checkpoint | Additional photos/ observations / reports attached
checkpoint-group |  |  | section | Individual Piling QA
checkpoint-group |  |  | section | Inspections/ Completion and Handover
checkpoint-status |  |  | checkpoint | Relevant inspections attached
checkpoint-status |  |  | checkpoint | Piling spoil removed and general observations attached
checkpoint-status |  |  | checkpoint | Any additional completion/ handover attachments
checkpoint-status |  |  | checkpoint | All piles completed correctly within tolerance
checklist-flat |  |  | checklist | Exterior Cladding |  |  |  |  | Yes | QA - Exterior ClQA -ing Checklist | 132eb429-3833-42b0-986d-2164f0a3be47
checkpoint-status |  |  | checkpoint | Membrane/Fixing brackets complete
checkpoint-status |  |  | checkpoint | Cavity system installed
checkpoint-status |  |  | checkpoint | Cladding overhangs FFL at correct hieghts
checkpoint-status |  |  | checkpoint | Flashings complete
checkpoint-status |  |  | checkpoint | Windows/Doors Installed
checkpoint-status |  |  | checkpoint | Cladding contractor sign-off
checklist-flat |  |  | checklist | Paving |  |  |  |  | Yes | Landscaping QA - Paving | 208302c7-239a-4a92-9da4-3c1d43a198f3
checkpoint-status |  |  | checkpoint | Exposed Aggregate & Saw Cuts
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Natural Balast Paving
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Firth Gobi Block
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Firth Flowpave
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Asphalt
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | V Channel
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Kerb
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Walks' natural (grey) tile paver
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | External Steps
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Canterbury Club Gate
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All Paving completed, reviewed and approved
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checklist-flat |  |  | checklist | Council Inspection - |  |  |  |  | Yes | Add Council Inspection Checklist (V3) | 234064a5-0e0d-403f-b03e-8fb9d214ed72
checkpoint-status |  |  | checkpoint | Council inspection completed, attached and any relevant observations closed out
label | 3444c651-e5e2-4a4d-87f9-f06b48de741d |  | note | PASS once all information is attached including Observations/Failed comments with evidence of closeout
text | dc83a024-74b8-4254-9ddd-e5098acc1bd8 |  | textbox | Date of Inspection:
text | 9078e12c-052d-4e8e-aaa0-bf0ee4a8e674 |  | textbox | Type of Inspection:
text | 52f91732-bf1d-45c6-bd07-b9da5bc92d07 |  | textbox | Area inspection relates to
select | b4da29de-ea63-439e-a19e-c0f75d938880 |  | dropdown | Inspection Outcome | Pass, Fail, Partial Pass,Completed, N/A
boolean | e163160e-48f6-4a1e-925a-fc9517380516 |  | tickbox | Council Inspection attached
text | 202aee45-e7db-4a11-a3cd-d58c1ed02669 |  | textbox | Failed Comment(s) & Required Action
label | 3c7bfeb2-48cc-4c75-8c53-db434c64e996 |  | note | Select N/A if there are no Observations/Failures requiring closeout
button | 5fc35eaa-61ff-4a6a-85df-bfb72c73a67d |  | button | All Relevant Observation Closeout evidence attached below if applicable (Pass once completed) | Pass, N/A
holdpoint |  |  | signoff | Request Signoff
checklist-sectioned |  |  | checklist | Drainage Inspection Checklist |  |  |  |  | Yes | Drainage Inspection Checklist | 249de87b-4ccd-45b3-8849-91b56e48e713
checkpoint-group |  |  | section | Pre Construction
checkpoint-status |  |  | checkpoint | All current IFC documentation, Statutes, Regulations and Manufacturers Instructions confirmed
checkpoint-status |  |  | checkpoint | Confirm all health and safety measures in place and understood
checkpoint-status |  |  | checkpoint | Identify all concealed services and hazards with means of control
checkpoint-status |  |  | checkpoint | Protect the public and adjacent property by providing all safety barriers, hoardings, underpinning, props, covers and the like
checkpoint-status |  |  | checkpoint | Drainlayer confirmed currently licensed
checkpoint-status |  |  | checkpoint | All TA notices and consents received and sighted
checkpoint-status |  |  | checkpoint | Confirm all materials conform to standards and specification, are ordered and will be available to meet the programmed installation
checkpoint-status |  |  | checkpoint | Confirm quantity / quality as ordered / specified and free of defect / damage on receipt
checkpoint-status |  |  | checkpoint | All work coordinated with all other trades and problem areas eliminated
checkpoint-group |  |  | section | During Construction
checkpoint-status |  |  | checkpoint | Confirm safety measures in place
checkpoint-status |  |  | checkpoint | Confirm substrate is approved to receive work
checkpoint-status |  |  | checkpoint | Confirm all work installed as specified
checkpoint-status |  |  | checkpoint | All TA / Consultant tests, inspections and approvals given and as built drawings marked up before work is covered in
checkpoint-status |  |  | checkpoint | Backfill checked, compacted and finished to specified / approved levels
checkpoint-group |  |  | section | On Completion
checkpoint-status |  |  | checkpoint | Remove all rubbish, surplus material and plant from the site
checkpoint-status |  |  | checkpoint | All works, roadways, finishes and structures confirmed undamaged / clean
checkpoint-status |  |  | checkpoint | System final inspection by TA / Consultants and approved
checkpoint-status |  |  | checkpoint | Supply marked up as-built drawings
checkpoint-status |  |  | checkpoint | ABL confirm completion and hand over of the work
checklist-sectioned |  |  | checklist | QA - GIB Fixing/Stopping |  |  |  |  | Yes | QA - GIB Fixing/Stopping | 272e73c6-5039-4ea2-9e45-001c111b01cf
checkpoint-group |  |  | section | Prestart Checks
checkpoint-status |  |  | checkpoint | Area, ready, clear & safe to start
checkpoint-status |  |  | checkpoint | Framing spacings correct
checkpoint-status |  |  | checkpoint | Nog/dwang & solid blocking correct
checkpoint-status |  |  | checkpoint | All previous QA requirements met (Preline Inspections,Insulation, Services, Framing) - approval given to line the area
checkpoint-group |  |  | section | Materials Check
checkpoint-status |  |  | checkpoint | Correct board type & thickness
checkpoint-status |  |  | checkpoint | Fastener type, gauge & length confirmed and correct
checkpoint-status |  |  | checkpoint | All materials correct, on site and accessable
checkpoint-group |  |  | section | Fixing of Board
checkpoint-status |  |  | checkpoint | Correct fastener positions & spacing
checkpoint-status |  |  | checkpoint | Screws not over screwed & flush
checkpoint-status |  |  | checkpoint | Bracing elements correct
checkpoint-status |  |  | checkpoint | Services cutout and accurate/within tolerance
checkpoint-status |  |  | checkpoint | Hatches cut out
checkpoint-status |  |  | checkpoint | Correct sealant used. No gaps.
checkpoint-status |  |  | checkpoint | Joints in multiple layer systems are staggered
checkpoint-status |  |  | checkpoint | No sheet joins on corners of doors/windows
checkpoint-status |  |  | checkpoint | All sheet joins in FRR systems on timber framing
checkpoint-status |  |  | checkpoint | Fixed at 100mm centres if being tiled over
checkpoint-status |  |  | checkpoint | Any additional/relevant information/photos attached
checkpoint-group |  |  | section | Area Handover/Postline Inspection
checkpoint-status |  |  | checkpoint | All Linings installed and area is 100% completed to required specification - reviewed and approved
checkpoint-status |  |  | checkpoint | Area left clean and tidy (attach relevant photos)
checkpoint-group |  |  | section | Gib Stopping
checkpoint-status |  |  | checkpoint | Substrate accepted and approval given to start gib stopping
checkpoint-status |  |  | checkpoint | Correct stopping product and applied correctly
checkpoint-status |  |  | checkpoint | Square stopping, slimlines and joints checked and acceptable
checkpoint-status |  |  | checkpoint | Adequate drying time between applications & No visibal bubbling
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
holdpoint |  |  | signoff | Request Trade Contractor QA & Signoff
checkpoint-status |  |  | checkpoint | All Stopping completed and specified level of finish achieved
holdpoint |  |  | signoff | Raise Remedial/ Request Signoff
checklist-flat |  |  | checklist | Site Concrete - |  |  |  |  | Yes | QA - Site Concrete Checklist | 2d208e06-656b-4695-bec3-56b740c6f834
checkpoint-status |  |  | checkpoint | Excavation depth and location checked and correct
checkpoint-status |  |  | checkpoint | Ground conditions acceptable
checkpoint-status |  |  | checkpoint | Concrete specifications checked, correct and delivery docket photographed
checkpoint-status |  |  | checkpoint | Site concrete placed
text | dbd1f518-4535-5f64-acff-f5c41749144a |  | textbox | Placed by:
checkpoint-status |  |  | checkpoint | Concrete placed to the correct height
checkpoint-status |  |  | checkpoint | Site concrete pour completed and finish acceptable
checklist-sectioned |  |  | checklist | Precast Walls - |  |  |  |  | Yes | QA - Precast Walls Checklist (V3) | 31b22fb1-3744-4a6a-99d6-bded8715f34f
checkpoint-group |  |  | section | Pre installation
checkpoint-status |  |  | checkpoint | Precast manufacturing completed and transported safely to the site
label | d7387eba-ac15-4cd8-af29-0b79bf64df86 |  | note | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Site Setout completed
checkpoint-status |  |  | checkpoint | Panel propping design approved and attached
checkpoint-status |  |  | checkpoint | Precast elements inspected, correct and damage free before placement
checkpoint-status |  |  | checkpoint | All pre installation work completed
holdpoint |  |  | signoff | Request Signoff
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Alignment and levels of the panel checked/correct
checkpoint-status |  |  | checkpoint | Panel propping checked & aligning with approved design
checkpoint-status |  |  | checkpoint | Checked rebar requirements for any insitu stich joints
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Panel installation completed within tolerance in respective area
label | 865b687f-bfbe-402a-bc60-fee340bd4f45 |  | note | Trades QA received, reviewed, attached and approved
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | First Fix Services |  |  |  |  | Yes | QA - First Fix Services | 34fdc2ae-82f7-413e-9489-f5fb8d321679
checkpoint-status |  |  | checkpoint | Plumbing First Fix
holdpoint |  |  | signoff | Request Hold Point Sign Off
checkpoint-status |  |  | checkpoint | Electrical First Fix
holdpoint |  |  | signoff | Request Hold Point Sign Off
checkpoint-status |  |  | checkpoint | Mechanical First Fix
holdpoint |  |  | signoff | Request Hold Point Sign Off
checkpoint-status |  |  | checkpoint | Sprinkler First Fix
holdpoint |  |  | signoff | Request Hold Point Sign Off
checkpoint-status |  |  | checkpoint | Security First Fix
holdpoint |  |  | signoff | Request Hold Point Sign Off
checkpoint-status |  |  | checkpoint | Any additional services/inspections completed
holdpoint |  |  | signoff | Request Hold Point Sign Off
checklist-sectioned |  |  | checklist | Mechanical Services Checklist |  |  |  |  | Yes | Mechanical Services Checklist | 35fcaa50-26fc-40cb-aaa6-7202434d0a9e
checkpoint-group |  |  | section | Pre Installation
checkpoint-status |  |  | checkpoint | IFC documentation, Statutes, Regulations and Manufacturers Instructions current and complete
checkpoint-status |  |  | checkpoint | All Health & Safety requirements implemented and understood
checkpoint-status |  |  | checkpoint | Other trade services and hazards identified with means of control
checkpoint-status |  |  | checkpoint | Provide samples and obtain all approved colours, layout, shop drawings from Architect
checkpoint-status |  |  | checkpoint | Confirm all materials / processes conform to documents in 1. above. Place orders and confirm delivery to meet programme
checkpoint-status |  |  | checkpoint | Material quantity / quality as ordered / specified and free of defect / damage on receipt
checkpoint-status |  |  | checkpoint | Liaise with all other trades (especially Electrician) and resolve coordination problems
checkpoint-status |  |  | checkpoint | Confirm all adjacent finishes are adequately protected
checkpoint-status |  |  | checkpoint | There is an additional sheet of specific checks for this work
checkpoint-status |  |  | checkpoint | ALL checks (including any attachments of specific checks) are complete
checkpoint-group |  |  | section | During Installation
checkpoint-status |  |  | checkpoint | Check and confirm standard of finish and all workmanship is as specified / Manufacturers Instructions and materials damage free before use
checkpoint-status |  |  | checkpoint | Check installation for damage / defect and as specified, record corrections and remedial
checkpoint-status |  |  | checkpoint | Pressure / water test all work and equipment prior to closing in
checkpoint-status |  |  | checkpoint | Check all firewall / floor collars / sleeves, pipe insulation and approval of exposed pipe / duct runs
checkpoint-status |  |  | checkpoint | Confirm all fittings installed in full working order as specified / manufacturers instructions
checkpoint-status |  |  | checkpoint | Check all finishes are free of defect or blemish and moving parts in full working order
checkpoint-status |  |  | checkpoint | ALL checks (including any attachments of specific checks) are complete
checkpoint-group |  |  | section | On Completion
checkpoint-status |  |  | checkpoint | Clean all finished work, make good all defects or damage. Moving parts operate freely
checkpoint-status |  |  | checkpoint | Check work is tested by TA / Consultant and signed / approved / commissioned complete
checkpoint-status |  |  | checkpoint | Remove all rubbish, material and plant from site
checkpoint-status |  |  | checkpoint | Clean all finished work and inspect for damage / defects
checkpoint-status |  |  | checkpoint | ALL checks (including any attachments of specific checks) are complete
checkpoint-status |  |  | checkpoint | Completed final inspection and confirmed complete and in full working order
checkpoint-status |  |  | checkpoint | Mark up as built drawings and operating instructions ready for handing to Contractor on practical completion
checkpoint-status |  |  | checkpoint | Check / confirm all protection of the work is in place for subsequent construction processes
checkpoint-status |  |  | checkpoint | ABL confirm completion and hand over of all work covered by this form
checklist-flat |  |  | checklist | External lighting |  |  |  |  | Yes | Landscaping QA - External Lighting | 3bbaf54c-1e1b-4dae-81bb-1c38a3b3bf27
checkpoint-status |  |  | checkpoint | L1 Bollard Lighttype 1 x 6
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | L2 Tree Uplight x 6
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All Exterior Lighting completed, reviewed and approved
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checklist-flat |  |  | checklist | Consultant Inspection - |  |  |  |  | Yes | Add Consultant Inspection Checklist (V3) | 3df40a7d-3df8-41a8-b81a-3d9a99419cd9
checkpoint-status |  |  | checkpoint | Consultant inspection completed, attached and any relevant observations closed out
text | 7b7a025d-81fa-4409-9ef9-3281b2d64523 |  | textbox | Date of Inspection
text | dd36bd0b-3ee0-4704-912f-3f8f961a2cb6 |  | textbox | Type of Inspection
text | da74bdd5-b086-41a1-94ef-12814f41c3f5 |  | textbox | Area inspection relates to
boolean | e495e118-490c-453e-af9d-13b99904e2dc |  | tickbox | Consultant Inspection attached
button | 0f8e78cc-ac2e-4458-b897-ef644c2cb994 |  | button | All Relevant Observation Closeout evidence attached here if applicable (Pass once completed) | PASS, N/A
label | 1f26a12b-97a7-4354-afab-298bf48ac079 |  | note | "PASS" once corrective closeout evidence has been attached
label | 5b90254d-0b5f-40ab-b626-60f2f7e09379 |  | note | If there are no corrective action requirements select "N/A"
text | 3d06351b-6af4-431a-909b-5a78ef041b49 |  | textbox | Corrective Actions (listed here if required)
holdpoint |  |  | signoff | Request Signoff
checkpoint-status |  |  | checkpoint | Remedial 1
checkpoint-status |  |  | checkpoint | Remedial 2
checkpoint-status |  |  | checkpoint | Remedial 3
checkpoint-status |  |  | checkpoint | Remedial 4
checkpoint-status |  |  | checkpoint | Remedial 5
checkpoint-status |  |  | checkpoint | Remedial 6
checkpoint-status |  |  | checkpoint | Remedial 7
checkpoint-status |  |  | checkpoint | Remedial 8
checkpoint-status |  |  | checkpoint | Remedial 9
checkpoint-status |  |  | checkpoint | Remedial 10
checklist-flat |  |  | checklist | Retaining Walls - |  |  |  |  | Yes | QA - Retaining Wall Checklist | 3e989168-5dbd-43fa-88d9-efc51b5e5d02
checkpoint-status |  |  | checkpoint | Retaining wall(s) setout/heights confirmed
checkpoint-status |  |  | checkpoint | Area prepared - Excavation depths and location correct
checkpoint-status |  |  | checkpoint | General install photos and observations attached
checkpoint-status |  |  | checkpoint | Correct materials used and installed using appropriate methodology
checkpoint-status |  |  | checkpoint | Additional observations/ inspections
checkpoint-status |  |  | checkpoint | Retaining wall completed to required specifications
checklist-flat |  |  | checklist | Timber Framing - |  |  |  |  | Yes | QA - Timber Framing Checklist | 441e60dc-4c37-4133-a52c-dcd1896c65a7
checkpoint-status |  |  | checkpoint | Area and substrates acceptable
checkpoint-status |  |  | checkpoint | Dimensions / locations checked and accurate
checkpoint-status |  |  | checkpoint | All frames are square
checkpoint-status |  |  | checkpoint | Frames are straight and level
checkpoint-status |  |  | checkpoint | Fixings are correct
checkpoint-status |  |  | checkpoint | Any bracing requirements installed
checkpoint-status |  |  | checkpoint | Insulation Installed
checkpoint-status |  |  | checkpoint | Nogs/ service nogs installed correctly as per plan
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | All framing completed correctly within tolerance in respective area
checklist-flat |  |  | checklist | Passive Fire / Approval to line Checklist |  |  |  |  | Yes | QA - Passive Fire/Approval to line | 4499ab12-cdfb-4f65-a134-cb3c32b928c4
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
holdpoint |  |  | signoff | Request Trade Contractor QA & Signoff
checkpoint-status |  |  | checkpoint | All Passive fire elements completed and approval to line
holdpoint |  |  | signoff | Raise Remedial/Request Signoff
checklist-sectioned |  |  | checklist | Membrane Roofing |  |  |  |  | Yes | Membrane Roofing | 4902d69c-30fb-416f-be98-29d7254fb9af
checkpoint-group |  |  | section | Substrate
checkpoint-status |  |  | checkpoint | Substrate membrane & adhesive checked for compatibility
checkpoint-status |  |  | checkpoint | Substrate approved
checkpoint-status |  |  | checkpoint | Surface finish accepted
checkpoint-status |  |  | checkpoint | Surface free from contaminants
checkpoint-status |  |  | checkpoint | Surface drainage discharge outlets and other services fitted & protected
checkpoint-status |  |  | checkpoint | Substrate clean and moisture content at correct level
checkpoint-status |  |  | checkpoint | Substrate cracks & expansion joints addressed
checkpoint-status |  |  | checkpoint | Council inspection required
checkpoint-group |  |  | section | Membrane Installation
checkpoint-status |  |  | checkpoint | Correct membrane applied as per specifications/manufacturer’s recommendations by approved installer
checkpoint-status |  |  | checkpoint | Primer (if required)
checkpoint-status |  |  | checkpoint | Membrane fully supported
checkpoint-status |  |  | checkpoint | Penetrations weather tight
checkpoint-status |  |  | checkpoint | Approved sealant used – type
checkpoint-status |  |  | checkpoint | Drainage / overflow outlets installed
checkpoint-status |  |  | checkpoint | Metallic collars used for drain holes
checkpoint-status |  |  | checkpoint | Gutters / valleys
checkpoint-status |  |  | checkpoint | Eaves drip edges installed
checkpoint-status |  |  | checkpoint | Flashings installed and weather tight
checkpoint-status |  |  | checkpoint | Foot traffic access provided
checkpoint-status |  |  | checkpoint | Flood test (block outlets, ensure no pounding, leaks)
checkpoint-status |  |  | checkpoint | Trades QA Received
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | Windows/Doors |  |  |  |  | Yes | QA - Windows/Doors Checklist | 49607a2d-2569-4e2d-8740-9bdd5dd3ee1c
checkpoint-status |  |  | checkpoint | Rebates installed
checkpoint-status |  |  | checkpoint | Opening Sizes
checkpoint-status |  |  | checkpoint | Sill Tape/Membrane Complete
checkpoint-status |  |  | checkpoint | Fixing adequate
checkpoint-status |  |  | checkpoint | Flashings installed
checkpoint-status |  |  | checkpoint | Weather sealing complete
checklist-flat |  |  | checklist | Rondo Ceiling Checklist |  |  |  |  | Yes | QA - Rondo Ceiling | 49b5ba67-bd8e-410a-b247-6c3a981c82f8
checkpoint-status |  |  | checkpoint | Ceiling heights checked and correct
checkpoint-status |  |  | checkpoint | Correct product and fixing used
checkpoint-status |  |  | checkpoint | Any bracing requirements installed
checkpoint-status |  |  | checkpoint | Nogs/ service nogs installed correctly as per plan
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
holdpoint |  |  | signoff | Request Trade Contractor QA & Signoff
checkpoint-status |  |  | checkpoint | All frondo completed correctly within tolerance in respective area
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checklist-flat |  |  | checklist | Setout/ Surveying Checklist |  |  |  |  | Yes | QA - Setout/Survey Checklist | 50eab666-804c-4dde-9a83-2d246f9c4eb3
checkpoint-status |  |  | checkpoint | Setout/ Surveying Details complete
text | 6c9eac71-e3c8-56d7-a475-6f028940b42d |  | textbox | Who is doing the setout/ survey:
checkpoint-status |  |  | checkpoint | Any RL's setout are correct, labelled and photographed
checkpoint-status |  |  | checkpoint | Any grid setout are correct, labelled and photographed
checkpoint-status |  |  | checkpoint | Any other relevant setout/ survey documentation attached
checklist-flat |  |  | checklist | Skirting and Trims |  |  |  |  | Yes | QA - Skirting and Trims | 52f9abd2-b9b2-4479-959f-4474cc39bb1f
checkpoint-status |  |  | checkpoint | Approval given to install Skirting / trims
checkpoint-status |  |  | checkpoint | Correct materail supplied and used in correct areas as per specification
checkpoint-status |  |  | checkpoint | Correct fixings used as per specification
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
holdpoint |  |  | signoff | Request Trade Contractor QA & Signoff
checkpoint-status |  |  | checkpoint | All skirting & trims completed, checked and approved
holdpoint |  |  | signoff | Raise Remedial/ Request Signoff
checklist-sectioned |  |  | checklist | QA - Double Tee Checklist |  |  |  |  | Yes | QA - Double Tee Checklist | 58174488-05e2-427f-ab57-87b43d34849f
checkpoint-group |  |  | section | Job Details
checkpoint-no-status |  |  | checkpoint | Invercargill CBD Development
label | 4c91b7a4-f574-5488-96c2-5279b41ad183 |  | note | 4543
text | eda1ecfc-a66a-566a-b9d6-bca23eee9d85 |  | textbox | Date:
text | 54281e24-2817-5826-87fc-c09ad495e39b |  | textbox | Unit Type:
text | cbb95483-8614-507d-9b50-4814f86a6995 |  | textbox | Unit Mark:
text | 1e5b4e99-f667-5393-abd4-07e6a5a3f6c2 |  | textbox | Cast Number:
checkpoint-group |  |  | section | Pre-Production Checks
checkpoint-status |  |  | checkpoint | Photograph of day sheet attached
checkpoint-status |  |  | checkpoint | Mould Cleaned
checkpoint-status |  |  | checkpoint | Mould Oiled
checkpoint-status |  |  | checkpoint | Strand Pattern Checked
checkpoint-status |  |  | checkpoint | Strand through Correct Holes in Cross Heads
checkpoint-status |  |  | checkpoint | End plates Fixed
checkpoint-status |  |  | checkpoint | Dimensional Check
checkpoint-status |  |  | checkpoint | Cover Checked
checkpoint-status |  |  | checkpoint | Leg Rebate Check
checkpoint-status |  |  | checkpoint | Flange PVC Ducts
checkpoint-status |  |  | checkpoint | End Cage Checked
checkpoint-status |  |  | checkpoint | Stirrups Fixed
checkpoint-status |  |  | checkpoint | Leg Mesh Check
checkpoint-status |  |  | checkpoint | Unstressed Strand / 20mm Bar
checkpoint-status |  |  | checkpoint | Lifting Checked
checkpoint-status |  |  | checkpoint | Unit Identified
checkpoint-group |  |  | section | Stressing Checks
checkpoint-status |  |  | checkpoint | Grips & Barrells Checked
checkpoint-status |  |  | checkpoint | Strands Not Crossed
checkpoint-status |  |  | checkpoint | Pre- Load
text | 6a0fe117-98e5-5d02-8974-3de8ccfbc081 |  | textbox | kpa
checkpoint-status |  |  | checkpoint | Extension
text | 8d44b78c-cb40-57d7-9e9c-9d815787613a |  | textbox | mm
checkpoint-status |  |  | checkpoint | Gauge Pressure
text | 8ab20b16-39c5-5b02-a39d-9a345484d17c |  | textbox | kpa
checkpoint-group |  |  | section | Concrete Checks
checkpoint-status |  |  | checkpoint | Concrete Vibrated
checkpoint-status |  |  | checkpoint | Surface Broomed
checkpoint-status |  |  | checkpoint | Concrete Docket/s received
checkpoint-status |  |  | checkpoint | Covers On
checkpoint-status |  |  | checkpoint | Test Cylinders Made
checkpoint-status |  |  | checkpoint | Curing on
checkpoint-group |  |  | section | Stripping Checks
checkpoint-status |  |  | checkpoint | Strands cut back flush with ends
checkpoint-status |  |  | checkpoint | Unit Identified
checkpoint-status |  |  | checkpoint | Unit Stacked Correctly
checkpoint-status |  |  | checkpoint | Release Strength
text | 72da1303-fe2b-5b77-8998-012ef1a74671 |  | textbox | MPa
checkpoint-status |  |  | checkpoint | Remedial Required
checkpoint-group |  |  | section | Remedial Work
checkpoint-status |  |  | checkpoint | Remedial Work Required?
text | 1095ce29-0447-5e08-9962-8515387f76f8 |  | textbox | State what work is required
checkpoint-group |  |  | section | Loading / Delivery
checkpoint-status |  |  | checkpoint | Delivery Details
text | 2b97e530-3a2f-57a4-8a6d-87e1d1e7a4d1 |  | textbox | Date Truck loaded
text | 35b118c4-6bfd-58c8-891d-cd8082690480 |  | textbox | Date of delivery
text | e2a141c9-1b0c-536a-b280-8ae84c094c13 |  | textbox | Delivery sheet number recorded
checkpoint-status |  |  | checkpoint | Photos of product on truck
checklist-flat |  |  | checklist | Observation Remedial: |  |  |  |  | Yes | QA - Observation Remedial | 5ce19f1c-88fa-44b5-b81b-3f8b7b6b69b9
checkpoint-status |  |  | checkpoint | Remedial Required
text | 74e557ef-61c4-5057-9518-0f79d4391278 |  | textbox | Action Required
text | 4cbddf9e-74bf-551f-b935-dc464bc8c518 |  | textbox | Remedial Reference (if applicable)
text | c4999122-a277-59d9-b70f-3e9167a09e88 |  | textbox | Location
holdpoint |  |  | signoff | Request Observation Approval
checklist-flat |  |  | checklist | QA - Internal Painting |  |  |  |  | Yes | QA - Internal Painting | 612d634b-51c4-4427-8955-f2cbd51bcdd5
checkpoint-status |  |  | checkpoint | Area and substrates acceptable
checkpoint-status |  |  | checkpoint | Paint specifications and colour checked
checkpoint-status |  |  | checkpoint | First coat/sealant coat completed
checkpoint-status |  |  | checkpoint | Light inspection completed and approved to continue
checkpoint-status |  |  | checkpoint | General comments and photos of additional paint application
checkpoint-status |  |  | checkpoint | Final coat completed
checklist-sectioned |  |  | checklist | Management of Site Fire Risk as part of CPU2 (Evening) |  |  |  |  | Yes | SYS - Management of Site Fire Risk as part of CPU2 (Evening) [old version] | 679ef890-052b-4770-91e5-c070dd8a0b4c
checkpoint-group |  |  | section | Carpark Stairs
checkpoint-status |  |  | checkpoint | Check fire doors are closed on Levels :
checkpoint-status |  |  | checkpoint | Available all Levels and check Hoardings
checkpoint-group |  |  | section | Amenities End (Stair 2.5)
checkpoint-status |  |  | checkpoint | Check fire doors are closed on Levels :
checkpoint-status |  |  | checkpoint | Available all Levels and check Hoardings
checkpoint-group |  |  | section | Farmers Carpark Stairwell 2.3
checkpoint-status |  |  | checkpoint | Farmers Carpark Stairwell - No combustible material within 5m L4
checkpoint-group |  |  | section | Carpark
checkpoint-status |  |  | checkpoint | No combustible material within 5m of stairway
checkpoint-group |  |  | section | Tay St Stairway 2.4
checkpoint-status |  |  | checkpoint | No combustible material within 5m of stairway
checkpoint-group |  |  | section | Retail
checkpoint-status |  |  | checkpoint | No combustible material within 5m of stairway
checkpoint-group |  |  | section | Esk St Stairway 2.2
checkpoint-status |  |  | checkpoint | No combustible material within 5m of stairway
checkpoint-group |  |  | section | Sprinkler Tank
checkpoint-status |  |  | checkpoint | Checked sprinkler tank level (Red arrow down is full)
checkpoint-group |  |  | section | Bike Store Beside Ramp
checkpoint-status |  |  | checkpoint | Bike store is clear of combustibles within 5m
checkpoint-group |  |  | section | Emergency Egress Ground Floor
checkpoint-status |  |  | checkpoint | No combustibles within 5m of emergency egress of the Fire Walls.
checkpoint-status |  |  | checkpoint | Clear Emergency Egress
checklist-sectioned |  |  | checklist | Management of Site Fire Risk as part of CPU2 (Morning) |  |  |  |  | Yes | SYS - Management of Site Fire Risk as part of CPU2 (Morning) [old version] | 6d85b842-7d22-4646-a9dc-f39160457b7a
checkpoint-group |  |  | section | Amenities End (Stair 2.5)
checkpoint-status |  |  | checkpoint | Check fire doors are closed on Levels :
checkpoint-status |  |  | checkpoint | Clear access on all levels
checkpoint-status |  |  | checkpoint | Hoarding secure at L4
checkpoint-group |  |  | section | Farmers Carpark Stairwell 2.3
checkpoint-status |  |  | checkpoint | Check Fire Doors are closed on Levels
checkpoint-status |  |  | checkpoint | Clear access on all levels
checkpoint-status |  |  | checkpoint | Hoarding secure at L4
checkpoint-group |  |  | section | Tay St Stairway 2.4
checkpoint-status |  |  | checkpoint | Check Fire Doors are closed on Levels
checkpoint-status |  |  | checkpoint | Clear access on all levels
checkpoint-status |  |  | checkpoint | Hoarding secure at L4
checkpoint-group |  |  | section | Esk St Stairway 2.2
checkpoint-status |  |  | checkpoint | No combustible material within 5m of stairway
checkpoint-status |  |  | checkpoint | Clear access
checkpoint-group |  |  | section | Sprinkler Tank
checkpoint-status |  |  | checkpoint | Checked sprinkler tank level (Red arrow down is full)
checkpoint-group |  |  | section | Bike Store Beside Ramp
checkpoint-status |  |  | checkpoint | Bike store is clear of combustibles within 5m
checkpoint-group |  |  | section | Emergency Egress Ground Floor
checkpoint-status |  |  | checkpoint | No combustibles within 5m of emergency egress of the Fire Walls.
checkpoint-status |  |  | checkpoint | Clear Emergency Egress
checklist-sectioned |  |  | checklist | Lift Services Checklist |  |  |  |  | Yes | Lift Services Checklist | 764d454b-9e99-4320-a3d4-8215f1afeafc
checkpoint-group |  |  | section | Pre Installation
checkpoint-status |  |  | checkpoint | Complete all preliminary checks on form CMD\494
checkpoint-status |  |  | checkpoint | Form CMD\495 completion (Daily, Weekly, Monthly, Once)
checkpoint-status |  |  | checkpoint | Confirm all site measurements lift well dimensions, openings etc
checkpoint-status |  |  | checkpoint | Confirm details for lift car fit out
checkpoint-status |  |  | checkpoint | Liaise with all other trades and resolve coordination problems
checkpoint-status |  |  | checkpoint | There is an additional sheet of specific checks for this work
checkpoint-status |  |  | checkpoint | ALL checks (including any attachments of specific checks) are complete
checkpoint-group |  |  | section | During Installation
checkpoint-status |  |  | checkpoint | All safety measures maintained on all levels
checkpoint-status |  |  | checkpoint | Check installation for damage / defect and as specified, record corrections and remedial
checkpoint-status |  |  | checkpoint | Confirm all is working in accordance with the specified / Manufacturers instructions
checkpoint-status |  |  | checkpoint | Check all finishes are free of defect or blemish and moving parts in full working order
checkpoint-status |  |  | checkpoint | ALL checks (including any attachments of specific checks) are complete
checkpoint-group |  |  | section | On Completion
checkpoint-status |  |  | checkpoint | Commission complete with Marine Certificate and test results confirming equipment performance is as specified
checkpoint-status |  |  | checkpoint | Remove all rubbish, material and plant from site
checkpoint-status |  |  | checkpoint | ALL checks (including any attachments of specific checks) are complete
checkpoint-status |  |  | checkpoint | Completed final inspection and confirmed complete and in full working order
checkpoint-status |  |  | checkpoint | As built drawings and maintenance / operating instructions handed to Contractor
checkpoint-status |  |  | checkpoint | Final inspection to confirm all work and checks completed including form CMD\496
checkpoint-status |  |  | checkpoint | Check / confirm all protection of the work is in place for subsequent construction processes
checkpoint-status |  |  | checkpoint | ABL confirm completion and hand over of all work covered by this form
checklist-flat |  |  | checklist | Set out & levels |  |  |  |  | Yes | Landscaping QA - Set out & levels | 7ecde845-0439-4581-9313-4dd6a35782ea
checkpoint-status |  |  | checkpoint | Filterra Stormwater treatment
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Kerb cutdown to swale
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Swale
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Sumps
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | 10m High telecom pole location
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Insol pergola
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | 1200mm garden wall
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Gate
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Patio level
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All Setout work/levels completed, reviewed and approved
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checklist-flat |  |  | checklist | Communal Service Shed |  |  |  |  | Yes | Landscaping QA - Communal Service Shed | 850062b4-9005-4353-a1ff-1808f10312f7
checkpoint-status |  |  | checkpoint | Foundations
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | RHS Mild Steel Post Set into Concrete
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Shadow Clad Marine Grade
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Oregan timber slats
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Oregan hardwood pergola
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | H3.2 Radiata Timber Rafters
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Eurotray Roofing
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | High Level Drainage Channel
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Down Pipe
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Outlet Pipe
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All Paving completed, reviewed and approved
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checklist-sectioned |  |  | checklist | Electrical Services Checklist |  |  |  |  | Yes | Electrical Services Checklist | 898f05d1-e840-4458-93e6-d6d0cd810aae
checkpoint-group |  |  | section | Pre Installation
checkpoint-status |  |  | checkpoint | IFC documentation, Statutes, Regulations and Manufacturers Instructions current and complete
checkpoint-status |  |  | checkpoint | All Health & Safety requirements implemented and understood
checkpoint-status |  |  | checkpoint | Other trade services and hazards identified with means of control
checkpoint-status |  |  | checkpoint | Provide samples and obtain all approved colours, layout, programme, shop drawings from Architect. Confirm current membership of ECANZ
checkpoint-status |  |  | checkpoint | Confirm all materials / processes conform to documents in 1. above. Place orders and confirm delivery to meet programme
checkpoint-status |  |  | checkpoint | Material quantity / quality as ordered / specified and free of defect / damage on receipt
checkpoint-status |  |  | checkpoint | Liaise with all other trades (especially Mechanical) and resolve coordination problems
checkpoint-status |  |  | checkpoint | Confirm all adjacent finishes are adequately protected
checkpoint-status |  |  | checkpoint | There is an additional sheet of specific checks for this work
checkpoint-status |  |  | checkpoint | ALL checks (including any attachments of specific checks) are complete
checkpoint-group |  |  | section | During Installation
checkpoint-status |  |  | checkpoint | Check and confirm standard of finish and all workmanship is as specified / Manufacturers Instructions and materials damage free before use
checkpoint-status |  |  | checkpoint | Check installation for damage / defect and as specified, record corrections and remedial
checkpoint-status |  |  | checkpoint | Test / check all wiring / fittings / equipment installed as specified prior to closing in
checkpoint-status |  |  | checkpoint | Approval of exposed wiring / trunking runs
checkpoint-status |  |  | checkpoint | ALL checks (including any attachments of specific checks) are complete
checkpoint-group |  |  | section | On Completion
checkpoint-status |  |  | checkpoint | Remove all rubbish, material and plant from site and clean down all work
checkpoint-status |  |  | checkpoint | Check all finishes are free of defect or blemish and moving parts in full working order
checkpoint-status |  |  | checkpoint | ALL checks (including any attachments of specific checks) are complete
checkpoint-status |  |  | checkpoint | As Built and Maintenance documents complete / approved by Consultant
checkpoint-status |  |  | checkpoint | Tests, commissioning and documentation completed / approved by Consultant / Electrical Authority
checkpoint-status |  |  | checkpoint | Completed final inspection and confirmed complete and in full working order
checkpoint-status |  |  | checkpoint | Certificate of Compliance and Producer Statement presented
checkpoint-status |  |  | checkpoint | Check / confirm protection of work from subsequent construction processes is in place
checkpoint-status |  |  | checkpoint | ABL confirm completion and hand over of all work covered by this form
checklist-flat |  |  | checklist | Comfloor - |  |  |  |  | Yes | QA - Comfloor Checklist | 8cf98537-5648-4e4a-accd-296e210a4f57
checkpoint-status |  |  | checkpoint | Resotec installed as required
checkpoint-status |  |  | checkpoint | Propping checked and correct
checkpoint-status |  |  | checkpoint | General photos, comments and observations during install
checkpoint-status |  |  | checkpoint | Comfloor laid in the correct place
checkpoint-status |  |  | checkpoint | Laps and welds correct and completed
checkpoint-status |  |  | checkpoint | Any perimeter/edging installed correctly
checkpoint-status |  |  | checkpoint | Comfloor Inspected and complete
checklist-flat |  |  | checklist | Irrigation |  |  |  |  | Yes | Landscaping QA - Irrigation | 8da41d19-e523-43ed-8a2f-d4386f0d59e5
checkpoint-status |  |  | checkpoint | Dripline Private
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Submain Private
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Submain Common
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Water Mains
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Conduit
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Dripline Common
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | CommonMD Sub Main
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Hunter PGV
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Controller
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Isolation Valve
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Hose Taps
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Check Valves
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Filters
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All Irrigation completed, reviewed and approved
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checklist-flat |  |  | checklist | Precast Panel - |  |  |  |  | Yes | QA - Precast Walls/Stairs Checklist | 952a1328-b816-4ec5-94e7-07b4d769881f
checkpoint-status |  |  | checkpoint | Inspection on arrival
checkpoint-status |  |  | checkpoint | Starter bars/packers installed to correct heights
checkpoint-status |  |  | checkpoint | Installed in correct location
checkpoint-status |  |  | checkpoint | Starter bars installed
checkpoint-status |  |  | checkpoint | Adequately braced
checkpoint-status |  |  | checkpoint | Grout sleeves correctly grouted
checklist-sectioned |  |  | checklist | Fitout / Finishing Checklist |  |  |  |  | Yes | QA - Fitout / Finishing - General QA Checklist | 9901feb3-d8e4-4696-b824-d1b9dccc1c0e
checkpoint-group |  |  | section | General QA
checkpoint-status |  |  | checkpoint | Gib Fixing Completed
holdpoint |  |  | signoff | Raise Remedial/Request trades QA/Signoff
checkpoint-status |  |  | checkpoint | Ceiling holes correctly located for lights etc
holdpoint |  |  | signoff | Raise Remedial/Request trades QA/Signoff
checkpoint-status |  |  | checkpoint | Access hatches
holdpoint |  |  | signoff | Raise Remedial/Request trades QA/Signoff
checkpoint-status |  |  | checkpoint | Joinery/Windows installed and back sealed (damage free and elements functioning)
holdpoint |  |  | signoff | Raise Remedial/Request trades QA/Signoff
checkpoint-status |  |  | checkpoint | Glazing Install completed and checked
holdpoint |  |  | signoff | Raise Remedial/Request trades QA/Signoff
checkpoint-status |  |  | checkpoint | All internal doors installed, checked and correct (margins neat)
holdpoint |  |  | signoff | Raise Remedial/Request trades QA/Signoff
checkpoint-status |  |  | checkpoint | Entrance door sealed
holdpoint |  |  | signoff | Raise Remedial/Request trades QA/Signoff
checkpoint-status |  |  | checkpoint | Finishing trims installed and completed
holdpoint |  |  | signoff | Raise Remedial/Request trades QA/Signoff
checkpoint-status |  |  | checkpoint | Gib Stopping completed - finish acceptable
holdpoint |  |  | signoff | Raise Remedial/Request trades QA/Signoff
checkpoint-status |  |  | checkpoint | Painting completed - correct colour and level of finish
holdpoint |  |  | signoff | Raise Remedial/Request trades QA/Signoff
checkpoint-status |  |  | checkpoint | lights installed, checked and correct
holdpoint |  |  | signoff | Raise Remedial/Request trades QA/Signoff
checkpoint-status |  |  | checkpoint | Switches and Power points checked and corrct (specs and location)
holdpoint |  |  | signoff | Raise Remedial/Request trades QA/Signoff
checkpoint-status |  |  | checkpoint | Switch board completed (appropriately labeled and fitted off)
holdpoint |  |  | signoff | Raise Remedial/Request trades QA/Signoff
checkpoint-status |  |  | checkpoint | H/W cylinder installed
holdpoint |  |  | signoff | Raise Remedial/Request trades QA/Signoff
checkpoint-status |  |  | checkpoint | Heat Pump second fix completed
holdpoint |  |  | signoff | Raise Remedial/Request trades QA/Signoff
checkpoint-status |  |  | checkpoint | Timber flooring completed & correct
holdpoint |  |  | signoff | Raise Remedial/Request trades QA/Signoff
checkpoint-status |  |  | checkpoint | Carpet flooring completed & correct
holdpoint |  |  | signoff | Raise Remedial/Request trades QA/Signoff
checkpoint-status |  |  | checkpoint | Wardrobes Install Completed, checked and approved
checkpoint-status |  |  | checkpoint | - Onsite measure
checkpoint-status |  |  | checkpoint | - Installation
holdpoint |  |  | signoff | Raise Remedial/Request trades QA/Signoff
checkpoint-status |  |  | checkpoint | Second fix door hardware installed and approved
holdpoint |  |  | signoff | Raise Remedial/Request trades QA/Signoff
checkpoint-group |  |  | section | Kitchen Install QA
checkpoint-status |  |  | checkpoint | Kitchen cabinetry installation completed and correct
holdpoint |  |  | signoff | Raise Remedial/Request trades QA/Signoff
checkpoint-status |  |  | checkpoint | Bench top install completed
boolean | 63bbae3e-358f-5805-b610-3605c8b53507 |  | tickbox | - Measure
boolean | 98c85ea1-8927-51bf-b0e1-5fa3ce6f9d5f |  | tickbox | - Install
holdpoint |  |  | signoff | Raise Remedial/Request trades QA/Signoff
checkpoint-status |  |  | checkpoint | All appliances Installed and comissioned
boolean | 20fd4106-43b1-58ff-ad9e-bd84f4c6404f |  | tickbox | - Range hood
boolean | 05f6f3bb-88c1-5eef-a522-858c729b43c2 |  | tickbox | - Oven
boolean | 84addc26-05fd-5e9d-8d6e-cca7e78deabc |  | tickbox | - Fridge
boolean | 5608e608-2bec-5aea-97a0-03fdf7304ca4 |  | tickbox | - Waste disposal unit
boolean | 3473d292-fb49-54ed-af6e-da27d24ffb35 |  | tickbox | - Dishwasher
holdpoint |  |  | signoff | Raise Remedial/Request trades QA/Signoff
checkpoint-status |  |  | checkpoint | Kitchen splash backs
boolean | d4db6214-c4e8-5d56-8b99-8779e81bb568 |  | tickbox | - Site measure
boolean | 9fc46f5b-204f-54bb-906c-6ed4937ff8ae |  | tickbox | -Install
holdpoint |  |  | signoff | Raise Remedial/Request trades QA/Signoff
checkpoint-group |  |  | section | Bathrooms
checkpoint-status |  |  | checkpoint | Shower trays installed correctly
holdpoint |  |  | signoff | Raise Remedial/Request trades QA/Signoff
checkpoint-status |  |  | checkpoint | Shower wall linings installed correctly
holdpoint |  |  | signoff | Raise Remedial/Request trades QA/Signoff
checkpoint-status |  |  | checkpoint | Underfloor heating completed and checked
holdpoint |  |  | signoff | Raise Remedial/Request trades QA/Signoff
checkpoint-status |  |  | checkpoint | Water proofing completed and correct
holdpoint |  |  | signoff | Raise Remedial/Request trades QA/Signoff
checkpoint-status |  |  | checkpoint | Floor tiles installed and acceptable
holdpoint |  |  | signoff | Raise Remedial/Request trades QA/Signoff
checkpoint-status |  |  | checkpoint | Wall tiles installed and acceptable
holdpoint |  |  | signoff | Raise Remedial/Request trades QA/Signoff
checkpoint-status |  |  | checkpoint | Grout installed and finish acceptable
holdpoint |  |  | signoff | Raise Remedial/Request trades QA/Signoff
checkpoint-status |  |  | checkpoint | Silicone installed and finish acceptable
holdpoint |  |  | signoff | Raise Remedial/Request trades QA/Signoff
checkpoint-status |  |  | checkpoint | Shower door installation completed and approved
holdpoint |  |  | signoff | Raise Remedial/Request trades QA/Signoff
checkpoint-status |  |  | checkpoint | Joinery installed checked and correct
holdpoint |  |  | signoff | Raise Remedial/Request trades QA/Signoff
checkpoint-status |  |  | checkpoint | Plumbing second fix completed and approved
holdpoint |  |  | signoff | Raise Remedial/Request trades QA/Signoff
checkpoint-status |  |  | checkpoint | Hardware second fix completed and approved
holdpoint |  |  | signoff | Raise Remedial/Request trades QA/Signoff
checkpoint-group |  |  | section | Unit Completion / Handover
checkpoint-status |  |  | checkpoint | All above QA items completed
checkpoint-status |  |  | checkpoint | Final Clean Completed & Apartment ready for handover
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checklist-flat |  |  | checklist | Sub Floor Services Installation - |  |  |  |  | Yes | QA - Subfloor Services Checklist | a69f6900-b0ee-499c-ab7a-b0d4732bbe05
checkpoint-status |  |  | checkpoint | Electrical services/ conduits installed, fixed in correct location, backfilled and correct as per design
checkpoint-status |  |  | checkpoint | Hydraulic services installed, fixed in correct location, backfilled and correct as per design
checkpoint-status |  |  | checkpoint | Gas installed, fixed in correct location, backfilled and correct as per design
checkpoint-status |  |  | checkpoint | Telecommunication/Fibre installed, fixed in correct location, backfilled and correct as per design
checkpoint-status |  |  | checkpoint | Any other relevant services installed, fixed in correct location, backfilled and correct as per design
checkpoint-status |  |  | checkpoint | Any additional observations / attachments
checkpoint-status |  |  | checkpoint | Any relevant inspections carried out and attached
checkpoint-status |  |  | checkpoint | All subfloor services correctly installed to respective area
checklist-flat |  |  | checklist | Second Fix Services |  |  |  |  | Yes | QA - Second Fix Services | bd1964d7-d7ac-4dd9-9882-35e8b57c8d95
checkpoint-status |  |  | checkpoint | Plumbing Second Fix
holdpoint |  |  | signoff | Request Hold Point Sign Off
checkpoint-status |  |  | checkpoint | Electrical Second Fix
holdpoint |  |  | signoff | Request Hold Point Sign Off
checkpoint-status |  |  | checkpoint | Mechanical Second Fix
holdpoint |  |  | signoff | Request Hold Point Sign Off
checkpoint-status |  |  | checkpoint | Sprinkler Second Fix
holdpoint |  |  | signoff | Request Hold Point Sign Off
checkpoint-status |  |  | checkpoint | Security Second Fix
holdpoint |  |  | signoff | Request Hold Point Sign Off
checkpoint-status |  |  | checkpoint | Any additional services and inspections completed
holdpoint |  |  | signoff | Request Hold Point Sign Off
checklist-flat |  |  | checklist | Overall site planting |  |  |  |  | Yes | Landscaping QA - Overall Site Planting | c219f2dd-a407-4e95-a772-ba04116baa69
checkpoint-status |  |  | checkpoint | Oioi x 16
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Cabbage tree x 6
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Dianella x 33
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Feijoa x 73
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Creeping Ficus x 61
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Grape x 31
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Rush x 161
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Creeping Wire Vine x 86
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Black Mondo Grass x 355
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Flax x 106
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Pittosporum x 22
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Ribbonwood x 29
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Upright Flowering Cherry x 10
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Lancewood x 27
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Star Jasmine x 15
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All planting completed, reviewed and approved
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checklist-flat |  |  | checklist | Waterproofing - |  |  |  |  | Yes | QA - Waterproofing Checklist | c5a8e9a1-a025-4111-b11c-e62ae1125691
checkpoint-status |  |  | checkpoint | Waterproofing installed correctly
text | ce00ee6d-09ed-59e0-8cb6-9d686992cc0b |  | textbox | Supplier:
text | cf518a47-486f-5b61-a15c-ea573d9df9fd |  | textbox | Product used:
text | 83e5ab8a-fac0-51fe-b210-baf848fe9fe4 |  | textbox | Applicator:
checkpoint-status |  |  | checkpoint | Preparation / Sub strade acceptable
checkpoint-status |  |  | checkpoint | Water stops installed
checkpoint-status |  |  | checkpoint | General install photos attached
checkpoint-status |  |  | checkpoint | Any inspections / observations completed and attached
checkpoint-status |  |  | checkpoint | Waterproofing install completed to meet required specifications
checklist-sectioned |  |  | checklist | Concrete Pour - |  |  |  |  | Yes | QA - Concrete Pour Checklist | c66ac751-53d1-4d75-b111-3f893126b31b
checkpoint-group |  |  | section | Pour Details
checkpoint-status |  |  | checkpoint | Pour details completed
text | 13d58e48-7c63-598d-8e74-bcab5cd8189c |  | textbox | Area to be poured:
button | 8f8e93e0-3d6e-56c2-a3e8-b6d06c3fbb23 |  | button | Are weather conditions suitable ( attach relevant photos ) | Yes,No
checkpoint-group |  |  | section | Formwork and Embedded Items
checkpoint-status |  |  | checkpoint | Grids and heights clearly marked for reference
checkpoint-status |  |  | checkpoint | Formwork - location, height, falls and dimensions checked, clearly marked and accurate
checkpoint-status |  |  | checkpoint | Formwork sufficiently fixed and braced
checkpoint-status |  |  | checkpoint | Any rebates/ nibs / cast in items are correctly positioned, correct size and appropriately fixed in place
checkpoint-status |  |  | checkpoint | Any hold down bolts checked and correct (location, height & size)
checkpoint-status |  |  | checkpoint | Service penetrations formed correctly and locations checked/correct
checkpoint-status |  |  | checkpoint | All surfaces correctly prepared (e.g joints to exisiting concrete, release agent to formwork etc)
checkpoint-status |  |  | checkpoint | Any control joints/ stop ends installed accurately and correctly
checkpoint-status |  |  | checkpoint | Any additional formwork photos and observations
checkpoint-status |  |  | checkpoint | All formwork elements completed and ready for concrete pour ( excess debris removed )
checkpoint-group |  |  | section | Reinforcing
checkpoint-status |  |  | checkpoint | Size and type correct to specification
checkpoint-status |  |  | checkpoint | Reinforcing spacing and location correct
checkpoint-status |  |  | checkpoint | Specified covers checked/correct
checkpoint-status |  |  | checkpoint | Splice laps checked/correct
checkpoint-status |  |  | checkpoint | Any starter bars are installed correctly ( location, size and spacing )
checkpoint-status |  |  | checkpoint | Any additional items installed/ completed ( trimmer bars etc ) and excess reinforcing removed
checkpoint-status |  |  | checkpoint | Reinforcing installed correctly to specification and ready for concrete to be placed
checkpoint-status |  |  | checkpoint | Observations
checkpoint-group |  |  | section | Pre-Pour Completion (Approval to pour)
checkpoint-status |  |  | checkpoint | Any waterproofing elements have been correctly installed and checked
checkpoint-status |  |  | checkpoint | Sand binding/poly checked and correct (foundation/ground floor slab)
checkpoint-status |  |  | checkpoint | Any relevant service requirements completed
checkpoint-status |  |  | checkpoint | Engineer inspection completed
checkpoint-status |  |  | checkpoint | Council inspection completed and attached
checkpoint-status |  |  | checkpoint | Any testing documentation attach (ND tests etc)
checkpoint-status |  |  | checkpoint | All relevant inspections completed and attached
checkpoint-status |  |  | checkpoint | Main contractor inspection completed - Approval given to pour concrete
checkpoint-group |  |  | section | Concrete Supplier
checkpoint-status |  |  | checkpoint | Concrete supplier details completed
text | 32d4ab03-3354-5f7a-a288-76bd642e1149 |  | textbox | Supplier:
text | cc2dbe23-7031-56fe-9575-0b7b9e427681 |  | textbox | Specified concrete strength: |  |  | mPA
text | 5671d32c-9760-5bd5-a8f2-a3cf4ce9e169 |  | textbox | Concrete strength ordered: |  |  | mPA
text | 69bd8c07-a307-5d9b-b4ad-67fb267afcbe |  | textbox | Concrete quantity ordered: |  |  | m3
button | 8bd43f7e-0e64-5c53-a652-b4ef7f206cf1 |  | button | Test blocks booked | Yes,No,N/A
checkpoint-status |  |  | checkpoint | All concrete dockets photographed/ attached
checkpoint-group |  |  | section | Concrete Distribution
checkpoint-status |  |  | checkpoint | Concrete distribution method details completed
text | 798fc77a-c93e-52b6-a5eb-c12af374b9b5 |  | textbox | Who distributed the concrete:
text | ef252c6d-547a-578e-a778-673904d24bff |  | textbox | How was the concrete distributed:
checkpoint-status |  |  | checkpoint | General distribution photos, documents and observations attached
checkpoint-status |  |  | checkpoint | All concrete distributed correctly ( area left clean and tidy )
checkpoint-group |  |  | section | Placement Method
checkpoint-status |  |  | checkpoint | Placement methodology confirmed and necessary plant and equipment on site
text | 9e944cb7-0215-5126-bfdb-1ae4a248ff3a |  | textbox | Who placed the concrete:
checkpoint-status |  |  | checkpoint | Heights and falls checked/ confirmed before placement
button | 792beb12-e306-5a69-a2b4-8596be7d1cf9 |  | button | Is the cover correct to specification | Yes,No
checkpoint-status |  |  | checkpoint | General photos and observations of concrete placement attached
checkpoint-group |  |  | section | Concrete Pour Final Checks
checkpoint-status |  |  | checkpoint | Heights and falls checked/ confirmed after placement
checkpoint-status |  |  | checkpoint | Any curing compound applied correctly
checkpoint-status |  |  | checkpoint | Concrete placement completed - specified level of finish achieved
checkpoint-status |  |  | checkpoint | Saw Cuts correctly marked and cut where required
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checklist-flat |  |  | checklist | Excavation - |  |  |  |  | Yes | QA - Excavation Checklist | c89d4e8b-9aaa-4698-92f4-fe9bfd3f755f
checkpoint-status |  |  | checkpoint | Excavation depth determined using appropriate RL's
checkpoint-status |  |  | checkpoint | Confirm location and isolation of relevant services
checkpoint-status |  |  | checkpoint | General excavation documentation and photos attached
checkpoint-status |  |  | checkpoint | Any batters formed correctly
checkpoint-status |  |  | checkpoint | Any trenches/ pits / hazardous areas appropriately isolated
checkpoint-status |  |  | checkpoint | Any soft spots identified and appropriate remedial completed
checkpoint-status |  |  | checkpoint | Any hardfill/ blinding installed correctly to required specification
checkpoint-status |  |  | checkpoint | Excavation completed - Correct locations and RL's achieved
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached
checklist-sectioned |  |  | checklist | Management of Site Fire Risk as part of CPU SP5 Once a day |  |  |  |  | Yes | Management of Site Fire Risk as part of CPU SP5 Once a day | cce0f76e-a5d8-44e1-963a-436d96e66ecb
checkpoint-group |  |  | section | Esk St Stairway 2.2
checkpoint-status |  |  | checkpoint | No combustible material within 5m of stairway
checkpoint-status |  |  | checkpoint | Clear emergency access
checkpoint-group |  |  | section | Emergency Egress Ground Floor
checkpoint-status |  |  | checkpoint | No combustibles within 5m of emergency egress of the Fire Walls.
checkpoint-status |  |  | checkpoint | Clear Emergency Egress
checklist-sectioned |  |  | checklist | Plumbing and Gas Checklist |  |  |  |  | Yes | Plumbing and Gas Checklist | d8814af3-51d4-4545-a565-e91f14a4dc31
checkpoint-group |  |  | section | Pre Installation
checkpoint-status |  |  | checkpoint | IFC documentation, Statutes, Regulations and Manufacturers Instructions current and complete
checkpoint-status |  |  | checkpoint | All Health & Safety requirements implemented and understood
checkpoint-status |  |  | checkpoint | Other trade services and hazards identified with means of control
checkpoint-status |  |  | checkpoint | Provide samples and obtain all approved colours, layout, shop drawings from Architect
checkpoint-status |  |  | checkpoint | Confirm all materials / processes conform to documents in 1. above. Place orders and confirm delivery to meet programme
checkpoint-status |  |  | checkpoint | Material quantity / quality as ordered / specified and free of defect / damage on receipt
checkpoint-status |  |  | checkpoint | Liaise with all other trades and resolve coordination problems.
checkpoint-status |  |  | checkpoint | All built in items handed to contractor to fit
checkpoint-status |  |  | checkpoint | Confirm all adjacent finishes are adequately protected
checkpoint-status |  |  | checkpoint | There is an additional sheet of specific checks for this work
checkpoint-status |  |  | checkpoint | ALL checks (including any attachments of specific checks) are complete
checkpoint-group |  |  | section | During Installation
checkpoint-status |  |  | checkpoint | Check and confirm standard of finish and all workmanship is as specified / Manufacturers Instructions and materials damage free before use
checkpoint-status |  |  | checkpoint | Check installation for damage / defect and as specified, record corrections and remedial
checkpoint-status |  |  | checkpoint | Test all in-wall / concealed pipe work and equipment prior to covering up
checkpoint-status |  |  | checkpoint | Check all firewall / floor collars / sleeves, pipe insulation and approval of exposed pipe runs
checkpoint-status |  |  | checkpoint | Confirm all fittings installed in full working order as specified / Manufacturers Instructions
checkpoint-status |  |  | checkpoint | Check all finishes are free of defect or blemish and moving parts in full working order
checkpoint-status |  |  | checkpoint | ALL checks (including any attachments of specific checks) are complete
checkpoint-group |  |  | section | On Completion
checkpoint-status |  |  | checkpoint | Clean all finished work, make good all defects or damage. Moving parts operate freely
checkpoint-status |  |  | checkpoint | Check work is tested by TA / Consultant and signed / approved in working order
checkpoint-status |  |  | checkpoint | Remove all rubbish, material and plant from site
checkpoint-status |  |  | checkpoint | ALL checks (including any attachments of specific checks) are complete
checkpoint-status |  |  | checkpoint | Completed final inspection and confirmed complete and in full working order
checkpoint-status |  |  | checkpoint | Mark up as built drawings and operating instructions ready for handing to Contractor on Practical Completion
checkpoint-status |  |  | checkpoint | Check / confirm all protection of the work is in place for subsequent construction processes
checkpoint-status |  |  | checkpoint | ABL confirm completion and hand over of all work covered by this form
checklist-flat |  |  | checklist | Backfill - |  |  |  |  | Yes | QA - Backfill Checklist | dae4e355-a559-4e1c-b039-3514c0272144
checkpoint-status |  |  | checkpoint | Backfill methodology and material confirmed
checkpoint-status |  |  | checkpoint | Any formwork/ debris removed from area
checkpoint-status |  |  | checkpoint | Any waterproofing/ drainage / service requirements completed and inspected
checkpoint-status |  |  | checkpoint | Approval given to commence backfill - attach any other relevant inspections
checkpoint-status |  |  | checkpoint | General photos and observations during backfill
checkpoint-status |  |  | checkpoint | Backfill correctly compacted
checkpoint-status |  |  | checkpoint | Backfill completed correctly and height checked/ correct
checklist-sectioned |  |  | checklist | Pre-Pour Inspection Checklist |  |  |  |  | Yes | QA - LBA Slab Pre-pour Inspection Checklist | db21aa32-68c4-429c-9567-b9ba695fc4a3
checkpoint-group |  |  | section | Concrete - Pre Pour
checkpoint-status |  |  | checkpoint | Roughening of Concrete at top of In-Situ Beam stitch joints complete?
checkpoint-status |  |  | checkpoint | Roughening of Concrete at North & South Faces of Precast Columns complete (where 3-RB20 come out)?
checkpoint-status |  |  | checkpoint | Roughening of Concrete at side Faces of Grid 3A/3B Precast Columns complete(where 3-RF16 slab ties come out)?
checkpoint-status |  |  | checkpoint | Roughening of Concrete at interface with previously poured slabs complete?
checkpoint-status |  |  | checkpoint | Have 50mm Double T packers been installed?
checkpoint-status |  |  | checkpoint | Does slab slope or have reduced cover in areas?
checkpoint-status |  |  | checkpoint | Have Reo spacers been installed around low areas?
checkpoint-status |  |  | checkpoint | As checked by Amalgamated Builders Ltd
label | 0351a336-bb74-49a7-9ec2-6fa876a2d118 |  | note | Name
text | e0ef997d-3e01-4a2b-8537-43b544906284 |  | textbox
label | f0e1c373-5242-4356-b83d-c7b786c054ce |  | note | Date
text | 0dc3ac87-0d56-4f9f-b964-873e202a40cf |  | textbox
checkpoint-status |  |  | checkpoint | As completed by LBA
label | c6275f85-1a25-4212-94a1-03bbf427f5cd |  | note | Name
text | 1056f387-0f0c-48c5-aa65-82904e80ef1e |  | textbox
label | b81461f7-eb64-4c52-8d47-dbaaebb73d3b |  | note | Date
text | eceff0a1-ab5f-481a-b566-3bd399c35072 |  | textbox
checklist-flat |  |  | checklist | Penetration: |  |  |  |  | Yes | QA - Fire Penetrations & Sleeves (detailed) | dc3cea49-6320-44bf-a8cc-aa95771854dc
checkpoint-status |  |  | checkpoint | Penetrations details
select | 420bfb9e-de00-53d3-87df-c3b52fcbd18b |  | dropdown | Area of Installation | Wall, Floor, Ceiling
select | b4779850-76dd-56c6-aec0-fa6837432fb4 |  | dropdown | Fire Rating (Minutes) | Smoke, FRR 30, FRR 60, FRR 120,FRR 180,Other
text | a05c4d93-cf42-5bbe-9811-569d7808df73 |  | textbox | If other - specify here:
label | 89d40043-8a02-5c41-88b8-a46a294bd6ef |  | note | Penetration Type
boolean | 22b43e05-86ab-523d-ab9e-ef40ae10aa5a |  | tickbox | Cables
boolean | eeace26e-5e52-5f8e-b2cc-816793c5588a |  | tickbox | Copper Pipe
boolean | 99488305-86f5-50ec-922e-c6b4e85e732c |  | tickbox | PVC Pipe
boolean | b0f7476c-1133-54a2-8c8d-80d88fea5bb6 |  | tickbox | PPR
boolean | 1c44783a-3a42-58a9-9e1d-7ef678f0cc86 |  | tickbox | DUX
boolean | fde1d4dc-305c-5c35-8dd7-4086e6e907c7 |  | tickbox | Stainless Steel Pipe
boolean | bdbee74f-aebb-5426-914c-926de9546dc7 |  | tickbox | Galvanised Steel Pipe
boolean | d20ced97-a84b-5083-9e3f-528722ac13f2 |  | tickbox | Metal Duct
boolean | 3eeabfa6-98dd-5ea9-842a-8ae38125d4d2 |  | tickbox | PVC Duct
boolean | 220a3afe-369c-5ac3-ac62-447bca591319 |  | tickbox | Pair Coil
boolean | 9037d294-9175-5229-9e9f-20aa22da0a22 |  | tickbox | Other
text | 14e50141-fc0d-5c37-8553-0ba1e74a995e |  | textbox | If other - specify here:
label | dd001e66-6b6e-5877-b8c4-5b77abdeb3c6 |  | note | Service Type
boolean | 4c4df00b-0de6-56b0-9cd1-d7b955448594 |  | tickbox | Sprinkler Services
boolean | 1bccaf52-76e0-5a34-90b1-d556336196ed |  | tickbox | Data & Security Systems
boolean | 49cfa692-678d-557b-9a3c-34872173ed40 |  | tickbox | Hydraulics / Plumbing
boolean | 2eded4e2-896f-559b-9ca7-b6d13b7393ca |  | tickbox | Electricals
boolean | bad0827c-7497-5c7e-9279-c5e68d38637e |  | tickbox | Mechanical
boolean | 8f936ab8-a47c-5ea4-a17f-8c2eba97acd9 |  | tickbox | Other
text | afb28794-9f6c-5b99-8279-c0b893fcfeba |  | textbox | If other - specify here:
select | 0d5ff19f-e75f-5e3a-9720-ec046463250c |  | dropdown | Product Used | Collars,Pipe Wraps,Fire Plates,Cast-In Collars,Fire Bonds,Boss FYRE Box,Cable Transit,Cable Collar,Fire Mortar,Compressed Material Wool,Fire Rated Fabric,Flexicoat Sealant,Fire Dampers,Fire Pillow,Downlight Cover,Ablative Coating,Fire Shield,Protecta FR Putty Cord,Intumescent Sealant,Fire Mastic Sealant,Weather Resistant Fire Sealant,Fire Foam,Other
text | 769974b4-f6db-506e-95f8-a68e0eede478 |  | textbox | If other - specify here:
button | 900bb93d-c922-5ab0-a50a-d266ec863b30 |  | button | Fire Sealant Used | Yes, No, N/A
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checklist-sectioned |  |  | checklist | Management of Site Fire Risk as part of CPU (Checklist) |  |  |  |  | Yes | SYS - Management of Site Fire Risk as part of CPU (Checklist) [old version] | dd793b1a-2622-4948-b675-cc4638e5799e
checkpoint-group |  |  | section | Carpark Stairs Amenities End
checkpoint-status |  |  | checkpoint | Check fire doors are closed on Levels : L1 & L2
checkpoint-status |  |  | checkpoint | No combustible material within 5m of doors on levels : L3 & L4
checkpoint-group |  |  | section | Carpark Level 3 Plant Deck
checkpoint-status |  |  | checkpoint | Plant Deck Level 3 – No fuel within 5m
checkpoint-group |  |  | section | Bulkheads Farmers Carpark Stairwell
checkpoint-status |  |  | checkpoint | Bulkheads by Carpark Stairways – No combustibles or Hot works within 5m
checkpoint-group |  |  | section | Farmers Carpark Stairwell
checkpoint-status |  |  | checkpoint | Farmers Carpark Stairwell – No combustible material within 5m L3 & L4
checkpoint-group |  |  | section | Carpark Tay St Stairway
checkpoint-status |  |  | checkpoint | No combustible material within 5m of stairway
checkpoint-group |  |  | section | Emergency Egress Ground Floor
checkpoint-status |  |  | checkpoint | No combustibles within 5m of emergency egress exterior.
checkpoint-group |  |  | section | Bike Store Beside Ramp
checkpoint-status |  |  | checkpoint | Bike store is clear of combustibles within 5m
checkpoint-group |  |  | section | Sprinkler Tank
checkpoint-status |  |  | checkpoint | Checked sprinkler tank level (Red arrow down is full)
checkpoint-group |  |  | section | Mall Toilet Corridor Gate
checkpoint-status |  |  | checkpoint | Gate in toilet hallway is not in use
checkpoint-group |  |  | section | Area of carpark with no sprinkler coverage - range pipes in but no heads
checkpoint-status |  |  | checkpoint | Road cones and frog system to make carparks effected as being blocked off. A map to be prepared and ABL Management to check twice daily
checkpoint-group |  |  | section | Level 1 offices area - sprinkler coverage - defeciant due to the gib ceiling
checkpoint-status |  |  | checkpoint | ABL Management instructed to remove the content under the bulkhead
checklist-flat |  |  | checklist | Internal Doors Fit-Off |  |  |  |  | Yes | QA - Internal Doors Fit-Off | e8de8787-4cdc-4312-b9e8-2328ebe6a207
checkpoint-status |  |  | checkpoint | Opening sizes correct
checkpoint-status |  |  | checkpoint | Correct door used
checkpoint-status |  |  | checkpoint | Door fixing adequate
checkpoint-status |  |  | checkpoint | Door Level/Plumb/Wind
checklist-sectioned |  |  | checklist | Management of Site Fire Risk as part of CPU2 (Morning) |  |  |  |  | Yes | SYS - Management of Site Fire Risk as part of CPU2 (Morning) (old version) | eb1598e3-dbc7-44c0-9dac-a1ed18988655
checkpoint-group |  |  | section | Carpark Stairs
checkpoint-status |  |  | checkpoint | Check fire doors are closed on Levels :
checkpoint-status |  |  | checkpoint | Available all Levels and check Hoardings
checkpoint-group |  |  | section | Amenities End (Stair 2.5)
checkpoint-status |  |  | checkpoint | Check fire doors are closed on Levels :
checkpoint-status |  |  | checkpoint | Available all Levels and check Hoardings
checkpoint-group |  |  | section | Farmers Carpark Stairwell 2.3
checkpoint-status |  |  | checkpoint | Farmers Carpark Stairwell - No combustible material within 5m L4
checkpoint-group |  |  | section | Carpark
checkpoint-status |  |  | checkpoint | No combustible material within 5m of stairway
checkpoint-group |  |  | section | Tay St Stairway 2.4
checkpoint-status |  |  | checkpoint | No combustible material within 5m of stairway
checkpoint-group |  |  | section | Retail
checkpoint-status |  |  | checkpoint | No combustible material within 5m of stairway
checkpoint-group |  |  | section | Esk St Stairway 2.2
checkpoint-status |  |  | checkpoint | No combustible material within 5m of stairway
checkpoint-group |  |  | section | Sprinkler Tank
checkpoint-status |  |  | checkpoint | Checked sprinkler tank level (Red arrow down is full)
checkpoint-group |  |  | section | Bike Store Beside Ramp
checkpoint-status |  |  | checkpoint | Bike store is clear of combustibles within 5m
checkpoint-group |  |  | section | Emergency Egress Ground Floor
checkpoint-status |  |  | checkpoint | No combustibles within 5m of emergency egress of the Fire Walls.
checkpoint-status |  |  | checkpoint | Clear Emergency Egress
checklist-flat |  |  | checklist | Internal Doors Fit-Off |  |  |  |  | Yes | QA - Internal Doors Fit-Off Checklist | eefb8e90-9c3b-4287-a261-cc89e12bf6b7
checkpoint-status |  |  | checkpoint | Opening sizes correct
checkpoint-status |  |  | checkpoint | Correct door used
checkpoint-status |  |  | checkpoint | Door fixing adequate
checkpoint-status |  |  | checkpoint | Door Level/Plumb/Wind
checklist-flat |  |  | checklist | Add Consultant Inspection Checklist (V3 50) |  |  |  |  | Yes | Add Consultant Inspection Checklist (V3 50) | f08525b1-8fc7-4150-b26e-ece3e2d80df6
checkpoint-status |  |  | checkpoint | Consultant inspection completed, attached and any relevant observations closed out
text | 37b9a88d-f0ec-5001-b831-151d8f3a4f11 |  | textbox | Date of Inspection
text | 682862ec-f4c1-5086-b8c4-1bc94dc8e02a |  | textbox | Type of Inspection
text | 5018f16c-f1b7-5dc2-addf-31c9b91fe73f |  | textbox | Area inspection relates to
boolean | 33afd0f9-53f7-5106-805d-b3bd239c668d |  | tickbox | Consultant Inspection attached
button | 516a8b53-ef2c-5558-9f46-ca77469a7317 |  | button | All Relevant Observation Closeout evidence attached here if applicable (Pass once completed) | PASS, N/A
label | 99553814-4b3b-5e23-93d7-6fc349ec9589 |  | note | "PASS" once corrective closeout evidence has been attached
label | a3704b5e-bd91-5502-9049-3aa9c1bd1800 |  | note | If there are no corrective action requirements select "N/A"
text | 3f56cedd-9074-5844-ae09-315820f7e7d9 |  | textbox | Corrective Actions (listed here if required)
holdpoint |  |  | signoff | Request Signoff
checkpoint-status |  |  | checkpoint | Remedial 1
checkpoint-status |  |  | checkpoint | Remedial 2
checkpoint-status |  |  | checkpoint | Remedial 3
checkpoint-status |  |  | checkpoint | Remedial 4
checkpoint-status |  |  | checkpoint | Remedial 5
checkpoint-status |  |  | checkpoint | Remedial 6
checkpoint-status |  |  | checkpoint | Remedial 7
checkpoint-status |  |  | checkpoint | Remedial 8
checkpoint-status |  |  | checkpoint | Remedial 9
checkpoint-status |  |  | checkpoint | Remedial 10
checkpoint-status |  |  | checkpoint | Remedial 11
checkpoint-status |  |  | checkpoint | Remedial 12
checkpoint-status |  |  | checkpoint | Remedial 13
checkpoint-status |  |  | checkpoint | Remedial 14
checkpoint-status |  |  | checkpoint | Remedial 15
checkpoint-status |  |  | checkpoint | Remedial 16
checkpoint-status |  |  | checkpoint | Remedial 17
checkpoint-status |  |  | checkpoint | Remedial 18
checkpoint-status |  |  | checkpoint | Remedial 19
checkpoint-status |  |  | checkpoint | Remedial 20
checkpoint-status |  |  | checkpoint | Remedial 21
checkpoint-status |  |  | checkpoint | Remedial 22
checkpoint-status |  |  | checkpoint | Remedial 23
checkpoint-status |  |  | checkpoint | Remedial 24
checkpoint-status |  |  | checkpoint | Remedial 25
checkpoint-status |  |  | checkpoint | Remedial 26
checkpoint-status |  |  | checkpoint | Remedial 27
checkpoint-status |  |  | checkpoint | Remedial 28
checkpoint-status |  |  | checkpoint | Remedial 29
checkpoint-status |  |  | checkpoint | Remedial 30
checkpoint-status |  |  | checkpoint | Remedial 31
checkpoint-status |  |  | checkpoint | Remedial 32
checkpoint-status |  |  | checkpoint | Remedial 33
checkpoint-status |  |  | checkpoint | Remedial 34
checkpoint-status |  |  | checkpoint | Remedial 35
checkpoint-status |  |  | checkpoint | Remedial 36
checkpoint-status |  |  | checkpoint | Remedial 37
checkpoint-status |  |  | checkpoint | Remedial 38
checkpoint-status |  |  | checkpoint | Remedial 39
checkpoint-status |  |  | checkpoint | Remedial 40
checkpoint-status |  |  | checkpoint | Remedial 41
checkpoint-status |  |  | checkpoint | Remedial 42
checkpoint-status |  |  | checkpoint | Remedial 43
checkpoint-status |  |  | checkpoint | Remedial 44
checkpoint-status |  |  | checkpoint | Remedial 45
checkpoint-status |  |  | checkpoint | Remedial 46
checkpoint-status |  |  | checkpoint | Remedial 47
checkpoint-status |  |  | checkpoint | Remedial 48
checkpoint-status |  |  | checkpoint | Remedial 49
checkpoint-status |  |  | checkpoint | Remedial 50
checklist-sectioned |  |  | checklist | Scaffold - |  |  |  |  | Yes | QA - Scaffolding Checklist | f5b65b00-bf5d-4847-81b2-3440e12899b0
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Area and ground conditions acceptable
checkpoint-status |  |  | checkpoint | Confirm scaffold location/clearance from structure
checkpoint-group |  |  | section | Scaffold Erection
checkpoint-status |  |  | checkpoint | Scaffold is level
checkpoint-status |  |  | checkpoint | All Decks installed and locked in place (bridge any gaps appropriately)
checkpoint-status |  |  | checkpoint | All Handrails in place at the appropriate heights
checkpoint-status |  |  | checkpoint | All Kickboards in place where required including stopends
checkpoint-status |  |  | checkpoint | Appropriate Ladder/Gate access to lifts
checkpoint-status |  |  | checkpoint | Adequately braced/tied back as required (Photograph braces/ties)
checkpoint-status |  |  | checkpoint | No gaps in scaffold and end of all walkways handrailed
checkpoint-status |  |  | checkpoint | General photos, comments, observations and inspections attached
checkpoint-status |  |  | checkpoint | Respective Lift 100% complete / Scaffold ready for use by others
checkpoint-group |  |  | section | Handover
checkpoint-status |  |  | checkpoint | Scaffold completed to designed height and inspected
checklist-flat |  |  | checklist | Structural Steel - |  |  |  |  | Yes | QA - Structural Steel Checklist | f95db8d5-dac0-4f94-b83e-d6cecd14e988
checkpoint-status |  |  | checkpoint | Hold down bolts in the correct location
checkpoint-status |  |  | checkpoint | Pre erection checks complete
checkpoint-status |  |  | checkpoint | Steel correct size and type
checkpoint-status |  |  | checkpoint | Correct location and orientation
checkpoint-status |  |  | checkpoint | Level, plumb, correct pitch and braced
checkpoint-status |  |  | checkpoint | All bolts secure/ correctly tensioned
checkpoint-status |  |  | checkpoint | All welds sited and tested.
checkpoint-status |  |  | checkpoint | All remedial paint work completed
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | All structural steel correctly installed in respective area