## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned | c7bd68c0-9c66-4720-8231-1b7948a2336f |  | checklist | ITP-002 - Installation of Sewer Drainage (Completion) |  |  |  |  | Yes | ITP-002 - Installation of Sewer Drainage (Completion) | 1cdc846e-856f-46e6-a1b0-70a08a9b22ec
checkpoint-group | d1f2b46f-f9f2-41de-ab40-248a911ad39c |  | section | Pre-Construction
checkpoint-no-status | 9cf5616e-02a2-4494-b291-2f165c88dd4d |  | checkpoint | Pre-Construction
text | fd4dd707-28df-58f7-8bde-a0e1f3ab65a1 |  | textbox | Date Works Commenced:
checkpoint-status | c13c218e-2a82-43f6-ba1f-406be8701a13 |  | checkpoint | All materials delivered to site have been inspected thoroughly by RCC Earthworks and the Client and:
label | c35457ed-2ed0-58c2-b7c5-6fffe0d9e14b |  | note | a) Are free of damage/cracks
label | 344a32e7-d05c-567b-b252-de56b5eb7c06 |  | note | b) Pipe class, type and size matches plans.
label | 249b99e3-0f37-54ee-90d6-5b9762c19f74 |  | note | (upload images of damaged materials here)
checkpoint-group | 06248bef-bf15-45fc-b4a5-f5c50b176c9c |  | section | Construction
checkpoint-status | ce350f80-8563-4459-9996-7b1e9429e4ee |  | checkpoint | Manholes/Trenches set out clearly & accurately
checkpoint-status | 0bdca05d-60ed-473f-a7e6-d23fd900195c |  | checkpoint | Manholes & Trenches excavated to depth and checked with laser (allowed for 100mm bedding)
checkpoint-status | 05db8801-aa4a-4b5d-bcfe-b31f1a2c188f |  | checkpoint | Trench bedding material installed as per specification
checkpoint-status | 7852e833-acea-43f1-ba95-ded9d82cb282 |  | checkpoint | Pipe laid to grade (as per drawings) ensuring socket faces upstream and is free of foreign materials prior to installation of adjoining pipe
checkpoint-status | 2344c032-bace-4857-b86e-bfbb9d1433d7 |  | checkpoint | Each joint visually inspected (rubber rings, witness marks, etc)
checkpoint-status | f9a835c3-c34e-4c5b-a859-9a63d6e09227 |  | checkpoint | Haunching compliant and accepted by the client.
checkpoint-group | 7f0667e7-5960-4a1a-960b-9f436ddc35ac |  | section | Backfill
checkpoint-status | 25d183cf-e760-41cc-9673-1750447ce493 |  | checkpoint | Suitable material backfilled in compacted layers
checkpoint-group | 2377b7b7-8c1a-4374-acac-7ebf93748eea |  | section | Quality Assurance
checkpoint-no-status | 0956c3e4-d3f6-4955-aa95-963411999356 |  | checkpoint | QA
text | d64ab432-438a-5dfb-8853-efbeb86de909 |  | textbox | Date Section Completed
checkpoint-status | 3491f088-038a-4cae-aaa9-53704b1bce06 |  | checkpoint | Compaction testing Completed and Complies (attach compaction test results)
checkpoint-status | 5d32d7ed-97ca-49a3-8091-8cfb1a81ffbb |  | checkpoint | Vacuum / Hydrostatic / Ovality Testing Completed
text | f78fbe6c-5793-54b1-991e-eb33199d5ace |  | textbox | Link to Test Results
checkpoint-status | eb312ae9-9a8a-4dd4-a440-a173da3c1ab0 |  | checkpoint | CCTV Carried out upon completion of works
text | 480f4f68-2c89-5220-a1b8-e766e63c2cb2 |  | textbox | CCTV Link:
checkpoint-status | 5754243b-536a-4429-bc68-b48297718d35 |  | checkpoint | Lean Mix / Concrete dockets attached (if applicable)
checkpoint-status | d12e1582-64ae-4ed2-ae48-9bc37cb769a2 |  | checkpoint | Quarry / Material Certificates attached
checkpoint-status | 84692c89-528f-4adc-8460-508a7cc29aa7 |  | checkpoint | Pipe / Pit / Fitting Certificates attached
checkpoint-status | ec9a45bc-1c15-4c48-bce2-a247a594c536 |  | checkpoint | Additional Tech Data (Mortars / Glues / etc)
checkpoint-status | 46cc57ea-ec21-4ecb-88b3-131d80f39ae3 |  | checkpoint | Images of the works
text | c8730a23-3cec-527d-b41b-1613e16768ce |  | textbox | Additional Comments
holdpoint | 95175c23-2b67-4788-8599-ccd668be5985 |  | signoff | Signatures
checklist-sectioned | fb069fa4-2345-4e37-b76c-9c49ffc9f93e |  | checklist | ITP-001 - Installation Of Stormwater Drainage |  |  |  |  | Yes | ITP-001 - Installation Of Stormwater Drainage | 6003e816-693a-41e0-90b5-76c8b29dfece
checkpoint-group | 58558654-8d49-4c06-9e8f-5b1b7352b455 |  | section | Pre-Construction
checkpoint-status | 09315d03-14fd-495e-ba9c-8c1d0f51b446 |  | checkpoint | Are approved "For Construction" plans available?
checkpoint-status | dbfe5313-f838-4aaa-a3bf-d9943804ac51 |  | checkpoint | Are Earthworks completed to Finished Level?
checkpoint-status | a738479f-543b-4f5c-9089-208eddc4757d |  | checkpoint | Has the Client been advised of start date?
text | 53941d33-ec4e-5d9c-8204-8064bcaa44df |  | textbox | Pit / Line Information:
text | 5e0e0764-3b26-580c-a146-e0a79838d21c |  | textbox | Date Works Commenced:
checkpoint-status | 104dcdd8-0e56-4e55-b399-614b2a8aa1e8 |  | checkpoint | Existing services located and clearly marked (attach DBYD if applicable)
checkpoint-status | 3e39c048-8bc2-4223-bec0-5d8973f30a8c |  | checkpoint | All materials delivered to site have been inspected thoroughly and:
label | 0a363437-4e66-5754-908a-36dd8255ec95 |  | note | a) Are free of damage/cracks
label | fb025449-bd7f-5ddd-adff-28735cd458e0 |  | note | b) Pipe class, type and size matches plans.
label | 53b0938e-5d94-559e-9bb3-b7e62be11212 |  | note | (upload images of damaged materials here)
holdpoint | a6cf02f3-061c-4765-83c4-4814d79815a7 |  | signoff | HOLD POINT - Clients representative to acknowledge materials have been inspected and are free of damage/cracks.
checkpoint-group | a0c471de-043f-4f75-950e-2335b6e744fd |  | section | Construction
checkpoint-status | 4b91c784-ff31-4343-8842-f94abeb091b1 |  | checkpoint | Excavation Permit Completed
checkpoint-status | 8e89ab69-93fe-4d4f-b914-8fcd47d934ec |  | checkpoint | Pits/Trenches set out clearly & accurately
checkpoint-status | c6a87acc-e2f6-45c8-a608-241200fb2ba9 |  | checkpoint | Pits excavated to depth and checked with laser (allowed for 100mm bedding)
checkpoint-status | b0a51d68-8ca8-4f31-9c8b-a9a0ff86a6e7 |  | checkpoint | Pits exceeding 1.5m are correctly battered or compliant shoring installed
checkpoint-status | 9bc3cc01-c8ca-4b63-b298-2a76d3427596 |  | checkpoint | Pits Installed at correct height and orientation
checkpoint-status | d03a16ef-361b-489b-a230-2c62f76e59b9 |  | checkpoint | Trenches excavated to depth and checked with grade laser (allowed for 100mm bedding)
checkpoint-status | 6ba37c78-491c-4ea0-bf90-eb580109d54e |  | checkpoint | Trenches exceeding 1.5m are correctly battered or compliant shoring installed
holdpoint | 2fd56c82-72d5-4e3c-ba47-e420c79e3c70 |  | signoff | HOLD POINT - Presence of groundwater or contaminated material authorisation to proceed Requested & Approved (If Applicable)
checkpoint-status | 077216af-a53f-49fe-b866-3f4de0c47e68 |  | checkpoint | Trench bedding material installed as per specification
checkpoint-status | e267c2bb-0ec4-4403-bb68-c0001828ca84 |  | checkpoint | Pipe laid to grade (as per drawings) ensuring socket faces upstream and is free of foreign materials prior to installation of adjoining pipe
checkpoint-status | 4c752d6f-071c-4a80-9ef4-5b71b133a55f |  | checkpoint | Each joint visually inspected (rubber rings, witness marks, etc) and lifting holes plugged
holdpoint | b3a4953a-010f-4bf3-a61a-0f0f764ec543 |  | signoff | HOLD POINT - Clients representative to acknowledge compliant Pipe/Pit Installation
checkpoint-group | 8db98e40-acea-45dd-baff-e2eb26fd4fe0 |  | section | Backfill
checkpoint-status | 36c4e357-4af8-418a-833e-60ef21c02dec |  | checkpoint | Suitable material backfilled in layers not exceeding 150mm compacted thickness
holdpoint | aa3d8dc6-bcc6-41f5-9355-5df9ca8e8f88 |  | signoff | HOLD POINT - Clients representative to acknowledge Bedding, Haunching & backfill compliance
checkpoint-status | 80b0311b-c714-4147-9969-6936083358dc |  | checkpoint | Compaction testing Completed and Complies (attach compaction test results)
checkpoint-status | 1c374b13-d7b6-4119-a360-08367b09453c |  | checkpoint | CCTV Carried out upon completion of works (If applicable)
text | 31b60819-837a-531d-bc56-1d43a4dba12b |  | textbox | Date Section Completed
text | 8ce2c1c0-9be3-5a25-9390-fafd388f4811 |  | textbox | Additional Comments
label | 2be72eb8-8fc7-57d6-b0c2-7e90d5c71088 |  | note | Concrete Dockets attached
label | c427feea-4c5a-5d34-85b5-53b92f67e130 |  | note | Concrete Test Reports Attached
label | 5ed0d617-82d9-5f09-bb92-327cc6487a71 |  | note | Images of works
holdpoint | 46080fde-f6bd-4f83-a624-e6afdf3c87c1 |  | signoff | Signatures
checklist-sectioned | 4c693de2-ea79-4e0d-8544-a82c9268f56a |  | checklist | ITP-001 - Installation Of Stormwater Drainage |  |  |  |  | Yes | zSYS - ITP-001 - Installation Of Stormwater Drainage (old version) | 6a9554a6-1686-4fed-8000-48dd0384d1a5
checkpoint-group | 8ba130ef-8d52-4d2b-b1fb-8983014d082b |  | section | Pre-Construction
checkpoint-status | 147ff91b-88a2-402e-a8bd-0fe28d09992b |  | checkpoint | Are approved "For Construction" plans available?
checkpoint-status | e3c09318-f07a-47c8-8f8a-732602ea476e |  | checkpoint | Are Earthworks completed to Finished Level?
checkpoint-status | a3682c1a-58e5-4736-a5a5-e732403aa917 |  | checkpoint | Has the Client been advised of start date?
text | 93242439-bdc6-5c43-8ab7-842feab02a0e |  | textbox | Pit / Line Information:
text | 52b4b9a8-0270-5362-bd17-32e2bbd54f87 |  | textbox | Date Works Commenced:
checkpoint-status | d55143f7-c345-421e-82f2-7c983e8ab5db |  | checkpoint | Existing services located and clearly marked (attach DBYD if applicable)
checkpoint-status | 22e4b410-58b2-4ad2-8919-2e4d4fa9857b |  | checkpoint | All materials delivered to site have been inspected thoroughly and: a) Are free of damage/cracks b) Pipe class, type and size matches plans. (upload images of damaged materials here)
holdpoint | 4b29a21c-9bb1-47c6-a238-514c5111ad33 |  | signoff | HOLD POINT - Clients representative to acknowledge materials have been inspected and are free of damage/cracks.
checkpoint-group | 5e373b6f-2775-4c40-b5dc-d4677f9266ae |  | section | Construction
checkpoint-status | 31586b2c-f12e-4c69-85ed-eb9015e3cfe3 |  | checkpoint | Excavation Permit Completed
checkpoint-status | 4ac79787-a8aa-4c3e-85d5-4735d629b9c6 |  | checkpoint | Pits/Trenches set out clearly & accurately
checkpoint-status | 848e17b1-521f-4e9f-9140-34df14bcad9c |  | checkpoint | Pits excavated to depth and checked with laser (allowed for 100mm bedding)
checkpoint-status | ca6e9ef4-f627-49fd-b21c-26653bddd290 |  | checkpoint | Pits exceeding 1.5m are correctly battered or compliant shoring installed
checkpoint-status | a9755b49-dd08-4523-b7ac-c246211d515a |  | checkpoint | Pits Installed at correct height and orientation
checkpoint-status | 689937ff-4ef6-467c-8d85-29f2960e4c36 |  | checkpoint | Trenches excavated to depth and checked with grade laser (allowed for 100mm bedding)
checkpoint-status | 19b3760a-703c-41ea-a66b-4840d449e914 |  | checkpoint | Trenches exceeding 1.5m are correctly battered or compliant shoring installed
holdpoint | 42d545d7-fdf5-4847-9030-9b6e04148c91 |  | signoff | HOLD POINT - Presence of groundwater or contaminated material authorisation to proceed Requested & Approved (If Applicable)
checkpoint-status | ba060d15-87a3-4b25-861e-6bb944038496 |  | checkpoint | Trench bedding material installed as per specification
checkpoint-status | 8fe3480b-edb6-4ac1-bf2b-f03827ab89f5 |  | checkpoint | Pipe laid to grade (as per drawings) ensuring socket faces upstream and is free of foreign materials prior to installation of adjoining pipe
checkpoint-status | 8fd3f034-1c7a-4ed8-b2e6-3369eb9b697a |  | checkpoint | Each joint visually inspected (rubber rings, witness marks, etc) and lifting holes plugged
holdpoint | bdbff812-69ce-4ed9-affa-18d08bcd072a |  | signoff | HOLD POINT - Clients representative to acknowledge compliant Pipe/Pit Installation
checkpoint-group | f7cf6161-6c14-4575-aac6-614437519c91 |  | section | Backfill
checkpoint-status | a9d311b9-ae0a-4e68-acc3-03508bcfe9e4 |  | checkpoint | Suitable material backfilled in layers not exceeding 150mm compacted thickness
holdpoint | c9830248-860f-4ae1-bdbc-4e2d2729ac12 |  | signoff | HOLD POINT - Clients representative to acknowledge Bedding, Haunching & backfill compliance
checkpoint-status | 3afd4683-aa16-41d3-bbde-4ede25245bfd |  | checkpoint | Compaction testing Completed and Complies (attach compaction test results)
checkpoint-status | 28b71c38-e887-4390-ba8a-f6bda3b58a32 |  | checkpoint | CCTV Carried out upon completion of works (If applicable)
text | 8544e9b4-0fb7-5bb7-86ec-fc5bb07cf189 |  | textbox | Date Section Completed
text | 670e8ad7-c4a2-5fcd-bdf3-869ce4560d52 |  | textbox | Additional Comments
label | b141f160-4be9-5b59-a7c1-546910554ab0 |  | note | Concrete Dockets attached
label | ef7f9414-a5ca-5d15-a133-ac655b97c859 |  | note | Concrete Test Reports Attached
label | c4f3b747-d14e-5629-8c8a-7bafa8924dfd |  | note | Images of works
holdpoint | 9037c056-f63d-4407-9d27-61bc48c1a66a |  | signoff | Signatures
checklist-sectioned | c0b320e5-f1cd-4545-86e6-b676f34ff957 |  | checklist | ITP-004 - Installation of WaterMain (Completion) |  |  |  |  | Yes | ITP-004 - Installation of WaterMain (Completion) | a4f22666-ed31-4de7-aa5d-dae05b0bdd29
checkpoint-group | 40f8d5ef-6281-4629-91ad-ee420c292210 |  | section | Pre-Construction
checkpoint-no-status | deca7a6f-3b00-40cc-8f12-5dc0cf99488e |  | checkpoint | Pre-Construction
text | 6afe1453-a645-59c9-a014-25d542edd35c |  | textbox | Date Works Commenced:
checkpoint-status | 0fb89586-db71-4355-8df5-4bc37df66d39 |  | checkpoint | All materials delivered to site have been inspected thoroughly by RCC Earthworks and the Client and:
label | bf94ed4d-20e3-5a13-837f-6144a6b654db |  | note | a) Are free of damage/cracks
label | 9fbf2c87-6bab-585a-b38f-dddd9f008a7f |  | note | b) Fittings, Pipe class, type and size matches plans.
label | 604480d7-ce38-513d-a240-f01d59bd3556 |  | note | (upload images of damaged materials here)
checkpoint-group | 1a748181-e6d4-401b-a191-3382baac2215 |  | section | Construction
checkpoint-status | 67813fe6-a294-4838-8390-3ac531cc1570 |  | checkpoint | Trenches set out clearly & accurately
checkpoint-status | 0e6fa672-acdb-4adc-81d7-70a6b7cdacd0 |  | checkpoint | Trenches excavated to depth and checked with laser (allowed for 100mm bedding)
checkpoint-status | 941125fa-387f-43f4-b2ee-b4d2a188a97d |  | checkpoint | Trench bedding material installed as per specification
checkpoint-status | a8c2b56d-9880-467c-b897-7627cd322132 |  | checkpoint | Pipe laid (as per drawings) ensuring socket is free of foreign materials prior to installation of adjoining pipe.
checkpoint-status | 52beed35-53f8-4b6b-87ea-2dc3e3bfc27d |  | checkpoint | Each joint visually inspected (rubber rings, witness marks, etc)
checkpoint-status | ab23fdcd-f571-4675-8500-1ecfa34efd0a |  | checkpoint | Thrust Blocks installed, where applicable. (Images Attached)
checkpoint-status | 71c00849-ac39-43b6-b357-8cd74acf5714 |  | checkpoint | Haunching compliant and accepted by the client.
checkpoint-group | 4f4bba4f-b46b-4132-8a65-8aa26702b792 |  | section | Backfill
checkpoint-status | ab114dd2-0c9f-4b8e-9092-5d5fb3afb14a |  | checkpoint | Suitable material backfilled in compacted layers
checkpoint-group | fd51dfcc-177e-4283-a999-d5cc2ea13213 |  | section | Quality Assurance
checkpoint-no-status | f1e7cc6d-0c84-47f9-b3e3-24292180a181 |  | checkpoint | QA
text | 42fbbd6f-24d8-55e5-99cc-64aba1c7f9d1 |  | textbox | Date Section Completed
checkpoint-status | 7db4c9f1-6a77-48bc-985e-6bd6f00ad0ae |  | checkpoint | Compaction testing Completed and Complies (attach compaction test results)
checkpoint-status | ab511ecd-9e9f-4909-a0ac-1b468e8b85c4 |  | checkpoint | Vacuum / Hydrostatic / Ovality Testing Completed
text | 82574d49-d71f-5e7e-8e32-d7c88d84f14b |  | textbox | Link to Test Results
checkpoint-status | 5afcae44-344b-4659-a315-0c3640ecf5a9 |  | checkpoint | Lean Mix / Concrete dockets attached (if applicable)
checkpoint-status | 0c181c18-4a65-48a8-bad1-8129bcf32117 |  | checkpoint | Quarry / Material Certificates attached
checkpoint-status | 602a9f19-2cc3-42a8-b2b0-98b9ae4a1a7c |  | checkpoint | Pipe / Pit / Fitting Tech Data attached
checkpoint-status | 7a97789d-e03e-4e82-90d4-36bfd49c9a1c |  | checkpoint | Additional Tech Data (Mortars / Glues / etc)
checkpoint-status | 0102d13f-1ee8-44d3-a584-304c004792d4 |  | checkpoint | Images of the works
text | a2b928ed-2250-5f9c-94e5-1ff6d51d08fa |  | textbox | Additional Comments
holdpoint | 85ad69be-273f-416a-86f0-d69a417a7aad |  | signoff | Signatures
checklist-sectioned | 460f3f80-694b-4496-b001-0d85974cb936 |  | checklist | ITP-003 - Installation of Stormwater Drainage (Completion) |  |  |  |  | Yes | ITP-003 - Installation of Stormwater Drainage (Completion) | bab5efaa-682b-459e-a3f4-b72d8a2c8db6
checkpoint-group | cadddb73-fd37-4ea6-b300-977c1985af40 |  | section | Pre-Construction
checkpoint-no-status | e543fa06-0f07-41f7-a76d-145cbaa2ad63 |  | checkpoint | Pre-Construction
text | f249c032-3ed4-5d19-bff0-f0318c22c318 |  | textbox | Date Works Commenced:
checkpoint-status | 22da906b-121a-4e6f-8b18-148f8dabc495 |  | checkpoint | All materials delivered to site have been inspected thoroughly by RCC Earthworks and the Client and:
label | e885dc7c-a3ed-56a5-86a3-e1be58024f12 |  | note | a) Are free of damage/cracks
label | a468a88f-3c7a-5924-9969-efd2bb241aa3 |  | note | b) Pipe class, type and size matches plans.
label | 9d264cee-8cc4-5846-be35-dd8ac47d906c |  | note | (upload images of damaged materials here)
checkpoint-group | 2c51a0cc-132e-4fdb-8d2a-5cb806ba4f26 |  | section | Construction
checkpoint-status | 043568f2-d812-46b8-9daa-778a750654d0 |  | checkpoint | Pits/Trenches set out clearly & accurately
checkpoint-status | 583f9479-2058-46f9-99a6-2874b42bfe39 |  | checkpoint | Pits & Trenches excavated to depth and checked with laser (allowed for 100mm bedding)
checkpoint-status | 5b07d951-3f49-4439-9f33-85e5dc725713 |  | checkpoint | Pits Installed at correct height and orientation
checkpoint-status | 09f893f3-da42-40a1-9d28-ebb240aa46f1 |  | checkpoint | Trench bedding material installed as per specification
checkpoint-status | 2062bc68-ede1-4c5b-99f1-9ba2e0797d1f |  | checkpoint | Pipe laid to grade (as per drawings) ensuring socket faces upstream and is free of foreign materials prior to installation of adjoining pipe
checkpoint-status | b6dcf5bd-af10-436d-aa3f-de9cbe4dd192 |  | checkpoint | Each joint visually inspected (rubber rings, witness marks, etc) and lifting holes plugged
checkpoint-status | 42732232-eecb-45d4-a57f-7dccc3e461af |  | checkpoint | Haunching compliant and accepted by the client.
checkpoint-group | 40349258-4595-48ef-89b2-6a194b0dcb83 |  | section | Backfill
checkpoint-status | 1aa8d16f-71a8-41b2-8b08-8a37b92c3fb4 |  | checkpoint | Suitable material backfilled in compacted layers
checkpoint-group | 644ea250-9fa3-4c81-afb9-bcb67caa3f91 |  | section | Quality Assurance
checkpoint-no-status | 733dc4d4-d203-41c8-8773-40746f7950de |  | checkpoint | QA
text | c2907100-9c67-541b-8c90-1740c842f307 |  | textbox | Date Section Completed
checkpoint-status | 304258f5-015b-4159-b057-9c3db9513fbf |  | checkpoint | Compaction testing Completed and Complies (attach compaction test results)
checkpoint-status | e1abf23f-0858-4a99-a006-2ca38975ed55 |  | checkpoint | CCTV Carried out upon completion of works
text | 6593b9da-e4a8-58ad-aa29-f2001e3dc7b7 |  | textbox | CCTV Link:
checkpoint-status | cef16e58-b885-40ed-91fb-e51b47861592 |  | checkpoint | Lean Mix / Concrete dockets attached (if applicable)
checkpoint-status | 9ffaab6c-c048-47d6-b11e-dd786f28d015 |  | checkpoint | Quarry / Material Certificates attached
checkpoint-status | 37ef5dc6-eded-4e62-b906-b759ff062291 |  | checkpoint | Pipe / Pit / Fitting Certificates attached
checkpoint-status | 2ed0b194-283e-4391-841c-1e4633b916e9 |  | checkpoint | Images of the works
text | 8b16c5d2-494b-5ed9-8813-b09e91094d60 |  | textbox | Additional Comments
holdpoint | dd553590-272f-4990-aad4-c61cc908f2fd |  | signoff | Signatures