## Checklists
PROJECT NAME: Industry Central Land Swap
CLIENT: Alder Constructions
type | name | values
checklist | ITP-004 - Installation of WaterMain (Completion)
section | Pre-Construction
Text | Date Works Commenced:
checkpoint | All materials delivered to site have been inspected thoroughly by RCC Earthworks and the Client and: a) Are free of damage/cracks b) Fittings, Pipe class, type and size matches plans. (upload images of damaged materials here)
Section | Construction
Checkpoint | Trenches set out clearly & accurately
Checkpoint | Trenches excavated to depth and checked with laser (allowed for 100mm bedding)
Checkpoint | Trench bedding material installed as per specification
Checkpoint | Pipe laid (as per drawings) ensuring socket is free of foreign materials prior to installation of adjoining pipe.
Checkpoint | Each joint visually inspected (rubber rings, witness marks, etc)
Checkpoint | Thrust Blocks installed, where applicable. (Images Attached)
Checkpoint | Haunching compliant and accepted by the client.
Section | Backfill
checkpoint | Suitable material backfilled in compacted layers
Section | Quality Assurance
Text | Date Section Completed
Checkpoint | Compaction testing Completed and Complies (attach compaction test results)
Checkpoint | Vacuum / Hydrostatic / Ovality Testing Completed
Text | Link to Test Results
Checkpoint | Lean Mix / Concrete dockets attached (if applicable)
Checkpoint | Quarry / Material Certificates attached
Checkpoint | Pipe / Pit / Fitting Tech Data attached
Checkpoint | Additional Tech Data (Mortars / Glues / etc)
Checkpoint | Images of the works
Text | Additional Comments
signoff | Signatures