## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned | 4c693de2-ea79-4e0d-8544-a82c9268f56a |  | checklist | ITP-001 - Installation Of Stormwater Drainage |  |  |  |  | Yes | ITP-001 - Installation Of Stormwater Drainage | 6a9554a6-1686-4fed-8000-48dd0384d1a5
checkpoint-group | 8ba130ef-8d52-4d2b-b1fb-8983014d082b |  | section | Pre-Construction
checkpoint-status | 147ff91b-88a2-402e-a8bd-0fe28d09992b |  | checkpoint | Are approved "For Construction" plans available?
checkpoint-status | e3c09318-f07a-47c8-8f8a-732602ea476e |  | checkpoint | Are Earthworks completed to Finished Level?
checkpoint-status | a3682c1a-58e5-4736-a5a5-e732403aa917 |  | checkpoint | Has the Client been advised of start date?
text | 93242439-bdc6-5c43-8ab7-842feab02a0e |  | textbox | Pit / Line Information:
text | 52b4b9a8-0270-5362-bd17-32e2bbd54f87 |  | textbox | Date Works Commenced:
checkpoint-status | d55143f7-c345-421e-82f2-7c983e8ab5db |  | checkpoint | Existing services located and clearly marked (attach DBYD if applicable)
checkpoint-status | 22e4b410-58b2-4ad2-8919-2e4d4fa9857b |  | checkpoint | All materials delivered to site have been inspected thoroughly and: a) Are free of damage/cracks b) Pipe class, type and size matches plans. (upload images of damaged materials here)
holdpoint | 4b29a21c-9bb1-47c6-a238-514c5111ad33 |  | signoff | HOLD POINT - Clients representative to acknowledge materials have been inspected and are free of damage/cracks.
checkpoint-group | 5e373b6f-2775-4c40-b5dc-d4677f9266ae |  | section | Construction
checkpoint-status | 31586b2c-f12e-4c69-85ed-eb9015e3cfe3 |  | checkpoint | Excavation Permit Completed
checkpoint-status | 4ac79787-a8aa-4c3e-85d5-4735d629b9c6 |  | checkpoint | Pits/Trenches set out clearly & accurately
checkpoint-status | 848e17b1-521f-4e9f-9140-34df14bcad9c |  | checkpoint | Pits excavated to depth and checked with laser (allowed for 100mm bedding)
checkpoint-status | ca6e9ef4-f627-49fd-b21c-26653bddd290 |  | checkpoint | Pits exceeding 1.5m are correctly battered or compliant shoring installed
checkpoint-status | a9755b49-dd08-4523-b7ac-c246211d515a |  | checkpoint | Pits Installed at correct height and orientation
checkpoint-status | 689937ff-4ef6-467c-8d85-29f2960e4c36 |  | checkpoint | Trenches excavated to depth and checked with grade laser (allowed for 100mm bedding)
checkpoint-status | 19b3760a-703c-41ea-a66b-4840d449e914 |  | checkpoint | Trenches exceeding 1.5m are correctly battered or compliant shoring installed
holdpoint | 42d545d7-fdf5-4847-9030-9b6e04148c91 |  | signoff | HOLD POINT - Presence of groundwater or contaminated material authorisation to proceed Requested & Approved (If Applicable)
checkpoint-status | ba060d15-87a3-4b25-861e-6bb944038496 |  | checkpoint | Trench bedding material installed as per specification
checkpoint-status | 8fe3480b-edb6-4ac1-bf2b-f03827ab89f5 |  | checkpoint | Pipe laid to grade (as per drawings) ensuring socket faces upstream and is free of foreign materials prior to installation of adjoining pipe
checkpoint-status | 8fd3f034-1c7a-4ed8-b2e6-3369eb9b697a |  | checkpoint | Each joint visually inspected (rubber rings, witness marks, etc) and lifting holes plugged
holdpoint | bdbff812-69ce-4ed9-affa-18d08bcd072a |  | signoff | HOLD POINT - Clients representative to acknowledge compliant Pipe/Pit Installation
checkpoint-group | f7cf6161-6c14-4575-aac6-614437519c91 |  | section | Backfill
checkpoint-status | a9d311b9-ae0a-4e68-acc3-03508bcfe9e4 |  | checkpoint | Suitable material backfilled in layers not exceeding 150mm compacted thickness
holdpoint | c9830248-860f-4ae1-bdbc-4e2d2729ac12 |  | signoff | HOLD POINT - Clients representative to acknowledge Bedding, Haunching & backfill compliance
checkpoint-status | 3afd4683-aa16-41d3-bbde-4ede25245bfd |  | checkpoint | Compaction testing Completed and Complies (attach compaction test results)
checkpoint-status | 28b71c38-e887-4390-ba8a-f6bda3b58a32 |  | checkpoint | CCTV Carried out upon completion of works (If applicable)
text | 8544e9b4-0fb7-5bb7-86ec-fc5bb07cf189 |  | textbox | Date Section Completed
text | 670e8ad7-c4a2-5fcd-bdf3-869ce4560d52 |  | textbox | Additional Comments
label | b141f160-4be9-5b59-a7c1-546910554ab0 |  | note | Concrete Dockets attached
label | ef7f9414-a5ca-5d15-a133-ac655b97c859 |  | note | Concrete Test Reports Attached
label | c4f3b747-d14e-5629-8c8a-7bafa8924dfd |  | note | Images of works
holdpoint | 9037c056-f63d-4407-9d27-61bc48c1a66a |  | signoff | Signatures