## Sheet1
Retaining Wall Checklist
Checkpoint | Pre Retaining Wall construction checks completed & approved | Yes, No, N/A
Checkpoint | Location reference attached | Photo
Text | Distance measured to the bottom of the pile toe | text
Text | Bored pile diameter | text
HOLDPOINT | Bored pile within tolerances (75mm horizontal position, 1:75 for pile verticality) | Yes, No, N/A
Checkpoint | Steel column location correct | Yes, No, N/A
Checkpoint | 75mm cover achieved between steel and column | Yes, No, N/A
Checkpoint | Steel posts shall be installed to the following max. tolerances (25mm in plan , 1:100 for post verticality) | Yes, No, N/A
Text | Approved Concrete Mix Code Ordered | specify concrete mix code
Checkpoint | Photographs of Concrete dockets (All relevant dockets photographed and attached) | Photo
HOLD POINT | Ensure that 75% of the specified 28 days concrete compressive strength is achieved before the installation of the panels. | Yes, No, N/A
HOLDPOINT | Provide lab results indicating 75% strength achieved | Photo
Checkpoint | Concrete Panel placed as per setout | Yes, No, N/A
Checkpoint | Bearing strip installed between the panel and the pile | Yes, No, N/A
Checkpoint | All reinforcing, shims and fixings line up with the appropriate items on the preceding work. | Yes, No, N/A
text | Top of Concrete Panel RL | Text
Checkpoint | Backfill: A19 geotextile is placed against cut face - minimum lap 300mm (photo) | Yes, No, N/A
Checkpoint | Subsoils location, grade and outlet points as per Jacobs instruction (photos and as-built) | Yes, No, N/A
Checkpoint | Backfilled behind the wall with drainage material (25) to agreed upon height - all voids filled (photo) | Yes, No, N/A
Checkpoint | Backfill between panels: 100mm thick compacted GAP40 - tested and passed | Yes, No, N/A
holdpoint | Request sign off