## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP - Concrete work |  |  |  |  | Yes | ITP - Concrete work | 1f69d4cd-1b01-4233-9408-575ff903190e
checkpoint-group |  |  | section | Pre-pour
checkpoint-status |  |  | checkpoint | Concrete mix design
label | 203df3b0-5bda-5fd7-9040-4c2ddf530d01 |  | note | Concrete mix certificates submitted and approved for concrete mixes to be used
checkpoint-status |  |  | checkpoint | Formwork
label | 98d6ce61-9253-5912-ba9d-945ab9b4874d |  | note | Check location, depth, height, falls and dimensions to be in accordance with plans.
checkpoint-status |  |  | checkpoint | Reinforcing
label | 5c3eee71-2926-517a-b424-11a9970da2d5 |  | note | Size, type, covers, position, lap, construction joints, spacing, started bars to be in accordance with plans.
checkpoint-status |  |  | checkpoint | HD Bolts
label | db37ebd9-a6df-5999-948b-7382ec8178f0 |  | note | Confirm location, install bolts in accordance with plans.
checkpoint-status |  |  | checkpoint | Overall
label | 2331aff6-74d0-54f9-8747-fe20595897d5 |  | note | Waterproof, bottom of concrete clean from debris, construction joints, existing services to be in accordance with plans.
checkpoint-group |  |  | section | Post-pour
checkpoint-status |  |  | checkpoint | Overall
label | 651e761a-8c43-5059-b153-f00d19619892 |  | note | Saw cuts, concrete curing as per specified methodology, formwork removed without damage to the concrete, to be in accordance with plans.
checklist-flat |  |  | checklist | ITP - Footpath, Kerbs, Dish Channels and Subsoils |  |  |  |  | Yes | ITP - Footpath, Kerbs, Dish Channels and Subsoils | 64b67995-2c60-43de-a95e-f8ee874fdef8
checkpoint-status |  |  | checkpoint | 2.1 - Material Compliance (subsoil)
label | 97b51119-edc4-5e30-818b-d0cd608138ff |  | note | Standard, Drawing or Specification Reference - 8624 Section 1.9
label | 6fc3ea1a-d9f5-5202-957c-eb7e65f8ecea |  | note | Construction Activity / Test Type / Acceptance Criteria - Subsoil installed as per manufacturers requirement. Subsoil locations and layout as per Civil IFC drawings
label | 8cf966d5-07be-5e8a-88d3-57e14f3a606e |  | note | Test Frequency - No test frequency
checkpoint-status |  |  | checkpoint | 2.2 - Concrete Strength
label | dccc5668-f2a5-55d3-9394-3b3276e3ce06 |  | note | Standard, Drawing or Specification Reference - 8241 Section 2.1
label | df23529e-18ef-5c9f-8120-2cd810351b07 |  | note | Construction Activity / Test Type / Acceptance Criteria - · Bedding: 10 MPa (not for work associated with roading) · Channel and haunching: 20 MPa · Precast kerbs: 20 MPa · Extruded concrete: 25 MPa · Footpaths and crossings 20 MPa · Capping beam: 40Mpa
label | bd08a7c8-c1f5-55bc-814b-1b7ef4f314b8 |  | note | Test Frequency - No test frequency
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Concrete Finishes
label | ad9cf5bf-699b-53e9-a9f3-07d64fb4cf97 |  | note | Standard, Drawing or Specification Reference - 8241 Section 2.2 Structural spec 3124 FINISHES TO WET CONCRETE
label | ae1e0e3d-ed87-5ecb-873d-cb89c88834b2 |  | note | Construction Activity / Test Type / Acceptance Criteria - Location: Top surface of external pathways, driveways, stairs, ramps and landings. Finish: U5 - Textured by Bass Broom. · Shallow textured to NZS 3114: clause 305.2, U5 finish, with abrupt changes not exceeding 3mm and gradual variations not exceeding 5mm. · To be finished to achieve slip resistance as per Table 2 of NZBC Section D1 Location: Exposed edges of ground floor slabs, ground beams and plinths Finish: F5, with abrupt changes not exceeding 2mm at construction joints nor 1mm at joints between abutting shutters or sheets that form face material. Gradual variations not exceeding 6mm
label | 51cff9ad-81b1-52a7-a160-c2efededd653 |  | note | Test Frequency - Visual Inspection as required
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | Concrete Pre Pour |  |  |  |  | Yes | Concrete Pre Pour | 80019633-bfc2-4c12-a399-00c3327d6ade
checkpoint-group |  |  | section | Preliminary
checkpoint-status |  |  | checkpoint | Location
checkpoint-status |  |  | checkpoint | Foundation / Base prep
checkpoint-group |  |  | section | Formwork / Falsework
checkpoint-status |  |  | checkpoint | Dimensionally correct - Heights/Falls checked
checkpoint-status |  |  | checkpoint | Secure / Stable
checkpoint-group |  |  | section | Reinforcing
checkpoint-status |  |  | checkpoint | Steel grade and size
checkpoint-status |  |  | checkpoint | Spacing of bars
checkpoint-status |  |  | checkpoint | Tie wire in place / secure
checkpoint-status |  |  | checkpoint | Steel cover correct
checkpoint-status |  |  | checkpoint | Steel is clean
checkpoint-group |  |  | section | Concrete
checkpoint-status |  |  | checkpoint | Concrete Strength
boolean | 1837f7bf-b667-5511-a86b-a26bdd661e1c |  | tickbox | Special Mix Code
checkpoint-status |  |  | checkpoint | Oxide State
checkpoint-status |  |  | checkpoint | Special Aggregate
checkpoint-status |  |  | checkpoint | Docket Numbers
text | bab83b22-e0a9-5ca6-b4d1-0aa66080a255 |  | textbox | Enter Docket Number:
checklist-sectioned |  |  | checklist | ITP - Roading |  |  |  |  | Yes | ITP - Roading | 9222aeae-2aee-4523-993f-d8789b652e28
checkpoint-group |  |  | section | Sub-Grade
checkpoint-status |  |  | checkpoint | Visually check materials. Quality and Condition
label | db42f380-0809-58d0-afe6-f497fb394bc1 |  | note | Check Material quality to be GAP 65 laid at depth specified on plans
checkpoint-status |  |  | checkpoint | Compaction Testing - testing every 100m2 or every 10m staggered in both lanes with Scalar Penetrometer
label | 502ba0ce-3eb5-576b-b951-dfefc8ab8889 |  | note | Compaction testing to achieve CBR value as per specific design
checkpoint-group |  |  | section | Sub-base
checkpoint-status |  |  | checkpoint | Material Grade Check
label | c8025ba3-dabb-5b97-9d51-cd9ac029b5cd |  | note | As per Civil Works specification
checkpoint-status |  |  | checkpoint | Visually check materials. Quality and Condition
label | 5d5dbbf4-873a-590d-8da4-60d2b8fab4ec |  | note | Check Material quality
checkpoint-status |  |  | checkpoint | Nuclear Densimeter
label | ed3c0388-a8c8-5e9b-bbaa-5f2efa0e8c82 |  | note | Sub-base 95% maximum dry density
checkpoint-status |  |  | checkpoint | Profile and depth
label | cce9299e-aea9-5576-ad0d-5c28f93d29ae |  | note | Check Sub base to be as specified in engineering drawings
checkpoint-group |  |  | section | Base Course
checkpoint-status |  |  | checkpoint | Material Grade Check
label | 65966a04-e117-5fac-8ee6-08ba00b8376a |  | note | As per Civil Works specification
checkpoint-status |  |  | checkpoint | Visually check materials. Quality and Condition
label | 4393ec3b-dd93-596d-997b-9edef66728dc |  | note | Check Material quality
checkpoint-status |  |  | checkpoint | Compaction Testing, (Clegg Hammer @ 20m centres at the edges and the centre of the pavement
label | 18fb39f8-97df-5ffc-a196-8ef662be6841 |  | note | As per Civil Works specification
checkpoint-status |  |  | checkpoint | Profile and depth
label | a4e6393d-03b0-5d6f-96eb-2c6e6322fbc7 |  | note | Check base layer to be 150mm thick as specified in engineering drawings
checkpoint-status |  |  | checkpoint | Nuclear Densometer
label | e58bcb5c-73b3-56c5-a73d-589fd7d69c63 |  | note | Basecourse 98% maximum dry density
checkpoint-group |  |  | section | Surfacing
checkpoint-status |  |  | checkpoint | Pre-seal inspection
label | a0600820-ba25-5d6b-9221-5f335fcbf2ce |  | note | As per Civil Works specification
checkpoint-status |  |  | checkpoint | Post-seal inspection
label | 67954801-ef04-594c-a898-5e81a37de76e |  | note | Visual inspection
checkpoint-group |  |  | section | Kerb and Channel
checkpoint-status |  |  | checkpoint | Visually check materials. Quality and Condition
label | 216de70c-3d5f-59e2-b42b-8958db669b16 |  | note | Material Quality - check for ponding along channel and all crossings