## Ftpath, Kerbs, Channels,Subsoil
type | Footpath, Kerbs, Channels,Subsoil | values | prefix | postfix
checklist | General
checkpoint | Concrete Strength as shown in the drawing | Specify concrete strength
checkpoint | Concrete Docket | Attach file
checkpoint | Concrete Finish as shown in spec | Specify Attach photos
checklist | Kerbs
checkpoint | String line set-up to the required level | Yes, No, N/A (Provide photo)
checkpoint | Standard pre-cast kerb blocks in concrete haunching, to line and levels show | Yes, No, N/A (Provide photo)
checkpoint | Ensure the formation to bedding sub-base level for the kerb and/or channel is well compacted, smooth, uniform and to the required level. | Yes, No, N/A (Provide photo)
checkpoint | Lay edging, kerbs and gutter channels, true and straight to grade, alignment and level. | Yes, No, N/A (Provide photo)
checkpoint | Form construction joints as per design | Yes, No, N/A (Provide photo)
checkpoint | Check kerb tolerance | Provide levels
checklist | Footpath
checkpoint | String line set-up to the required level | Yes, No, N/A (Provide photo)
checkpoint | Footpath and vehicle crossings to levels and geometry shown in the drawings

## Subbase
type | name | values | prefix | postfix
checklist | Subbase
checkpoint | Fill placed using approved methods, to required dimensions, levels, line and profiles | Yes, No, N/A
checkpoint | Deviation of <12mm from a 3.0m straight edge laid parallel | Yes, No, N/A
HOLDPOINT | Clegg test top of subgrade every 10m | Pass/Fail Provide test results
HOLDPOINT | NDM test results | Pass/Fail Provide test results
Checkpoint | Beam test results (optional) | Pass/Fail Provide test results
HOLDPOINT | Completion Inspection of sub-grade for acceptance | Pass/Fail
checkpoint | As-built documents received | Yes, No, N/A
checkpoint | General progress photos recorded | Provide Photos
checklist | Basecourse
checkpoint | Fill placed using approved methods, to required dimensions, levels, line and profiles | Yes, No, N/A
checkpoint | No point than 10mm deviation from a 3.0m straight-edge | Yes, No, N/A
checkpoint | No depressions that would hold water. | Yes, No, N/A
HOLDPOINT | NDM test results | Pass/Fail Provide test results
Checkpoint | Beam test results (optional) | Pass/Fail Provide test results
HOLDPOINT | Ensure that degree of saturation is <80% before sealing | Pass/Fail Provide test results
checkpoint | As-built documents compiled | Yes, No, N/A
checkpoint | General progress photos recorded | Provide Photos