## QA Folder Structure
Site QA |  |  | Checklists | CONQA Notes
Keller Site QA
Retention Piles
|  | 1 - 114 | Piling Records ITP | The 1 - 114 needs to be expanded out into individual Piles
Foundation Piles
|  | 1 - 144 | Piling Records ITP | The 1 - 144 needs to be expanded out into individual Piles
Delta Site QA
Capping Beam
Shotcrete Walls
Ground Anchors
Footings
Slab On Ground
Photos
12 Months (Starting October)
|  | Days (expanded out) | Document / Photo Upload Checklist

## Copy of Checklists
type | name | values | prefix | postfix | usage count | user addable
checklist-flat | Capping Beams ITP
checkpoint | Drawing & Reference
text | Drawing & Revision Number(s)
text | Reference (Use Gridlines / Pile Numbers, etc.)
label | Surveyor to Check Position of Capping beam
text | Blinding RL
text | Top of Capping Beam RL
checkpoint | Reo Placement
text | Pile Reo Length
text | Reo Size/Configuration as per schedule
label | Cover: 50mm
label | Photos attached
label | Engineers Inspection - sign off attached
checkpoint | Commencement of pour
label | OK to Pour. Shotcrete methodology attached
checkpoint | Concrete
text | Concrete Strength
label | Concrete dockets/test Docket attached
checkpoint | Signed off / Handed Over
checklist-flat | Pad Footing - Crane Base ITP
checkpoint | Drawing & Reference
text | Drawing & Revision Number(s)
text | Reference (Use Gridlines / Pile Numbers, etc.)
label | Surveyor to set out pads and starter positions - Check position
text | Top blinding
text | Top of pad
checkpoint | Reo Placement
text | Pile Reo Length
text | Reo Size/Configuration as per schedule
label | Cover: 50mm
label | Photos attached
label | Engineers Inspection - sign off + evidence of close out attached
checkpoint | Commencement of pour
checkpoint | Concrete
text | Concrete Strength
label | Concrete dockets/test Docket attached
checkpoint | Signed off / Handed Over
checklist-flat | Rafts ITP
checkpoint | Drawing & Reference
text | Drawing & Revision Number(s)
text | Reference (Use Gridlines / Pile Numbers, etc.)
label | Surveyor to set out pads and starter positions - Check position
text | Top blinding
text | Top of pad
checkpoint | Reo Placement
text | Pile Reo Length
text | Reo Size/Configuration as per schedule
label | Cover: 50mm
label | Photos attached
label | Engineers Inspection - sign off + evidence of close out attached
checkpoint | Commencement of pour
checkpoint | Concrete
text | Concrete Strength
label | Concrete dockets/test Docket attached
checkpoint | Signed off / Handed Over
checklist-flat | Shotcrete Walls ITP
checkpoint | Concrete mix design confirmed
checkpoint | Soil cleaned off piles and back of the wall
checkpoint | Reinforcement installed as per drawings and specifications
checkpoint | Reinforcement drilled and epoxied (correct epoxy being used and embedment)
checkpoint | Cover to reinforcement as per specifications
checkpoint | CHS Confirmed as per drawings
text | Thickness
text | Size Gauge
text | Length
checkpoint | Water Proofing installed
checkpoint | Engineer inspection completed or photos sent
label | Engineer sign off attached
checkpoint | Concrete mix design checked upon delivery of concrete
label | Delivery docket attached
checkpoint | Wall trowelled, and finish completed as per architectural (or architectural sample)
checkpoint | Slab Starters for B1
checklist-flat | Document / Photo Upload Checklist
checkpoint | Photo / Doc Uploaded below
checklist-flat | Piling Records ITP
checkpoint | Pile Drilling Sequence
text | Platform Level (RL m)
text | Diameter (mm)
text | Concrete Grade (MPa)
text | Drill Depth (m)
text | Socket Length (m)
text | Top of Concrete (RL m)
text | Concrete Volume (m3)
checkpoint | Reinforcement - Cage
text | Top of Cage (RL m)
text | Bars xNyy
text | Spiral Size (mm)
text | Spiral Pitch (mm)
text | Length (m)
checkpoint | Reinforcement - Bundled Bars
text | Bars xNyy
text | Length (m)
checkpoint | Final
text | Verticality (mm / m)
text | Offsets (mm / direction)
button | Concrete Test | Yes,No
text | Concrete Test Result
checkpoint | Keller Superviser Sign Off / Handover
checkpoint | Delta Group Sign Off