## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP 004 Earthworks Cut | [5 empty] | ITP 004 Earthworks Cut
section | 1.0 Pre-Construction
checkpoint | 1.01 - Approved CWP
note | Method/Description - Document Review
note | Test frequency - Prior to personal starting
note | Constructor - H
note | Verifying Records - signed off CWP
checkpoint | 1.02 - IFC issued
note | Method/Description - Document Review
note | Test frequency - Prior to starting
note | Constructor - H
note | Verifying Records - IFC drawings or written approval from PAB
checkpoint | 1.03 - Approved SCWMP
note | Method/Description - Document Review
note | Test frequency - Once prior to works commencing
note | Constructor - H
note | Verifying Records - Approved SCWMP
section | 2.0 During Construction
checkpoint | 2.01 - Set out extents
note | Method/Description - Survey/visual
note | Test frequency - Prior to Commencement
note | Constructor - H
note | Verifying Records - Earthworks Cut Checklist dsr reports
checkpoint | 2.02 - Verify Machine Control
note | Method/Description - Survey/visual
note | Test frequency - Daily
note | Constructor - W
note | Verifying Records - Plant Pre Starts
checkpoint | 2.03 - Assess Crest detail
note | Method/Description - Hand augers/ slope assess
note | Test frequency - Prior to Excavation
note | Constructor - H
note | Designer - H
note | Verifying Records - Earthworks Cut Checklist dsr reports
signoff | HOLDPOINT
checkpoint | 2.04 - Install crest detail
note | Method/Description - Visual Inspection
note | Test frequency - Prior to cutting rock slope
note | Constructor - H
note | Designer - H
note | Verifying Records - Sub Contractor QA Records
signoff | HOLDPOINT
checkpoint | 2.04.1 - Install crest detail
note | Method/Description - Visual Inspection
note | Test frequency - Prior to cutting rock slope
note | Constructor - H
note | Designer - W
note | Verifying Records - Sub Contractor QA Records
checkpoint | 2.05 - Cut Face inspection
note | Method/Description - Survey check by construction team, visual inspection by designer.
note | Test frequency - 100m2 or maximum 5m vertical cut
note | Constructor - H
note | Verifying Records - Earthworks Cut Checklist, Survey record, As-built
signoff | HOLDPOINT
checkpoint | 2.06 - Cut Face inspection
note | Method/Description - Geo inspection and face mapping
note | Test frequency - At soil-rock interface, each Each 100m2 or maximum 5m vertical cut
note | Constructor - H
note | Designer - H
note | Verifying Records - Earthworks Cut Checklist dsr reports, And face map from geotechnical engineer/geologist
signoff | HOLDPOINT
checkpoint | 2.07 - Install Rock Drape
note | Method/Description - Geo walk over
note | Test frequency - Prior to drilling
note | Constructor - H
note | Designer - H
note | Verifying Records - Sub Contractor QA Records
signoff | HOLDPOINT
checkpoint | 2.08 - Install Rock Drape
note | Method/Description - Drill and grout records. Stressing records.
note | Test frequency - During construction and at end
note | Constructor - H
note | Designer - H
note | Verifying Records - Sub Contractor QA Records. Calibration certificates for stressing equipment.
signoff | HOLDPOINT
checkpoint | 2.09 - Install Rock Drape
note | Method/Description - Visual inspection
note | Test frequency - During construction and at end
note | Constructor - H
note | Designer - H
note | Verifying Records - Sub Contractor QA Records
signoff | HOLDPOINT
checkpoint | 2.1 - Install Rock Bolts
note | Method/Description - Drill and grout records. Stressing records.
note | Test frequency - During construction and at end
note | Constructor - H
note | Designer - H
note | Verifying Records - Sub Contractor QA Records. Calibration certificates for stressing equipment.
signoff | HOLDPOINT
checkpoint | 2.11 - Catch Ditch Inspection
note | Method/Description - Visual inspection
note | Test frequency - During construction and at end
note | Constructor - W
note | Designer - H
note | Verifying Records - EarthworksCut Checklist
signoff | HOLDPOINT
section | 3.0 Post Construction
checkpoint | 3.01 - Rock Fall Test
note | Method/Description - Visual inspection
note | Test frequency - After catch ditch is formed at each rock cutting site
note | Constructor - H
note | Designer - H
note | Verifying Records - Designer assessment Memo
signoff | HOLDPOINT
checkpoint | 3.02 - Survey As-builts
note | Method/Description - Survey As-built
note | Test frequency - During construction and at end
note | Constructor - H
note | Verifying Records - Digital file
checkpoint | 3.03 - Monitoring Data
note | Method/Description - Visual inspection and review of monitoring data review.
note | Test frequency - End of construction
note | Constructor - H
note | Designer - H
note | Verifying Records - Digital file
signoff | HOLDPOINT
checkpoint | 3.04 - Red Line Mark Ups
note | Method/Description - Red Pen Mark up
note | Test frequency - End of construction
note | Constructor - H
note | Designer - W
note | Verifying Records - Red Pen mark ups