## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned | a4820cfa-0138-4654-93a4-12ca64292415 |  | checklist | S - S - Electrical |  |  |  |  | Yes | Stage 3 - S - S - Electrical | 1ce978bd-a346-4ee5-afef-9c66584c2a4a
checkpoint-group | 7f9c41c9-472a-49a1-9c98-14a9859e6837 |  | section | First Fix
checkpoint-status | 09e32fbd-ca88-482b-acf9-f1f4d720473a |  | checkpoint | Handover Accepted/Nogs Installed and area clean and tidy before starting
checkpoint-status | 8d0b5050-9dd2-43e0-97bd-7037f7356410 |  | checkpoint | Check all drawings, plan symbols are identified and wired for, raise any anomalies
checkpoint-status | 09b7bd0f-1481-4465-8bbc-3b79d8566287 |  | checkpoint | Check wall and ceiling outlets and fitting positions against Architectural/ Electrical drawings and acceptable
checkpoint-status | 126c0715-cca4-4f1a-9e23-0c733037c7dc |  | checkpoint | Check for any purchaser variations/ client extras
checkpoint-status | bd463887-925e-4787-a0ea-c3add3464964 |  | checkpoint | Check all power & light feeds present and acceptable
checkpoint-status | 1d6ba7af-8139-4d1a-a152-b677672d51b1 |  | checkpoint | Check loop wires insatlled and acceptable
checkpoint-status | 5cb94df1-4377-4854-9152-802366fa5634 |  | checkpoint | All joinery plans are followed and correct position of outlets installed and acceptable
checkpoint-status | 23fbab7c-03f3-4931-a4dd-a8fc1d32c529 |  | checkpoint | Flush boxes straight and level and acceptable
checkpoint-status | 0e1dcbdf-912a-4308-a237-9c3ef1a486ea |  | checkpoint | Fire rated flush boxes where required + fire pads installed and acceptable
checkpoint-status | 3d500def-0c0e-4365-bc25-0e08e07b7b80 |  | checkpoint | Lights are marked out on plans or floor ready for cut out
checkpoint-status | 0250b49f-c9ac-4792-8d76-ef94ad1ecae9 |  | checkpoint | Electrical First Fix completed and acceptable and area clean and tidy for next trade
checkpoint-group | cf5edd31-c1c0-4e89-991c-253256a8f618 |  | section | Second Fix
checkpoint-status | 1b3c5a05-6425-4500-9824-f71b1416e78f |  | checkpoint | All cover plates in place & fitted correctly and striaght
checkpoint-status | 12fa2830-94a7-4ef8-834e-8c7b6820bd5f |  | checkpoint | All light fittings tight & secure and acceptable
checkpoint-status | dc62acba-eac8-4d75-8966-7df8464d11f3 |  | checkpoint | All cables are tied up
checkpoint-status | afd787d3-117a-4a08-8986-d8a2e39aa434 |  | checkpoint | Switch board fit off is completed and acceptable
checkpoint-status | 187e6a76-4114-4009-b954-c1aaca9034c4 |  | checkpoint | Test sheet for insulation Resistance are completed and acceptable
checkpoint-status | 942baea9-2586-4584-bfa9-e2237d8810f5 |  | checkpoint | Fixtures level & in place and acceptable
holdpoint | 418a1c54-1c1e-4866-a207-69a99ce845b6 |  | signoff | Request Signoff
checklist-flat | 64c200f6-7b9d-4fc8-8e82-7232506b8c03 |  | checklist | CST - S - Completion Documents |  |  |  |  | Yes | Stage 3 - CST - S - Completion Documents | 28aa6991-66ce-44be-87d5-7573960772e2
checkpoint-status | 5564d161-2575-4d07-a1d0-988c26157306 |  | checkpoint | All relevant Compliance Documentation completed and attached above
button | 4ed7342a-7958-5be2-9988-2b4c290b5fb2 |  | button | LBP Memorandum/ Record of works filled out, signed and attached | Yes,No
button | ffb00628-adf0-50e9-8da2-ae364aff2a57 |  | button | Any Additional Compliance Documentation - Completed and Attached | Yes,No
label | 08b01490-44ee-556d-9fb2-42074c9f01f9 |  | note | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint | e531888c-fa7b-45c8-8616-6d0fc9b6a671 |  | signoff | Request Signoff
checklist-flat | aea6c262-14d3-47f4-9a00-c7a6128f100f |  | checklist | Second Fix Electrical (V2) |  |  |  |  | Yes | QA - Second Fix Electrical (V2) | 304c9a2f-4667-4792-8ebf-d6fda5c69b3c
checkpoint-status | ec0862d4-3269-421b-8354-c70249802316 |  | checkpoint | Area is tidy and accessible
checkpoint-status | a12278a6-d080-4d7e-b344-546db78dd00c |  | checkpoint | substrate acceptable
checkpoint-status | da3d90e1-113e-4d12-bc60-be7042ccfd81 |  | checkpoint | Fire pads installed in fire walls
boolean | 06a66839-7f15-5dc4-ac9e-78071a549ff8 |  | tickbox | Photos attached
checkpoint-status | 7e9bf65a-0303-49e2-af83-25ede6358101 |  | checkpoint | Switches and sockets fit off
boolean | 77d4257a-bb90-5108-bfce-64ab0af51319 |  | tickbox | Photos attached
checkpoint-status | 241b5ca6-84ed-4059-859e-2e6ca26ad4f4 |  | checkpoint | Light fittings fit off
boolean | cbad3bee-5db5-57b1-8d3f-64b7ea2a394a |  | tickbox | Photos attached
checkpoint-status | d985be7d-2079-474c-a309-7f03ab5634c8 |  | checkpoint | Fixed appliances fitted
boolean | f21b6bad-7b4f-56a9-8282-b192db398d96 |  | tickbox | Photos attached
checkpoint-status | 10ad5e97-dad6-4439-9d29-76b8b85abe8f |  | checkpoint | All fittings level and secure
boolean | a8d5beb9-1f23-5330-bad2-a060161c0c0a |  | tickbox | Photos attached
checkpoint-status | c5be6e54-1953-46ac-bfa7-9a8d3a8eab80 |  | checkpoint | Mains installed from meter- switchboard
boolean | 8833164c-5c16-5c37-a402-6d1fddcdad78 |  | tickbox | Photos attached
checkpoint-status | ba716840-163b-41dd-a515-be16e4b3cb63 |  | checkpoint | All cover plates fitted
checkpoint-status | 474a6d6b-abe7-48f9-bb74-0c301a2a6a8c |  | checkpoint | Electrical testing completed
checkpoint-status | d9f62c94-4e5a-40a1-a57c-5b9555e49af7 |  | checkpoint | Inspection and metering completed
checkpoint-status | 399dbcf7-2afe-42dd-b287-8b0bcdc20121 |  | checkpoint | Certification complete
checkpoint-status | d7be3e49-bf0e-486d-8d62-fd0d4a05f071 |  | checkpoint | Unit clean and tidy
holdpoint | 38e82f21-1703-45dd-a685-4ba843ff0fbc |  | signoff | Request sign off
checklist-flat | 5e9c88d5-39e0-4d7d-8ce1-79e6cd252b64 |  | checklist | CST - S - Completion Documents |  |  |  |  | Yes | SYS - CST - S - Completion Documents (old version) | 53fcc485-d595-43a8-9ff3-1bc9061b08ca
checkpoint-status | 0ad58009-f10d-4077-be73-7109bc2b8ce3 |  | checkpoint | All relevant Compliance Documentation completed and attached above
button | f16a99bf-d21e-5906-b442-cc43692cb0d3 | DataPoint is missing 'button' values | button | LBP Memorandum/ Record of works filled out, signed and attached
button | 798420bf-474f-50f0-8d50-a4f42e29dd34 | DataPoint is missing 'button' values | button | Any Additional Compliance Documentation - Completed and Attached
label | 4d32ca3f-9f37-58fa-b374-01b1b14949c7 |  | note | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint | f01736c1-7137-4c1d-9305-3dc297044bec |  | signoff | Request Signoff
checklist-flat | 8fd8e222-5d83-49ab-a73f-536b9e84604a |  | checklist | S - S - Electrical - Cable Trays |  |  |  |  | Yes | S - S - Electrical - Cable Trays | 55392a2d-9de7-4aa6-aa2d-434eed13a9c3
checkpoint-status | f9d32f3c-8249-4bcc-9fd4-be460d886c2d |  | checkpoint | Tray ready to start
checkpoint-status | 66c3f373-e006-4b58-aba1-f74b5416746f |  | checkpoint | Building to correct Drawings (BIM model)
checkpoint-status | 96d62782-d055-4f3f-a2a0-174b1db88038 |  | checkpoint | Correct Tray / Basket size used
checkpoint-status | 3684c542-9a49-4e77-8705-6f5dcfeaab7d |  | checkpoint | Tray height correct of RL
checkpoint-status | 3985eeeb-322f-4c07-b35d-b3c6a9163f5c |  | checkpoint | Tray position as per BIM model measurements
checkpoint-status | a3498174-9fc3-4f1d-a8e5-e37c0fcb5582 |  | checkpoint | Tray level
checkpoint-status | a18fb3bc-406f-4310-9fcf-71bbb051b543 |  | checkpoint | Tray locked down
checklist-flat | e8da64e1-d949-4b3a-beaa-3e16db72374d |  | checklist | Second Fix Electrical |  |  |  |  | Yes | Second Fix Electrical | 6542769b-4d77-44bb-ada4-230a58341fc3
checkpoint-status | b128105e-9957-4ed8-a6a6-60242a6a1e95 |  | checkpoint | Area is tidy and accessible
checkpoint-status | 7f11ed10-b10c-4b02-ae8d-a4f93182b2b2 |  | checkpoint | substrate acceptable
checkpoint-status | 437ce38b-a031-49dd-a933-fb68399de3d4 |  | checkpoint | Fire pads installed in fire walls
label | 07fe61d9-7102-53f3-85ce-a41e14103df5 |  | note | Photos attached
checkpoint-status | b92414e1-d164-445f-bce1-35a280dc5b1a |  | checkpoint | Switches and sockets fit off
label | e216f45a-f185-5ae7-87ee-74f289e51b16 |  | note | Photos attached
checkpoint-status | 090dcea4-145f-4e45-84c0-8cc56b16bd6c |  | checkpoint | Light fittings fit off
label | 5c37783b-5519-5b58-b270-c0c0354e6929 |  | note | Photos attached
checkpoint-status | 042a22a3-e1d3-4e0d-ae4a-ec66e72d0b49 |  | checkpoint | Fixed appliances fitted
label | af7c4f23-cc28-557c-9c03-03421ae9c27e |  | note | Photos attached
checkpoint-status | 7cb8404e-eef2-4c09-a404-161b98138dba |  | checkpoint | All fittings level and secure
label | 7f7a152b-f807-50b6-82aa-e7d1f5ba3931 |  | note | Photos attached
checkpoint-status | 4ed0fc2c-61e5-47d4-8d4a-5927e201a40b |  | checkpoint | Mains installed from meter- switchboard
label | 2ce33433-215a-5797-a833-e5a21d0340bc |  | note | Photos attached
checkpoint-status | a5c926f5-cab3-4105-b01b-f7d905667da7 |  | checkpoint | All cover plates fitted
checkpoint-status | 7d182ee1-5d8b-4993-b980-71248fcce69a |  | checkpoint | Electrical testing completed
checkpoint-status | e65c2634-3f08-4172-8680-3c489a3cf31d |  | checkpoint | Inspection and metering completed
checkpoint-status | d84216a1-964c-4f02-8425-289802041cc4 |  | checkpoint | Certification complete
checkpoint-status | 21a4dd9d-c367-4b1b-bd51-54399ed050e0 |  | checkpoint | Unit clean and tidy
holdpoint | 497ee5b6-e7d6-4f2f-9f21-6b8a8398a3d7 |  | signoff | Request sign off
checklist-flat | 171e0e38-41c4-4bbf-b935-93be34cce71d |  | checklist | First Fix Electrical (V2) |  |  |  |  | Yes | QA - First Fix Electrical (V2) | 6adec58d-1e46-4554-b4bc-950b2d14bbc8
checkpoint-status | 4e9dde90-ac50-443a-a2de-f30608fd9097 |  | checkpoint | Area is tidy and accessible
checkpoint-status | 5d7310b7-7360-48cc-b5cf-67a0bafce2c1 |  | checkpoint | Check plan against architectural drawings (plans attached)
checkpoint-status | 06c00fbc-f641-48df-88fe-06a9b49c1dec |  | checkpoint | Check for any purchaser variations
checkpoint-status | 61ede21a-593d-4aa7-8a65-af110ee4840e |  | checkpoint | Flush boxes installed and correct
button | 57491ae9-ea24-5bd8-b1a7-a2faa08863e2 |  | button | Check flush boxes - all present | Yes, No, N/A
button | 8a091427-7ef2-5f47-87ed-9445e4d100cc |  | button | Check flush boxes - correct position | Yes, No, N/A
button | b2c19419-6d15-5b02-b210-ed46500f3c1e |  | button | Check flush boxes - Height and orientation | Yes, No, N/A
boolean | 4d3ebf0b-fd16-5006-bc63-17296129d7f0 |  | tickbox | Photos attached
checkpoint-status | 30f3568e-d5fa-4c9f-bbb7-48db4767e01a |  | checkpoint | Check fixing installed for fittings
boolean | 42dd10da-d20a-5865-abc8-253e83525ad2 |  | tickbox | Photos attached
checkpoint-status | 75224ebf-543d-437f-9d57-952a2fd1124d |  | checkpoint | All power feeds present and labelled
boolean | 4a3b3557-a336-5eee-964a-0632f49ad795 |  | tickbox | Photos attached
checkpoint-status | 89196a06-a5f1-4c2f-82c1-2923e33fda46 |  | checkpoint | Light feeds present and labelled
boolean | a3227dd2-4a05-53d7-9457-84023e335782 |  | tickbox | Photos attached
checkpoint-status | 175793af-61b1-4289-8fe9-c0623da12d6c |  | checkpoint | Loop wiring present and labelled
boolean | c5c1d49c-2ee1-59fb-b3bb-918e4fec84da |  | tickbox | Photos attached
checkpoint-status | 2f5c60b2-dc38-4b37-b899-a590fcd55792 |  | checkpoint | Lighting controls present and labelled
boolean | 3e19ca4f-655b-5ab0-b866-f4379813d933 |  | tickbox | Photos attached
checkpoint-status | c9c7cded-1a54-4bd8-bde9-508d0a9cf555 |  | checkpoint | Light positions recorded
boolean | 8bf346bf-40b9-5295-a533-88416a8b52a6 |  | tickbox | Photos attached
checkpoint-status | 2c592292-4e77-4b89-be58-79a71ef4f587 |  | checkpoint | Hot water cylinder is fit off
boolean | 043ea16b-6915-5e13-bd6a-c99160135868 |  | tickbox | Photos attached
checkpoint-status | 7297d30a-8627-4309-9da3-776661cb9062 |  | checkpoint | Extraction fans fit off
boolean | c0e50b25-9f0a-5e18-b462-e8382ddbbff9 |  | tickbox | Photos attached
checkpoint-status | 83a1e79e-0d89-489d-82a4-e4137430579c |  | checkpoint | Kitchen wiring is in place
boolean | 728cda73-0fd3-5040-bd2f-62c71b42bc5b |  | tickbox | Photos attached
checkpoint-status | 1f8890d2-be28-462e-b45a-6ceb7a4e4778 |  | checkpoint | Draw wire for underfloor heating
boolean | d0322678-3ac7-5170-bce4-6b62e1b11c62 |  | tickbox | Photos attached
checkpoint-status | 19813e81-5456-4afc-a5f8-4716bc9e25ee |  | checkpoint | Cables secured
boolean | 2d1fca60-0141-55f1-b8f1-d7c84f37e237 |  | tickbox | Photos attached
checkpoint-status | c49cee6f-d4b8-4b78-9340-80346542d1a4 |  | checkpoint | Exterior penetrations complete and sealed
boolean | 48654899-ecd3-593a-a65c-3ce45633c8c9 |  | tickbox | Photos attached
checkpoint-status | cf639c3f-8bd7-4d45-839c-a08c73580307 |  | checkpoint | Switchboard installed
button | 25221fe9-33f3-5fcd-854c-e12110a1d647 |  | button | Switchboard is fit off | Yes, No, N/A
boolean | 0b97532c-7a48-584a-980c-2740c2395fb1 |  | tickbox | Photos attached
checkpoint-status | 89f0b3f8-7b06-4668-afa0-956e70291a94 |  | checkpoint | Main earth and bonding run
boolean | ef123c5b-a180-5c7c-97cd-8b72cc2afda6 |  | tickbox | Photos attached
checkpoint-status | ce31fd0c-d946-4880-950f-ac0c20a63b67 |  | checkpoint | Earth electrode placed
boolean | 8441d8d7-2372-5f21-9903-a318eaed0142 |  | tickbox | Photos attached
checkpoint-status | 0290c582-536e-424f-a061-362010501b1d |  | checkpoint | Draw wire for supply mains
boolean | 868dd712-c0ce-55a7-af26-33cc107d8b36 |  | tickbox | Photos attached
checkpoint-status | 54d2c337-52a8-4044-8e33-90cf52e784d4 |  | checkpoint | Unit is clean and tidy
holdpoint | e8dbdede-c1ed-4dd3-adab-9cc5b8de6155 |  | signoff | Request sign off
checklist-flat | 0a3ec995-a028-4dba-a1f1-53726f7c829c |  | checklist | Distribution Board Checklist |  |  |  |  | Yes | Distribution Board Checklist | 6d764a12-103a-457d-af07-c89b0075a7d9
checkpoint-status | c508a454-a708-4baf-9de2-cfd2b734fda3 |  | checkpoint | DB details
text | 1042fe2f-c134-51fb-aa76-54d51501962c |  | textbox | Engineer
text | 77db2690-0d2f-5eae-a741-23e59bb77d99 |  | textbox | Test Instrument
text | 083e72f3-147a-5e82-958b-328b2044ede1 |  | textbox | Cable Size/Type
text | 1eb8e2ae-99ac-5563-bfba-4721a50100af |  | textbox | Main SW Size (A)
text | 9127f301-0320-543b-ae8f-7384f1392217 |  | textbox | Submain Insulation Resistance
select | 78e85201-e5e1-54d0-9562-118f715a96ea |  | dropdown | Polarity | pass, fail
text | d06f767d-a1b6-5fc7-a3b9-1772e7ca3457 |  | textbox | Main SW Voltage E-N (V)
text | 34cc659a-987d-5566-8027-0367ade8460d |  | textbox | Main SW Voltage R-E/N (V)
text | 3d966834-bbcf-5cb6-9261-ac16f6c9fa1a |  | textbox | Main SW Fault Loop Impedance (Z)
checkpoint-status | a10ef7da-1dd3-4a0a-820e-799a51a38dab |  | checkpoint | DB completed as per spec 100%
checklist-flat | 67caf2c9-881d-4aef-a24f-d1946bfefd9f |  | checklist | Compliance / Completion Documentation |  |  |  |  | Yes | Add Compliance / Completion Documentation | 722a5252-d161-4eff-8ba4-835f680408bc
checkpoint-status | 24abf986-b82a-46a0-a80b-0ca4ecca28dc |  | checkpoint | All relevant Compliance Documentation completed and attached below
button | 3e00b8d1-83f7-529e-ad6f-7c982cb384b7 |  | button | LBP Memorandum/ Record of works filled out, signed and attached | YES, N/A
button | daca4f07-8512-5073-a92d-82f211779c4c |  | button | COC / Electrical work certificates signed and attached | YES, N/A
button | 31fdb5ae-21bb-53e3-b7ed-b02ceac7ea66 |  | button | Any Additional Compliance Documentation - completed and attached | YES, N/A
label | 096bb8b3-90fa-5d56-a4c4-c80c1a49efe4 |  | note | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint | 5ea2ac07-8e39-49f4-b9cc-ae14509ec944 |  | signoff | Request Sign Off
checklist-flat | 4bf5f37e-2713-4ce9-b610-edf4d87ad2b9 |  | checklist | CST - S - Completion Documents |  |  |  |  | Yes | CST - S - Completion Documents | 93d11d29-3728-47ef-9f94-62246c45b531
checkpoint-status | 078f9538-9083-4c3c-8b79-fd4cef2eda4f |  | checkpoint | All relevant Compliance Documentation completed and attached above
boolean | ad7594df-1aef-57e4-8ed4-d2354ce561a1 |  | tickbox | Any Additional Compliance Documentation (Required under Section C and by Consultants) - Completed and Attached
label | 1ba14187-bfa6-54c9-b056-6042f50ab7ea |  | note | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint | e3b247d1-7777-44db-9dae-f06085d47dde |  | signoff | Request Signoff
checklist-flat | 799a7996-d5bc-4d51-86bc-d3cf8251181f |  | checklist | Cable Tray Checklist |  |  |  |  | Yes | Cable Tray Checklist | 9f6ad157-4c77-4829-9d59-8501c603b7ec
checkpoint-status | e2c22d39-5a32-4c9d-bb2b-544357580aca |  | checkpoint | Tray ready to start
checkpoint-status | 9f44c035-a87a-4255-b897-c55fd4e89900 |  | checkpoint | Building to correct Drawings (BIM model)
checkpoint-status | 29564124-efd2-47c5-810c-04fe78d45f39 |  | checkpoint | Correct Tray / Basket size used
checkpoint-status | ba8a9444-ec02-4846-b2cb-327299c0277b |  | checkpoint | Tray height correct of RL
checkpoint-status | ae8ae7de-c7e6-4950-a7c7-484694bcaf0a |  | checkpoint | Tray position as per Bim model measurements
checkpoint-status | 71cfaef6-421b-45be-8094-381a0523ff6b |  | checkpoint | Tray level
checkpoint-status | d1691016-a961-4524-8ac0-747c86bae344 |  | checkpoint | Tray locked down
checklist-flat | 77b3e8c9-b862-465b-a56f-6c1d9464a98a |  | checklist | Power Reticulation QA |  |  |  |  | Yes | Power Reticulation QA | a350ac17-fa50-4050-a4d3-b0533eff0306
checkpoint-status | cd0e9cb0-7931-4a7d-a8dd-0cf5048dbccd |  | checkpoint | Power Mains are installed
checkpoint-status | 8e2cb5ef-7e6a-425d-85dc-0b52dd2c4199 |  | checkpoint | Street Lighting installed
checkpoint-status | 4a1c4143-d554-4ebb-97a5-10133ea0c577 |  | checkpoint | Bollard Lighting installed
checkpoint-status | 2afa5549-7e75-4822-99a9-d65dd05ebbbb |  | checkpoint | Nurse Call Power installed
holdpoint | 89ff1e1e-d534-4c6e-ad87-e717ee6a255e |  | signoff | Request Sign Off
checklist-sectioned | e85fba74-8360-49ce-84eb-f913c0bb81cb |  | checklist | S - S - Electrical |  |  |  |  | Yes | S - S - Electrical | b014c553-7196-4bf6-bbe2-e3356413eef3
checkpoint-group | 7409e04a-7d13-4d04-a318-537bb595bb26 |  | section | First Fix
checkpoint-status | 930eec45-ad93-4739-b2a4-13ad9afd528c |  | checkpoint | Handover Accepted/Nogs Installed and area clean and tidy before starting
checkpoint-status | 7bbaafe5-15ba-4cde-8b49-b3507ea73c36 |  | checkpoint | Check all drawings, plan symbols are identified and wired for, raise any anomalies
checkpoint-status | b59e1db3-726c-448c-9f43-bc2080579795 |  | checkpoint | Check wall and ceiling outlets and fitting positions against Architectural/ Electrical drawings and acceptable
checkpoint-status | 08163af0-1f59-4793-bf23-f75864cde6ed |  | checkpoint | Check for any purchaser variations/ client extras
checkpoint-status | 1bb4fe0c-cb23-4307-bb13-1b4a515a2c69 |  | checkpoint | Check all power & light feeds present and acceptable
checkpoint-status | ee0e2376-3feb-4557-b0a4-d301bf3ef645 |  | checkpoint | Check loop wires installed and acceptable
checkpoint-status | 5fb55a85-e948-4d02-9ed5-c442903e507d |  | checkpoint | All joinery plans are followed and correct position of outlets installed and acceptable
checkpoint-status | 3e87194b-e9f4-44ec-9d17-300db8fb2466 |  | checkpoint | Flush boxes straight and level and acceptable
checkpoint-status | be4c5d72-4322-4e68-a5c5-816b0bafeb30 |  | checkpoint | Fire rated flush boxes where required + fire pads installed and acceptable
checkpoint-status | 49168509-8d37-40e4-afb4-fbc795e85e21 |  | checkpoint | Lights are marked out on plans or floor ready for cut out
checkpoint-status | 25d7bca8-b3d9-4142-a246-df022eb9c5b5 |  | checkpoint | Electrical First Fix completed and acceptable and area clean and tidy for next trade
checkpoint-group | 87f1a30b-afaa-423a-8dad-94c1e6a001da |  | section | Second Fix
checkpoint-status | af1975c2-404d-4690-8f09-4bf755e2b0d5 |  | checkpoint | All cover plates in place & fitted correctly and straight
checkpoint-status | c9982777-ad18-400a-828b-0726f88f387c |  | checkpoint | All light fittings tight & secure and acceptable
checkpoint-status | ed29e0a4-8c19-4193-a6f1-59aea59eada7 |  | checkpoint | All cables are tied up
checkpoint-status | 2368bbd2-6084-4931-b90f-49284dde4360 |  | checkpoint | Switch board fit off is completed and acceptable
checkpoint-status | f15d1dc6-9ae7-4ec0-95e6-391e2425f60c |  | checkpoint | Test sheet for insulation Resistance are completed and acceptable
checkpoint-status | 2a394839-a71d-4c32-8591-8910e4779e5b |  | checkpoint | Fixtures level & in place and acceptable
checklist-flat | bc23db9b-9e2f-49a3-8b74-4e716b6ab228 |  | checklist | First Fix Electrical |  |  |  |  | Yes | First Fix Electrical | c12e2943-060a-4f93-8159-333972b8e0ad
checkpoint-status | 1ece7d08-a01a-4c0f-b0e1-f627e73195a7 |  | checkpoint | Area is tidy and accessible
checkpoint-status | 44c7ad25-b755-42c0-8023-f99a11aa882d |  | checkpoint | Check plan against architectural drawings (plans attached)
checkpoint-status | 3e1d3c47-0a40-4721-9af0-bf8f030d43f1 |  | checkpoint | Check for any purchaser variations
checkpoint-status | 1b1192bc-bbac-4279-8a2d-e09c45caffd3 |  | checkpoint | Flush boxes installed and correct
boolean | 34df0733-46a8-581d-a878-ad6d4cd09c15 |  | tickbox | Check flush boxes - all present
boolean | ea9411e3-a9d6-5b3e-ab8d-05b3dde0b09b |  | tickbox | Check flush boxes - correct position
boolean | 6f6cc2d9-ff79-5782-9478-a91aaae810af |  | tickbox | Check flush boxes - Height and orientation
label | 91a8b7a0-881c-5abe-b366-aac5ca5be2ec |  | note | Photos attached
checkpoint-status | 5ae9e398-88ea-419a-9938-7e0b53cf2758 |  | checkpoint | Check fixing installed for fittings
label | 3c199e8c-2a8a-50c9-a747-63590c662b0d |  | note | Photos attached
checkpoint-status | d9a1267f-c8d1-49cd-bef3-304c042d08f2 |  | checkpoint | All power feeds present and labelled
label | 8e84dd5b-a527-504d-83ae-65ad8fef75aa |  | note | Photos attached
checkpoint-status | a387262c-7cbd-4598-a626-dd6940d2810b |  | checkpoint | Light feeds present and labelled
label | ec09b5b2-1b67-5087-86e1-7b71ac313ace |  | note | Photos attached
checkpoint-status | 30c7a2f8-de00-411a-b568-e9220972e91b |  | checkpoint | Loop wiring present and labelled
label | 6c8dad8c-2b83-575f-8fc8-15904de62dc5 |  | note | Photos attached
checkpoint-status | 9d3b635a-1f95-41c6-9f6f-d963dd9f8cc9 |  | checkpoint | Lighting controls present and labelled
label | 66721aa9-287b-57d3-a9b6-5c8fba8dca77 |  | note | Photos attached
checkpoint-status | 27014e67-7b10-484d-90ba-dfdfc9070027 |  | checkpoint | Light positions recorded
label | 6d7f673b-b612-5307-81ed-595a6403daa4 |  | note | Photos attached
checkpoint-status | 5c6c1ecf-3afe-4476-b275-6ac102047dd5 |  | checkpoint | Hot water cylinder is fit off
label | 6d4f8eec-a525-566d-afa4-26555c9cc120 |  | note | Photos attached
checkpoint-status | c7a99709-f2b0-4048-b8f4-ea5b2b9ce2af |  | checkpoint | Extraction fans fit off
label | af44053e-a487-553e-9e22-55d131c87d40 |  | note | Photos attached
checkpoint-status | 9a7fc776-7954-4420-9d34-8193d53a93c5 |  | checkpoint | Kitchen wiring is in place
label | 45a56d2d-d217-56da-9009-2eac03dc1ba9 |  | note | Photos attached
checkpoint-status | b0f89bf2-1068-4e9e-a8a5-7967773f8973 |  | checkpoint | Draw wire for underfloor heating
label | 0e6dc22c-aed6-5b7c-a4e6-d93293e27af3 |  | note | Photos attached
checkpoint-status | c4e5477f-747b-47e6-876f-3662b9297801 |  | checkpoint | Cables secured
label | 8970c145-3fc8-5921-81c5-a23a2f064e6f |  | note | Photos attached
checkpoint-status | 6a98dae7-e1e1-4b16-8f08-722ff49960fd |  | checkpoint | Exterior penetrations complete and sealed
label | fb30244e-7941-5eeb-a6a1-7a6f535c031f |  | note | Photos attached
checkpoint-status | 464d0482-d408-488f-9610-3665f9f7802c |  | checkpoint | Switchboard installed
boolean | a5cc21ef-2ce8-5f25-b051-96ca451e7f28 |  | tickbox | Switchboard is fit off
label | 75816f17-d139-5de5-9bf5-cea7b7b06b6e |  | note | Photos attached
checkpoint-status | 91a93e3a-d3c0-482b-a35c-a2b1f8a596da |  | checkpoint | Main earth and bonding run
label | 0b62f7fa-05d4-574a-9ce3-6daf4ba4be74 |  | note | Photos attached
checkpoint-status | 84ad8ab4-95a9-4183-a51b-ff2a060d455e |  | checkpoint | Earth electrode placed
label | 167bc36e-34b0-53f8-9026-a192c941659d |  | note | Photos attached
checkpoint-status | fbe36fb9-53e0-4e55-81d8-c615e02ea9dd |  | checkpoint | Draw wire for supply mains
label | af69445d-7724-58b1-8ec2-b388d7607fe0 |  | note | Photos attached
checkpoint-status | ae071982-2b9c-4e0f-aa48-6fa02cc08dbd |  | checkpoint | Unit is clean and tidy
holdpoint | e708546c-f94f-477d-9b40-a525df26c1e7 |  | signoff | Request sign off
checklist-flat | f024b5b0-efe4-4c47-8714-527736782255 |  | checklist | S - S - Electrical - Distribution Boards |  |  |  |  | Yes | S - S - Electrical - Distribution Boards | fc42005b-f5dd-4e2b-be6e-f55bbc2c1fb7
checkpoint-status | ab70cee0-ed56-458b-9cb2-85b6ac5ac1c9 |  | checkpoint | DB details
text | e4b10342-12dc-5395-9d31-1bb7161cbdd4 |  | textbox | Engineer
text | d9d2a12e-5cf2-5242-90aa-43c7ad0453e2 |  | textbox | Test Instrument
text | 96b5f2e8-cbb4-547b-83b9-450c3687de92 |  | textbox | Cable Size/Type
text | 237662f7-64b9-5c6e-93bc-e5ee6709b1fa |  | textbox | Main SW Size (A)
text | 2c22e601-d266-5cab-b019-92fa75e3d5e3 |  | textbox | Sub Main Insulation Resistance
select | aba5e7de-e1d3-5d3c-b1a0-ca782e2674ce | DataPoint is missing 'select' values | dropdown | Polarity
text | 915e5fa3-9052-5406-ae69-88e93d07cd1c |  | textbox | Main SW Voltage E-N (V)
text | 2e8aeb55-26ef-558d-b883-1bcd22a5f963 |  | textbox | Main SW Voltage R-E/N (V)
text | bc1c0027-0280-5217-bd7b-dba1d127751f |  | textbox | Main Sw Fault Loop Impedance (Z)
checkpoint-status | 48f3d865-e68e-4bc3-8130-a023d2b31f75 |  | checkpoint | DB completed as per spec 100%