## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned | 23d077e4-7271-4988-bef3-4d7c277d0f8a |  | checklist | Concrete Pour for Area: |  |  |  |  | Yes | SYS - QA - Concrete Pour Checklist (old version) | f660194d-048b-4cc3-acb2-825a643ad53f
checkpoint-group | df4cade4-644d-4cb6-9752-f71d7f156859 |  | section | Pour Details
checkpoint-status | 9b8a82b3-6f1d-4c1e-ae02-4d47b9a834a9 |  | checkpoint | Pour details entered
text | 228a87c2-c4fc-528b-b148-3367e32e6a9a |  | textbox | Area to be poured (grid lines, location):
text | 5278331b-f876-56b0-85a3-4f9d2523931f |  | textbox | Drawing numbers and revisions
text | 19ca0f3c-08f4-567f-b8cd-17309dbb4f9d |  | textbox | Date of pour
checkpoint-group | 246a43ae-7357-488f-a2e4-463daca0f66f |  | section | Formwork and embedded items
checkpoint-status | 34ed4b21-b2be-4ac1-b184-3ac4e79ba423 |  | checkpoint | Grids and RLs clearly marked for reference
checkpoint-status | 61905e2c-0473-4694-ac3c-7558a936315a |  | checkpoint | Formwork - location, heights, falls and dimensions checked and accurate
checkpoint-status | ef39c091-3f3e-4ef7-849f-41b7a5b5d180 |  | checkpoint | Formwork sufficiently fixed and braced
checkpoint-status | 0a49f692-f700-4c0d-a47a-c55573db8a61 |  | checkpoint | Any rebates / nibs / cast in items are correctly positioned, sized and appropriately fixed in place.
boolean | a9d46929-2553-504b-89ee-ea45651168f6 |  | tickbox | Hold down bolts checked and correct
boolean | c4b20aca-f494-507f-96cc-5b8fc468a3a6 |  | tickbox | Precast panel starters checked and correct
checkpoint-status | fcd662d3-12a4-4337-8051-fe61a08d853d |  | checkpoint | Service penetrations formed correctly and locations checked/correct
checkpoint-status | efc13c0b-7170-48ab-b46f-9ff59f5dcae7 |  | checkpoint | All surfaces correctly prepared (e.g. joints to existing concrete, release agent to formwork, etc.)
checkpoint-status | 5624e7c6-9103-472f-b8fc-18ee5b10f73d |  | checkpoint | Any control joints / stop ends installed accurately and correctly braced
checkpoint-status | 83af4a1a-d94b-4c9b-a120-cd29f7977336 |  | checkpoint | DPM & Connection to other waterproofing completed
checkpoint-status | bd517ae6-a1dc-40bd-95dc-35e34f907ed0 |  | checkpoint | Any additional formwork photos and observations
checkpoint-status | 32b2f5e8-6222-4cb5-90cd-dbbc8498d23a |  | checkpoint | All formwork elements completed and ready for concrete pour (excess debris removed)
checkpoint-status | cacb6b94-fb04-4c99-a20b-578889895330 |  | checkpoint | Concrete ordered - correct mix and strength
text | c3b1317d-0675-5bdc-aa34-9d48fe0a420b |  | textbox | Mix
text | 90d654b6-13b4-542d-aef5-d614ff03b318 |  | textbox | Strength:
text | 1af2a3c5-1784-5877-8dce-7411582b80f8 |  | textbox | Summary of Proposed cement mix date and revision checked:
text | ba0a9a35-7c96-53b5-a723-22111870db39 |  | textbox | Structrual services specifications number and revision checked:
checkpoint-status | f8c51566-8dc7-4f6c-a029-fcf6e0c52929 |  | checkpoint | Slump test/Spread test (only applicable for special mix)
checkpoint-group | 3bb14464-1db2-4ff6-8e62-82bd7b3c9872 |  | section | Placement Method
checkpoint-status | df416dea-2706-4be6-a677-f6ac6161bf3d |  | checkpoint | Placement methodology confirmed and necessary plant and equipment on site
text | 0728475c-9ce0-509e-82b8-999e2610e96d |  | textbox | Who is placing the concrete
checkpoint-status | 3588b4ef-300f-4e91-a241-5ceaac8a2b8a |  | checkpoint | Height and falls checked / confirmed before placement
checkpoint-status | 729f57b3-0f92-4754-b3dd-afc38289e172 |  | checkpoint | Cover correct to specification
checkpoint-status | 9e29c331-0aff-4152-a158-39d82f97d5b9 |  | checkpoint | All concrete checked and correct on arrival (mix and strength)
boolean | 5e74aef3-cfbc-5431-a8c3-4326f5b12008 |  | tickbox | All concrete dockets attached
checkpoint-status | a578d2f7-5cd7-49bd-ab9b-1c61e2813b57 |  | checkpoint | General photos and observations of concrete placement attached
checkpoint-status | 5d9b8c07-01a8-4125-ae26-3de5809c5699 |  | checkpoint | Heights and falls checked / confirmed after placement
checkpoint-status | 88e5e337-c4c0-445e-9b65-faeeae31d236 |  | checkpoint | Any curing compound applied correctly
checkpoint-status | f350ca97-55f7-4e54-8748-8eba97a339a5 |  | checkpoint | Concrete placement completed - specified level of finish achieved
checkpoint-status | 4e41cbd5-2a55-4329-8247-aa41b525a966 |  | checkpoint | Area left clean and tidy
checkpoint-group | 3747f9de-59e4-4013-9c1c-801413e24739 |  | section | Post Pour Checks / Signoff
checkpoint-status | 0ea2d8e3-fe67-4139-9306-2f8289155a15 |  | checkpoint | Any remedial work completed
checkpoint-status | 8dda0684-8f10-4073-8d0c-f2436754203a |  | checkpoint | Concrete Pour completed - all final checks and documentation completed and attached
checkpoint-status | 42a0ba64-df64-4a58-b333-444359a90c29 |  | checkpoint | Report sent through to client
checklist-flat | a841648e-e155-4245-ae76-575fcac4ad1f |  | checklist | QA - Base Set Out Checklist |  |  |  |  | Yes | QA - Base Set Out Checklist | f676fe1a-e1b3-4bb2-aff5-fe04a1de5678
checkpoint-status | 2a789262-deb8-4ee6-ab14-acb3f2173991 |  | checkpoint | All relevant drawings and revision numbers checked and attached/commented
checkpoint-status | 144d20c0-ec31-4140-a31d-56a99473f698 |  | checkpoint | Set out points and Datum to be established by surveyor
checkpoint-status | b41edaf8-208b-4878-bb5e-c5f9fd1d5781 |  | checkpoint | Obtain written confirmation from surveyor
checkpoint-status | fd0bb3a2-9a83-4ee5-a8e9-7eba95fbc3ab |  | checkpoint | Send Report to client