## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | 67acd195-2dba-4427-b78a-383e27cfea41 |  | checklist | Stairs |  |  |  |  | Yes | Stairs | 08ad467b-b40d-4388-87bc-5980f71e24b3
checkpoint-status | 095ac068-7946-4223-8883-b8e190f8a8cb |  | checkpoint | Area Ready for TK Works
checkpoint-status | a6f46546-72a4-499d-a2bc-1b42e139a1cd |  | checkpoint | 15mm Ply Installed to Steel Frame
checkpoint-status | d4e1d3a6-b914-4b62-8340-731e6c71e299 |  | checkpoint | Plywood Secure and Defect Free
checklist-flat | 9298b79a-275b-45c9-b0aa-881d839d52a0 |  | checklist | Bumper Rails |  |  |  |  | Yes | Bumper Rails | 1379dd83-2d2f-461a-bad0-941289ecbc56
checkpoint-status | abc4d53b-0b9f-461b-9bfb-459cb2849f2f |  | checkpoint | Ensure Noggins In all Walls
checkpoint-status | 8e1fd9c0-1f6a-4424-807a-7523ed6f44c5 |  | checkpoint | Bumper Rail Fixed Securely
checkpoint-status | 5efda03c-9399-4d43-8453-eded3bfd3a2f |  | checkpoint | Bumper Rail installed - Damage Free
checkpoint-status | e523ce42-2f92-4437-9340-dfd96d783b6a |  | checkpoint | Protection Installed (If Applicable)
checklist-flat | fe58c9e1-e675-45ab-92b4-6a12455cbde4 |  | checklist | Ply Catwalk T250 |  |  |  |  | Yes | Ply Catwalk T250 | 1790871b-7bde-4399-b755-b49220c71e7f
checkpoint-status | eaf9a660-3826-4319-a2a6-70387391fda2 |  | checkpoint | Area Ready for TK Works
checkpoint-status | 12c84d83-e39a-4440-95c7-42b503447431 |  | checkpoint | Packing applied where necessary
checkpoint-status | 5b733eaf-2581-4d49-95ad-ead0f36761fa |  | checkpoint | T250 Plywood Installed and secured
checkpoint-status | f99fa809-ccac-451d-8e6a-6c21c55282ac |  | checkpoint | Area complete - Defect Free
checklist-flat | 71671191-ee63-4877-934a-4d58e8cb8083 |  | checklist | Meeting Room Door ITP |  |  |  |  | Yes | Meeting Room Door ITP | 30d3fdc7-9f3e-4f08-ad94-4c24f1746213
checkpoint-status | 9f4d6afe-b041-4f4e-9da4-9b778002e96c |  | checkpoint | Works Installed free of defect & damage
checkpoint-status | 57966886-9990-4b55-83b8-e6c848b36bef |  | checkpoint | Joinery supplied and installed as per signed off shop drawing.
checkpoint-status | a833adc0-7095-41ba-b2b1-5476b8d9ac15 |  | checkpoint | All fixing Screws capped
checkpoint-status | 365d8711-ec11-4ade-b0bf-d45c4942b61c |  | checkpoint | Joinery Protection Installed
checkpoint-status | 7bd5e604-3412-4078-af5d-f56b7d8629bf |  | checkpoint | Joinery installed as per mark-up
checkpoint-status | 91826c53-a799-462a-99f3-3f6adddcbe36 |  | checkpoint | Installed with consistent margins
checklist-sectioned | 903e8055-afd5-4e8a-a453-ff1799c040c3 |  | checklist | Doors & Frames |  |  |  |  | Yes | Doors & Frames | 3e298c87-bf34-463f-ac1b-df6dcba36118
checkpoint-group | 51bd6846-9071-46fd-9185-9a64b47614a6 |  | section | Frames
checkpoint-status | 178ad10a-d936-4a67-8ad2-4ab0f340685c |  | checkpoint | Frame Installed Level and Securely. (If Applicable)
checkpoint-status | 5f18602f-ccba-48ca-8ef2-5ee6e81a14db |  | checkpoint | Frame Installed Damage Free (If Applicable) (photo)
checkpoint-status | 4126c8a3-f519-411c-b522-b6650c1ffecd |  | checkpoint | Framing Caulked and Filled (If Applicable)
checkpoint-group | 699268df-022c-4087-a2a2-9d7b50d8d7e7 |  | section | Doors
checkpoint-status | da45375a-7062-4270-a7d0-e65b5e39f339 |  | checkpoint | Door Installed with Correct Margins
checkpoint-status | 0b9da016-6dd2-4a14-be26-292d1cf6e240 |  | checkpoint | Door Installed with Correct Hardware and Operating.
checkpoint-status | 037cb3b4-2aa6-4591-96ce-106b5824c847 |  | checkpoint | All Hinge Screws Installed
checkpoint-status | 560e3ea1-b72b-4653-91fd-9090e26a4b5a |  | checkpoint | Door Installed Damage Free (photo)
checkpoint-group | 3dd94d5d-db5e-4326-a47f-1e8e90baa5d3 |  | section | Hardware
checkpoint-status | 95c6dd4a-5703-4165-85a4-9f3095feadf0 |  | checkpoint | Face Plate Fitted Square
checkpoint-status | 7da443cb-98ac-4fb2-9c06-fdd80e5c1bed |  | checkpoint | Escutcheons Installed
checkpoint-status | 5bbef305-aae4-43ba-a60a-e4f4604b3b9c |  | checkpoint | Lock Fitted As Required
checkpoint-status | 86321a4a-d740-423b-b7fe-11aed157d76f |  | checkpoint | Closer Speed Checked
checkpoint-status | fa94d6f2-2fa1-47c5-a186-3d9136eb3175 |  | checkpoint | Door Latches Into Frame
checkpoint-status | 4c2d4e75-0f3c-464c-9911-9052253a3d13 |  | checkpoint | Batwing Seal Installed
checkpoint-status | 44198431-2fdf-4349-b163-de0f19e0380b |  | checkpoint | 3mm Margin or Under to All Uprights and Across the Head
checkpoint-status | f9cd3257-5b3e-490f-a817-e70e237037b6 |  | checkpoint | Margin to Underside of the FR Door within 6-10mm
checkpoint-status | c05c6596-186b-42a4-b968-b356f24dd263 |  | checkpoint | Meeting Stiles Even & Neat (If Applicable)
checkpoint-status | b1468858-e4a2-4839-99d6-214e949271da |  | checkpoint | Fire Tag Installed
checkpoint-status | 68713dc9-7bd4-45a0-8645-9211462b6df6 |  | checkpoint | Top and Bottom Edge of Door Painted
checklist-flat | fe965616-0611-4df5-8717-837a6a59f7b5 |  | checklist | Sprung Floor |  |  |  |  | Yes | Sprung Floor | 41763e84-d857-4a9a-b502-4f024bdc0b0b
checkpoint-status | 52451584-28f5-4f9c-8c36-df1f28a208a7 |  | checkpoint | Area Ready for Top Knot to Start Works
checkpoint-status | 949755a8-3a78-40eb-bc81-ac630cf9d8ae |  | checkpoint | Ensure Substrate is level within Tolerance
checkpoint-status | 2ed96608-996f-4be5-a837-10327e331f8f |  | checkpoint | Timber Frame Installed - Both Layers of Ply
checkpoint-status | 1bae2fea-a98f-40dc-8093-e053f09aa02a |  | checkpoint | Sprung Floor Installed
checkpoint-status | f08f8a74-d071-41ff-a1e1-43048b8a7fd3 |  | checkpoint | Masonite Underlay Installed
checklist-flat | 18bfcd20-9d6d-4dbc-a1aa-1e1cb36547ad |  | checklist | FTM01 Flooring |  |  |  |  | Yes | FTM01 Flooring | 7a82ad4c-060e-4cc6-9fa0-f97da566a94a
checkpoint-status | f91d95bf-3784-44cc-987a-4406b40cb382 |  | checkpoint | Area Ready for TK Works
checkpoint-status | 38020108-c38a-4a74-93fe-bfbda6b403b7 |  | checkpoint | Ply Substrate Installed and Secured
checkpoint-status | 56e58bf1-d36d-4a73-a264-ec3eeccb1060 |  | checkpoint | Substrate Protection Installed (Variation)
checkpoint-status | 141bd30f-a627-4848-8737-0784453740b3 |  | checkpoint | Tiered Seating Framing Installed (If Applicable)
checkpoint-status | 52bf9714-28d6-490b-ad81-054ff5c2102a |  | checkpoint | FTM01 Flooring installation (Dual Bond)
checkpoint-status | 268c0e6e-66a5-4048-bc2b-eca411ba7651 |  | checkpoint | Risers Installed (If Applicable)
checkpoint-status | f02ace11-41c7-45fa-8d24-52a7a3f80e40 |  | checkpoint | Protection applied
checkpoint-status | 597f9190-b137-4d48-aed0-a51916a65cf8 |  | checkpoint | Area Complete - Defect Free
checklist-flat | 965b4f37-eaee-4bc6-914f-fe5f3ca89abe |  | checklist | Structural ply |  |  |  |  | Yes | Structural ply | 7ede4708-6bfb-42c4-a94f-1d544e2fe5e4
checkpoint-status | 30228b81-e5ff-49a3-83cf-a682992dafe8 |  | checkpoint | Surface ready/Clear for install
checkpoint-status | ceeec14f-51be-4ba3-895b-e52dcdb9cbc0 |  | checkpoint | ply installed plumb/level
checkpoint-status | 871caa97-5b52-438c-88c5-2c9eb46f7210 |  | checkpoint | Ply Installed as per manufacturers specifications
checkpoint-status | c1ace7e7-f1e5-48ed-b0ee-2cb14c6ffd67 |  | checkpoint | ply fixed as per applicable Australian standards.
checklist-sectioned | 72402f6c-a69b-4793-a513-9fd929ed5f36 |  | checklist | Sanitary Hardware |  |  |  |  | Yes | Sanitary Hardware | 94c85de8-3844-4415-a736-e59dd7796dca
checkpoint-group | f4d16873-bf13-482a-a0bc-aeb51eccec08 |  | section | Nogs
checkpoint-status | 14c4075e-c9b2-4d1c-b9dc-989c3ae0f8aa |  | checkpoint | Wall Framing Complete
checkpoint-status | 81b5de9e-77bc-4a97-8f6b-a62ecfbb41d0 |  | checkpoint | Wall Framing Fixed of Secure
checkpoint-status | ac6dc478-a8a0-4410-afb2-01f4e1b87711 |  | checkpoint | Noggins Marked Out by Top Knot
checkpoint-status | a70993cc-dfa0-4d21-9ae2-bbd7d7ac0315 |  | checkpoint | Noggins Installed by Others.
checkpoint-group | 1dc55813-474e-4b9e-b8d0-cf0401ea4d44 |  | section | Hardware
checkpoint-status | 9196984b-140c-431e-af96-43d2e60cba8d |  | checkpoint | Installed as per Latest Elevations
checkpoint-status | 373cd5ad-1524-40de-984a-efbbce0e372a |  | checkpoint | Installed and Fixed off Securely
checklist-flat | 74ba8ec1-7762-4b93-8c5b-3e6112513a08 |  | checklist | Ramp |  |  |  |  | Yes | Ramp | 9867c16a-f283-4a2d-ada7-26e400ca7609
checkpoint-status | c7c97b13-544c-476b-8d2a-43ec696b362c |  | checkpoint | Area Ready for TK Works
checkpoint-status | 480e5e11-b22d-4f00-8603-fdba31b85fad |  | checkpoint | Timber Frame Installed
checkpoint-status | d01ad5a9-37cb-486d-86a5-49b714c5f7b0 |  | checkpoint | Ply Substrate Installed and Secured
checkpoint-status | 614f5035-2c7d-4d0b-b5b5-d237ca8300f9 |  | checkpoint | Area complete - Defect Free
checklist-flat | 797b2e6d-0748-4ffd-8fe8-791d83e3ba8a |  | checklist | Structural Frame |  |  |  |  | Yes | Structural Frame | f965a06e-58a1-457e-ac0a-fe37d6795a17
checkpoint-status | 2871467f-dbbf-471b-906d-d75778e91d9e |  | checkpoint | Area is clean ready for install
checkpoint-status | 86b172bd-fdda-4d7e-ab92-18dcbfceb666 |  | checkpoint | Framing is plumb and Level , ready to review floor / wall finishes
checkpoint-status | e5c36c6c-8906-457f-bb92-9d69576b3fb8 |  | checkpoint | Framing is Installed as per AS requirements
checkpoint-status | 02fcd59c-164b-4731-8df6-ca90a16fe15a |  | checkpoint | Framing reflects , shop drawings , engineering reports.