## ITP Cover Page
Combined Remaining Items Inspection and Test Plan
Project: SH1/29 Intersection Upgrade
Number and Revision: - 105 - Rev A
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | SH1/29 Intersection Upgrade |  |  |  |  | ITP Number: |  |  | 105
Project Number: | [7 empty] | ITP Status: |  |  | Draft For Approval
ITP Description: |  |  | Combined Remaining Items Inspection and Test Plan |  |  |  |  | Revision: | 1000 |  | A
Contract Number: |  |  | 7991 |  |  |  |  | Drawing Sets:
Customer: |  |  | Waka Kotahi |  |  |  |  | Specification:
Quality Specified: |  |  | Z8
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
A | Draft for Approval | 2023-12-18 |  | Stuart McCarron |  | Combined Remaining Items Inspection and Test Plan |  |  |  | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
[10 empty] | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
[10 empty] | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – Master ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM | [7 empty] | Downer PM
Downer QM | [7 empty] | Downer QM
Client (If Applicable) | [7 empty] | Client (If Applicable)

## ITP Body
Combined Remaining Items Inspection and Test Plan
Project: SH1/29 Intersection Upgrade
Number and Revision: - 105 - Rev A
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Testing Quantity Required | Verification Activity |  | Downer Conformance of Compliance Signoff
[7 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details | ENGINEERS COMMENTS - Date: | DOWNER RESPONSE - Date:
SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
3.01 | General
3.01.01 | Precondition Surveys | A precondition survey of Waka Kotahi and other public / private assets within the extent of the Site and immediately beyond the outside area of the construction activities shall be undertaken in conjunction with the Engineer prior to the Contractor taking possession of the Site. | PS 2.13 | Precondition Survey | Prior to the Contractor taking possession of the Site. |  | H | PM
SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
4.34 | Traffic Service Materials
| Safe Lane Delineator Concrete | Unless otherwise stated, concrete shall have a minimum compressive strength of 20 MPa at 28 days. | PS 23.7 | Datasheet / Mix Design | Prior to use |  | R | SE
| Guard Rail Concrete | Unless otherwise stated, concrete shall have a minimum compressive strength of 20 MPa at 28 days. | PS 23.6 M23 | Datasheet / Mix Design | Prior to use |  | R | SE
| Proposed Guard Rails | The Contractor shall submit details of proposed proprietary materials and systems. | PS 23.6 M23 | Datasheets | Prior to material order (4 weeks prior to installation) |  | HP | ENG
| Guard Rail Maintenance Instructions | The Contractor shall submit details of the manufacturers maintenance instructions for the type of barrier installed. | PS 23.6 M23 | Maintenance Instructions | Upon completion of the Guardrail Construction |  | HP | ENG
| Coloured Surfacing | The contractor shall provide evidence to the Engineer before preparation and marking of the surfacing, that the material conforms in its entirety to the requirements of NZTA P33. | PS 23.4 | Datasheets | Prior to use |  | R | SE
4.35 | Sign Materials
| Retro-reflective sheeting | All retro-reflective sheeting must be approved for use in New Zealand and comply with the following requirements of NZTA P24 Specification for Permanent Traffic Signs and AS/NZS 1906.1: 1993 Retro-reflective Materials and Devices for Road Traffic Control Purposes, Part 1 Retroreflective Sheeting. | PS 23.2.6 | Datasheet | Prior to use |  | R | SE
| Anti-Graffiti Coating | Graffiti protective coating shall be applied to all ground mounted sign and shall be approved for such use by the reflective sheeting manufacturer and shall maintain all guarantees for the sign. | PS 23.2.14 | Datasheet | Prior to use |  | R | SE
| Dew Effect Coating | All overhead mounted signs, except for bridge name plates, shall be manufactured with an overlay that is designed to prevent dew droplets forming to overcome the phenomenon known as ‘dew effect’. | PS 23.2.15 | Datasheet | Prior to use |  | R | SE
| Sign Shop Drawings | The supplier shall prepare shop drawings detailing the panel layout, positions of channel framing, and assembly systems prior to the manufacture of any sign. The shop drawings shall be submitted for review and comment at least ten working days prior to manufacture of the sign. | PS 23.2.6 | Shop Drawings | At least ten working days prior to manufacture of the sign. |  | R | SE
| Timber Posts | Timber posts shall not exceed 100mm x 100mm section size. They shall be Building Grade or Number 1 Framing grade timber as specified in NZS 3631, dried to 20-24% moisture content, and treated in accordance with the New Zealand Timber Preservation Council’s requirements as specified in NZS 3640 for Hazard Class H4. The timber finish may be gauged or dressed. The timber posts shall be primed and finished with white high gloss paint over the length above ground level. | PS 23.2.19 | Datasheet | Prior to use |  | R | SE
| Steel Posts | Steel posts shall be of an approved frangible design. They shall be hot-dip galvanised and finished with white high gloss paint. The paint system shall be specified and applied in accordance with AS/NZS 2312.1. All poles shall be fitted with white PVC caps. | PS 23.2.20 | Datasheet | Prior to use |  | R | SE
| Aluminium Poles | Aluminium poles shall conform to Alloy 6261 T5 as required in NZTA P24. All poles shall be fitted with white PVC caps. | PS 23.2.21 | Datasheet | Prior to use |  | R | SE
| Impact Resistant System Posts | Aluminium poles shall conform to Alloy 6261 T5 as required in NZTA P24. All poles shall be fitted with white PVC caps. | PS 23.2.22 | Datasheet | Prior to use |  | R | SE
| Sign Fixings | All signs shall be installed using approved sign support channel bracket fittings that do not penetrate the front face of the sign. No bolts, rivets or other fixings shall penetrate the front face of the sign. | PS 23.2.23 | Datasheet | Prior to use |  | R | SE
| Training | The installer shall demonstrate prior to undertaking the works that its staff has attended, or are scheduled to attend, a recognised training course in the handling, installation, and maintenance of retro-reflective road signs. | PS 23.2.25 | Training Records | Prior to Installation |  | R | SE
4.36 | Long-life Road Markings Materials
| Applicator Approval | The applicator(s) used for the contract works must be certified to NZTA/NZRF T/12. No installation shall commence without the written approval of the Engineer accepting the certification and suitability of the applicator(s) proposed. | PS 23.5.2 | Engineers Approval | Prior to Installation |  | HP | ENG
| Long-life Road Markings Materials, Marking System and Format | Only products approved to NZTA specifications are to be used. The Contractor must submit to the Engineer details of each of the products that will be used in the contract works. The submission must include: | PS 23.5.3 | Engineers Approval | Prior to Installation |  | HP | ENG
| Installation Limitations | The Contractor shall supply the Engineer with the Supplier Specifications or Instructions on Installation for the long-life road marking system proposed to be used. No installation shall commence without the written approval of the Engineer accepting the suitability of the long-life road marking system proposed. | PS 23.5.4 | Engineers Approval | Prior to Installation |  | HP | ENG
| Glass beads | The Contractor shall ensure that glass beads have appropriate adhesive coatings for the long-life road marking product being used. No installation shall commence without the written approval of the Engineer accepting the suitability of the glass beads proposed. | PS 23.5.5 | Engineers Approval | Prior to Installation |  | HP | ENG
| Raised Pavement Markers | All raised pavement markers shall be in accordance with TNZ M/12 Raised Pavement Markers. | PS 23.5.6 | Datasheets | Prior to Installation |  | R | SE
| Application Crew | The Contractor is to notify the Engineer of any proposed changes to the crew. The Contractor shall provide a CV outlining their qualifications, skills and experience related to installation of long-life road marking systems. No installation shall commence without the written approval of the Engineer accepting the suitability of the nominated crew or any changes proposed. | PS 23.5.7 | Engineers Approval | Prior to Installation |  | HP | ENG
4.37 | Pavement Marking Materials
| High performance markings | All road marking installed is to be high performance textured pavement markings in accordance with NZTA P30 High Performance Road markings unless otherwise specified. The Contractor shall nominate the brand, type and proposed application methods for materials to be used. This information shall be provided for approval prior to application. | PS 23.3.1 | Datasheets | Prior to Installation |  | HP | ENG
| Glass beads | All glass beads added to the paint for reflectorised line application shall be in accordance with AS/NZS 2009 Glass Beads for Road-Marking Materials and the current NZTA Policy and Testing Regime for Heavy Metals (T17). | PS 23.3.1 | Datasheets | Prior to Installation |  | R | SE
| Raised Pavement Markers | All raised pavement markers shall be in accordance with TNZ M/12 Raised Pavement Markers. | PS 23.3.1 | Datasheets | Prior to Installation |  | R | SE
| Edge Marker Posts: | Edge Marker posts shall be non-wood and shall comply with NZTA M14. Non-wood posts shall have current NZTA M14 type approval. | PS 23.3.1 | Datasheets | Prior to Installation |  | R | SE
4.38 | Fencing Materials
| Post and Wire Fencing Materials | All in ground timber posts shall be treated to H4 standard and all other timber shall be treated to H3 standard. All posts to be sunk to the required depth and supported to form a rigid boundary fence. | PS 25.12.2 | Datasheet / Docket | Prior to Installation
4.39 | Landscaping Material Supply
| Plant Supply | All plants shall be supplied true to the species and grades specified on the approved landscape plans and fill the specified planter bag. All street trees, unless specified otherwise, shall be of a minimum grade of 45 litres with a minimum 30mm calliper. All other stock shall be of minimum 2 litre grade for groundcover and 3 litre grades for shrubs. | PS 25.2.1 | Plant Details | Prior to supply |  | R | PE
| General plant species and quality | The Overseeing Organisation shall be provided with not less than five working days’ notice of dates upon which plants are to be delivered on site, so that arrangements can be made for quality inspection and confirmation of identification of plant material. | PS 25.2.1 | Notice | 5 working day notice |  | R | PE
| Street tree grades, species, and form | All street trees, unless specified otherwise, shall be of a minimum grade of PB 95 and be first grade nursery specimens. No substitution of species or grade shall be made without the written approval of the Engineer. | PS 25.2.2 | Plant Details | Prior to supply |  | R | PE
| Chemical applications for weed and pest control | All chemical application on planted areas shall be carried out by qualified, trained personnel and according to NZS 8409 Management of Agrichemicals, any relevant local Herbicide Policy and manufacturers’ requirements. | PS 25.5.2 | Qualifications and Datasheet | Prior to Application |  | R | SE
| Biodegradable plant guards | All plant and animal pest control used for the landscaping works shall fully comply with Section D of NZTA P39. | PS 25.6 | Datasheet | Prior to supply |  | R | PE
| Fertilisers | Fertilisers shall be either an approved pelletised natural or organic fertiliser or an approved synthetic fertiliser. | PS 25.7.3.2 | Datasheet | Prior to supply |  | R | PE
| Imported Topsoil | Topsoil, both imported and existing on site, shall be a loam soil of good quality, free draining, free of weeds and contaminates, free of building materials and debris, screened, health, and contain no pans. | PS 25.8.1 | Datasheet | Prior to supply |  | R | PE
| Biodegradable Weed Matting | The biodegradable weed matting shall conform with NZTA P39 and be coconut fibre mat, Woolmat or similar approved. | PS 25.9.1 | Datasheet | Prior to supply |  | R | PE
| Mulching fabric Testing | A simple test to ascertain whether the mulching fabric is viable is to hold a sample to the sky. It should be mostly opaque. This density inhibits weed seeds trapped under the mulching fabric from sprouting, provides good moisture retention and assists with batter erosion control. | PS 25.9.2 | Test Results | Prior to use |  | R | SE
| Mulch | The mulch shall be supplied as scheduled, clean, and free of soil, sawdust and wood preservatives, and a sample shall be provided to the Engineer for approval prior to spread. | PS 25.9.2 | Engineers Approval | Prior to use |  | HP | ENG
| Turf / Instant turf | The turf shall be of good quality in line with industry standards. | PS 25.10.5 | Datasheet | Prior to supply |  | R | PE
SECTION 15 – CONSTRUCTION ACTIVITY – STREETLIGHTING
15.01 | Streetlighting Quality Assurance plan
| Streetlighting Quality Assurance plan | Provide a Quality Assurance plan to propose, establish, maintain, monitor and document a quality assurance system covering all aspects of the procurement, fabrication, installation and completion of the works. | PS 22.4.6 | Streetlighting QA Plan | Prior to Streetlighting |  | HP | ENG |  |  | Plan and ITP top be developed by Subcontractor
SECTION 16 – CONSTRUCTION ACTIVITY – TRAFFIC SERVICES
16.01 | Signs
| Redundant Signs | All redundant sign equipment shall be offered to the New Zealand Transport Agency to be uplifted for possible future use. All redundant equipment not required by New Zealand Transport Agency, shall be uplifted, removed completely off site, and disposed of in an appropriate manner. | PS 23.2.2 | Site Records | Where Required |  | R | SE
| Relocated Signs | All relocated signs shall be Firmly installed in a vertical position and securely attached to posts where appropriate. Fixed to posts with appropriate fixing brackets. Signs shall not be fixed to posts by bolting through the sign unless specifically approved by the Engineer. | PS 23.2.3 | Site Records | Each Sign |  | R | SE
| Posts and poles | The Contractor shall maintain construction records for each sign that clearly shows that all post, poles and foundation details comply with the requirements of this Specification. The design of foundations should, where required, consider the very close proximity of services and not subject these services to any dead or live loadings from the sign support structures. | PS 23.2.17 PS 23.2.18 PS 23.2.24 | Checksheet | Each Sign |  | I | SE
| Ground Mounted Signs | All ground mounted signs shall be orientated such that they are turned about five degrees away from the driver’s line of sight or the normal to-the-road centreline as detailed in Clause 1.10 ‘Orientation’ of the Waka Kotahi NZ Transport Agency Manual of Pavement Markings and Signs Part 1. | PS 23.2.27 | Site Records | Each Ground Mounted Sign |  | V | SE
16.02 | Pavement Markings
| Surplus Chip Removal | Accumulations of surplus chip and other coarse material shall be removed prior to road marking. | PS 23.3.2 | Site Records | Prior to Marking |  | V | SE
| High Performance Marking | All road marking installed is to be high performance textured pavement markings in accordance with NZTA P30 High Performance Road markings unless otherwise specified. | PS 23.3.1 | Site Records | Each Marking |  | V | SE
| Roadmarking Removal | All road markings that are to be permanently removed must be either by water blasting or milling off in line with the NZRF line removal guide. The removal of all redundant pavement marking shall be such that The shape of the marking cannot be distinguished, The final surface texture is like the surrounding pavement; and No evidence of the paint remains. | PS 23.3.2 | Site Records | Each Removed marking |  | V | SE
| Raised Pavement Markers | These shall be located as detailed on the Drawings and installed in accordance with the requirements of TNZ P/14. The applicator shall ensure that the placement surface is dry and free of all foreign material and loose chip, which would hinder the correct installation of the raised pavement markers. | PS 23.3.2 | Site Records | Each Marking |  | V | SE
| Edge Marker Posts: | Edge marker posts shall be installed in accordance with the requirements of NZTA M14. Setting out shall be in accordance with the latest amendment of the Manual of Traffic Signs and Markings and the Drawings. | PS 23.3.2 | Site Records | Each Marking |  | V | SE
| Coloured Surfacing | Coloured surfacing shall be laid in accordance with the requirements of NZTA P33. | PS 23.3.2 PS 23.4 | Site Records | Each Application |  | V | SE
16.03 | Long-life Road Markings
| Mark out the Contract Works with Engineer | The Contractor is required to mark out the contract works with the Engineer in accordance with the NZTA Traffic Control Devices Manual Part 5 before any installation commences. The application shall be in accordance with the Land Transport Rule: Traffic Control Devices 2004. The Contractor must give the Engineer 5 Working Day notice of the proposed date the Contractor intents to mark out the extent of the contract works on site. | PS 23.5.9 | Markout Records | 5 Working Day notice prior to mark out |  | HP | ENG
| Applicator, Marking System, Marking Format and Applicator Crew Trial | The trial shall be completed using the applicator(s), marking system(s), marking format and crew approved for the contract works. The Contractor shall give the Engineer 5 Working Day notice of the date for the trial(s). Installation shall commence only if the Engineer is satisfied with the trial result(s). Verbal acceptance will be given to the Contractor immediately after the trial with written confirmation to follow. | PS 23.5.11 | Trail Results | Prior to Installation |  | HP | ENG
| Inspection and Measuring During Installation | The Contractor shall inspect the long-life road marking against dimensional and installation tolerances as installation progresses. The Contractor shall on a daily frequency complete a Daily Quality Assurance Form (Thermoplastic and CAP respectively). The form records the material data, environmental conditions, etc. | PS 23.5.13 PS 23.5.15 | Daily Quality Assurance Form | During installation |  | V | SE
| Inspection Post Installation | Formal visual drive over inspections. The visual inspection shall include An initial night inspection followed by a day inspection shall be carried out by the Engineer and Contractor of the first 25 to 50km per type of roadmarking installed (approximately 5 to 7 days of installation). The inspection shall be carried out 2 to 4 weeks post installation to allow for trafficking and a rainfall event. Subsequent visual inspections by the Engineer and the Contractor shall be jointly carried out of a sample of the contract works. | PS 23.5.16 | Report | Minimum of 20% of the total contract works will be inspected per type of roadmarking |  | V | SE
| Monitoring Post Installation | The Engineer and the Contractor shall agree on representative sites for ongoing monitoring. Monitoring sites shall be 2 per 100km of edge-line per roadmarking type. Three sets of monitoring shall be carried out First monitoring following installation of all contract works. The monitoring shall be carried out 2 to 4 weeks post installation to allow for trafficking and a rainfall event. Second monitoring approximately six months after the first monitoring. The Engineer may waive the monitoring if they are satisfied with the performance of the markings based on the first monitoring. Third monitoring prior the issue of Final Completion Certificate. | PS 23.5.17 | Report | 2 per 100km of edge-line per roadmarking type |  | HP | ENG
16.04 | Safety Barriers
| Ground profile | The finished ground profile from the edge of the pavement to the guardrail and for at least 600mm behind the guardrail shall be a maximum crossfall of + or -1 in 10. | PS 23.6 M23 | Site Records | Prior to post installation |  | V | SE
| Installation Notice | The Engineer shall be notified and given opportunity to inspect the set-out for the guardrail at least 24 hours prior to construction. | PS 23.6 M23 | Notice | Prior to Guardrail Construction |  | HP | ENG
| Guardrail Alignment Visual Inspection | The horizontal alignment of the barrier shall not deviate more than ± 10 mm from the specified positions and levels. When erected but before posts are permanently fixed the completed guardrail alignment shall be visually acceptable. | PS 23.6 M23 | Site Records | When erected but before posts are permanently fixed |  | V | SE
| Guard Rail and End Post Installation Checksheets | The Contractor shall submit a completed and signed installation check sheet for each terminal and guardrail section installed to the Engineer for acceptance | PS 23.6 M23 | Checksheets | Upon completion of the Guardrail Construction |  | HP | ENG
| Galvanising Repair | After assembly, any areas of the galvanised coating that have been damaged or show signs of deterioration shall be wire brushed and washed to thoroughly clean down to fresh zinc or parent metal. They shall then be spot painted with two brush coats of un-thinned approved zinc rich paint the first coat being applied to a dry surface immediately after cleaning. | PS 23.6 M23 | Site Records | Where Required |  | S | SE
16.05 | Safe Lane Delineators
| Safe Lane Delineator Installation | The safe lane delineators are to be installed in accordance with the manufacturer’s specification unless otherwise directed in the Contract Drawings. | PS 23.7 | Site Records | Post Installation |  | S | SE
| Chemset Safe Lane Delineator | Where detailed in the Contract Drawings the Contractor shall excavate a 300mm x 300mm diameter hole and ensure all loose debris is removed from the hole. The hole shall be back filled with 20MPa concrete and the safe lane delineator is to be chemset in place. The concrete shall be level with the existing surfacing around the hole and water shall drain away from the delineator. | PS 23.7 | Site Records | Each Post |  | S | SE
SECTION 17 – CONSTRUCTION ACTIVITY – UTILITIES
17.01 | Services
| Existing Services | The Contractor shall locate or arrange for the relevant service authority to locate existing services prior to commencing work in any area. Where a clash of services is identified the Contractor shall summit a proposal for overcoming the problem to the Engineer. The Contractor shall give service authorities reasonable notice when excavating within close proximity to their services. | PS 24.1.1 | Comms | Prior to commencing work |  | HP | ENG
| Private Services | Any private services such as domestic water and power supplies, rural mailboxes etc., damaged by the Contractor’s operations shall be repaired at the Contractor’s expense. The Contractor shall keep disruptions to individual landowners/occupiers to the minimum practicable. The Contractor shall consult with all affected landowners/occupiers to arrange for a mutually acceptable time for works that will interrupt availability of services and to identify any special requirements for continuity of supply. Where there is a requirement for continuity of supply the Contractor shall take all reasonable measures necessary to satisfy the affected party’s requirements. Where possible at least 10 Working Days’ notice should be given before shutdowns. | PS 24.1.2 | Comms | 10 Working Days’ notice should be given before shutdowns. |  | R | SE
| Service Connections | The Contractor shall liaise with the appropriate service provider to coordinate connection of the new service into the existing service. | PS 24.1.3 | Comms | Prior to connections |  | R | SE
17.02 | Locate and Pothole Services
| Service Location | All locations where connection to an existing pipe is proposed, the Contractor shall pothole and expose the pipe and level the crown. If an issue is identified from potholing, the Contractor shall notify the Engineer. | PS 24.2 | Potholing Record | Prior to Excavation |  | H | PE
| Service Clashes | The Contractor shall notify the Engineer immediately of any service clashes identified and the Engineer will advise on how to proceed. | PS 24.2 | Notice | Each Occurrence |  | HP | ENG
| Service Plans | The Contractor shall be responsible for obtaining all service plans and identifying all existing services on site, including potholing where required to confirm the exact location and depth. | PS 24.2 | Service Plans | Prior to Excavation |  | H | PE
SECTION 18 – CONSTRUCTION ACTIVITY – LANDSCAPING
18.01 | General
| Topsoil Placement Inspection | The Engineer shall inspect the cut surfaces prior to the placement of topsoil and planting. | PS 15.10.10 | Engineers Approval | Prior to Topsoil Placement |  | HP | ENG
| Setting out Notice | The Contractor shall provide written notice to the Engineer, at least two days prior to Setting out. | PS 25.1.6 | Notice | At least two days prior |  | HP | ENG
| Applying herbicide Notice | The Contractor shall provide written notice to the Engineer, at least two days prior to Applying herbicide. | PS 25.1.6 | Notice | At least two days prior |  | HP | ENG
| Cultivation of planting areas Notice | The Contractor shall provide written notice to the Engineer, at least two days prior to Cultivation of planting areas. | PS 25.1.6 | Notice | At least two days prior |  | HP | ENG
| Delivery of plants and trees Notice | The Contractor shall provide written notice to the Engineer, at least two days prior to Delivery of plants and trees. | PS 25.1.6 | Notice | At least two days prior |  | HP | ENG
| Planting or seeding Notice | The Contractor shall provide written notice to the Engineer, at least two days prior to Planting or seeding. | PS 25.1.6 | Notice | At least two days prior |  | HP | ENG
| Site visits during maintenance period Notice | The Contractor shall provide written notice to the Engineer, at least two days prior to Site visits during maintenance period. | PS 25.1.6 | Notice | At least two days prior |  | HP | ENG
18.02 | Weed, Pest, and Litter Control
| Litter control | The planting area shall be kept clear of all rubbish, including domestic and building materials. | PS 25.5.1 | Site Records | Ongoing |  | S | SE
| Spraying Operations | All spraying operations shall be carried out in windless, dry conditions, when rain is not imminent for at least 12 hours and at times which minimise possible hazards or disruption to the public, animals or other beneficial fauna. Care shall be taken to prevent spray drifting onto non-target areas or plants and comply with notification requirements as required by the proposed Waikato Regional Plan. | PS 25.5.2 | Site Records | Each Application |  | R | SE
| Chemical weed control in planting areas | Chemical weed control in planting areas shall be kept within the edge of the planting beds, within a maximum of 500mm of tree trunks, within 50mm of the edge of any undefined mulch surface, and within 50mm of any posts or the base of any landscape structures. | PS 25.5.2 | Site Records | Each Application |  | R | SE
| Biodegradable plant guards | All plants to be fitted with biodegradable plant guards. | PS 25.6 | Site Records | Each Plant |  | R | SE
18.03 | Planting
| Planting Layout | All plants shall be positioned in the locations and in the quantities shown on the drawings., Planting Schedule and Typical Cross Sections for inspection and authorisation by the Engineer prior to planting. | PS 25.7.1 | Site Records | Prior to Planting |  | HP | ENG
| Specimen and street trees | Newly planted specimen trees shall be staked with two 50 x 50 x 1.8m rough sawn Pine H4 treated or hardwood stakes with at least one third of their length (600mm) in the ground and at least 1.0m exposed minimum, or as specified on the plan with the approval of the Overseeing Organisation. | PS 25.7.2.1 | Site Records | Each Tree |  | R | SE
| Irrigation and Fertilising | During installation and establishment, the soil in all planting areas moisture shall be retained to ensure active plant growth throughout the growing season (September – May).. | PS 25.7.2.3 | Site Records | Each Area |  | S | SE
| Fertilising | Generally, some form of fertiliser shall be applied to planting depending on the soil type. For shrubs and trees, all fertiliser shall be well mixed with the backfilled soil. For bedding or groundcover all fertiliser shall be well mixed with the site topsoil prior to planting. | PS 25.7.3.2 | Site Records | Each Area |  | S | SE
| Plantings | All specimen tree plantings shall have two-year slow release fertiliser tablets installed at the time of planting. | PS 25.7.3.3 | Site Records | Each Tree |  | R | SE
| Topsoiling | All topsoil and operations relating to topsoil for the project shall fully conform to Section F of NZTA P39. | PS 25.8.1 | Site Records | prior to planting. |  | V | SE
| Topsoiling | All new planting areas on existing topsoil shall be deep ripped to a minimum of 300mm prior to planting. | PS 25.8.1 | Site Records | prior to planting. |  | V | SE
18.04 | Biodegradable Weed Matting and Mulching
| Biodegradable high density mulch matting | The blanket shall be installed according to the Manufacturer’s directions and shall include stapling the blanket at a minimum of 1 metre centres and perimeter edges buried to 300mm depth buried soil. | PS 25.7.1 | Site Records | Each Area |  | R | SE
| Flat Site Mulch | On sites flatter than a 1:2 grade (1.0m high by 3.0m metres long), bark or arb mulch shall be spread evenly to a depth of 80-100mm over the planted area, creating an inverted cone hollow around each plant stem with a maximum 25mm depth around plant stems. | PS 25.9.2 | Site Records | Each Area |  | R | SE
| Steep Site Mulch | On slopes steeper than 1:2 mulching for weed control shall consist of an Engineer approved matting with the following criteria: | PS 25.9.2 | Site Records | Each Area |  | R | SE
| Very Steep Slopes Mulch | On steep slopes (1 in 4) with erosion issues that are receiving planting, biodegradable netting with no geotextile or geonet content shall be used at the Engineer’s discretion. | PS 25.9.2 | Site Records | Each Area |  | R | SE
18.05 | Grassing, Sowing and Turfing
| Preparation for sowing or turfing | Excessive compaction of subsoil in existing grassed areas shall be relieved to achieve satisfactory long-term growing conditions. All topsoil removed to permit contract works to be carried out shall be stockpiled for reuse. All new grass areas shall be built on soil prepared to industry best practice standards. Sloped areas shall be neatly contoured into adjoining grassed areas. Perennial weeds shall be controlled with industry best practice methods. | PS 25.10.1 | Site Records | Each Area |  | S | SE
| Fertilisers | Fertilisers shall be lightly arrowed into the topsoil, 2-3 days prior to seed sowing, at the following rates at 200kg/ha. This shall be followed one month after sowing, with an application of: Di-ammonium Phosphate (DAP) 100 kg/ha. | PS 25.10.2 | Site Records | 2-3 days prior to seed sowing and 1 month after sowing |  | S | SE
| Grass sowing | On large areas the seed shall be “check” sown in at least two directions and surface rolled with suitable flat roller. On small areas the grass seed shall be evenly applied and raked into the soil. | PS 25.10.3 | Site Records | Each Area |  | S | SE
| Establishment of sown areas | Newly established grass shall be protected from damage by pedestrian and vehicular traffic until grass has reached a self-sustaining state. Grassed areas shall be watered as required to achieve an efficient germination of the seed. Newly grassed areas shall be maintained with regular mowing (90mm-30mm) ensuring that all clippings are removed from adjacent hard surfaces. | PS 25.10.4 | Site Records | Each Area |  | S | SE
| Grassed areas adjacent hardscape | If base of grass level is 30mm lower or more than adjacent hardstand, grass will need to be removed min 1m back from path, soil put back in, levelled and re-consolidated to spec and grass res-own to correct level. If less than 30mm top dressing at 10mm each time, over time will be acceptable until the correct level is achieved. | PS 25.10.4 | Site Records | Each Area |  | S | SE
| Turf / Instant turf | Turf shall be installed and maintained in accordance with supplier’s requirements. | PS 25.10.5 | Site Records | Each Area |  | S | SE
| Slope areas | In all sites, except natural gully systems, where the slope gradient is steeper than 1:3 (one metre high by three metres long), it is preferable that the embankment is either scarified or grooved on an angle to a depth of 200mm, from the top of the bank to the base. This assists topsoil adhesion and prevents separation of the top 150mm topsoil from the base material due to gravity and/or glazed/planning of base material. | PS 25.10.6 | Site Records | Each Area |  | S | SE
18.06 | Fencing
| Seven Wire Fencing Order | The Contractor is to liaise with the property owner to establish the preferred spacing and order of the seven wires. | PS 25.12.2 | Comms | Prior to Installation |  | R | PE
| Post and Wire Fencing Installation | New seven wire standard boundary fence shall be erected with the following Offset tolerances 0.0m towards the centreline and 0.0m to 0.3m away from the centreline. The fence shall be vertical, and the grade shall generally follow the contour of the ground. | PS 25.12.2 | Survey Records | Each Fence |  | I | SV
SECTION 19 – COMMISSIONING
19.01 | Road Opening
19.01.01 | Pre-Opening Safety Review | Prior to opening the Works for use by the general travelling public, a pre-opening safety review will be undertaken by the Engineer and the Principal’s Road Safety Audit team, to approve the removal of any temporary works, speed limits and traffic management. | PS 7.5.1 | Report | Prior to opening the Works for use |  | HP | ENG
19.01.02 | Post Construction Safety Audit | Prior to the issue of Practical Completion, a post construction safety audit must be completed by the Engineer and the Principal’s Road Safety Audit team. | PS 7.5.2 | Report | Prior to the issue of Practical Completion |  | HP | ENG

## General - Materials
General Materials Inspection and Test Plan
Project: SH1/29 Intersection Upgrade
Number and Revision: - 105 - Rev A
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Testing Quantity Required | Verification Activity |  | Downer Conformance of Compliance Signoff
[7 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details | ENGINEERS COMMENTS - Date: | DOWNER RESPONSE - Date:
SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
3.01 | General
3.01.01 | Precondition Surveys | A precondition survey of Waka Kotahi and other public / private assets within the extent of the Site and immediately beyond the outside area of the construction activities shall be undertaken in conjunction with the Engineer prior to the Contractor taking possession of the Site. | PS 2.13 | Precondition Survey | Prior to the Contractor taking possession of the Site. |  | H | PM
SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
4.34 | Traffic Service Materials
| Safe Lane Delineator Concrete | Unless otherwise stated, concrete shall have a minimum compressive strength of 20 MPa at 28 days. | PS 23.7 | Datasheet / Mix Design | Prior to use |  | R | SE
| Guard Rail Concrete | Unless otherwise stated, concrete shall have a minimum compressive strength of 20 MPa at 28 days. | PS 23.6 M23 | Datasheet / Mix Design | Prior to use |  | R | SE
| Proposed Guard Rails | The Contractor shall submit details of proposed proprietary materials and systems. | PS 23.6 M23 | Datasheets | Prior to material order (4 weeks prior to installation) |  | HP | ENG
| Guard Rail Maintenance Instructions | The Contractor shall submit details of the manufacturers maintenance instructions for the type of barrier installed. | PS 23.6 M23 | Maintenance Instructions | Upon completion of the Guardrail Construction |  | HP | ENG
| Coloured Surfacing | The contractor shall provide evidence to the Engineer before preparation and marking of the surfacing, that the material conforms in its entirety to the requirements of NZTA P33. | PS 23.4 | Datasheets | Prior to use |  | R | SE
4.35 | Sign Materials
| Retro-reflective sheeting | All retro-reflective sheeting must be approved for use in New Zealand and comply with the following requirements of NZTA P24 Specification for Permanent Traffic Signs and AS/NZS 1906.1: 1993 Retro-reflective Materials and Devices for Road Traffic Control Purposes, Part 1 Retroreflective Sheeting. | PS 23.2.6 | Datasheet | Prior to use |  | R | SE
| Anti-Graffiti Coating | Graffiti protective coating shall be applied to all ground mounted sign and shall be approved for such use by the reflective sheeting manufacturer and shall maintain all guarantees for the sign. | PS 23.2.14 | Datasheet | Prior to use |  | R | SE
| Dew Effect Coating | All overhead mounted signs, except for bridge name plates, shall be manufactured with an overlay that is designed to prevent dew droplets forming to overcome the phenomenon known as ‘dew effect’. | PS 23.2.15 | Datasheet | Prior to use |  | R | SE
| Sign Shop Drawings | The supplier shall prepare shop drawings detailing the panel layout, positions of channel framing, and assembly systems prior to the manufacture of any sign. The shop drawings shall be submitted for review and comment at least ten working days prior to manufacture of the sign. | PS 23.2.6 | Shop Drawings | At least ten working days prior to manufacture of the sign. |  | R | SE
| Timber Posts | Timber posts shall not exceed 100mm x 100mm section size. They shall be Building Grade or Number 1 Framing grade timber as specified in NZS 3631, dried to 20-24% moisture content, and treated in accordance with the New Zealand Timber Preservation Council’s requirements as specified in NZS 3640 for Hazard Class H4. The timber finish may be gauged or dressed. The timber posts shall be primed and finished with white high gloss paint over the length above ground level. | PS 23.2.19 | Datasheet | Prior to use |  | R | SE
| Steel Posts | Steel posts shall be of an approved frangible design. They shall be hot-dip galvanised and finished with white high gloss paint. The paint system shall be specified and applied in accordance with AS/NZS 2312.1. All poles shall be fitted with white PVC caps. | PS 23.2.20 | Datasheet | Prior to use |  | R | SE
| Aluminium Poles | Aluminium poles shall conform to Alloy 6261 T5 as required in NZTA P24. All poles shall be fitted with white PVC caps. | PS 23.2.21 | Datasheet | Prior to use |  | R | SE
| Impact Resistant System Posts | Aluminium poles shall conform to Alloy 6261 T5 as required in NZTA P24. All poles shall be fitted with white PVC caps. | PS 23.2.22 | Datasheet | Prior to use |  | R | SE
| Sign Fixings | All signs shall be installed using approved sign support channel bracket fittings that do not penetrate the front face of the sign. No bolts, rivets or other fixings shall penetrate the front face of the sign. | PS 23.2.23 | Datasheet | Prior to use |  | R | SE
| Training | The installer shall demonstrate prior to undertaking the works that its staff has attended, or are scheduled to attend, a recognised training course in the handling, installation, and maintenance of retro-reflective road signs. | PS 23.2.25 | Training Records | Prior to Installation |  | R | SE
4.36 | Long-life Road Markings Materials
| Applicator Approval | The applicator(s) used for the contract works must be certified to NZTA/NZRF T/12. No installation shall commence without the written approval of the Engineer accepting the certification and suitability of the applicator(s) proposed. | PS 23.5.2 | Engineers Approval | Prior to Installation |  | HP | ENG
| Long-life Road Markings Materials, Marking System and Format | Only products approved to NZTA specifications are to be used. The Contractor must submit to the Engineer details of each of the products that will be used in the contract works. The submission must include: | PS 23.5.3 | Engineers Approval | Prior to Installation |  | HP | ENG
| Installation Limitations | The Contractor shall supply the Engineer with the Supplier Specifications or Instructions on Installation for the long-life road marking system proposed to be used. No installation shall commence without the written approval of the Engineer accepting the suitability of the long-life road marking system proposed. | PS 23.5.4 | Engineers Approval | Prior to Installation |  | HP | ENG
| Glass beads | The Contractor shall ensure that glass beads have appropriate adhesive coatings for the long-life road marking product being used. No installation shall commence without the written approval of the Engineer accepting the suitability of the glass beads proposed. | PS 23.5.5 | Engineers Approval | Prior to Installation |  | HP | ENG
| Raised Pavement Markers | All raised pavement markers shall be in accordance with TNZ M/12 Raised Pavement Markers. | PS 23.5.6 | Datasheets | Prior to Installation |  | R | SE
| Application Crew | The Contractor is to notify the Engineer of any proposed changes to the crew. The Contractor shall provide a CV outlining their qualifications, skills and experience related to installation of long-life road marking systems. No installation shall commence without the written approval of the Engineer accepting the suitability of the nominated crew or any changes proposed. | PS 23.5.7 | Engineers Approval | Prior to Installation |  | HP | ENG
4.37 | Pavement Marking Materials
| High performance markings | All road marking installed is to be high performance textured pavement markings in accordance with NZTA P30 High Performance Road markings unless otherwise specified. The Contractor shall nominate the brand, type and proposed application methods for materials to be used. This information shall be provided for approval prior to application. | PS 23.3.1 | Datasheets | Prior to Installation |  | HP | ENG
| Glass beads | All glass beads added to the paint for reflectorised line application shall be in accordance with AS/NZS 2009 Glass Beads for Road-Marking Materials and the current NZTA Policy and Testing Regime for Heavy Metals (T17). | PS 23.3.1 | Datasheets | Prior to Installation |  | R | SE
| Raised Pavement Markers | All raised pavement markers shall be in accordance with TNZ M/12 Raised Pavement Markers. | PS 23.3.1 | Datasheets | Prior to Installation |  | R | SE
| Edge Marker Posts: | Edge Marker posts shall be non-wood and shall comply with NZTA M14. Non-wood posts shall have current NZTA M14 type approval. | PS 23.3.1 | Datasheets | Prior to Installation |  | R | SE
4.38 | Fencing Materials
| Post and Wire Fencing Materials | All in ground timber posts shall be treated to H4 standard and all other timber shall be treated to H3 standard. All posts to be sunk to the required depth and supported to form a rigid boundary fence. | PS 25.12.2 | Datasheet / Docket | Prior to Installation
4.39 | Landscaping Material Supply
| Plant Supply | All plants shall be supplied true to the species and grades specified on the approved landscape plans and fill the specified planter bag. All street trees, unless specified otherwise, shall be of a minimum grade of 45 litres with a minimum 30mm calliper. All other stock shall be of minimum 2 litre grade for groundcover and 3 litre grades for shrubs. | PS 25.2.1 | Plant Details | Prior to supply |  | R | PE
| General plant species and quality | The Overseeing Organisation shall be provided with not less than five working days’ notice of dates upon which plants are to be delivered on site, so that arrangements can be made for quality inspection and confirmation of identification of plant material. | PS 25.2.1 | Notice | 5 working day notice |  | R | PE
| Street tree grades, species, and form | All street trees, unless specified otherwise, shall be of a minimum grade of PB 95 and be first grade nursery specimens. No substitution of species or grade shall be made without the written approval of the Engineer. | PS 25.2.2 | Plant Details | Prior to supply |  | R | PE
| Chemical applications for weed and pest control | All chemical application on planted areas shall be carried out by qualified, trained personnel and according to NZS 8409 Management of Agrichemicals, any relevant local Herbicide Policy and manufacturers’ requirements. | PS 25.5.2 | Qualifications and Datasheet | Prior to Application |  | R | SE
| Biodegradable plant guards | All plant and animal pest control used for the landscaping works shall fully comply with Section D of NZTA P39. | PS 25.6 | Datasheet | Prior to supply |  | R | PE
| Fertilisers | Fertilisers shall be either an approved pelletised natural or organic fertiliser or an approved synthetic fertiliser. | PS 25.7.3.2 | Datasheet | Prior to supply |  | R | PE
| Imported Topsoil | Topsoil, both imported and existing on site, shall be a loam soil of good quality, free draining, free of weeds and contaminates, free of building materials and debris, screened, health, and contain no pans. | PS 25.8.1 | Datasheet | Prior to supply |  | R | PE
| Biodegradable Weed Matting | The biodegradable weed matting shall conform with NZTA P39 and be coconut fibre mat, Woolmat or similar approved. | PS 25.9.1 | Datasheet | Prior to supply |  | R | PE
| Mulching fabric Testing | A simple test to ascertain whether the mulching fabric is viable is to hold a sample to the sky. It should be mostly opaque. This density inhibits weed seeds trapped under the mulching fabric from sprouting, provides good moisture retention and assists with batter erosion control. | PS 25.9.2 | Test Results | Prior to use |  | R | SE
| Mulch | The mulch shall be supplied as scheduled, clean, and free of soil, sawdust and wood preservatives, and a sample shall be provided to the Engineer for approval prior to spread. | PS 25.9.2 | Engineers Approval | Prior to use |  | HP | ENG
| Turf / Instant turf | The turf shall be of good quality in line with industry standards. | PS 25.10.5 | Datasheet | Prior to supply |  | R | PE

## Streetlighting
Streetlighting Inspection and Test Plan
Project: SH1/29 Intersection Upgrade
Number and Revision: - 105 - Rev A
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Testing Quantity Required | Verification Activity |  | Downer Conformance of Compliance Signoff
[7 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details | ENGINEERS COMMENTS - Date: | DOWNER RESPONSE - Date:
SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
3.01 | General
3.01.01 | Precondition Surveys | A precondition survey of Waka Kotahi and other public / private assets within the extent of the Site and immediately beyond the outside area of the construction activities shall be undertaken in conjunction with the Engineer prior to the Contractor taking possession of the Site. | PS 2.13 | Precondition Survey | Prior to the Contractor taking possession of the Site. |  | H | PM
SECTION 15 – CONSTRUCTION ACTIVITY – STREETLIGHTING
15.01 | Streetlighting Quality Assurance plan
| Streetlighting Quality Assurance plan | Provide a Quality Assurance plan to propose, establish, maintain, monitor and document a quality assurance system covering all aspects of the procurement, fabrication, installation and completion of the works. | PS 22.4.6 | Streetlighting QA Plan | Prior to Streetlighting |  | HP | ENG |  |  | Plan and ITP top be developed by Subcontractor

## Traffic Services
Traffic Services Inspection and Test Plan
Project: SH1/29 Intersection Upgrade
Number and Revision: - 105 - Rev A
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Testing Quantity Required | Verification Activity |  | Downer Conformance of Compliance Signoff
[7 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details | ENGINEERS COMMENTS - Date: | DOWNER RESPONSE - Date:
SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
3.01 | General
3.01.01 | Precondition Surveys | A precondition survey of Waka Kotahi and other public / private assets within the extent of the Site and immediately beyond the outside area of the construction activities shall be undertaken in conjunction with the Engineer prior to the Contractor taking possession of the Site. | PS 2.13 | Precondition Survey | Prior to the Contractor taking possession of the Site. |  | H | PM
SECTION 16 – CONSTRUCTION ACTIVITY – TRAFFIC SERVICES
16.01 | Signs
| Redundant Signs | All redundant sign equipment shall be offered to the New Zealand Transport Agency to be uplifted for possible future use. All redundant equipment not required by New Zealand Transport Agency, shall be uplifted, removed completely off site, and disposed of in an appropriate manner. | PS 23.2.2 | Site Records | Where Required |  | R | SE
| Relocated Signs | All relocated signs shall be Firmly installed in a vertical position and securely attached to posts where appropriate. Fixed to posts with appropriate fixing brackets. Signs shall not be fixed to posts by bolting through the sign unless specifically approved by the Engineer. | PS 23.2.3 | Site Records | Each Sign |  | R | SE
| Posts and poles | The Contractor shall maintain construction records for each sign that clearly shows that all post, poles and foundation details comply with the requirements of this Specification. The design of foundations should, where required, consider the very close proximity of services and not subject these services to any dead or live loadings from the sign support structures. | PS 23.2.17 PS 23.2.18 PS 23.2.24 | Checksheet | Each Sign |  | I | SE
| Ground Mounted Signs | All ground mounted signs shall be orientated such that they are turned about five degrees away from the driver’s line of sight or the normal to-the-road centreline as detailed in Clause 1.10 ‘Orientation’ of the Waka Kotahi NZ Transport Agency Manual of Pavement Markings and Signs Part 1. | PS 23.2.27 | Site Records | Each Ground Mounted Sign |  | V | SE
16.02 | Pavement Markings
| Surplus Chip Removal | Accumulations of surplus chip and other coarse material shall be removed prior to road marking. | PS 23.3.2 | Site Records | Prior to Marking |  | V | SE
| High Performance Marking | All road marking installed is to be high performance textured pavement markings in accordance with NZTA P30 High Performance Road markings unless otherwise specified. | PS 23.3.1 | Site Records | Each Marking |  | V | SE
| Roadmarking Removal | All road markings that are to be permanently removed must be either by water blasting or milling off in line with the NZRF line removal guide. The removal of all redundant pavement marking shall be such that The shape of the marking cannot be distinguished, The final surface texture is like the surrounding pavement; and No evidence of the paint remains. | PS 23.3.2 | Site Records | Each Removed marking |  | V | SE
| Raised Pavement Markers | These shall be located as detailed on the Drawings and installed in accordance with the requirements of TNZ P/14. The applicator shall ensure that the placement surface is dry and free of all foreign material and loose chip, which would hinder the correct installation of the raised pavement markers. | PS 23.3.2 | Site Records | Each Marking |  | V | SE
| Edge Marker Posts: | Edge marker posts shall be installed in accordance with the requirements of NZTA M14. Setting out shall be in accordance with the latest amendment of the Manual of Traffic Signs and Markings and the Drawings. | PS 23.3.2 | Site Records | Each Marking |  | V | SE
| Coloured Surfacing | Coloured surfacing shall be laid in accordance with the requirements of NZTA P33. | PS 23.3.2 PS 23.4 | Site Records | Each Application |  | V | SE
16.03 | Long-life Road Markings
| Mark out the Contract Works with Engineer | The Contractor is required to mark out the contract works with the Engineer in accordance with the NZTA Traffic Control Devices Manual Part 5 before any installation commences. The application shall be in accordance with the Land Transport Rule: Traffic Control Devices 2004. The Contractor must give the Engineer 5 Working Day notice of the proposed date the Contractor intents to mark out the extent of the contract works on site. | PS 23.5.9 | Markout Records | 5 Working Day notice prior to mark out |  | HP | ENG
| Applicator, Marking System, Marking Format and Applicator Crew Trial | The trial shall be completed using the applicator(s), marking system(s), marking format and crew approved for the contract works. The Contractor shall give the Engineer 5 Working Day notice of the date for the trial(s). Installation shall commence only if the Engineer is satisfied with the trial result(s). Verbal acceptance will be given to the Contractor immediately after the trial with written confirmation to follow. | PS 23.5.11 | Trail Results | Prior to Installation |  | HP | ENG
| Inspection and Measuring During Installation | The Contractor shall inspect the long-life road marking against dimensional and installation tolerances as installation progresses. The Contractor shall on a daily frequency complete a Daily Quality Assurance Form (Thermoplastic and CAP respectively). The form records the material data, environmental conditions, etc. | PS 23.5.13 PS 23.5.15 | Daily Quality Assurance Form | During installation |  | V | SE
| Inspection Post Installation | Formal visual drive over inspections. The visual inspection shall include An initial night inspection followed by a day inspection shall be carried out by the Engineer and Contractor of the first 25 to 50km per type of roadmarking installed (approximately 5 to 7 days of installation). The inspection shall be carried out 2 to 4 weeks post installation to allow for trafficking and a rainfall event. Subsequent visual inspections by the Engineer and the Contractor shall be jointly carried out of a sample of the contract works. | PS 23.5.16 | Report | Minimum of 20% of the total contract works will be inspected per type of roadmarking |  | V | SE
| Monitoring Post Installation | The Engineer and the Contractor shall agree on representative sites for ongoing monitoring. Monitoring sites shall be 2 per 100km of edge-line per roadmarking type. Three sets of monitoring shall be carried out First monitoring following installation of all contract works. The monitoring shall be carried out 2 to 4 weeks post installation to allow for trafficking and a rainfall event. Second monitoring approximately six months after the first monitoring. The Engineer may waive the monitoring if they are satisfied with the performance of the markings based on the first monitoring. Third monitoring prior the issue of Final Completion Certificate. | PS 23.5.17 | Report | 2 per 100km of edge-line per roadmarking type |  | HP | ENG
16.04 | Safety Barriers
| Ground profile | The finished ground profile from the edge of the pavement to the guardrail and for at least 600mm behind the guardrail shall be a maximum crossfall of + or -1 in 10. | PS 23.6 M23 | Site Records | Prior to post installation |  | V | SE
| Installation Notice | The Engineer shall be notified and given opportunity to inspect the set-out for the guardrail at least 24 hours prior to construction. | PS 23.6 M23 | Notice | Prior to Guardrail Construction |  | HP | ENG
| Guardrail Alignment Visual Inspection | The horizontal alignment of the barrier shall not deviate more than ± 10 mm from the specified positions and levels. When erected but before posts are permanently fixed the completed guardrail alignment shall be visually acceptable. | PS 23.6 M23 | Site Records | When erected but before posts are permanently fixed |  | V | SE
| Guard Rail and End Post Installation Checksheets | The Contractor shall submit a completed and signed installation check sheet for each terminal and guardrail section installed to the Engineer for acceptance | PS 23.6 M23 | Checksheets | Upon completion of the Guardrail Construction |  | HP | ENG
| Galvanising Repair | After assembly, any areas of the galvanised coating that have been damaged or show signs of deterioration shall be wire brushed and washed to thoroughly clean down to fresh zinc or parent metal. They shall then be spot painted with two brush coats of un-thinned approved zinc rich paint the first coat being applied to a dry surface immediately after cleaning. | PS 23.6 M23 | Site Records | Where Required |  | S | SE
16.05 | Safe Lane Delineators
| Safe Lane Delineator Installation | The safe lane delineators are to be installed in accordance with the manufacturer’s specification unless otherwise directed in the Contract Drawings. | PS 23.7 | Site Records | Post Installation |  | S | SE
| Chemset Safe Lane Delineator | Where detailed in the Contract Drawings the Contractor shall excavate a 300mm x 300mm diameter hole and ensure all loose debris is removed from the hole. The hole shall be back filled with 20MPa concrete and the safe lane delineator is to be chemset in place. The concrete shall be level with the existing surfacing around the hole and water shall drain away from the delineator. | PS 23.7 | Site Records | Each Post |  | S | SE

## Utilities
Utilities Inspection and Test Plan
Project: SH1/29 Intersection Upgrade
Number and Revision: - 105 - Rev A
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Testing Quantity Required | Verification Activity |  | Downer Conformance of Compliance Signoff
[7 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details | ENGINEERS COMMENTS - Date: | DOWNER RESPONSE - Date:
SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
3.01 | General
3.01.01 | Precondition Surveys | A precondition survey of Waka Kotahi and other public / private assets within the extent of the Site and immediately beyond the outside area of the construction activities shall be undertaken in conjunction with the Engineer prior to the Contractor taking possession of the Site. | PS 2.13 | Precondition Survey | Prior to the Contractor taking possession of the Site. |  | H | PM
SECTION 17 – CONSTRUCTION ACTIVITY – UTILITIES
17.01 | Services
| Existing Services | The Contractor shall locate or arrange for the relevant service authority to locate existing services prior to commencing work in any area. Where a clash of services is identified the Contractor shall summit a proposal for overcoming the problem to the Engineer. The Contractor shall give service authorities reasonable notice when excavating within close proximity to their services. | PS 24.1.1 | Comms | Prior to commencing work |  | HP | ENG
| Private Services | Any private services such as domestic water and power supplies, rural mailboxes etc., damaged by the Contractor’s operations shall be repaired at the Contractor’s expense. The Contractor shall keep disruptions to individual landowners/occupiers to the minimum practicable. The Contractor shall consult with all affected landowners/occupiers to arrange for a mutually acceptable time for works that will interrupt availability of services and to identify any special requirements for continuity of supply. Where there is a requirement for continuity of supply the Contractor shall take all reasonable measures necessary to satisfy the affected party’s requirements. Where possible at least 10 Working Days’ notice should be given before shutdowns. | PS 24.1.2 | Comms | 10 Working Days’ notice should be given before shutdowns. |  | R | SE
| Service Connections | The Contractor shall liaise with the appropriate service provider to coordinate connection of the new service into the existing service. | PS 24.1.3 | Comms | Prior to connections |  | R | SE
17.02 | Locate and Pothole Services
| Service Location | All locations where connection to an existing pipe is proposed, the Contractor shall pothole and expose the pipe and level the crown. If an issue is identified from potholing, the Contractor shall notify the Engineer. | PS 24.2 | Potholing Record | Prior to Excavation |  | H | PE
| Service Clashes | The Contractor shall notify the Engineer immediately of any service clashes identified and the Engineer will advise on how to proceed. | PS 24.2 | Notice | Each Occurrence |  | HP | ENG
| Service Plans | The Contractor shall be responsible for obtaining all service plans and identifying all existing services on site, including potholing where required to confirm the exact location and depth. | PS 24.2 | Service Plans | Prior to Excavation |  | H | PE

## Landscaping
Landscaping Inspection and Test Plan
Project: SH1/29 Intersection Upgrade
Number and Revision: - 105 - Rev A
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Testing Quantity Required | Verification Activity |  | Downer Conformance of Compliance Signoff
[7 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details | ENGINEERS COMMENTS - Date: | DOWNER RESPONSE - Date:
SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
3.01 | General
3.01.01 | Precondition Surveys | A precondition survey of Waka Kotahi and other public / private assets within the extent of the Site and immediately beyond the outside area of the construction activities shall be undertaken in conjunction with the Engineer prior to the Contractor taking possession of the Site. | PS 2.13 | Precondition Survey | Prior to the Contractor taking possession of the Site. |  | H | PM
SECTION 18 – CONSTRUCTION ACTIVITY – LANDSCAPING
18.01 | General
| Topsoil Placement Inspection | The Engineer shall inspect the cut surfaces prior to the placement of topsoil and planting. | PS 15.10.10 | Engineers Approval | Prior to Topsoil Placement |  | HP | ENG
| Setting out Notice | The Contractor shall provide written notice to the Engineer, at least two days prior to Setting out. | PS 25.1.6 | Notice | At least two days prior |  | HP | ENG
| Applying herbicide Notice | The Contractor shall provide written notice to the Engineer, at least two days prior to Applying herbicide. | PS 25.1.6 | Notice | At least two days prior |  | HP | ENG
| Cultivation of planting areas Notice | The Contractor shall provide written notice to the Engineer, at least two days prior to Cultivation of planting areas. | PS 25.1.6 | Notice | At least two days prior |  | HP | ENG
| Delivery of plants and trees Notice | The Contractor shall provide written notice to the Engineer, at least two days prior to Delivery of plants and trees. | PS 25.1.6 | Notice | At least two days prior |  | HP | ENG
| Planting or seeding Notice | The Contractor shall provide written notice to the Engineer, at least two days prior to Planting or seeding. | PS 25.1.6 | Notice | At least two days prior |  | HP | ENG
| Site visits during maintenance period Notice | The Contractor shall provide written notice to the Engineer, at least two days prior to Site visits during maintenance period. | PS 25.1.6 | Notice | At least two days prior |  | HP | ENG
18.02 | Weed, Pest, and Litter Control
| Litter control | The planting area shall be kept clear of all rubbish, including domestic and building materials. | PS 25.5.1 | Site Records | Ongoing |  | S | SE
| Spraying Operations | All spraying operations shall be carried out in windless, dry conditions, when rain is not imminent for at least 12 hours and at times which minimise possible hazards or disruption to the public, animals or other beneficial fauna. Care shall be taken to prevent spray drifting onto non-target areas or plants and comply with notification requirements as required by the proposed Waikato Regional Plan. | PS 25.5.2 | Site Records | Each Application |  | R | SE
| Chemical weed control in planting areas | Chemical weed control in planting areas shall be kept within the edge of the planting beds, within a maximum of 500mm of tree trunks, within 50mm of the edge of any undefined mulch surface, and within 50mm of any posts or the base of any landscape structures. | PS 25.5.2 | Site Records | Each Application |  | R | SE
| Biodegradable plant guards | All plants to be fitted with biodegradable plant guards. | PS 25.6 | Site Records | Each Plant |  | R | SE
18.03 | Planting
| Planting Layout | All plants shall be positioned in the locations and in the quantities shown on the drawings., Planting Schedule and Typical Cross Sections for inspection and authorisation by the Engineer prior to planting. | PS 25.7.1 | Site Records | Prior to Planting |  | HP | ENG
| Specimen and street trees | Newly planted specimen trees shall be staked with two 50 x 50 x 1.8m rough sawn Pine H4 treated or hardwood stakes with at least one third of their length (600mm) in the ground and at least 1.0m exposed minimum, or as specified on the plan with the approval of the Overseeing Organisation. | PS 25.7.2.1 | Site Records | Each Tree |  | R | SE
| Irrigation and Fertilising | During installation and establishment, the soil in all planting areas moisture shall be retained to ensure active plant growth throughout the growing season (September – May).. | PS 25.7.2.3 | Site Records | Each Area |  | S | SE
| Fertilising | Generally, some form of fertiliser shall be applied to planting depending on the soil type. For shrubs and trees, all fertiliser shall be well mixed with the backfilled soil. For bedding or groundcover all fertiliser shall be well mixed with the site topsoil prior to planting. | PS 25.7.3.2 | Site Records | Each Area |  | S | SE
| Plantings | All specimen tree plantings shall have two-year slow release fertiliser tablets installed at the time of planting. | PS 25.7.3.3 | Site Records | Each Tree |  | R | SE
| Topsoiling | All topsoil and operations relating to topsoil for the project shall fully conform to Section F of NZTA P39. | PS 25.8.1 | Site Records | prior to planting. |  | V | SE
| Topsoiling | All new planting areas on existing topsoil shall be deep ripped to a minimum of 300mm prior to planting. | PS 25.8.1 | Site Records | prior to planting. |  | V | SE
18.04 | Biodegradable Weed Matting and Mulching
| Biodegradable high density mulch matting | The blanket shall be installed according to the Manufacturer’s directions and shall include stapling the blanket at a minimum of 1 metre centres and perimeter edges buried to 300mm depth buried soil. | PS 25.7.1 | Site Records | Each Area |  | R | SE
| Flat Site Mulch | On sites flatter than a 1:2 grade (1.0m high by 3.0m metres long), bark or arb mulch shall be spread evenly to a depth of 80-100mm over the planted area, creating an inverted cone hollow around each plant stem with a maximum 25mm depth around plant stems. | PS 25.9.2 | Site Records | Each Area |  | R | SE
| Steep Site Mulch | On slopes steeper than 1:2 mulching for weed control shall consist of an Engineer approved matting with the following criteria: | PS 25.9.2 | Site Records | Each Area |  | R | SE
| Very Steep Slopes Mulch | On steep slopes (1 in 4) with erosion issues that are receiving planting, biodegradable netting with no geotextile or geonet content shall be used at the Engineer’s discretion. | PS 25.9.2 | Site Records | Each Area |  | R | SE
18.05 | Grassing, Sowing and Turfing
| Preparation for sowing or turfing | Excessive compaction of subsoil in existing grassed areas shall be relieved to achieve satisfactory long-term growing conditions. All topsoil removed to permit contract works to be carried out shall be stockpiled for reuse. All new grass areas shall be built on soil prepared to industry best practice standards. Sloped areas shall be neatly contoured into adjoining grassed areas. Perennial weeds shall be controlled with industry best practice methods. | PS 25.10.1 | Site Records | Each Area |  | S | SE
| Fertilisers | Fertilisers shall be lightly arrowed into the topsoil, 2-3 days prior to seed sowing, at the following rates at 200kg/ha. This shall be followed one month after sowing, with an application of: Di-ammonium Phosphate (DAP) 100 kg/ha. | PS 25.10.2 | Site Records | 2-3 days prior to seed sowing and 1 month after sowing |  | S | SE
| Grass sowing | On large areas the seed shall be “check” sown in at least two directions and surface rolled with suitable flat roller. On small areas the grass seed shall be evenly applied and raked into the soil. | PS 25.10.3 | Site Records | Each Area |  | S | SE
| Establishment of sown areas | Newly established grass shall be protected from damage by pedestrian and vehicular traffic until grass has reached a self-sustaining state. Grassed areas shall be watered as required to achieve an efficient germination of the seed. Newly grassed areas shall be maintained with regular mowing (90mm-30mm) ensuring that all clippings are removed from adjacent hard surfaces. | PS 25.10.4 | Site Records | Each Area |  | S | SE
| Grassed areas adjacent hardscape | If base of grass level is 30mm lower or more than adjacent hardstand, grass will need to be removed min 1m back from path, soil put back in, levelled and re-consolidated to spec and grass res-own to correct level. If less than 30mm top dressing at 10mm each time, over time will be acceptable until the correct level is achieved. | PS 25.10.4 | Site Records | Each Area |  | S | SE
| Turf / Instant turf | Turf shall be installed and maintained in accordance with supplier’s requirements. | PS 25.10.5 | Site Records | Each Area |  | S | SE
| Slope areas | In all sites, except natural gully systems, where the slope gradient is steeper than 1:3 (one metre high by three metres long), it is preferable that the embankment is either scarified or grooved on an angle to a depth of 200mm, from the top of the bank to the base. This assists topsoil adhesion and prevents separation of the top 150mm topsoil from the base material due to gravity and/or glazed/planning of base material. | PS 25.10.6 | Site Records | Each Area |  | S | SE
18.06 | Fencing
| Seven Wire Fencing Order | The Contractor is to liaise with the property owner to establish the preferred spacing and order of the seven wires. | PS 25.12.2 | Comms | Prior to Installation |  | R | PE
| Post and Wire Fencing Installation | New seven wire standard boundary fence shall be erected with the following Offset tolerances 0.0m towards the centreline and 0.0m to 0.3m away from the centreline. The fence shall be vertical, and the grade shall generally follow the contour of the ground. | PS 25.12.2 | Survey Records | Each Fence |  | I | SV

## Commissioning
Commissioning Inspection and Test Plan
Project: SH1/29 Intersection Upgrade
Number and Revision: - 105 - Rev A
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Testing Quantity Required | Verification Activity |  | Downer Conformance of Compliance Signoff
[7 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details | ENGINEERS COMMENTS - Date: | DOWNER RESPONSE - Date:
SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
3.01 | General
3.01.01 | Precondition Surveys | A precondition survey of Waka Kotahi and other public / private assets within the extent of the Site and immediately beyond the outside area of the construction activities shall be undertaken in conjunction with the Engineer prior to the Contractor taking possession of the Site. | PS 2.13 | Precondition Survey | Prior to the Contractor taking possession of the Site. |  | H | PM
SECTION 19 – COMMISSIONING
19.01 | Road Opening
19.01.01 | Pre-Opening Safety Review | Prior to opening the Works for use by the general travelling public, a pre-opening safety review will be undertaken by the Engineer and the Principal’s Road Safety Audit team, to approve the removal of any temporary works, speed limits and traffic management. | PS 7.5.1 | Report | Prior to opening the Works for use |  | HP | ENG
19.01.02 | Post Construction Safety Audit | Prior to the issue of Practical Completion, a post construction safety audit must be completed by the Engineer and the Principal’s Road Safety Audit team. | PS 7.5.2 | Report | Prior to the issue of Practical Completion |  | HP | ENG