## Sheet1
SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
3.01 | General
3.01.01 | Precondition Surveys | A precondition survey of Waka Kotahi and other public / private assets within the extent of the Site and immediately beyond the outside area of the construction activities shall be undertaken in conjunction with the Engineer prior to the Contractor taking possession of the Site. | PS 2.13 | Precondition Survey | Prior to the Contractor taking possession of the Site. | H | PM
SECTION 15 – CONSTRUCTION ACTIVITY – STREETLIGHTING
15.01 | Streetlighting Quality Assurance plan
| Streetlighting Quality Assurance plan | Provide a Quality Assurance plan to propose, establish, maintain, monitor and document a quality assurance system covering all aspects of the procurement, fabrication, installation and completion of the works. | PS 22.4.6 | Streetlighting QA Plan | Prior to Streetlighting | HP | ENG | Plan and ITP top be developed by Subcontractor