## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned | 0662e4dc-3578-4d72-b1c6-e7d0bb098472 |  | checklist | ITP 006 FF&E Installation |  |  |  |  | Yes | ITP 006 FF&E Installation | 1cc56100-b0b4-489b-b85b-b25e1ddd0818
checkpoint-group | 967d1a14-ff44-48fa-a521-cd4fccbef38f |  | section | Materials
checkpoint-status | be404213-4fdd-4e87-9a98-1fb0a6b36d22 |  | checkpoint | Materials Inspected upon delivery
label | 8594033d-3b9d-54ad-95cb-ea5200045165 |  | note | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | b008b84d-5f54-51d8-8af2-88fcca8bfba6 |  | note | Buildup Inspection Code: W
label | c6cfeec6-7022-5433-a8e7-5bdd2a3b5de6 |  | note | Lendlease Inspection Code:
label | d8b415e9-6f20-5809-9af7-c6adfad817bb |  | note | Lendlease Sign/Date:
label | 49361d50-5e91-5692-a60d-a3178d6e4784 |  | note | Lendlease Comment/Result:
checkpoint-group | 19d99dc6-0ab4-452e-af84-96ab88136eef |  | section | FFE Installation
checkpoint-status | bd4fe732-16cf-4f82-898a-a4b1efd81aa1 |  | checkpoint | All of FFE Products must approved by Lendlease
label | e2d6021d-d9b3-501a-b79d-770cbc7174a0 |  | note | Acceptance Criteria: Sample Form Approval Finish Schedule
label | 820bdf0a-dac5-52b5-84db-0c92b0781ecb |  | note | References:Series: BR3ADL2-Internal Architectural Details
label | cd62cfaf-f876-5c23-b2ad-cf9e9ba41a54 |  | note | Buildup Inspection Code: H
label | 155d5876-02f6-5045-902a-c9f6f4e1f326 |  | note | Lendlease Inspection Code:
label | 55260e9a-909d-55e7-82d3-e8d246011a09 |  | note | Lendlease Sign/Date:
label | 3cb1a928-d378-5cd8-b589-bc7b0538e3ed |  | note | Lendlease Comment/Result:
checkpoint-status | 54a14b4d-124b-4b90-87af-3bebd7721c7a |  | checkpoint | All of FFE products have to supported by Noggins
label | 90dbc15b-bec5-5aa5-9126-026ce0196acf |  | note | Acceptance Criteria: Noggin Markup Plan
label | 27314926-1861-500b-8537-64a7254b8c74 |  | note | Buildup Inspection Code: W
label | 562390f3-9d38-56e9-87e4-23fde949e835 |  | note | Lendlease Inspection Code:
label | d8a3e702-5cca-56f2-ac3d-4dfaedb94bb2 |  | note | Lendlease Sign/Date:
label | 191d3203-e503-5a7a-8efd-6f06bca88a37 |  | note | Lendlease Comment/Result:
checkpoint-status | 7496e263-dd5a-48e5-a5fd-8a061dbaa7c7 |  | checkpoint | No unreasonable gap or holes on the wall
label | 976230dc-38cd-5308-87a0-0de384eac634 |  | note | Acceptance Criteria: Eye Inspection
label | f9b3fd73-6f0a-5847-804c-8441c0447825 |  | note | Buildup Inspection Code: W
label | 3aa80999-b45d-50e8-ab8b-8483a061a60d |  | note | Lendlease Inspection Code:
label | 61d9fc03-0c3f-5485-b37e-c81e57d500ec |  | note | Lendlease Sign/Date:
label | 531d33d5-f82a-572c-a388-54741c728da1 |  | note | Lendlease Comment/Result:
checkpoint-status | 4dc57913-bdde-4c80-bcdc-9fef364b2bf4 |  | checkpoint | Height and location must follow the requirement
label | bec8f3b7-c7c7-5253-8f9b-7e7ea08f2c1f |  | note | Acceptance Criteria: Noggin Markup Plan
label | 67758e48-8d9b-580f-af75-608a909b7714 |  | note | References: Series: BR3ADL2-Internal Architectural Details
label | b45cce7c-550a-594b-8c74-a41c02ab85cc |  | note | Buildup Inspection Code: W
label | cde0cfd5-cfec-5a48-a9d7-89266c6bb7ec |  | note | Lendlease Inspection Code:
label | 46114b2c-4ce4-5156-a3f1-1c0281192c7c |  | note | Lendlease Sign/Date:
label | 8ed943d3-1ce6-5f73-8148-f431eff5ca8d |  | note | Lendlease Comment/Result:
checkpoint-status | 9de05d25-e213-4f67-9925-06a9859fbbbb |  | checkpoint | FFE installation should not affect the wall finish. The wall with good patching as well
label | 1f54c4df-223c-5191-9830-94a774840d33 |  | note | Acceptance Criteria: Eye Inspection
label | 2c9e0dd0-6fac-53ae-878d-96548b524cca |  | note | Buildup Inspection Code: H
label | 43afa790-2100-5387-bba2-4beae3d04006 |  | note | Lendlease Inspection Code:
label | 831ec162-af86-58ba-9c5e-2ccba8086a53 |  | note | Lendlease Sign/Date:
label | 708a7739-832d-56f2-b46a-674f9f8dc3e4 |  | note | Lendlease Comment/Result:
checklist-sectioned | 1140dc7e-0c75-45aa-908a-11f5d983b388 |  | checklist | ITP 005 Installation of Ceiling System |  |  |  |  | Yes | ITP 005 Installation of Ceiling System | 5aeabc3e-f84a-403e-abaa-398f6c449fa5
checkpoint-group | 21fb093d-3ac5-40c6-93cb-0aee5f9ab29e |  | section | Ceiling Framing
checkpoint-status | 624f664a-6317-4155-aa8f-b75f9cbced91 |  | checkpoint | Materials Inspected upon delivery
label | d169be91-162c-54fc-927e-4622f38b33cc |  | note | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | 595cfa26-5574-560f-ad68-9c15dd979d98 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008
label | 86e9589f-c96c-501d-9bd8-bd56f6643bb6 |  | note | Buildup Inspection Code: W
label | 924ea309-fc49-50d1-9d80-46a780407f13 |  | note | Lendlease Inspection Code:
label | 49da8f48-b972-5144-b5a9-b0272ccb08b3 |  | note | Lendlease Sign/Date:
label | b4b2a354-8dad-58f3-b300-fdd51bc74257 |  | note | Lendlease Comment/Result:
checkpoint-status | 8711f35e-dee3-4665-bf4c-57661a17e283 |  | checkpoint | Ceiling framing dimension and FCL checked against drawings and Setout, Ceiling types confirmed against RCPs
label | c7cdd076-0d08-549a-9111-2a78bc3f2482 |  | note | Acceptance Criteria: Latest Drawing Revision Checked
label | e2bf6ef3-2435-5e7b-bb31-637ec3de6385 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008; Series: BR3ADG1-Reflected Ceiling Plans
label | 34ffcdde-499a-52e5-976a-f6cfb732c9f7 |  | note | Buildup Inspection Code: W
label | e28d2d54-49e8-5267-bc7c-1e1a3c60b2ea |  | note | Lendlease Inspection Code:
label | 8f4f06e5-a380-5707-870d-d836e0c3b048 |  | note | Lendlease Sign/Date:
label | fc44e82c-3017-56b7-8873-123620efe802 |  | note | Lendlease Comment/Result:
checkpoint-status | 50b52a7e-9fd5-441c-bfc5-f5d193000ab4 |  | checkpoint | All above-ceiling services are installed and ready for ceiling framing
label | 089730c5-b3b4-5d59-b704-74432f5db4f5 |  | note | Acceptance Criteria: Confirm with Lendlease that all wall service rough ins have been completed and approved prior to sheeting
label | 093c0b13-e4dd-5e4a-9bb0-6c6fb91f2ac7 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008
label | e7afce05-d721-5a8b-a2aa-1890b1c25886 |  | note | Buildup Inspection Code: W
label | 473a7e08-a3fe-592a-9d3f-0a9672f13543 |  | note | Lendlease Inspection Code:
label | 173291ce-237a-5f88-873e-d44f5093f520 |  | note | Lendlease Sign/Date:
label | aec02a45-1d86-54c0-bb74-4c5522e3e093 |  | note | Lendlease Comment/Result:
checkpoint-status | 8bcfea76-db27-47ec-b59d-794eb5008948 |  | checkpoint | Ceiling framing completed as Rondo designs
label | 8d2cce50-ed7c-5c89-9d34-114e0abb8678 |  | note | Acceptance Criteria: Suspending point max 1200mm*1200mm Grid, TCR @max 600 space and max200 from wall, FC @max 600 space and max 100 from wall. Correctly braced. Two sides fixed and two sides free
label | 720f02f4-9d8f-59b6-806c-0c3bfa716973 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;KEY-LOCK Suspended Seismic Ceiling Specification
label | bd28102c-4a28-5a40-aeb0-14d8a1192489 |  | note | Buildup Inspection Code: W
label | 9c77d530-c120-53c5-9d1c-d477b3d6ecda |  | note | Lendlease Inspection Code:
label | 7cceab80-a269-583b-a0a2-818ec0aa1a7f |  | note | Lendlease Sign/Date:
label | 535b33ba-57fe-5c0b-bb57-5a293dae3293 |  | note | Lendlease Comment/Result:
checkpoint-status | 0cd729d2-7232-4411-96ee-9db39fd0e88f |  | checkpoint | Bulkhead and Bracing completed as Kanuf designs
label | 55380391-9c35-5f52-bf08-b18882f75f6a |  | note | Acceptance Criteria: Anchor used with Load sharing washer
label | 6dc1af68-6197-5467-8fc6-abcc6f37ff6b |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;KEY-LOCK Suspended Seismic Ceiling Specification
label | cd294cf5-419d-53a5-83bb-074017ecf59c |  | note | Buildup Inspection Code: W
label | 6500a00f-7995-5972-beed-920c0ec9ac55 |  | note | Lendlease Inspection Code:
label | 3f2e473a-fa28-5716-868e-4c1c1fa4a9e7 |  | note | Lendlease Sign/Date:
label | 39cfba15-d6e4-53b3-a0f9-c2e5ae6c1071 |  | note | Lendlease Comment/Result:
checkpoint-status | bfbb01e9-141d-4fc2-a2b9-7232d6caf560 |  | checkpoint | Allowance for access panels and service penetration (Lights and Grill)
label | 4d7633c3-51cf-5f06-a455-d66152017035 |  | note | Acceptance Criteria: Framing not in the way of services or AP
label | a3ddc1ab-19a3-518f-aee6-562032bf07df |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Coordinated RCP drawing series
label | 8ad31283-955c-5f25-aca4-1b93af0b89f3 |  | note | Buildup Inspection Code: W
label | f4867643-e019-5a61-bb14-c28e7bc08921 |  | note | Lendlease Inspection Code:
label | 6f529be0-8468-5374-93ad-65de8010ad56 |  | note | Lendlease Sign/Date:
label | 65354005-8887-560a-9991-30bb7c634796 |  | note | Lendlease Comment/Result:
checkpoint-status | ea3e8620-b6e4-44ed-9e04-92c606386842 |  | checkpoint | Timber Noggins and Ceiling support installed as required
label | 5ddcc72c-642c-558b-b618-7287602f40e1 |  | note | Acceptance Criteria: Reference that set out of noggins to be checked against Room Layout sheet Elevations
label | 6458629b-7c82-5cf3-8cc0-e53a26e71fa1 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008
label | aad87553-ce90-53ab-9751-4bcd97395f3b |  | note | Buildup Inspection Code: H
label | 9b46cfe0-94eb-5eff-9be8-33215b263ea9 |  | note | Lendlease Inspection Code:
label | 956914be-4b30-5e12-b436-3cc8aaa51d50 |  | note | Lendlease Sign/Date:
label | 18fa6a7b-adb7-5460-9a40-7bc123fc03b4 |  | note | Lendlease Comment/Result:
checkpoint-group | 4c8742ac-a4c3-40eb-9f06-7f15a0b7bd52 |  | section | Close Ceiling
checkpoint-status | 445ce822-311d-45fc-9e3c-56b4bf73d301 |  | checkpoint | Materials Inspected upon delivery
label | 632436cf-48b0-571e-9950-40a18ed97751 |  | note | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | 0f840803-6c51-5235-b004-d798931e9e07 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008
label | d12b9516-42c2-5cb2-9883-7eb86442c7c3 |  | note | Buildup Inspection Code: W
label | 8553cfb1-f0b1-5659-9a49-15563cce2cb6 |  | note | Lendlease Inspection Code:
label | 2e8ac0d9-9ce9-5cbe-92c1-6a826011bcaf |  | note | Lendlease Sign/Date:
label | 74b722ae-526f-5035-b965-6282535b56ce |  | note | Lendlease Comment/Result:
checkpoint-status | b7e59912-9a00-4a39-bbeb-19d5e4aabc87 |  | checkpoint | Check all services roughed in and not using ceiling frame as a support, all seismic supports have been installed for service by others, ceiling closeout checklist received by Lendlease
label | b57ae913-6eb9-57fe-947b-ab025aa92277 |  | note | Acceptance Criteria: Minimum 3mm gap kept from ceiling frame
label | 360fa374-3273-5b20-986d-fa1818e59e60 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;KEY-LOCK Suspended Seismic Ceiling Specification
label | c0189afa-7c9f-5735-bb2c-9628d5538458 |  | note | Buildup Inspection Code:H
label | 43df43ad-653c-509f-a19d-fba657358440 |  | note | Lendlease Inspection Code:
label | d877d1bb-d507-5be1-bc30-75e2f99a38b5 |  | note | Lendlease Sign/Date:
label | 78a19513-e967-5f28-957a-20340ad033db |  | note | Lendlease Comment/Result:
checkpoint-status | e2a13fdf-b9a0-4f2a-96ed-615770fb57d6 |  | checkpoint | Installation of acoustic insulation to the ceiling
label | 54b21481-d5cf-574e-aae5-9f16414be3e6 |  | note | Acceptance Criteria: acoustic insulation must extend 900mm from acoustic wall
label | 457d8eda-fbce-5dc0-890d-037e09ea30cc |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008; Series: BR3ADS2-Insulation Ceiling Plans
label | 224a78b0-bc29-5636-aed8-476b40b5dd69 |  | note | Buildup Inspection Code: W
label | 36d6e665-78cf-5224-bf55-3b5087a09c9b |  | note | Lendlease Inspection Code:
label | fdb61bd0-d3a0-5f4f-aafc-2be6a3b9f71e |  | note | Lendlease Sign/Date:
label | a0283e97-458d-54ca-96df-1b69ad48df7c |  | note | Lendlease Comment/Result:
checkpoint-status | 3f7831b7-1ff4-4452-82e6-79e6be28699e |  | checkpoint | Sheeting carried as per manufacturer’s specification, specified sheeting as per schedule. Ensuring correct layering and components and completed fixing as pec
label | 64d11d66-a94c-5e5f-950b-19cb424ce56c |  | note | Acceptance Criteria: Staged Fixing @200mm max centre at edges, fixing @300mm max centre in field, Staged butt joint by 600mm min. Back blocking battens used on butt joints
label | b0b10bfc-950a-54ce-8dbc-994869710175 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;BCA Report 210721: 1740 R1.0
label | adefeb91-4412-5ca4-86a0-00a3cd059bb2 |  | note | Buildup Inspection Code: W
label | 0aaa3027-f55f-5c0c-928f-e15aea82c648 |  | note | Lendlease Inspection Code:
label | 674a3f18-e2c7-567d-bd68-0572989c943f |  | note | Lendlease Sign/Date:
label | 54d2817c-b6e4-53a6-97f0-5182ef04f0da |  | note | Lendlease Comment/Result:
checkpoint-status | 4daa70aa-e057-48a8-94b1-dd985d36d492 |  | checkpoint | Access panel installed as required
label | 1e8ecbce-0062-5411-a886-98551ec6fcab |  | note | Acceptance Criteria: Correct location, square with wall or bulkhead
label | e50d5abc-9669-5ea9-b746-075fc67e9eca |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;BCA Report 210721: 1740 R1.0
label | 9a6eaaf7-b52d-5ea5-9563-2d8ce5a17315 |  | note | Buildup Inspection Code: W
label | 5c0f4255-868d-5c3f-96ce-c15de458b458 |  | note | Lendlease Inspection Code:
label | 813b47ae-b6e5-578c-9513-91d153075bbf |  | note | Lendlease Sign/Date:
label | e782be04-9900-54a8-8e59-4d77d7b2e8dd |  | note | Lendlease Comment/Result:
checkpoint-status | c9328cde-aede-4f78-9982-a34c98fe423f |  | checkpoint | Caulking to acoustic / fire / smoke/ details.
label | 55948492-b8b5-5db8-bd6a-083f34573030 |  | note | Acceptance Criteria: Max 20mm with slab/ column, flush
label | 56a2ebda-d71e-59e6-9756-25274edc7335 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;BCA Report 210721: 1740 R1.0
label | 330b1047-6274-5a83-8f33-99635b1d061e |  | note | Buildup Inspection Code: W
label | 810e23b5-0411-5abe-9bfb-f2fa2533f973 |  | note | Lendlease Inspection Code:
label | 20700f55-08fb-5baf-b967-b1dff6945f52 |  | note | Lendlease Sign/Date:
label | 326ee572-76ef-56aa-a19f-78dd76ed23c6 |  | note | Lendlease Comment/Result:
checkpoint-status | 658b9df2-a18e-4403-8102-0a4f86780853 |  | checkpoint | Set and sand ready for painting
label | 8fec81c7-bac4-5594-8774-4601af29804c |  | note | Acceptance Criteria: No bubbles, no lump, square, not over sanded
label | de7e8416-59b4-56ba-a30e-09b13ab58c90 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;BCA Report 210721: 1740 R1.0
label | 0243983e-ab9c-540a-a2a8-1898c8d901bb |  | note | Buildup Inspection Code: H
label | 4fe66785-10f4-55d9-ad51-18cf27b7966c |  | note | Lendlease Inspection Code:
label | 6c098e94-71f5-5f1b-bcbb-69441720df49 |  | note | Lendlease Sign/Date:
label | de0533ca-2975-5038-aef7-3021ad5e4e33 |  | note | Lendlease Comment/Result:
checkpoint-status | 6582a334-6d72-4c1b-948d-530074448a58 |  | checkpoint | COMPREHENSIVE FIRST-OF-TYPE INSPECTION
label | d7eac971-fb77-559f-be9a-0e0402d17d1e |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Siniat&Rondo Inspection
label | 0967d9a2-f668-5473-80cb-91e9556d7503 |  | note | Buildup Inspection Code: H
label | 676b0886-63a9-50ba-9648-0f0a50d4778b |  | note | Lendlease Inspection Code:
label | 6065fee6-8714-5143-9b43-b4a48eb8d2de |  | note | Lendlease Sign/Date:
label | c03bc23b-9bec-5d87-ba66-3a5d8c7c8f1b |  | note | Lendlease Comment/Result:
checklist-flat | ccc83a11-22e9-4f6f-98cb-0405ebc32db4 |  | checklist | ITP 001 Speed Panel |  |  |  |  | Yes | ITP 001 Speed Panel | 5f0857f6-12cf-442b-83a9-c8de8b3b9ee0
checkpoint-status | 677689cb-4630-47f2-bac1-7b13eb4ab668 |  | checkpoint | Materials Inspected upon delivery
label | af90810d-2ad5-5597-82d1-41d177f0d380 |  | note | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | f23b8c9c-d1d6-546d-a86e-144b3577dfd5 |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4
label | 386ec293-a5ed-571c-a8b3-eeada093100d |  | note | Buildup Inspection Code: W
label | ba8ff93b-b701-57df-b68d-2c29c31960c6 |  | note | Lendlease Inspection Code:
label | c58a2e94-8c33-5864-88de-ce7db6bafce6 |  | note | Lendlease Sign/Date:
label | b06f4bb4-d19d-54a0-8a62-fe1911264158 |  | note | Lendlease Comment/Result:
checkpoint-status | d550f32d-6834-45fe-98ac-3a8b8486aeb3 |  | checkpoint | Wall dimension checked against drawings & setout; Wall types confirmed against partition plans
label | b5ddcf37-b8c5-5957-81b6-efde6f7a00f5 |  | note | Acceptance Criteria: Latest drawing revision checked
label | a86fb133-faf1-547d-ad96-0b061e0b89ea |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Series BR3ADB2 -; Wall Setout Plans BR3ADF3 - Fire Stairs
label | dfa62c34-209b-5696-abdc-e7b2267c7903 |  | note | Buildup Inspection Code: W
label | 1926ca74-5649-5b9b-9189-cd4c140d9d75 |  | note | Lendlease Inspection Code:
label | 83649bac-caa2-52e7-beb7-be2fffc33090 |  | note | Lendlease Sign/Date:
label | 48b4d902-29e6-5873-ac9d-bde523feca1a |  | note | Lendlease Comment/Result:
checkpoint-status | 45c68cb6-ac52-4810-bc65-6eceedba1a37 |  | checkpoint | C-Track installed as manufacturer's specification to top, bottom and both sides
label | 3fd5d466-9f28-5835-bdb8-95d1d3b55d55 |  | note | Acceptance Criteria: Hilti 606 Sealant applied between C-track and concrete and along internal corner. Anchor @500 Centre & max 100 from end
label | ff6d491d-2827-5482-808d-207df6340888 |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | 5ee5db57-8946-529f-9a15-760d40b10b86 |  | note | Buildup Inspection Code: W
label | 9593849a-d975-5a73-a0ba-adef96ebbe76 |  | note | Lendlease Inspection Code:
label | 0ee6b35c-64b0-5642-966a-7357081ff6fa |  | note | Lendlease Sign/Date:
label | 71d3f216-08af-5f7e-94b6-467a5dc79bb0 |  | note | Lendlease Comment/Result:
checkpoint-status | ead99cfb-de5e-460b-a4f0-4c15b5935116 |  | checkpoint | Panels installed as manufacturer's specifications
label | f689bb5c-520e-5754-b739-c8f0d9d2a4ed |  | note | Acceptance Criteria: Each panel interlocked, fixing @ max vertically 1000mm centre on joints and 250 mm horizontally, fixing @ max 500mm on C-track, 2 fixings at 45" for every corner. Sealant full placed around C-track
label | 9652a842-4019-5e5e-81d9-070e6b904622 |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | 71402a69-57ba-57e0-9e1b-df46ea39a75a |  | note | Buildup Inspection Code: W
label | 3609a4b5-b343-5734-8fb5-7284ba8f3ece |  | note | Lendlease Inspection Code:
label | 3f0034cd-2300-5e4c-a1e4-e027b4d53187 |  | note | Lendlease Sign/Date:
label | 91536da0-4db8-5d41-a071-496e3b5a69e4 |  | note | Lendlease Comment/Result:
checkpoint-status | 0661530e-5548-47be-9ba0-1ad4688b79c5 |  | checkpoint | Comprehensive first of type inspection
label | 76b8c9d9-871f-5d5e-8a0c-12e3f2fdca8d |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4; Supplier / Manufacturer inspection report
label | 8b60c65e-db23-5106-bfa0-140a7e55f9a5 |  | note | Buildup Inspection Code: H
label | ce9a71ad-cb1d-5982-a481-7a1d59ce4d36 |  | note | Lendlease Inspection Code:
label | ac53a3a5-617c-54e9-866f-f84ecb7557a0 |  | note | Lendlease Sign/Date:
label | 68855a6e-7322-5572-8c80-071019e2d517 |  | note | Lendlease Comment/Result:
checklist-sectioned | 67f7d821-d997-4428-87ec-d8fdbf284268 |  | checklist | ITP 002 Installation of Soffit Insulation |  |  |  |  | Yes | ITP 002 Installation of Soffit Insulation | 6fbca39f-884f-4857-a922-b02acc521aab
checkpoint-group | 697cd8df-58b6-4e8a-bec8-6a922249a2c6 |  | section | Materials delivery
checkpoint-status | 7b373018-2a79-42bb-9c44-ea187fc9f113 |  | checkpoint | Materials Inspected upon delivery
label | d4cf8c77-c19b-5b56-ba2a-aec7b7f8bddf |  | note | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | 3dd7c8cf-48be-5de8-bbf5-3a97ff932248 |  | note | References: Australian Standards AS/NZS 4859.1 and AS 5637.1.
label | 2ee9a4b7-b0be-54b6-b480-1c358759696b |  | note | Buildup Inspection Code: W
label | 6160043e-e198-51d6-9087-b84d395d3522 |  | note | Lendlease Inspection Code:
label | 5ec602d6-5225-5112-9eda-977d00bfbd9e |  | note | Lendlease Sign/Date:
label | 5157a0a0-ef44-50e6-be1e-abb6fa181dc2 |  | note | Lendlease Comment/Result:
checkpoint-group | 7fbe0649-b0ed-4c04-b61b-fd96b98d1218 |  | section | Under Slab Insulation
checkpoint-status | 6de7e6e7-d4cf-4dc7-9db4-48bab9d82d14 |  | checkpoint | Insulation dimension checked against drawings and Setout; Insulation types confirmed against Insulation set out plans
label | cb4ecc21-c9c2-5897-9ca3-239d5973befc |  | note | Acceptance Criteria: Latest drawing revision checked
label | fd00029c-cb43-53b0-af6d-3c2e3bae6478 |  | note | References: Australian Standards AS/NZS 4859.1 and AS 5637.1;Series: BR3ADS2-Insulation Ceiling Plans
label | a24631ea-3241-52fa-8ad3-062138a8c06e |  | note | Buildup Inspection Code: W
label | 9c4d113b-55af-5a73-a286-755040c141dd |  | note | Lendlease Inspection Code:
label | 9b9534c3-e55f-5b16-a995-e33e2cac66fc |  | note | Lendlease Sign/Date:
label | bd88b231-3539-5720-8241-45800378eafc |  | note | Lendlease Comment/Result:
checkpoint-status | 9dd715f7-6669-4939-b0a2-a4dc494b77a8 |  | checkpoint | The foil surface of the insulation board should face down
label | 5244f4aa-4c3e-54c7-b010-8861be900e78 |  | note | Acceptance Criteria: Inspected and confirmed
label | 2befcf4d-cdb1-5b57-82bd-1af1f9330ca7 |  | note | References: Australian Standards AS/NZS 4859.1 and AS 5637.1;Australian Insulation Manufacturers Group – Prime Panel Soffit Insulation Installation Guide
label | 27f864c8-1b1f-508c-9609-9003dd3a723a |  | note | Buildup Inspection Code: W
label | 155620ee-2d58-50ab-a137-77f6f1f8dc19 |  | note | Lendlease Inspection Code:
label | b67f298a-b023-5a47-942c-d78b90e7edb3 |  | note | Lendlease Sign/Date:
label | 1b40282b-414c-5a31-bfbb-4bf94ac40877 |  | note | Lendlease Comment/Result:
checkpoint-status | 3d061461-4795-4b99-9e71-f09667624739 |  | checkpoint | Fix insulation panel to concrete soffits with minimum 5 No. Appropriate insulation fasteners with a minimum head diameter of 35 mm
label | db70d058-144f-5224-8748-bcf48df0eb34 |  | note | Acceptance Criteria: Inspected and confirmed
label | d14d798f-6ea8-54c3-bb59-73866c2472e9 |  | note | References: Australian Standards AS/NZS 4859.1 and AS 5637.1;Australian Insulation Manufacturers Group – Prime Panel Soffit Insulation Installation Guide
label | 7997086a-d455-575d-9c48-6b295cdda3dd |  | note | Buildup Inspection Code: W
label | a240e825-33aa-5923-a4d5-db66c6134eb8 |  | note | Lendlease Inspection Code:
label | a6151afe-eb38-5591-9b7e-d77b09f9f7df |  | note | Lendlease Sign/Date:
label | d9a3db50-5a47-5d5c-afa0-a74eed5abb57 |  | note | Lendlease Comment/Result:
checkpoint-status | 410ae3af-44c5-4d7d-a7d0-f7e13c755c16 |  | checkpoint | Tape board joints with a minimum 96mm wide appropriate aluminium foil tape, detail as per attached Installation Instructions
label | 76a8190d-a749-5885-a29e-6cba929da54c |  | note | Acceptance Criteria: Inspected and confirmed
label | 2de437b3-0f43-5e8c-937e-35e46872ba00 |  | note | References: Australian Standards AS/NZS 4859.1 and AS 5637.1;Australian Insulation Manufacturers Group – Prime Panel Soffit Insulation Installation Guide
label | 4b81b8a3-42ea-55a5-995f-be2fbd653bf1 |  | note | Buildup Inspection Code: H
label | 207353f5-49af-52c3-a53f-6298a1a1a32f |  | note | Lendlease Inspection Code:
label | 34f008c4-0ec1-5799-82ea-9a4e340d43cf |  | note | Lendlease Sign/Date:
label | 3fa62860-a531-5ac7-84ad-6da15d1e09fc |  | note | Lendlease Comment/Result:
checkpoint-status | 38ff0e80-2d8b-492a-8bb9-dfcc2da19706 |  | checkpoint | Exposed board edge covered with foil tape lapped 48mm on to underside
label | 32f3b430-f213-5ff7-bd78-0054633f612b |  | note | Acceptance Criteria: Inspected and confirmed
label | 4cc4028f-7b4b-5296-a816-3cb6a077e584 |  | note | References: Australian Standards AS/NZS 4859.1 and AS 5637.1;Australian Insulation Manufacturers Group – Prime Panel Soffit Insulation Installation Guide
label | 4921ccbd-2afd-5d77-99b6-ac982653d4d3 |  | note | Buildup Inspection Code: H
label | d8c5c5ef-39f9-5694-80de-9e5d387e000d |  | note | Lendlease Inspection Code:
label | 0d68a89c-cdd1-5f9f-9e42-85ad4aab9445 |  | note | Lendlease Sign/Date:
label | 2f7c6744-6a64-5df1-8428-bd14877f1067 |  | note | Lendlease Comment/Result:
checkpoint-status | 0e95d734-1875-4de6-85b5-dd43b2f1c8e6 |  | checkpoint | Check against cast-in penetrations. All penetrations/collars/dampers to be fully exposed
label | dd2b48ba-132e-5170-9d37-d9bfa1e60a5f |  | note | Acceptance Criteria: Inspected and confirmed
label | 65182e93-ac24-5af7-8b9b-19b77ff8e2ff |  | note | References: Australian Standards AS/NZS 4859.1 and AS 5637.1;Australian Insulation Manufacturers Group – Prime Panel Soffit Insulation Installation Guide
label | 6a410a9d-8865-58c8-8a47-65f9240edf96 |  | note | Buildup Inspection Code: H
label | a1225369-08fe-56ac-9230-0f5ae753bdf7 |  | note | Lendlease Inspection Code:
label | 7a51aa69-f187-538f-b100-724e7133e6cf |  | note | Lendlease Sign/Date:
label | 6adcd8c2-c441-51d0-9b86-443ce62a3548 |  | note | Lendlease Comment/Result:
checklist-flat | 4ce92a5e-d4f5-49fe-b7a5-4bb682454544 |  | checklist | ITP 001b Speed Panel |  |  |  |  | Yes | ITP 001b Speed Panel | 7abe3302-7e56-4750-afff-a1e0fe30cce1
checkpoint-status | bd5749a9-b1db-4660-a443-79ceba726d07 |  | checkpoint | Materials Inspected upon delivery
label | 1df34246-acdb-5ca4-8415-05da09ccc21b |  | note | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | 6c1c091b-2f36-5212-9fff-e62e871d7234 |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4
label | ff710fdb-a8f5-53ff-ade3-a59caa700d46 |  | note | Buildup Inspection Code: W
label | b8332c18-060a-51ff-83c7-2e1678bee06f |  | note | Lendlease Inspection Code:
label | 3bab6f10-a7a1-53e1-9f4b-4e3d7a941580 |  | note | Lendlease Sign/Date:
label | 61e46ef4-a319-5dbd-a24c-ad0eb638a792 |  | note | Lendlease Comment/Result:
checkpoint-status | 74d9d107-2845-4145-be56-3d03b4062ee3 |  | checkpoint | Wall dimension checked against drawings & setout; Wall types confirmed against partition plans
label | a18b3252-1e4c-55e3-8181-65d5ea58b8f7 |  | note | Acceptance Criteria: Latest drawing revision checked
label | be98a9c6-10b5-5dcb-bad3-b6bb2bb83009 |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Series BR3ADB2 -; Wall Setout Plans BR3ADF3 - Fire Stairs
label | e3ea57cd-4901-5ade-91f9-d1ecf33a800f |  | note | Buildup Inspection Code: W
label | 6013b7ab-49a8-5e3d-b1d0-61ad6c8eb894 |  | note | Lendlease Inspection Code:
label | a53ca1a4-4729-5130-a34d-62ba0b5a2933 |  | note | Lendlease Sign/Date:
label | ba59b067-47b1-5528-9687-408f458c5c6f |  | note | Lendlease Comment/Result:
checkpoint-status | da2beccb-16de-4e9b-8d3c-f49b08f6e0f1 |  | checkpoint | C-Track installed as manufacturer's specification to top, bottom and both sides
label | 3a4e6373-94e8-5ccc-bb53-53c943d7d47c |  | note | Acceptance Criteria: Hilti 606 Sealant applied between C-track and concrete and along internal corner. Anchor @500 Centre & max 100 from end
label | 255a0bd1-84f8-5a8f-910a-3053ae84430b |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | d2c1d635-ba79-54b9-9bdb-8eddeaf96ec4 |  | note | Buildup Inspection Code: W
label | fbc9db1e-f4d7-5387-be2e-332c29510304 |  | note | Lendlease Inspection Code:
label | 655e9dd9-a033-58e4-a722-f71c4c1dad91 |  | note | Lendlease Sign/Date:
label | 14676fff-5b7f-55d2-9f43-3b855e0fae5a |  | note | Lendlease Comment/Result:
checkpoint-status | 17e32274-22c1-4ff8-b5a8-58576236836f |  | checkpoint | Panels installed as manufacturer's specifications
label | 56fa7902-4cad-518e-9feb-b6913c92a1c8 |  | note | Acceptance Criteria: Each panel interlocked, fixing @ max vertically 1000mm centre on joints and 250 mm horizontally, fixing @ max 500mm on C-track, 2 fixings at 45" for every corner. Sealant full placed around C-track
label | a8d8705c-0dc6-590d-a6d2-311d191f134e |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | cb4758e2-c48d-57fb-84c7-d45dd327592e |  | note | Buildup Inspection Code: W
label | b097b0f7-3a14-5999-b688-28f64c7f0576 |  | note | Lendlease Inspection Code:
label | faf20886-1492-5f4c-8ee3-bbfba30f7834 |  | note | Lendlease Sign/Date:
label | 0e3b221c-c29b-5d13-a080-c8d8411557ce |  | note | Lendlease Comment/Result:
checkpoint-status | eb0398dc-9cc6-4d23-bece-18af8912031b |  | checkpoint | Penetration cut, trimmed and sealed as per builder' drawings
label | 25eb0680-0869-57f0-b4e2-5bbbfca2e965 |  | note | Acceptance Criteria: Max 500mm centre fixing on C-track, 2*fixings on corner, fully sealed with Hilti 606
label | a6bc0c3d-54ec-5f0b-a17a-e48c9a43348a |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | 8a61830f-3bda-51ac-8815-ef2af02f7afd |  | note | Buildup Inspection Code: H
label | 4da29fb9-1dec-5beb-9ec5-ddcf1d2b85c1 |  | note | Lendlease Inspection Code:
label | a1ab724e-8aba-5adc-a4ba-5a900636e5d7 |  | note | Lendlease Sign/Date:
label | b42e69af-c4d4-5cf9-b6ad-26d4a66ae33a |  | note | Lendlease Comment/Result:
checkpoint-status | 0da811c7-2f13-4bba-ae71-fa4d1b5a2c54 |  | checkpoint | Door Frame installed as per manufacturer's specification
label | 1fb8e0e4-cdbc-5b1a-a6c5-a19cb41e2466 |  | note | Acceptance Criteria: Plumb, square and same height, core-filled
label | f4eccb82-847d-53a1-a76e-c6fc249b091a |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | c2d4f5ca-411b-5df4-8e39-1c402f509d90 |  | note | Buildup Inspection Code: H
label | a33722ef-4f5a-54c5-ac29-a063f64bb1a1 |  | note | Lendlease Inspection Code:
label | 1d49236e-749b-5afc-a4e7-79edd185b527 |  | note | Lendlease Sign/Date:
label | 08966104-a3dd-5720-a174-2e589be86f19 |  | note | Lendlease Comment/Result:
checkpoint-status | c5d33dbb-0b3d-4b78-9275-79ef2ed9508a |  | checkpoint | Flashing head-protection
label | d0105ad9-632d-5e10-aafe-02da6850da3d |  | note | Acceptance Criteria:Min 120mm deep, stagged fixing @max 250mm
label | 8e93fda9-ca9d-5652-93b0-3074e6e0798e |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | 9eb49773-a722-5a05-b8b2-ccae71f1b9cc |  | note | Buildup Inspection Code: W
label | 92ea38e9-330a-540d-9916-116ef68ab19d |  | note | Lendlease Inspection Code:
label | c0f738c4-1fb7-507b-acd6-658eb25ba3d1 |  | note | Lendlease Sign/Date:
label | e1c97b2c-a48c-535c-8d87-be8fceb8e5bb |  | note | Lendlease Comment/Result:
checkpoint-status | a9b1209e-f154-4abd-83da-02bfdfbbfa06 |  | checkpoint | Fully sealed joints one side in pressurized shaft
label | f203f650-b6cd-59a2-a2ab-15e7263b95bb |  | note | Acceptance Criteria: Continues beads
label | c7281c09-652d-5cec-a4d6-6522a62b92cd |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | dc66df6b-1ad2-5375-9121-a0890b086e8a |  | note | Buildup Inspection Code: H
label | 7673d390-afa9-5d11-ac53-9b069953cf8a |  | note | Lendlease Inspection Code: H
label | 9df03ea0-45d5-5f13-afe6-fa2e666a0e14 |  | note | Lendlease Sign/Date:
label | cd6fcb3a-e40a-5853-b035-1d048facbca8 |  | note | Lendlease Comment/Result:
checkpoint-status | d9f1df25-e42b-4627-abea-c097abd9d3fa |  | checkpoint | Comprehensive first of type inspection
label | d2f7f198-6e32-50e2-a4ac-3010deba8134 |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4; Supplier / Manufacturer inspection report
label | c60f0925-6afa-5495-92f9-6ec36668207e |  | note | Buildup Inspection Code: H
label | 026844a4-87c3-5726-a573-a088e1dbfe2b |  | note | Lendlease Inspection Code:
label | 67d6a1d4-665b-586e-b519-8ea8d48c8582 |  | note | Lendlease Sign/Date:
label | 024e1e41-70d3-5393-b1e7-7df94d0429da |  | note | Lendlease Comment/Result:
checklist-flat | 710d3a03-f1b6-417b-a302-c8d89da31991 |  | checklist | ITP 007 Skirting Installation |  |  |  |  | Yes | ITP 007 Skirting Installation | 9184cdb3-cd25-4791-9074-fdc1d03c5014
checkpoint-status | 850ac992-b49b-4120-b1fa-0a76bab18447 |  | checkpoint | Materials Inspected upon delivery
label | f7066f9a-ea40-556a-ad84-4d8fc01951e3 |  | note | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | 5aa939e9-6cd3-530c-a0ad-da4e55636d3d |  | note | Buildup Inspection Code: W
label | 4e3543fc-9935-5a08-8765-b9f2c6146278 |  | note | Lendlease Inspection Code:
label | 561a7ccf-abab-5796-a370-18f3a5364375 |  | note | Lendlease Sign/Date:
label | 5da442ae-c9ed-517e-9cbe-6880431ecc66 |  | note | Lendlease Comment/Result:
checkpoint-status | 9c5038b1-eac4-4437-9285-465515621ac5 |  | checkpoint | Set out Timber skirting size & type as per wall finish set out plan
label | e46e9452-5776-591a-8892-0fadbe07c72e |  | note | Acceptance Criteria: Latest Drawing Revision Checked
label | 849c2fc6-ab1d-58a8-b72c-47ffddabba8d |  | note | References:Series: BR3ADL2-Internal Architectural Details; BR3ADB2-Wall Setout Plans
label | bc58341c-13f2-5ba6-ab11-5f6140b44348 |  | note | Buildup Inspection Code: W
label | f56ffac7-3b0a-5507-aab3-bae5536b07fe |  | note | Lendlease Inspection Code:
label | 3c79bac5-7259-54a9-97bf-cba175fd4125 |  | note | Lendlease Sign/Date:
label | 04735fcd-e263-52bf-91c7-2894f554ef28 |  | note | Lendlease Comment/Result:
checkpoint-status | cc882852-ddd4-4db5-90bb-7d4705c8faff |  | checkpoint | Timber skirting installed as manufacturer's specification to Top, bottom side
label | 45194fdd-5bbf-5dfc-bc07-73becde2d375 |  | note | Acceptance Criteria: Straight and plumb and square, no sharp edge, gap less than 3mm, sealed with silicone Ref
label | 2483f54b-9d85-5506-a829-8dc261a6cc6a |  | note | Buildup Inspection Code: W
label | 5a9eb00d-936c-5f6a-aedf-312159a430be |  | note | Lendlease Inspection Code:
label | b401a607-d0a6-5921-9392-b4f1143e007a |  | note | Lendlease Sign/Date:
label | f6e6d773-11e8-5abb-861a-77bec3273b3d |  | note | Lendlease Comment/Result:
checkpoint-status | 5e323528-f76d-4821-8197-a8947348a86f |  | checkpoint | No unreasonable gap or holes on the wall
label | 5153e3a9-0e8d-5cf9-a67a-d02867f3a141 |  | note | Acceptance Criteria: Eye Inspection
label | 6fbf49e2-ac15-523c-92d7-e66f936df255 |  | note | Buildup Inspection Code: W
label | da714714-9dee-5662-ba1f-6e6dec17a81b |  | note | Lendlease Inspection Code:
label | 55528ce5-a091-5f4d-853e-778a4aabcc46 |  | note | Lendlease Sign/Date:
label | 31e17250-0111-5980-965b-c75e1edced36 |  | note | Lendlease Comment/Result:
checkpoint-status | 747c5f2a-b8f0-4fed-9d35-e0f55a3eb56a |  | checkpoint | Timber skirting fixing and inspect for damage prior to hand over
label | 5864fabe-87e0-588b-af37-4a2bc7b33bf1 |  | note | Acceptance Criteria: Inspected and approved
label | 97dfa76c-ed32-5782-a271-dc0894bfa39f |  | note | Buildup Inspection Code: H
label | 5f2187dc-a057-5db0-880d-4977432e4615 |  | note | Lendlease Inspection Code:
label | 11b528b4-098f-5626-aef7-f0819f59eb22 |  | note | Lendlease Sign/Date:
label | 5bfb2237-ee8a-5387-a483-758eff80c0fe |  | note | Lendlease Comment/Result:
checkpoint-status | d1813e1f-a16e-43bb-80af-f117f9c7bb0e |  | checkpoint | COMPREHENSIVE FIRST-OF-TYPE INSPECTION
label | a2e8d389-976e-54ae-bab0-96a14e78d478 |  | note | Buildup Inspection Code: H
label | 7552cc05-b1eb-5654-ae47-ee4016f7128f |  | note | Lendlease Inspection Code:
label | afd9fb3e-813e-54b9-88fc-c08e31c981d0 |  | note | Lendlease Sign/Date:
label | 5ac13735-7c36-553f-b88b-51c3037f9f5c |  | note | Lendlease Comment/Result:
checklist-sectioned | d69baf01-14fe-4ce4-933e-57128978fd44 |  | checklist | ITP 003 Installation of Internal Partitions |  |  |  |  | Yes | ITP 003 Installation of Internal Partitions | bc8a9d88-7b23-467c-8193-4e931356aa04
checkpoint-group | d00867e7-098d-4db0-b335-6b0d9e28e0d5 |  | section | Wall Framing
checkpoint-status | 6a114a1b-449a-4f87-8c92-d06fcea6e1a3 |  | checkpoint | Materials Inspected upon delivery
label | d9510775-4220-59cc-9de3-a8b424b328c4 |  | note | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | 7f98b4b2-3ed6-56f7-8b2c-a13ec5b55936 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008
label | fa16f93f-84a4-5488-a8de-4908e09c9871 |  | note | Buildup Inspection Code: W
label | 814d7722-2578-5761-9aec-c5db2eabaa06 |  | note | Lendlease Inspection Code:
label | f9944d84-940b-53cb-bd56-43bf45ab43fb |  | note | Lendlease Sign/Date:
label | e0380a2d-4c6e-5bf8-ab67-a585cc54785e |  | note | Lendlease Comment/Result:
checkpoint-status | 79dcffa5-65e2-49ee-a9c9-020c0b35c3b1 |  | checkpoint | Wall framing completed to Rondo designs, checked for square, plumb and twisting
label | d2617fba-2b81-5a0e-a3da-d960fd07f264 |  | note | Acceptance Criteria: slotted Deflection Track used; additional noggin installed for onside sheeting frame
label | d930c9b0-2c99-5152-b904-cc8fa304636e |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Internal partition designs: 10246-22001 SK00 - 1024622-001-SK15; Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | 1ee52ae4-3761-5b3b-ac39-a33cd1f51046 |  | note | Buildup Inspection Code: W
label | 7952244c-2ec6-5a8c-ad06-87f2d18d772e |  | note | Lendlease Inspection Code:
label | e022b4cc-602e-5079-a92d-d9490632d7cc |  | note | Lendlease Sign/Date:
label | 63ef4645-3597-549d-b9c2-2c24e094220e |  | note | Lendlease Comment/Result:
checkpoint-status | b7094f71-68f5-4b6d-ba12-4dfc9825eeaa |  | checkpoint | Allowance for access panels and service penetration
label | 3899078d-9330-52e7-8bb6-e0fa2f1edf4d |  | note | Acceptance Criteria: Bridging Track supported by offcut studs
label | 31eb79d2-af23-5aba-a891-0cbe17e56669 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Internal partition designs: 10246-22001 SK00 - 1024622-001-SK15; Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | ffe9f760-17b2-51fd-aacd-b05cb57ea4b0 |  | note | Buildup Inspection Code: W
label | 4ff21cc1-a2a8-5268-9252-61da7d9f96b6 |  | note | Lendlease Inspection Code:
label | e8b38c9b-08b0-586f-9d73-bc463a7444b3 |  | note | Lendlease Sign/Date:
label | b2d97e72-9a26-5d48-bca7-8b7dc04da1da |  | note | Lendlease Comment/Result:
checkpoint-status | 5548a1bf-a1c5-4600-badd-d721c359ac68 |  | checkpoint | Openings (Including doors, windows, removable parts) installed to correct position and height, with right opening towards, plumb and square, as per Rondo designs
label | c4100639-a7ff-5865-936a-76d0cf6ee44b |  | note | Acceptance Criteria: Jamb header or sill used correct components
label | 6e04e645-e452-504d-87fc-33bcd25e9392 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Internal partition designs: 10246-22001 SK00 - 1024622-001-SK15; Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | 7a14a3fa-dede-5b01-b7de-7ed5650a52be |  | note | Buildup Inspection Code: H
label | 6290a41f-ed3c-5939-be9b-4518701935e6 |  | note | Lendlease Inspection Code:
label | c74de6a1-2773-5440-9f22-0b4a77b0d27d |  | note | Lendlease Sign/Date:
label | a42478d3-38df-5339-869b-847907df4123 |  | note | Lendlease Comment/Result:
checkpoint-status | f0322517-8adf-4bd1-9428-b78aef91afee |  | checkpoint | Plywood Noggins and structural stud installed for all fixtures
label | f2bab960-711f-57f2-9245-52a0e39ab7a2 |  | note | Acceptance Criteria: Reference that set out of noggins to be checked against Room Layout sheet Elevations
label | bc5f52ce-7ec7-57fc-b825-34a8039ee582 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Internal partition designs: 10246-22001 SK00 - 1024622-001-SK15; Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | 0b28b17c-4464-5f43-bbcf-fc84eef3b6c7 |  | note | Buildup Inspection Code: W
label | 5cb87860-5029-59a1-af12-b8d9b0c26165 |  | note | Lendlease Inspection Code:
label | 0479c41e-c787-599d-9548-fcf9057f5756 |  | note | Lendlease Sign/Date:
label | 089057db-b147-5e72-afbe-6cd3c5830e3b |  | note | Lendlease Comment/Result:
checkpoint-status | bfac7ba6-a6f2-4b1a-a60c-688742bfea0d |  | checkpoint | Door and window Frame installed as per manufacturer's specification stud installed for all fixtures
label | d1428aa5-6d22-5398-a6c6-e4c6b7a320b2 |  | note | Acceptance Criteria: Plumb, square and same height, core-filled
label | e4928876-e6f1-5314-98c4-ed6cc718385e |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Internal partition designs: 10246-22001 SK00 - 1024622-001-SK15; Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | aff6fa0e-ecc3-5cac-8598-cfa339a7254a |  | note | Buildup Inspection Code: H
label | 7501fe87-0d7d-5f19-8920-b9d8652ff854 |  | note | Lendlease Inspection Code:
label | 7157c26c-1526-570b-8e1b-5ea82942f929 |  | note | Lendlease Sign/Date:
label | de213dbc-2cfe-559e-a372-03cffa4a6b06 |  | note | Lendlease Comment/Result:
checkpoint-group | 342a4f3a-5746-4f22-80e4-25dd23eb59d6 |  | section | Wall Sheeting
checkpoint-status | c49e9126-6ad7-4ad9-8a58-e82ca1f7c449 |  | checkpoint | Materials Inspected upon delivery
label | 2fba1d78-e901-5790-a4a4-f6a25e3c160d |  | note | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | e11f3289-2c7a-5e8d-a5bc-7695a28d2c60 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008
label | ae74c744-43b3-50d4-b6e2-092b2632bf33 |  | note | Buildup Inspection Code: W
label | 3f92c7c1-6b39-57fd-a550-7c3c384e88e4 |  | note | Lendlease Inspection Code:
label | 99d82caf-b96b-5c7e-8fe7-2a5b3bd3007c |  | note | Lendlease Sign/Date:
label | 1859bb72-2d63-5f69-af39-7f2d52e5ccde |  | note | Lendlease Comment/Result:
checkpoint-status | b817ad4f-c92e-42a0-b850-3f43ecb71c85 |  | checkpoint | Sheeting carried as per manufacturer’s specification, specified sheeting as per schedule. Ensuring correct layering and components and completed fixing as specification
label | fb698d2b-d6ca-510f-aef1-e6de1c107a02 |  | note | Acceptance Criteria: Staged Fixing at edges, fixing@50mm max centre in field, Staged joints min 300 mm between different layers
label | fe7318bc-c97e-52f5-8325-78221714ba31 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | dd25b0af-941a-56a2-9f60-ac2817c82142 |  | note | Buildup Inspection Code: W
label | 8c14aeeb-fcb7-5086-8360-b94dd1ff444c |  | note | Lendlease Inspection Code:
label | d1e55e88-1682-5427-bfc4-827902dbce86 |  | note | Lendlease Sign/Date:
label | caf385ea-f79d-5f31-8f12-6745f2a415ed |  | note | Lendlease Comment/Result:
checkpoint-status | 868425da-df30-4880-96a4-0dba8e483f2b |  | checkpoint | Caulking to acoustic / fire / smoke/ details.
label | df88dd32-68a7-5d38-9b99-3777bde010b7 |  | note | Acceptance Criteria: Max 20mm with slab/ column, flush
label | c69f2259-37c4-5389-87d1-260e548f6173 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | e671b400-89d2-5801-a069-85d075354579 |  | note | Buildup Inspection Code: W
label | 6f25914d-6200-5d1a-ba21-6bba2f2719fe |  | note | Lendlease Inspection Code:
label | 4811055b-e34c-5317-a0f5-2c40f9976dac |  | note | Lendlease Sign/Date:
label | 00a9e8a0-df3e-5784-b8dc-59f96b986051 |  | note | Lendlease Comment/Result:
checkpoint-status | 7b7cff22-4ab7-473c-99e4-4481871c5817 |  | checkpoint | Penetration sheeted and sealed as per builder' drawings
label | 282f646e-fae0-5f3c-aef0-61d278fed902 |  | note | Acceptance Criteria: Opening square and flush, fully sealed
label | e80c04fd-d1b9-5b64-8a6c-db74d5ae1136 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | 5f54bb6b-7f4a-53a2-9757-594d29817824 |  | note | Buildup Inspection Code: H
label | 099261d5-96f4-5e34-b716-3d2356db363d |  | note | Lendlease Inspection Code:
label | bea6ea58-072e-5c38-8fa8-506cfa2fd530 |  | note | Lendlease Sign/Date:
label | 5f677992-10ca-5f01-a231-016df38edbfa |  | note | Lendlease Comment/Result:
checkpoint-status | 1997f48a-4902-41ed-a747-4a6845011b0b |  | checkpoint | All in wall Services signed off by other trades, wall closeout checklist received by Lendlease
label | b741fffc-f551-51fe-8857-96caacd8aa2d |  | note | Acceptance Criteria: Confirm with Lendlease that all wall service rough in have been completed and approved prior to sheeting
label | e9ed7a25-a062-5720-923d-9e5ba0d12615 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008
label | 17df2a80-5134-5ed8-a054-966aba43a5fe |  | note | Buildup Inspection Code: H
label | 3a3ebb21-c32c-501b-855b-7949b2e12942 |  | note | Lendlease Inspection Code:
label | 40a971fc-c5b6-5e24-adad-1b6e0ccf3ca8 |  | note | Lendlease Sign/Date:
label | 9cafbeb3-da6f-5207-905b-7c4b50bc83b1 |  | note | Lendlease Comment/Result:
checkpoint-status | 58ede02a-9c07-4bae-a5a6-4eacb6427dbd |  | checkpoint | Insulation completed as per acoustic report, partition plans and spec
label | fbe8384b-0b4f-5d98-bd32-28b014cf6c37 |  | note | Acceptance Criteria: As required Insulation, no gap can be seen
label | d3153b97-4bae-566c-ac4d-9700729c55b5 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Series: BR3ADL1-Wall Type
label | d1e3d66f-c6de-55b3-bdd9-4edc92069290 |  | note | Buildup Inspection Code: W
label | 87837888-7c72-522b-8a41-928ce57c695a |  | note | Lendlease Inspection Code:
label | 07d9a5fa-baa9-5364-87db-0291f7dc5f35 |  | note | Lendlease Sign/Date:
label | 010b3167-0581-5f0b-af7c-4ce66ab23032 |  | note | Lendlease Comment/Result:
checkpoint-status | 4a2f7c60-c186-4272-86b0-780b9557638f |  | checkpoint | Plywood Noggins and structural stud installed for all FFE
label | 43a1d729-2b74-5297-96c8-88ec353570eb |  | note | Acceptance Criteria: Checked against current RLS
label | 697ca396-6911-5b89-a684-1eab7efb6443 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Series: BR3ADL2Internal Architectural Details
label | 30e39b73-def9-5329-abd9-5af9817a4574 |  | note | Buildup Inspection Code: W
label | f6ced5f4-5514-5809-aa26-1a5a25955636 |  | note | Lendlease Inspection Code:
label | 808341bc-a4ca-52d6-b767-41714e3a5500 |  | note | Lendlease Sign/Date:
label | 231d935c-6e95-518f-b2f9-2c74983a3dbf |  | note | Lendlease Comment/Result:
checkpoint-status | f81ceef9-27eb-47e3-b8e8-2ee6b3941bf2 |  | checkpoint | Close wall
label | dbaf785c-ac90-5103-8bb9-d402aedc560c |  | note | Acceptance Criteria: Staged Fixing at edges, fixing@50mm max centre in field, Staged joints min 300 mm between different layers
label | d973ca30-a819-533e-bb67-235f24c562d5 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | 3bbc54b9-0227-5b84-aa2b-5b0fe0602194 |  | note | Buildup Inspection Code: W
label | 330b68d9-3624-5839-9192-d5374afd8199 |  | note | Lendlease Inspection Code:
label | ba108395-bcc2-5c4a-a3d4-9f62ddf9399b |  | note | Lendlease Sign/Date:
label | 0c7dbd3e-a4ea-592f-a132-60a2bd4a9887 |  | note | Lendlease Comment/Result:
checkpoint-status | 682a1e01-6a25-4454-b685-cc20435b6452 |  | checkpoint | Caulking to acoustic / fire / smoke/ details
label | 1ba8dd62-7402-5396-a980-75294068d327 |  | note | Acceptance Criteria: Max 20mm with slab/ column, flush
label | 25aec399-ed37-532a-9f65-c3abf4e568cf |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008
label | 92b33517-f283-518f-8c6e-051535ad9617 |  | note | Buildup Inspection Code: H
label | 3eb1c342-8408-58b6-a6b9-5e962f66667c |  | note | Lendlease Inspection Code:
label | c26639c5-b98d-5214-a88b-4e1826ee1823 |  | note | Lendlease Sign/Date:
label | 7b9d62cf-dd7f-5b97-a85e-03740786178f |  | note | Lendlease Comment/Result:
checkpoint-status | b702050b-0f40-40f8-a39e-cbc86ba4dcb6 |  | checkpoint | Set and sand ready for painting
label | 05634049-dfc2-5a0a-a233-38b2b71964ce |  | note | Acceptance Criteria: Meet Level 4 of finish requirement
label | 5eaac810-a809-5bb6-8c03-f4bd50a7aad4 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008
label | 0cc43790-94ce-5423-ada2-0f69cedfbefc |  | note | Buildup Inspection Code: H
label | 6ce47659-86f2-590c-8c68-742ba96de717 |  | note | Lendlease Inspection Code:
label | 4bb82f74-587a-56a5-b15a-0b1c56064d56 |  | note | Lendlease Sign/Date:
label | 334619a0-a2a8-55e9-a0d8-dadb51621922 |  | note | Lendlease Comment/Result:
checkpoint-status | 8ed61194-83c2-4e77-a612-b5e622c0a479 |  | checkpoint | COMPREHENSIVE FIRST-OF-TYPE INSPECTION
label | 82f095b4-abf0-5069-95b9-c6feeca15531 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008; Siniat & Rondo Inspection
label | c0f3f673-cfcb-5233-8cb2-3f4406e5f9f0 |  | note | Buildup Inspection Code: H
label | 3f2b4966-5db5-500e-a2ae-0cb1764b225f |  | note | Lendlease Inspection Code:
label | 0948e1dd-7c7c-5d92-a599-16d95f3f551c |  | note | Lendlease Sign/Date:
label | e9bf2552-9ee4-5a28-94ed-3d3dda7cbb90 |  | note | Lendlease Comment/Result:
checklist-flat | a227292b-c906-4886-bf27-ba90a9ecd514 |  | checklist | ITP 001a Speed Panel |  |  |  |  | Yes | ITP 001a Speed Panel | f7b00233-62c3-4965-85e0-cbfcfd1b83fc
checkpoint-status | 49181939-b51e-456c-9642-e7ab69512279 |  | checkpoint | Materials Inspected upon delivery
label | a158be88-b970-5327-a9ef-648b2b94c44b |  | note | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | 696b2303-0ae0-5609-b1f4-39f9f92cb3fa |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4
label | 42e1bef0-58a3-586b-93e7-9cc9e2613753 |  | note | Buildup Inspection Code: W
label | 181094c5-3094-5c26-9f88-981fb1362e48 |  | note | Lendlease Inspection Code:
label | bbd4bf9e-519c-51c2-8aef-53a63f93a69d |  | note | Lendlease Sign/Date:
label | bc937d77-a826-5856-9d07-67795c3abbc9 |  | note | Lendlease Comment/Result:
checkpoint-status | ca101550-5bcb-4cbb-9884-694b1917be47 |  | checkpoint | Wall dimension checked against drawings & setout; Wall types confirmed against partition plans
label | 83f8e56d-0f9c-54c9-97c4-5eb143911bfd |  | note | Acceptance Criteria: Latest drawing revision checked
label | f12324e3-8c2d-5144-8dd1-ca43ca924d4f |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Series BR3ADB2 -; Wall Setout Plans
label | 9ff72a3b-0000-5b9e-a06d-f77ef572f986 |  | note | Buildup Inspection Code: W
label | 93315d64-97fd-5f64-b931-5ba84e93a9bf |  | note | Lendlease Inspection Code:
label | ae5d0e2b-b11f-5703-9820-3388bf84eabd |  | note | Lendlease Sign/Date:
label | 52688bd0-952b-509b-a24a-1a6c1e6397f5 |  | note | Lendlease Comment/Result:
checkpoint-status | 89bd589d-cc8e-4a1f-9b42-56c9f93526fa |  | checkpoint | C-Track installed as manufacturer's specification to top, bottom and both sides
label | c082d057-c6b4-5c0e-8a03-c3a4adc668ac |  | note | Acceptance Criteria: Hilti 606 Sealant applied between C-track and concrete and along internal corner. Anchor @500 Centre & max 100 from end
label | 5221664c-0b14-51e7-ab4f-296de6c17899 |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | 011de391-729d-50ff-a75a-d43bc6f6e03f |  | note | Buildup Inspection Code: W
label | bf60a8de-e14a-53f1-b64c-8da8a8ed6399 |  | note | Lendlease Inspection Code:
label | 13bceb38-76b9-5683-a461-4555dd213221 |  | note | Lendlease Sign/Date:
label | 7fff21a0-c055-5a5c-bca9-ad0fd8bc11a1 |  | note | Lendlease Comment/Result:
checkpoint-status | 2038fe07-afdb-4b62-8397-d0a1721e57e5 |  | checkpoint | Panels installed as manufacturer's specifications
label | 5134dda7-8227-5642-93e5-a0bf865d3200 |  | note | Acceptance Criteria: Each panel interlocked, fixing @ max vertically 1000mm centre on joints and 250 mm horizontally, fixing @ max 500mm on C-track, 2 fixings at 45" for every corner. Sealant full placed around C-track
label | 7d29e1b4-6390-5408-94bb-f499af7c866f |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | aae7d992-b2c7-5cb5-9107-e914e79678c7 |  | note | Buildup Inspection Code: W
label | f4b68d88-6b43-533d-a85a-e27abe11cf04 |  | note | Lendlease Inspection Code:
label | fee042f3-2fbb-56d4-9f1f-9f7c20e5cfbd |  | note | Lendlease Sign/Date:
label | 9b482cb0-38d8-5bd0-830b-884df58ce303 |  | note | Lendlease Comment/Result:
checkpoint-status | ac77c2ee-3bc3-4965-8f74-4855b147453a |  | checkpoint | Penetration cut, trimmed and sealed as per builder' drawings
label | c4b7685b-999e-5639-8ff6-37cfacd9314c |  | note | Acceptance Criteria: Max 500mm centre fixing on C-track, 2*fixings on corner, fully sealed with Hilti 606
label | 01643470-60a7-54f7-a518-b780db342ce0 |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | 6da2051f-469c-5966-a192-185b2e941136 |  | note | Buildup Inspection Code: H
label | 144bc2cd-a4e9-57a4-8950-19b64529ef6c |  | note | Lendlease Inspection Code:
label | eaea9ab4-17f4-5322-9983-6001d7256e5c |  | note | Lendlease Sign/Date:
label | f456a90b-eaa9-5abb-b3bf-b7b9afe7b805 |  | note | Lendlease Comment/Result:
checkpoint-status | c9cdf172-b741-49e5-94a9-bbabac1c827e |  | checkpoint | Door Frame installed as per manufacturer's specification
label | d85e4c16-6a50-5971-b535-0cf5d51e8e0f |  | note | Acceptance Criteria: Plumb, square and same height, core-filled
label | 42281626-063a-5a2c-a748-a68264054a77 |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | 272363c1-997d-5c5a-92dd-4b3af4a02f38 |  | note | Buildup Inspection Code: H
label | d0ea5d11-2805-524b-9676-2247041915b3 |  | note | Lendlease Inspection Code:
label | 6313ee9a-9115-5ac4-ac4d-36bfe6577e06 |  | note | Lendlease Sign/Date:
label | f0e4735a-6ce7-50ec-b033-1d039298c71d |  | note | Lendlease Comment/Result:
checkpoint-status | 3ff07a19-1757-4dce-b8cb-4ee0aa0a547b |  | checkpoint | Flashing head-protection
label | 9067ae34-16c6-5e2b-8594-84d0a2ea2f53 |  | note | Acceptance Criteria:Min 120mm deep, stagged fixing @max 250mm
label | 21953207-404e-5a1d-b53f-3be8b5fbda6f |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | 87dd63b5-4bb6-5405-98dc-16da90d1d5fd |  | note | Buildup Inspection Code: W
label | a2b86697-0674-5f5b-88d1-3fb49a62042f |  | note | Lendlease Inspection Code:
label | bf0ee5c3-5e3b-58a7-a4e0-c18d01feba76 |  | note | Lendlease Sign/Date:
label | 034d964d-de24-53ce-a14c-7629b21ae0b7 |  | note | Lendlease Comment/Result:
checkpoint-status | 6b88e9ab-987a-4c12-9edd-1ae0c5a9d1c4 |  | checkpoint | Comprehensive first of type inspection
label | 605f8b65-bf91-5130-b15e-58d8e7279542 |  | note | References: Australian Standards:AS1530.4;AS1191;AS1170.4; Supplier / Manufacturer inspection report
label | 1d1cbadf-458a-5f73-8c8a-e83bf4e41f31 |  | note | Buildup Inspection Code: H
label | 0a501d88-6912-56df-8290-7e097bcd72b1 |  | note | Lendlease Inspection Code:
label | 78c72b49-167c-5c94-a356-01d5b904fc8a |  | note | Lendlease Sign/Date:
label | 315eb41d-8514-5ed2-ba87-4478306d1198 |  | note | Lendlease Comment/Result:
checklist-flat | 413ae7a6-9013-4a2e-a0b4-3938e1b56cda |  | checklist | ITP 004 Door and Door Hardware Installation |  |  |  |  | Yes | ITP 004 Door and Door Hardware Installation | f846819b-ffc2-405a-b37e-b53bba96716e
checkpoint-status | a9b4816c-7a9b-4329-bb8a-37b08ad9a81f |  | checkpoint | Materials Inspected upon delivery
label | ba170659-1103-5518-bf3e-6facd1f7847b |  | note | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | 4bcfccdb-9715-5fe5-8501-87ca7485b031 |  | note | Buildup Inspection Code: W
label | 1a8cf9d1-b2c9-5530-acd1-0a12ea7dbb87 |  | note | Lendlease Inspection Code:
label | d45492e4-b2a3-53cc-86cf-a12ab6103302 |  | note | Lendlease Sign/Date:
label | 1ddff8d3-cf9c-520e-b39b-1c8d0fe5152c |  | note | Lendlease Comment/Result:
checkpoint-status | ebae31c8-756b-4eeb-8c6a-9029452b8d63 |  | checkpoint | Opening dimension checked against drawings and Setout, Door types and leaf size confirmed against partition plan
label | ec97dc4f-ca5e-5994-82a7-d706f5c5305a |  | note | Acceptance Criteria: Latest Drawing Revision Checked
label | c8119a4a-4354-5ce5-bfa6-dc4cec2dfc54 |  | note | References: Series:BR3ADB2-Wall Setout Plans; Door Schedule - BR3AT1332[C2]
label | aba98f45-0cf1-57c9-8f7e-c62d9b988279 |  | note | Buildup Inspection Code: W
label | de5a3ecf-c320-52a4-ad93-65656a12fb38 |  | note | Lendlease Inspection Code:
label | 7fd7f260-d574-56a2-b84f-69a3fe6a97f5 |  | note | Lendlease Sign/Date:
label | 21d483da-5def-57f9-910e-0e0d99df573a |  | note | Lendlease Comment/Result:
checkpoint-status | 948433fc-1f8c-41e7-a494-2b88a8c755d9 |  | checkpoint | Door frame installed as manufacturer's specification to Top, bottom and both sides
label | 4f49f21a-1d7c-5dd9-bbe0-c6d7ea694800 |  | note | Acceptance Criteria:Straight and plumb and square, no sharp edge, gap less than 20mm, sealed with silicone
label | 257fd917-47f8-59b2-8ac5-f521385eca1d |  | note | Buildup Inspection Code: H
label | 0f652492-72bb-5749-bb7a-a8f1ffdbc7e0 |  | note | Lendlease Inspection Code:
label | 1553db73-701b-5a63-97c8-0fba3dd39f50 |  | note | Lendlease Sign/Date:
label | 197db408-9d54-5190-bd8b-366e49736cc8 |  | note | Lendlease Comment/Result:
checkpoint-status | 886c2876-2c69-4c0b-b6c3-e60fa70f6bf9 |  | checkpoint | Door Hardware Installation and Check
label | 7dc6030f-d599-5699-a5cf-a5420961c142 |  | note | Acceptance Criteria: Correct Hardware type followed as shop drawings. All of door hardware followed the finish Schedule
label | 9089cc64-8cb2-5ec8-9d7b-a5f977ae1712 |  | note | Buildup Inspection Code: W
label | 98745fa4-413b-540d-9438-d4558caa0c1a |  | note | Lendlease Inspection Code:
label | 79da12d4-201f-5912-ba6c-775393f4cfca |  | note | Lendlease Sign/Date:
label | b04fd14e-2270-52ee-a3dd-361e5b72488a |  | note | Lendlease Comment/Result:
checkpoint-status | e3228387-7fb0-48e9-a639-d2ce4f533898 |  | checkpoint | Door Smoke sealed cabinet
label | 192b67d5-c784-5047-b61b-5ee2672b26eb |  | note | Acceptance Criteria: Latest Drawing Revision Checked
label | 4c3d19d1-6948-5ed4-9133-f8c17c1b6ca8 |  | note | Buildup Inspection Code: W
label | 0b757550-4fd1-53f8-9aa2-5c057e86a51b |  | note | Lendlease Inspection Code:
label | daf55fca-6265-5306-bd08-7f434a27ba9f |  | note | Lendlease Sign/Date:
label | 69b18622-85d6-5901-b6cf-9759d90fbe8d |  | note | Lendlease Comment/Result:
checkpoint-status | d9816774-486f-419e-a7ea-c2e411c8af01 |  | checkpoint | COMPREHENSIVE FIRST-OF-TYPE INSPECTION
label | a64a6c8a-64d3-59f7-8e83-9a8528666c6e |  | note | Buildup Inspection Code: H
label | c07db11f-2fcb-5391-8243-16507beec32a |  | note | Lendlease Inspection Code:
label | d7b60638-4529-52c5-95aa-9c060459e6ee |  | note | Lendlease Sign/Date:
label | 4e4ce480-978e-5216-9fe7-268002290569 |  | note | Lendlease Comment/Result: