## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-sectioned | ITP 006 FF&E Installation |  |  |  |  | Yes | ITP 006 FF&E Installation
checkpoint-group | Materials
checkpoint-status | Materials Inspected upon delivery
label | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-group | FFE Installation
checkpoint-status | All of FFE Products must approved by Lendlease
label | Acceptance Criteria: Sample Form Approval Finish Schedule
label | References:Series: BR3ADL2-Internal Architectural Details
label | Buildup Inspection Code: H
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
signoff | HOLD POINT - Signed by Lendlease
checkpoint-status | All of FFE products have to supported by Noggins
label | Acceptance Criteria: Noggin Markup Plan
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | No unreasonable gap or holes on the wall
label | Acceptance Criteria: Eye Inspection
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | Height and location must follow the requirement
label | Acceptance Criteria: Noggin Markup Plan
label | References: Series: BR3ADL2-Internal Architectural Details
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | FFE installation should not affect the wall finish. The wall with good patching as well
label | Acceptance Criteria: Eye Inspection
label | Buildup Inspection Code: H
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
signoff | HOLD POINT - Signed by Lendlease
checklist-sectioned | ITP 005 Installation of Ceiling System |  |  |  |  | Yes | ITP 005 Installation of Ceiling System
checkpoint-group | Ceiling Framing
checkpoint-status | Materials Inspected upon delivery
label | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | Ceiling framing dimension and FCL checked against drawings and Setout, Ceiling types confirmed against RCPs
label | Acceptance Criteria: Latest Drawing Revision Checked
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008; Series: BR3ADG1-Reflected Ceiling Plans
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | All above-ceiling services are installed and ready for ceiling framing
label | Acceptance Criteria: Confirm with Lendlease that all wall service rough ins have been completed and approved prior to sheeting
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | Ceiling framing completed as Rondo designs
label | Acceptance Criteria: Suspending point max 1200mm*1200mm Grid, TCR @max 600 space and max200 from wall, FC @max 600 space and max 100 from wall. Correctly braced. Two sides fixed and two sides free
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;KEY-LOCK Suspended Seismic Ceiling Specification
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | Bulkhead and Bracing completed as Kanuf designs
label | Acceptance Criteria: Anchor used with Load sharing washer
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;KEY-LOCK Suspended Seismic Ceiling Specification
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | Allowance for access panels and service penetration (Lights and Grill)
label | Acceptance Criteria: Framing not in the way of services or AP
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Coordinated RCP drawing series
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | Timber Noggins and Ceiling support installed as required
label | Acceptance Criteria: Reference that set out of noggins to be checked against Room Layout sheet Elevations
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008
label | Buildup Inspection Code: H
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
signoff | HOLD POINT - Signed by Lendlease
checkpoint-group | Close Ceiling
checkpoint-status | Materials Inspected upon delivery
label | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | Check all services roughed in and not using ceiling frame as a support, all seismic supports have been installed for service by others, ceiling closeout checklist received by Lendlease
label | Acceptance Criteria: Minimum 3mm gap kept from ceiling frame
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;KEY-LOCK Suspended Seismic Ceiling Specification
label | Buildup Inspection Code:H
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
signoff | HOLD POINT - Signed by Lendlease
checkpoint-status | Installation of acoustic insulation to the ceiling
label | Acceptance Criteria: acoustic insulation must extend 900mm from acoustic wall
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008; Series: BR3ADS2-Insulation Ceiling Plans
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | Sheeting carried as per manufacturer’s specification, specified sheeting as per schedule. Ensuring correct layering and components and completed fixing as pec
label | Acceptance Criteria: Staged Fixing @200mm max centre at edges, fixing @300mm max centre in field, Staged butt joint by 600mm min. Back blocking battens used on butt joints
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;BCA Report 210721: 1740 R1.0
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | Access panel installed as required
label | Acceptance Criteria: Correct location, square with wall or bulkhead
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;BCA Report 210721: 1740 R1.0
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | Caulking to acoustic / fire / smoke/ details.
label | Acceptance Criteria: Max 20mm with slab/ column, flush
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;BCA Report 210721: 1740 R1.0
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | Set and sand ready for painting
label | Acceptance Criteria: No bubbles, no lump, square, not over sanded
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;BCA Report 210721: 1740 R1.0
label | Buildup Inspection Code: H
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
signoff | HOLD POINT - Signed by Lendlease
checkpoint-status | COMPREHENSIVE FIRST-OF-TYPE INSPECTION
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Siniat&Rondo Inspection
label | Buildup Inspection Code: H
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
signoff | HOLD POINT - Signed by Lendlease
checklist-flat | ITP 001 Speed Panel |  |  |  |  | Yes | ITP 001 Speed Panel
checkpoint-status | Materials Inspected upon delivery
label | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | References: Australian Standards:AS1530.4;AS1191;AS1170.4
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | Wall dimension checked against drawings & setout; Wall types confirmed against partition plans
label | Acceptance Criteria: Latest drawing revision checked
label | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Series BR3ADB2 -; Wall Setout Plans BR3ADF3 - Fire Stairs
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | C-Track installed as manufacturer's specification to top, bottom and both sides
label | Acceptance Criteria: Hilti 606 Sealant applied between C-track and concrete and along internal corner. Anchor @500 Centre & max 100 from end
label | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | Panels installed as manufacturer's specifications
label | Acceptance Criteria: Each panel interlocked, fixing @ max vertically 1000mm centre on joints and 250 mm horizontally, fixing @ max 500mm on C-track, 2 fixings at 45" for every corner. Sealant full placed around C-track
label | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | Comprehensive first of type inspection
label | References: Australian Standards:AS1530.4;AS1191;AS1170.4; Supplier / Manufacturer inspection report
label | Buildup Inspection Code: H
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
signoff | HOLD POINT - Signed by Lendlease
checklist-sectioned | ITP 002 Installation of Soffit Insulation |  |  |  |  | Yes | ITP 002 Installation of Soffit Insulation
checkpoint-group | Materials delivery
checkpoint-status | Materials Inspected upon delivery
label | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | References: Australian Standards AS/NZS 4859.1 and AS 5637.1.
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-group | Under Slab Insulation
checkpoint-status | Insulation dimension checked against drawings and Setout; Insulation types confirmed against Insulation set out plans
label | Acceptance Criteria: Latest drawing revision checked
label | References: Australian Standards AS/NZS 4859.1 and AS 5637.1;Series: BR3ADS2-Insulation Ceiling Plans
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | The foil surface of the insulation board should face down
label | Acceptance Criteria: Inspected and confirmed
label | References: Australian Standards AS/NZS 4859.1 and AS 5637.1;Australian Insulation Manufacturers Group – Prime Panel Soffit Insulation Installation Guide
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | Fix insulation panel to concrete soffits with minimum 5 No. Appropriate insulation fasteners with a minimum head diameter of 35 mm
label | Acceptance Criteria: Inspected and confirmed
label | References: Australian Standards AS/NZS 4859.1 and AS 5637.1;Australian Insulation Manufacturers Group – Prime Panel Soffit Insulation Installation Guide
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | Tape board joints with a minimum 96mm wide appropriate aluminium foil tape, detail as per attached Installation Instructions
label | Acceptance Criteria: Inspected and confirmed
label | References: Australian Standards AS/NZS 4859.1 and AS 5637.1;Australian Insulation Manufacturers Group – Prime Panel Soffit Insulation Installation Guide
label | Buildup Inspection Code: H
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
signoff | HOLD POINT - Signed by Lendlease
checkpoint-status | Exposed board edge covered with foil tape lapped 48mm on to underside
label | Acceptance Criteria: Inspected and confirmed
label | References: Australian Standards AS/NZS 4859.1 and AS 5637.1;Australian Insulation Manufacturers Group – Prime Panel Soffit Insulation Installation Guide
label | Buildup Inspection Code: H
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
signoff | HOLD POINT - Signed by Lendlease
checkpoint-status | Check against cast-in penetrations. All penetrations/collars/dampers to be fully exposed
label | Acceptance Criteria: Inspected and confirmed
label | References: Australian Standards AS/NZS 4859.1 and AS 5637.1;Australian Insulation Manufacturers Group – Prime Panel Soffit Insulation Installation Guide
label | Buildup Inspection Code: H
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
signoff | HOLD POINT - Signed by Lendlease
checklist-flat | ITP 001b Speed Panel |  |  |  |  | Yes | ITP 001b Speed Panel
checkpoint-status | Materials Inspected upon delivery
label | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | References: Australian Standards:AS1530.4;AS1191;AS1170.4
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | Wall dimension checked against drawings & setout; Wall types confirmed against partition plans
label | Acceptance Criteria: Latest drawing revision checked
label | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Series BR3ADB2 -; Wall Setout Plans BR3ADF3 - Fire Stairs
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | C-Track installed as manufacturer's specification to top, bottom and both sides
label | Acceptance Criteria: Hilti 606 Sealant applied between C-track and concrete and along internal corner. Anchor @500 Centre & max 100 from end
label | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | Panels installed as manufacturer's specifications
label | Acceptance Criteria: Each panel interlocked, fixing @ max vertically 1000mm centre on joints and 250 mm horizontally, fixing @ max 500mm on C-track, 2 fixings at 45" for every corner. Sealant full placed around C-track
label | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | Penetration cut, trimmed and sealed as per builder' drawings
label | Acceptance Criteria: Max 500mm centre fixing on C-track, 2*fixings on corner, fully sealed with Hilti 606
label | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | Buildup Inspection Code: H
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
signoff | HOLD POINT - Signed by Lendlease
checkpoint-status | Door Frame installed as per manufacturer's specification
label | Acceptance Criteria: Plumb, square and same height, core-filled
label | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | Buildup Inspection Code: H
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
signoff | HOLD POINT - Signed by Lendlease
checkpoint-status | Flashing head-protection
label | Acceptance Criteria:Min 120mm deep, stagged fixing @max 250mm
label | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | Fully sealed joints one side in pressurized shaft
label | Acceptance Criteria: Continues beads
label | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | Buildup Inspection Code: H
label | Lendlease Inspection Code: H
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
signoff | HOLD POINT - Signed by Lendlease
checkpoint-status | Comprehensive first of type inspection
label | References: Australian Standards:AS1530.4;AS1191;AS1170.4; Supplier / Manufacturer inspection report
label | Buildup Inspection Code: H
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
signoff | HOLD POINT - Signed by Lendlease
checklist-flat | ITP 007 Skirting Installation |  |  |  |  | Yes | ITP 007 Skirting Installation
checkpoint-status | Materials Inspected upon delivery
label | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | Set out Timber skirting size & type as per wall finish set out plan
label | Acceptance Criteria: Latest Drawing Revision Checked
label | References:Series: BR3ADL2-Internal Architectural Details; BR3ADB2-Wall Setout Plans
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | Timber skirting installed as manufacturer's specification to Top, bottom side
label | Acceptance Criteria: Straight and plumb and square, no sharp edge, gap less than 3mm, sealed with silicone Ref
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | No unreasonable gap or holes on the wall
label | Acceptance Criteria: Eye Inspection
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | Timber skirting fixing and inspect for damage prior to hand over
label | Acceptance Criteria: Inspected and approved
label | Buildup Inspection Code: H
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
signoff | HOLD POINT - Signed by Lendlease
checkpoint-status | COMPREHENSIVE FIRST-OF-TYPE INSPECTION
label | Buildup Inspection Code: H
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
signoff | HOLD POINT - Signed by Lendlease
checklist-sectioned | ITP 003 Installation of Internal Partitions |  |  |  |  | Yes | ITP 003 Installation of Internal Partitions
checkpoint-group | Wall Framing
checkpoint-status | Materials Inspected upon delivery
label | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | Wall framing completed to Rondo designs, checked for square, plumb and twisting
label | Acceptance Criteria: slotted Deflection Track used; additional noggin installed for onside sheeting frame
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Internal partition designs: 10246-22001 SK00 - 1024622-001-SK15; Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | Allowance for access panels and service penetration
label | Acceptance Criteria: Bridging Track supported by offcut studs
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Internal partition designs: 10246-22001 SK00 - 1024622-001-SK15; Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | Openings (Including doors, windows, removable parts) installed to correct position and height, with right opening towards, plumb and square, as per Rondo designs
label | Acceptance Criteria: Jamb header or sill used correct components
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Internal partition designs: 10246-22001 SK00 - 1024622-001-SK15; Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | Buildup Inspection Code: H
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
signoff | HOLD POINT - Signed by Lendlease
checkpoint-status | Plywood Noggins and structural stud installed for all fixtures
label | Acceptance Criteria: Reference that set out of noggins to be checked against Room Layout sheet Elevations
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Internal partition designs: 10246-22001 SK00 - 1024622-001-SK15; Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | Door and window Frame installed as per manufacturer's specification stud installed for all fixtures
label | Acceptance Criteria: Plumb, square and same height, core-filled
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Internal partition designs: 10246-22001 SK00 - 1024622-001-SK15; Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | Buildup Inspection Code: H
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
signoff | HOLD POINT - Signed by Lendlease
checkpoint-group | Wall Sheeting
checkpoint-status | Materials Inspected upon delivery
label | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | Sheeting carried as per manufacturer’s specification, specified sheeting as per schedule. Ensuring correct layering and components and completed fixing as specification
label | Acceptance Criteria: Staged Fixing at edges, fixing@50mm max centre in field, Staged joints min 300 mm between different layers
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | Caulking to acoustic / fire / smoke/ details.
label | Acceptance Criteria: Max 20mm with slab/ column, flush
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | Penetration sheeted and sealed as per builder' drawings
label | Acceptance Criteria: Opening square and flush, fully sealed
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | Buildup Inspection Code: H
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
signoff | HOLD POINT - Signed by Lendlease
checkpoint-status | All in wall Services signed off by other trades, wall closeout checklist received by Lendlease
label | Acceptance Criteria: Confirm with Lendlease that all wall service rough in have been completed and approved prior to sheeting
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008
label | Buildup Inspection Code: H
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
signoff | HOLD POINT - Signed by Lendlease
checkpoint-status | Insulation completed as per acoustic report, partition plans and spec
label | Acceptance Criteria: As required Insulation, no gap can be seen
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Series: BR3ADL1-Wall Type
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | Plywood Noggins and structural stud installed for all FFE
label | Acceptance Criteria: Checked against current RLS
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Series: BR3ADL2Internal Architectural Details
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | Close wall
label | Acceptance Criteria: Staged Fixing at edges, fixing@50mm max centre in field, Staged joints min 300 mm between different layers
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | Caulking to acoustic / fire / smoke/ details
label | Acceptance Criteria: Max 20mm with slab/ column, flush
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008
label | Buildup Inspection Code: H
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
signoff | HOLD POINT - Signed by Lendlease
checkpoint-status | Set and sand ready for painting
label | Acceptance Criteria: Meet Level 4 of finish requirement
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008
label | Buildup Inspection Code: H
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
signoff | HOLD POINT - Signed by Lendlease
checkpoint-status | COMPREHENSIVE FIRST-OF-TYPE INSPECTION
label | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008; Siniat & Rondo Inspection
label | Buildup Inspection Code: H
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
signoff | HOLD POINT - Signed by Lendlease
checklist-flat | ITP 001a Speed Panel |  |  |  |  | Yes | ITP 001a Speed Panel
checkpoint-status | Materials Inspected upon delivery
label | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | References: Australian Standards:AS1530.4;AS1191;AS1170.4
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | Wall dimension checked against drawings & setout; Wall types confirmed against partition plans
label | Acceptance Criteria: Latest drawing revision checked
label | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Series BR3ADB2 -; Wall Setout Plans
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | C-Track installed as manufacturer's specification to top, bottom and both sides
label | Acceptance Criteria: Hilti 606 Sealant applied between C-track and concrete and along internal corner. Anchor @500 Centre & max 100 from end
label | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | Panels installed as manufacturer's specifications
label | Acceptance Criteria: Each panel interlocked, fixing @ max vertically 1000mm centre on joints and 250 mm horizontally, fixing @ max 500mm on C-track, 2 fixings at 45" for every corner. Sealant full placed around C-track
label | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | Penetration cut, trimmed and sealed as per builder' drawings
label | Acceptance Criteria: Max 500mm centre fixing on C-track, 2*fixings on corner, fully sealed with Hilti 606
label | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | Buildup Inspection Code: H
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | Door Frame installed as per manufacturer's specification
label | Acceptance Criteria: Plumb, square and same height, core-filled
label | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | Buildup Inspection Code: H
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
signoff | HOLD POINT - Signed by Lendlease
checkpoint-status | Flashing head-protection
label | Acceptance Criteria:Min 120mm deep, stagged fixing @max 250mm
label | References: Australian Standards:AS1530.4;AS1191;AS1170.4;Speedpanel Installation Guide 2017
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | Comprehensive first of type inspection
label | References: Australian Standards:AS1530.4;AS1191;AS1170.4; Supplier / Manufacturer inspection report
label | Buildup Inspection Code: H
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
signoff | HOLD POINT - Signed by Lendlease
checklist-flat | ITP 004 Door and Door Hardware Installation |  |  |  |  | Yes | ITP 004 Door and Door Hardware Installation
checkpoint-status | Materials Inspected upon delivery
label | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | Opening dimension checked against drawings and Setout, Door types and leaf size confirmed against partition plan
label | Acceptance Criteria: Latest Drawing Revision Checked
label | References: Series:BR3ADB2-Wall Setout Plans; Door Schedule - BR3AT1332[C2]
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | Door frame installed as manufacturer's specification to Top, bottom and both sides
label | Acceptance Criteria:Straight and plumb and square, no sharp edge, gap less than 20mm, sealed with silicone
label | Buildup Inspection Code: H
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
signoff | HOLD POINT - Signed by Lendlease
checkpoint-status | Door Hardware Installation and Check
label | Acceptance Criteria: Correct Hardware type followed as shop drawings. All of door hardware followed the finish Schedule
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | Door Smoke sealed cabinet
label | Acceptance Criteria: Latest Drawing Revision Checked
label | Buildup Inspection Code: W
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
checkpoint-status | COMPREHENSIVE FIRST-OF-TYPE INSPECTION
label | Buildup Inspection Code: H
label | Lendlease Inspection Code:
label | Lendlease Sign/Date:
label | Lendlease Comment/Result:
signoff | HOLD POINT - Signed by Lendlease