## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Concrete Pour Checklist |  |  |  |  | Yes | Concrete Pour Checklist | 117e0c9c-b635-45c0-a080-3f25315c5173
checkpoint-status |  |  | checkpoint | General Details
text | ed6cb7eb-86a8-57ee-af6f-b50eca1006c1 |  | textbox | Location
text | caf2ed35-29b1-5ea1-ad58-3f04eef64333 |  | textbox | Pre Pour Date
text | 43c81ae8-0670-5449-b46a-416fdd4abe52 |  | textbox | Concrete Strength (mPa)
text | 49d92feb-dd3a-5a79-8a66-3dda0f10471e |  | textbox | Volume (m3)
text | 52a0ebb3-f114-5e29-acf2-cf1e2d810732 |  | textbox | Mix Design
text | fc80e085-05c3-5b80-97a4-1ea053248326 |  | textbox | Additives
checkpoint-status |  |  | checkpoint | Formwork has been Checked and conforms to the drawings including:
label | 62e5b632-9007-5dd9-9c1d-0545a78c749f |  | note | Overall location, Bracing & Supports, Cleanliness, Construction Joint Positions, Construction Joints Prepared, Plan Dimensions, Pour Thickness, Diagonals, Straightness, Grout Tightness, Surface Finish, Rebate, Penetrations, Formwork Oiled, Angle Fillet , Divi nuts tight
checkpoint-status |  |  | checkpoint | Reinforcing has been checked and conforms to the drawings included:
label | 9cdb9cb9-0641-55be-a98f-4b74537ef7c8 |  | note | Bar Size & Grade, Lap Lengths, Lap Locations, Bar Supports, Bar Spacing, Cover, Steel Cleanness, Starter Positions
checkpoint-status |  |  | checkpoint | Pre Pour Sign Off
holdpoint |  |  | signoff | Pre Pour Acceptance
checkpoint-status |  |  | checkpoint | Pour Commenced
text | a3edf8dc-d005-51c2-b3fb-68622a9801bf |  | textbox | Pour Date
text | d9c6a144-6ad8-55b5-a73c-df307ea137fc |  | textbox | Pour Time
checkpoint-status |  |  | checkpoint | Slump Measured
text | be3ffe44-5cfe-5087-ae24-a257c1d28248 |  | textbox | Measurements
checkpoint-status |  |  | checkpoint | Dockets Attached
checkpoint-status |  |  | checkpoint | Concrete Cylinders Taken
checklist-sectioned |  |  | checklist | DS2672-ITP-S103 - Rev 1 - Jet Grout Installation |  |  |  |  | Yes | DS2672-ITP-S103 - Jet Grout Installation - Rev 1 | 235f83fc-0a31-406a-9db3-609d1fc91af3
checkpoint-group |  |  | section | 3.01 Site Requirements
checkpoint-status |  |  | checkpoint | 3.01.01 - Construction Pack
label | 8a8f0ff7-8cef-5d97-8a6d-b67c943409dc |  | note | Acceptance / Conformance Criteria - Submit a Construction Pack including a Methodology and JESA to the Engineer before works
label | f54a4c43-3c99-50ea-831c-f16c26b4b896 |  | note | Standard / Specification - Downer
label | b716779f-2b80-54b9-aea4-d07499d170b6 |  | note | Verifying Document - Construction Pack
label | 419b6164-ed03-5893-a91a-a72f007e26dc |  | note | Frequency - Submit Prior to commencement of works
label | 55f58789-9fa0-5f51-b068-7a81fd75c51a |  | note | Activity - H
label | 67c711fe-120a-583a-a9c5-35fa49b01aba |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.01.02 - Survey Setout
label | 24cce936-5e41-595c-9865-fa6f5920cc56 |  | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
label | bfaea4ce-f7dd-5387-a89f-9bab84877368 |  | note | Standard / Specification - Downer
label | cb457985-3697-5e24-8796-f36a773dcec6 |  | note | Verifying Document - Survey Records
label | 865eae83-6239-5bcd-8ef9-740dee09d59c |  | note | Frequency - Prior to Works
label | a9b9bd3e-3a0f-5af1-95d7-538cde74d9c9 |  | note | Activity - H
label | 948a1298-7696-5557-ae5c-25bdbd595e69 |  | note | By - SV
checkpoint-status |  |  | checkpoint | 3.01.03 - Service Location
label | 5d9fb48a-cef3-53da-8500-9ddcf0c6839f |  | note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
label | 3c77e130-4b72-5855-8208-c98ee9c2b324 |  | note | Standard / Specification - Downer
label | 2b6a1968-00a0-5384-b58b-a891598af506 |  | note | Verifying Document - Excavation Permit
label | 50e6d473-1519-5141-9716-af1f37dbbd0f |  | note | Frequency - Prior to Excavation
label | b0d3d605-38f5-5c75-b4b6-41c02e9ee809 |  | note | Activity - H
label | bb681ad0-815d-5db0-98d5-c12bc537588b |  | note | By - SE
checkpoint-status |  |  | checkpoint | 3.01.04 - Internal Permits
label | 16735e39-60b4-59bc-917d-5c4837422376 |  | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
label | 6b283994-6d2f-563d-9bf9-d460d97a8856 |  | note | Standard / Specification - Downer
label | c5451da6-8813-5a8c-99cf-54b038a96d3c |  | note | Verifying Document - Internal Permits
label | 0bc520eb-e4c8-55b6-a99d-d04b09f04698 |  | note | Frequency - Prior to Excavation
label | ff6a4e4f-4888-5d78-82b1-4c665f11f050 |  | note | Activity - H
label | 4a6494ee-68ad-5438-8763-23aebae87400 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 3.01.05 - External Permits
label | 54398eff-fc52-5919-81f1-b9fc1ddb1f65 |  | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
label | 4ce9b9f7-a9a1-5a5b-bf38-fc03fa593565 |  | note | Standard / Specification - Downer
label | 740658b3-5b76-5a18-b809-60c7fd621b79 |  | note | Verifying Document - External Permits
label | cc2e58c0-5bcb-5ae5-8e02-2efd1c6bfe25 |  | note | Frequency - Prior to Excavation
label | afc37158-3ec8-5274-aaed-08736c0a5134 |  | note | Activity - H
label | b93725d8-e217-59aa-a3a1-0d0c1df3b950 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.01.06 - Approved Construction Drawings
label | 969607d2-8b1f-52d1-95b4-dbbbd15f7f31 |  | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | 9f1a8acb-62e5-5af0-9d23-04d851ef5e2d |  | note | Standard / Specification - Downer
label | 734fb7d6-2e90-5032-b1ee-b995225abec8 |  | note | Verifying Document - IFC Drawings
label | 2bddaf2d-18c7-574c-a4ec-d7bf8320bdec |  | note | Frequency - Prior to works start
label | d7f20f79-388c-5e1a-b7c2-09d4ffef35d1 |  | note | Activity - H
label | 353ff513-a70d-57a7-9348-35602d16f431 |  | note | By - PE
checkpoint-group |  |  | section | 6.02 Jet Grout Installation
checkpoint-status |  |  | checkpoint | 6.02.01 - Jet Grout Work Start Notification
label | 4c07f364-3199-51d4-8de7-0f1c0f22ecfa |  | note | Acceptance / Conformance Criteria - Give the Engineer at least two Working Days’ notice prior to commencement of work on-site
label | fa7d008e-34fd-5b8b-8399-abd7f4147e06 |  | note | Standard / Specification - 14AED/AD4-C - 140.1.6
label | 48da341e-090f-5bec-b5ba-d6d88a82dee6 |  | note | Verifying Document - Hold Point Release
label | 2af7eabf-4998-5c62-94b0-de0de000f50a |  | note | Frequency - 48 Hours Notice Prior to Each Occurrence
label | 05ae61b5-9055-5589-a8b4-28025d70e130 |  | note | Activity - HP
label | 4e548b91-ae80-50aa-822d-0f9cf8d18d41 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.02.02 - Setting out
label | ada62adb-e7f1-5a98-8ff8-b9d03c314361 |  | note | Acceptance / Conformance Criteria - Setting out shall be carried out from reference lines and points shown in the drawings and approved by the Engineer. Immediately before commencement of jet grouting works, the jet grout column positions shall be marked with suitable identification pins or markers.
label | d194ae37-c6af-5d17-b6ed-4d50e270231f |  | note | Standard / Specification - 14AED/AD4-C - 140.1.7 / 140.3.1
label | 4ea28953-0d77-57a6-8c24-fd6ce4e75116 |  | note | Verifying Document - Survey Records
label | 599cdd38-957e-57d8-ad1d-0e26d010ea9b |  | note | Frequency - Prior to Jet Grouting
label | 506201f0-3216-5ded-b0d4-2a7ad7a81eb8 |  | note | Activity - HP
label | 29ffd062-5661-5097-8ac1-8ec4f1e4a837 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.02.03 - Services
label | 19f64327-fab3-5c8e-900f-2686b5337cba |  | note | Acceptance / Conformance Criteria - All services and shall be located and be clearly marked out on-site by the appropriate utility authorities prior to construction commencing.
label | 7a8456db-608f-5532-9b5b-9b6328539db3 |  | note | Standard / Specification - 14AED/AD4-C - 140.1.8
label | 2ddaa016-55af-5365-b4d0-d39020cd1610 |  | note | Verifying Document - Markout Record
label | 58389081-8e89-522a-b13f-28e00553c1a3 |  | note | Frequency - Prior to Jet Grouting
label | 47554b86-ecd9-5931-8d47-a6ea36873a53 |  | note | Activity - I
label | bebbe6b3-4138-5602-bc6e-c1ccb614160a |  | note | By - SE
checkpoint-status |  |  | checkpoint | 6.02.04 - Jet Grout First Column Notification
label | ba826b3e-7faa-593c-a07a-111e66bd2b81 |  | note | Acceptance / Conformance Criteria - Give the Engineer at least two Working Days’ notice prior to Commencement of column installation within the dam;
label | 402cf302-cb4e-54a5-b886-19c9bc011ab2 |  | note | Standard / Specification - 14AED/AD4-C - 140.1.6
label | a0f556a7-d983-5b9c-8b4b-9be748338bc8 |  | note | Verifying Document - Hold Point Release
label | 97b58ae3-ec73-5f4d-b60c-e41a743fddb0 |  | note | Frequency - 48 Hours Notice Prior to Each Occurrence
label | be721ed6-d071-5229-b6e6-93df2678468a |  | note | Activity - HP
label | eab550a5-22c8-5dec-87a2-66f8eecce771 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.02.05 - Jet-Grout Cut-off Wall Inspection
label | accc90b8-07fa-53bd-8131-e1aa4473961c |  | note | Acceptance / Conformance Criteria - Jet-grout cut-off wall: full-time designer site presence during installation must be inspected by the Engineer prior to further work being carried out in the area.
label | 1a313b7a-fa0f-5a0c-b242-b3d2aceed486 |  | note | Standard / Specification - 14AED/AD4-C - 030.3
label | 30e07865-2dcd-53c6-bcc1-ee2e8d402033 |  | note | Verifying Document - Hold Point Release
label | a742523f-ebd9-5797-abe0-ed511bac2fc5 |  | note | Frequency - 48 Hours Notice Prior to Each Occurrence
label | e40cd607-a426-53c7-a4e7-0cd2dff76e3f |  | note | Activity - HP
label | bde08d20-5cc8-5c64-a437-2beb489f56e9 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.02.06 - Drilling Records
label | 52d2cc18-37d3-504e-b88d-8c0b541c67e0 |  | note | Acceptance / Conformance Criteria - Each grout hole shall be Evaluated for continuous drilling and grouting with drilling records being submitted daily to the Engineer.
label | dfb85a2c-3551-5c01-ba3d-6c13e1664436 |  | note | Standard / Specification - 14AED/AD4-C - 140.5.2.3 140.5.2.4
label | 7dde778a-764b-58b8-8463-4aa52a272d75 |  | note | Verifying Document - Daily Checksheets
label | 19bdd9ff-c112-57d0-8f48-ac6438c7ee7a |  | note | Frequency - Each grout hole
label | 32976cfa-3468-5c45-990e-314731d0f13e |  | note | Activity - C
label | 88d98dda-e5ba-5c07-a552-0f0f3cd4cfeb |  | note | By - SUP
checkpoint-status |  |  | checkpoint | 6.02.07 - Spoil Return
label | f11965ff-54c7-55d0-b6a7-40fb33f1579a |  | note | Acceptance / Conformance Criteria - Visual observation of the flow and features of the spoil shall be maintained during jet grouting.
label | 7b5efea4-3f3f-5f4c-b6a8-88d24f753ae8 |  | note | Standard / Specification - 14AED/AD4- C - 140.3.8
label | 6e68e527-675a-51c6-b544-97c76d3f3e6d |  | note | Verifying Document - Daily Checksheets
label | b90e28bc-7a17-5ae7-accc-eedbbe056867 |  | note | Frequency - Each grout hole
label | 594ad826-9714-5c53-be1f-8161cf49005a |  | note | Activity - C
label | 5b1d3126-4543-5a80-a725-bda70b49c4d6 |  | note | By - SUP
checkpoint-status |  |  | checkpoint | 6.02.08 - Overlap
label | 096884db-7980-5a08-9a63-9e9e5ea75037 |  | note | Acceptance / Conformance Criteria - Jet-grouted cut-off wall with approx. 20% overlap between each column
label | 58a406aa-2460-5d15-8d32-8c34daff05ec |  | note | Standard / Specification - DWG 14AED-AD4-116
label | 21819bd4-b1c4-5925-a2d0-48ab54ea152f |  | note | Verifying Document - Daily Checksheets
label | 7f1eb3ee-156f-5dd8-8554-5f78e86bcb80 |  | note | Frequency - Each grout hole
label | bf69f598-e220-5bc0-8d00-9fa0ea6c713b |  | note | Activity - C
label | 3695d7f0-d2e8-5588-9e9c-0778cb36a079 |  | note | By - SUP
checkpoint-status |  |  | checkpoint | 6.02.09 - Adjacent Structure Damage
label | 0a48bd6a-38fe-5bc3-8908-9ef3943aa451 |  | note | Acceptance / Conformance Criteria - If damage to the existing dam is suspected during the jet grouting operations, the work shall cease immediately, and the Engineer shall be informed.
label | dacdb34b-63bf-5a7c-8249-8aa8b47a584f |  | note | Standard / Specification - 14AED/AD4-C - 140.5.2.5
label | d634332b-4ccc-52fe-ad0b-cb12acaecc12 |  | note | Verifying Document - Daily Checksheets
label | b2e7f56e-3500-5ead-bebb-563fb7320cff |  | note | Frequency - Each grout hole
label | 63e9dc30-2c6e-5b87-8c52-6d3d46e4a559 |  | note | Activity - C
label | 3f364ddb-9b3c-5186-b798-392d764b8dca |  | note | By - SUP
checkpoint-status |  |  | checkpoint | 6.02.10 - Position
label | 394168ea-2e03-5060-a0e9-c30a8c42dcf1 |  | note | Acceptance / Conformance Criteria - The maximum permissible deviation of the centre of each grouting point from the correct centre point as shown in the setting out drawing shall be 100mm in any direction.
label | f2890206-8331-5abd-801a-d16245de9e67 |  | note | Standard / Specification - 14AED/AD4-C - 140.3.2
label | cf7198bb-dc32-5a36-83f2-835e0d2f9f20 |  | note | Verifying Document - Daily Checksheets
label | afc2eec6-92ce-5cf3-88f5-f395243d904f |  | note | Frequency - Each grout hole
label | 524c5df0-214e-520c-a187-36c5b27f5f98 |  | note | Activity - C
label | 5c85ef1d-03ad-5593-9558-79e29ae67467 |  | note | By - SUP
checkpoint-status |  |  | checkpoint | 6.02.11 - Verticality
label | 518bb5f4-eb7b-5d71-ae7b-87ea3bab1800 |  | note | Acceptance / Conformance Criteria - Jet grouting for vertical bore hole shall be carried out as near vertical as possible. The drilling rod shall not deviate by more than 1 in 100 during drilling.
label | f568e2dd-e0b8-54a7-8bd3-627a44159cfc |  | note | Standard / Specification - 14AED/AD4-C - 140.3.3
label | a304ed48-3b44-5a86-be0a-1f454fafee52 |  | note | Verifying Document - Daily Checksheets
label | 4852007b-c296-537e-8665-730abf54f6a0 |  | note | Frequency - Each grout hole
label | 55c5cb61-1fe7-5173-b24b-6a7bacb21142 |  | note | Activity - C
label | 537cc0e1-7eec-5e9d-ac94-3e64ffb94992 |  | note | By - SUP
checkpoint-status |  |  | checkpoint | 6.02.12 - Length, Diameter and Spacing of Columns
label | bd012498-2cfc-5d3e-8da6-af5c6111ba7c |  | note | Acceptance / Conformance Criteria - The length, diameter and spacing of the jet grouting columns shown on the drawings are indicative only and shall be adjusted to suit site conditions when deemed necessary.
label | 92c6e6e3-59e5-5fb5-a518-a839a74b674b |  | note | Standard / Specification - 14AED/AD4- C - 140.3.5
label | f8d15458-6149-55e5-a51f-0239dbb38337 |  | note | Verifying Document - Daily Checksheets
label | 03e1c24f-5ab1-5521-96ae-49228d601d5b |  | note | Frequency - Each grout hole
label | 304b209d-ed4c-55cf-bcde-baa5da1bf26a |  | note | Activity - C
label | 09933f24-c5d4-5d7b-96aa-f487bfbf84c1 |  | note | By - SUP
checkpoint-status |  |  | checkpoint | 6.02.13 - Jet Grouting Interruption
label | 15130126-fe61-53da-a60b-429982596bf9 |  | note | Acceptance / Conformance Criteria - If the jet grouting operation is interrupted for any reason, re-grouting may be required upon confirmation from the Engineer on site to ensure continuity of the column.
label | 0b400254-b211-53d6-82ea-d9a95216752f |  | note | Standard / Specification - 14AED/AD4- C - 140.5.2.1
label | c363f2de-0dda-52a2-af61-86d7af34df90 |  | note | Verifying Document - Daily Checksheets
label | eb9a14b7-739e-5b85-896d-71c4ce53ab4c |  | note | Frequency - Each grout hole
label | a42d798e-426b-545c-8da8-467d69edebcd |  | note | Activity - HP
label | a09f31aa-d7e0-55e5-aa47-281572e75cba |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.02.14 - Jet Grouting Cleaning
label | ee2c8cda-fd5f-5e53-8ea6-e50e85d3514d |  | note | Acceptance / Conformance Criteria - At completion of daily jet grouting operations, the site shall be thoroughly cleaned, and all spoil debris, water, and spilled material shall be disposed appropriately. Spoil stockpiling overnight is permitted prior to transfer to a predetermined waste or fill location.
label | ce14cdce-7724-5e90-aab5-77d9042c11b5 |  | note | Standard / Specification - 14AED/AD4- C - 140.5.2.1
label | 8717a7ae-4cdd-5818-a970-29dcfb4d9bde |  | note | Verifying Document - Daily Checksheets
label | 30d4a979-c16b-5187-82e6-d79db67cd703 |  | note | Frequency - Each grout hole
label | 5989d42e-ba1f-5ecd-89a1-6d9f388361dd |  | note | Activity - C
label | 10cc0632-2534-5ce7-af03-43f408c36525 |  | note | By - SUP
checkpoint-status |  |  | checkpoint | 6.02.15 - Daily Grout Density Tests
label | 82cece44-fc2e-5039-9188-ce291844a6ba |  | note | Acceptance / Conformance Criteria - The quality as well as the suitability of the fresh grout shall be constantly assured by measuring its density with a hydrometer.
label | 794c45d6-70e6-512e-98a7-4d4a2a7a7444 |  | note | Standard / Specification - 14AED/AD4-C - 140.5.2.4 / 140.4.1
label | b32bc6d7-aea0-5a9b-9e25-8f892b1df9cb |  | note | Verifying Document - Site Results
label | b5311da5-c8ce-5e0a-954a-ec8d090f8cf0 |  | note | Frequency - Daily
label | 15f1dbfb-f941-58dc-8ed6-201f7d4c46ce |  | note | Activity - C
label | 8b100782-3701-5881-8764-ecd086668372 |  | note | By - SUP
checkpoint-status |  |  | checkpoint | 6.02.16 - Daily Spoil Density Tests
label | dc7d568a-521a-530d-bf16-db45044d93aa |  | note | Acceptance / Conformance Criteria - Three cube samples shall be collected from spoil return during jetting at different levels of each column for subsequent laboratory tests.
label | 447d78b5-2cd8-5f62-b644-374c8e5ddc6a |  | note | Standard / Specification - 14AED/AD4-C - 140.5.2.4 / 140.3.8
label | 32bdf648-cf2e-519f-b8fb-016719bdfa8f |  | note | Verifying Document - Lab Report
label | b21671d7-f7c7-5eec-8710-3a0d3a0dc79c |  | note | Frequency - Daily
label | 0a820f31-5e70-53dc-9630-e72bfc709db3 |  | note | Activity - R
label | e66c6fa9-0753-557b-ac85-22694492fa00 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 6.02.17 - Weekly Grout Compressive Strength
label | bc6820b2-8d92-5fe8-806d-7e027362aedc |  | note | Acceptance / Conformance Criteria - The minimum unconfined compressive strength (28 day) of the selected working columns shall be a minimum of 2 MPa. This shall be confirmed through laboratory tests on samples collected Weekly from backflow on site.
label | 95efffa8-4b2d-5b42-bb6d-a49cc0cba83a |  | note | Standard / Specification - 14AED/AD4-C - 140.3.6 / 140.5.2.4
label | 678a4616-7c4f-5359-a7f5-95322a9e1f65 |  | note | Verifying Document - Lab Report
label | a2522085-a6e1-5305-9758-c843eb9225e8 |  | note | Frequency - Weekly
label | 1907a343-676d-52e0-b428-5bcc482cf633 |  | note | Activity - R
label | 5f0e69ea-8b24-5052-be63-07c3e496073a |  | note | By - PE
checkpoint-group |  |  | section | 10.01 Site Post Construction Activities
checkpoint-status |  |  | checkpoint | 10.01.01 - Construction Record Compilation
label | e65b0100-b5d8-552a-a259-b303768162ed |  | note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
label | 230c756a-720a-5969-a651-b2fb450f41b5 |  | note | Standard / Specification - Downer
label | fc043049-d918-572e-9cb8-c8c132ba7dd2 |  | note | Verifying Document - Records
label | 504a7bbb-1736-53e6-978a-1598f16621c7 |  | note | Frequency - Post construction
label | 167f3617-6646-5a8b-96b7-d59527ba76a9 |  | note | Activity - H
label | 08853699-6e0e-55d4-bb98-e13edd75e9cc |  | note | By - SE
checkpoint-status |  |  | checkpoint | 10.01.02 - Survey Records
label | ae616771-42b0-525b-96b0-54e50e971bc4 |  | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
label | 77084a6b-a55b-5d3b-9d1c-52b286fc3567 |  | note | Standard / Specification - Downer P&G 20.1
label | 02e21bd9-a78f-5f80-9fb2-cc4371f2c676 |  | note | Verifying Document - Records
label | 91fdbbd5-c2e6-5cb5-b7df-1e8fd71b78a7 |  | note | Frequency - Post construction
label | 16c32516-7664-56a7-8207-0f5be4a842dc |  | note | Activity - H
label | b26f7a53-fb71-5cb0-aa18-22a294d2bf14 |  | note | By - SV
checkpoint-status |  |  | checkpoint | 10.01.03 - Redline Drawings
label | a61e2787-e2b6-56db-9d18-20dc84d0d081 |  | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. Red-pen mark-up copies of the Drawings and Specifications and other design documentation showing any deviations from the specified details and requirements produced in accordance with industry good practice.
label | 974188f6-7f1e-54cc-8984-fc81ce8e1df0 |  | note | Standard / Specification - Downer P&G 20.1
label | 53423a98-ba11-541b-99cf-0890f934defd |  | note | Verifying Document - Redlines
label | d2bbd8b5-d717-5025-ad53-f485e1b9cee7 |  | note | Frequency - Post construction
label | edf0fb85-7a51-5546-afd6-c7e0bc01bf7b |  | note | Activity - H
label | b1550515-f847-5c92-9649-b5ae90eace08 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 10.01.04 - Defect, Snag and Punch List
label | aeeef459-0f28-59eb-949e-893dac36a6a7 |  | note | Acceptance / Conformance Criteria - Update the project Defect, Snag and Punch List Register
label | d58fc400-bb2a-5a5c-bec8-cda72be46141 |  | note | Standard / Specification - Downer
label | fe288a98-5d10-5a7e-a60b-11f6ea363c01 |  | note | Verifying Document - Register
label | 1d141bef-af6a-5bb0-abb7-4e983b0b75dd |  | note | Frequency - Post construction
label | 6f30a09e-215d-51a2-a5b9-510233e2e987 |  | note | Activity - H
label | e3681fa5-c4e5-5111-abd4-24c935bdfd6b |  | note | By - PE
checklist-sectioned |  |  | checklist | DS2672-ITP-S102 - Rev 1 - Jet Grout Trial Columns |  |  |  |  | Yes | DS2672-ITP-S102 - Jet Grout Trial Columns - Rev 1 | 6c6b8741-c2d5-40f1-a5d3-911f7aaf10dc
checkpoint-group |  |  | section | 3.01 Site Requirements
checkpoint-status |  |  | checkpoint | 3.01.01 - Construction Pack
label | b8869eb6-2974-5114-9ad3-7761177899f5 |  | note | Acceptance / Conformance Criteria - Submit a Construction Pack including a Methodology and JESA to the Engineer before works
label | c01b26c4-df7e-5fca-8678-4d7ec13a0d61 |  | note | Standard / Specification - Downer
label | ad715a6f-e510-5d0a-af0c-8c6ffa7c4eeb |  | note | Verifying Document - Construction Pack
label | eea2b2dd-3adf-56f6-84d8-587822ae4890 |  | note | Frequency - Submit Prior to commencement of works
label | d773901a-f047-59b7-98f2-f3d01f48dd6b |  | note | Activity - H
label | da4a65db-cfbc-5268-a896-9e1d8369ab2d |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.01.02 - Survey Setout
label | b63370e5-5cf1-580f-a4ec-88ea8b6a73db |  | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
label | 9c58a725-aa09-5694-9831-77df88feece3 |  | note | Standard / Specification - Downer
label | b35459d2-9c2b-5687-aa50-1ee4bff5d503 |  | note | Verifying Document - Survey Records
label | 2489d652-d3ff-5a53-a203-b522b2adf08a |  | note | Frequency - Prior to Works
label | 367efa8e-37f5-521f-b456-994f5562db4b |  | note | Activity - H
label | 6b30348e-74c7-5b55-8661-855dc00dabbe |  | note | By - SV
checkpoint-status |  |  | checkpoint | 3.01.03 - Service Location
label | 09bbe2c2-7885-5f31-9510-fb9dafe4eb82 |  | note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
label | 17788d64-342d-58f1-8cf2-ab2065940058 |  | note | Standard / Specification - Downer
label | 81c4fe83-1907-56ce-9553-4eb131663003 |  | note | Verifying Document - Excavation Permit
label | b0f8069e-10cf-5a5c-b786-7e83c1c88346 |  | note | Frequency - Prior to Excavation
label | e7af6958-4927-56b0-ab63-cbf341558ca0 |  | note | Activity - H
label | 3714d652-cfef-55e6-a019-544c5c792833 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 3.01.04 - Internal Permits
label | 68909a69-d858-5c97-a46c-587e54902278 |  | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
label | 735822d4-c4d3-5e95-881d-97a4f526116d |  | note | Standard / Specification - Downer
label | ca0a8629-c89e-598f-aa86-dcd907eaacae |  | note | Verifying Document - Internal Permits
label | 9ffc016d-144e-5e0d-b916-7a4c4be9231a |  | note | Frequency - Prior to Excavation
label | d6718158-e31d-51d4-8223-d3a4d6d083fd |  | note | Activity - H
label | e313d5b6-59cb-5736-9873-6acbf71c128b |  | note | By - SE
checkpoint-status |  |  | checkpoint | 3.01.05 - External Permits
label | 24134141-83fb-59c6-969f-c1367971370f |  | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
label | 17208da2-7439-5c64-896a-33c2495ef3da |  | note | Standard / Specification - Downer
label | d55c7e25-c2fc-5974-990b-9932212459e5 |  | note | Verifying Document - External Permits
label | 09731e45-9c41-5b92-b974-cccf039293f8 |  | note | Frequency - Prior to Excavation
label | 890cd651-5762-58af-a364-eeb7bdcd8fbd |  | note | Activity - H
label | 644cb1d7-20cf-5b4c-afd0-89a0bdbd313b |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.01.06 - Approved Construction Drawings
label | 9e71687c-c9d8-5f23-b7b0-a44f9806ed44 |  | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | cf0c9679-91fd-5aa0-837e-2b0d974d9a26 |  | note | Standard / Specification - Downer
label | 28e69320-6380-5a7d-949b-c43ffeefa695 |  | note | Verifying Document - IFC Drawings
label | 6eae0ab1-b5ad-5484-8b35-f3f111585022 |  | note | Frequency - Prior to works start
label | 06a78d1d-0001-5ba6-85cf-e303995ec768 |  | note | Activity - H
label | 0f7dbae9-23b1-5f40-899a-efd5efbe1c8a |  | note | By - PE
checkpoint-group |  |  | section | 6.01 Jet Grout Trial Columns
checkpoint-status |  |  | checkpoint | 6.01.01 - Jet Grout Methodology
label | 7d00df6b-8447-512b-a942-4818f107d08c |  | note | Acceptance / Conformance Criteria - Before starting the jet grouting works, a method statement shall be submitted.
label | 4954c7df-8bd9-5dd4-8ed3-11851ecead93 |  | note | Standard / Specification - 14AED/AD4-C - 115.1.11 / 140.5.1.1
label | a7fd506f-6d8f-5694-b050-8fa51e453c58 |  | note | Verifying Document - Method Statement
label | 1e3a7ba0-6163-5158-a7eb-49714daea6d3 |  | note | Frequency - Prior to Trial
label | 319fff97-d17e-50d4-b150-b0924188d9c3 |  | note | Activity - R
label | dc585efc-2be4-5cfd-a879-758b59c8219c |  | note | By - PE
checkpoint-status |  |  | checkpoint | 6.01.02 - Supervision
label | 996edaf4-0428-5f5a-8dbc-8e212f1cd6fb |  | note | Acceptance / Conformance Criteria - Execution shall be supervised by trained and experienced personnel.
label | b44b1d9e-2fd1-567f-9759-fbcab9a0785f |  | note | Standard / Specification - 14AED/AD4-C - 140.5.2.2
label | ebec093c-aba4-5b8f-96b7-a43e976c4074 |  | note | Verifying Document - Site Records
label | 04a9f4da-1661-5b6a-a67d-99e9761aceb0 |  | note | Frequency - Each Column
label | f3f2d723-b219-507b-ace6-0bbb47e36e14 |  | note | Activity - R
label | f76ac9fc-5b94-5116-9981-eff73c71a116 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 6.01.03 - Jet Grout Work Start Notification
label | 5dc748e1-93e5-5ce3-a801-2c74f02fb33c |  | note | Acceptance / Conformance Criteria - Give the Engineer at least two Working Days’ notice prior to commencement of work on-site
label | 17da409c-a0e1-5124-a732-aaf417d5dece |  | note | Standard / Specification - 14AED/AD4-C - 140.1.6
label | c47e0e08-ec41-5d58-bfc8-51bb6282c2f2 |  | note | Verifying Document - Hold Point Release
label | f6ee8fb7-3900-50e9-8223-85e818962bf5 |  | note | Frequency - 48 Hours Notice Prior to Each Occurrence
label | 282f9eb9-28f6-5879-8c2d-a896188a371d |  | note | Activity - HP
label | 200b4e82-a0df-50c5-8ff9-564c194d8cc9 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.01.04 - Jet-grout Onsite Trial Inspection
label | 2a148728-78bd-57f9-b6c9-317bc6c6f29b |  | note | Acceptance / Conformance Criteria - Jet-grout onsite trial away from the dam must be inspected by the Engineer prior to further work being carried out in the area.
label | 271f1c8e-c634-5ec6-96ab-5a8bcff1cf84 |  | note | Standard / Specification - 14AED/AD4-C - 030.3
label | 6114bf65-fe45-580a-bac0-b587d31a0e31 |  | note | Verifying Document - Hold Point Release
label | f36ba862-8632-58d6-b35d-91f583c3e54f |  | note | Frequency - 48 Hours Notice Prior to Each Occurrence
label | 08f82004-5e88-59cf-bcad-2c0a964accaa |  | note | Activity - HP
label | 962d5561-0258-5c88-8c6d-e994544be93c |  | note | By - ENG
checkpoint-status |  |  | checkpoint | 6.01.05 - Trail Location
label | 55cf8c98-ae38-5666-98c8-dd74bb65c7b0 |  | note | Acceptance / Conformance Criteria - The trial location will be agreed upon by the nominated Contractor and the Engineer and shall consist of a single module of at least two jet grout columns to 4m depth.
label | 04a02c67-470a-5d6a-b30f-33873d2c5389 |  | note | Standard / Specification - 14AED/AD4-C - 140.2.3
label | fbb12b1d-624e-5342-a616-49f47494c483 |  | note | Verifying Document - Survey Records
label | f60bb0ae-fa9a-5731-b4d4-e2ff282a4c68 |  | note | Frequency - Each Column
label | ccc93222-eef4-5602-a654-5879e1126e67 |  | note | Activity - D
label | cb598002-26ab-5627-8dbd-0f4f45218ecc |  | note | By - SV
checkpoint-status |  |  | checkpoint | 6.01.06 - Trial Details
label | 1d2f6615-ef54-5f20-8046-ed4faa6201a1 |  | note | Acceptance / Conformance Criteria - Tests will be performed at the centre of the module prior to and after grouting. Where excavation is possible, assessment of the geometric and mechanical characteristics of the jet grout column should be made by visual inspection. Laboratory tests on samples recovered by coring or excavation can be made.
label | 64d6fb56-6dcd-55f4-8c14-189ab1c41dcc |  | note | Standard / Specification - 14AED/AD4-C - 140.2.3 / 140.5.2.3 / 140.5.2.4
label | 79685e3f-2add-595b-8f32-498e605a29dd |  | note | Verifying Document - Trail Records
label | e005a387-a5fd-58f3-b2a3-a5fdf70ce7e3 |  | note | Frequency - Each Column
label | fd2cf483-73c2-5383-86d6-ae659eea736c |  | note | Activity - I
label | cf6a5a6f-d9df-5bb2-a299-1921f9b5922d |  | note | By - SE
checkpoint-status |  |  | checkpoint | 6.01.07 - Trail Results
label | 6dc106e3-eab4-5f45-aad4-787e48cfd24e |  | note | Acceptance / Conformance Criteria - If the trial indicates that the required design parameters has not been achieved, the nominated Contractor shall revise the Work Procedure Plan and re-test.
label | 0248acb4-f69e-56bd-93a3-c14cd02b8ba1 |  | note | Standard / Specification - 14AED/AD4-C - 140.2.3
label | 553b4a85-af3d-5552-9cac-83a3929e8c1b |  | note | Verifying Document - Trial Report
label | b17b6699-db06-54c9-9c5c-5dbd6511cd87 |  | note | Frequency - Prior to Production
label | e216ce5a-3daf-5f4e-958d-2d5394891eef |  | note | Activity - R
label | df799e7c-b12c-5544-8a12-85632a3d2405 |  | note | By - PE
checkpoint-group |  |  | section | 10.01 Site Post Construction Activities
checkpoint-status |  |  | checkpoint | 10.01.01 - Construction Record Compilation
label | 64803cfa-298e-5558-b077-27521ce137c5 |  | note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
label | 019384f9-34d1-5bbc-8856-59d3c0910516 |  | note | Standard / Specification - Downer
label | 0099d855-0310-5f7f-aa89-0376769e3fe2 |  | note | Verifying Document - Records
label | df5e33d3-dc32-5aeb-80eb-7711e16ca2ed |  | note | Frequency - Post construction
label | 94d057dc-9a95-58e3-8ac0-4560e24ac2e2 |  | note | Activity - H
label | eec43fb2-4358-57fe-88e7-627959757af8 |  | note | By - SE
checklist-sectioned |  |  | checklist | DS2672-ITP-S101 - Rev 1 - Jet Grouting Materials |  |  |  |  | Yes | DS2672-ITP-S101 - Jet Grouting Materials - Rev 1 | d23dfd72-9434-4cff-954b-1735b40f6290
checkpoint-group |  |  | section | 4.06 Jet Grouting Materials
checkpoint-status |  |  | checkpoint | 4.06.01 - Grouting Equipment
label | 6b205fe1-f6ab-5575-a144-0d81255fe9f9 |  | note | Acceptance / Conformance Criteria - Jet grouting equipment meet the requirements set out in the specification
label | ee980eab-4d33-5f70-ad3f-32e9108efaf5 |  | note | Standard / Specification - 14AED/AD4-C - 140.3.7
label | ee0ae534-121f-5bc3-abec-55269920da0a |  | note | Verifying Document - Datasheet
label | 1ef8e8a8-d063-5d2f-a78d-56e8678ce515 |  | note | Frequency - Prior to commencement of work.
label | 3089994a-d64c-5c96-8f51-cb91d9d559ac |  | note | Activity - R
label | 644c8413-f9e0-5892-9952-eb4ec6a72f8a |  | note | By - PE
checkpoint-status |  |  | checkpoint | 4.06.02 - Personnel
label | 73d9478c-3cdd-5e1c-84eb-adff980c8e4e |  | note | Acceptance / Conformance Criteria - The nominated Contractor shall employ only personnel experienced in jet grouting for this part of the Works.
label | f40756bc-f5d4-5054-b539-78292575166d |  | note | Standard / Specification - 14AED/AD4-C - 140.3.4
label | 61f550fc-c09a-5bf1-a0ef-18b8cdfdbab9 |  | note | Verifying Document - Training Records
label | 720af314-3a4e-5160-b5dc-31959c592355 |  | note | Frequency - Prior to commencement of work.
label | ea2a8cb3-05a6-52fd-bd2b-0f4de82fa70e |  | note | Activity - R
label | 6dc2a66c-6f9b-5d7b-af17-edbed4e743d2 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 4.06.03 - Grout Mix Design
label | 7ff5b532-81ec-54ca-baf4-7c7d8c06c936 |  | note | Acceptance / Conformance Criteria - The cement grouts shall comprise Portland cement, water and occasionally bentonite or additives as approved by the Engineer. The minimum unconfined compressive strength (28 day) of the selected working columns shall be a minimum of 2 MPa.
label | a5496a32-74f7-5e29-b7d3-561a2a85102e |  | note | Standard / Specification - 14AED/AD4-C - 140.4.1
label | a5ea86e1-ed28-5d42-bc28-cfcd1cffee8b |  | note | Verifying Document - Approved Mix Design
label | 5bee8560-daa9-509c-b2d8-4caf3aae30db |  | note | Frequency - Prior to commencement of Trials
label | 446b9b27-49aa-5462-bd2e-8fe1975abe91 |  | note | Activity - HP
label | 87ae4b3e-e981-5fbc-80d7-750612ff3e3b |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT