## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | DS2672-ITP-S105 - Pile Construction Card - Rev 1 | itp |  |  |  |  | DS2672-ITP-S105 - Pile Construction Card - Rev 1
section | 7.02 Setout and Excavation - (Pile Construction Card)
checkpoint | 7.02.01 - Pile Set Out
note | Acceptance / Conformance Criteria - The position of all piles shall be accurately set out and checked by a suitably experienced surveyor prior to installation
note | Standard / Specification - 51/33669 - 3.7
note | Verifying Document - Survey Records:
note | Frequency - Each Pile
note | Activity - D
note | By - SV
textbox | Location Co-Ordinate - X:
textbox | Location Co-Ordinate - Y:
textbox | Ground Surface Elevation - RL:
textbox | Expected Stratum Elevation - RL:
checkpoint | 7.02.02 - Nature of Ground and Subsurface Conditions
note | Acceptance / Conformance Criteria - The Constructor shall inform the Designer where circumstances indicate that ground and / or groundwater conditions differ from those presented in the reports, indicated on the Drawings or interpreted from proof bores.
note | Standard / Specification - 51/33669 - 3.5
note | Verifying Document - Notice
note | Frequency - Ongoing
note | Activity - S
note | By - SE
checkpoint | 7.02.03 - Pile Logging Inspection
note | Acceptance / Conformance Criteria - The logging of selected piles shall also be undertaken by the Designer to agree with the Constructor in identifying the founding stratum.
note | Standard / Specification - 51/33669 - 6.2.2
note | Verifying Document - Site Log
note | Frequency - Each Pour
note | Activity - W
note | By - ENG
note | Comments / Closeout Details - Add First Pile Hold Points Checksheet and / or Selected Logging Hold Points Checksheet as required.
checkpoint | 7.02.04 - Pile Logging
note | Acceptance / Conformance Criteria - The Constructor shall keep an excavation log for each pile that records the types of materials encountered and the depths at which those materials were encountered and any groundwater levels and inflows inside the pile
note | Standard / Specification - 51/33669 - 6.2.2
note | Verifying Document - Site Log
note | Frequency - Each Pour
note | Activity - I
note | By - SE
textbox | Casing Type - Permanent or Temporary:
textbox | Casing Finished elevation top (RL):
textbox | Casing Finished elevation bottom (RL):
textbox | Casing Depth (m):
textbox | Casing Thickness (mm):
textbox | Excavation Commencement - Date and Time:
textbox | Detail Materal Type and when it Chages - Type and Depth:
textbox | The Depth to the Founding Stratum (m)
textbox | Actual Stratum Elevation (RL):
textbox | Water Ingress - Depth (m) and Details:
textbox | Excavation Completion - Date and Time:
checkpoint | 7.02.05 - Pile Dimensions
note | Acceptance / Conformance Criteria - Constructed piles shall not deviate outside the tolerances, unless otherwise shown on the Drawings or as accepted by the Designer.
note | Standard / Specification - 51/33669 - 3.8.1
note | Verifying Document - Site Record
note | Frequency - Each Pile
note | Activity - D
note | By - SV / SE
textbox | Actual Diameter:
textbox | Actual Length:
checkpoint | 7.02.06 - Pile Pumping
note | Acceptance / Conformance Criteria - Pumping from pile excavations are permitted provided the Constructor can demonstrate that the excavation has been sealed against further water entry (e.g. through sufficient keying into rock) or that the pile excavation is stable and will allow pumping to take place without ground disturbance below or around the pile.
note | Standard / Specification - 51/33669 - 6.2.1
note | Verifying Document - Site Record
note | Frequency - Each Pour
note | Activity - I
note | By - SE
checkpoint | 7.02.07 - Full Length of Pile
note | Acceptance / Conformance Criteria - Unless shown otherwise on the Drawings, each pile shall be in intimate contact with the ground over its full length.
note | Standard / Specification - 51/33669 - 6.2.3
note | Verifying Document - Site Record
note | Frequency - Each Pour
note | Activity - I
note | By - SE
checkpoint | 7.02.08 - Pile Hole Side Cleaning
note | Acceptance / Conformance Criteria - On completion of the pile excavation and immediately prior to installation of the reinforcement cage Loose and / or smeared material shall be removed from the sides of the rock socket
note | Standard / Specification - 51/33669 - 6.3.1
note | Verifying Document - Site Record
note | Frequency - Prior to installation of the reinforcement cage
note | Activity - I
note | By - SE
checkpoint | 7.02.09 - Pile Hole Base Cleaning
note | Acceptance / Conformance Criteria - On completion of the pile excavation and immediately prior to installation of the reinforcement cage Loose, disturbed and / or softened materials and any sedimentation shall be removed from the pile base
note | Standard / Specification - 51/33669 - 6.3.1
note | Verifying Document - Site Record
note | Frequency - Prior to installation of the reinforcement cage
note | Activity - I
note | By - SE
checkpoint | 7.02.10 - Pile Hole Inspection and Acceptance
note | Acceptance / Conformance Criteria - The reinforcement cage shall not be installed, nor concreting begin for any pile, until the as-built founding level of the pile, the condition of the rock socket (where relevant) and the condition of the pile base has been accepted by the Designer
note | Standard / Specification - 51/33669 - 6.3.2
note | Verifying Document - Hold Point Release
note | Frequency - Each Pile
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 7.03 Permanent Casings - (Pile Construction Card)
checkpoint | 7.03.01 - Pile Annulus
note | Acceptance / Conformance Criteria - Permanent casings shall be installed in such a manner as to minimise any annulus between the outside of the casing and the in-situ ground.
note | Standard / Specification - 51/33669 - 6.1.1
note | Verifying Document - Site Records
note | Frequency - Each Pile Post Installation
note | Activity - D
note | By - SE
checkpoint | 7.03.02 - Installed Casing Profile
note | Acceptance / Conformance Criteria - The installed casing profile shall be circular, with a deviation from the specified completed pile diameter of not greater than +5%, –0% of the pile diameter and with no distortions, dents, gouges or similar.
note | Standard / Specification - 51/33669 - 6.1.1
note | Verifying Document - Site Records
note | Frequency - Each Pile Post Installation
note | Activity - D
note | By - SE
section | 7.04 Temporary Casings - (Pile Construction Card)
checkpoint | 7.04.01 - Up-stand
note | Acceptance / Conformance Criteria - As a minimum, an up-stand of temporary casing of at least 1 m above existing ground level shall be provided to prevent material falling into and contaminating the pile bore prior to and during excavation and concreting works.
note | Standard / Specification - 51/33669 - 6.1.2
note | Verifying Document - Site Records
note | Frequency - Each Pile
note | Activity - S
note | By - SE
checkpoint | 7.04.02 - Annulus Extra Concrete
note | Acceptance / Conformance Criteria - Prior to the temporary casing being extracted, concrete shall be poured to the pile cut-off level plus the minimum over-cast allowance plus an allowance for the volume of annulus created by the extracted casing.
note | Standard / Specification - 51/33669 - 6.1.2
note | Verifying Document - Site Records
note | Frequency - Prior to the temporary casing being extracted
note | Activity - I
note | By - SE
checkpoint | 7.04.03 - Extraction Top-up Concrete
note | Acceptance / Conformance Criteria - When the temporary casing is being extracted, a sufficient quantity of concrete shall be maintained within such that the pressure from external water or soil is exceeded and that the pile concrete is not reduced in section or contaminated.
note | Standard / Specification - 51/33669 - 6.1.2
note | Verifying Document - Site Records
note | Frequency - Each Pour
note | Activity - S
note | By - SE
checkpoint | 7.04.04 - Temporary casing Removal
note | Acceptance / Conformance Criteria - The temporary casing shall be extracted whilst the concrete within the pile remains sufficiently workable such that the concrete is not lifted. The temporary casing shall be removed vertically without applying lateral force. The rate of extraction shall not exceed 1 m per 5 seconds. The time at which the temporary casing is extracted shall be recorded by the Constructor.
note | Standard / Specification - 51/33669 - 6.1.2
note | Verifying Document - Site Records
note | Frequency - Each Casing
note | Activity - S
note | By - SE
checkpoint | 7.04.05 - Permanent Temporary Casings
note | Acceptance / Conformance Criteria - Temporary casings that are in contact with concrete and which are not withdrawn prior to the initial set of the concrete has taken place, shall be left in place and the Designer notified.
note | Standard / Specification - 51/33669 - 6.1.2
note | Verifying Document - Site Records
note | Frequency - Each Occurrence
note | Activity - M
note | By - SE
section | 7.05 Concreting in Dry Conditions (Preferred) - (Pile Construction Card)
checkpoint | 7.05.01 - Dry Hole Concrete Placement
note | Acceptance / Conformance Criteria - Where a dry excavation can be maintained and the depth of water at the base of the pile at the commencement of concrete placement is less than 25 mm, concrete may be chuted into piles and allowed to free-fall to the pile base by no more than 5 m and without striking the pile reinforcement cage.
note | Standard / Specification - 51/33669 - 6.5.2
note | Verifying Document - Pile Construction Record Card
note | Frequency - Each Dry Pile Pour
note | Activity - I
note | By - PE
checkpoint | 7.05.02 - Groundwater Inflow Measurement
note | Acceptance / Conformance Criteria - Unless clearly not significant, the rate of groundwater inflow shall be measured prior to placing concrete. Concrete shall be placed using under water concreting techniques, unless otherwise accepted by the Designer, when The rate of groundwater inflow compared to the rate of concrete placement is such that more than 5 litres of groundwater per cubic metre of concrete could be incorporated into the completed pile, or when The depth of water at the base of the pile at the commencement of concrete placement is more than 25 mm.
note | Standard / Specification - 51/33669 - 6.5.2
note | Verifying Document - Pile Construction Record Card
note | Frequency - Each Dry Pile Pour
note | Activity - I
note | By - PE
section | 7.06 Concreting under water (Alternative) - (Pile Construction Card)
checkpoint | 7.06.01 - Concreting Under Water - Timing
note | Acceptance / Conformance Criteria - The time taken between placement of the reinforcement cage and commencement of concreting shall not exceed 4 hours. Reasonable efforts must be made to achieve this requirement. Where this requirement cannot be reasonably met, then the Designer shall re-check pile cleanliness and, if deemed necessary, the Constructor shall re-clean the pile immediately prior to concreting.
note | Standard / Specification - 51/33669 - 6.5.3
note | Verifying Document - Pile Construction Record Card
note | Frequency - Each Wet Pile Pour
note | Activity - R
note | By - PE
checkpoint | 7.06.02 - Concreting Under Water - Loss of Immersion of Discharge Pipe
note | Acceptance / Conformance Criteria - When the immersion of the discharge pipe is lost during concreting (for example, to repair breakages or to remove a blockage), further placement of concrete shall not proceed unless The concrete into which fresh concrete is to be placed has maintained its workability, The discharge pipe is re-immersed sufficiently deep into the previously placed concrete, and No water or other contaminant is introduced into concrete that will remain below the final pile cut-off level. If these conditions cannot be met, concrete placement shall be suspended, the discharge pipe shall be removed and alternative measures shall be agreed with the Designer to form a sound pile.
note | Standard / Specification - 51/33669 - 6.5.3
note | Verifying Document - Pile Construction Record Card
note | Frequency - When Required
note | Activity - R
note | By - PE
section | 7.07 Pile Concreting - (Pile Construction Card)
checkpoint | 7.07.01 - Cleaning of the Excavated Pile Bore
note | Acceptance / Conformance Criteria - Cleaning of the excavated pile bore, as specified in subsection 6.3.1 of this Specification, shall be completed immediately prior to the installation of the reinforcement cage.
note | Standard / Specification - 51/33669 - 6.4
note | Verifying Document - Site Record
note | Frequency - Each Pile Prior to the Cage Installation
note | Activity - I
note | By - PE
checkpoint | 7.07.02 - Cleanliness State of the Pile Excavation
note | Acceptance / Conformance Criteria - The Constructor shall confirm, prior to the commencement of concreting, that the cleanliness state of the pile excavation has been maintained at the level required by this Specification and no circumstances have arisen that could change the condition at the base of the pile.
note | Standard / Specification - 51/33669 - 6.5.1
note | Verifying Document - Site Record
note | Frequency - Each Pile Prior to the Commencement of Concreting
note | Activity - I
note | By - PE
checkpoint | 7.07.03 - Loose and / or disturbed material during pour
note | Acceptance / Conformance Criteria - No loose and / or disturbed material shall remain along the sides of the pile excavation nor lie at the pile base when concreting is started, nor be permitted to fall into the concrete as concreting proceeds.
note | Standard / Specification - 51/33669 - 6.3.1
note | Verifying Document - Site Record
note | Frequency - Each Pile
note | Activity - I
note | By - SE
checkpoint | 7.07.04 - Reinforcement Cage Cover
note | Acceptance / Conformance Criteria - Pile reinforcement cages shall be located centrally within the pile excavation, such that final concrete cover to the extremities of the reinforcement cages is not less than 75 mm at any location.
note | Standard / Specification - 51/33669 - 3.8.2
note | Verifying Document - Site Record
note | Frequency - Each Pile
note | Activity - D
note | By - SV / SE
checkpoint | 7.07.05 - Pile Head casting Level
note | Acceptance / Conformance Criteria - The heads of bored piles shall be over-cast by a minimum of 300 mm (concreting in dry conditions) / 1000 mm (concreting under water) above the cut-off levels.
note | Standard / Specification - 51/33669 - 3.8.3
note | Verifying Document - Site Record
note | Frequency - Each Pile
note | Activity - D
note | By - SV / SE
checkpoint | 7.07.06 - Concreting Timing
note | Acceptance / Conformance Criteria - Concreting shall commence in a timely manner following installation of the reinforcement cage to minimise the potential for water ingress and/or collapse of the hole and/or sedimentation on the pile base, all of which could adversely affect the performance of the completed pile. Where it is suspected that these adverse conditions exist, the Designer shall re-check pile cleanliness and, if deemed necessary, the Constructor shall re-clean the pile immediately prior to concreting
note | Standard / Specification - 51/33669 - 6.5.1
note | Verifying Document - Site Record
note | Frequency - Each Pile
note | Activity - W
note | By - ENG
checkpoint | 7.07.07 - Pile Concrete Compaction
note | Acceptance / Conformance Criteria - The concrete in the upper 2 m of the pile is to be thoroughly compacted using vibrators.
note | Standard / Specification - 51/33669 - 6.5.1
note | Verifying Document - Site Record
note | Frequency - Each Pour
note | Activity - R
note | By - PE
checkpoint | 7.07.08 - Piling Timing
note | Acceptance / Conformance Criteria - The time period between commencement of pile excavation and completion of concreting shall not exceed 24 hours
note | Standard / Specification - 51/33669 - 6.2.1
note | Verifying Document - Site Record
note | Frequency - Concreting shall not exceed 24 hours
note | Activity - S
note | By - SE
section | 8.02 Concrete Pour - (Pile Construction Card)
checkpoint | General Details
textbox | Pre Pour Date
textbox | Concrete Strength (mPa)
textbox | Volume (m3)
textbox | Mix Design
textbox | Additives
checkpoint | Reinforcing has been checked and conforms to the drawings included:
textbox | Bar Size & Grade, Lap Lengths, Lap Locations, Bar Supports, Bar Spacing, Cover
checkpoint | 8.02.03 - Reinforcement Washdown
note | Acceptance / Conformance Criteria - Washdown all steel reinforcement prior to pouring concrete to remove salts.
note | Standard / Specification - RSV - CS - 1.19
note | Verifying Document - Pre-Pour Checksheet
note | Frequency - Prior to Pour
note | Activity - R
note | By - SE
checkpoint | 8.02.04 - Pre-Pour Inspections
note | Acceptance / Conformance Criteria - Pouring of any concrete must be inspected by the Engineer prior to further work being carried out in the area.
note | Standard / Specification - P&G 14
note | Verifying Document - Signed Pre-Pour
note | Frequency - 48 Hours Notice Prior to Each Occurrence
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Pour Details
textbox | Pour Commencement Date and Time:
textbox | Weather
textbox | Water level in pile from top - Distance from top of casing (m)
textbox | Break in Continuity
textbox | Tremie pipe to elevation - Distance from top of casing (m)
textbox | Concrete top elevation - Distance from top of casing (m)
textbox | Actual concrete volume
textbox | Pour Completion Date and Time:
textbox | Casing removal - Date and Time:
checkpoint | 8.02.05 - Delivery Dockets
note | Acceptance / Conformance Criteria - The delivery docket of each batch delivered certifying the mix designation, cement type, specified strength, slump, date, mixing time, water added during batching and maximum aggregate size.
note | Standard / Specification - RSV - CS - 1.9
note | Verifying Document - Dockets
note | Frequency - Each Pour
note | Activity - R
note | By - PE
checkpoint | 8.02.06 - Slump Testing
note | Acceptance / Conformance Criteria - Slump tests shall be taken for each delivery of concrete and the results recorded by the Contractor.
note | Standard / Specification - RSV - CS - 1.12
note | Verifying Document - Pre Pour
note | Frequency - Each Pour
note | Activity - R
note | By - PE
checkpoint | 8.02.07 - Compression Testing
note | Acceptance / Conformance Criteria - A set of specimens for concrete tests shall consist of four specimens from each major pour of concrete, one of which shall be tested at 7 days and the remaining three at 28 days after casting.
note | Standard / Specification - RSV - CS - 1.12
note | Verifying Document - Test Results
note | Frequency - Each Pour
note | Activity - R
note | By - PE
section | 7.08 Pile Post Pour - (Pile Construction Card)
checkpoint | 7.08.01 - Pile Head Break Back
note | Acceptance / Conformance Criteria - Pile heads shall be broken back to achieve A slightly convex profile so that the middle of the pile is nominally 25 mm above the average level at the perimeter of the pile and A Type B construction joint in accordance with standard NZS3109:1997.
note | Standard / Specification - 51/33669 - 3.8.3
note | Verifying Document - Pile Construction Record Card
note | Frequency - Each Pile
note | Activity - I
note | By - SE
checkpoint | 7.08.02 - Pipe Asbuilting
note | Acceptance / Conformance Criteria - On completion of pile installation and prior to incorporating any piles into the permanent works, the actual pile locations and verticality shall be confirmed by a suitably experienced surveyor.
note | Standard / Specification - 51/33669 - 3.7
note | Verifying Document - Survey Records
note | Frequency - 5 working days prior to incorporating any piles into the permanent works.
note | Activity - D
note | By - SV
checkpoint | 7.08.03 - Bored Pile Construction Record Card
note | Acceptance / Conformance Criteria - Pile construction records shall be submitted to the Designer within 24 hours of completion of any particular pile. Copies of the records shall be retained on site and made available for inspection by the Designer as required.
note | Standard / Specification - 51/33669 - 7
note | Verifying Document - Pile Construction Record Card
note | Frequency - Within 24 hours of completion of any particular pile
note | Activity - W
note | By - ENG