## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | DS2672-ITP-S106 - Piling First Pile Hold Points - Rev 1 | itp |  |  |  |  | DS2672-ITP-S106 - Piling First Pile Hold Points - Rev 1
section | 7.07 First Pile at Every Structure
checkpoint | 7.07.01 - Inspection of any Reinforcement Cage Extension
note | Acceptance / Conformance Criteria - Designer inspection of reinforcement cage extensions for the first pile at every structure with the Opportunity to inspect (at random for subsequent piles at the same structure).
note | Standard / Specification - 51/33669 - 9.4
note | Verifying Document - Reinforcement Cage Inspection Record
note | Frequency - First pile at every structure with the Opportunity to inspect remainder
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.07.02 - Inspection of Reinforcement Cages Prior to Installation
note | Acceptance / Conformance Criteria - Designer inspection of the reinforcement cage for the first pile at every structure with the Opportunity to inspect (at random for subsequent piles at the same structure).
note | Standard / Specification - 51/33669 - 9.4
note | Verifying Document - Reinforcement Cage Inspection Record
note | Frequency - First pile at every structure with the Opportunity to inspect remainder
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.07.03 - Concreting of Piles
note | Acceptance / Conformance Criteria - Designer inspection of concreting for the first pile at every structure with the Opportunity to inspect (at random for subsequent piles at the same structure).
note | Standard / Specification - 51/33669 - 9.4
note | Verifying Document - Pile Construction Record Card
note | Frequency - First pile at every structure with the Opportunity to inspect remainder
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.07.08 - Pile Head Initial Inspection
note | Acceptance / Conformance Criteria - Designer inspection of the pile head prior to incorporation into the connecting structure for the first pile at every structure with the Opportunity to inspect (at random for subsequent piles at the same structure)
note | Standard / Specification - 51/33669 - 9.4
note | Verifying Document - Hold Point Release
note | Frequency - First pile at every structure
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT