## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | DS2672-ITP-S108 - Piling Materials - Rev 1 | itp |  |  |  |  | DS2672-ITP-S108 - Piling Materials - Rev 1
section | 4.07 Piling Materials
checkpoint | 4.07.01 - Piling Supervisor
note | Acceptance / Conformance Criteria - A suitably qualified and experienced person shall be nominated by the Constructor as the ‘Piling Supervisor’.
note | Standard / Specification - 51/33669 - 3.9
note | Verifying Document - Supervisor Approval
note | Frequency - Prior to any piling works commencing.
note | Activity - W
note | By - ENG
checkpoint | 4.07.02 - Pile Mix Design
note | Acceptance / Conformance Criteria - The Designer shall be provided with the proposed concrete mix design for review, prior to any piling works commencing.
note | Standard / Specification - 51/33669 - 5.1
note | Verifying Document - Mix Design
note | Frequency - Prior to any piling works commencing.
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.07.03 - Spiral Reinforcement Welding
note | Acceptance / Conformance Criteria - Spiral reinforcement shall not be lapped. Spiral reinforcement shall start and stop with 1.5 x pile cage circumference overlap and a single sided lap weld. Laps in longitudinal bars shall be made with D-clamps or similar means accepted by the Designer. Lapped joints shall achieve the full strength of the bar.
note | Standard / Specification - 51/33669 - 5.2
note | Verifying Document - TPI Report
note | Frequency - Prior to Installation
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.07.04 - Reinforcement Cage Fabrication Inspection
note | Acceptance / Conformance Criteria - Designer inspection of reinforcement cage fabrication process for the first pile at every structure with the Opportunity to inspect (at random for subsequent piles at the same structure)
note | Standard / Specification - 51/33669 - 9.4
note | Verifying Document - Hold Point Release
note | Frequency - First pile at every structure
note | Activity - HP
note | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.07.05 - Permanent Casings
note | Acceptance / Conformance Criteria - The casing dimensions shall comply with the outside diameter, wall thickness and internal diameter as shown on the Drawings
note | Standard / Specification - 51/33669 - 6.1.1
note | Verifying Document - Mill Certs and Dimensions
note | Frequency - Prior to Installation
note | Activity - R
note | By - PE
checkpoint | 4.07.06 - Temporary Casings
note | Acceptance / Conformance Criteria - the Constructor shall confirm that the properties of the casing are such that the bored piles are constructed to the dimensions, shape and depth.
note | Standard / Specification - 51/33669 - 6.1.2
note | Verifying Document - Dimensions
note | Frequency - Prior to Installation
note | Activity - R
note | By - PE
checkpoint | 4.07.07 - Bored Pile Construction Record Card Template
note | Acceptance / Conformance Criteria - Supply a Template for the bored pile construction record card a minimum of 3 weeks prior to the commencement of any piling works.
note | Standard / Specification - 51/33669 - 9.1
note | Verifying Document - Construction Record Card Template
note | Frequency - 3 weeks prior to the commencement of any piling
note | Activity - R
note | By - PE
section | 4.08 Concrete Materials
checkpoint | 4.08.06 - Reinforcement
note | Acceptance / Conformance Criteria - Reinforcing bars and mesh shall comply with AS/NZS4671:2001.
note | Standard / Specification - RSV - CS - 1.19
note | Verifying Document - Mill Certs
note | Frequency - Prior to Installation
note | Activity - R
note | By - PE