## Table 1
|  |  |  | INSPECTION AND TEST PLAN |  |  |  |  | ITP no: | Z1-SR-PAV
|  |  |  | Project: NZTA 5363 CIP SH30 Te Ngae Road Corridor-Iles Rd to Coulter Rd |  |  |  |  | Associated Docs
|  |  |  | Construction Process: Side Road Pavement |  |  |  |  | Rev number: | V1
Client: NZTA |  | Head Contractor Subcontractor |  | Specification: 600 - Pavement
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record Document | Responsibility | Comments | Checked by
|  | Detail of Activity | Action (Hold, Monitor, Witness) | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) | Inspection / Test method |  |  |  |  | Engineer | Contractor | Date
600 | Pre-construction / Preliminary Compliance Requirements
600.1 | Method Statement Development / Job Safety Analysis / Enviro Site Specific Plans |  | H | Prior to Construction |  | Method Statement and JSEA Completed and signed by relevant authority |  | Downer
600.2 | Drawings and Specification |  | H | Prior to Construction |  | DWG’s and Specifications are of For Construction and latest revision. Reviewed and approved by Designer and Client. |  | Downer
600.3 | Set out |  | H | Prior to Construction |  | Set out as per latest Design Model / For Construction Drawings. |  | Designer
600.4 | Material Approvals | Submit testing data for the following materials: - AP65 | H | Prior to Construction | Quarry Testing Data | Material approvals to be sent to the Engineer. Refer Project Specs and Drawings; • AP65: o Crushing Resistance < 100kN o Weathering Quality Index of A,AB, AC, BA, BB or CA o Sand Equivalent ≥ 25 if > 4% passing 75um sieve o CBR minimum 40 using heavy compaction o Grading |  | Designer
600.5 | Material Approvals | Submit testing data for the following materials: - AP40 | H | Prior to Construction | Quarry Testing Data | Material approvals to be sent to the Engineer. Refer Project Specs and Drawings; • AP40: o Crushing Resistance <10% fines passing 2.36mm under 130 KN load o Weathering Quality Index of AA,AB, AC, BA, BB or CA o Sand Equivalent ≥ 40 o Soaked CBR ≥ 80% o Solid Density > report value only o Determination of MDD & OWC > report value only o Broken Face Content: each of the three aggregate fractions between the 37.5mm and 4.75mm sieves shall not be less than 70% by weight and shall have two or more broken faces o Particle size distribution / Grading 100% passing 37.5mm 66 - 81% passing 19mm 43 - 57 passing 9.5mm 28 - 43 passing 4.75mm 19 - 33 passing 2.36mm 12 - 25 passing 1.18mm 7 - 19 passing 600µm 3 - 14 Passing 300µm 0 - 10 passing 150µm 0 - 7 passing 75µm Plasticity Index: Basecourse passing the 425μm sieve shall not be greater than 5 when the aggregate is tested according to NZS 4407 : 1991, Test 3.4 Plasticity Index Test. Clay Index: Basecourse passing the 75μm sieve |  | Designer
600.6 | Identification of Underground Services |  | H | Prior To Construction |  | Ensure underground services are positively identified and asbuilt. Where this interferes with design permanent works, Service provider and Designer to be notified immediately. | InEight Records | Contractor
|  |  |  | INSPECTION AND TEST PLAN |  |  |  |  | ITP no: | Z1-SR-PAV
|  |  |  | Project: NZTA 5363 CIP SH30 Te Ngae Road Corridor-Iles Rd to Coulter Rd |  |  |  |  | Associated Docs
|  |  |  | Construction Process: Side Road Pavement |  |  |  |  | Rev number: | V1
Client: NZTA |  | Head Contractor Subcontractor |  | Specification: 600 - Pavement
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record Document | Responsibility | Comments | Checked by
|  | Detail of Activity | Action (Hold, Monitor, Witness) | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) | Inspection / Test method |  |  |  |  | Engineer | Contractor | Date
Subgrade Construction
600.7 | Subgarde Inspection | Subgrade Levels | M | 20m centres | Visual Inspection | Cut subgrade to 355mm below finished level. String line tolerance to be within +0mm/-30mm (i.e. 0mm high, 30mm deep) | QC Sheets | Contractor
600.8 |  | Bearing Strength | H | Inferred CBR, 5 tests per 500m2.1 per 20lm | Scala Panatrometer | Scala (bearing Strength on insitu subgrade) to depth 500mm, with the following requirement to be achieved;≥ 5 blows per 100mm - No undercut 4 blows per 100mm - 100mm 3 blows per 100mm - 175mm 2 blows per 100mm - 275mm <1 blow per 100mm - 500mm undercut | QC Sheets (Scala Sheet) | Contractor | Scala results to meet or exceed per below: 0mm - 100mm - ≥ 3 blows per 100mm 100mm - 200mm - ≥ 2 blows per 100mm 200mm - 300mm - ≥ 2 blows per 100mm 300mm - 400mm - ≥ 1 blow per 100mm 400mm - 500mm - ≥ 1 blow per 100mm
600.9 |  | Proof Roll | H | One per lot | Visual Inspection | Proof roll – Check for uniformity, soft areas to be undercut 200mm and backfilled with recycled pavement, AP40 Hardfill or AP65. | (Scala Sheet) | Contractor
Subbase Construction
600.1 | Finished Level | String line or equivalent | H | 20m centres each side | Stringline, tape measure | Layer Finished Level – String Line, each lane, Tolerance: +5mm/-25mm | QC Sheets | Contractor
600.11 | Compaction | Basecourse Compaction | M | Direct Transmission NDM (1 per 200m2) | NDM | Mean ≥ 95% MDD, Min ≥92% | QC Sheets | Contractor
Basecourse Construction
600.12 | Finished Level | String line or equivalent | H | 20m centres each side | Stringline, tape measure | Layer Finished Level – String Line, each lane, Tolerance: +15mm/-5mm | QC Sheets | Contractor
600.13 | Compaction | Basecourse Compaction | M | Direct Transmission NDM (1 per 200m2) | NDM | Mean ≥ 98% MDD, Min ≥95% | QC Sheets | Contractor
600.14 | Degree of Saturation | Basecourse Compaction | M | Direct Transmission NDM (1 per 200m2) | NDM | < 60% (or 80% on consultation with the pavement designer) | QC Sheets | Contractor
Close Out
600.15 | Collate above documentation | Document review | H | Each ITP | Review |  | N/A | Contractor
600.16 | As-built drawings | Survey | H | At completion of construction | Asbuilts to be submitted at the completion of construction | -As-built to be submitted at the completion of construction -Information to be captured: -Maintain Redline drawings through works. | N/A | Contractor
600.17 | RAMM Data |  | H |  | Info to be submitted by the completion of project construction | -Information to be captured: | N/A | Contractor
Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance. Contractor's Rep Name: BBO Engineers Rep Name:
[6 empty] | Date: Date: | H Hold Point
W Witness Point
M Monitor Point