## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Side Road Pavement | itp |  |  |  | Yes | ITP - Side Road Pavement | 2cfba3d9-449a-4da6-ba6a-eed0c5b69af5
section | Pre-construction / Preliminary Compliance Requirements
checkpoint | 600.1 - Method Statement Development / Job Safety Analysis / Enviro Site Specific Plans
label | H
label | Minimum Test Frequency - Prior to Construction
label | Acceptance Criteria - Method Statement and JSEA Completed and signed by relevant authority
label | Responsibility - Downer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 600.2 - Drawings and Specification
label | H
label | Minimum Test Frequency - Prior to Construction
label | Acceptance Criteria - DWG’s and Specifications are of For Construction and latest revision. Reviewed and approved by Designer and Client.
label | Responsibility - Downer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 600.3 - Set out
label | H
label | Minimum Test Frequency - Prior to Construction
label | Acceptance Criteria - Set out as per latest Design Model / For Construction Drawings.
label | Responsibility - Designer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 600.4 - Material Approvals
label | Detail of Activity - Submit testing data for the following materials: AP65
label | H
label | Minimum Test Frequency - Prior to Construction
label | Inspection / Test method - Quarry Testing Data
label | Acceptance Criteria - Material approvals to be sent to the Engineer. Refer Project Specs and Drawings;
label | • AP65:
label | o Crushing Resistance < 100kN
label | o Weathering Quality Index of A,AB, AC, BA, BB or CA o Sand Equivalent ≥ 25 if > 4% passing 75um sieve
label | o CBR minimum 40 using heavy compaction
label | o Grading
label | Responsibility - Designer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 600.5 - Material Approvals
label | Detail of Activity - Submit testing data for the following materials: AP40
label | H
label | Minimum Test Frequency - Prior to Construction
label | Inspection / Test method - Quarry Testing Data
label | Acceptance Criteria - Material approvals to be sent to the Engineer. Refer Project Specs and Drawings;
label | • AP40:
label | o Crushing Resistance <10% fines passing 2.36mm under 130 KN load o Weathering Quality Index of AA,AB, AC, BA, BB or CA
label | o Sand Equivalent ≥ 40 o Soaked CBR ≥ 80%
label | o Solid Density > report value only
label | o Determination of MDD & OWC > report value only
label | o Broken Face Content: each of the three aggregate fractions between the 37.5mm and 4.75mm sieves shall not be less than 70% by weight and shall have two or more broken faces
label | o Particle size distribution / Grading
label | • 100% passing 37.5mm
label | • 66 - 81% passing 19mm
label | • 43 - 57 passing 9.5mm
label | • 28 - 43 passing 4.75mm
label | • 19 - 33 passing 2.36mm
label | • 12 - 25 passing 1.18mm
label | • 7 - 19 passing 600µm
label | • 3 - 14 Passing 300µm
label | • 0 - 10 passing 150µm
label | • 0 - 7 passing 75µm
label | o Plasticity Index: Basecourse passing the 425μm
label | o Sieve shall not be greater than 5 when the aggregate is tested according to NZS 4407 : 1991, Test 3.4 Plasticity Index Test.
label | o Clay Index: Basecourse passing the 75μm sieve
label | Responsibility - Designer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 600.6 - Identification of Underground Services
label | H
label | Minimum Test Frequency - Prior To Construction
label | Acceptance Criteria - Ensure underground services are positively identified and asbuilt. Where this interferes with design permanent works, Service provider and Designer to be notified immediately.
label | Record Document - InEight Records
label | Responsibility - Contractor
holdpoint | AUTHORITY HOLDPOINT
section | Subgrade Construction
checkpoint | 600.7 - Subgrade Inspection
label | Detail of Activity - Subgrade Levels
label | M
label | Minimum Test Frequency - 20m centres
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - Cut subgrade to 355mm below finished level. String line tolerance to be within +0mm/-30mm (i.e. 0mm high, 30mm deep)
label | Record Document - QC Sheets
label | Responsibility - Contractor
checkpoint | 600.8 - Subgrade Inspection
label | Detail of Activity - Bearing Strength
label | H
label | Minimum Test Frequency - Inferred CBR, 5 tests per 500m2.1 per 20lm
label | Inspection / Test method - Scala Panatrometer
label | Acceptance Criteria - Scala (bearing Strength on insitu subgrade) to depth 500mm, with the following requirement to be achieved;≥
label | • 5 blows per 100mm - No undercut 4 blows per 100mm - 100mm
label | • 3 blows per 100mm - 175mm 2 blows per 100mm - 275mm
label | • <1 blow per 100mm - 500mm undercut
label | Record Document - QC Sheets (Scala Sheet)
label | Responsibility - Contractor
label | Comments - Scala results to meet or exceed per below:
label | • 0mm - 100mm - ≥ 3 blows per 100mm
label | • 100mm - 200mm - ≥ 2 blows per 100mm
label | • 200mm - 300mm - ≥ 2 blows per 100mm
label | • 300mm - 400mm - ≥ 1 blow per 100mm
label | • 400mm - 500mm - ≥ 1 blow per 100mm
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 600.9 - Subgrade Inspection
label | Detail of Activity - Proof Roll
label | H
label | Minimum Test Frequency - One per lot
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - Proof roll – Check for uniformity, soft areas to be undercut 200mm and backfilled with recycled pavement, AP40 Hardfill or AP65.
label | Record Document - (Scala Sheet)
label | Responsibility - Contractor
holdpoint | AUTHORITY HOLDPOINT
section | Subbase Construction
checkpoint | 600.10 - Finished Level
label | Detail of Activity - String line or equivalent
label | H
label | Minimum Test Frequency - 20m centres each side
label | Inspection / Test method - Stringline, tape measure
label | Acceptance Criteria - Layer Finished Level – String Line, each lane, Tolerance: +5mm/-25mm
label | Record Document - QC Sheets
label | Responsibility - Contractor
checkpoint | 600.11 - Compaction
label | Detail of Activity - Basecourse Compaction
label | M
label | Minimum Test Frequency - Direct Transmission NDM (1 per 200m2)
label | Inspection / Test method - NDM
label | Acceptance Criteria - Mean ≥ 95% MDD, Min ≥92%
label | Record Document - QC Sheets
label | Responsibility - Contractor
section | Basecourse Construction
checkpoint | 600.12 - Finished Level
label | Detail of Activity - String line or equivalent
label | H
label | Minimum Test Frequency - 20m centres each side
label | Inspection / Test method - Stringline, tape measure
label | Acceptance Criteria - Layer Finished Level – String Line, each lane, Tolerance: +15mm/-5mm
label | Record Document - QC Sheets
label | Responsibility - Contractor
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 600.13 - Compaction
label | Detail of Activity - Basecourse Compaction
label | M
label | Minimum Test Frequency - Direct Transmission NDM (1 per 200m2)
label | Inspection / Test method - NDM
label | Acceptance Criteria - Mean ≥ 98% MDD, Min ≥95%
label | Record Document - QC Sheets
label | Responsibility - Contractor
checkpoint | 600.14 - Degree of Saturation
label | Detail of Activity - Basecourse Compaction
label | M
label | Minimum Test Frequency - Direct Transmission NDM (1 per 200m2)
label | Inspection / Test method - NDM
label | Acceptance Criteria - < 60% (or 80% on consultation with the pavement designer)
label | Record Document - QC Sheets
label | Responsibility - Contractor
section | Close Out
checkpoint | 600.15 - Collate above documentation
label | Detail of Activity - Document review
label | H
label | Minimum Test Frequency - Each ITP
label | Inspection / Test method - Review
label | Record Document - N/A
label | Responsibility - Contractor
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 600.16 - As-built drawings
label | Detail of Activity - Survey
label | H
label | Minimum Test Frequency - At completion of construction
label | Inspection / Test method - Asbuilts to be submitted at the completion of construction
label | Acceptance Criteria - A s-built to be submitted at the completion of construction
label | • Information to be captured:
label | • Maintain Redline drawings through works.
label | Record Document - N/A
label | Responsibility - Contractor
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 600.17 - RAMM Data
label | H
label | Inspection / Test method - Info to be submitted by the completion of project construction
label | Acceptance Criteria - Information to be captured:
label | Record Document - N/A
label | Responsibility - Contractor
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Client Final Inspection - Contractor
label | The signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
text | Contractor's Rep Name:
holdpoint | Add Signature
checkpoint | Client Final Inspection - BBO Engineer
label | The signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
text | BBO Engineers Rep Name:
holdpoint | Add Signature