## Structure
Tier 1 | Tier 2 | Tier 3 | Tier 4 | Checklist to use
Site QA
| Phase 1 |  |  | Phased Installation QC
| Phase 2 |  |  | Phased Installation QC
| Phase 3 |  |  | Phased Installation QC
| Phase 4 |  |  | Phased Installation QC
| Phase 5 |  |  | Phased Installation QC
| Phase 6 |  |  | Phased Installation QC
| Phase 7 |  |  | Phased Installation QC
| Phase 8 |  |  | Phased Installation QC
| Phase 9 |  |  | Phased Installation QC
| Phase 10 |  |  | Phased Installation QC
| Phase 11 |  |  | Phased Installation QC
| Phase 12 |  |  | Phased Installation QC
| Phase 13 |  |  | Phased Installation QC
| Phase 14 |  |  | Phased Installation QC
| Phase 15 |  |  | Phased Installation QC

## Checklists
Type | Name | Values
Phased Installation QC (Installation Methodology)
checkpoint | Phase commencement date |  | Manual entry
checkpoint | Acclimatized Material (Remove from pallet and package lay out on floor) |  | x1 Picture
checkpoint | Floor condition after uplift |  | x1 Picture
checkpoint | Clean grind subfloor and vac |  | x1 Picture
checkpoint | Apply UZIN PE460 Moisture Barriers (Trowel and roll) |  | x1 Picture
checkpoint | Apply UZIN PE 280 Primer |  | x1 Picture
checkpoint | Apply UZIN NC160 - Bag count after pour |  | Manual entry | Client Signature
checkpoint | Polyvac NC160 |  | Tick box
checkpoint | Dry lay Norament |  | Tick box
checkpoint | Apply Uzin 68T adhesive with CRAIN 424 Trowel |  | Tick box
checkpoint | Norament Adhesive - UZIN 68T |  | x1 Picture
checkpoint | Heavy roll Norament during installation |  | x1 Picture
checkpoint | Heavy roll Norament after installation |  | x1 Pictures
checkpoint | Completed Norament installation |  | x4 Pictures
checkpoint | Completed Carpet Tile installation- Direct stick method |  | x2 Pictures
checkpoint | Transition between other floor covering level and flush DT039 & DT084 |  | x2 Pictures
checkpoint | Phase completed with no damage ?
signoff | Please signoff / request sign off