## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
a74b5a06-67d6-4f07-9ac6-3f2505336408 | checklist | Phased Installation QC (Installation Methodology) |  | Phased Installation QC (Installation Methodology)
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint-no-value | Phase commencement date
| date | Phase commencement date:
| checkpoint | Acclimatized Material (Remove from pallet and package lay out on floor)
| note | x1 Picture
| checkpoint | Floor condition after uplift
| note | x1 Picture
| checkpoint | Clean grind subfloor and vac
| note | x1 Picture
| checkpoint | Apply UZIN PE460 Moisture Barriers (Trowel and roll)
| note | x1 Picture
| checkpoint | Apply UZIN PE 280 Primer
| note | x1 Picture
| checkpoint-no-value | UZIN NC160 - Bag count after pour
| textbox | UZIN NC160 - Bag count after pour
| note | Client Signature
| signoff | Add Client Signature
| checkpoint | Polyvac NC160
| checkpoint | Dry lay Norament
| checkpoint | Apply Uzin 68T adhesive with CRAIN 424 Trowel
| checkpoint | Norament Adhesive - UZIN 68T
| note | x1 Picture
| checkpoint | Heavy roll Norament during installation
| note | x1 Picture
| checkpoint | Heavy roll Norament after installation
| note | x1 Pictures
| checkpoint | Completed Norament installation
| note | x4 Pictures
| checkpoint | Completed Carpet Tile installation- Direct stick method
| note | x2 Pictures
| checkpoint | Transition between other floor covering level and flush DT039 & DT084
| note | x2 Pictures
| checkpoint | Phase completed with no damage?
| signoff | Please signoff / request sign off