## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | 246 Mt Smart Road - ITP - Enabling Works - Footpath, Kerb and channel | itp | ITP - Enabling Works - Footpath, Kerb and channel | 34aea8a2-1fbd-4386-aab5-88fdc41f3678
| section | Site Set Out
| checkpoint | 1 - Site Set out
28af9067-3907-573c-b149-9e433af09fe3 | note | Verification Activity: Surveyor
5bbe611c-dd9a-5ba4-a9bf-0c5349513c1b | note | Methods or Reference: Surveyor
a38833fa-8eaa-56ff-a785-0818981183fc | note | Frequency: Everysite
90980f30-5aff-5489-abcb-ddb628d28b6b | note | Acceptance Criteria: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
9016cb4e-fb45-5f1b-8676-e7deeb9cc31e | note | Hold Point: Mandatory HOLD POINT -
a3127981-4140-5ff4-b8f8-6c93a74c2b37 | note | Records: Onsite records/photos
f8557566-c692-572e-8618-629ce9ba60ec | note | Onsite Responsibility: Site Engineer
| signoff | HOLD POINT
| section | Materials
| checkpoint | 2 - Kerb & Channel
ae98441b-72f4-5d91-bf36-d263f68c546d | note | Verification Activity: QA FORM
e591172f-ce4a-50d0-a7c5-c572d8964e6d | note | Methods or Reference: TDM Technical Standards - KC0001
bd73ea22-8391-5ca7-9e54-818e367adaf6 | note | Frequency: Everysite
599a7f43-a4e9-557f-ba49-7d9974865ac7 | note | Acceptance Criteria: Kerb & Channel to be laid using precast hand-laid. On compacted GAP40. Concrete 20MPa @28 Days on 100mm GAP40 with the subgrade CBR>5
63de1870-9256-5ea0-ae46-c72523d3c5a4 | note | Hold Point: Inprocess Inspection
5a03c66b-a02d-556c-9dc0-ec7571047f5b | note | Records: FH concrete QA sheet, photos. Concrete Plant Docket
4a693427-e21c-55f8-8ee6-867138c51f0e | note | Onsite Responsibility: Site Engineer
| checkpoint | 3 - Channel Level
69588501-1c81-5531-96a5-d0ef2b35fa45 | note | Verification Activity: QA FORM
501a4de2-2ab8-5599-8a26-00db66daacf3 | note | Methods or Reference: TDM Technical Standards - KC0001
2481e9ce-9467-5bf0-b749-85e5810b9be0 | note | Frequency: Everysite
26eb411a-58b1-5395-bd4b-50d8731bf94a | note | Acceptance Criteria: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
dcf1d24c-ef92-5170-83ce-2fda9203bf55 | note | Hold Point: Inprocess Inspection
dcd48ffa-e8a6-5c0d-b47f-46a02c1e37ef | note | Records: FH concrete QA sheet
470cffb4-c802-50c7-aaef-62b754a05df2 | note | Onsite Responsibility: Site Engineer
| section | Civil Works
| checkpoint | 4 - AC Footpaths
360faaa3-58da-5716-b511-8c7f99a05809 | note | Verification Activity: QA FORM
76df872c-3de4-5e44-813b-e6e45d79401f | note | Methods or Reference: TDM Technical Standards - FP0001
b87b6aeb-9adb-57c3-b344-864da35083de | note | Frequency: 10m Intervals
4c926d4f-aea4-59c3-b98b-a57c25b98983 | note | Acceptance Criteria: Subgrade -(CBR > 3) Basecourse - 100mm min. thickness GAP40 Clegg CIV > 13 DG7/Fine asphalt mix used
44be6f0b-5cb4-5463-b3cd-95a824f55bec | note | Hold Point: Inprocess Inspection
648f5e7c-cc7c-5c48-ab10-b28ca423e01e | note | Records: FH concrete QA sheet. Concrete delivery Dockets kept as record
4fd3179f-cbcc-5636-9017-aa73c5ce366d | note | Onsite Responsibility: Site Engineer
| checkpoint | 5
1a4eeb7c-706d-5154-91b0-f1b863b9fc43 | note | Methods or Reference: TDM Technical Standards - FP0010
aa1c3723-0526-58cf-9602-33119ad96cbd | note | Frequency: Each PX
9de28d85-3dbf-55d9-acc2-e45a1bcb1b7a | note | Acceptance Criteria: Warning TGSI tiles should have 100mm concrete slab underneath
13ae3394-e7da-5d38-9c12-25b9cb87972f | note | Hold Point: Inprocess Inspection, Measurement
51631c4f-75cb-5cbb-85e2-7297528f3cc7 | note | Records: FH concrete QA sheet. Concrete delivery Dockets kept as record
9e8bc478-a192-5d54-8e98-f8d2af7f4d28 | note | Onsite Responsibility: Site Engineer
| checkpoint | 6 - Tactiles
7a408965-998e-51d7-8c09-bfab333c63a3 | note | Verification Activity: Visual
54b5acee-0b96-5195-ad4d-c66201c09bc6 | note | Methods or Reference: NZTA RTS Guidelines for facilities for blind and vision impaired pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
04fad576-b129-5785-8cd8-eff41bd93252 | note | Frequency: Everysite
8f1783c7-09e0-56fe-8131-156a58a74435 | note | Acceptance Criteria: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
ed0bb9cd-2fa5-5926-9f3c-0c822e65221b | note | Hold Point: Inprocess Inspection
88724539-c8a4-5d23-bb54-eaf00ed3c266 | note | Records: Photos
7b2d7616-cb9a-53e3-a08d-79a29ec904df | note | Onsite Responsibility: Site Engineer
| checkpoint | 6.1
aaa81e67-21af-50b1-98fc-aaca7781a2b2 | note | Methods or Reference: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
2263b8af-4814-5bd4-89d0-fa12efb4eb15 | note | Frequency: Everysite
57c3a1cd-b97a-5e3a-9df4-77241fc41c86 | note | Acceptance Criteria: Edge of warning indicators to set back 300mm from the face of the kerb or lane, extend the full width of ramp and be 600mm deep.
8c24a03a-e90f-505f-9945-37cc5df97aef | note | Hold Point: Inprocess Inspection
33ff4d8e-93ed-593b-b419-2fab03c7189d | note | Records: Photos
d85ba369-1150-58de-be1d-465699e213bb | note | Onsite Responsibility: Site Engineer
| checkpoint | 6.2
7f18ef1b-5c6d-59d2-87dd-476e3648dcbd | note | Methods or Reference: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
84e9fb5b-e95a-5dae-8e7a-bcd0ed955df7 | note | Frequency: Everysite
c0b22230-f005-58e0-8692-8e1ce4079496 | note | Acceptance Criteria: TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
20b62379-331e-5e75-9d03-1751e73fb35d | note | Hold Point: Inprocess Inspection
c38114f2-ef79-55fe-91f1-83ea0e287b91 | note | Records: Photos
92f470ef-0879-52f9-82f2-b92735fd69ad | note | Onsite Responsibility: Site Engineer
| section | RAMM Data
| checkpoint | 7 - As built information
381f7027-a38e-5552-8866-90e621159167 | note | Verification Activity: RAMM DATA SHEET
11174d25-8cc1-5386-a032-616ab1e60de3 | note | Methods or Reference:
493982f8-e13d-5495-92a0-66eb2fbbe661 | note | Frequency: Every Site
09238ef7-8dcb-55ed-91f2-5b73764f6eab | note | Acceptance Criteria: As built drawings and Ramm Sheets Completed
c8c6ab3a-753d-5ce7-9acf-01954db369ff | note | Hold Point: In Process Inspection
af8f41a2-a384-5545-931b-b4681e7afe5e | note | Records: Asbuilt records
26fa43cc-8986-5046-8076-83ace7b0e518 | note | Onsite Responsibility: Supervisor and Engineer
| checkpoint-no-value | ITP Approval
8593682a-9a1d-5656-affd-18e2fbb6a540 | note | Prepared by: Cimyona Vinbi (02/08/21)
a4278548-6457-585c-909b-682143522766 | note | Approving Delegate: Daniel Tat (25/08/21)
| checklist | Aspiring Avenue/Thomas Road Intersection - ITP - Enabling Works - Footpath, Kerb and channel | itp | ITP - Enabling Works - Footpath, Kerb and channel | ad7ba7d6-b4f6-4657-b29f-802c6e094fcc
| section | Site Set Out
| checkpoint | 1 - Site Set out
d8e170c9-4452-5932-8f68-a1eaf70d699a | note | VERIFICATION ACTIVITY: Surveyor
aed25dfc-ddea-50ff-8b0c-73894b1a9103 | note | METHODS OR REFERENCE: Surveyor
332d0ac0-49cc-5b8e-b960-f3b5477629ec | note | FREQUENCY: Everysite
029b7bbe-f22b-5292-82a1-ed4b22203cee | note | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criterea is acceptable.
adde3a9a-dbf5-5dff-bd98-6ad426ee209e | note | HOLD POINT: Mandatory HOLD POINT -
ba393471-255f-5a1e-bf30-a2588873d986 | note | RECORDS: Onsite records/photos
f950add6-36d7-514d-91f5-ed4c7ca9a1fc | note | ONSITE RESPONSIBILITY: Site Engineer
| signoff | Mandatory HOLD POINT
| section | Materials
| checkpoint | 2 - Kerb & Channel
3bde02df-f5e7-5023-9168-b0d8ca74cc35 | note | VERIFICATION ACTIVITY: QA FORM
fcf52a52-41f2-5da6-84ac-7c8716577490 | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
4dad173c-11ca-5d00-9efe-94875d55ff50 | note | FREQUENCY: Everysite
6fce77b8-1fc4-593b-9d99-e4b13f20f725 | note | ACCEPTANCE CRITERIA: Kerb & Channel to be laid using precast hand-laid. On compacted GAP40. Concrete 20MPa @28 Days on 100mm GAP40
527e03b4-ee6b-5202-bec9-2672bd4045da | note | HOLD POINT: Inprocess Inspection
f8e56142-f2de-50ad-b7dd-81e505d69aad | note | RECORDS: FH concrete QA sheet, photos. Concrete Plant Docket
31ce6c93-7099-57d4-9aa2-805bc552a352 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3 - Channel Level
2f5fb5ad-2f7b-5aae-9a95-f52901337a2a | note | VERIFICATION ACTIVITY: QA FORM
2c781e71-638d-554f-bfe9-99bdb3ad83bb | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
02e0a49c-66ec-56c1-9598-3ce911eb48c2 | note | FREQUENCY: Everysite
f9fc9f2d-bdf9-5306-99e1-bef890d32659 | note | ACCEPTANCE CRITERIA: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
96b6a18d-2ff4-5bcc-a8a6-651afc317d66 | note | HOLD POINT: Inprocess Inspection
2f24dc56-e808-514e-9e07-99695943395b | note | RECORDS: FH concrete QA sheet, Photos
7fce3311-dcf1-5a8f-a02c-77625e01cb9c | note | ONSITE RESPONSIBILITY: Site Engineer
| section | CIVIL WORKS
| checkpoint | 4 - Concrete Footpaths
b27c88d1-357e-54cf-8c53-7f91cf7e9637 | note | VERIFICATION ACTIVITY: QA FORM
ea2fe24a-3076-51e1-a9f9-d5b4d87630e4 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
7e4a8e89-01b9-5267-856a-2c41950b9544 | note | FREQUENCY: 10m Intervals
01806c0f-9058-5c5b-8b60-532ff3f9a4f5 | note | ACCEPTANCE CRITERIA: Basecourse - 100mm min. thickness GAP40
2e5c2c1d-d43a-5a9a-887c-460a00b0fb53 | note | ○ Clegg CIV > 12
79d13c1a-6a43-59ae-bc69-01fb46c790da | note | ○ Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish
461cf90a-aac0-50a0-a647-159913b66a33 | note | HOLD POINT: Inprocess Inspection
52acfbd1-bb76-58b2-af81-bb822384a4ee | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
e91d19ff-f47a-57f2-bf36-06567d60d314 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 5 - Tactiles
de0a7340-b4b6-550e-9fd9-99918cd9f3b2 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0010
37769fcc-cfd9-5f70-8bc9-bbdf6876aeaa | note | FREQUENCY: Each PX
480ab108-9a56-5eaa-b124-83012bf9e96c | note | ACCEPTANCE CRITERIA: Warning TGSI tiles should have 150mm concrete slab underneath
8a4c8e82-b9db-5465-9fa0-4c8e0832919a | note | HOLD POINT: Inprocess Inspection, Measurement
5ceb7d29-54d1-57d5-97da-81cb9a0cd232 | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
06cdb787-72b6-5b68-b233-5cb0b09a0082 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 5.1 -
c89a9797-b8d2-58a9-baa1-343151547e85 | note | VERIFICATION ACTIVITY: Visual
b6d4a4fb-be90-5972-a0b1-1ef8e0c16886 | note | METHODS OR REFERENCE: NZTA RTS Guidelines for facilities for blind and vision impared pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
30d1cf00-3b4c-5d72-bd6e-6457acdd2ae7 | note | FREQUENCY: Everysite
792b483c-5af1-5bab-8fea-136b3c8b368e | note | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
f1a4bcf8-ec3d-5a79-ba81-38308e8b755f | note | HOLD POINT: Inprocess Inspection`
1af62466-7ffa-5b00-8611-284417d87eda | note | RECORDS: Photos
6346185c-61d8-5a21-9b6f-0724e719bd55 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 5.2 -
996f1207-ad93-5ffa-998f-26896ac34cfd | note | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
27e6ba73-4d8f-511a-a587-af6a616b9b50 | note | FREQUENCY: Everysite
c27ba3ed-f305-5cc6-9045-40cc27a59211 | note | ACCEPTANCE CRITERIA: Edge of warning indicators to set back 300mm from the face of the kerb or lane.
1000ed9a-415c-5bed-a91a-f1da7c721227 | note | HOLD POINT: Inprocess Inspection
60b85795-1f54-5bf9-aa1c-271f23c6d014 | note | RECORDS: Photos
aa8cd6e7-0cc2-55f7-9743-13b7f4ee6986 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 5.3 -
0d456dd9-f47b-549d-bc80-d175cbc98b2c | note | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
f682f302-1158-5fa0-878b-89bd27bff8d1 | note | FREQUENCY: Everysite
9f2efa06-e9ed-5369-90ce-9650be265686 | note | ACCEPTANCE CRITERIA: TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
e668477e-8c35-554c-bd6a-1030ec08a11d | note | HOLD POINT: Inprocess Inspection
7435c673-1f6d-5b37-8502-7a375f468d9a | note | RECORDS: Materials Dockets
8ac2d3f8-6622-5f71-a256-ac38f5a2ef1e | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 6 - Grass Berms
8a757713-5c33-5e66-845a-fc0d32bbc68e | note | VERIFICATION ACTIVITY: Visual
ba13a29d-ab5d-500d-b0c9-bc75acf42be3 | note | METHODS OR REFERENCE: ATCOP Section 12 Footpaths and Pedestrian Facilities
96d21a73-61d5-567e-9bd3-cf6fa76ad73f | note | FREQUENCY: 10m Intervals
42d7671f-608e-5ff4-9d57-6cecdef8cff2 | note | ACCEPTANCE CRITERIA: 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
e750a3c8-f1ce-5d40-9d3f-119840309bb5 | note | HOLD POINT: Inprocess Inspection
af0ed0a7-910f-59b6-9b6d-9be15a07fa82 | note | RECORDS: Photos
a85e80fc-dd3e-50c9-804e-cba917a3c31e | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Asbuilts
| checkpoint | 7 - As built information
bdd6cf1c-2f4e-5814-8104-41013229533a | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
bcdc2cf5-8644-58c7-92d8-a1f14c4aa806 | note | FREQUENCY: Every Site
17753442-a742-5340-ad4b-3bdc64c2796d | note | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
18354e52-81d0-57af-8f5d-e4a6884afdf7 | note | HOLD POINT: Inprocess Inspection
87888cbb-0255-5191-b610-c96c24c55894 | note | RECORDS: Asbuilt records
5eb08213-cb84-5778-b994-c388d1e719a2 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| section | ITP APPROVAL
| checkpoint | ITP Approval
87ec2545-784d-5636-b0b7-6b1713d3280c | note | Prepared by: Yeswanth Vemulaa
d59ddc74-d134-54ad-939a-a02815250283 | note | Approving Delegate: Daniel Tat
| checklist | Aspiring Avenue/Thomas Road Intersection - ITP - Pavement Construction | itp | ITP - Pavement Construction | 34c906ef-d9e7-470d-8ed5-115a921fed8d
| section | Precom
| checkpoint | 1 - Permits & Services (1)
14560f60-95ff-5219-abbd-9a214b462ff1 | note | ACTION (Hold, Monitor, Witness): H
4ee00951-4597-5cc9-8587-f9b302354ba5 | note | DETAIL: Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
d50802b0-e879-5ef6-9871-3f5517976749 | note | FREQUENCY: Prior to any construction commencing
43d356ca-ca5e-54ba-acbc-a31990962146 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
7f5e1526-db06-5c1e-be72-9300d26c1db7 | note | CONFORMANCE CRITERIA: Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority
975075ae-eaac-5cd0-948a-3f13b3bf0a7e | note | RECORDS: Permit attached or permit number noted.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1 - Permits & Services (2)
55be0ded-16f5-528d-916b-8902be08b852 | note | ACTION (Hold, Monitor, Witness): H
25a28444-936f-58b7-983d-5ab7c0788f02 | note | DETAIL: Locate and mark out all existing services
ebbb31b3-77b7-5eaa-a7ad-62fb46b88013 | note | FREQUENCY: Prior to any construction commencing
557013ff-e7ab-5cd4-81a5-a7a8257ed2aa | note | CONFORMANCE CRITERIA: B4u dig procedure - follow utility protocols
20bc6258-a86d-5834-b73a-eaf2c251c60a | note | RECORDS: B4u dig plans
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1 - Permits & Services (3)
81543bda-f7fe-5e72-901a-4bbd96ad3eed | note | ACTION (Hold, Monitor, Witness): H
4e7daae1-c983-5421-a204-bbde42fa775e | note | DETAIL: Approved TMP
140540e0-37d8-5856-9c80-d9514c9c4ed9 | note | FREQUENCY: Prior to any construction commencing
8fd8c582-fc9f-5a56-989b-e0c1cf8ae539 | note | CONFORMANCE CRITERIA: Approved TMP and WAP onsite befor establishing traffic management
f3ca4dac-65d9-50c0-9f89-80e9fc0b0f14 | note | RECORDS: TMP Plans
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Pre-Construction Sign Offs
822f0eba-7e49-5fbd-8fe0-eae5d8fae561 | note | ACTION (Hold, Monitor, Witness): H
ac4eae75-8601-51ee-b26e-ab61d6ad439e | note | DETAIL: Sub-Contract and Supplier Agreements
183b79dd-108c-50bd-8e1b-687420a74ab0 | note | FREQUENCY: Prior to commencement.
d290036a-d9ab-5eaa-a566-89483a745004 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
7b4107f2-b681-57a4-a46a-72be8ec7dc98 | note | CONFORMANCE CRITERIA: Sub-Contract and Supplier Agreements to be agreed and signed
26cb3a27-af55-5762-9a78-be1ff212936b | note | RECORDS: Subcontract and Supplier Agreements
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Design
e27eaf91-3bcf-542b-b1e4-0ca2468738f7 | note | ACTION (Hold, Monitor, Witness): H
e15fcd12-1a9f-51ac-b897-0e1deca85054 | note | DETAIL: Design is approved and Drawings are of the latest revision.
87e2b15a-1a78-5d91-8cfc-ff58203cfa32 | note | FREQUENCY: Prior to commencement.
b60041f9-cbef-5556-a938-aee661b61767 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
866662dd-ec35-58b7-a4d9-0e19cf7ce757 | note | CONFORMANCE CRITERIA: Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
e1cdb1ea-2e4d-515e-aade-532e5d89e88a | note | RECORDS: Drawing Register.
| signoff | AUTHORITY HOLDPOINT
| section | SAC Pavement & Surfacing
| checkpoint | 4 - Bitumen
69c52475-ee10-5b85-a4e7-d9c3dda906ae | note | ACTION (Hold, Monitor, Witness): H
95c3062a-e44e-5bb9-b76b-4a28ee84b9b4 | note | DETAIL: NZTA M/1
2e228746-f53b-5a08-80b6-a5c26d9ad85f | note | FREQUENCY: Passing all tests listed in Table 1 of NZTA M/1
eda7223b-456c-5b32-b549-e234f52f5151 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Testing
63b065ea-0f21-5028-b6a5-b22b18328c84 | note | CONFORMANCE CRITERIA: Passing all tests listed in Table 1 of NZTA M/1
b5cc7016-c14d-515d-9f95-187a93909386 | note | RECORDS: IANZ Lab results
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Asphalt Mix Design
0f447f06-e771-5785-90c8-89eedb6fc0bc | note | ACTION (Hold, Monitor, Witness): H
ad156da7-8838-5223-9827-5369c970c016 | note | DETAIL: JMF approved
feb2dd9d-3fd8-5ac2-a21d-c5fb5601a819 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Review
4d13fe0a-aa2f-5dd5-a6c4-42d862d79805 | note | CONFORMANCE CRITERIA: AUSTROADS
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Production Tests
0db1fe17-eb9c-56bf-bda1-95fc48781cdd | note | ACTION (Hold, Monitor, Witness): M
cf3603f7-05d4-5baa-9de3-31a942863e0f | note | DETAIL: NAS 2004 & TNZ sup to NAS 2006 TNZ P/9P (M/10 Table 5.1)/
e407dedb-db8d-5366-bd72-faf289735206 | note | FREQUENCY: 1 set every 300t
1e6de3fc-8dd4-5100-9c30-cd0a8055c21a | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Review
22c4846e-bd93-51c5-8f03-b1b87194b52d | note | CONFORMANCE CRITERIA: NAS 2004 & TNZ sup to NAS 2006 TNZ P/9P or NZTA M/10 - Grading, Binder content, Max Density, Temprature
00829dff-53cb-569e-bf8b-ddba34852215 | note | RECORDS: IANZ Lab results
| checkpoint | 7 - Check Weather Reports
f094e1ac-45ab-5448-9e60-c0300ba8d210 | note | ACTION (Hold, Monitor, Witness): W
60902068-5952-52af-bfa0-c298958bf63b | note | DETAIL: No fog, rain or wet surface. Base temp greater or equal to 7 deg celcius
a943d11e-05a7-5da8-955e-42a4f08d0258 | note | FREQUENCY: Weather call the day before
c7cc3dd2-0131-5248-aa87-28d3ee13d783 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual
21718f9c-5c7d-5dfb-af1a-01c823c47279 | note | CONFORMANCE CRITERIA: Forecast and thermometer
61567e64-7ff1-5ab3-b043-a6d48b59c14a | note | RECORDS: Radar and Asphalt QA
| checkpoint | 8 - Pre-Seal Inspection
4aee56d6-015f-5362-be39-f70ab3cc3e87 | note | ACTION (Hold, Monitor, Witness): H
41f80c49-8f5c-5407-8bc6-72d0430cc668 | note | DETAIL: Surface finish
246b865c-4fb9-53ec-ae75-b213a5d02fac | note | FREQUENCY: Continuous
4ce86cf1-bb90-5cc0-9c65-be8d0eea9b90 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual
3daadbdc-8d63-5ec2-b128-4fc5df66874b | note | CONFORMANCE CRITERIA: The surface must be clear of deleterious material and not chocked with fines. The basecourse surface must present a stone mosaic surface with larger aggregates protruding and not appear damp
d8b2bd91-f6f1-556f-bf14-29c2c13c97ed | note | RECORDS: Sealing QA
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Tack Coat
a9279cda-3efa-5845-bd81-b268ee58948f | note | ACTION (Hold, Monitor, Witness): M
70729d34-2ede-56e0-8b7d-ea15af3d0ed3 | note | DETAIL: Minimum residual binder application of 0.3l/m2
f27e6dec-76fb-5c9c-9ab4-16d9accb9abf | note | FREQUENCY: Each Run
00f4a169-3e32-56fe-97a5-f681d35f4269 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Testing & Visual
1c722ffe-0112-59d2-a43c-db872510a9ce | note | CONFORMANCE CRITERIA: Each spray of bitumen
c0308302-6781-514b-a827-60505eeaa3dd | note | RECORDS: Asphalt QA
| checkpoint | 10 - Construct 50MM PMB AC14
58d7e871-8b18-5d02-a318-9d554073e63f | note | ACTION (Hold, Monitor, Witness): M
d4513abb-c9ef-5b9a-8883-3e728d878c22 | note | DETAIL: NZTA M/10 NDM and Stringline
9941f784-e5b1-5abc-8bd2-4c0f42a15dda | note | FREQUENCY: Each Run
81d4ec84-1f32-55a4-a211-3d5fe45060f9 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Testing & Visual
95226298-9eb7-56b9-837a-52b908e8c8fc | note | CONFORMANCE CRITERIA: Construct 50mm PMB AC14 . - Design air voids 4% and level tolerance of +10mm, 0mm. NDM testing undertaken in accordance with NZTA M/10
25ae94ce-d827-59d3-82bf-c23204f4b75a | note | RECORDS: Asphalt QA
| checkpoint | 11 - Construct 50MM HF AC14
de309526-a870-572d-85c4-0ebe20d0c096 | note | ACTION (Hold, Monitor, Witness): M
b26c4ec5-4010-5a01-b396-6b7c550da41f | note | DETAIL: NZTA M/10 NDM and Stringline
ece8c5f5-a560-5abb-bbd5-85932cecae36 | note | FREQUENCY: Each Run
02230c56-b915-5ef8-abe7-748227615fa8 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual
76548e84-febd-54d9-b29b-f82553ea00cd | note | CONFORMANCE CRITERIA: Construct 50mm PMB AC14 in 1layer
95dc3d98-5470-5393-bd6e-ea2bb98a5bba | note | RECORDS: Asphalt QA
| checkpoint | 16 - Construct 80MM AC 20
ef6685fe-622e-51ad-8a1b-c185d424610a | note | ACTION (Hold, Monitor, Witness): M
156bad09-5b47-5416-a3bb-b0a8ee854c86 | note | DETAIL: NZTA M/10 NDM and Stringline
1de82596-e3ea-5c0b-ab35-e762bb32955e | note | FREQUENCY: Each Run
ed1bd7d9-b868-55d0-aed4-a20791613150 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Testing & Visual
ba8caf98-e650-56f1-b12c-8d36583c3ed3 | note | CONFORMANCE CRITERIA: Construct 80 MM AC20. - Design air voids 4% and level tolerance of +10mm, 0mm. NDM testing undertaken in accordance with NZTA M/10
f1352741-745c-5d4e-bad6-4f23e598c1c9 | note | RECORDS: Asphalt QA
| checkpoint | 17 - Benkelman Beam deflection testing - (If Required)
8b59681b-8250-5263-b26f-cea0bd06f055 | note | ACTION (Hold, Monitor, Witness): M
7a882e6d-21e5-56b3-9678-33e49654e4d6 | note | DETAIL: NZTA M/10 NDM and Stringline
a3c7f8ce-2dc9-50fe-96fb-2f077aea44b1 | note | FREQUENCY: Each Run
1da4b995-e8ca-53dd-9455-9dabfc070924 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Testing & Visual
38cee890-9e7e-5b4a-b469-f82501192040 | note | CONFORMANCE CRITERIA: where Benkelman Beam deflection is greater than 2.4mm and less than 3.0 mm, excavate further 70mm depth, place an ARG GEOGRID on top of exposed subbase and replace with 70mm AC20 Asphalt and static roll.
baf713dc-ea9b-5879-a3c9-f3afd79caa00 | note | RECORDS: Asphalt QA
| checkpoint | 18 - Clegg Hammer testing
93472187-7e7f-55e3-8aa2-a02cfdbae410 | note | ACTION (Hold, Monitor, Witness): M
d25a54df-39bc-5102-83f6-02600008d153 | note | DETAIL: Design is approved and Drawings are of the latest revision.
62ae5b2e-c263-5d26-a27f-e12d62eff7c1 | note | FREQUENCY: Every 10 M intervals
717f314b-6d70-5eb7-a5ed-b9b097f699af | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Testing & Visual
834ffdee-f938-54c7-97d6-a86c0fe3dc65 | note | CONFORMANCE CRITERIA: CIV>=32
1cadc978-2a74-5bc5-9a40-139e238492a7 | note | RECORDS: Asphalt QA/Photos
| checkpoint | 19 - Surface Finish
a0aee9bd-eeeb-5abb-ba27-e5c1a309680a | note | ACTION (Hold, Monitor, Witness): W
a44532f9-b142-5711-8f55-a49dad751141 | note | DETAIL: TNZ P/9P
3f3f32f5-2193-5b90-99bc-4497233ab68b | note | FREQUENCY: Each Lot
dac2be3e-1e32-5463-bf3a-df25d20f9fb0 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual
8a3c6ea0-b36c-5f20-8ec0-a5a8de552828 | note | CONFORMANCE CRITERIA: Inspection: Uniform texture, no roller marks, no bleeding, cracking or shoving, no crushing of the aggregate
70679430-5b04-5f41-8382-3d09d0021d70 | note | RECORDS: Photos
| checkpoint | 20 - Reinstatement of Linemarking and RRPM's
f06f1e95-416d-5382-a356-fd9753f57708 | note | ACTION (Hold, Monitor, Witness): M
10353a1a-70c1-525b-8f45-39177c896a77 | note | DETAIL: NZTA M7 approved (Class B or C as required for anticipated traffic level)
2da7360e-e98b-5fc0-8fdf-864c6c57b23e | note | FREQUENCY: Every site
64cdad9d-71a5-5b23-9c14-5b08bb479f7d | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual
0c925bce-093c-5da0-8490-011f5ffd9909 | note | CONFORMANCE CRITERIA: Carried out within 12 hours of each shift completed and as per the existing markings
8712f397-8dc0-5c0e-8c11-a9bbe3e33fe4 | note | ○ Suitable Traffic Control to remain in place until pavement markings have been reinstated
e341a145-bf9a-5079-b5f1-0507dd756366 | note | RECORDS: Photos
| checklist | Aspiring Avenue/Thomas Road Intersection - ITP - Roundabout | itp | ITP - Roundabout | b37173d2-1c42-424a-9f6a-45a58496b1e7
| section | Construction
| checkpoint | 1 - Survey Setout
e267c551-62dc-5fea-b937-d14290681d99 | note | VERIFICATION ACTIVITY: Survey
9a92b015-8d8d-54e8-a74a-3a8896aafcf9 | note | METHODS OR REFERENCE: Setout Kerb Alignment required to construct to design
6e19d764-cc3c-5cd8-a37f-28470e9ba348 | note | FREQUENCY: Prior to commencement.
b547504d-f773-5971-babe-e610a351a5da | note | ACCEPTANCE CRITERIA: Survey
86c11592-555b-50c0-8b96-25c13acb7f84 | note | HOLD POINT: As per Drawings
b1607d36-c688-514a-b908-1b6d876477eb | note | RECORDS: Survey Receipt.
fb090939-04dd-51c8-a456-6d3fa2f17eed | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 2 - Concrete Roundabout - Central Island (1)
e18f5d38-1953-517f-812f-fd2893344266 | note | VERIFICATION ACTIVITY: QA FORM/ Drawings
27496bcf-9282-583d-be01-afe5003fec2d | note | METHODS OR REFERENCE: Construction Drawings
d037fb94-e58a-591b-9734-e6819ebb4b4d | note | FREQUENCY: Each Site
c162160e-48ea-5239-ae13-18ecabad3902 | note | ACCEPTANCE CRITERIA: Standard precast kerb to be hand-laid with 120mm reveal. Diameter to varies across with 2% cross fall.Kerbs to be sitted on 300mm Min AP40 Sub Basecourse , with CBR>5
e7310b15-8400-5dba-970a-1780e25be251 | note | HOLD POINT: Inprocess Inspection
7b1f047c-d5f6-56b7-be35-5b91a57a8231 | note | RECORDS: Photos
5a1ce8c8-38bf-50ee-bdfd-e9a34d27cb8e | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 2 - Concrete Roundabout - Central Island (2)
253c34f2-d76b-51b9-a937-c3d67f5fd2a7 | note | VERIFICATION ACTIVITY: QA FORM/ Drawings
64db97ba-d4bc-5a17-921c-24d227b4f337 | note | METHODS OR REFERENCE: Construction Drawings
a3cd80ca-0310-5fb6-a272-bd89cf2d98b8 | note | FREQUENCY: Each Site
dd5067a3-a319-5a3c-a637-5b4ead19bf3d | note | ACCEPTANCE CRITERIA: Central island to have 150mm GAP 65 Granular base course on removed pavement surface.
59ee57fc-45ca-53d8-82b5-11186efdddd4 | note | HOLD POINT: Inprocess Inspection
03145fce-c9bf-595d-8174-3a53c164820c | note | RECORDS: Photos
3475a165-4ed0-56b2-8d0b-6e2fdb34fca7 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3 - Concrete Infill - Central Island
658a44dd-491d-5cae-91ec-8b1a7ecf77ea | note | VERIFICATION ACTIVITY: QA FORM
fc266387-445b-5d66-bf47-cd9b062e1782 | note | METHODS OR REFERENCE: Construction Drawings
88fb8d9d-b970-5ebb-9600-6e3c565df917 | note | FREQUENCY: Each Site
8f65a592-b88e-5181-a57c-d7a6f1ab8f79 | note | ACCEPTANCE CRITERIA: 180mm depth of 20MPa Unreinforced Concrete with 3kg/m3 red oxide and Broom Finish
07b6a827-75df-58eb-838a-3e36f0209f0a | note | HOLD POINT: Inprocess Inspection
0074813f-ac6b-5922-910e-fc4f38a3e800 | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
4e0cf1bc-4abf-512c-915c-81420f28b3ef | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 4 - Apron (1)
30f15493-9af4-56fe-90fa-eafca254c737 | note | VERIFICATION ACTIVITY: QA FORM/ Drawings
7f20b137-db77-593d-8676-7ab612533c5b | note | METHODS OR REFERENCE: Construction Drawings
eba55cfe-09c0-56ca-b91c-5cd369bc9f15 | note | FREQUENCY: Each Site
46b7b240-8baf-5aa8-a2ef-5a1064f629b1 | note | ACCEPTANCE CRITERIA: Slip formed 25Mpa fibre reinforced concrete for roundabout edging
a107926f-462b-5f7b-8942-7fc5d0352f69 | note | HOLD POINT: Inprocess Inspection
3803b992-1304-56a3-b441-8002ded7842e | note | RECORDS: Photos
03ee46a6-6712-5a5f-a0d1-29ea235f18cf | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 4 - Apron (2)
1f61a866-a306-51dc-97f1-9db10adc699b | note | VERIFICATION ACTIVITY: QA FORM/ Drawings
94915d2e-4209-50b9-9c73-42edcee3c3ef | note | METHODS OR REFERENCE: TDM Technical Standards - IS0007
415db4fe-2115-5b62-8e2f-38c8d6d99605 | note | FREQUENCY: Each Site
0c8a5cea-4182-5b30-808a-332e7349d697 | note | ACCEPTANCE CRITERIA: Kerbs to be sitted on 300mm Min AP40 Sub Basecourse , with CBR>5
a07e2eca-984a-5766-b04c-d0bee293e28d | note | HOLD POINT: Inprocess Inspection
fc7d18bb-2c70-58ee-8bfd-3c31421745c5 | note | RECORDS: Photos of smart level/ Asbuilts
8156b613-52dd-531e-9413-0d758948d3d4 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 4 - Apron (3)
4bde5124-11dc-5670-a932-187db0032099 | note | VERIFICATION ACTIVITY: QA FORM/ Drawings
eb789ae4-a02f-5f50-9fe2-3650e5b74ca7 | note | METHODS OR REFERENCE: Construction Drawings
bff2811d-ec2d-5ab9-8a80-f8f73f818931 | note | FREQUENCY: Each Site
bb8fac79-ffc8-5bf2-811a-f715a8c0f36f | note | ACCEPTANCE CRITERIA: Apron to have 2% min fall towards the road and 2 m wide throughout.
c95e82d2-70c4-516e-9349-ef56d192970d | note | HOLD POINT: Inprocess Inspection
55a21f91-1199-521c-9564-a44fd8686c39 | note | RECORDS: Photos of smart level/ Asbuilts
1d470a26-e307-5366-8e5c-a5f481d10d48 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 4 - Apron (4)
59867f53-3610-573f-adc5-c0f6577802d1 | note | VERIFICATION ACTIVITY: QA FORM/ Drawings
bc9df65b-8628-598c-bbe3-bf87b85fb6b2 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0007
81163864-8e84-55f1-902f-362cea34fd7a | note | FREQUENCY: Each Site
85f54c13-679b-5444-b8a4-4c209b77f88a | note | ACCEPTANCE CRITERIA: Apron to have 50mm thick AC14 HF with 0.25mm Polythene layer on top below concrete
d69ff90a-1506-5032-b110-943d9e05fdf0 | note | HOLD POINT: Inprocess Inspection
e330313a-a4f8-5f5a-8522-101b62bc6cf7 | note | RECORDS: Photos of smart level/ Asbuilts
bc5f8ded-472c-501d-abe2-2fca63ba3c36 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 4 - Apron (5)
f57bd132-92eb-5925-966f-f0996b28872b | note | VERIFICATION ACTIVITY: Concrete Dockets
75fbe7b8-4594-5be5-b304-d66c96eeac1c | note | METHODS OR REFERENCE: Construction Drawings
f71d62a6-cb88-599f-bb27-a223fbdb4920 | note | FREQUENCY: Each Site
82486872-a04b-5fbb-acf9-c55c2428010b | note | ACCEPTANCE CRITERIA: 195mm depth of 40 Mpa concrete with 4kg/m3 Black oxide and Broom Finish
184b716c-6cbd-5a97-b960-6289be86f819 | note | HOLD POINT: Inprocess Inspection
627120cd-bcf6-5f05-8ba3-54c8da49e711 | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
ca9eae54-f0c1-52a8-8293-f876249cd71c | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Asbuilts
| checkpoint | 7 - As built information
a1d77dcb-f628-5963-a74d-173c7754c6d6 | note | VERIFICATION ACTIVITY: Drawings
3df4a4b1-2d7e-5075-bd5c-e303ad4d8358 | note | FREQUENCY: Every Site
31ba5d5a-dcce-5614-9415-0c5b65919361 | note | ACCEPTANCE CRITERIA: As built drawings
a6331f13-cbd2-59ed-a817-5b82b9cd626c | note | HOLD POINT: Inprocess Inspection
c9efed68-7dc1-5216-aa08-8165c4bb21c6 | note | RECORDS: Asbuilt records
3fef1d01-60fa-53e9-94d3-b2f885454ab6 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| checkpoint | 7 - RAMM DATA
b2354c69-62ea-57d1-9668-2e936c4621cc | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
f2e64a05-9191-5ce0-b489-be6b903b6538 | note | FREQUENCY: Every Site
b5806d3a-1a53-5468-b356-047d72c1090e | note | ACCEPTANCE CRITERIA: RAMM SHEET
0fec1540-bcac-5a6e-83cd-eb2fc2368a76 | note | HOLD POINT: Inprocess Inspection
eb048f85-6aa8-5f26-bbfb-02632331d1cd | note | RECORDS: Asbuilt records
48e81f3b-e0cf-53b8-98e1-b252c33cb612 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| section | ITP APPROVAL
| checkpoint | ITP Approval
5f1ce3b2-d597-56dd-8df1-1c75d6014806 | note | Prepared by: Cimyona
a3767b46-a902-591b-ab1d-b7035ef147bc | note | Approving Delegate: Daniel Tat
| checklist | Aspiring Avenue/Thomas Road Intersection - ITP - Signage | itp | ITP - Signage | 24a4fdc5-0c89-4471-b9bb-cee9148ce77d
| section | Site Set Out
| checkpoint | 1 - Site Set out
43d1dad6-953a-5490-9378-b144a1c25400 | note | VERIFICATION ACTIVITY: Surveyor
63ab6d8c-6ccb-546a-ab81-486626a1f633 | note | METHODS OR REFERENCE: Surveyor
ef00f50f-39c5-533d-8f19-4110265a17db | note | FREQUENCY: Everysite
164d3088-ab90-5958-a112-728cfdc284c1 | note | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable. Alternatively like for like.
4578e170-eb67-5ae1-bb03-49c66c1e77a8 | note | HOLD POINT: Mandatory HOLD POINT -
7635ce31-2b79-51ae-87aa-680b9377379b | note | RECORDS: Survey Receipt
c8a0a333-892c-5591-a9ad-6675f147e2c2 | note | ONSITE RESPONSIBILITY: Site Engineer
| signoff | Mandatory HOLD POINT
| section | Materials
| checkpoint | 2 - Signs/Belisha Disk
7d1253d9-45d2-58f9-965a-b03dd1c4918c | note | VERIFICATION ACTIVITY: QA FORM
8e54cfd2-c85b-5ea1-a018-501854d10626 | note | METHODS OR REFERENCE: TDM Technical Standards
c86afba0-0ed0-5a1e-8e1f-cb57397401e9 | note | FREQUENCY: Every site
7091bbd4-f509-52d3-b4f7-4d34d29651b2 | note | ACCEPTANCE CRITERIA: All signs to looking in excellent condition. Signs to have good reflection and visibility. NO scratches or markings. All signs to match with construction drawings provided by designers.
e2505098-1e84-5705-8954-f6eeca4fc82b | note | HOLD POINT: Inprocess Inspection
0cf1973d-2599-5d0a-9380-ab514c375baa | note | RECORDS: Dockets/Photos
e07b2c76-6173-5a22-a5c4-c189f01888ac | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3 - Pole, Impact recovery post and Ground Socket
6c146a3b-241f-5149-b375-02925924372c | note | VERIFICATION ACTIVITY: QA FORM
b45fb782-fe43-5d58-aef9-ca7e4b47b9b0 | note | METHODS OR REFERENCE: TDM Technical Standards
e6966bd1-80b6-502d-ac94-099d66edf219 | note | FREQUENCY: Every site
3e7f4e0c-7da0-5e79-99e9-98759462c509 | note | ACCEPTANCE CRITERIA: Check for underground service before installtion. All poles and post to be looking in excellent conditon with end caps - 3m long. Ground socket to be 60mm dia, 600mm deep with grouted screw or pins. For Black and white pole 76mm dia and 600mm deep
349ef3f4-61a2-58d2-aeab-e4a0bf01f231 | note | HOLD POINT: Inprocess Inspection
da71e2d8-5da7-568d-9111-76808e4b096d | note | RECORDS: Dockets/Photos
d4b5368e-19ef-508e-92c6-a6fa60f8d9aa | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Construction
| checkpoint | 4a - Ground Socket
be68af75-dc61-5049-8efb-49c92fd1d1bc | note | VERIFICATION ACTIVITY: QA FORM
d284d26b-9f41-54c6-9341-a186c359c6d9 | note | METHODS OR REFERENCE: TDM Technical Standards
032930b4-7458-54df-af2c-562496f96fb5 | note | FREQUENCY: Each Socket
1f748ea4-1a4b-529d-8f5f-20a680f9443b | note | ACCEPTANCE CRITERIA: The dug out hole to be 300mm wide and 600mm deep. 20Mpa concrete with 50mm cover at bottom to be used for installing socket. The sockets to have 50mm reveal at top and smooth finish of concrete around the socket.
54f82943-fe13-5c2e-aa51-2216cf078b35 | note | HOLD POINT: Inprocess Inspection
10221428-a148-50e0-9d7c-e0efe5f53c44 | note | RECORDS: Dockets/Photos with tape measurement
a2c15515-d002-5e90-8ae6-8fb412c50cf2 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 4b - Pole and Impact recovery post
92f3d015-331a-52ce-94a0-67bac67b3e2d | note | VERIFICATION ACTIVITY: QA FORM
4ea73228-d8fd-558c-bf25-f82d0511778e | note | METHODS OR REFERENCE: TDM Technical Standards
45327af6-32e0-50f9-a571-83dd114c9f92 | note | FREQUENCY: Each Post or pole
f0f6b8fd-1360-5cac-a932-b61de8ce2045 | note | ACCEPTANCE CRITERIA: All poles to inserted into the socket after the concrete curing. And, the screw or pins to be used to prevent thr pole rotation. The impact recovery post installed on the island infill surface after curing period by drilling and using Dyna bolts. The bolts are tightned sufficent to prevent rotation.
2b6a39cf-51cc-56fe-b679-cc6432dd3ab3 | note | HOLD POINT: Inprocess Inspection
7efad214-b1ae-5aaf-9f8c-70d1ae04cf00 | note | RECORDS: Dockets/Photos
72ab3c9c-99c9-52b2-8eee-66f3a472f189 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 5 - Signs/Belisha Disk
19c8ca63-a43c-5c92-9561-bad0fbd277cc | note | VERIFICATION ACTIVITY: QA FORM
67d95e19-5f3a-570a-b326-89af63dbbdef | note | METHODS OR REFERENCE: TDM Technical Standards
30db924d-f0dd-5a0c-8838-6352cc46676a | note | FREQUENCY: Each Sign
bb183aca-abb9-5fe8-8459-2256d4696fc5 | note | ACCEPTANCE CRITERIA: All the sign/Belisha disk to be fixed with the pole or post with ARC brackets and tightened adequately.
5645f92c-f1b2-5195-b034-5b0a6e6cd149 | note | HOLD POINT: Inprocess Inspection
0b4c4928-b69d-5a50-809c-0bf07736e937 | note | RECORDS: Dockets/Photos
85679136-9b3b-569f-9579-731f3b37814d | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Asbuilts
| checkpoint | As built information
a5a30423-0697-51f3-9a4a-a06c509d1ef8 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
5daadf3e-582e-5a8e-9c9d-9df8c15c3cd0 | note | FREQUENCY: Every Site
e55139db-666b-55b7-b7a0-9cca9f216221 | note | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
9e2520de-953f-52bf-b882-8ac8a598e939 | note | HOLD POINT: In Process Inspection
cea3f69a-329b-58cd-8890-61ea6d98da1b | note | RECORDS: Asbuilt records
3779d47b-7338-5c75-9b36-950078e5afd6 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| section | ITP APPROVAL
| checkpoint | ITP Approval
db9f91ab-5a06-5255-b1e5-6344c3a7862f | note | Prepared by: Ajithkumar Ayyanar
e272b6fd-b4d8-504b-9e84-af415b005f54 | note | Approving Delegate: Nithin Thomas
| checklist | Aspiring Avenue/Thomas Road Intersection - ITP - Stormwater Drainage | itp | ITP - Stormwater Drainage | 556a2524-dc9b-431e-9c42-0324b77f20d0
| section | Details
| checkpoint | 1 - Permits & Services (1)
452703bc-554d-5834-b594-b29087a4418e | note | ACTION (Hold, Monitor, Witness): H
ac162532-2bdc-54e9-95fb-78f80730da10 | note | DETAIL: Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
a54e1f06-279b-5b15-b9a6-d77f8f4f3c27 | note | FREQUENCY: Prior to any construction commencing
62cad3ef-010f-559d-877c-cdee030a73cd | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
9f54ff8e-9ead-593e-bc4a-e1f6469b9f0c | note | CONFORMANCE CRITERIA: Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority
7ca778a6-8667-5f9e-ac06-2da3334ea1ac | note | RECORDS: Permit attached or permit number noted.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1 - Permits & Services (2)
73686674-29b1-5d51-b5eb-35be6b81dc25 | note | ACTION (Hold, Monitor, Witness): H
5290ce4d-9748-5688-8807-75d1a0d96b40 | note | DETAIL: Locate and mark out all existing services
e5476c62-a0e5-51f8-a8e2-937d655ad6e1 | note | FREQUENCY: Prior to any construction commencing
5afdfa46-6d49-5c83-8214-3e0396898d54 | note | CONFORMANCE CRITERIA: B4u dig procedure - follow utility protocols
803c9dd3-af2b-5d12-b046-be78658b8bbd | note | RECORDS: B4u dig plans & GPR report attached
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Pre-Construction Sign Offs
4240c31f-968f-5f3c-9324-5fda438dae42 | note | ACTION (Hold, Monitor, Witness): H
1b6d9fa4-a0ed-50ed-a69e-81122bb110f1 | note | DETAIL: Sub-Contract and Supplier Agreements
5310a383-1345-5c97-8740-63b5781bbc68 | note | FREQUENCY: Prior to commencement.
f92ddbeb-863f-51aa-b2b8-f7c0f27e5617 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
247e79a3-b39c-5091-877c-950a8211c75c | note | CONFORMANCE CRITERIA: Sub-Contract and Supplier Agreements to be agreed and signed
297f233e-ceac-57c6-a69a-82294ba44c77 | note | RECORDS: Subcontract and Supplier Agreements
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Design
124e2c83-6a28-58f1-8e69-1a87924bec7c | note | ACTION (Hold, Monitor, Witness): H
385aecb9-357f-5886-a3b2-f65a16ac3ef6 | note | DETAIL: Design is approved and Drawings are of the latest revision.
d62bc87a-cba4-5053-91a2-4e23e1f4d874 | note | FREQUENCY: Prior to commencement.
ef49cb61-0187-5c80-9e47-1f5792495bbe | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
0647647e-5e05-5045-8469-d9beacc35099 | note | CONFORMANCE CRITERIA: Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
e80929ca-0ad3-5be3-83c1-643168f71453 | note | RECORDS: Drawing Register.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Survey Set out
d64fafd1-3157-5cea-a340-8e37bbcefd46 | note | ACTION (Hold, Monitor, Witness): H
6e09fcbc-af24-56e5-98ea-c370575cea77 | note | DETAIL: Set out Pipe Alignment and Service Locations with inlet & outlet points and inverts as required to construct to design
68781224-ae46-5331-903b-aa03fa1a2fa5 | note | FREQUENCY: Prior to commencement.
75499ca4-deca-5cd3-bd46-524d7fa5c019 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Survey
898da259-3769-5660-ab6d-1564f65917ff | note | CONFORMANCE CRITERIA: As per BlueBarn Engineering Drawings: 02237.17-T-400 & Set out files
1ea42f9a-9b18-5347-b817-cc470434482b | note | RECORDS: Survey Receipt.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Pipe and Manhole Material Compliance
eb4fe9b7-ad17-5fc0-8989-f02678ae8d3f | note | ACTION (Hold, Monitor, Witness): H
b3ed3ede-50c6-5a9c-8d03-ad6368f1e291 | note | DETAIL: Cesspit, Manhole and Pipe shall comply with relevant AT/TDM standards
64bdae02-f633-5e1f-a91a-724de1f68742 | note | FREQUENCY: Prior to commencement.
b64aef36-1ecb-5955-bbe8-2846f9f255f6 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review, Visual Inspection
82f38cb9-202e-513f-9e32-10349b7e8697 | note | CONFORMANCE CRITERIA: Pipe shall be checked for freshly formed pipes and return if required:
27cf0fc6-8a53-5a5a-900f-84448436ecf8 | note | 1). DN225 Class 4 RCRRJ pipes AS/NZS 4058
30de62de-aab4-565f-bfaf-6d08b8f30731 | note | 2). All Concrete RCRRJ pipes to be fitted with Rubber rings
c4fc0a4c-c021-5889-93c9-585bd2c85543 | note | 3). Pipes shall have product certification (ISO Type 5) to AS/NZS 4058
7ee380ae-d24b-5679-9ded-cec54b48837a | note | ○ Prefabricated concrete Manhole shall be in accordance with TDM Standards & AC COP
646745c3-f492-5749-824b-20a47c21e911 | note | RECORDS: Manufacturers Data Sheets, Delivery Dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Locate Existing Services by Hand Digging / Hydro Vac
7b52310f-b2ed-5cf7-9cf8-9cdf6d5a7d75 | note | ACTION (Hold, Monitor, Witness): H
c6772513-cfdc-5544-b5aa-12f00a0866a9 | note | DETAIL: Ensure all services conflicting with the line of trench have been exposed by hand digging.
cb678f90-c7ef-56e0-a031-a6d214b158d0 | note | FREQUENCY: Prior to commencement.
4498559c-2722-57d4-99f9-8972415fefe3 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Potholing / Survey
71b37e19-a278-597f-b283-62b878d22c17 | note | CONFORMANCE CRITERIA: All conflicts have been located. New services and / or conflicts to be advised to Project Manager.
69fb4ee1-1400-5d40-be4e-d3d361bf440f | note | RECORDS: As-built Drawings. Doc. Review
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Trenching & Excavation (1)
548fc5f6-9950-5c22-8399-384e468d9ff5 | note | ACTION (Hold, Monitor, Witness): H
d48797fc-f9f1-5be0-8698-16134eb89469 | note | DETAIL: Excavation methodology
ff3b328b-70c0-57b2-b581-febf0179c3b1 | note | FREQUENCY: Daily
f88a7af3-ee77-5450-9d1d-5b87231a9455 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Prestart review
8e38735a-bab3-5b84-b31c-0982f892ca50 | note | CONFORMANCE CRITERIA: The excavation, benching and shoring requirements shall be in accordance with Worksafe Excavation safety guidelines (2016)
6354f7ea-1a4e-5950-906c-677339748876 | note | RECORDS: Prestart RCP
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Trenching & Excavation (2)
223a3d2c-d8ca-5152-9c5c-b694a1977937 | note | ACTION (Hold, Monitor, Witness): M
c7af4189-5fd3-5e88-9b85-79e2420ffcc9 | note | DETAIL: Trench Profile - Width
2f1b9342-1c04-5b15-8731-a27ff211fa68 | note | FREQUENCY: Daily / as trenching takes place. Different depth methodology
2917a694-18db-5068-acaa-9d25d2046050 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection, Excavation methodology
58cace97-3539-5215-b948-66eafb96efe2 | note | CONFORMANCE CRITERIA: Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing
63452837-b65a-56f3-94ac-e6dbad7d09b2 | note | RECORDS: Construction Photos
| checkpoint | 7 - Trenching & Excavation (3)
e4eefefd-e31c-5377-bb60-b250df323d72 | note | ACTION (Hold, Monitor, Witness): W
17cbdf81-b785-55e2-942b-391ce4523b2a | note | DETAIL: Trench Profile - Depth
54aecb41-7550-51fe-b401-777b2e41593a | note | FREQUENCY: Daily / as trenching takes place.
77611264-3d10-57a5-a2aa-3b8d8a5c4c09 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection, Measurement
1ae0606b-dd55-56fc-ac6e-6c46c7895f32 | note | CONFORMANCE CRITERIA: Trench depth varies according to long section and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings
42021b18-243e-5b55-ba8f-2bd35419abbe | note | RECORDS: FH Drainage Line Record / Construction Photos
| checkpoint | 8 - Bedding for Concrete Pipe Laying & Manhole & Cesspit
dbf75dd5-c325-5c69-a755-89ff7ccb227b | note | ACTION (Hold, Monitor, Witness): W
ca4a444d-1e9f-5088-932e-83019b33fd13 | note | DETAIL: Placing and compaction of Bedding Material.
0aac8e8d-07c9-5972-9892-698c0dcf716b | note | FREQUENCY: Inspected continuously during placing and compaction of Bedding Material.
0f9ee56b-2aae-53c9-91ed-fa402978f8ff | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
44ab7bec-d0c1-512a-8833-148ee6a7ed3f | note | CONFORMANCE CRITERIA: Bedding & Pipe surround material to be GAP7 or GAP 20 (Stevenson Quarry) or alternate material that complies with AS/NZS 3725
5098cf37-c716-5883-ae3e-d2da866d37a0 | note | RECORDS: FH Drainage Line Record / Construction Photos
| checkpoint | 9 - Pipe Position Tolerance
482e4bb5-3771-5187-b557-f6b686f699e8 | note | ACTION (Hold, Monitor, Witness): M
5b897091-f6f7-51bb-92b0-59eedb784686 | note | FREQUENCY: At any point of pipe
79548c2d-9f90-586f-b3aa-e2224f0b22df | note | CONFORMANCE CRITERIA: Position tolerance for pipe laying at any point along the length of the installation shall be within ±30 mm from the specified design.
424ed329-800a-59b4-9820-41bf055779b7 | note | RECORDS: FH Drainage Line Record, Survey Data.
| checkpoint | 10 - Trench Backfill - Placing & Compacting
61ebb949-29f0-5640-bb36-eed1976f9141 | note | ACTION (Hold, Monitor, Witness): M
96dfe2c9-ddef-5de2-9971-fbee3a3adb44 | note | DETAIL: Placing and compacting of Trench Backfill Material
7515e1b8-8160-5f6f-9550-7cdc64f03883 | note | FREQUENCY: Throughout Trench Backfilling operation.
e866823e-273a-55c2-87f3-7366b53e1c78 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
86712bed-42f2-58f7-b904-cd74cf7392ff | note | CONFORMANCE CRITERIA: Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm
dcf0ef26-c084-5a02-aad1-81fa76737827 | note | RECORDS: Construction Photos
| checkpoint | 11 - As-Built Drawings
fd877d0e-83ce-5caa-97fd-f63ade03edc6 | note | ACTION (Hold, Monitor, Witness): W
15f5f821-628f-5545-9a5f-5f511a52232e | note | DETAIL: Red pen marked-up As-Built of every 'Issued for Construction' AT drawings
1e5a6e22-6a74-5b58-9089-b5659366da0f | note | FREQUENCY: Final As-Built Drawings to be completed within three months of the construction completion of the asset or infrastructure.
3e687eb7-2413-5e13-89ea-3ff6814c3750 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Drawings / Visual Inspection
b18c8fca-bd3f-5b30-b84e-d215a09de309 | note | CONFORMANCE CRITERIA: As Built and GIS Data
03402247-d579-59f9-bb62-65fe7abb306a | note | RECORDS: Redline As-Built Drawings, scanned as .pdf files.
| checklist | Aspiring Avenue/Thomas Road Intersection - ITP - Traffic Islands | itp | ITP - Traffic Islands | 9b92b4e8-8caa-4c4b-aece-f2832e3b09af
| section | Materials
| checkpoint | 1 - Mountable Kerb
d38fd770-edd7-5c83-ac72-248384d23901 | note | VERIFICATION ACTIVITY: QA FORM
d3fe3443-f868-5126-b5c9-fd25aa5ee001 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
62b521ac-6e68-56e3-9d88-5af7739207a4 | note | FREQUENCY: Everysite
c8cd3904-7032-5623-9b81-aad0489c2251 | note | ACCEPTANCE CRITERIA: Mountable Kerb to be laid using precast hand-laid and painted with two coats of reflective paint
99de6075-a62b-59b6-bd03-0654ee9aae7f | note | HOLD POINT: Inprocess Inspection
bc8577df-eba4-5ab1-a140-2c2406f95265 | note | RECORDS: FH concrete QA sheet, photos.
7bc84177-6234-5385-a2fc-ccba7f0000ac | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Construction
| checkpoint | 2 - Survey Setout
4a4c257f-9f07-54a0-bacb-b4403d858fa4 | note | VERIFICATION ACTIVITY: Survey
3b163d88-7354-5f61-aed4-936a613ec694 | note | METHODS OR REFERENCE: Setout Kerb Alignment required to construct to design
e514d4db-bfba-5ef8-a46c-9aeec1daeafb | note | FREQUENCY: Prior to commencement.
13280ebc-9aa2-599d-98b1-fd3e38eb8035 | note | ACCEPTANCE CRITERIA: Survey
2fdbd7e8-6eb3-58a7-92cd-ed7ed1bd0896 | note | HOLD POINT: As per Construction Drawings
c92bc491-e2b1-50aa-b68a-a8a4aa08a47e | note | RECORDS: Survey Receipt.
9837c982-e240-5c17-ae51-48c32bfde9e1 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3 - Concrete Island (1)
e9b81451-bdea-5bb5-95f7-614c23635178 | note | VERIFICATION ACTIVITY: QA FORM
14e75135-c768-5bd8-ad9b-d1174eafbbd1 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
041b49a5-1c28-53c5-9496-9c4514843110 | note | FREQUENCY: Each Site
c4aee28f-6f1e-5a14-baf1-df02695e5ae8 | note | ACCEPTANCE CRITERIA: Kerbs to be haunced with 20MPa Concrete
33d98ad4-9159-5c50-8d72-4cab8088bb90 | note | HOLD POINT: Inprocess Inspection
728299e1-acf2-5f67-a829-a0f806f75b47 | note | RECORDS: Photos
f8a73f79-99e8-5e63-be7b-d619b478c0de | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3 - Concrete Island (2)
8873a134-c11a-55ca-9f45-d25dcd9c5d44 | note | VERIFICATION ACTIVITY: QA FORM
fbc6872a-fa8d-5493-8625-5cb32db997c3 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0003
d95056c0-8201-5ee1-9d18-4bc2a82053c3 | note | FREQUENCY: Each Site
62a182d5-7d42-5e17-86e4-239912169750 | note | ACCEPTANCE CRITERIA: Basecourse to be 150mm min thickness of GAP65
b3834096-6ded-518f-8ce2-6fef5d92369a | note | HOLD POINT: Inprocess Inspection
d283711c-330e-5b87-b793-2e99be3f67b6 | note | RECORDS: Photos
36baf4a6-6558-5d50-b9c4-ab93833b76b0 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 4 - Concrete Infil
38f4769b-a921-556f-a981-e2fb615220d1 | note | VERIFICATION ACTIVITY: QA FORM
dee4b2e8-b052-5cb2-8fcf-d6f3653c9e43 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
771486e4-224b-509b-b18c-15190ab6aa0b | note | FREQUENCY: Each Site
695cf374-431f-5758-b2ca-06a4837e39f8 | note | ACCEPTANCE CRITERIA: 180mm depth of 20MPa broom finish unreinforced Concrete with 3 kg/m3 Red oxide Cross Fall of 2% or max rise in centre of 180mm
fd1ba9eb-fbd9-54a5-bc53-8be211c13f2f | note | HOLD POINT: Inprocess Inspection
66aaf7bd-4b85-59cc-b7fb-a797d8525a18 | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
57cc3bee-36d2-5f3f-8ed0-8075c9ff8210 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Asbuilts
| checkpoint | 5 - As built information
213167b9-6bd2-5239-ae2b-a1b16e1079a9 | note | VERIFICATION ACTIVITY: Drawings
50953463-c98d-5fcb-8748-68dae37de24b | note | FREQUENCY: Every Site
9763fb8b-5813-55f7-ba6d-db9c62d1b263 | note | ACCEPTANCE CRITERIA: As built drawings
d41592d7-24c3-5fb9-9da0-1498c9393869 | note | HOLD POINT: Inprocess Inspection
7e2706dd-a40f-58b4-9465-14a867fb2e76 | note | RECORDS: Asbuilt records
96691325-1c6c-5b6f-99a4-352cb138d1ea | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| checkpoint | 6 - RAMM DATA
7abf95ba-b102-5525-b277-83e2c3878d0f | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
1eb62423-663b-557e-ae59-456135eacebd | note | FREQUENCY: Every Site
f23ea4ee-a92b-576a-8d3c-be7294e5f1bb | note | ACCEPTANCE CRITERIA: RAMM SHEET
a343156c-6a13-5edc-9278-7c6df19bb4c5 | note | HOLD POINT: Inprocess Inspection
1059e392-fc40-583c-b529-cbc37adb2285 | note | RECORDS: Asbuilt records
14735c05-32a6-5607-ba36-1b48e3e58ffe | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| section | ITP APPROVAL
| checkpoint | ITP Approval
f6bf240d-30d9-5455-88f9-cd332286eba1 | note | Prepared by: Yeswanth Vemula
46f7028e-70a5-52f2-8d19-bc1b73f34dad | note | Approving Delegate: Daniel Tat
| checklist | Atkinson Ave - ITP - Raised AC Table & Intersection | itp | ITP - Raised AC Table & Intersection | 7e7cfc68-a499-49e2-9350-d80d5af84f23
| checkpoint | 1 - Permits
af21b676-d32e-58d4-9ecf-a6a29451ce96 | note | H
3964272c-2e2e-5484-8394-36d20d5abe70 | note | Detail: Obtain Permits
34d0409b-feae-5f33-8c70-f9c7971b95c9 | note | Frequency: As required
dd29353f-e4b6-57af-a6d5-6862ddd9a2a8 | note | Inspection / Test Method: Document Review
2ea5a2bb-438b-505b-865a-b50edc1c42d1 | note | Conformance Criteria: Control Checklist - Fall Prevention (if applicable). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
5cb2201f-8aad-579b-bcfb-20d8f704b6a4 | note | Records: Permit attached or permit number noted
3a093025-6d25-52bb-8996-05ec4648636e | textbox | FH Initials - Site Engineer:
| signoff | HOLD POINT
| checkpoint | 2 - Pre-construction sign offs
f3db8d0c-8c4c-5a3e-b054-433dd18f2074 | note | H
1d3874ef-ec93-5661-b529-e8fae6b2f55f | note | Detail: Ensure that Sub-Contract and Supplier Agreements are signed
8bfb4edf-fcec-52b8-8701-90b53f04c77e | note | Frequency: Prior to commencement
8892e96a-d75f-5c15-90e6-a1d5b6f4a4df | note | Inspection / Test Method: Document Review
c109d9cd-863f-5c27-8da6-35ff049b78fd | note | Conformance Criteria: Signed Subcontractor and Supplier Agreements
1ae1a34b-03dc-5557-806f-10526686233b | note | Records: Subcontract and Supplier Agreements
21c50b37-0cf9-581d-854f-4d07656510d6 | textbox | FH Initials - Site Engineer:
| signoff | HOLD POINT
| checkpoint | 2.1 - Pre-construction sign offs
f6026cdd-80e2-50bd-815b-d9cfb32fb575 | note | H
9998b4cf-37be-5327-802e-da2999a69acf | note | Detail: Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
1dc46e8c-c76c-575a-9d9d-5f99e3211dbd | note | Frequency: Prior to commencement
79e16082-52cc-5b0f-9f8c-38d524e90f12 | note | Inspection / Test Method: Document Review
b0239f68-0f08-59d8-b6aa-990d3c961727 | note | Conformance Criteria: TMP is approved by CAR manager for each site and works are only completed within the approved dates..
2c921d2d-008a-5bae-838c-5f2c97edd94d | note | Records: TMP on MyWorksites/On Site
2c713837-f71b-5886-8ce4-9a64c9cb55be | textbox | FH Initials - Site Engineer:
| signoff | HOLD POINT
| checkpoint | 2.2 - Pre-construction sign offs
fc0f1c40-4a8b-501d-91e8-82d32c418d16 | note | H
d62fd30c-0580-5fac-8eae-d28dab6cb43a | note | Detail: Ensure all Sub-Contractors and Suppliers go through FH induction
70cd0c92-9432-5d94-9f23-39285688515e | note | Frequency: On site daily
b1a58794-01c4-5863-9936-645cb02514ff | note | Inspection / Test Method: Induction
4b46b496-1f42-5249-9131-aa58010ed731 | note | Conformance Criteria: Supplier's and Subcontractor's signatures on hazard ID and pre-start documentation
6bf2b116-8843-534e-86e7-4b25b5b61694 | note | Records: Hazard ID and Pre-starts to safety team
b30e912b-6c44-50b0-b341-6385dcb71bb2 | textbox | FH Initials - Site Engineer:
| signoff | HOLD POINT
| checkpoint | 3 - Design
d6994a8f-6cff-567a-ba9b-63127b4aa4b5 | note | H
8a94ae40-2601-52e6-80dd-517efdc9b76a | note | Detail: Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
deb263ed-7822-5586-8ee9-b0cbbd59afe0 | note | Frequency: Prior to commencement
8c0f7813-8b50-5c49-8678-d574feacf828 | note | Inspection / Test Method: Document Review
93ac07f7-f9fa-501a-9545-1f33dc8a6b51 | note | Conformance Criteria: IFC drawings have been received by Contractor
7bed29bd-9f42-58fa-8dd5-7eb666f77673 | note | Records: Check Drawing Register
74dcc125-206c-5272-adc9-fe421ecce6bf | textbox | FH Initials - Site Engineer:
98bf0ac9-ade3-5da6-9cbc-493e3f25ca33 | textbox | Design Engineer Initials:
| signoff | HOLD POINT
| checkpoint | 3.1 - Design
75bb0303-fa07-59fd-8d14-c73a460f7b61 | note | H
f96da6f1-414f-569c-a7ec-4c79c049ecf4 | note | Detail: Crossing to comply with AT TDM chapter Traffic Calming and TDM TC0003
247524fb-8d66-5be5-b90f-e1072a163f38 | note | Frequency: Prior to commencement
7b3fdbf0-9617-5868-88c4-90268c00c1a8 | note | Inspection / Test Method: Document Review
e57ca0fc-7727-5e9c-b5be-0937654d4cbb | note | Conformance Criteria: IFC drawings have been received by Contractor
c6719590-9e62-5861-ba98-a885c6bd2639 | note | Records: Check Drawing Register
c81ecd67-fd15-5854-b186-82f38423fd1d | textbox | FH Initials - Site Engineer:
f87149e4-c1d6-5dda-a789-c4e515bdd5b8 | textbox | Design Engineer Initials:
| signoff | HOLD POINT
| checkpoint | 4 - Installation of Erosion and Sediment Controls
3889f520-5e18-5cdb-b348-10395dfb86b5 | note | H
671a1dd8-e3b1-500e-8f80-cb6b67bb4063 | note | Detail: Ensure that Erosion & Sediment Control in place
055f4159-1486-5989-9430-90da90d22a16 | note | Frequency: Prior to commencement
e1f97454-fb2e-5a19-acf9-699d2855356f | note | Inspection / Test Method: Visual Inspection
823a320e-57ed-5bec-9e57-c6f60ea484da | note | Conformance Criteria: Cesspit Covered
c6a58ada-d553-582f-9689-63dbdabd0b9f | note | Records: Environmental Controls Audit
db35af76-cf99-567c-8168-a08c66809297 | textbox | FH Initials - Environmental Manager/Site Engineer:
| signoff | HOLD POINT
| checkpoint | 5 - Survey Setout
47b0e8dc-2f79-5ae1-85fe-ad6cf3580330 | note | H
54201b03-b721-52e7-85d1-d50482845c35 | note | Detail: Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations)
00be5d2b-6c03-5ce0-b5cf-fc5b9f28e7ab | note | Frequency: Prior to commencement
d0f271e7-f646-51cc-b91b-9ef0817be526 | note | Inspection / Test Method: Survey + Smart Level
877fe557-dabc-5935-8a6b-c9cb35b8d819 | note | Conformance Criteria: Consistency with Construction Drawing
b370ef01-8675-5ea1-ac29-29249d34a730 | note | Records: Site Photos post surveying
f4f9731a-52c0-500d-96d4-77f7e094dd6b | textbox | FH Initials - Site Engineer:
| signoff | HOLD POINT
| checkpoint | 6 - Locate Existing Services by Hand Digging
40f66042-9cb1-54c9-b6b7-5641526083d0 | note | H
cd204d1e-0d3e-5e2f-91b0-2aa350c82a1b | note | Detail: Ensure all services conflicting with the line of trench has been exposed by hand digging
3cdd2053-606c-5071-9abe-7a31cac3911d | note | Frequency: Prior to commencement
51127c67-48c3-51d4-81d2-2fe394898a0b | note | Inspection / Test Method: Potholing
521bd02c-1410-5818-be1a-f88679c90134 | note | Conformance Criteria: All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. Asbuilt all services
32236c30-f260-5a0e-a00b-2be9396f8910 | note | Records: Digging and excavation checklist, service planes,As-Built Drawings Doc. Review
2e23e88d-bf94-517c-ab11-6191d52aceba | textbox | FH Initials - Site Engineer:
| signoff | HOLD POINT
| checkpoint | 7 - Asphalt laying
f70787d0-fb3b-52f8-87be-0994c75fbb36 | note | W
5c32750f-d250-5b13-a1a9-f18f5aeca447 | note | Detail: Raised table and raised intersection formwork to be 75mm above existing road level and be 175mm in depth and gradients respectively of entry and exit ramps
69cf4635-7c5b-58fb-a966-f5fa5fb036d8 | note | Frequency: Grade on ramps
0397eae5-accd-5a42-b950-3c7f332c009f | note | Inspection / Test Method: Measurement
5962cf4e-013b-5c72-bc22-25da14c324fd | note | Conformance Criteria: Designer to inspect formation level
03502a03-59e6-5ec7-8c89-3d68ce91ca27 | note | Records: Site photos
8ccfb68e-2fa9-5dda-92db-9e22f58b2502 | textbox | FH Initials - Site Engineer:
eaafdf36-a574-5504-877a-ef314b0d6f6a | textbox | MSQA Engineer Initials:
| checkpoint | 7.1 - Asphalt laying
4441b4e8-0e29-54d2-944c-bb24c7eb8f96 | note | H
e463eb7f-6642-53ec-84cb-d4c0cfc27f98 | note | Detail: Raised table and raised intersection ramps to have 100mm depth at entry point and tie into 175mm depth to meet raised table
b62d31db-f44e-5452-9e93-b5d499fc135b | note | Frequency: Grade on ramps
fd4482b1-25b5-5e99-91de-d6447d4b1a1c | note | Inspection / Test Method: Measurement
f5c344d6-d6fc-57b1-b304-7208e760607c | note | Conformance Criteria: Designer to inspect formation level
87a77715-548d-532b-8a71-be5e995f8ef2 | note | Records: Site photos
bf92aad0-3db2-5dad-adcb-816fca76b145 | textbox | MSQA Engineer Initials:
| signoff | HOLD POINT
| checkpoint | 7.2 - Asphalt laying
6fa401b5-c6b5-507d-9c7d-fd2e742a96f6 | note | H
030a34ca-4728-56fa-91af-729f65dc231a | note | Detail: Raised table ramps to be 750mm across for entry and 750mm for departure ramp. Raised intersection ramps to be 1125mm across for entry and 1125mm for departure ramp.
7e1f2984-ef16-5bbd-9362-23f964559279 | note | Frequency: Grade on ramps
87a98649-9bc3-53b3-aac1-ea9b9d6599bf | note | Inspection / Test Method: Measurement
cfdb0b5f-6af4-5930-a12b-8a8280eda813 | note | Conformance Criteria: Designer to inspect formation level
70e8817d-2f1a-5de3-8faa-a652fc172b3a | note | Records: Site photos
26d75f00-255b-5aed-b7fc-11ace349dba2 | textbox | MSQA Engineer Initials:
| signoff | HOLD POINT
| checkpoint | 8 - Asphalt laying
c3b3f8b2-9e7b-5e3e-9e3e-c746283dab4e | note | H
666ac5ad-c715-57b5-b205-2f2b1cd3e923 | note | Detail: Raised Table ramps to be 1:10 gradient for ramps - As per Relative gradients provided in IFC drawing No. 12544375-C151. Raised Intersection ramps to be 1:15 gradient for ramps - As per Relative gradients provided in IFC drawing No. 12544375-C152.
92776ce6-8fe1-516d-be79-73d75adb4672 | note | Frequency: Grade on ramps
36e0aa76-aeaa-58f9-97f5-a98254aa944d | note | Inspection / Test Method: Measurement
4f443e6f-7630-5313-9b8d-71698a755f50 | note | Conformance Criteria: Designer to inspect gradient level
4fca9d47-fa75-533f-9bf4-2494a647ff09 | note | Records: Site photos / Concrete Formwork Checklist
6fb16e5e-c924-50f7-b63a-7051c9f0e745 | textbox | MSQA Engineer Initials:
| signoff | HOLD POINT
| checklist | Atkinson Ave - ITP - Stormwater Drainage |  | ITP - Stormwater Drainage (Atkinson Ave) | 7e146bcd-0c2e-4f2d-8faa-99ff1cce41dc
| section | Stormwater Drainage
| checkpoint | 1 - Permits & Services
54a8b32a-a081-5df2-acc8-ae705735776d | note | H
cb11189f-87eb-52a7-a742-56fb0b0e6c3d | note | Detail: Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
e179bcb7-9380-5ac7-92df-59ccd65bc847 | note | Frequency: Prior to any construction commencing
2720ca53-6ba2-5aa6-9680-63babc04ba1f | note | Inspection / Test Method: Document Review
793ebc32-34f4-51f2-8e9f-877457565c63 | note | Conformance Criteria: Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority
aa57d955-8f54-5b0a-abc8-efb8cf8f4747 | note | Records: Permit attached or permit number noted.
6c7f5c6e-a285-5019-a759-4d87d1027355 | textbox | FH Initials - Site Engineer:
| signoff | HOLD POINT
| checkpoint | 1.1 - Permits & Services
32d1352e-9e8a-501c-8d4f-9e62835b9d2a | note | H
dce47360-e661-53da-8054-32537684441e | note | Detail: Locate and mark out all existing services
72e066a3-49a9-53b6-b687-f7b7a6e4ae6a | note | Frequency: Prior to any construction commencing
556736ed-b010-597e-9018-58ddeeafa267 | note | Inspection / Test Method:
67903b7b-97a5-5efb-bbfc-1feaf71eb4b2 | note | Conformance Criteria: B4u dig procedure - follow utility protocols
9f78abde-4c5c-5d29-a631-6d89e8180da9 | note | Records: B4u dig plans & GPR report attached
e5a598a3-9a9c-578e-aceb-f30f5d863f67 | textbox | FH Initials - Site Engineer:
| signoff | HOLD POINT
| checkpoint | 2 - Pre-Construction Sign Offs
89f66310-ff3f-56f1-9804-fd2d001aae13 | note | H
59211db5-188f-5742-824e-4dbef1096fc4 | note | Detail: Sub-Contract and Supplier Agreements
435274b0-9a98-513f-b6d9-77f57d357352 | note | Frequency: Prior to commencement.
2ae07466-e0de-582b-92c4-4b549e9d5c86 | note | Inspection / Test Method: Document Review
2ad7695a-637a-559c-8697-236a7ab8eeca | note | Conformance Criteria: Sub-Contract and Supplier Agreements to be agreed and signed
91f229a9-c755-5933-b850-89b8e8eddbab | note | Records: Subcontract and Supplier Agreements
4c989ba1-6169-5aa6-8749-d0bdc4d46d93 | textbox | FH Initials - Site Engineer:
| signoff | HOLD POINT
| checkpoint | 3 - Design
ded785e6-f901-5e3b-bf55-5c815d321ca0 | note | H
1e5309aa-73c2-5ded-904c-8ccf23657d74 | note | Detail: Design is approved and Drawings are of the latest revision.
a3b1e17d-360e-5f68-ab5b-a48f08334b8c | note | Frequency: Prior to commencement.
ee3e26f7-2847-55fd-8cff-91904cce0f3a | note | Inspection / Test Method: Document Review
31bb8f07-b542-58c2-895d-db959f758cd9 | note | Conformance Criteria: Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
bae788a2-3cb5-549f-8439-51576b235bcc | note | Records: Drawing Register.
ac21f9f3-2088-586f-b534-62ead8893116 | textbox | FH Initials - Site Engineer:
2d8f346e-b80d-5c5d-806b-f7ffbf330b4b | textbox | Design Engineer Initials:
| signoff | HOLD POINT
| checkpoint | 4 - Survey Setout
9b0a5f26-480d-5447-92ac-fc59af5a12a1 | note | H
df6374d1-3ca0-5d7b-8554-8508e0528890 | note | Detail: Setout Pipe Alignment and Service Locations with inlet & outlet points and inverts as required to construct to design
a22bb920-5a20-5120-992e-414a10df2184 | note | Frequency: Prior to commencement.
85ce5f45-de35-5d6f-bcb4-978f4bf4bc78 | note | Inspection / Test Method: Survey
fa8d1e34-dcf5-5b1a-9488-6c106b7cd247 | note | Conformance Criteria: As per GHD Drawings & Setout files
b96af3a9-9ada-5f83-b183-7082558d0531 | note | Records: Survey Receipt.
9aac3cd7-de91-5894-83e6-e1db3ea9a853 | textbox | FH Initials - Site Engineer:
| signoff | HOLD POINT
| checkpoint | 5 - Pipe and Manhole Material Compliance
2d8362b2-4dda-5b68-ac07-5ea1022e7fb1 | note | H
b67d4bf6-c5e4-59f2-b588-07e3e333e066 | note | Detail: Cesspit, Manhole and Pipe shall comply with relevant AT/TDM standards
15faa754-9ac8-50cb-9f15-3ffe2abb8155 | note | Frequency: Prior to commencement.
b46630c6-9a87-50a6-aa27-43eb090b5fb7 | note | Inspection / Test Method: Document Review, Visual Inspection
34088e69-117d-5a04-a2a5-1ccf9acb3987 | note | Conformance Criteria: Pipe shall be
484942a4-9b9f-5d1c-a0f8-46a43de46837 | note | Check for freshly formed pipes and return if required 1) DN225 Class 4 RCRRJ pipes AS/NZS 4058 2). All Concrete RCRRJ pipes to be fitted with Rubber rings 3). Pipes shall have product certification (ISO Type 5) to AS/NZS 4058 Prefabricated concrete Manhole shall be in accordance with TDM Standards & AC COP
365b710d-d314-5861-8f18-ee6afb4fb1e2 | note | Records: Manufacturers Data Sheets, Delivery Dockets
1b994bca-41d8-5056-b94a-9c5aec899ee8 | textbox | FH Initials - Site Engineer:
| signoff | HOLD POINT
| checkpoint | 6 - Locate Existing Services by Hand Digging / Hydro Vac
f44ee40e-2d71-5841-8382-dff171350909 | note | H
83cc5819-c3f5-5fa4-9b73-18bfa3e0746b | note | Detail: Ensure all services conflicting with the line of trench have been exposed by hand digging.
a59ac2fe-0bf0-5ab8-b2b9-9b12aad2f7eb | note | Frequency: Prior to commencement.
4204c881-b9ac-5bf6-8c5c-9fa0d265c093 | note | Inspection / Test Method: Potholing / Survey
867b9177-fb8d-5a31-aa5b-e40c73992123 | note | Conformance Criteria: All conflicts have been located. New services and / or conflicts to be advised to Project Manager.
256a835d-f3b1-5b01-8192-3a20ddc4d4fc | note | Records: As-built Drawings. Doc. Review
7616d9b1-2646-5180-9ab2-f69b3d25401b | textbox | FH Initials - Site Engineer:
| signoff | HOLD POINT
| checkpoint | 7 - Trenching & Excavation
c5016120-35e3-5e5e-b8d5-a5c887260488 | note | H
9d123b79-4ebb-5493-92ed-3f91b5995206 | note | Detail: Excavation methodology
8924745b-6cf3-5bc5-a7e5-26f1363a0cae | note | Frequency: Daily
e842cb53-3070-5554-a8cb-5ee4d5bdd907 | note | Inspection / Test Method: Prestart review
f1b1ac81-dbcb-57c1-bee7-1383b8204077 | note | Conformance Criteria: The excavation, benching and shoring requirements shall be in accordance with Worksafe Excavation safety guidelines (2016)
c463a754-9d02-5206-ad20-49c051514451 | note | Records: Prestart RCP
6db03f94-c94f-55da-a726-1703b67268a7 | textbox | FH Initials - Site Engineer:
| signoff | HOLD POINT
| checkpoint | 7.1 - Trenching & Excavation
8daa23bf-5d66-5d52-82b1-3d889b296e72 | note | H
fa497f14-8a7b-5fba-82d8-80667fc1f7f6 | note | Detail: Trench Profile - Width
7f0789f7-f2db-503e-824c-417906bc114e | note | Frequency: Daily / as trenching takes place. Different depth methodology
0ac317fd-4373-54fa-9e82-55039c601cde | note | Inspection / Test Method: Visual Inspection, Excavation methodology
67a1462d-0760-5a7e-9119-972ca4812a60 | note | Conformance Criteria: Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing
02c86a70-f5a5-5eac-9937-d287b9c7b7dd | note | Records: Construction Photos
17f60569-a1ac-5e81-884a-3e70865f5dfa | textbox | FH Initials - Site Engineer:
| signoff | HOLD POINT
| checkpoint | 7.2 - Trenching & Excavation
bbe58c03-9c6e-5442-803e-e79fdcc39f0a | note | H
0a11977d-20a1-58a7-a9b4-c7e7c020106a | note | Detail: Trench Profile - Depth
943699d8-e7e5-5b3f-b3da-49f4e0194eb8 | note | Frequency: Daily / as trenching takes place.
b60c0841-48c7-5e0c-a9a6-acc3c3250e49 | note | Inspection / Test Method: Visual Inspection, Measurement
c6772970-5a49-5d24-aefd-dbe37340df1b | note | Conformance Criteria: Trench depth varies according to long section and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings
b1a192a6-5bb6-5e8b-b43f-ecd3c3408919 | note | Records: FH Drainage Line Record / Construction Photos
fdd1c438-35aa-5c4c-81a2-449e48d4b1c8 | textbox | FH Initials - Site Engineer:
| signoff | HOLD POINT
| checkpoint | 8 - Bedding for Concrete Pipe Laying & Manhole & Cesspit
a22af2cd-a2e9-543a-80b1-03e2ac3c507e | note | H
353f8791-76c8-55c7-b644-ed7d2d3f6df8 | note | Detail: Placing and compaction of Bedding Material.
6e2f4b7c-6ee6-5805-b384-f6fc616986e6 | note | Frequency: Inspected continuously during placing and compaction of Bedding Material.
180f5009-96a1-5c41-8f19-7b164220681f | note | Inspection / Test Method: Visual Inspection
cff6e18b-b58a-508e-a3fe-c07b9727eb98 | note | Conformance Criteria: Bedding & Pipe surround material to be GAP7 or GAP 20 (Stevenson Quarry) or alternate material that complies with AS/NZS 3725
e864d4da-99c1-5bed-bb77-5c2609721c2a | note | Records: FH Drainage Line Record / Construction Photos
d5913f1f-d80a-5200-9608-558fb31bc63f | textbox | FH Initials - Site Engineer:
| checkpoint | 9 - Pipe Position Tolerance
89318e59-41a7-5f4e-83c4-10ed1eb1aefe | note | H
d15950e4-c671-5adb-b308-0bc844c37a33 | note | Detail:
be340e94-946e-57b6-869c-20aac1ebef77 | note | Frequency: At any point of pipe
92ef161e-7a75-59a8-8aae-6ebfc066fa21 | note | Inspection / Test Method:
870b6c26-c968-5a8d-87a6-7da7f45880ab | note | Conformance Criteria: Position tolerance for pipe laying at any point along the length of the installation shall be within ±30 mm from the specified design.
b84746b8-557e-5ae3-93ed-9e83d37f1d5d | note | Records: FH Drainage Line Record, Survey Data.
585b18f9-c71b-5d91-b6b1-f488c19a0a8d | textbox | FH Initials - Site Engineer:
| checkpoint | 10 - Trench Backfill - Placing & Compacting
76fd93c5-53f4-5518-9cfa-c780bf246ac6 | note | H
55d5fcde-3cd5-5e66-b62d-aa2147e1a137 | note | Detail: Placing and compacting of Trench Backfill Material
658980b5-7acf-57f4-b7da-6d40f1feab4d | note | Frequency: Throughout Trench Backfilling operation.
1dcf8d66-25bf-5cc0-b63b-8775253391ad | note | Inspection / Test Method: Visual Inspection
7fa2ef7e-f73a-50fd-b9e5-1efd6eac22de | note | Conformance Criteria: Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm
5f964fb1-53bd-5912-b8a4-47ba07ec339c | note | Records: Construction Photos
dabc42bc-b195-5c16-936e-accba4cf2aed | textbox | FH Initials - Site Engineer:
| signoff | HOLD POINT
| section | Subsoil Construction
| checkpoint | 11 - As-Built Drawings
85ba14c0-393b-513f-9774-4aaaa6e4f138 | note | H
0477eda2-2e6d-5a12-b4cd-b94862dcbf54 | note | Detail: Red pen marked-up As-Builts of every 'Issued for Construction' AT drawings
9393a182-6b79-5c0f-b5a6-4466c058b531 | note | Frequency: Final As-Built Drawings to be completed within three months of the construction completion of the asset or infrastructure.
b661066f-02fd-565a-bb9a-5a957a1de29e | note | Inspection / Test Method: Drawings / Visual Inspection
0d2cb6ad-5646-51e9-bcba-1ccf499f53b9 | note | Conformance Criteria: As Built and GIS Data
c05690f3-491d-57c7-8bee-1e2021cf8815 | note | Records: Redline As-Built Drawings, scanned as .pdf files.
702c9bf4-3cab-5195-a819-b3f3e8e5ea2e | textbox | FH Initials - Site Engineer:
| signoff | HOLD POINT
| checklist | Devonport Town Centre - ITP - Construction Works - Signage & E-Signage | itp | ITP - Construction Works - Signage & E-Signage | 5a6fefba-2564-4291-96ff-0741d37d7271
| section | Signage Construction
| checkpoint | 1 - Survey Setout
2c5e5675-0677-5b23-95c3-536cbfa87887 | note | VERIFICATION ACTIVITY: Records
9a90c032-65c0-5599-a443-e731def9c4bc | note | METHODS OR REFERENCE: Signage set out, check for clearance and sight distances
92fd3282-005f-50c0-8d37-8d5afad1a262 | note | FREQUENCY: Prior to commencement.
c7815f09-33c1-528b-a7bd-e1745d0eb48f | note | ACCEPTANCE CRITERIA: Survey
50398926-eb7b-5513-a165-ecb5cf0fae67 | note | HOLD POINT: HOLD POINT
61b9e953-190a-5283-b67b-d3d98b1becc3 | note | RECORDS: Survey Receipt.
84ecdb49-5b61-5662-b751-12d2da690bb4 | note | ONSITE RESPONSIBILITY: Site Engineer
| signoff | HOLD POINT
| checkpoint | 1 - Signage Foundation
6feed15f-7c45-579e-b12b-719e119948c9 | note | VERIFICATION ACTIVITY: In Situ
1e389dba-2851-5cf7-b826-b32d32fe9a1b | note | METHODS OR REFERENCE: MOTSAM Technical Standards
9a40e3c2-2ba4-527e-9cf0-2d3573cfa778 | note | FREQUENCY: Each sign
352a350c-a305-5b5c-bdad-db9f8766599d | note | ACCEPTANCE CRITERIA: Boxed Foundation of dimension 300x300mm. Depth 600mm.
e0fe586d-82d8-5256-8d0a-da31eea1ba50 | note | HOLD POINT: Inprocess Inspection
4c71d517-cc59-5bbd-83d5-7d64308d4970 | note | RECORDS: Photos. Concrete Bag Spec.
a3325259-cba6-5b9d-865d-463aec01d0db | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 2 - Signage Foundation
7ce891a7-3e52-5df3-b9f4-056920c7df49 | note | VERIFICATION ACTIVITY: In Situ
47c6457d-d4eb-5ab0-bc89-75fa103c1d44 | note | METHODS OR REFERENCE: MOTSAM Technical Standards
e0cd6da8-118f-519c-bb96-7da51a5228f4 | note | FREQUENCY: Each sign
a7b9b098-7489-5e62-8771-10bf45f3d14e | note | ACCEPTANCE CRITERIA: Put up sign on 60mm or 76mm steel galv pole. Angle sign towards traffic at 15 degrees.
8f93ef2d-bd15-50df-816d-9b2df0132f69 | note | HOLD POINT: Inprocess Inspection
b09ff682-0634-587c-839b-e06c20b7ec15 | note | RECORDS: Photos.
4db96212-9937-5ad1-a337-bcd4377c479d | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Asbuilts
| checkpoint | 3 - As built information
85104bdf-7ec9-50ee-9a9c-48feb54461cc | note | VERIFICATION ACTIVITY: Drawings
102fb066-cfed-57e6-a3a7-153c0b11f164 | note | FREQUENCY: Every Site
bed756ef-dfcb-5f3f-b89b-dc4a92a98b92 | note | ACCEPTANCE CRITERIA: As built drawings
04c9ed3f-6574-5670-8f4a-0377d109a6e8 | note | HOLD POINT: In Process Inspection
0562308a-57cf-5a78-9fa3-a5a300098bc7 | note | RECORDS: Asbuilt records
2821a38c-39e0-5d63-b93a-ce7d0c94112b | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| checkpoint | 4 - RAMM DATA
0064eea8-beac-5e97-9fd0-ba31f380f2f5 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
7154b9ac-2bbd-59ac-9c48-8587b33e954f | note | FREQUENCY: Every Site
f39b73a9-67b3-577a-82ea-68786a150a0a | note | ACCEPTANCE CRITERIA: RAMM SHEET
4160fe40-c987-5207-8fd2-b34186160882 | note | HOLD POINT: In Process Inspection
25e38357-53fe-56be-8d4e-15568570709f | note | RECORDS: Asbuilt records
e46a4f44-6e99-5044-9611-c191547d5503 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| section | ITP APPROVAL
| checkpoint | ITP Approval
d6b577a3-c11f-5584-b7ac-8d2cced90f4e | note | Prepared by: Genald Sebastian
05be3b39-2487-5bb6-8e36-20087bf2c547 | note | Approving Delegate: Ben Lin
31265e75-35df-5c88-b073-04cebb4afec4 | textbox | Engineer's Rep
| checklist | Devonport Town Centre - ITP - Ducting | itp | ITP - Ducting | 3bf8e3dd-9c70-49a3-8433-d90d56430dc1
| section | Pre-Construction
| checkpoint | 1 - Permits
024ebf81-f9ff-5c51-908b-56a962725377 | note | ACTION (Hold, Monitor, Witness): H
3f4084d4-2c0f-53ed-8b22-c451a963b109 | note | DETAIL: Obtain Permits
a92f07eb-5007-556d-b4e7-9527f9a135f6 | note | FREQUENCY: As required
0312175b-bdf1-50ae-9c21-c84d9fc89ba2 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
78875378-c85c-5a93-b181-6159fa84515a | note | CONFORMANCE CRITERIA: Authorisation to work, dig permit and first gas permit obtained
82cf3b55-e2f5-5fcf-887e-2180211e5bd5 | note | RECORDS: This ITP signed
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Design
fbcdaee9-63c3-5bc1-80fb-618b24a3c272 | note | ACTION (Hold, Monitor, Witness): H
f07f43ee-8a62-52c2-a803-e98d855446f7 | note | DETAIL: Ensure that Design is approved and Drawings are of the latest revision
c7c8c1ce-e33e-567e-9a5a-6e49bc8da483 | note | FREQUENCY: Prior to commencement
c0d243ab-e503-5dd4-96ad-a2dc45c11b82 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
0141667f-9318-5f16-baa5-78709531f77b | note | CONFORMANCE CRITERIA:
625978fb-1d68-5fc8-8c77-0b432586dd19 | note | RECORDS: Check Drawing Register
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Survey Setout (1)
a1fb75c8-1b91-5d6c-9d19-5af359b3eed3 | note | ACTION (Hold, Monitor, Witness): H
b7ba13e2-a318-5a28-86ab-6fada84c1a7d | note | DETAIL: Setout ducting alignment and EOS FL depths. Setout and mark all known services along the cable corridor.
ec75e170-63ee-5652-8b7d-e19d496974ed | note | FREQUENCY: Prior to commencement
24354d31-63f5-5ae9-8088-1514f0bdb3a6 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Survey
4d25e83d-558d-5b8f-bc2a-89edcb194a97 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
9e48ddea-0c03-5265-ad7f-510f5c77a1a8 | note | RECORDS: Survey Records
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Survey Setout (2)
154416eb-0bda-503b-8e5f-5b1415c94e5a | note | ACTION (Hold, Monitor, Witness): H
6e85e255-5877-5e61-9ecc-e32fdbdae46d | note | DETAIL: Confirm with Engineer on site the exact location of all posts, foundations, signs, cable chambers, cable ducts, loops and loop termination boxes( Toby boxes) before installation.
042d07eb-7bc6-5b59-89c6-cb54764eeba0 | note | FREQUENCY: Prior to commencement
0ef014ec-3d5b-5fca-b6b8-1c36c9a7c85c | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
1695717c-2e82-5a1c-bf3e-3bf7037ba710 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
25de8551-7783-5769-bdff-626bef15d26f | note | RECORDS: Photos / Engineers approval documentation
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Locate existing services by hand digging/ hydrovac
84c8b253-f56e-5a94-94b9-3e550edf9e03 | note | ACTION (Hold, Monitor, Witness): W
5bbfbacf-06b4-5c3f-b752-057f251f0bf7 | note | DETAIL: Ensure all services conflicting with the line of trench has been exposed by hand digging or hydro excavation
7ff41a16-3bd7-5c6d-aec1-1a9e392ce1b6 | note | FREQUENCY: Prior to Installation
c7dbd3ef-848b-5d75-893a-5e6c2f741d84 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Potholing
3973265f-26fe-5d31-ac16-f401699748ec | note | CONFORMANCE CRITERIA: All conflicts have been located and survey as built recorded
3a3c01a0-8523-5c2f-b13b-14210a996c6c | note | RECORDS: Digging/Excavating Control Checklist
| checkpoint | 5 - Material Compliance (1)
3ce692b4-866d-598f-9007-0e3bac96cbe8 | note | ACTION (Hold, Monitor, Witness): H
7a331bba-6f3b-5399-8d88-455941cbcb42 | note | DETAIL: Ensure duct pipes and poles are as per drawings and specification
f1f56634-3956-54d0-9261-37466af5e66b | note | FREQUENCY: Upon delivery to site
72e9881f-0fe6-51d4-970b-162bfae5e875 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Ensure delivery docket matches materials
fb9d971e-06ca-5d8e-9aca-f3d018f21b23 | note | CONFORMANCE CRITERIA:
2a532b4c-fa82-5a72-a7f6-65a7fd6a04f5 | note | RECORDS: Delivery Docket
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Material Compliance (2)
f1e7504c-7a32-5bdb-bfea-89dd813c8bfc | note | ACTION (Hold, Monitor, Witness): H
5d6e2c7e-a81a-5193-a140-77ed65bc763d | note | DETAIL: Ensure all concrete used is 20MPa mix
f64c6e7e-a846-58a1-b3f0-8d7420bd2da1 | note | FREQUENCY: Upon delivery to site
1a9e7ca1-5665-51b7-b1f3-21fa0f6c723b | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Ensure delivery docket matches materials
3578d3d9-f29b-5db2-bb67-41fc55b1148e | note | CONFORMANCE CRITERIA:
878c3552-7a8e-5150-a9e7-ccc09b3867fc | note | RECORDS: Delivery Docket
| signoff | AUTHORITY HOLDPOINT
| section | Ducting
| checkpoint | 6 - Trenching
3001d05a-9103-5262-84b1-4f3e6ebda4fd | note | ACTION (Hold, Monitor, Witness): H
655ea225-1b6f-5abc-bf27-395c72c0a21d | note | DETAIL: Inspect trench profile to ensure walls vertical, widths is 300mm max (single ducts). Ensure trench depth is sufficient to provide 600mm cover to duct when under berm (900mm cover when under road crossing)
7b5a7c34-0b28-5354-9bdd-b5ab72d76e4f | note | FREQUENCY: 10m Intervals
ad34168d-3ad8-59b5-a0e9-267044911c43 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
12a099aa-3cb0-53c1-a59f-aaac7e22f60d | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
22fbc0b1-8409-5a3f-9790-24e672fddfb7 | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.1 - Trenching
6d690777-acfe-5ae6-9554-369698c8a583 | note | ACTION (Hold, Monitor, Witness): H
20e6fa63-0866-5ddd-9ddf-7ad0dfae4176 | note | DETAIL: Ensure trench is cut in a manner that will ensure ducts are layed at correct depths,grades and alignment as per design dwgs
c531a2d6-9f64-594c-9f61-e5e871e3db30 | note | FREQUENCY: 10m Intervals
6aa5143c-5cad-5819-b529-e90e48d29412 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measure
46c66a61-d04c-59da-b9e9-195d489ab6dc | note | CONFORMANCE CRITERIA: Ensure trench alignment and levels match the design drawings
af68ce36-bd75-5393-9a9b-c9460bbaf07d | note | RECORDS: Stringline records & Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Duct Installation
4de68332-bd59-55b3-ba98-e349dc56daac | note | ACTION (Hold, Monitor, Witness): W
111981f9-822d-58af-9d4c-66b2b1186665 | note | DETAIL: Place proposed ducts in locations where required. Draw wire tapes required and cap ducts where required to prevent ingress of material into duct.
28a6deaf-9175-5d93-8039-d7eddeff5b96 | note | FREQUENCY: Prior to Installation
b8102828-b7e2-596d-9f8b-13646340799d | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
3112b171-69d9-5b3d-a580-e5d22b6c0866 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
e04b507a-1594-5e7f-aec4-8e919339573b | note | RECORDS: Photos
| checkpoint | 7.1 - Duct Installation
1c91ec72-0460-5e1e-bec4-bed6d4680033 | note | ACTION (Hold, Monitor, Witness): H
3e298012-6d3e-555f-b08b-0ffd373c39bd | note | DETAIL: Ensure minimum spacing of ducts requirements are met as per design dwgs and ATCop min spacing tables
ac031bed-80b2-5378-b45a-ff13d1eac48b | note | FREQUENCY: 10m Intervals
36f67329-8d00-50ee-8923-bdbc7f734531 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
3e85c792-f7ec-5534-8e7c-94dc37eaae6f | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
05f3e0d2-6912-5319-bbef-2f30639feebd | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.2 - Duct Installation
35f774f8-68c8-592d-b532-a08cf10a882a | note | ACTION (Hold, Monitor, Witness): H
46705007-0572-5a93-ba5d-0859d521164c | note | DETAIL: Asbuilt Survey
5abf2297-4f26-5bdf-bdad-1f8eaafa886d | note | FREQUENCY: 10m Intervals
5c78dfbe-00f1-5732-9151-722e20df6342 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
e185a955-db65-5888-9d1d-a13763f330d4 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
6f1c23aa-e134-5dd6-9646-ef563db6c4c2 | note | RECORDS: Survey Records
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8 - Bedding
9999b2c1-c5e0-587a-903a-9d58d14dc6ee | note | ACTION (Hold, Monitor, Witness): H
3ebff242-8797-584e-9eb3-9fbe552aae34 | note | DETAIL: Lay min. 150mm gap20 or finer for bedding and haunching
f748a4c6-65a4-51fa-b4d7-c199cf102e53 | note | FREQUENCY: 10m Intervals
1d683331-e919-50dc-b84c-25191c0dabc1 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
6de8d567-dd56-5078-8f48-c7861a8f3482 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
54df4539-3f4f-5022-bbe3-52319c5fc1ba | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Warning Tape
a16064fd-2e6d-5fbf-b6f6-3b6410f964e6 | note | ACTION (Hold, Monitor, Witness): H
0ade823d-cf99-5c46-806f-e512c8ce6868 | note | DETAIL: Ensure warning tape gets installed 300mm above duct pipe for all new ducting lines.
69351312-d463-5507-bc84-56ba44e3a685 | note | FREQUENCY: 10m Intervals
c915e1a0-4aaf-549a-8269-24390e4f3d53 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
37305b19-0158-5330-8ca4-a514b581e6a5 | note | CONFORMANCE CRITERIA: Consistency with Drawings and Specifiactions
94e6e2bf-f21e-56c1-bb05-dd1fdd11b09e | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| section | Asbuilts
| checkpoint | 8 - As built information
7589235f-7297-5147-9eb4-38d36226306e | note | DETAIL: Drawings
46a5a06a-5a34-5d47-b275-b3a21a0fc052 | note | FREQUENCY: Every Site
65bb1c63-8501-5533-a358-08ce8ba9b307 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): As built drawings
9ff74f6e-67b8-5ce8-b900-ac3822fd2527 | note | CONFORMANCE CRITERIA: In Process Inspection
e8767571-0b05-5539-9645-5a221295eb64 | note | RECORDS: Asbuilt records
| checkpoint | 9 - RAMM DATA
393896de-5ce1-5b8c-a731-af56c3c7c99e | note | DETAIL: RAMM DATA SHEET
a7080348-c23f-552b-98c2-b987566f4cf1 | note | FREQUENCY: Every Site
e4e27d71-0de6-5009-a428-8c6edb6258bd | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): RAMM SHEET
88f00766-5ad0-5bbb-89c5-6c449e8aed64 | note | CONFORMANCE CRITERIA: In Process Inspection
719c9451-c150-589c-a895-46017f49ac2c | note | RECORDS: Asbuilt records
| section | ITP APPROVAL
| checkpoint | ITP Approval
3a5d6827-0a1a-5c1f-99c8-8c840a330b16 | note | Prepared by: Genald Sebastian
15993cce-e77e-55ff-8145-53faa4a87846 | note | Approving Delegate: Ben Lin
ba80a4c8-81c8-57ea-961e-3a8397db4752 | textbox | Engineer's Rep
| checklist | Devonport Town Centre - ITP - Enabling Works - Footpath, Kerb and channel | itp | ITP - Enabling Works - Footpath, Kerb and channel | 68cfd15d-68a6-4fcd-860a-2117ea028769
| section | Pre-construction
| checkpoint | 1 - Permits & Services (1)
cf5d410e-cf77-5f3b-aee3-1ff9c5a907fe | note | VERIFICATION ACTIVITY: Records
4981bb01-2a2e-532e-91a3-faaf3e77e891 | note | METHODS OR REFERENCE: Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
1eed0d2e-546f-5fb6-a9f7-f3f513913211 | note | FREQUENCY: Prior to any construction commencing
ee8e1349-01b5-5049-8ad0-cefe2cfc5182 | note | ACCEPTANCE CRITERIA: Document Review
858d0351-3b79-5c9a-acdd-5e0a656ca5b1 | note | HOLD POINT: Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority.
a3702f44-4c88-5b87-94c3-ab6269aae158 | note | RECORDS: Permit attached or permit number noted.
| checkpoint | 1 - Permits & Services (2)
ddb303e7-f169-5afa-bf1e-ddb4ea6cb7c2 | note | VERIFICATION ACTIVITY: Site Record
d52c60f9-a048-5770-a102-15546fa81513 | note | METHODS OR REFERENCE: Locate and mark out all existing services
8040fc75-08f3-51bd-9b48-e84d56c719c0 | note | FREQUENCY: Prior to any construction commencing
bc294bf9-6aca-55de-be5e-4ccbbb63259b | note | ACCEPTANCE CRITERIA: GPR & Document
1bbe5994-9112-53a4-bb32-de7b7ba5a550 | note | HOLD POINT: B4u dig procedure - follow utility protocols
e51cbf75-c0dc-503e-be08-06adaee544c6 | note | RECORDS: B4u dig plans & GPR report attached
| checkpoint | 2 - Pre-Construction Sign Offs
720830b2-aec7-5420-b6e7-9cb77497fd66 | note | VERIFICATION ACTIVITY: Records
c1a25793-8c81-513f-a4cb-ab547dbf0f35 | note | METHODS OR REFERENCE: Sub-Contract and Supplier Agreements
74fb38ae-091d-5049-ba0b-9a25d25d56e2 | note | FREQUENCY: Prior to commencement.
36a87cd3-eb74-53b3-9daa-c97f8f991dab | note | ACCEPTANCE CRITERIA: Document Review
fc616308-a15d-579a-9d29-74718838cebf | note | HOLD POINT: Sub-Contract and Supplier Agreements to be agreed and signed
c83b2071-b438-5681-a5a0-960b0268db39 | note | RECORDS: Subcontract and Supplier Agreements
| checkpoint | 3 - Design
060d15ba-6133-50e9-bd6b-08bb0aa6de23 | note | VERIFICATION ACTIVITY: Construction drawing
0218c0d0-1ef7-5bbe-b9e7-1da9c5acb8f9 | note | METHODS OR REFERENCE: Design is approved and Drawings are of the latest revision.
e79c46e3-c9a8-50ae-9aaa-39c83e9a41b8 | note | FREQUENCY: Prior to commencement.
945ec092-5c51-5a9a-b2b8-8545893e0459 | note | ACCEPTANCE CRITERIA: Document Review
5ac524b1-44ba-5f9e-996a-0495953c48e2 | note | HOLD POINT: Ensure that Design is approved and Drawings are of the latest revision.
33691188-ac85-5e22-a25b-ac0c9d55fa0d | note | ○ Drawings to be 'ISSUED FOR CONSTRUCTION' status.
52d5e9ea-39ad-5012-a5d5-55f7069124be | note | ○ HOLD POINT of not issued to IFC.
6dfa8468-185d-55bb-9b77-68c42c0e303f | note | RECORDS: Drawing Register.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Survey Setout
2da6dcd8-f9f8-5d58-bc24-e0c71dac5fcd | note | VERIFICATION ACTIVITY: Records
29819bbb-06fb-5636-a0d4-ded8871b0d48 | note | METHODS OR REFERENCE: Kerb & Channel set out, catchpit, bottom of ramp, table top, streetlight, HFS extent, footpath extent, street furniture
d7562db9-95e2-5bb7-867a-40be4abdd72a | note | ○ Verify existing levels vs. design
6bdbb4ef-301a-5c73-91fa-18a5723c40dd | note | ○ Verify grades
2800f540-5e06-5112-9ae2-40b89feefa7b | note | FREQUENCY: Prior to commencement.
2ea77b75-bc85-5444-9a4f-ba6a2575f03c | note | ACCEPTANCE CRITERIA: Survey
95f61f9c-61d1-5d3d-a15a-76443dcf28d5 | note | HOLD POINT: As per the Drawings: T18092 - R1-001 & Setout files, HOLD POINT
566ea61a-0973-5522-9fdb-f697873c02a5 | note | RECORDS: Survey Receipt.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Locate Existing Services by Hand Digging / Hydro Vac
4b729ef9-e3b9-5ca9-8980-44e426f871a2 | note | VERIFICATION ACTIVITY: Site Record
8297e71c-2ce4-52e1-9f67-c3a3bb2a376f | note | METHODS OR REFERENCE: Ensure all services conflicting with the line of trench have been exposed by hand digging.
2cf3168f-993f-5a64-b1c4-128b3ac20ee0 | note | FREQUENCY: Prior to commencement.
55ec42cd-5e64-59de-9928-500ea8215c40 | note | ACCEPTANCE CRITERIA: Potholing / Survey
c08add3a-ff5a-5786-9438-80446f771cb9 | note | HOLD POINT: All conflicts have been located. New services and / or conflicts to be advised to Project Manager.
8c83c1ee-f318-526f-8146-8f1066794219 | note | RECORDS: GPR report, Photos
| section | Kerb & Channel
| checkpoint | 2 - Channel Level
76bfeaba-7f20-5b1b-a245-412701e9d411 | note | VERIFICATION ACTIVITY: QA FORM
cbc5e7e5-86b0-594e-a9e2-7d0065b6304e | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
ee1d2ac6-e4ae-55e6-b828-35b998103137 | note | FREQUENCY: Everysite
6b252c79-879e-5eda-bfde-e9f01dd0b32e | note | ACCEPTANCE CRITERIA: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level >1% fall
f4e0999a-6a66-524b-9ba2-c2d208203e48 | note | HOLD POINT: Inprocess Inspection
a3f44360-7a13-5423-91d9-bdcb38a08b5c | note | RECORDS: FH concrete QA sheet
| section | Footpath & Berm Construction
| checkpoint | 3 - Concrete Footpaths
98fb7868-c1d2-5420-a18c-7cabf5040395 | note | VERIFICATION ACTIVITY: QA FORM
9962cb0d-6b44-5eeb-b1c8-36f25d710419 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
2b70777a-accc-5009-be18-b58c99e38a69 | note | FREQUENCY: 10m Intervals
9addfe7a-8f38-5c4c-b433-351c20dd19b8 | note | ACCEPTANCE CRITERIA: Basecourse - 100mm min. thickness
8b8d5720-1b93-560b-b871-73642e6b5c7c | note | ○ Clegg CIV > 12
9008eec4-2dc1-5688-b1a1-36ccaf6e5f4c | note | ○ Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish
5187eaa5-3cef-580b-9716-3828b204e754 | note | HOLD POINT: Inprocess Inspection, HOLD POINT, Prepour inspection
745fc064-906f-5393-bae2-ae0b682ff40c | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets, Scala
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - AC Footpaths
676dd280-3cff-513d-9f5a-69b3c6f54b24 | note | VERIFICATION ACTIVITY: QA FORM
c4ba6445-d953-5bbb-b4a5-29d742ad74cb | note | METHODS OR REFERENCE: TDM Technical Standards - FP0003
b6aa108b-06b8-5b43-92b5-10ec82d7b7f8 | note | FREQUENCY: 10m Intervals
37b3384a-04ba-52d3-9ea8-31b5b38bc269 | note | ACCEPTANCE CRITERIA: Subgrade -(CBR > 3)
9c57f4a2-0926-5d10-8f6e-0a17226980b8 | note | ○ Basecourse - 150mm min. thickness GAP40
44908764-e52c-521b-9788-ea23b74bcb35 | note | ○ Clegg CIV > 13
f6bbc4aa-27b0-552a-920a-0773bcd3158b | note | ○ DG10/Fine asphalt mix used 25mm
e6430eeb-8d06-5815-8872-32fdbd7f4769 | note | HOLD POINT: Inprocess Inspection, HOLD POINT
2debeb85-afc7-5579-a285-96cfad67dbff | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Paver type FP
55f911d8-d267-5155-8ef2-ddd3c289b6cc | note | VERIFICATION ACTIVITY: QA FORM
bcb706ab-c7c8-57d6-9225-6e7efb57560f | note | METHODS OR REFERENCE: TDM Technical Standards - FP0004
74534dc1-871d-5c75-9a50-ea4aa53ee6f7 | note | FREQUENCY: 10m Intervals
7171a054-781a-5fb1-977c-f20b6a544294 | note | ACCEPTANCE CRITERIA: 80mm concrete Pavers,30mm compacted bedding sand,150mm Gap 40 compacted
a1b308a0-920e-57b9-84f7-20ccd552de10 | note | HOLD POINT: Inprocess Inspection
d34e7dbb-e6d6-547f-9431-4456234676c3 | note | RECORDS: Photos
| checkpoint | 6 - Concrete Vehicle Crossings (VX)
bd6062cf-1eaa-51d5-883c-7313c489e6cf | note | VERIFICATION ACTIVITY: QA FORM
3b11ef47-48c4-5d3a-89e6-f10b538b49dc | note | METHODS OR REFERENCE: TDM Technical Standards - VX0103
be8e3632-e1f8-591e-89b0-3d7315be394d | note | FREQUENCY: Each VX
4f866631-02b8-5d06-a08a-20859c387445 | note | ACCEPTANCE CRITERIA: Basecourse - 100mm min. thickness
7aa4468a-0fe4-554c-b976-461117f57651 | note | ○ Clegg CIV > 36
8c22f724-61dd-549f-8040-e5f01606246f | note | ○ Surfacing - Concrete 150mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish
195a7a3a-c85e-5bae-9dd4-be13f4570257 | note | ○ 665 mesh placed centrally
e4ea7e90-39b7-5296-bc70-87aede1c5175 | note | HOLD POINT: Inprocess Inspection, HOLD POINT, Prepour inspection
ff61937f-5872-5cb0-89b0-2da1e5d69abb | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets, Scala
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Pram Crossing
7adc3f80-1a14-5485-bfcd-e32837365773 | note | VERIFICATION ACTIVITY: QA FORM
5255cac0-c18b-58ff-bd9f-2aa79a9df546 | note | METHODS OR REFERENCE: TDM Technical Standards - FP006
f4be7724-96f3-515a-ad93-11808913e2ff | note | FREQUENCY: Each Xing
62fddb71-cf31-502d-b042-0f20e0b31cc2 | note | ACCEPTANCE CRITERIA: Tactiles Directional & Dot - 60mm
40b88835-4ef3-53dc-bff6-fa4eef760164 | note | ○ 1500mm min width; 600mm flares
efa22453-2470-52ca-a39f-b13295556ce0 | note | ○ Slope as per criteria
867c5e0a-304d-51eb-b16f-f1dddd58977b | note | HOLD POINT: Inprocess Inspection, HOLD POINT, Prepour inspection
ad58adaf-eb0a-5c20-b68b-4f2cd1e89f49 | note | RECORDS: Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8 - Grass Berms
f38009c5-ee0f-5348-8b53-153bfe0bf3ea | note | VERIFICATION ACTIVITY: Visual
2cbde76a-157d-5126-afd1-2bc0d731e834 | note | METHODS OR REFERENCE: ATCOP Section 12 Footpaths and Pedestrian Facilities
9e4532ff-0eed-5e95-af0f-023be6699762 | note | FREQUENCY: 10m Intervals
0df6a5ce-cca8-521b-8dc8-51437350f3b3 | note | ACCEPTANCE CRITERIA: 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
86e81386-80a4-5944-a0f5-f6cee38f4679 | note | HOLD POINT: Inprocess Inspection
70e15972-8ddb-5479-b7a4-bada7d285af1 | note | RECORDS: Photos
| checkpoint | 9 - Service Covers and Street Furniture
899bcafe-1e2d-55b2-a06f-6342f349d82e | note | VERIFICATION ACTIVITY: Visual
3c102d64-5ff2-5c04-be29-c7551d23c78a | note | METHODS OR REFERENCE: AT Contract Specification 14000
addb188a-13c7-5f9e-9a94-6dbeaa4abb8b | note | FREQUENCY: Everysite
c814a799-d56a-5062-8d0f-701b7d494c9e | note | ACCEPTANCE CRITERIA: Service covers to be adjusted to new surface levels. Ensure no damage is done to street furniture in the vicinity while carrying out works.
3ebbb10a-7d67-505a-9d50-675e694103e7 | note | HOLD POINT: Inprocess Inspection
67fc26e7-6a33-5651-8aec-b59ebe2de9f3 | note | RECORDS: Nil
| section | Asbuilts
| checkpoint | 10 - As built information
aa684867-e11d-53f8-a36a-1b547358cabe | note | VERIFICATION ACTIVITY: Drawings
35929b43-3c61-5c9c-ace2-26b069f92f2d | note | FREQUENCY: Every Site
d1321ff9-35e6-5dec-b943-044927a2ae36 | note | ACCEPTANCE CRITERIA: As built drawings
585d2677-7fc4-5038-968b-8d1c0c08f14a | note | HOLD POINT: In Process Inspection
b27e8ca2-4492-5133-ac47-ef930688da45 | note | RECORDS: Asbuilt records
| checkpoint | 11 - RAMM DATA
477eb564-1c0e-5258-839f-777b49d40c73 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
7aa20833-d8ee-5a8e-bfca-3d48dcdc4d5c | note | FREQUENCY: Every Site
cba99df7-67d9-50f5-b06e-fd9be7da5cec | note | ACCEPTANCE CRITERIA: RAMM SHEET
964bf29d-eacb-5e86-b160-394e787dba2f | note | HOLD POINT: In Process Inspection
56adba6b-5cca-5a51-a129-b5c46d8bdd7e | note | RECORDS: Asbuilt records
| section | ITP APPROVAL
| checkpoint | ITP Approval
5352600c-b51e-50c6-883f-5b47bd91e73e | note | Prepared by: Genald Sebastian
75aa65da-a510-5168-b9ba-427e596f5d3f | note | Approving Delegate: Ben Lin
686e4fdd-f234-5803-a4ea-f45f406c0230 | textbox | Engineer's Rep
| checklist | Devonport Town Centre - ITP - Raised Table | itp | ITP - Raised Table | c9fdd2d2-612e-4004-9188-cb145b5c1a5c
| section | Details
| checkpoint | 1 - Permits
8c4cfa08-9d6e-57b6-a247-ca07472a237e | note | ACTION (Hold, Monitor, Witness): H
2edf9d00-e679-5ff5-891d-1e5105dd17be | note | DETAIL: Obtain Permits
d400e18e-9050-5bf9-8557-a377f6da5fa4 | note | FREQUENCY: As required
ba64b9c7-13bc-5e5d-ad40-dfa73ae7d29a | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
e79e0672-7e60-5e05-9ada-b9b17729bdfe | note | CONFORMANCE CRITERIA: Control Checklist - Fall Prevention (if applicable). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
cb6f2cc2-35a2-5081-b914-2fd3cd2a73cd | note | RECORDS: Permit attached or permit number noted
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Pre-construction sign offs
c046a59c-110d-5beb-a492-e1fe4ba9e60b | note | ACTION (Hold, Monitor, Witness): H
80adc2da-06f5-5872-9085-460f4ff2809f | note | DETAIL: Ensure that Sub-Contract and Supplier Agreements are signed
e66caf4c-65be-5d49-b522-77b47e9c8396 | note | FREQUENCY: Prior to commencement
f903bbc6-c804-5bde-aa5f-8319d770488e | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
77cd52f6-ed50-5ca3-8a51-def33a564e41 | note | CONFORMANCE CRITERIA: Signed Subcontractor and Supplier Agreements
8b034c35-d2c7-510e-adcc-adaebce7e1b2 | note | RECORDS: Subcontract and Supplier Agreements
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.1 - Pre-construction sign offs
66ce472a-c397-5949-ad92-e5a70071ffad | note | ACTION (Hold, Monitor, Witness): H
5323001e-758d-51d8-bde1-b8bd1ab0e1d0 | note | DETAIL: Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
d863e120-acee-5b74-be3f-e9e223d3e0a8 | note | FREQUENCY: Prior to commencement
bfba3e2a-659b-55a1-8dd1-bd588ae95b20 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
b51992ce-77a8-5a1d-b745-052800ee08e4 | note | CONFORMANCE CRITERIA: TMP is approved by CAR manager for each site and works are only completed within the approved dates..
3abfd7d0-422b-5a50-94f3-4bf3b1e80eeb | note | RECORDS: TMP on MyWorksites/On Site
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Pre-construction sign offs
073b3b42-2234-5fb7-a69f-2874c5693027 | note | ACTION (Hold, Monitor, Witness): H
d87097c6-c9c0-5831-a65c-cf6b696bfcf2 | note | DETAIL: Ensure all Sub-Contractors and Suppliers go through FH induction
b9e8a3c6-edfa-5fcf-a417-530a036cbd23 | note | FREQUENCY: On site daily
5357748e-5a0b-50f5-b860-5b299b544b80 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Induction
eaf537b4-01e4-5a2f-8b67-ddbb75804899 | note | CONFORMANCE CRITERIA: Supplier's and Subcontractor's signatures on hazard ID and pre-start documentation
5d1a7f4f-974c-55e8-a60b-868af9138b3c | note | RECORDS: Hazard ID and Pre-starts to safety team
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Design
9b3757b2-66a6-5d4d-a058-e1e12b023fe0 | note | ACTION (Hold, Monitor, Witness): H
ddfe3291-a058-527d-8b40-d934ff80872a | note | DETAIL: Ensure that Design is approved and Drawings are of the latest revision.
bf32a4a4-8f69-538b-b485-6091e37fd7da | note | ○ Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
fa065559-febc-5acb-b841-ada5e38be51e | note | FREQUENCY: Prior to commencement
6e0eed56-edbe-54dd-aab5-17c2b78cd5fb | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
b4459440-c204-5d61-aa45-7ee08506a3a9 | note | CONFORMANCE CRITERIA: IFC drawings have been received by Contractor
f6696a23-fa07-57ef-b44b-fad8ed850a18 | note | RECORDS: Check Drawing Register
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Installation of Erosion and Sediment Controls
ed963001-5983-5675-9f5a-9ad5761734b1 | note | ACTION (Hold, Monitor, Witness): H
b7cc7612-e487-5ab0-9083-43eebfc8f3cd | note | DETAIL: Ensure that Erosion & Sediment Control in place
926e0766-adb1-52cb-82c1-bdc0d711f42e | note | FREQUENCY: Prior to commencement
e32eb786-a789-5fa5-b63b-a9be5136cf80 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
519a1e52-34f7-5eb7-a2a5-5f1243aa0eb0 | note | CONFORMANCE CRITERIA: Territorial Authority has approved the asbuilts for the ESC controls constructed onsite and gives approval for construction to commence
d21abaeb-d04b-512d-8d2f-2c4914dd641a | note | RECORDS: Environmental Controls Audit
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Survey Setout
263314f7-4bb4-5413-ae7b-f20a0034c8e1 | note | ACTION (Hold, Monitor, Witness): H
f3e84267-7752-5d0a-ac4c-3de19d7bed0c | note | DETAIL: Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations)
6359aee6-8cf9-5c71-9513-89c70259fee5 | note | FREQUENCY: Prior to commencement
d48f5a80-a619-5c62-be1d-e2f0b74fd511 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Survey + Smart Level
57d9c4f9-86a8-571f-8da4-908c38725049 | note | CONFORMANCE CRITERIA: Consistency with Construction Drawing
fde01346-3209-52f4-864d-a6cb7bf3d1b3 | note | RECORDS: Site Photos post surveying
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Locate Existing Services by Hand Digging
fff250ae-4a4b-5bc0-a941-c2e37083ae34 | note | ACTION (Hold, Monitor, Witness): H
c18d6e0a-58a9-5835-977e-839a3a6c6376 | note | DETAIL: Ensure all services conflicting with the line of trench has been exposed by hand digging
cf9650b2-950d-5013-b539-8971f32ff2f4 | note | FREQUENCY: Prior to commencement
8624bad3-3251-5ce0-80e0-445ca269536a | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Potholing
8efe90e9-4712-5c2c-85c7-683e111ffd4f | note | CONFORMANCE CRITERIA: All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. Asbuilt all services
d6ccfe34-3d5d-54e7-beb0-78b45d8af881 | note | RECORDS: Digging and excavation checklist, service planes,As-Built Drawings Doc. Review
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Material Compliance
43eea3af-d326-5d03-95ee-79939e3d46ec | note | ACTION (Hold, Monitor, Witness): H
dc516cf0-856a-5d2e-8164-6d8e8575fa50 | note | DETAIL: LESA dowels to be used at all construction joints
80902db7-e802-53fb-8b21-3b158f31ff2b | note | FREQUENCY: Prior to pouring concrete
62063961-da43-5213-928f-5a43422d3060 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
f7c3f192-3ec9-5019-9f9c-a7a3be87fd9b | note | CONFORMANCE CRITERIA: Photos + Delivery Docket added to QA folder
ede39bc5-2c54-53aa-9040-64ca4c7b0cd5 | note | RECORDS: Delivery Dockets / Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.1 - Material Compliance
bb902610-bbd2-57c7-8633-264238795207 | note | ACTION (Hold, Monitor, Witness): H
dc4ccba4-e578-5ea0-b5ab-632ba4d9a35d | note | DETAIL: 0.25mm polythene layer placed across all surface area at bottom of raised table
9abcef38-f39c-5c53-9d02-8d53f911920c | note | FREQUENCY: Prior to pouring concrete
1287a14b-3fa8-5bfe-8c4c-3042e939e987 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection, Document Review
f940b919-0b7f-5154-b738-93663f097124 | note | CONFORMANCE CRITERIA: Photos + Delivery Docket added to QA folder
2ecbb17d-4c1e-5761-8ee4-7e92cee68255 | note | RECORDS: Delivery Dockets / Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.2 - Material Compliance
2165d686-3be7-51e7-b793-3eb1a5ae05a1 | note | ACTION (Hold, Monitor, Witness): H
b4124161-2895-5c3e-a3ee-1f0b89371004 | note | DETAIL: 30mm thick compacted layer of AP20 aggregate placed underneath polyethene layer.
39190e59-737c-5d40-aaf0-6a167f5ea6aa | note | FREQUENCY: Prior to pouring concrete
bb260f96-ba70-53ea-a2fc-54c2a3f6130a | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
736c0107-d4d5-5dd5-9b8a-91b77bc3fd10 | note | CONFORMANCE CRITERIA: CIV >32
a9b43256-e351-5d7d-a012-3c810a72bb0a | note | RECORDS: Delivery Dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.4 - Material Compliance
d862aec7-0af6-529c-bf73-5dd55bd9d28a | note | ACTION (Hold, Monitor, Witness): H
2d2f8787-3b85-5314-b1b5-80457984289e | note | DETAIL: All concrete delivered to site shall have 50MPa 28 day compressive strength with 4kg/m3 of Black Oxide Powder and 19mm aggregate chip size RadForce Fibre
72437e8e-87ba-5267-b020-e2d22961f0e3 | note | FREQUENCY: Prior to pouring concrete
24446fcc-c871-5bb6-9256-f2988aae06b7 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Concrete Delivery Dockets
946150ba-8872-5f52-a317-90cd0df0abcc | note | CONFORMANCE CRITERIA: Delivery Docket added to QA folder
db873a8d-4cad-5b8a-86d5-8c2938710988 | note | RECORDS: Concrete Delivery Dockets
| signoff | AUTHORITY HOLDPOINT
| section | Raised table Construction
| checkpoint | 8 - Temporary Works (Formwork)
57354a04-eaaa-52db-9187-7d5d5afa8ce3 | note | ACTION (Hold, Monitor, Witness): W
30a0dc28-3da9-5a0e-bded-74f6c456ee00 | note | DETAIL: Formwork to be set to correct line and level
dd0022be-2c28-598a-a01b-758f274168c8 | note | FREQUENCY: Prior to pouring concrete
159de6cc-e417-5440-85a6-8467308e9b09 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
9f5c7308-3da0-58f4-acc2-c8bdd9a6ca94 | note | CONFORMANCE CRITERIA: Concrete Inspection Record
61d2b635-17f8-5b73-a835-46df1610176a | note | RECORDS: Concrete Formwork Checklist
| checkpoint | 8.1 - Temporary Works (Formwork)
87bd0207-def5-58a3-8f28-300f1cb8ded9 | note | ACTION (Hold, Monitor, Witness): H
a24f76e7-2983-56cb-84d2-4c4b220a23ca | note | DETAIL: Raised table formwork to be 75mm above existing road level and be 300mm in depth and gradients respectively of entry and exit ramps
e36ab613-acc2-5638-abc6-b951d0288a27 | note | FREQUENCY: Prior to pouring concrete
a375e82f-7569-54b0-b240-a0d270ab7e9e | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measurement
af07b494-7173-505d-9198-7edefc9c2130 | note | CONFORMANCE CRITERIA: Designer to inspect formation level
694a8d3b-aa1b-5487-883e-424a4b11269f | note | RECORDS: Site photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8.2 - Temporary Works (Formwork)
98a938f0-0833-55d0-945e-9d09b84f8994 | note | ACTION (Hold, Monitor, Witness): H
8ebb4edd-9351-5dd6-9be4-b3d93cd4a3a7 | note | DETAIL: Raised Table ramps to have 200mm depth at entry point and tie into 300mm depth to meet raised table
bb2d6c7f-dff7-5468-a56d-71c328643796 | note | FREQUENCY: Prior to pouring concrete
bd7392fb-7bdb-5c51-a46a-a35bce0ed01d | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measurement
7e3f22c2-328a-5902-918f-54c3bf71d7cb | note | CONFORMANCE CRITERIA: Designer to inspect formation level
47e8da7c-c133-5106-9830-9d9e370a380d | note | RECORDS: Site photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8.3 - Temporary Works (Formwork)
634db78c-9626-5582-a8d1-e01ae06c75de | note | ACTION (Hold, Monitor, Witness): H
62ce1de5-8c07-5b70-8c42-f68215ac4e73 | note | DETAIL: Raised Table ramps to be 1.125m across for entry and 1.125m for departure ramp
ee5f7352-9e50-5fcc-a1dd-4e852e50e1bd | note | ○ Swedish table ramps to be 1.125m across for entry and 4m for departure ramp
c5231bb8-eaa4-5764-a58b-5ea4d40e1897 | note | FREQUENCY: Prior to pouring concrete
dd0479e6-031e-5d33-a04b-8e837cca1a5a | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measurement
8cd2ce8d-ab80-54ef-9d9e-8a92bbf6599d | note | CONFORMANCE CRITERIA: Designer to inspect formation level
16857c3c-0a34-560a-b1d5-73d731683a9f | note | RECORDS: Site photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8.4 - Temporary Works (Formwork)
9a48f731-2143-5193-b96d-e91a11a7ae94 | note | ACTION (Hold, Monitor, Witness): H
39171083-b202-5b44-a46f-06569344f366 | note | DETAIL: Raised Table ramps to be 1:15 gradient for entry and exit
44dbd026-e91e-567d-9de9-eb064818e897 | note | ○ Swedish table ramps to be 1:15 gradient for entry and 1:40 for exit
30e9ed3a-c335-5e41-8ad9-26abab1145fe | note | FREQUENCY: Prior to pouring concrete
23e13896-6511-55e6-b80f-73a1c9028283 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measurement
0f472d65-962a-51c1-8206-db72394d9246 | note | CONFORMANCE CRITERIA: Tolerance +0.5% -1%
5c6b85b6-8348-5d7b-bb66-61ec04581066 | note | RECORDS: Site photos / Concrete Formwork Checklist
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8.5 - Temporary Works (Formwork)
cda150a9-0b8c-5c25-a0d9-b0c496591f19 | note | ACTION (Hold, Monitor, Witness): H
b85e391a-56c6-53a4-a1a2-400227419d64 | note | DETAIL: The Site Engineer and MSQA Engineer must sign off the formwork prior to concrete being poured
9ce3618c-b9c2-593e-ab08-b2013204384b | note | FREQUENCY: Prior to concrete pour
4eb7a486-b115-518d-9643-86704de8fa53 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
e92c46d9-2358-545b-9e8f-653496a8b542 | note | CONFORMANCE CRITERIA: Concrete Inspection Record
5ff0d22b-072d-5643-b67d-50e5d5d85859 | note | RECORDS: Concrete Formwork Checklist
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Reinforcing
9573e2b5-ca97-544a-af58-2f81ed724a19 | note | ACTION (Hold, Monitor, Witness): H
f8d5efde-b819-5cee-8c9a-fdfecff6b4dc | note | DETAIL: All construction joints are to contain 2 rows of LESA dowels or similar approved dowels . Speed basket system 260mm w/ Black 300*50*6mm plates @400 centres placed across the construction joint
06c1a902-cefe-5aa0-b772-a7dd91898cf6 | note | FREQUENCY: Prior to pouring concrete
db073420-9ea2-5a23-ba30-b6c7cc682f4d | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measurement
7f8d1427-5c4a-5d1d-8ac5-f590a82a6744 | note | CONFORMANCE CRITERIA: Concrete Inspection Record
c9f4c663-ea99-55ab-b002-4761065b004e | note | RECORDS: Site photos/Concrete Formwork Checklist
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10 - Concreting (1)
6efdae72-01af-5842-9f3e-e77e1f96e1f5 | note | ACTION (Hold, Monitor, Witness): H
037ae388-68af-5ce7-9608-00c726d65d2e | note | DETAIL: The MSQA Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required
f521aac6-4bcf-54e4-bb45-9f44c8a19f12 | note | FREQUENCY: Prior to concrete pour
899b11a7-19b6-535e-97fd-77f12a272c2a | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
eb4f09fa-16c7-5e4f-994f-aa14c23175ff | note | CONFORMANCE CRITERIA: Engineer will be notified via email/SMS at least 24 hours before required for inspection
170c22da-efb0-55d3-82a2-6ea590fc3a44 | note | RECORDS: Email / SMS
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10 - Concreting (2)
1f2da5a9-1fa1-5e67-b860-f95c577429cd | note | ACTION (Hold, Monitor, Witness): W
a86d5ef1-2039-5741-b4e9-1a39a5e6625c | note | DETAIL: Vibrator to be used throughout concrete pour
d5b14489-3f76-5b08-8ff1-eb47cc8138d5 | note | FREQUENCY: When pouring concrete
4a3c223e-70fd-53a0-859b-d6c68bf2b85c | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
07686f11-c4bb-5bff-aeb6-5586b390b159 | note | CONFORMANCE CRITERIA: Concrete Inspection Record
df9cdf6e-13b0-5802-bcd5-0bee2401ddef | note | RECORDS: Concrete Formwork Checklist
| checkpoint | 11 - Concreting
b1c024df-3cf8-521a-950e-dafd3c81845d | note | ACTION (Hold, Monitor, Witness): W
6e569325-de7f-5d71-a356-474d39bad63d | note | DETAIL: Concrete ramp surfaces shall be U5 broomed finish & Table will be exposed
a6ec9536-7d9e-55a1-9c1a-6e0537a0a6f8 | note | FREQUENCY: At completion of pour
aeccbd1d-3b6d-57d8-821d-393b3f49a3b0 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
92ce5f42-ae0d-54fc-a429-fe709e0bd204 | note | CONFORMANCE CRITERIA: Concrete Inspection Record
4edb3479-6bfd-5a9c-b1c7-3110773ddf17 | note | RECORDS: Concrete Formwork Checklist
| checkpoint | 12 - Curing
c0ea0ede-01a5-583f-8182-45bae31fa51e | note | ACTION (Hold, Monitor, Witness): M
ba89ec1a-25fe-5388-b095-f0f30fbfecac | note | DETAIL: Concrete will be left for 48 hours minimum to cure before traffic is allowed on it. / 36hrs with 50Mpa
4187f280-fb7f-5f79-b2eb-9dc341e3bfd5 | note | FREQUENCY: Post Pour
fc4534d1-8d53-529d-bd71-25c994a0fdb9 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Monitoring the time allowed for curing
93981ad0-16ba-5575-a6a7-d19acc7dfa38 | note | CONFORMANCE CRITERIA: 48 hours minimum have passed/ 36hrs with 50Mpa
ba448c51-7f91-5583-bad0-ae178edfaab2 | note | RECORDS: Concrete Formwork Checklist
| checkpoint | 13 - Remove formwork
22d2a28d-2e11-56cd-b12b-3451eb6df592 | note | ACTION (Hold, Monitor, Witness): W
8736a81a-ce6d-561d-8d35-ec5d7188f0ac | note | DETAIL: Remove formwork after 48 hours/ 36hrs with 50Mpa
063a3929-6379-5604-a071-ce2ad8eee0c1 | note | FREQUENCY: Post Curing
41bd9781-c562-558b-a122-21fe59215656 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
728f2fc7-b203-57b3-95d8-ac505476c699 | note | CONFORMANCE CRITERIA: Concrete Inspection Record
c2397a94-b4ea-5ec2-bfe0-e18ab53f4cd4 | note | RECORDS: Concrete Formwork Checklist
| checkpoint | 14 - Asphalt- Concrete extension slab/ Toe (1)
da934435-a93f-536c-9076-a991c1114aa5 | note | ACTION (Hold, Monitor, Witness): H
04708c01-333e-5b32-8684-6493be376bbb | note | DETAIL: Two rows of Lesa diamond placed mid depth @600mm C/C along construction joint as per R5-004
141cefe9-fd48-5375-a84e-84ee28f842b5 | note | FREQUENCY: Prior to pouring concrete
3dc67e0e-5bde-510b-8e7a-86e009748dfb | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measurement
114190e5-ead2-5da9-9af8-c24e858675eb | note | CONFORMANCE CRITERIA: Pre pour Inspection Checklist, Concrete Inspection records
6348edf4-f7bf-53a5-b180-d4b1e5ac8419 | note | RECORDS: Site photos,delivery dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 14 - Asphalt- Concrete extension slab/ Toe (2)
cb74b1d0-3b52-524a-83d8-f6a03abe8ca3 | note | ACTION (Hold, Monitor, Witness): H
3ba57c98-9bd6-5602-8397-638e885f60b3 | note | DETAIL: 250mm thick 40/50MPa Concrete with two layers of 663 mesh, 60mm cover
881b7deb-c231-5b4f-a043-af76762f7562 | note | FREQUENCY: Prior to pouring concrete
6bd660be-8a4e-559f-ae0a-3dbea9d0d7c3 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measurement
9d3dbd69-f1ae-55f9-8047-c1a169eb8100 | note | CONFORMANCE CRITERIA: Pre pour Inspection Checklist, Concrete Inspection records
f2efc675-7dcd-54ed-a037-b25b519fa798 | note | RECORDS: Site photos,delivery dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 14 - Asphalt- Concrete extension slab/ Toe (3)
304600d6-8735-518a-ba1f-55b70e7417e9 | note | ACTION (Hold, Monitor, Witness): W
8758f301-8a3c-5b7d-b00a-c3bf1b77a4e3 | note | DETAIL: Tack Coat between DG10/AC14 and Concrete slab
468681fd-2614-5b5b-9ad9-59708a315faf | note | FREQUENCY: Post Curing
5acb77cb-6724-58b4-b3f7-c9e03d49753e | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
10f36044-f41c-59e8-b10a-d55617b99a54 | note | CONFORMANCE CRITERIA: Photos + Delivery Docket added to QA folder
ec9bbd2e-4bb9-54d6-b513-5d6966693f43 | note | RECORDS: Site photos
| checkpoint | 14 - Asphalt- Concrete extension slab/ Toe (4)
2ab5090f-c1d2-5c0f-ba37-a5218872a11b | note | ACTION (Hold, Monitor, Witness): W
ed2578a4-e296-54e6-86f9-fe88b38d21c4 | note | DETAIL: 50mm thick DG10/AC14
19f37b9b-4af7-521a-bff7-e42da9e003bf | note | FREQUENCY: Post Curing
dfbddbaa-4667-597f-85b9-72c986e942a8 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measurement
40cfdcae-5d53-5cab-88d4-e7b761728367 | note | CONFORMANCE CRITERIA: Photos + Delivery Docket added to QA folder
66235d0e-7c0b-5b45-ba07-95e0db5f7f94 | note | RECORDS: Site photos, QA records,delivery dockets
| checkpoint | 15 - Lot Number QA File (1)
833a66cf-62d8-5546-b4eb-5dd57f42e118 | note | ACTION (Hold, Monitor, Witness): W
dc86131a-52eb-5695-b7ec-0deea4d8ecd5 | note | DETAIL: Ensure all QA Records,site photos and incident cases (OFIs) are closed and included within QA file
127173f7-a857-5168-987d-03dab302539a | note | FREQUENCY: At completion of Lot
28573589-7675-5e49-8f33-ed69326ae1cb | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
44776d56-af7e-5045-908e-800efefa0f4c | note | CONFORMANCE CRITERIA: All QA files compiled and sumbitted to client
0656c46c-f705-5660-9819-0fa917864665 | note | RECORDS: QA records
| checkpoint | 15 - Lot Number QA File (2)
3652a6ae-4c80-5e4f-9291-b297dea289c5 | note | ACTION (Hold, Monitor, Witness): W
2bf6ffaa-a84e-5599-9d14-cadecf0a8867 | note | DETAIL: Delivery Dockets to be included in QA file
94f594b8-338b-5425-ad0d-409f59d605c8 | note | FREQUENCY: At completion of Lot
66619508-6f80-5cd2-87f5-cf15fef1298c | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
6676990e-05f3-5cf0-951a-2eba341da779 | note | CONFORMANCE CRITERIA: Delivery Dockets to be included in QA file
d95653f4-8724-594c-a5ac-4f8312947bf7 | note | RECORDS: QA records
| section | Asbuilts
| checkpoint | 8 - As built information
59d61596-1310-536c-a289-af00ec9ff52b | note | DETAIL: Drawings
ce2162d1-d253-5f77-982a-7ff39a9331e3 | note | FREQUENCY: Every Site
2b58a5a3-8c8d-5636-8e55-525827da6905 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): As built drawings
99615d2d-7b15-574c-b039-93bdf1710d54 | note | CONFORMANCE CRITERIA: In Process Inspection
f34e7df8-83d3-5bc2-83de-8fc683b25ca2 | note | RECORDS: Asbuilt records
| checkpoint | 9 - RAMM DATA
9d17cb7b-2071-555c-8016-81f536340fa7 | note | DETAIL: RAMM DATA SHEET
9acf6ace-9531-533a-b0da-1214b4a0d502 | note | FREQUENCY: Every Site
95d7a222-e909-570a-b7ec-baa6a9ef13b8 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): RAMM SHEET
dff871ff-09ec-5fce-9fa5-9e67173974e2 | note | CONFORMANCE CRITERIA: In Process Inspection
9a31688e-b604-55bb-94d3-0ab4e3d1cb40 | note | RECORDS: Asbuilt records
| section | ITP APPROVAL
| checkpoint | ITP Approval
dcda9760-3c61-53e8-9ade-118a76313897 | note | Prepared by: Genald Sebastian
7062797f-75e6-5ac6-9e30-30aa45b510ed | note | Approving Delegate: Ben Lin
a7a9997d-db8a-52a0-9dec-56c5e76590ad | textbox | Engineer's Rep
| checklist | Devonport Town Centre - ITP - Stormwater Drainage | itp | ITP - Stormwater Drainage | 5cdeec09-266f-4d8d-b1f3-c361a43c7352
| section | Pre-construction
| checkpoint | 1 - Permits & Services (1)
fb67b198-3c07-593f-8781-1cfd16c185d2 | note | ACTION (Hold, Monitor, Witness): H
4408c4ec-e4c3-50c9-8d63-44ee1da99039 | note | DETAIL: Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
b8e5b581-bcdc-553b-ba87-d71704cda451 | note | FREQUENCY: Prior to any construction commencing
eb5153a9-788e-535f-99a0-4959accfce28 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
100e9631-4016-5f6d-af3a-7cb42c615394 | note | CONFORMANCE CRITERIA: Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority.
0d597b27-3305-5155-8de8-0b78f8a1fbec | note | RECORDS: Permit attached or permit number noted.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1 - Permits & Services (2)
7bccbe33-6833-572c-8831-50611fb93d36 | note | ACTION (Hold, Monitor, Witness): H
9e207a66-2b58-5e33-b55e-ab44b1c54270 | note | DETAIL: Locate and mark out all existing services
6485a908-f102-584c-83c3-04db619962c6 | note | FREQUENCY: Prior to any construction commencing
f806a93e-832d-5c9b-8278-954af826d71a | note | CONFORMANCE CRITERIA: B4u dig procedure - follow utility protocols
46e68009-9a05-5c7e-a5eb-0094356ab2a5 | note | RECORDS: B4u dig plans & GPR report attached
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Pre-Construction Sign Offs
1482ae6a-ad58-5f40-aa32-f193414af1b2 | note | ACTION (Hold, Monitor, Witness): H
e8ddc783-65e5-5ffa-931b-3bd61e04ccf4 | note | DETAIL: Sub-Contract and Supplier Agreements
33f8433c-887d-5138-956a-6cfc384cddca | note | FREQUENCY: Prior to commencement.
61bffd17-4c19-5ec9-8560-5b1089648e24 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
9f99f411-4e4a-508d-b27f-2c010c3d3af4 | note | CONFORMANCE CRITERIA: Sub-Contract and Supplier Agreements to be agreed and signed
b1f7bcc1-48e5-533f-8c18-fa8ed1a520de | note | RECORDS: Subcontract and Supplier Agreements
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Design
4dd83491-06d6-52a2-96ea-3824dd80b135 | note | ACTION (Hold, Monitor, Witness): H
58a41589-d443-5b76-a5c6-c08da0e287fc | note | DETAIL: Design is approved and Drawings are of the latest revision.
95a7058d-e56e-57d7-b566-061df7562a1b | note | FREQUENCY: Prior to commencement.
e8d14301-53a8-551e-84cc-dd3e2026aeea | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
db2eb705-d219-59c7-95a2-a79a7f3f9f96 | note | CONFORMANCE CRITERIA: Ensure that Design is approved and Drawings are of the latest revision.
00925f90-339e-5550-ad2b-29c97961d32b | note | ○ Drawings to be 'ISSUED FOR CONSTRUCTION' status.
1a765a02-8e12-582e-b4a8-8848558da805 | note | ○ HOLD POINT of not issued to IFC.
03db2acd-a470-5554-aab1-d8f4d25fe182 | note | RECORDS: Drawing Register.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Survey Setout
49ba7ebb-e99d-5183-8c69-dcbf3aff1348 | note | ACTION (Hold, Monitor, Witness): H
832e969a-b2a1-526e-adee-d62f901ca3f8 | note | DETAIL: Setout Pipe Alignment and Service Locations with inlet & outlet points and inverts as required to construct to design
9f626138-1414-574a-a84d-5d0a7753eb2d | note | FREQUENCY: Prior to commencement.
6fe6f32a-5760-540f-9f77-8e62364a99d1 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Survey
9873e737-0328-571a-864e-c474dd9b1448 | note | CONFORMANCE CRITERIA: As per Drawings: T18092 - R1-001 & Setout files
fbc17f50-33dd-500d-bc18-d2e6337e846d | note | RECORDS: Survey Receipt.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Pipe and Manhole Material Compliance
fd016ebf-1ca1-5c4c-a172-d1b470a6a4ff | note | ACTION (Hold, Monitor, Witness): H
eb636546-7f8d-56c3-9fa0-8a042ade2fc1 | note | DETAIL: Cesspit, Manhole and Pipe shall comply with relevant AT/TDM standards
9305bbc8-9563-5d65-bc5b-eb3bf0e89d16 | note | FREQUENCY: Prior to commencement.
b198a7f9-6845-5ef8-a676-01cfcc827299 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review, Visual Inspection
95991ba0-1c6c-512d-87c4-36b5d6ba0696 | note | CONFORMANCE CRITERIA: Pipe shall be Check for freshly formed pipes and return if required
f278ee96-13ac-5b41-aa4b-1b9b487ebcfa | note | 1) DN225 Class 4 RCRRJ pipes AS/NZS 4058
e8196bdd-68b3-5698-82db-18b627ce175d | note | 2). All Concrete RCRRJ pipes to be fitted with Rubber rings
dade0910-defc-518b-b8bc-b7173c0eaf26 | note | 3). Pipes shall have product certification (ISO Type 5) to AS/NZS 4058
0b7bcdb6-d67a-54d1-9347-ca5c08626d93 | note | ○ Prefabricated concrete Manhole shall be in accordance with TDM Standards & AC COP
da14779f-fc33-5970-9309-dd0ac95f86fe | note | RECORDS: Manufacturers Data Sheets, Delivery Dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Locate Existing Services by Hand Digging / Hydro Vac
4cc36b1e-eac1-5712-aabf-ee5c3457ff19 | note | ACTION (Hold, Monitor, Witness): H
b22a2891-1b8e-5365-b247-4d7bb2a11362 | note | DETAIL: Ensure all services conflicting with the line of trench have been exposed by hand digging.
b45e023f-038c-5efe-9ed7-2a9e5a253e1e | note | FREQUENCY: Prior to commencement.
11ab576c-7f13-506d-9e2a-9d37a3d3e754 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Potholing / Survey
fe1be23d-48b1-5a97-ab6d-0840479f9680 | note | CONFORMANCE CRITERIA: All conflicts have been located. New services and / or conflicts to be advised to Project Manager.
46480b8d-5c51-50af-b50f-23388709b95c | note | RECORDS: GPR report, Photos
| signoff | AUTHORITY HOLDPOINT
| section | Stormwater Construction
| checkpoint | 7 - Trenching & Excavation (1)
790df7a3-09e9-509e-bd45-3bebd0ec6851 | note | ACTION (Hold, Monitor, Witness): H
35c5d130-f82f-597a-9b51-b3ea20b47a0e | note | DETAIL: Excavation methodology
5b126d95-fe6d-5fa3-9391-fdf4ad8710d3 | note | FREQUENCY: Daily
548180d3-8b06-50c2-9861-ff190153f1bc | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Prestart review
fa930db0-d92b-543d-9ae0-4858a221a4e3 | note | CONFORMANCE CRITERIA: The excavation, benching and shoring requirements shall be in accordance with Worksafe Excavation safety guidelines (2016)
452a2fe4-be1e-576f-a5de-aa1ba95c930b | note | RECORDS: Prestart RCP
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Trenching & Excavation (2)
ede6a684-641e-5214-824a-8f3a851054ef | note | ACTION (Hold, Monitor, Witness): M
db96cb46-4a28-534a-acc1-ddf6bccb7078 | note | DETAIL: Trench Profile - Width
ca9acec1-68f3-58cd-9af7-4d643645e5a2 | note | FREQUENCY: Daily / as trenching takes place. Different depth methodology
025b33d5-2796-5462-a704-c9d4c3e69c37 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection, Excavation methdology
1bd00d00-1444-543c-9c89-2fd5afa4e65a | note | CONFORMANCE CRITERIA: Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing
4a71f530-2ce6-54eb-9277-c4f6781827ed | note | RECORDS: Construction Photos
| checkpoint | 7 - Trenching & Excavation (3)
cb08780f-1320-58e8-9550-1b5726288057 | note | ACTION (Hold, Monitor, Witness): W
a34ee5a7-8549-57ae-8c79-4b083703d1b1 | note | DETAIL: Trench Profile - Depth
6e494ae0-4506-5436-a774-b5cd074d2f78 | note | FREQUENCY: Daily / as trenching takes place.
7714419e-2f50-55c1-bed5-5e965792d1db | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection, Measurement
2c93db50-973e-54ba-ba78-d34a20ea3211 | note | CONFORMANCE CRITERIA: Trench depth varies according to longsection and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings
3f180596-1909-55c7-9081-e55dac110048 | note | RECORDS: FH Drainage Line Record / Construction Photos
| checkpoint | 8 - Bedding for Concrete Pipe Laying & Manhole & Cesspit
ec7321e4-7cd6-520b-9acf-e28961cbdfb6 | note | ACTION (Hold, Monitor, Witness): W
db4fa8ab-ee08-5e5d-abe9-2968c498628d | note | DETAIL: Placing and compaction of Bedding Material.
6a28edd5-a793-5b48-be52-932db41f7f72 | note | FREQUENCY: Inspected continuously during placing and compaction of Bedding Material.
9367765c-e67e-5f24-8ed5-9030cd3c12cf | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
50bbb728-0700-5218-b5a2-c6b4f5a40f91 | note | CONFORMANCE CRITERIA: Bedding & Pipe surround material to be GAP7 or GAP 20 (Stevenson Quarry) or alternate material that complies with AS/NZS 3725
01afcdaf-4054-5a04-ac4b-81c297736ed0 | note | RECORDS: FH Drainage Line Record / Construction Photos
| checkpoint | 10 - Trench Backfill - Placing & Compacting
3b5f0768-1990-5425-bbbe-c35fb7c84731 | note | ACTION (Hold, Monitor, Witness): M
6379560e-55b3-5c62-a304-f6250cc1cad0 | note | DETAIL: Placing and compacting of Trench Backfill Material
be92a42d-27ef-5e23-b1fb-70654567e05c | note | FREQUENCY: Throughout Trench Backfilling operation.
d9597b40-8a2e-5eb8-99c2-99ec7baac9db | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
45e55362-f768-58f9-901b-50c6f734cf9d | note | CONFORMANCE CRITERIA: Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm
9553467e-044d-5ab4-874a-e99874a5776b | note | RECORDS: Construction Photos
| checkpoint | 14 - Trenching (1)
62dab0ac-de6d-5fd5-926a-e83554f06184 | note | ACTION (Hold, Monitor, Witness): H
41472516-d583-5aac-84fc-854826a1b104 | note | DETAIL: Inspect trench profile and ensure it is 0.300m wide
dd28f700-a74d-56ef-8b78-3ea6ed87d4f9 | note | FREQUENCY: 10m intervals
19bd5cb4-3b3a-5558-8a25-60768bd4430e | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection and measurement
2e5eac4c-c47e-5267-ae4a-f559ba25cd39 | note | CONFORMANCE CRITERIA: Record levels of base of trench on dip sheet
96b84021-9277-5adc-9045-a185613d52f0 | note | RECORDS: Photo / subsoil log
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 14 - Trenching (2)
996856ff-b246-5906-9adf-bc4bf8bf798a | note | ACTION (Hold, Monitor, Witness): H
9a950fd0-f836-5902-9cf3-1896a33f0336 | note | DETAIL: Ensure the trench is cut in a manner than will ensure that the pipes will be laid true to the depths, grades and lines shown on the drawings.
9b09625c-bbeb-5c12-b11f-dfbdeb02273b | note | FREQUENCY: 10m intervals
e95dc2f7-7180-5bc8-912c-67e6208d8507 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection and measurement
270c8b86-f09e-5adf-8d9d-fedfbaeecee3 | note | CONFORMANCE CRITERIA: Ensure trench line and levels match the design drawings
f4a7d3e1-cfa8-54ab-8ac1-670d82103e98 | note | RECORDS: Photo / subsoil log
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 15 - Catchpit Connection (1)
caf72c27-84ed-548c-98a4-7b2cc8a3a9a9 | note | ACTION (Hold, Monitor, Witness): W
caf1182e-9f39-5649-bc4c-9e73970a5f5d | note | DETAIL: Ensure minimum entry point 150mm above soffit of outlet stormwater pipe
f80d4f59-5e7e-5e16-acad-1671dc36e5bf | note | FREQUENCY: As required
fa134b6e-5894-5d19-83fa-dbef0b698bab | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
da312143-4d5e-5ce6-b116-effdefa3aa50 | note | CONFORMANCE CRITERIA: Consistency with Subsoil Details
e09af512-400b-5ecd-be44-6d677eb880c4 | note | RECORDS: Photo
| checkpoint | 15 - Catchpit Connection (2)
ce67d7eb-8d38-5f9b-ab51-05e0b11a9b39 | note | ACTION (Hold, Monitor, Witness): W
e23f005a-7765-5363-af46-8a267e29c0a2 | note | DETAIL: Perforate Catchpit and epoxy grout pipe from inside to completely seal connection.
75b1069b-b652-573e-95c8-d3d6b5fac4cc | note | FREQUENCY: As required
f15e0946-6266-58e0-96f5-fac32d60a844 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
886a677c-992c-5a56-85ca-dbce8ea9f168 | note | CONFORMANCE CRITERIA: Consistency with Subsoil Details
8eca1fa7-5249-5975-969a-1932c9ebe478 | note | RECORDS: Photos
| checkpoint | 16 - Gradient
df0b9c2a-945c-5c1a-9a61-f4fd3b91ca99 | note | ACTION (Hold, Monitor, Witness): W
e71e4e4c-4bed-58ab-9249-f7cb234456aa | note | DETAIL: Ensure water falls in intended direction
64c56b6c-3f6b-57a8-b18d-55dcbe5fb14a | note | FREQUENCY: Throughout
bcb65bd4-a0d0-5f13-b2d9-870785665399 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
de600156-ff6e-53c9-85db-ba1cbf196ddd | note | CONFORMANCE CRITERIA: Grade >1%, No undulation in subsoils
5908b892-3101-50ca-be21-607a1d59d337 | note | RECORDS: Photos
| checkpoint | 17 - As-Built Drawings
159583a9-9585-59fc-bea9-efb20992d99c | note | ACTION (Hold, Monitor, Witness): W
7cccaaa8-b1c0-55c3-9b09-9f18843e8b15 | note | DETAIL: Red pen marked-up As-Builts of every 'Issued for Construction' AT / drawings
0e4d4f72-ae62-5a9f-b088-612da0e75780 | note | FREQUENCY: Final As-Built Drawings to be completed within three months of the construction completion of the asset or infrastructure.
e4ac8911-a834-5503-b3c3-bb31b5625819 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Drawings / Visual Inspection
e62a411a-3f6b-5d5e-b704-e2953c0e6c04 | note | CONFORMANCE CRITERIA: As Built and GIS Data
f2fc4481-2971-52b9-945b-fd4a2191f1f4 | note | RECORDS: Redline As-Built Drawings, scanned as .pdf files.
| section | Subsoil Construction
| checkpoint | 17 - Subsoil Material Compliance (1)
729264c2-3aeb-5215-8335-1537ecf0614e | note | ACTION (Hold, Monitor, Witness): H
520587e2-c59f-5d35-a3bc-173ebbaed7b2 | note | DETAIL: Ensure Subsoil Drainage pipe complies with TDM RD0010
86944a2b-9d24-5e30-8f0b-7f0e1fb218bf | note | FREQUENCY: Upon delivery to site
6fef6203-cb10-5422-bffd-8549dfc94324 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Ensure delivery docket matches materials delivered
63a13d6b-09b2-5c3a-a05a-1ee2b3f09ca7 | note | CONFORMANCE CRITERIA: 110mm diameter Drain flow TNZ F/2 Grade pipe - filter sock
9d2a8305-a565-5666-9ae3-05ee07c185c9 | note | RECORDS: Delivery docket
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 17 - Subsoil Material Compliance (2)
6e360c11-9c07-57a9-ac54-6a54b501844a | note | ACTION (Hold, Monitor, Witness): H
174a5c7c-2090-504f-9cb3-ecf77b6763e5 | note | DETAIL: Ensure Material for Bedding, Side support and backfill F6 filter sand drainage aggregate
62bf37fa-480d-5a2c-a13b-68cac35428ad | note | FREQUENCY: Throughout Subsoil
f59e6ad0-650a-5228-a765-118940b2e6a5 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
65ff98b2-ef4d-5d3e-b538-1db09445f8ca | note | CONFORMANCE CRITERIA: Ensure clean drainage aggregate - F2 Spec
3af70eea-e80e-5ff8-b76a-9093617c49cc | note | RECORDS: Delivery docket
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 17 - Subsoil construction Compliance
78e428ed-9ee0-5e08-a316-b08f97905784 | note | ACTION (Hold, Monitor, Witness): H
dd9bc44c-fb1c-575b-9fbe-037215228f02 | note | DETAIL: Inspect trench profile and ensure it is 0.300m wide
89d4834d-7c66-573b-9dea-5dd3da6b20ac | note | ○ Located below 300mm below subgrade
54c452a6-2f4a-581e-ac74-f632a4b6e9ef | note | FREQUENCY: 10m intervals
5771dd00-49ce-50bd-987e-7c8f96a728ab | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection and measurement
ad9868fa-3eee-5f35-872e-9f36e7740fcf | note | CONFORMANCE CRITERIA: Record levels of base of trench on dip sheet
4d8da859-9a31-532c-a98a-690c14daee05 | note | RECORDS: Photo / subsoil log
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 18 - Bedding, pipe installation and Backfill. (1)
ef954f9b-f95e-5c78-a8a0-309bbcd9867f | note | ACTION (Hold, Monitor, Witness): W
7a2e04b2-d35b-56ca-8108-c017327f9aed | note | DETAIL: Ensure 50mm thick F6 Drainage aggregate bedding is placed in base of trench.
80c98387-979d-58d5-a0ab-cccce0bda8d8 | note | FREQUENCY: 10m intervals
97c7194f-3877-5d97-8014-9aa548ff5870 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
c61e815b-7506-537e-a4ea-4e68f9d58311 | note | CONFORMANCE CRITERIA: Record levels of top of bedding on dip sheet
1d3804a9-32d2-53ea-ba49-6a9b5fe70523 | note | RECORDS: Photo / subsoil log
| checkpoint | 18 - Bedding, pipe installation and Backfill. (2)
a8418e1c-e0cb-5bdf-ae76-bcbfebf21b22 | note | ACTION (Hold, Monitor, Witness): W
011854f4-7555-5431-a1f2-74be6e7fa136 | note | DETAIL: Ensure Subsoil Pipe is laid on the Bedding in the centre of the trench
d1053541-d704-5f62-869b-dd82eca0e92f | note | FREQUENCY: 10m intervals
b2c28dae-1457-5daf-92b7-12c48f651082 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
72e0367d-1caa-594e-b0df-bacd8a294294 | note | CONFORMANCE CRITERIA: Consistency with Subsoil Details
6056d0c2-c869-52bc-9dc9-36739da6831e | note | RECORDS: Photos
| checkpoint | 18 - Bedding, pipe installation and Backfill. (3)
d43c531d-5294-5a56-a6da-59f5ff70c7a5 | note | ACTION (Hold, Monitor, Witness): W
b5446b93-fa85-539e-a0f8-9f6a74cf9dde | note | DETAIL: Backfill by tipping F2 Sand into the trench
99d91487-8829-5afb-a0d8-d039889fbc46 | note | FREQUENCY: -
e6287d4f-996d-58e4-83d8-565edba3d7b2 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
628bd0bd-4220-5cdf-81cd-4c46c146754a | note | CONFORMANCE CRITERIA: Ensure good coverage
65e8c5bb-6860-596d-9244-db211c7cef28 | note | RECORDS: Photos
| checkpoint | 18 - Bedding, pipe installation and Backfill. (4)
0e72866f-448e-5d8c-b17f-b56ab5446f0b | note | ACTION (Hold, Monitor, Witness): M
52152d47-85b5-58b0-a4f2-22b20cbd5d55 | note | DETAIL: Ensure water falls in intended direction
df9d3027-ae54-53db-869d-eb7e156f8a2e | note | FREQUENCY: Throughout
3be10d46-d14a-59c5-8294-03a5462aeee8 | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
45c1d7ae-3f8f-58f1-bcc3-ca236cac28c0 | note | CONFORMANCE CRITERIA: Grade >1%, No undulation in subsoils
f5899d1a-1206-536c-b3ee-f6d1ee083ad5 | note | RECORDS: Photos
| section | Asbuilts
| checkpoint | 8 - As built information
29b8fa46-0198-50db-8dc7-a812a3044dba | note | DETAIL: Drawings
70d519e1-79ea-508d-851f-46ac735b76df | note | FREQUENCY: Every Site
0c282a86-b5cb-5f19-a477-dd7c51a8305c | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): As built drawings
550b3f10-827a-5c0d-9b44-65a963bf2552 | note | CONFORMANCE CRITERIA: In Process Inspection
e192f6dc-301f-5cf7-b904-7d9d982265cc | note | RECORDS: Asbuilt records
| checkpoint | 9 - RAMM DATA
d6cd0815-d04b-563f-8441-c70e9a294dd8 | note | DETAIL: RAMM DATA SHEET
4a13bbf4-d7e5-54c5-a9a0-616bd3b73278 | note | FREQUENCY: Every Site
64c6828b-7d56-5a68-80d8-f8756bf5d00a | note | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): RAMM SHEET
213d5444-2cf8-5bd0-8d83-27d6ff08b850 | note | CONFORMANCE CRITERIA: In Process Inspection
fca109c6-bba4-56ad-aa49-a527b4a823b5 | note | RECORDS: Asbuilt records
| section | ITP APPROVAL
| checkpoint | ITP Approval
fa46ba07-bb18-5a8c-8e69-1183f159fa24 | note | Prepared by: Genald Sebastian
2ac1e25f-3d89-5ad0-9cb8-be0215218aaf | note | Approving Delegate: Ben Lin
6680f8b8-02dc-5ddf-bca4-87d67acb2bfe | textbox | Engineer's Rep
| checklist | Devonport Town Centre - ITP - Traffic Islands | itp | ITP - Traffic Islands | 5462f3f5-3392-4666-ae95-bf1d79ffafc1
| section | Materials
| checkpoint | 1 - Mountable Kerb
8e34faf8-b01c-5651-9c6e-71ac6fdb5d9d | note | VERIFICATION ACTIVITY: QA FORM
99e06ca7-193d-531d-bfb8-b2605772938e | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
621e2339-b42e-5dd5-aed0-91ac4349d241 | note | FREQUENCY: Every site
1c4c7c2e-80bb-5889-aff4-4208d1f4b277 | note | ACCEPTANCE CRITERIA: Mountable Kerb to be laid using precast hand-laid and painted with two coats of reflective paint
81837583-6fdc-5c30-b432-6b9cf41c2525 | note | HOLD POINT: Inprocess Inspection
5bd8f8c4-1a42-56f0-bac0-c3b9a79f3ae2 | note | RECORDS: FH concrete QA sheet, photos.
6fa4db72-7f69-5eaf-9efc-aef945b8984c | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Construction
| checkpoint | 2 - Survey Setout
fd4f628e-2d35-5e1d-b1b5-e59d0623b998 | note | VERIFICATION ACTIVITY: Survey
9ea28513-078b-57c4-9f36-cb5183e657e4 | note | METHODS OR REFERENCE: Setout Kerb Alignment required to construct to design
48d603dd-ab93-50ba-b829-0d4d29d289c2 | note | FREQUENCY: Prior to commencement.
002f1d57-f900-5636-b2f7-be7e85616086 | note | ACCEPTANCE CRITERIA: Survey
19ecc8d7-b056-5d1f-bbba-3fc61b98385f | note | HOLD POINT: As per Construction Drawings, HOLD POINT
020fa343-3737-501a-8ff3-66b9b3871ad0 | note | RECORDS: Survey Receipt.
88820771-c8c1-5a41-bc01-18434360c1d5 | note | ONSITE RESPONSIBILITY: Site Engineer
| signoff | HOLD POINT
| checkpoint | 3 - Concrete Island (1)
4bb2f995-0b5b-5858-994c-fa475717bfe8 | note | VERIFICATION ACTIVITY: QA FORM
51e56567-50fe-54ab-b38b-d4dc3ade6b1c | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
cb83ca60-605f-5468-b723-625f552f9657 | note | FREQUENCY: Each Site
af3c8f9f-959a-56e6-8350-0a8e2714db93 | note | ACCEPTANCE CRITERIA: Kerbs to be haunced with 20MPa Concrete
0905e488-39b9-5eb2-9fb5-47cd88564753 | note | HOLD POINT: Inprocess Inspection
9bf7628e-3bf1-534e-adde-3694630e1232 | note | RECORDS: Photos
b95ee952-5856-5cfa-8fb0-185b94fe363f | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3 - Concrete Island (2)
2aa14b01-37dc-589e-b559-310f6b020992 | note | VERIFICATION ACTIVITY: QA FORM
faac6b6a-5582-5213-bd00-aa5d0d64a7db | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0003
3ed48d36-ff66-5f07-b8b4-dbaf71e390be | note | FREQUENCY: Each Site
e2040aba-1c58-525e-80e5-6f5148878376 | note | ACCEPTANCE CRITERIA: Basecourse to be 150mm min thickness of GAP65
8266bab9-f02b-5777-96d5-3b29c0617d80 | note | HOLD POINT: Inprocess Inspection
98dc368e-01be-5be1-80fc-9ad49490bbf3 | note | RECORDS: Photos
578594bb-131f-5fd6-8d34-3a21e2adf4a0 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 4 - Concrete Infill
22b057b4-137f-54ff-a615-4e30d975b91c | note | VERIFICATION ACTIVITY: QA FORM
befd2e36-eeb6-55c0-b96f-31bd9b731576 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
39703d63-b73c-53d2-8e08-c51aa09983da | note | FREQUENCY: Each Site
dddc92d9-d79a-535a-b574-2bd413873a48 | note | ACCEPTANCE CRITERIA: 180mm depth of 20MPa broom finish unreinforced Concrete with 4kg/m3 black oxide
1a420864-05ba-5d85-bf9e-dcd4e5b466b3 | note | ○ Cross Fall of 2% or max rise in centre of 180mm
c591b834-d792-5d59-9da7-7b0f4c78f4fe | note | HOLD POINT: Inprocess Inspection
465a7212-1221-5124-a657-33b8c94b2e05 | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
30f0ddab-2b25-5dfe-bbf1-dab70f491b44 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Asbuilts
| checkpoint | 3 - As built information
27fd9b50-8f07-5b89-84eb-e9b8ed829676 | note | VERIFICATION ACTIVITY: Drawings
e3ac2cfd-821a-51e2-b0cc-1d72222dbbc4 | note | FREQUENCY: Every Site
f47f1841-62b9-5eca-a6f7-dcaad8ac0e79 | note | ACCEPTANCE CRITERIA: As built drawings
ed0a3cce-3499-52b7-88dd-b20b3326eff7 | note | HOLD POINT: In Process Inspection
7b0a4730-beb4-5455-b92e-934d8b30cf61 | note | RECORDS: Asbuilt records
8d6ea349-ab4c-5878-9d57-744ba608fdce | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| checkpoint | 4 - RAMM DATA
c967c896-d1d7-5e86-b412-b62cc5fa6bd2 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
89b58607-b824-5930-83a0-34965fa73858 | note | FREQUENCY: Every Site
78dcb2a0-3f8c-59f1-8c63-c931b8ec2b6d | note | ACCEPTANCE CRITERIA: RAMM SHEET
1c0f7b9d-e9ad-5bf6-9657-2a8517a43d30 | note | HOLD POINT: In Process Inspection
e8827ace-7769-5676-9fe4-6d6948778f63 | note | RECORDS: Asbuilt records
b9c91579-af28-583f-9191-a347ee741c66 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| section | ITP APPROVAL
| checkpoint | ITP Approval
34357e7f-0356-5f73-a96b-1b7d40c27324 | note | Prepared by: Genald Sebastian
11a8b3ed-cc42-5e29-83bf-6f65e6ccda40 | note | Approving Delegate: Ben Lin
9a6e3aa5-8943-5e45-868b-9d072c645fcc | textbox | Engineer's Rep
| checklist | Drainage Checklist |  | Drainage Checklist | 400c3f10-644b-4774-8a10-9fcad652b2dc
| checkpoint | Alignment set out by surveyor
| checkpoint | All existing services identified before trenching
| checkpoint | Trench must be made safe before any person may enter the trench
| checkpoint | Base of trench is clean and inspected Scalar penetrometer testing
337c4845-f58b-5f5e-88ca-305aa8898bb3 | note | Every 10m , >3 Blows/150mm [CBR 3.5] , >3 Blows/200mm [CBR 2]
| checkpoint | Undercut Required
eb6fd978-ec14-53e4-bf36-15eef0127fa3 | note | Cleg > 25
| checkpoint | Geotextile Required
6e4d2364-70bf-54d9-a1e5-ff69a719ef52 | note | Cleg > 25
| checkpoint | Clegg Impact Value
bc1a74e6-9859-52c4-b418-16d4fb6b36fe | note | Cleg > 25
| checkpoint | Drainage pipes, M/H, C/P to be:
4697cc2e-9114-5864-a359-3ffa1b1e1998 | tickbox | Inspected and shows no signs of “greening”
1bd87336-6775-53d3-b56d-33ffbb61650f | tickbox | Rubber rings (pipes)
fc4bc9c5-434d-5d15-9f8f-6b5b1ecafadc | tickbox | Product certification
| checkpoint | Trench width and depth to correct target
49fa4f14-3e0b-5a89-9cb4-9b15fcc80caf | note | Photos – per 20m
| checkpoint | Pipe alignment and laser level check
| checkpoint | Bedding and Pipe surround to be placed at specified pipe diameter requirements 100mm bedding; 200mm wall; 150mm cover
3321a537-9425-5cb6-b3a0-b6cfb6b2e16e | note | G/SAP <12 Pipe Photos – per 20m
| checkpoint | Backfill in layers less than 200mm
e703a204-a4c6-513b-8919-0cf7da836ef9 | note | ITP requirements Photos – per 20m Clegg > 25
| checkpoint | CCTV Inspection
| checklist | Graeme Ave - ITP - Enabling Works - Footpath, Kerb and channel | itp | ITP - Enabling Works - Footpath, Kerb and channel | 26de9b44-2721-45c2-890f-743eb66c5fa2
| section | Site Set Out
| checkpoint | 1 Site Set out
f2acdc02-3166-5ba5-993a-bd0c9dce52ea | note | VERIFICATION ACTIVITY: Surveyor
03786190-b6f9-539d-8b4d-81df6e3c217f | note | METHODS OR REFERENCE: Surveyor
2b63c981-c7c3-56aa-b0d2-70415e943bad | note | FREQUENCY: Everysite
cd523aef-4413-5bf8-ba1d-7a97ee7362b9 | note | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
cf954a8a-3e06-51e9-b5d1-2b5f36231808 | note | Hold Point: Mandatory HOLD POINT -
6da3a5cc-59bc-55b0-a538-f86327aacc5c | note | Records: Onsite records/photos
36c8c73f-5a8d-5d9f-8d48-f5c61bdc073a | note | Onsite Responsibility: Site Engineer
| signoff | HOLD POINT
| section | Materials
| checkpoint | 2 Kerb & Channel
e4ef2523-9d2e-547e-b615-44553508a81a | note | VERIFICATION ACTIVITY: QA FORM
a0b1bd11-6361-55e4-9f57-c5eb4ca409a6 | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
c32df728-ca88-5467-93f2-573972936a6b | note | FREQUENCY: Everysite
12c86a17-a53d-5e21-b0c9-5524332fcc8e | note | ACCEPTANCE CRITERIA: Kerb & Channel to be precast hand-laid. . Kerbing laid on 300mm min Gap 65 subbase in roads and 100mm GAP 40 in footpaths (CBR>5).Concrete 20mpa @28 Days
daba7c95-2885-5fb3-92a7-2172ceeccda9 | note | Hold Point: In process Inspection
a7f092a5-6dc7-5efe-a8a4-b2ada733d014 | note | Records: FH concrete QA sheet, photos. Concrete Plant Docket
58e62e1c-37bd-5ab1-8ed6-cb8ce8b3daed | note | Onsite Responsibility: Site Engineer
| checkpoint | 3 Channel Level
04c75814-f1eb-5e74-a6bc-687979668806 | note | VERIFICATION ACTIVITY: QA FORM
52cd32cc-bc2d-54a4-a8de-aa9253f929ed | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
2ef4b251-dd04-596c-b3ca-32dcc791c375 | note | FREQUENCY: Everysite
3d8f4d58-4ffd-50f4-a462-aa25b42ee3a6 | note | ACCEPTANCE CRITERIA: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
61f789f1-7114-55d1-a9f4-12d9aef6f059 | note | Hold Point: In process Inspection
d132bfd3-9dd9-5f55-b52a-c04bda96c137 | note | Records: FH concrete QA sheet
6616f82f-0a19-599d-a955-ac8d2b7389bd | note | Onsite Responsibility: Site Engineer
| section | Civil Works
| checkpoint | 4 Concrete Footpaths
09108c75-652a-51ab-a457-c54194f2a4ae | note | VERIFICATION ACTIVITY: QA FORM
cb4b4db8-5d2f-5c15-9b51-df1545a110a3 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
d8270b92-3ad0-5086-a878-227ee0191036 | note | FREQUENCY: 10m Intervals
10d7632c-d34c-5ee7-ae20-3f2be0476f98 | note | ACCEPTANCE CRITERIA: Subgrade -(CBR > 3); Basecourse - 100mm min. thickness GAP40; Clegg CIV > 13; Surfacing - Concrete 100mm and 20 Mpa @ 28 days. 4kg/m3 blackoxide with broom finish
373d404a-891b-5298-be69-b19d8160ca95 | note | Hold Point: In process Inspection
d87c7183-3ade-599f-8cab-bb57c5a7168e | note | Records: FH concrete QA sheet. Concrete delivery Dockets kept as record
86a36192-9b35-5096-ad2e-df0b6420b880 | note | Onsite Responsibility: Site Engineer
| checkpoint | 5 Concrete Pram Crossings (PX)
5649fcf2-b647-57f3-aa1c-78b529c73366 | note | VERIFICATION ACTIVITY: QA FORM
cdfa94c3-ad24-5927-a44c-1b6bc5456b77 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0006
d16216b9-3455-58f0-9153-6205e1a52302 | note | FREQUENCY: Each PX
9ea4788e-35a7-55ff-9bde-649c9e4dbe06 | note | ACCEPTANCE CRITERIA: Subgrade - (CBR > 3); Basecourse - 100mm min. GAP40 thickness; Clegg CIV > 15; Surfacing - Concrete 150mm and 20 Mpa @ 28 days. 4kg/m3 blackoxide with broom finish
9845b809-bf91-5aeb-91b8-8e134331772d | note | Hold Point: In process Inspection
4830c30a-4acd-5ead-852f-aaa896b96757 | note | Records: FH concrete QA sheet. Concrete delivery Dockets kept as record
9fdd09f9-cddb-5548-81cf-c6ba806d220b | note | Onsite Responsibility: Site Engineer
| checkpoint | 5.1 Concrete Pram Crossings (PX)
1926d4a1-a2ae-5c57-a300-a53e022be695 | note | VERIFICATION ACTIVITY: QA FORM
7c83d6cf-9c44-57c2-afbb-9aa862635398 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0006
efc7a520-b3f1-5378-8ae8-f2c4057814f3 | note | FREQUENCY: Each PX
de3de784-3674-5e2d-bc62-e5efab923c4c | note | ACCEPTANCE CRITERIA: Warning TGSI tiles should have 100mm concrete slab underneath
a5fa5a4a-56e9-5336-bcf0-2e8e3e7ae4af | note | Hold Point: In process Inspection, Measurement
95bbdea2-769c-5f67-8d46-435be8fe06d9 | note | Records: FH concrete QA sheet. Concrete delivery Dockets kept as record
50d095f0-5385-5efd-ae41-5361aee526cf | note | Onsite Responsibility: Site Engineer
| checkpoint | 6 Grass Berms
7d669ef3-518b-5076-86cd-4c4a880f9a3f | note | VERIFICATION ACTIVITY: Visual
23b7915f-ad06-5010-80a7-bf0334546652 | note | METHODS OR REFERENCE: ATCOP Section 12 Footpaths and Pedestrian Facilities
3ef6647e-5500-562e-bfff-7e5d99ffeb27 | note | FREQUENCY: 10m Intervals
6c4daa15-f718-5bec-910f-012ff201b659 | note | ACCEPTANCE CRITERIA: 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
6024d63d-ba04-51e4-9681-78b0c3498e0e | note | Hold Point: In process Inspection
88f46918-9fa3-5d77-99ca-1817c5282d71 | note | Records: Photos
5b96d5ff-66bf-586d-8a47-fa766d549694 | note | Onsite Responsibility: Site Engineer
| checkpoint | 7 Tactiles
3e7bf4e7-728a-5132-8710-ef5f750812b6 | note | VERIFICATION ACTIVITY: Visual
31fdae54-7791-5ef0-96a5-fe62e94be9fe | note | METHODS OR REFERENCE: NZTA RTS Guidelines for facilities for blind and vision impaired pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
0a62939f-426f-505d-9c74-9806dc8dcaa2 | note | FREQUENCY: Everysite
29013c46-7669-53d2-8250-310c4d794073 | note | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
82e1d73b-f91c-5263-8612-e0db02a60226 | note | Hold Point: In process Inspection
3a19a80b-f778-560f-8937-266076f20a5c | note | Records: Photos
10c84099-bedb-5702-8a3c-1cad3d46a7aa | note | Onsite Responsibility: Site Engineer
| checkpoint | 7.1 Tactiles
d9f2b062-2bec-5690-9c6c-1cfab0dab920 | note | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
ed7a4d7c-6ebe-50e4-9183-26f9c3e3cd43 | note | FREQUENCY: Everysite
4e0276f6-d22e-5b98-a4d5-b0538556cce9 | note | ACCEPTANCE CRITERIA: Edge of warning indicators to set back 300mm from the face of the kerb or lane, extend the full width of ramp and be 600mm deep.
6c9ba8c1-e233-51e2-ac5b-891dcbafa0f0 | note | Hold Point: In process Inspection
a3f40aa2-f5a8-545f-8882-0dd9c6c1ed92 | note | Records: Photos
d345bece-edfd-5f34-9243-db7d1369570e | note | Onsite Responsibility: Site Engineer
| checkpoint | 7.2 Tactiles
146e4317-08ad-538e-9b1e-51b1c0f87ba5 | note | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
1b83a998-b23b-554c-8c0c-3a7f88116149 | note | FREQUENCY: Everysite
8be958b0-e5cb-5acf-a8f4-17120423cb68 | note | ACCEPTANCE CRITERIA: TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
172ebfa9-b0ea-5931-9951-01fa947fa53d | note | Hold Point: In process Inspection
4cb61080-5852-5883-b26d-586ab07a1a8d | note | Records: Photos
fa34d376-3e38-5f5e-b42c-62f594a2c7fd | note | Onsite Responsibility: Site Engineer
| section | RAMM Data
| checkpoint | 8 As built information
78516180-81cd-51cc-95b8-761f9639fc1a | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
2a71c6eb-02be-500d-94da-3d1f69a7cfea | note | FREQUENCY: Every Site
58154f07-ff0a-5019-adc4-a70034930c43 | note | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
c2f351da-a3aa-5af0-b126-95f90bed971a | note | Hold Point: In Process Inspection
3e21d62c-5075-53af-ab4d-d8cf556fe061 | note | Records: Asbuilt records
02dbc33b-f793-5498-90ba-1c992fdddd4e | note | Onsite Responsibility: Supervisor and Engineer
| checklist | Graeme Ave - ITP - Raised Pedestrian Crossing | itp | ITP - Raised Pedestrian Crossing | 4c53c2e9-ffa0-412c-af33-09747135a1de
| checkpoint | 1 Permits
e3772de8-9031-4f31-ac21-e75bea8b05ab | note | ACTION (Hold, Monitor, Witness): H
0251b105-7c3e-404f-966c-4365ec6b0ccd | note | Detail: Obtain Permits
423efb66-1cf7-461b-aa01-94ca7be9198e | note | Frequency: As required
9fa73610-3bbb-45a0-9135-b8aab3924c81 | note | Inspection / Test Method: Document Review
3ef3c21f-98b8-4994-b1f8-92b53affc7ed | note | Conformance Criteria: Control Checklist - Fall Prevention (if applicable). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
2b797ee5-1f0c-467c-ade4-ba2ddfbb4fe7 | note | Records: Permit attached or permit number noted
| signoff | HOLD POINT
| checkpoint | 2 Pre-construction sign offs
54f2c045-9d7a-4375-aa56-28ea8db68f67 | note | ACTION (Hold, Monitor, Witness): H
4e5698ab-f4ec-4936-b50d-607229e2fa1d | note | Detail: Ensure that Sub-Contract and Supplier Agreements are signed
1c1c9e69-cd91-4794-96c8-dec58bea07d1 | note | Frequency: Prior to commencement
6b26cea4-7921-4453-9522-722f6681793a | note | Inspection / Test Method: Document Review
9db8ba76-81e0-4cc3-8961-318790cf01b8 | note | Conformance Criteria: Signed Subcontractor and Supplier Agreements
bcdf3872-9cb4-4366-9293-9c205b51047c | note | Records: Subcontract and Supplier Agreements
| signoff | HOLD POINT
| checkpoint | 2.1 Pre-construction sign offs
aedbe013-d502-4dd9-ba71-54f22adc0572 | note | ACTION (Hold, Monitor, Witness): H
f866abf6-7db3-4ca9-84e7-bd24f8a19eb2 | note | Detail: Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
c2abc95c-b900-4048-9f1e-11922f7a8609 | note | Frequency: Prior to commencement
43d58893-ebe2-4a2a-9607-c3e0ff05b85d | note | Inspection / Test Method: Document Review
529ff974-b64f-4b90-9bc3-619b1deef417 | note | Conformance Criteria: TMP is approved by CAR manager for each site and works are only completed within the approved dates..
48f4c14d-b5b5-4627-96e7-63bda9508cb1 | note | Records: TMP on MyWorksites/On Site
| signoff | HOLD POINT
| checkpoint | 2.2 Pre-construction sign offs
9f2360f0-9874-4b1b-830d-e0d23b121eab | note | ACTION (Hold, Monitor, Witness): H
cd90c7b2-068a-401b-b99d-c8ea923f07f4 | note | Detail: Ensure all Sub-Contractors and Suppliers go through FH induction
41cc387e-b077-4b0b-80f4-03711c8e9301 | note | Frequency: On site daily
b6be9723-5c9e-4d21-b32f-47f2def5ee42 | note | Inspection / Test Method: Induction
f6d28e7d-b7c9-40e1-943d-4b52e489e804 | note | Conformance Criteria: Supplier's and Subcontractor's signatures on hazard ID and pre-start documentation
ce0de8b2-0256-428f-81dc-3c1d627658a7 | note | Records: Hazard ID and Pre-starts to safety team
| signoff | HOLD POINT
| checkpoint | 3 Design
6803b7fb-3ae0-40f6-bf9c-0afbfb36c32e | note | ACTION (Hold, Monitor, Witness): H
6b4910e2-d74a-4463-ae24-6606cdcf85f6 | note | Detail: Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
db342fb6-fc2d-40c2-9836-bfb53c82b990 | note | Frequency: Prior to commencement
08fc29ec-f214-4fae-a270-81dcf78be152 | note | Inspection / Test Method: Document Review
36cb06a9-93f2-4f37-9415-57ddb5e47034 | note | Conformance Criteria: IFC drawings have been received by Contractor
1a56bdcd-7bd0-4668-853f-70f531d59af5 | note | Records: Check Drawing Register
| signoff | HOLD POINT
| checkpoint | 3.1 Design
c9181eae-ecb2-421a-9a51-e797628e3c20 | note | ACTION (Hold, Monitor, Witness): H
b8219358-95d3-4c86-ad73-58a874ef5f85 | note | Detail: Crossing to comply with AT TDM chapter Traffic Calming and TDM TC0010
e2e16105-fbb3-4b63-98a1-a95221c8bbbd | note | Frequency: Prior to commencement
fb733392-2074-4547-8937-eaebddb0d081 | note | Inspection / Test Method: Document Review
304e3706-680f-464d-aa5e-2f3ea11fff01 | note | Conformance Criteria: IFC drawings have been received by Contractor
501a2134-219c-461b-95ee-c4973a50429c | note | Records: Check Drawing Register
| signoff | HOLD POINT
| checkpoint | 4 Installation of Erosion and Sediment Controls
f41e9388-dd6d-4517-ade0-0d914ce0bfc0 | note | ACTION (Hold, Monitor, Witness): H
851aa34b-41b9-4f99-b8ab-f41adf29e983 | note | Detail: Ensure that Erosion & Sediment Control in place
556780fb-f2cc-4b54-a985-e01182ddfc10 | note | Frequency: Prior to commencement
245ef2d2-545b-4940-9d03-db159543f963 | note | Inspection / Test Method: Visual Inspection
05dcf38b-4fd5-4ef7-89a3-4e0b67c9955c | note | Conformance Criteria: Territorial Authority has approved the as-builts for the ESC controls constructed onsite and gives approval for construction to commence
1246346c-8d3e-4f2b-a65b-468acd0a3cbe | note | Records: Environmental Controls Audit
| signoff | HOLD POINT
| checkpoint | 5 Survey Setout
303a5f11-1b35-45bf-8615-91046d3cef0c | note | ACTION (Hold, Monitor, Witness): H
9ce4ccb9-0c19-4d1c-adc2-308a118d44c9 | note | Detail: Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations)
f1c50ea2-c3a4-4b7f-8052-5a179e22e28c | note | Frequency: Prior to commencement
8364b1d8-be60-4e87-9496-94ef7826cc3b | note | Inspection / Test Method: Survey + Smart Level
d6fb3aee-4c30-4e47-8727-3a3240cff503 | note | Conformance Criteria: Consistency with Construction Drawing
8a8910df-2f5a-4435-a309-95f27bb0d4d9 | note | Records: Site Photos post surveying
| signoff | HOLD POINT
| checkpoint | 6 Locate Existing Services by Hand Digging
82e95836-520f-4bec-88bd-322098aa4b12 | note | ACTION (Hold, Monitor, Witness): H
13b57a33-92f1-49e5-ba65-4cf854547b4e | note | Detail: Ensure all services conflicting with the line of trench has been exposed by hand digging
49396fdb-fa6c-4e6e-90b1-3c2dc434c8a3 | note | Frequency: Prior to commencement
1967fa22-045f-4cd8-9e16-81a64e68d942 | note | Inspection / Test Method: Potholing
f52e67ea-fb62-47a6-bbf1-638412072063 | note | Conformance Criteria: All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. As-built all services
3f46b59f-245a-46c8-9338-2deb437a5042 | note | Records: Digging and excavation checklist, service planes, As-Built Drawings Doc. Review
| signoff | HOLD POINT
| checkpoint | 7 Material Compliance
205effa0-49cc-4488-bbf0-8a1f66bb3055 | note | ACTION (Hold, Monitor, Witness): H
dfbdd436-e240-44a0-984b-8a5629fa6372 | note | Detail: LESA dowels to be used at all construction joints
543af136-9426-4f7d-984d-292b4fa07692 | note | Frequency: Prior to pouring concrete
41e028b0-47fd-4259-98ef-d6b7796df90e | note | Inspection / Test Method: Document Review
ecc6472d-3557-4a8c-8da6-8dbfbfc98b26 | note | Conformance Criteria: Photos + Delivery Docket added to QA folder
bd4ec2d1-39d6-4fac-9e4d-e4b41213e6e2 | note | Records: Delivery Dockets / Photos
| signoff | HOLD POINT
| checkpoint | 7.1 Material Compliance
35005638-4a31-472c-aae4-4199a6f863c5 | note | ACTION (Hold, Monitor, Witness): H
6763146f-d4ee-45a3-a339-e6636b0a19e1 | note | Detail: 0.25mm polythene layer placed across all surface area at bottom of raised table
a8a179fd-2ae9-4627-a0b9-5ea9b84aeeff | note | Frequency: Prior to pouring concrete
1f136df4-3fb3-4fd8-afda-7e68c02be98a | note | Inspection / Test Method: Visual Inspection, Document Review
19de9bff-3dc0-4d83-96a2-da243af2693c | note | Conformance Criteria: Photos + Delivery Docket added to QA folder
2cdaf490-caac-4ec1-bd9e-7054cdb7538c | note | Records: Delivery Dockets / Photos
| signoff | HOLD POINT
| checkpoint | 7.2 Material Compliance
ebf621ac-0006-4446-a3c1-72d8387e0029 | note | ACTION (Hold, Monitor, Witness): H
0ad11bd6-d228-441d-a7f8-6e49e5bf26dc | note | Detail: 30mm thick compacted layer of AP20 aggregate placed underneath polyethene layer.
70162f9f-4d59-4974-ba7a-84c47d42f767 | note | Frequency: Prior to pouring concrete
1bee1a06-8ba5-4971-96b0-2a07853ee701 | note | Inspection / Test Method: Visual Inspection
12622c4b-0c31-4240-ab16-516fc8872a14 | note | Conformance Criteria: CIV >15
1d41b38f-be2c-4736-8b24-f65f094057c8 | note | Records: Delivery Dockets
| signoff | HOLD POINT
| checkpoint | 7.3 Material Compliance
e3098afa-5ce5-49ff-b5f9-4a55dc7e301d | note | ACTION (Hold, Monitor, Witness): H
9156e99a-518e-4611-b2c1-c492eec2f2d5 | note | Detail: Two layers of 663 mesh 50mm cover from top and bottom to be placed inside with 70mm plastic chairs separating.
b89e8fa7-79d3-4aee-a99b-fb82e49e51d3 | note | Frequency: Prior to pouring concrete
30e51180-914c-4cc5-b45d-ea8f1ac1c72f | note | Inspection / Test Method: Visual Inspection
dbad7283-bac3-4267-b4d4-7cc169e3a8f2 | note | Conformance Criteria: Photos + Delivery Docket added to QA folder
3fb22059-fa4d-431f-857b-41352b65c77a | note | Records: Delivery Dockets / Photos
| signoff | HOLD POINT
| checkpoint | 7.4 Material Compliance
ea54a2ff-1ac7-4581-aa6c-a6b2dbf2cf67 | note | ACTION (Hold, Monitor, Witness): H
3dfc93ae-2cde-4c6a-90bb-6928502767ad | note | Detail: All concrete delivered to site shall have 40MPa 28 day compressive strength with 4kg/m3 of Black Oxide Powder
6c13f93d-c363-4795-8c5c-e9e59cc52835 | note | Frequency: Prior to pouring concrete
b5c5f05b-a7b1-4e0a-880f-647a988ec13c | note | Inspection / Test Method: Concrete Delivery Dockets
f427c388-666b-4149-8164-67d593c0c36c | note | Conformance Criteria: Delivery Docket added to QA folder
d05a7f31-f68b-40ff-96bf-fa7d162839fd | note | Records: Concrete Delivery Dockets
| signoff | HOLD POINT
| checkpoint | 8 Temporary Works (Formwork)
dc656339-11fa-46ff-b168-73de4d130c5b | note | ACTION (Hold, Monitor, Witness): W
4d389484-0982-4a3d-b3ce-ffbf4184f679 | note | Detail: Formwork to be set to correct line and level
96ecffe6-da2d-4540-9d98-bc359eee7a5b | note | Frequency: Prior to pouring concrete
a7ba028f-2a32-4290-994e-48ad2eb1d2aa | note | Inspection / Test Method: Visual inspection
adc07e26-5741-4c2c-b432-4ef7367a0540 | note | Conformance Criteria: Concrete Inspection Record
3d031b82-4046-4192-8661-0e211044dbe2 | note | Records: Concrete Formwork Checklist
| checkpoint | 8.1 Temporary Works (Formwork)
9e5b4d31-5b12-473b-82ef-032867c7481d | note | ACTION (Hold, Monitor, Witness): H
f20f406e-1bf6-4efa-8b1f-5e0b487e7309 | note | Detail: Raised table formwork to be 100mm above existing road level and be 300mm in depth and gradients respectively of entry and exit ramps
14458b4e-9ceb-4485-a48a-260911ff6464 | note | Frequency: Prior to pouring concrete
60bafdad-c5b2-419b-886f-7019bd5c94a6 | note | Inspection / Test Method: Measurement
63a734e9-7895-4cdc-9277-8e5a1213b4ec | note | Conformance Criteria: Designer to inspect formation level
75e84d09-9195-4e1e-ae2e-6d007bb7a2df | note | Records: Site photos
| signoff | HOLD POINT
| checkpoint | 8.2 Temporary Works (Formwork)
49db2aa6-9c6a-4cec-bd39-2d5eb43bc2f6 | note | ACTION (Hold, Monitor, Witness): H
691e2f56-14c0-494b-b0ab-68c5450ec12d | note | Detail: Raised Table ramps to have 200mm depth at entry point and tie into 300mm depth to meet raised table
d31a423d-e3e3-43ca-b1e7-9e5c0be3735d | note | Frequency: Prior to pouring concrete
2c6ea28e-7dec-4c6f-93db-a49398f42575 | note | Inspection / Test Method: Measurement
05c76cb8-0f22-432a-bba8-8f769eead7e2 | note | Conformance Criteria: Designer to inspect formation level
846514d3-bd80-4522-b676-da0fba800447 | note | Records: Site photos
| signoff | HOLD POINT
| checkpoint | 8.3 Temporary Works (Formwork)
53daead9-9f52-4f09-8c53-4fa37bc833f6 | note | ACTION (Hold, Monitor, Witness): H
24b12bb8-5921-414b-9b6e-f51de766e036 | note | Detail: Raised Table ramps to be 1m across for entry and 1m for departure ramp. Toe to be 0.5m across for both entry and departure.
b7d17358-c008-400d-a2b8-eba6034a3939 | note | Frequency: Prior to pouring concrete
ce0a294d-7f9b-4ce9-84c0-6d13fb14afe0 | note | Inspection / Test Method: Measurement
644fc96f-69c8-4232-9e00-fff8d92371e8 | note | Conformance Criteria: Designer to inspect formation level
a92ca88b-5469-4a00-bef4-f927c8142885 | note | Records: Site photos
| signoff | HOLD POINT
| checkpoint | 8.4 Temporary Works (Formwork)
9a4315f5-a1e0-4657-a3a1-a543f69286c4 | note | ACTION (Hold, Monitor, Witness): H
8641573b-fcf7-4aa1-9471-f102648c8ddb | note | Detail: Raised Table ramps to be 1:10 gradient for ramps - Relative gradient on North facing gradient -11% and opposite ramp to be 9% relative to the existing road.
d2b83539-83e2-464d-8a54-8e18c9e82c01 | note | Frequency: Prior to pouring concrete
b1b3d16b-91d9-4799-b509-5205c897030e | note | Inspection / Test Method: Measurement
f9c2fcf9-4a3e-4eb8-a24d-9c07e547928d | note | Conformance Criteria: Designer to inspect gradient level
976efb25-ecde-4a15-b674-20624be064af | note | Records: Site photos / Concrete Formwork Checklist
| signoff | HOLD POINT
| checkpoint | 8.5 Temporary Works (Formwork)
bc2f182d-4ec3-4bb7-b317-4aa9479e0521 | note | ACTION (Hold, Monitor, Witness): H
dc5af71c-2f45-413b-85df-d4506299fd9f | note | Detail: The Site Engineer and MSQA Engineer must sign off the formwork prior to concrete being poured
ad3046ca-aafe-431c-b281-a5ce8628acd9 | note | Frequency: Prior to concrete pour
646b30be-9d75-4093-8417-e2ade8be01b6 | note | Inspection / Test Method: Visual inspection
4974acd6-027e-4e80-a93d-54757d3cc37f | note | Conformance Criteria: Concrete Inspection Record
60d1ec7b-ce1f-4191-8e16-0e0906d8a1f3 | note | Records: Concrete Formwork Checklist
| signoff | HOLD POINT
| checkpoint | 9 Reinforcing
688176f1-51c0-4bb5-904f-59a05960f09f | note | ACTION (Hold, Monitor, Witness): H
d869eccd-24fe-4234-aa79-cb13785303b4 | note | Detail: All construction joints are to contain 2 rows of LESA dowels or similar approved dowels . Dominator dowell system 50mm w/ Black 300*50*6mm plates @400 centres placed across the construction joint
74aac687-a812-44df-8f60-195960b45fbd | note | Frequency: Prior to pouring concrete
d46cb7bc-8c35-4b4f-b9e3-a2e40aae3304 | note | Inspection / Test Method: Measurement
eeb744b2-85ae-4603-9ca0-c883dbbac701 | note | Conformance Criteria: Concrete Inspection Record
e97488a1-061e-4a37-8ade-96d988610453 | note | Records: Site photos/Concrete Formwork Checklist
| signoff | HOLD POINT
| checkpoint | 10 Concreting
92296d26-548b-47d1-a9fc-4e45c5269423 | note | ACTION (Hold, Monitor, Witness): H
621452c1-a58c-47d0-b88e-7f40bfef2011 | note | Detail: The MSQA Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required
423166a3-ae0a-4ea2-aa34-ceadbc0fb0a9 | note | Frequency: Prior to concrete pour
4816b1ab-9e47-442e-b19f-a16b125aad5c | note | Inspection / Test Method: Visual inspection
c5328e23-17ac-48fd-aaaa-e5d5f048572a | note | Conformance Criteria: Engineer will be notified via email/SMS at least 24 hours before required for inspection
5e65da80-89b4-4987-a4ea-e79fdd5d8722 | note | Records: Email / SMS
| signoff | HOLD POINT
| checkpoint | 10.1 Concreting
6b5990d4-a6be-40ea-b8ab-3ba919693c7d | note | ACTION (Hold, Monitor, Witness): W
a099c204-6efa-4b01-a54e-5412360ea47b | note | Detail: Vibrator to be used throughout concrete pour
bf912907-3791-4170-80e7-3e174309808b | note | Frequency: When pouring concrete
cbd80b98-b359-4317-ab3b-87d0f249eb61 | note | Inspection / Test Method: Visual Inspection
8fb71db6-2c37-4288-befd-969173419ee7 | note | Conformance Criteria: Concrete Inspection Record
9d0987ab-eba9-4a99-a907-24c644d306ae | note | Records: Concrete Formwork Checklist
| checkpoint | 10.2 Concreting
95b75c4e-3f1d-47c2-97a4-316560b7dad3 | note | ACTION (Hold, Monitor, Witness): H
01cf754e-257b-4c77-b687-4678938f7077 | note | Detail: Concrete surfaces shall be U5 broomed finish
34852c3d-e42f-4d37-a485-518ea8b95dcf | note | Frequency: At completion of pour
00cc8241-3856-4bd2-ad4a-8621321eab9a | note | Inspection / Test Method: Visual inspection
65d8ae45-9383-4fe5-b08e-339181d3a295 | note | Conformance Criteria: Concrete Inspection Record
b64e8c26-e00b-4739-8b1f-9717152cb26e | note | Records: Concrete Formwork Checklist
| signoff | HOLD POINT
| checkpoint | 11 Curing
1d579aba-15a9-426e-9017-032775707ddb | note | ACTION (Hold, Monitor, Witness): M
79bdda79-962c-463d-9fe6-a1de53120da3 | note | Detail: Concrete will be left for 48 hours minimum to cure before traffic is allowed on it.
da9fa3e0-57d7-4105-8f21-aa1da4c4bc27 | note | Frequency: Post Pour
f2f5cca0-37f1-4610-87f9-0f8b4832f497 | note | Inspection / Test Method: Monitoring the time allowed for curing
b5d1ea64-0230-4907-b63b-91d9b1584e2e | note | Conformance Criteria: 48 hours minimum have passed
b281e85b-779d-4602-8b19-69c752c36e8e | note | Records: Concrete Formwork Checklist
| checkpoint | 12 Remove formwork
c7e17704-1911-472b-bf2d-72ab46e0bc34 | note | ACTION (Hold, Monitor, Witness): W
a99c8fa1-db9a-4487-a517-462db717d5a0 | note | Detail: Remove formwork after 48 hours
982a08b5-8213-45e2-af2a-1a7339cbfe6d | note | Frequency: Post Curing
35757059-fe65-4249-b915-3c514cb2f8af | note | Inspection / Test Method: Visual inspection
ffcd7ec7-b38e-4c4d-880d-f8c10fa16179 | note | Conformance Criteria: Concrete Inspection Record
c8c5bac4-cf68-48ea-821a-368cf7501033 | note | Records: Concrete Formwork Checklist
| checkpoint | 13 Asphalt- Concrete extension slab/ Toe
43586bb3-867a-4677-b5cd-5a839e099079 | note | ACTION (Hold, Monitor, Witness): H
43cb51bb-2d7c-4528-b601-05b688a64cd0 | note | Detail: One row of Lesa diamond placed mid depth @400 C/C along construction joint as per TDM TC003
b7ac0039-f604-4b7e-9d56-6f90ed4af0c1 | note | Frequency: Prior to pouring concrete
e5e10ec4-dd3e-41b6-b941-f689ac1d2b2c | note | Inspection / Test Method: Measurement
55aefa6c-c459-4be3-a649-53f69658823f | note | Conformance Criteria: Pre pour Inspection Checklist, Concrete Inspection records
9be4cc19-fe38-41c2-bda6-a6a46695d68f | note | Records: Site photos, delivery dockets
| signoff | HOLD POINT
| checkpoint | 13.1 Asphalt- Concrete extension slab/ Toe
1e8e9c8f-ff77-444c-82ca-e11ad3c7e310 | note | ACTION (Hold, Monitor, Witness): H
17efc7d1-240e-43bc-bd25-2ce607b8cd6e | note | Detail: 150mm thick 40Mpa Concrete with two layers of 663 mesh
6236faba-0cb2-4904-9703-8cd99bb1e8a9 | note | Frequency: Prior to pouring concrete
443a60eb-8b7b-4208-aa29-3e517c7c7d11 | note | Inspection / Test Method: Measurement
79ccb58a-d29b-4b7e-9723-77ac0743f4b6 | note | Conformance Criteria: Pre pour Inspection Checklist, Concrete Inspection records
04ba7ea4-3e2e-4258-96e5-60fffa099514 | note | Records: Site photos, delivery dockets
| signoff | HOLD POINT
| checkpoint | 13.2 Asphalt- Concrete extension slab/ Toe
3f97f870-9dfa-4b1b-8905-fc8109ccf122 | note | ACTION (Hold, Monitor, Witness): W
0e7d8e53-8003-4faa-9f9e-8179d3d08951 | note | Detail: Tack Coat between AC14 and Concrete slab
eec9b916-d426-4b84-ade2-8223301fa27d | note | Frequency: Post Curing
c821f634-0221-454c-98bd-ab2bca8c7674 | note | Inspection / Test Method: Visual inspection
d217415a-f55d-4b01-b84e-c2cda00effba | note | Conformance Criteria: Photos + Delivery Docket added to QA folder
54245f5e-6e21-4a69-838b-b3cd2508045d | note | Records: Site photos
| checkpoint | 13.3 Asphalt- Concrete extension slab/ Toe
75ad1a49-5878-44ed-9c7d-6f034e1ed124 | note | ACTION (Hold, Monitor, Witness): W
6e1c6461-446e-4261-b197-bb06a79ebabc | note | Detail: 50mm thick AC14
5bfac21e-2be8-48b6-b60b-a89a490d6365 | note | Frequency: Post Curing
9461ed70-067c-45b8-8808-5aa6307a050a | note | Inspection / Test Method: Measurement
3b69f42d-d522-485d-8da0-2bb892a7fb10 | note | Conformance Criteria: Photos + Delivery Docket added to QA folder
19abf383-0807-4a83-abec-79b7c89b5e82 | note | Records: Site photos, delivery dockets
| checkpoint | 14 Lot Number QA File
ebb9247f-383f-4bd2-ab35-d05926721d13 | note | ACTION (Hold, Monitor, Witness): W
ea8dd881-1efb-4a26-aebc-1c4e8c1bc332 | note | Detail: Ensure all QA Records, site photos and incident cases (OFIs) are closed and included within QA file
ca476484-9124-41ac-87ad-0fdbb154d40c | note | Frequency: At completion of Lot
10fafd7c-8141-4a82-85d9-b322b0203545 | note | Inspection / Test Method: Document Review
18d63bca-553e-4e20-99e8-a8c04b4f39e3 | note | Conformance Criteria: All QA files compiled and submitted to client
524faa11-41fb-4519-9fce-858b7b8671f0 | note | Records: QA records
| checkpoint | 14.1 Lot Number QA File
5183a539-db39-4b55-aa6e-61eee979ce9d | note | ACTION (Hold, Monitor, Witness): W
e2ab51f0-3803-4347-a29a-14ed8988f494 | note | Detail: Delivery Dockets to be included in QA file
1758994f-30b1-4745-8485-5bb173e6544b | note | Frequency: At completion of Lot
910a31ee-01d0-4a4e-9b0c-33b34234c173 | note | Inspection / Test Method: Document Review
477e50f3-f83e-4fdd-bdbf-57f52060909c | note | Conformance Criteria: Delivery Dockets to be included in QA file
893befc3-a11f-48d2-b452-62f4e995fecb | note | Records: QA records
| checkpoint | 15 As-builts
d13a786f-cd1c-49fd-9f62-dd1953e73d4a | note | ACTION (Hold, Monitor, Witness): H
3ca04f16-a973-42e4-95a6-e106b9304d9d | note | Detail: Red pen mark up drawings to be included in QA file
1261195d-7238-4003-8e8b-de43c68fe0e7 | note | Frequency: At the completion of the Lot of work
dbe918d8-2c0e-4bf5-88c4-6ba283af7360 | note | Inspection / Test Method: Drawings
5e8a8923-360e-4793-87f0-985be527068d | note | Conformance Criteria:
9b824be4-b391-4791-a14f-2db403414e5f | note | Records: As-built Drawing
| signoff | HOLD POINT
| checkpoint | ITP Completion
d0b6b882-7d12-4822-adab-c039b47f6bc0 | textbox | IFC Drawings used for Construction incl. Rev numbers:
bf7b73b4-fdd8-4b4e-aed8-509b589fc1f5 | textbox | Reference Documentation (Notices/OFIs etc.):
bcd61098-cc8c-42ed-bb37-fd6a838870ec | textbox | QA Compiled By :
537633ea-3b54-4fec-92fe-3469f44420e2 | textbox | QA checked By Discipline Manager:
dff82a78-b78a-443e-b5d8-e85b264a354c | textbox | QA checked By Quality Manager:
7c10f9d6-43b1-4856-8b13-4e941b195ae4 | textbox | Accepted By Design Engineer:
| checklist | Graeme Ave - ITP - Stormwater Drainage | itp | ITP - Stormwater Drainage | d4aa4c14-fcdc-4ab6-852a-267c01f23c45
| checkpoint | 1 Permits & Services
b7ec7a87-3953-4188-a75c-6c0f2e119de6 | note | ACTION (Hold, Monitor, Witness): H
ad5f1e43-52c7-44e1-9061-651cf401c3d7 | note | Detail: Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
925aa715-6553-493f-81ee-e4ec332149e6 | note | Frequency: Prior to any construction commencing
c55dad23-de86-46d7-8560-14474d013142 | note | Inspection / Test Method: Document Review
6b4610b1-7d70-4d0c-9de2-731cfde4e143 | note | Conformance Criteria: Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority
93d9f389-dd39-4921-90e6-5d70d5c032cf | note | Records: Permit attached or permit number noted.
| signoff | HOLD POINT
| checkpoint | 1.1 Permits & Services
d8fe82ab-864b-47bf-a9d6-7bc7e1be8c0f | note | ACTION (Hold, Monitor, Witness): H
116ae0cc-d56c-4cef-b276-f9e4992a0644 | note | Detail: Locate and mark out all existing services
be23b614-687f-4316-9b78-2c459195683e | note | Frequency: Prior to any construction commencing
aa7a04c4-37df-441c-986e-924f2698cd66 | note | Conformance Criteria: B4u dig procedure - follow utility protocols
2d7db214-9f55-4989-9de8-2063ad6c83c9 | note | Records: B4u dig plans & GPR report attached
| signoff | HOLD POINT
| checkpoint | 2 Pre-Construction Sign Offs
66945c5b-93bb-432e-aba3-a8fa39445b6e | note | ACTION (Hold, Monitor, Witness): H
6dd3afae-5fdc-40e0-addd-755a9366d752 | note | Detail: Sub-Contract and Supplier Agreements
ea47f085-5bd7-4f22-9d79-f9547b74ddb1 | note | Frequency: Prior to commencement.
a85c61bb-4146-4305-823c-e516dacee613 | note | Inspection / Test Method: Document Review
554a05b6-86d0-49e1-928a-882a306830ec | note | Conformance Criteria: Sub-Contract and Supplier Agreements to be agreed and signed
160cdefa-2fd6-4dd8-9df7-46df06d1decb | note | Records: Subcontract and Supplier Agreements
| signoff | HOLD POINT
| checkpoint | 3 Design
d5c72e03-034a-41e1-8ffe-65a463fdd064 | note | ACTION (Hold, Monitor, Witness): H
dc683c62-0ea5-426c-a727-dc6ce2dd0f46 | note | Detail: Design is approved and Drawings are of the latest revision.
6d59f248-9640-405f-860e-5fe7fc441ef0 | note | Frequency: Prior to commencement.
e841c7ed-b7e6-4ab3-beb6-f064ba2e39bf | note | Inspection / Test Method: Document Review
e0ccad98-e930-4311-8708-b25827c0595b | note | Conformance Criteria: Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
0a9aeb7c-3aeb-4c1e-b7d2-afd5d41f5de5 | note | Records: Drawing Register.
| signoff | HOLD POINT
| checkpoint | 4 Survey Setout
3a8209d7-3065-4acf-8afe-6b1dc718189f | note | ACTION (Hold, Monitor, Witness): H
1e4e0175-50f1-4836-8797-60a914e590f4 | note | Detail: Setout Pipe Alignment and Service Locations with inlet & outlet points and inverts as required to construct to design
bab53349-2b0e-41b2-aaf6-d0883defec6b | note | Frequency: Prior to commencement.
2ec43d8c-a143-450f-a13a-419d5f0cbe5d | note | Inspection / Test Method: Survey
573b55e1-a528-435c-a1da-1590277ea2bf | note | Conformance Criteria: As per Blue Barn Consulting Engineering Drawings: 02188-T-400 & Setout files
c2758e35-c837-4883-9739-2f927f3deb8f | note | Records: Survey Receipt.
| signoff | HOLD POINT
| checkpoint | 5 Pipe and Manhole Material Compliance
5e57cc77-cb04-48ee-80a2-9bb90e087c9f | note | ACTION (Hold, Monitor, Witness): H
1b951c79-7e83-40bc-b01b-83230cbbf37a | note | Detail: Cesspit, Manhole and Pipe shall comply with relevant AT/TDM standards
b86b784b-ff59-451b-9112-69e7eabe7cfd | note | Frequency: Prior to commencement.
f38d79be-7970-40b5-9c95-b0f197391be9 | note | Inspection / Test Method: Document Review, Visual Inspection
69f2354d-d35a-4979-8d61-50372e9f69be | note | Conformance Criteria: Pipe shall be Check for freshly formed pipes and return if required 1) DN225 Class 4 RCRRJ pipes AS/NZS 4058 2). All Concrete RCRRJ pipes to be fitted with Rubber rings 3). Pipes shall have product certification (ISO Type 5) to AS/NZS 4058 Prefabricated concrete Manhole shall be in accordance with TDM Standards & AC COP
f62d0ff4-d2d3-4fcd-a490-eef89723d455 | note | Records: Manufacturers Data Sheets, Delivery Dockets
| signoff | HOLD POINT
| checkpoint | 6 Locate Existing Services by Hand Digging / Hydro Vac
05c12c8e-2691-4b4c-9000-e7e3714cc7b4 | note | ACTION (Hold, Monitor, Witness): H
807cee40-0fd7-41d0-aae6-085b32a67138 | note | Detail: Ensure all services conflicting with the line of trench have been exposed by hand digging.
9dff6fef-83e7-4460-9043-c749f20f74a1 | note | Frequency: Prior to commencement.
ea282c22-4f4c-46ae-81ee-09e0c404a403 | note | Inspection / Test Method: Potholing / Survey
4c7f2d95-1866-479a-81dc-b10e334f469f | note | Conformance Criteria: All conflicts have been located. New services and / or conflicts to be advised to Project Manager.
3bf0b62e-288a-4dd8-8f0c-c7713fd3f66d | note | Records: As-built Drawings. Doc. Review
| signoff | HOLD POINT
| checkpoint | 7.1 Trenching & Excavation
3c4f85f8-accf-4f7e-9d6b-7ddb8584588c | note | ACTION (Hold, Monitor, Witness): H
2bdfadb7-a312-4306-a130-c04743827681 | note | Detail: Excavation methodology
a900b1e3-664c-4667-b447-3b5cc62ad5d9 | note | Frequency: Daily
a7727bba-dd6f-4567-bf4e-788a60a9919c | note | Inspection / Test Method: Prestart review
788f8e63-886d-4172-bf33-f8c12d611eb3 | note | Conformance Criteria: The excavation, benching and shoring requirements shall be in accordance with Worksafe Excavation safety guidelines (2016)
4cd09fb3-8cac-4c16-b52e-1783bed95435 | note | Records: Prestart RCP
| signoff | HOLD POINT
| checkpoint | 7.2 Trenching & Excavation
0a231706-9abf-462e-95ca-6495862f9c9c | note | ACTION (Hold, Monitor, Witness): M
5ed268ba-f0b2-4d72-94ac-a42dd657a34d | note | Detail: Trench Profile - Width
0fa29df7-fcc3-44e0-8cb9-ce31de8f77c2 | note | Frequency: Daily / as trenching takes place. Different depth methodology
eab6a6d9-c90d-4184-9b76-86b0cdc54980 | note | Inspection / Test Method: Visual Inspection, Excavation methodology
8951f026-3f3d-4c16-bed4-d8038a3d78af | note | Conformance Criteria: Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing
0ad97960-d1ec-419e-be02-b484e8e795c2 | note | Records: Construction Photos
| checkpoint | 7.3 Trenching & Excavation
639ed2d1-2f4f-460e-b0f6-299f559bbc73 | note | ACTION (Hold, Monitor, Witness): W
8ae5f038-715d-48a6-b95d-9e019d66faf8 | note | Detail: Trench Profile - Depth
a980c10b-e150-46f0-a334-ca3977825d0f | note | Frequency: Daily / as trenching takes place.
c4aa66fd-f57c-4914-a6fe-23e805bf6820 | note | Inspection / Test Method: Visual Inspection, Measurement
3503bbb5-333f-4265-882b-ef6f478e9337 | note | Conformance Criteria: Trench depth varies according to long section and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings
6e5168a0-01b1-44a7-8d97-6b96f6c0067a | note | Records: FH Drainage Line Record / Construction Photos
| checkpoint | 8 Bedding for Concrete Pipe Laying & Manhole & Cesspit
6df61f31-ab55-41c7-af26-25a339ab3737 | note | ACTION (Hold, Monitor, Witness): W
a04e9e6e-6afd-4cdc-b401-61d60b453389 | note | Detail: Placing and compaction of Bedding Material.
a8069920-80ac-4df1-a222-60026049c7db | note | Frequency: Inspected continuously during placing and compaction of Bedding Material.
42970406-2f5f-4dd1-96bd-5737a0543f0e | note | Inspection / Test Method: Visual Inspection
0cdaf7cd-a658-47ad-85d2-c96f232dcc0d | note | Conformance Criteria: Bedding & Pipe surround material to be GAP7 or GAP 20 (Stevenson Quarry) or alternate material that complies with AS/NZS 3725
2b437bd1-f274-4007-be92-46b83744b29b | note | Records: FH Drainage Line Record / Construction Photos
| checkpoint | 9 Pipe Position Tolerance
d8da1ffe-bc30-4cea-b4c8-55f0b9ed94d6 | note | ACTION (Hold, Monitor, Witness): M
fc129e97-340c-4a49-a199-fa89e5ce8a9e | note | Frequency: At any point of pipe
da07c6ae-c50b-41c1-9bae-d574c0354a8b | note | Conformance Criteria: Position tolerance for pipe laying at any point along the length of the installation shall be within ±30 mm from the specified design.
d018aec5-a833-4a52-8a15-f00389a25291 | note | Records: FH Drainage Line Record, Survey Data.
| checkpoint | 10 Trench Backfill - Placing & Compacting
56e8b10d-7b1f-44b7-9f1a-1a5bc23373d5 | note | ACTION (Hold, Monitor, Witness): M
499bae44-505c-410a-9e0f-dd822013cad5 | note | Detail: Placing and compacting of Trench Backfill Material
ed4d79e3-8883-4dd6-9629-8b76e9270752 | note | Frequency: Throughout Trench Backfilling operation.
965c6718-b497-435f-8ae4-2586d5e145e2 | note | Inspection / Test Method: Visual Inspection
ffc18123-f027-4e2f-9bfb-7347a7dc948c | note | Conformance Criteria: Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm
9835e08a-0d74-4103-845c-1bd50870adc3 | note | Records: Construction Photos
| checkpoint | 11 As-Built Drawings
9a480ad1-8dfc-4395-b769-a5276929ece8 | note | ACTION (Hold, Monitor, Witness): W
a17a6e2c-bcc5-44aa-9f15-349d67aab1a8 | note | Detail: Red pen marked-up As-Builts of every 'Issued for Construction' AT drawings
595fb929-4b5a-4a08-b716-d265df471db0 | note | Frequency: Final As-Built Drawings to be completed within three months of the construction completion of the asset or infrastructure.
df8ef794-01ee-46e6-ab7a-a44a29f5455d | note | Inspection / Test Method: Drawings / Visual Inspection
03a11c25-22d5-4284-bb6e-e6027474ce77 | note | Conformance Criteria: As Built and GIS Data
97f9d110-b94c-4672-8f08-59bef070f3b0 | note | Records: Redline As-Built Drawings, scanned as .pdf files.
| checkpoint | ITP Completion
d5030a00-ac11-4f4b-a79c-114988f29b54 | textbox | QA checked By Quality Manager:
fe763a8f-dc87-412c-9251-64a35a6f6594 | textbox | Accepted By Engineers Rep:
| checklist | Halsey/Maich RAB - ITP - Concrete Speedtable |  | Concrete Speedtable | 6029d447-1159-4b55-a3b7-e47cc77209a7
| checkpoint | 1 - Permits
a3d7c0a2-faf8-5a2a-a369-747714b508f9 | note | ACTION (Hold, Monitor, Witness) - H
c00aed18-ec0b-57c0-98c0-5c4d6e5dde14 | note | Detail - Obtain Permits
480e5eac-8004-508c-a94d-b7e15c0ad104 | note | Frequency - As required
d51529e7-420a-58f7-a01a-4724345c5b5a | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
222618c8-ef8e-55b8-8e17-a3192d18e7ea | note | Conformance Criteria - Control Checklist - Fall Prevention (if applicable). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
5a22fc9c-1517-5a56-970a-2312c2bd4c33 | note | Records - Permit attached or permit number noted
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Pre-construction sign offs
050ab25f-2fab-5ee0-9eb4-b5cce4a452c4 | note | ACTION (Hold, Monitor, Witness) - H
82316814-8337-5cf1-b036-430a95a6f6ae | note | Detail - Ensure that Sub-Contract and Supplier Agreements are signed
7ff2cc82-0f11-5c6b-aad7-9af62fa09b3a | note | Frequency - Prior to commencement
830a0e51-d427-5ee3-bfc2-b87494867243 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
36f1f15c-1fe4-511a-8be6-b0983f168d84 | note | Conformance Criteria - Signed Subcontractor and Supplier Agreements
70685f1c-711c-5dba-99a3-ce3f74fffe03 | note | Records - Subcontract and Supplier Agreements
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.1 -
cb73371d-aa15-5fea-87bc-11c7d44cd2eb | note | ACTION (Hold, Monitor, Witness) - H
7972e538-3671-5791-bd8d-6fbb9b63203a | note | Detail - Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
569a30c5-776a-58b2-96d9-299dfc91aa1d | note | Frequency - Prior to commencement
120a60f4-0f69-548f-9c64-f737f0321b53 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
0a144905-094a-54b0-859d-d9aaf3ad0875 | note | Conformance Criteria - TMP is approved by CAR manager for each site and works are only completed within the approved dates..
0013b39d-782b-5528-b37b-0b314b085f4e | note | Records - TMP on MyWorksites/On Site
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 -
0c640a71-6f2c-5360-beb3-c4851b9fcbd2 | note | ACTION (Hold, Monitor, Witness) - H
454f1ea6-2c21-50eb-bcd4-29ab96be59c0 | note | Detail - Ensure all Sub-Contractors and Suppliers go through FH induction
c14f9eaa-25d4-5340-836e-d181565116e2 | note | Frequency - On site daily
be2716a4-acac-5e38-a77f-8aaaef78bb30 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Induction
7d90da74-2531-54b4-9411-dfb2d0cbf5a6 | note | Conformance Criteria - Supplier's and Subcontractor's signatures on hazard ID and pre-start documentation
088ba123-2fdc-5ae4-9347-65db801cf192 | note | Records - Hazard ID and Pre-starts to safety team
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Design
ac35ecbe-6d5f-50be-9c8a-6797979301c4 | note | ACTION (Hold, Monitor, Witness) - H
f8e1cc66-ada0-5853-9c9b-9b5fd4bb480b | note | Detail - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
1125f9b0-a763-5cb4-8efb-5e6084db9d87 | note | Frequency - Prior to commencement
e65dd631-a0dd-5e51-94f4-25a3f7fc6bcd | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
cd644869-5f75-5a21-a21f-20b6b6fb383a | note | Conformance Criteria - IFC drawings have been received by Contractor
2c9ff25e-814e-5291-a277-e377730afbca | note | Records - Check Drawing Register
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Installation of Erosion and Sediment Controls
6ccbc7c4-e14b-5c2c-a09f-d6e743623463 | note | ACTION (Hold, Monitor, Witness) - H
b16a0287-1faf-545b-9fff-ea5eb326afda | note | Detail - Ensure that Erosion & Sediment Control in place
4249f251-3f75-5aa5-8a54-97b7046cdd0e | note | Frequency - Prior to commencement
ff2a924f-b80e-5c9f-8529-bec72384fec6 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
0226af5f-4643-5506-9af4-b1ec7ff6c9fc | note | Conformance Criteria - Territorial Authority has approved the asbuilts for the ESC controls constructed onsite and gives approval for construction to commence
7d5ba5cd-ee14-5b28-a5db-14dc23622a4d | note | Records - Environmental Controls Audit
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Survey Setout
efb3a1e2-9ce3-5c49-ad27-07a4b837843d | note | ACTION (Hold, Monitor, Witness) - H
59d2c2c5-a30f-596f-bd74-c9f05aa8de26 | note | Detail - Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations)
643cd3a2-3f83-543e-964f-46d411036c5b | note | Frequency - Prior to commencement
7318be6c-010c-59aa-8106-0c2991fc800c | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Survey + Smart Level
eae06f90-42f3-57c4-9f7d-d3c9ec3ed7d1 | note | Conformance Criteria - Consistency with Construction Drawing
d6b86a25-dba0-51d9-afc3-9b79b36fc722 | note | Records - Site Photos post surveying
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Locate Existing Services by Hand Digging
affc6c61-afa5-538e-9a17-f7ecdf794c12 | note | ACTION (Hold, Monitor, Witness) - H
9421575e-7718-5f23-b55c-454a758d3fc5 | note | Detail - Ensure all services conflicting with the line of trench has been exposed by hand digging
05248dc5-80eb-57c6-a8c2-929756bf7aa7 | note | Frequency - Prior to commencement
0acdb4db-1819-501e-96c0-5369eac37c9d | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Potholing
3a317abe-fefc-5310-a774-f48e71d8b27a | note | Conformance Criteria - All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. Asbuilt all services
e6751289-836e-55e7-b96b-7be8cfe68448 | note | Records - Digging and excavation checklist, service planes,As-Built Drawings Doc. Review
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Material Compliance
e91b2830-c669-595b-ada9-9cb13cc0013b | note | ACTION (Hold, Monitor, Witness) - H
4fe1c0c2-01c8-55ee-807d-67a7ca5e10c3 | note | Detail - LESA dowels to be used at all construction joints at 600mm clearance
0e8e33f5-93b4-5a13-b6e6-e18366252af4 | note | Frequency - Prior to pouring concrete
982ecc7a-fbe7-5802-8ac8-7c1591f6f42d | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
1020e2fc-dc6d-5d1f-aa3c-816b398f4583 | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
f3cf4127-f77b-5ffd-8da6-a7f271a4bdb7 | note | Records - Delivery Dockets / Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.1 -
a82641ee-7da5-5fd9-b752-f11927b5a114 | note | ACTION (Hold, Monitor, Witness) - H
b1341c9d-e8f1-56c0-b9fc-07b5c2f9e576 | note | Detail - 0.25mm polythene layer placed across all surface area at bottom of raised table
2d6dc70c-e72b-5b8b-9f9d-e2a10a1b3e9c | note | Frequency - Prior to pouring concrete
a00b3ea0-78d0-5363-a817-ba8bb7dffbe3 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection, Document Review
a17d6bcf-344c-5d5b-af1a-d0ca32bb6a16 | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
658a9f99-40f6-5b2d-9e4c-b8060f409fbb | note | Records - Delivery Dockets / Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.2 -
91186963-1db8-593f-b86d-d324d9cbcb53 | note | ACTION (Hold, Monitor, Witness) - H
6cea52ad-aa4f-53e5-b2aa-3aa4d9a73b03 | note | Detail - 50mm thick compacted layer of AP20 aggregate placed underneath polyethene layer.
797ff7e6-16f8-5baf-b678-464d3c68859a | note | Frequency - Prior to pouring concrete
af66bc93-e2bc-5ebd-b001-8e13a1ffa0a9 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
b16faf2a-0f4c-58bf-ad37-9539da268f3f | note | Conformance Criteria - CIV >15
8f0bfbf2-fc0d-585a-8fc5-50e1f2ecc053 | note | Records - Delivery Dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.3 -
1b246522-abc3-5516-b0c4-68c1dce7975e | note | ACTION (Hold, Monitor, Witness) - H
a9d778f4-6a66-5662-a5a9-d05d049ec396 | note | Detail - Two layers of 663 mesh 50mm cover from top and bottom to be placed inside with 70mm plastic chairs seperating.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.4 -
31e5c64b-5cac-5384-a5b3-98635875abf7 | note | ACTION (Hold, Monitor, Witness) - H
60dc3f6c-f881-5865-9dc4-a1759247f098 | note | Detail - All concrete delivered to site shall have 50MPa 28 day compressive strength with 4kg/m3 of Black Oxide Powder
35aa1bd5-2c5a-51ed-a295-d5c4d917f570 | note | Frequency - Prior to pouring concrete
8adc2eb2-6ccf-531a-861a-a447f78c0b55 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Concrete Delivery Dockets
eca4d011-d1ee-5141-a639-8353b0b4928f | note | Conformance Criteria - Delivery Docket added to QA folder
2c0fc66b-8746-5619-b0ba-aa4b6e8b32f4 | note | Records - Concrete Delivery Dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8 - Temporary Works (Formwork)
c82ac61c-5041-5b6b-8e92-5f177400d517 | note | ACTION (Hold, Monitor, Witness) - W
ff651f64-e03a-5317-86f2-c2a3037de8e7 | note | Detail - Formwork to be set to correct line and level
7ed0fb60-41e8-58d4-87df-76afa1dd79d7 | note | Frequency - Prior to pouring concrete
676d2a27-0920-5908-a8f6-4b8b0bca7fbb | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
e18d9829-7bec-5f0e-acf2-f986c90a83bd | note | Conformance Criteria - Concrete Inspection Record
9ab2522a-ce6c-5c98-a03a-4bba4fa2ae4a | note | Records - Concrete Formwork Checklist
| checkpoint | 8.1 -
af4108c6-ed0a-51e6-902b-14e95fbee5ae | note | ACTION (Hold, Monitor, Witness) - H
9f28e69b-6da0-52b5-839d-cc4edaf2b855 | note | Detail - Raised table formwork to be 75mm above existing road level and be 300mm in depth and gradients respectively of entry (1:15) and exit ramps (1:15)
bf903985-e39c-513a-adf7-c5c7e525eeb3 | note | Frequency - Prior to pouring concrete
5f3866e2-4095-5914-b2f8-a68d51a8b740 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Measurement
0d41b2ff-ca8f-53d9-a366-e8452a3d384c | note | Conformance Criteria - Designer to inspect formation level
faa60b92-e214-5f3f-973f-4ea424fd47d1 | note | Records - Site photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8.2 -
4b23fed0-7d31-5aed-a1cd-25ddf8e644c0 | note | ACTION (Hold, Monitor, Witness) - H
6d3094d0-1079-5263-a11a-0852e98c0091 | note | Detail - Raised Table ramps to have 250mm depth at entry point and tie into 300mm depth to meet raised table
751f0cd5-3c76-5667-91ad-ab9caf090c0c | note | Frequency - Prior to pouring concrete
bd80a18f-f2f7-5599-b007-9cedb5f60996 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Measurement
b34714bf-b66a-5201-a3d7-9c412ce24399 | note | Conformance Criteria - Designer to inspect formation level
40e72d95-2a63-55c5-8b54-37184c7c4de9 | note | Records - Site photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8.3 -
e6b43de1-3d5c-59d9-9ddc-18f3c6c89e68 | note | ACTION (Hold, Monitor, Witness) - H
3b4920c2-1593-599c-b72c-277fc410ed24 | note | Detail - Raised Table ramps to be 1.125m across for entry and 1.125m for departure ramp.Toe to be 0.5 to 1m across for both entry and departure with 50mm asphaltic wearing course
b7c86849-840a-5ef3-a587-621e87600504 | note | Frequency - Prior to pouring concrete
e6184790-962d-54a1-9393-dd0380459a89 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Measurement
be3e373b-45dc-5f3c-ad0a-e60f295e6299 | note | Conformance Criteria - Designer to inspect formation level
1e4d3a7d-2f63-5d0b-8425-831e59aeda71 | note | Records - Site photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8.4 -
a73f583e-7b41-5f46-98c6-e8d18a04e526 | note | ACTION (Hold, Monitor, Witness) - H
15ca70e7-39f5-51c3-b58d-c33fd0a997ef | note | Detail - Raised Table ramps to be 1:15 gradient for ramps at entry and exit ramps to be 1:15 relative to the road
6b705729-baa9-5ae0-93d2-9c48b329388e | note | Frequency - Prior to pouring concrete
7c370c15-9d18-5a9e-8d9c-25ea31d5e8c4 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Measurement
62fc1b18-6501-5284-8aed-413c566a50b5 | note | Conformance Criteria - Designer to inspect gradient level
b8513826-534b-5d49-9407-e80f828e6e51 | note | Records - Site photos / Concrete Formwork Checklist
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8.5 -
92d91029-1dc0-5d71-b135-ba41d3835dfc | note | ACTION (Hold, Monitor, Witness) - H
fd1fd8c6-ccb6-5c5c-a00e-d88b8f9cb398 | note | Detail - The Site Engineer and MSQA Engineer must sign off the formwork prior to concrete being poured
73a9a8e1-4ad1-5ad5-977f-24c938591846 | note | Frequency - Prior to concrete pour
674bc715-e1c6-5d1b-91e9-57761f28f3c8 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
fa1130a4-bcfc-5acf-9e83-6f6554286044 | note | Conformance Criteria - Concrete Inspection Record
ed8f546b-a82c-5a40-9682-5b8c30bcd833 | note | Records - Concrete Formwork Checklist
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Reinforcing
a5d85161-2480-52cd-942f-775669f65757 | note | ACTION (Hold, Monitor, Witness) - H
3bbf215f-0890-5d30-9ad7-c0840e6cb21a | note | Detail - All construction joints are to contain 2 rows of LESA dowels or similar approved dowels .Dowell system 50mm w/ Black 300*50*6mm plates @400 centres placed across the construction joint
936f5505-a412-5685-9cd6-53bd3efd20ff | note | Frequency - Prior to pouring concrete
a3da9c24-8636-5aa1-b743-0402ea30671b | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Measurement
24bb2e21-1af8-5901-a728-f3839a027996 | note | Conformance Criteria - Concrete Inspection Record
779588f0-7ebc-54fe-80e1-cc789a1f2628 | note | Records - Site photos/Concrete Formwork Checklist
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10 - Concreting
c831fb5f-9d01-5b16-8c26-e827eb54f0c6 | note | ACTION (Hold, Monitor, Witness) - H
40999f73-dd06-5ded-bd8c-9fef17eb611f | note | Detail - The MSQA Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required
c8107520-f58d-5b07-858e-65f04287bbac | note | Frequency - Prior to concrete pour
d0cd7ccb-b762-5123-8d60-12b5ca357217 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
0fd09365-802c-5c9f-84f9-517e5a8df5c8 | note | Conformance Criteria - Engineer will be notified via email/SMS at least 24 hours before required for inspection
134d4830-5ddc-53de-adca-ae2b48a9712a | note | Records - Email / SMS
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10.1 -
a758b7b9-3d0e-5717-87db-b76eab1ce3c2 | note | ACTION (Hold, Monitor, Witness) - W
4288441e-9910-5e81-833c-d4ac09813405 | note | Detail - Vibrator to be used throughout concrete pour
9875c12a-6c7b-56bd-bc16-c4b01fad1aa5 | note | Frequency - When pouring concrete
b9693773-311e-5416-b232-d2b8b6c5fec7 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
85de7d14-7f49-50ea-b954-9e8d5f811147 | note | Conformance Criteria - Concrete Inspection Record
7a56e556-4235-57d5-b23f-f04fee6c3060 | note | Records - Concrete Formwork Checklist
| checkpoint | 10.2 -
9b64dad5-f1ff-5dc3-afe6-14940aae3de8 | note | ACTION (Hold, Monitor, Witness) - H
efb64ee1-213d-5c1c-8844-e7c99b2c0512 | note | Detail - Concrete surfaces shall be U5 broomed finish for ramps, and exposed aggregate finish for table top.
7f957016-968e-5b4c-994c-8a4d2f210f34 | note | Frequency - At completion of pour
7bad9dc3-aeec-55d8-9c67-2e9519a4991e | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
66a2bb14-6374-5e95-a8dd-acd650072063 | note | Conformance Criteria - Concrete Inspection Record
9a414280-a244-56dc-bb52-bdeaf548777c | note | Records - Concrete Formwork Checklist
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 11 - Curing
f07155d9-3dd9-55bb-a75e-e65f8a584daa | note | ACTION (Hold, Monitor, Witness) - M
683af135-58f6-5243-85f4-e37bf84e4cf4 | note | Detail - Concrete will be left for 48 hours minimum to cure before traffic is allowed on it.
b89a17ad-cfad-5db4-b8c9-823f9ad7ab35 | note | Frequency - Post Pour
55ecc52d-00e4-5986-9bc6-1f615c5856c7 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Monitoring the time allowed for curing
fa9bd73f-2ba4-51bb-a59a-852a4ba0ff5c | note | Conformance Criteria - 48 hours minimum have passed
9af66ba4-1e63-5972-93bb-c1d0d7377441 | note | Records - Concrete Formwork Checklist
| checkpoint | 12 - Remove formwork
87d0bcbc-0c44-5855-8240-92a054f594fc | note | ACTION (Hold, Monitor, Witness) - W
ec7a7d83-c632-5a37-b636-c9bfb6d38d24 | note | Detail - Remove formwork after 48 hours
485604c4-37fd-51c3-b4ef-482b75ed51b2 | note | Frequency - Post Curing
27f97c77-faf3-5433-ae57-94d8cec25c06 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
930a1a18-2f61-598d-8b89-884c4f2a8a33 | note | Conformance Criteria - Concrete Inspection Record
076c7ba7-82ac-5c26-95ae-31152c548181 | note | Records - Concrete Formwork Checklist
| checkpoint | 13 - Asphalt- Concrete extension slab/ Toe
d4ea41b1-fc75-5628-8160-74cd6582ab80 | note | ACTION (Hold, Monitor, Witness) - H
8db1e2b6-e9f5-59e7-a03e-beabceaac8dd | note | Detail - Two rows of Lesa diamond placed mid depth @600 C/C along construction joint as per TDM TC003
e54bb9ca-3fe5-55c3-b3ab-f90091baccc4 | note | Frequency - Prior to pouring concrete
182862ee-de73-5631-b1b2-4b9450f1e574 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Measurement
f7a17d43-f00f-5cff-b011-66c6ba5342b2 | note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
5792b006-2ea2-5344-b3ca-dcca1a8aea9f | note | Records - Site photos,delivery dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 13.1 -
2e7dda5f-b8c3-5697-88b4-dad1098529ae | note | ACTION (Hold, Monitor, Witness) - H
77a7b42d-dc1d-520a-8e75-7a45c99cb326 | note | Detail - 200mm thick 50MPa Concrete with two layers of 663 mesh
8d21bd56-5d86-5e46-ba78-491d50889f2a | note | Frequency - Prior to pouring concrete
481f7072-4581-5f56-8457-a12c0637187a | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Measurement
498b9a88-a343-5cac-8ce4-7096d9d14a91 | note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
9da8e39a-d98e-59ec-93e0-0b9fbccb4b51 | note | Records - Site photos,delivery dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 13.2 -
8fba5f04-b8b1-5d65-82a3-9ef61d8c74c7 | note | ACTION (Hold, Monitor, Witness) - W
1500b25f-15eb-5da0-a311-ec28b0b514c3 | note | Detail - Tack Coat between AC and Concrete slab
cdcb883d-cbe8-5a8a-966f-6c76cdb46ea6 | note | Frequency - Post Curing
18c0776a-1245-5636-9487-dc96ecc2b341 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
94380c4d-1e1d-597f-9fdc-33de80f50f6b | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
9f95b444-3930-5f23-be8e-1bdcb0447760 | note | Records - Site photos
| checkpoint | 13.3 -
2ba77e2a-9c1c-5c4e-9af3-35cfeeaa7d61 | note | ACTION (Hold, Monitor, Witness) - W
36e8857a-c4de-5b3b-8c9a-98adf2888815 | note | Detail - 50mm thick DG10 / Mix 7
fd94851a-0bd7-5256-a883-82fdfffe8dfe | note | Frequency - Post Curing
10cf311d-281d-5069-b598-79affe56571d | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Measurement
bc9798bf-3d46-584e-b4c2-49d9c9d9c082 | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
4c5d72da-19a5-54ee-8088-3947f9928c33 | note | Records - Site photos, delivery dockets
| checkpoint | 14 - Lot Number QA File
5eed5326-6250-5d35-bfa9-f0b01c64a29f | note | ACTION (Hold, Monitor, Witness) - W
2b4b413f-d09d-5cfd-b10f-99d4c950d424 | note | Detail - Ensure all QA Records,site photos and incident cases (OFIs) are closed and included within QA file
fccb1b8d-9976-5d2c-8240-e7355f65cd87 | note | Frequency - At completion of Lot
5309daaa-0683-504a-b555-8e0442918a94 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
30c953a6-2543-598b-8c4f-c0586c2d0a51 | note | Conformance Criteria - All QA files compiled and sumbitted to client
17c32aff-a1d8-5831-a94a-fd4c2a277cb8 | note | Records - QA records
| checkpoint | 14.1 -
3fbd5cd0-a951-58cf-9d74-28584d422082 | note | ACTION (Hold, Monitor, Witness) - W
07844a6a-dc3e-5603-841b-2d0f2c19fe6f | note | Detail - Delivery Dockets to be included in QA file
599230c4-ac3f-533a-aac2-d92c1752f036 | note | Frequency - At completion of Lot
8bf0de6e-3214-5234-b798-a96c270df098 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
594d5961-99ae-5bdc-8c5f-375def337334 | note | Conformance Criteria - Delivery Dockets to be included in QA file
e2fba0a2-deb5-528c-b74b-eabae715a804 | note | Records - QA records
| checkpoint | 15 - As-builts
55e8c4d5-b3c0-5385-8a53-9d1636f4ad3d | note | ACTION (Hold, Monitor, Witness) - H
87ab7f4d-8c10-5de5-a43c-2e009f588f7b | note | Detail - Red pen mark up drawings to be included in QA file
d9391bc5-a97c-59ed-b574-c804bf32551c | note | Frequency - At the completion of the Lot of work
3f8fc941-160d-5e9c-b01d-f709cc6038f8 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Drawings
8d0846c4-6119-54d9-94f0-efdd38c159ba | note | Records - Asbuilt Drawing
| signoff | AUTHORITY HOLDPOINT
| checklist | Halsey/Maich RAB - ITP - Enabling Works - Footpath, Kerb and channel |  | Enabling Works - Footpath, Kerb and channel | 1689d1b2-64fe-414b-bf85-4aec14562790
| section | Site Set Out
| checkpoint | 1 - Site Set out
10977638-1625-53c7-a92b-f12c815a330e | note | VERIFICATION ACTIVITY - Surveyor
09313a9b-9f76-5da6-b129-078a3645311c | note | METHODS OR REFERENCE - Surveyor
c483eefd-fdf0-5a0f-86e3-e0f2dc71b491 | note | FREQUENCY - Everysite
a90c6f8e-c1be-5866-a999-02b4bc5c719b | note | ACCEPTANCE CRITERIA - Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criterea is acceptable.
dd166184-484a-55e9-9d20-f63c90921294 | note | Hold Point - Mandatory HOLD POINT -
68dd43ff-15f6-5c3f-8b55-056da8dbe9bb | note | Records - Onsite records/photos
d801a316-09f4-5ec9-87ae-26043ffccc71 | note | Onsite Responsibility - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| section | Materials
| checkpoint | 2 - Kerb & Channel
ca6eaee4-7bd3-593f-9d3e-a273b3b91ac2 | note | VERIFICATION ACTIVITY - QA FORM
d366edc6-b6be-59f4-b8ce-af35db2d68f5 | note | METHODS OR REFERENCE - TDM Technical Standards - KC0001
bdf1e016-f129-5d1a-aa4c-4b5fa6e20ccd | note | FREQUENCY - Everysite
046c9637-dd20-5c60-8d05-e581c5a8de8f | note | ACCEPTANCE CRITERIA - Kerb & Channel to be laid using precast hand-laid. On compacted GAP40. Concrete 20MPa @28 Days on 100mm GAP40
e741e130-ff47-5c8c-8738-4880a83f0c10 | note | Hold Point - Inprocess Inspection
52335437-a63e-5bc6-beaa-9829b9a73f96 | note | Records - FH concrete QA sheet, photos. Concrete Plant Docket
009a656e-8d39-507e-b37d-d282d381b535 | note | Onsite Responsibility - Site Engineer
| checkpoint | 3 - Channel Level
6adb15c9-c5f2-52f5-ac7d-7f8474c73df0 | note | VERIFICATION ACTIVITY - QA FORM
5aa50664-cc06-5ab8-af9b-a05606d9bf6d | note | METHODS OR REFERENCE - TDM Technical Standards - KC0001
6a14352a-403b-5e34-bc22-0b0531046a80 | note | FREQUENCY - Everysite
d1f3b24c-ad43-55ab-88fa-49553579193a | note | ACCEPTANCE CRITERIA - Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
3d83baa0-9d69-52de-8983-2d2c3943d47e | note | Hold Point - Inprocess Inspection
68069259-77c0-5406-abe3-6ae8078e86ca | note | Records - FH concrete QA sheet, Photos
6ab6d591-606e-5d6a-9a93-541accbb44bd | note | Onsite Responsibility - Site Engineer
| section | CIVIL WORKS
| checkpoint | 4 - Concrete Footpaths
b2c975a0-89d7-55cb-88d1-8d117333c5b4 | note | VERIFICATION ACTIVITY - QA FORM
3b499e6d-4a29-536b-9408-81b23f050aa2 | note | METHODS OR REFERENCE - TDM Technical Standards - FP0001
2651e231-d7e6-5532-a86f-9f5b9f935c09 | note | FREQUENCY - 10m Intervals
c1baf555-71fa-5f4c-8e38-c1b1e256c186 | note | ACCEPTANCE CRITERIA - Basecourse - 100mm min. thickness GAP40
bea19ec4-d318-555c-9d99-73cd30d89c61 | note | • Clegg CIV > 12
84fd2f33-50a4-54e9-85db-330b3c7a8d9b | note | • Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish
eaad7a27-7c5d-5fa4-9d43-debbdb410b31 | note | Hold Point - Inprocess Inspection
6024b409-0770-5247-8e16-719b0023db8c | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
731c6be3-9123-5fe0-bd87-5c697eb67140 | note | Onsite Responsibility - Site Engineer
| checkpoint | 5 - Tactiles
9fff2919-9a7c-540d-84ad-1ee144e471bf | note | METHODS OR REFERENCE - TDM Technical Standards - FP0010
36c3f4eb-0a36-584a-b2a8-c03a74195e25 | note | FREQUENCY - Each PX
0aff6bce-7bb4-538b-aaaa-4235a8219afe | note | ACCEPTANCE CRITERIA - Warning TGSI tiles should have 150mm concrete slab underneath
0640625e-ebc4-5b93-a639-aa31d2ca86b7 | note | Hold Point - Inprocess Inspection, Measurement
1c9012b2-13ab-5679-ad0b-7a4b9ad205cb | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
ad8061db-8459-5dd1-9aed-641b5bee911d | note | Onsite Responsibility - Site Engineer
| checkpoint | 5.1 -
372f1c53-6118-5e39-ba4e-8a30a3a67ef1 | note | VERIFICATION ACTIVITY - Visual
5290af57-16d5-5725-92fb-97bb5f04188f | note | METHODS OR REFERENCE - NZTA RTS Guidelines for facilities for blind and vision impared pedestrians
28d8fa26-d131-57d1-a7d3-aa2333495088 | note | • AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
941073b5-c32c-55f7-b74e-9eb6a4934afb | note | FREQUENCY - Everysite
e7dc2bfc-f856-54ca-8b66-85dcc711ced0 | note | ACCEPTANCE CRITERIA - Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
27a96295-4e8d-54f3-b820-3cafff56ad2a | note | Hold Point - Inprocess Inspection
aa1be699-d04c-512c-a13b-945dad3b27fd | note | Records - Photos
5e6fb141-b461-5ba3-adbf-c0b3816c29ca | note | Onsite Responsibility - Site Engineer
| checkpoint | 5.2 -
1ff3378e-677d-5ac0-9649-5356220f8f68 | note | METHODS OR REFERENCE - AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
bd32e448-c479-50ee-b303-278c2aff7065 | note | FREQUENCY - Everysite
ec3d296e-6a49-5a60-8886-30d8709e6f79 | note | ACCEPTANCE CRITERIA - Edge of warning indicators to set back 300mm from the face of the kerb or lane.
438858f8-09e4-5ff3-be5b-889ef694051a | note | Hold Point - Inprocess Inspection
e53dbca2-5155-5163-81bf-20b1cad37d6f | note | Records - Photos
58f113aa-8ab2-5781-a7fe-ae699eb8d618 | note | Onsite Responsibility - Site Engineer
| checkpoint | 5.3 -
dd2f8cba-9a93-585d-8358-a167ebcce95b | note | METHODS OR REFERENCE - AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
b1677563-b08f-55b8-87dc-5cd14e20c115 | note | FREQUENCY - Everysite
9685bc67-fdb5-5608-84f5-a323822e9350 | note | ACCEPTANCE CRITERIA - TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
d5667c7a-6fe5-558e-9574-383b933eac9b | note | Hold Point - Inprocess Inspection
8ed95bf5-e22f-5bfa-a75d-88fb3750d022 | note | Records - Materials Dockets
4f5d4930-53e8-5c92-b015-5276fd01a60d | note | Onsite Responsibility - Site Engineer
| checkpoint | 6 - Grass Berms
5f3a7c0d-431e-5228-8a60-64ff02c7395f | note | VERIFICATION ACTIVITY - Visual
f3f9b0a7-97b3-5192-92b2-f20f18618f4d | note | METHODS OR REFERENCE - ATCOP Section 12 Footpaths and Pedestrian Facilities
66e131e7-c2ac-58a0-9a54-63800d11ea6f | note | FREQUENCY - 10m Intervals
d424e7d1-0b1d-596c-afb8-398f354bbc2d | note | ACCEPTANCE CRITERIA - 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
98b56cd8-2b7d-53d5-b63e-a51af7c2c9a6 | note | Hold Point - Inprocess Inspection
11ef74ad-c380-50a4-b2cf-ba454bca07b0 | note | Records - Photos
5db74583-91a2-5bff-88bc-ecc2e88052db | note | Onsite Responsibility - Site Engineer
| section | 6
| checkpoint | 7 - As built information
a7f3d049-1305-5f6d-bf3d-5855b501303f | note | VERIFICATION ACTIVITY - RAMM DATA SHEET
1e01c51b-683a-5b15-833b-300ae727e0d8 | note | FREQUENCY - Every Site
ee5dd4f2-897d-5a5f-8d9a-b99fff79b2fb | note | ACCEPTANCE CRITERIA - As built drawings and Ramm Sheets Completed
107d67c1-e87e-5f94-ae9a-854ac058c192 | note | Hold Point - In Process Inspection
c8493b55-b54c-590f-8d34-11222fe7ea9b | note | Records - Asbuilt records
8cffca3b-1f5c-59d3-b96f-d1a6d5f81087 | note | Onsite Responsibility - Supervisor and Engineer
| section | ITP APPROVAL
| checkpoint-no-value | ITP Approval
b6413876-20e5-5e00-acaf-eb5b0c4b445f | note | Prepared by: Yeswanth Vemula (1/05/2023)
2d92f182-766e-59e4-b92f-95e112b6b343 | note | Approving Delegate: Daniel Tat (27/01/2023)
| checklist | Halsey/Maich RAB - ITP - Pavement Construction |  | Pavement Construction | 0af5a3e1-3f76-4dc6-8b71-0b7d947a7748
| section | Precom
| checkpoint | 1 - Permits & Services
ecd89b00-4258-5b71-8262-de5a7a11b732 | note | ACTION (Hold, Monitor, Witness) - H
89f7c429-787b-529b-b516-68d4685338b6 | note | Detail - Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
6a049b6f-a861-51b0-a1d5-082c8104cf57 | note | Frequency - Prior to any construction commencing
5eb00e2a-a594-59fe-98ec-d91d2a28a15c | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
132ed97c-0c7f-54b3-a567-457ba9bdef0c | note | Conformance Criteria - Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority
09a3e30b-af06-5f19-b908-e05aebee5f59 | note | Records - Permit attached or permit number noted.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1 - Permits & Services (2)
f8c3108d-82cf-5ea7-a5fa-b7eb8dba6b28 | note | ACTION (Hold, Monitor, Witness) - H
60f1fe91-c3c9-578e-b814-bbe7d3723942 | note | Detail - Locate and mark out all existing services
7227d345-7188-57df-bc7f-0c1aa0d5372b | note | Frequency - Prior to any construction commencing
8ce0d899-3f46-5ec1-b531-23fbff7bc0e5 | note | Conformance Criteria - B4u dig procedure - follow utility protocols
119b52a2-b0f2-5fa6-b0a1-023af403f48a | note | Records - B4u dig plans
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1 - Permits & Services (3)
8c1b576b-1742-5f4a-8342-d615cb93eab4 | note | ACTION (Hold, Monitor, Witness) - H
2ff1f7b4-659f-5974-b2eb-0e6a9a585386 | note | Detail - Approved TMP
fd95ff3c-f793-588f-99af-cc473453ee01 | note | Frequency - Prior to any construction commencing
cf401228-b2fa-5c8b-867f-698320fd5948 | note | Conformance Criteria - Approved TMP and WAP onsite befor establishing traffic management
0095a760-371c-5569-ba08-434880334fa2 | note | Records - TMP Plans
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Pre-Construction Sign Offs
fa37090f-4999-520d-b7a3-65f1a1ee0af7 | note | ACTION (Hold, Monitor, Witness) - H
12645261-e6d0-5885-90d2-4babb2e96cb8 | note | Detail - Sub-Contract and Supplier Agreements
a72d48a1-8d3f-5065-819c-c75e6fa5a4db | note | Frequency - Prior to commencement.
c666234b-668e-5a0c-a2a4-f445909d7936 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
93873cdb-82ea-5dbc-b118-0f45e7cd629e | note | Conformance Criteria - Sub-Contract and Supplier Agreements to be agreed and signed
2424981f-fcc6-55ee-b9a6-c80cd77ef7da | note | Records - Subcontract and Supplier Agreements
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Design
8a2d55d2-8f7c-5292-b1e1-edf13b544dcd | note | ACTION (Hold, Monitor, Witness) - H
feabdd99-cd5c-5366-86c6-41df5fc750c2 | note | Detail - Design is approved and Drawings are of the latest revision.
52a22fe0-934f-54bb-83a3-5929561712db | note | Frequency - Prior to commencement.
3b65d6ff-a7fd-5a07-9553-6cdcf158451d | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
6fa45ab1-58d2-58bc-ab30-9c27a54de2e1 | note | Conformance Criteria - Ensure that Design is approved and Drawings are of the latest revision.
3201c9c3-bc7e-543d-8f91-c1dabc852cf7 | note | • Drawings to be 'ISSUED FOR CONSTRUCTION' status.
b434b04d-c8f6-595b-ae6e-a3f8def0acbe | note | • HOLD POINT of not issued to IFC.
4509afa4-38da-5287-aed4-3855ffe07ad5 | note | Records - Drawing Register.
| signoff | AUTHORITY HOLDPOINT
| section | SAC Pavement & Surfacing
| checkpoint | 4 - Bitumen
68f75255-0d13-5747-9629-e30c1ba6d645 | note | ACTION (Hold, Monitor, Witness) - H
066a918b-77a0-5390-9b41-ada03261d9ac | note | Detail - NZTA M/1
9b25ff1e-7cbf-5116-a9be-aaaa8ca2f0d4 | note | Frequency - Passing all tests listed in Table 1 of NZTA M/1
b0ad2cad-3d53-5ebb-9e10-7540742609eb | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Testing
807f1016-43d9-53e6-b894-49d6874ef469 | note | Conformance Criteria - Passing all tests listed in Table 1 of NZTA M/1
08cfd5f7-84c5-5625-a287-6854e7fb8fa0 | note | Records - IANZ Lab results
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Asphalt Mix Design
40a889a4-777a-51e1-bd81-2d80d14dfc7f | note | ACTION (Hold, Monitor, Witness) - H
10392982-aa0f-504c-8d62-39be0a0d03ac | note | Detail - JMF approved
2b37eb51-1733-562b-8850-c2119663f3e1 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Review
86c4c883-9754-585b-8ef0-3e08bc77cabb | note | Conformance Criteria - AUSTROADS
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Production Tests
cf88b822-b2ac-5f0e-a602-a5cbe44e1ab7 | note | ACTION (Hold, Monitor, Witness) - M
79c0d356-76d1-5f19-8788-b7cd3ada535e | note | Detail - NAS 2004 & TNZ sup to NAS 2006, TNZ P/9P (M/10 Table 5.1)/
fc951b28-ec63-5739-8dde-9c2cdb6d5af8 | note | Frequency - 1 set every 300t
89418e5b-f53a-5ab7-bb1d-7f60f1c45396 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Review
e4f2a371-3132-5a41-a9aa-70ec96b79b7e | note | Conformance Criteria - NAS 2004 & TNZ sup to NAS 2006 TNZ P/9P or NZTA M/10 - Grading, Binder content, Max Density, Temprature
8f4335ac-765c-5a53-b4a3-07fd618c4a00 | note | Records - IANZ Lab results
| checkpoint | 7 - Check Weather Reports
303dea3f-dd3c-58d4-88e1-b79462edcb54 | note | ACTION (Hold, Monitor, Witness) - W
5a783ae4-516f-5cbe-81fe-448a95066d9b | note | Detail - No fog, rain or wet surface. Base temp greater or equal to 7 deg celcius
3b55cffe-b45a-52df-b6d7-f26ffe1241cf | note | Frequency - Weather call the day before
2e20e834-f7b6-5f9b-a33f-94164d643675 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual
0705ea3d-ad5f-5a5d-8fde-f93b7098c50a | note | Conformance Criteria - Forecast and thermometer
2c58e189-522a-5d93-82c0-862ef5b7fb53 | note | Records - Radar and Asphalt QA
| checkpoint | 8 - Pre-Seal Inspection
db2c46e4-c016-53f3-b542-5d0c57a21106 | note | ACTION (Hold, Monitor, Witness) - H
479bf882-888c-59e1-a7c1-0ceee5dee59e | note | Detail - Surface finish
16b70717-7336-5094-a2e6-2e5017d49c7e | note | Frequency - Continuous
1176ec81-9d72-5642-ac96-ed5429836803 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual
dd285702-4bc3-5e08-a4b5-acb9658a83ec | note | Conformance Criteria - The surface must be clear of deleterious material and not chocked with fines. The basecourse surface must present a stone mosaic surface with larger aggregates protruding and not appear damp
077d3198-2c5c-5ca2-856a-fe70d9d6eca4 | note | Records - Sealing QA
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Tack Coat
f3084355-a482-58c2-bdaf-84ba853e7c02 | note | ACTION (Hold, Monitor, Witness) - M
90981153-416d-56d0-bfdc-04575ce2206a | note | Detail - Minimum residual binder application of 0.3l/m2
3acc4ddd-f6ff-5743-a5c4-d5eb7e1d21d3 | note | Frequency - Each Run
5a317f83-05b0-5896-ace1-d79c5b61a7e5 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Testing & Visual
5eb5c51f-1116-5acd-a7b9-4f9bc6282fef | note | Conformance Criteria - Each spray of bitumen
8bdb78aa-cc2d-531a-9c1a-0738c3e87ff9 | note | Records - Asphalt QA
| checkpoint | 10 - Construct 50MM PMB AC14
028a7cdc-2879-514f-9ea5-99b74ae8aae8 | note | ACTION (Hold, Monitor, Witness) - M
449cbcdd-b61e-52f0-bc60-4c8bd169109d | note | Detail - NZTA M/10, NDM and Stringline
eff235db-54f4-5629-8c87-ce8ee5693035 | note | Frequency - Each Run
6877ed8c-4bf4-581e-a736-8ef2f86cf6d7 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Testing & Visual
77381468-7fc4-5646-9539-911fb28762ff | note | Conformance Criteria - Construct 50mm PMB AC14 . - Design air voids 4% and level tolerance of +10mm, 0mm. NDM testing undertaken in accordance with NZTA M/10
7222640f-9a28-5b3c-952c-21422266c868 | note | Records - Asphalt QA
| checkpoint | 11 - Construct 50MM HF AC14
79e01922-37e4-5b3e-8253-4b972bcc232f | note | ACTION (Hold, Monitor, Witness) - M
6436c7eb-389e-5574-9996-0b8ca5d7201c | note | Detail - NZTA M/10, NDM and Stringline
5eb44a66-c1d2-5b68-9357-93cf82bbf0a7 | note | Frequency - Each Run
c67fdcda-cddd-5db5-8518-9884a3bc7796 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual
f49d3a47-5d40-57d2-911d-37179193716f | note | Conformance Criteria - Construct 50mm PMB AC14 in 1layer
d6a63263-deae-5902-89aa-8115ce73768d | note | Records - Asphalt QA
| checkpoint | 16 - Construct 80MM AC 20
994c74f1-7d49-5914-8a30-9fb8bde6ac46 | note | ACTION (Hold, Monitor, Witness) - M
eb194b36-5944-595b-af77-9375dc739b7f | note | Detail - NZTA M/10, NDM and Stringline
ca6ec17a-234c-520b-8b98-342522e49581 | note | Frequency - Each Run
762b3fa3-84ae-5a0e-9cb7-1a71853f8e39 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Testing & Visual
c76815e6-90da-52e1-a96e-7e016880f1ff | note | Conformance Criteria - Construct 80 MM AC20. - Design air voids 4% and level tolerance of +10mm, 0mm. NDM testing undertaken in accordance with NZTA M/10
e6fa1d9f-040d-5fb7-8567-74f2391082a9 | note | Records - Asphalt QA
| checkpoint | 17 - Surface Finish
41637f97-2803-5167-9dd1-487bdf64affa | note | ACTION (Hold, Monitor, Witness) - W
36901ebc-187a-5fd3-8dd0-07a43a5d4dd1 | note | Detail - TNZ P/9P
bd9396ba-c1bf-52a3-8a3d-85a2831fae8f | note | Frequency - Each Lot
da637903-4ba4-5056-9a07-6da8a9d1dab9 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual
e0cfd3d5-0cbd-54eb-befb-02432151ec71 | note | Conformance Criteria - Inspection: Uniform texture, no roller marks, no bleeding, cracking or shoving, no crushing of the aggregate
7c555031-ac4f-56fa-a48b-53c935299afc | note | Records - Photos
| checkpoint | 18 - Reinstatement of Linemarking and RRPM's
05a805c0-b782-514f-8e1e-605d100202d3 | note | ACTION (Hold, Monitor, Witness) - M
50799c3b-0a6e-58d8-8617-77115be01371 | note | Detail - NZTA M7 approved (Class B or C as required for anticipated traffic level)
3b5a9a0d-75dc-57b2-99ad-babb08d7a929 | note | Frequency - Every site
5699909c-d446-56ec-919a-6f727909e454 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual
e1dee3b5-170a-59a2-840d-777788379d90 | note | Conformance Criteria - Carried out within 12 hours of each shift completed and as per the existing markings
78d4663d-ad3c-537a-8d30-336e457e8b08 | note | • Suitable Traffic Control to remain in place until pavement markings have been reinstated
912ff5a7-f070-5c76-a08f-110c67ff9da4 | note | Records - Photos
| checklist | Halsey/Maich RAB - ITP - Roundabout |  | Roundabout | fce87690-771a-4f22-ba9f-0c2c3fbef255
| section | Construction
| checkpoint | 1 - Survey Setout
fb0e7618-0e7c-5957-9bd5-52231192561a | note | VERIFICATION ACTIVITY - Survey
6a808e75-ff15-5e99-8d45-9c64caeaa1bd | note | METHODS OR REFERENCE - Setout Kerb Alignment required to construct to design
0008a52c-765b-5281-96da-9c59e7fc04a1 | note | FREQUENCY - Prior to commencement.
27b5e7a5-995d-5e61-ada9-227c1c780be8 | note | ACCEPTANCE CRITERIA - Survey
62a04765-95af-5511-994b-ae454acfcabf | note | Hold Point - As per Drawings
5ebf8eab-edda-5424-b0c2-02f1df0cdc38 | note | Records - Survey Receipt.
b2dca72f-2555-56ac-8c85-1b6ec0e8b0c1 | note | Onsite Responsibility - Site Engineer
| checkpoint | 2 - Concrete Roundabout - Central Island
5e76a7ba-c2c6-53dc-8665-a033f3389265 | note | VERIFICATION ACTIVITY - QA FORM/ Drawings
a111c3b4-897d-56b7-bc6f-9a3272ce4ecd | note | METHODS OR REFERENCE - Construction Drawings
b45f3b68-a473-5c1a-96c8-01ebe6cefa3e | note | FREQUENCY - Each Site
af730fb9-6a41-5c0a-9cc7-7f85d4e544b2 | note | ACCEPTANCE CRITERIA - Standard precast kerb to be hand-laid with 120mm reveal. Diameter to varies across with 2% cross fall.Kerbs to be sitted on 300mm Min AP40 Sub Basecourse, with CBR>5
a96e8f21-0a6b-51cc-a2c3-d14add6d7307 | note | • Central island to have 150mm GAP 65 Granular base course on removed pavement surface.
d10ca27c-6e9e-505f-8277-a120b460dee7 | note | Hold Point - Inprocess Inspection
4527f6c7-8b50-5d99-a511-1f5b27c5f0e6 | note | Records - Photos
bea27791-3972-58c4-933b-7978220201f9 | note | Onsite Responsibility - Site Engineer
| checkpoint | 3 - Concrete Infill - Central Island
aee87e25-8e84-5448-83c4-6ca695fad09f | note | VERIFICATION ACTIVITY - QA FORM
544edd09-b55e-5e32-baae-d0b3e15ca645 | note | METHODS OR REFERENCE - Construction Drawings
48134a99-a430-5a44-9d22-cb4e06b05cf1 | note | FREQUENCY - Each Site
fab51903-afff-5266-85cf-051737fd6beb | note | ACCEPTANCE CRITERIA - 180mm depth of 20MPa Unreinforced Concrete with 3kg/m3 red oxide and Broom Finish
56144e23-6785-5688-abd9-eb25b305bba0 | note | Hold Point - Inprocess Inspection
fd155c9f-bc21-513b-ba51-036ec0d014d5 | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
3a43ecaf-1155-5032-9c8d-5229d7f13996 | note | Onsite Responsibility - Site Engineer
| checkpoint | 4 - Apron
7950cc02-be0d-5c2c-b126-a79b0da7de2b | note | VERIFICATION ACTIVITY - QA FORM/ Drawings, Concrete Dockets
2578ec58-4ad0-5c88-9df7-83ec1ff80509 | note | METHODS OR REFERENCE - Construction Drawings, TDM Technical Standards - IS0007
25ef7c9f-7617-5a32-9cad-532c11d8b497 | note | FREQUENCY - Each Site
ad5a2140-f059-5bab-95da-121690853615 | note | ACCEPTANCE CRITERIA - Slip formed 25Mpa fibre reinforced concrete for roundabout edging
c252335b-2da7-5a1c-9695-962e5070e053 | note | • Kerbs to be sitted on 300mm Min AP40 Sub Basecourse, with CBR>5
5f6ae2b5-2f02-5a78-b1d0-e412978f1956 | note | • Apron to have 2% min fall towards the road and 2 m wide throughout.
75acfb11-b5c6-5744-979c-309d44ac2f6f | note | • Apron to have 50mm thick AC14 HF with 0.25mm Polythene layer on top below concrete
6873123c-0f47-51b7-b24d-afd2d44ee9d1 | note | • 195mm depth of 40 Mpa concrete with 4kg/m3 Black oxide and Broom Finish
2619e4c7-72d9-54c4-b460-101196e98985 | note | Hold Point - Inprocess Inspection
78719144-3af2-57e3-ad57-668786c6bd64 | note | Records - Photos of smart level/ Asbuilts, FH concrete QA sheet. Concrete delivery Dockets kept as record
f07d34a8-d111-5c8b-82f0-437797912cb6 | note | Onsite Responsibility - Site Engineer
| section | Asbuilts
| checkpoint | 7 - As built information
7c451498-a4f3-50fe-b462-a3298708ce48 | note | VERIFICATION ACTIVITY - Drawings
c092b679-93e3-55f7-b520-89b7cef67f26 | note | FREQUENCY - Every Site
7c0f1602-9c87-5561-af4b-0986287bdf9f | note | ACCEPTANCE CRITERIA - As built drawings
cf3f2bf2-529a-58f8-8819-e3fbce9a6e33 | note | Hold Point - In Process Inspection
9460e910-01b8-55d8-b768-53085a21b464 | note | Records - Asbuilt records
575ccb70-5b86-553d-b89a-7359a8c836ff | note | Onsite Responsibility - Supervisor and Engineer
| checkpoint | 7 - RAMM DATA
1e81e83a-dd8c-5fd5-9ba6-05443850a755 | note | VERIFICATION ACTIVITY - RAMM DATA SHEET
98d26b5b-f20f-5520-8c38-468db235c8d5 | note | FREQUENCY - Every Site
303e1a7f-d0c7-5f9d-aee6-02b3d898c9f0 | note | ACCEPTANCE CRITERIA - RAMM SHEET
aabb14b1-90b5-5f88-96a1-826170b309f0 | note | Hold Point - In Process Inspection
098c5713-7671-507b-8fbf-a6f09312139b | note | Records - Asbuilt records
dbf802a0-0ada-570d-a138-720ee409b3c9 | note | Onsite Responsibility - Supervisor and Engineer
| section | ITP APPROVAL
| checkpoint-no-value | ITP Approval
ee86fe3c-8f20-52d3-9996-e8037f3ae674 | note | Prepared by: Cimyona (4/02/2022)
3f0abf8c-3dd2-551f-b22f-962da9981e16 | note | Approving Delegate: Daniel Tat (4/02/2022)
| checklist | Halsey/Maich RAB - ITP - Stormwater Drainage |  | Stormwater Drainage | fba3b7be-026c-400a-bc02-9de4791e11b3
| checkpoint | 1 - Permits & Services
82d38025-9b2a-590c-a404-94c0cecbc760 | note | ACTION (Hold, Monitor, Witness) - H
5f6d9de9-7516-52db-9128-a99e8cd6fdc1 | note | Detail - Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
a474e32a-14da-5f4c-91bf-378527c9b1fd | note | Frequency - Prior to any construction commencing
f6ec15ea-22b6-57ed-b9b9-0e23e557b0ec | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
f1d1ef3d-7dad-51ad-8488-0f3ec4a72905 | note | Conformance Criteria - Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority
d0def003-2149-59a1-9d8a-1ee093728327 | note | Records - Permit attached or permit number noted.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1 - Permits & Services (2)
7cd5b1e9-c36c-547f-a3fa-dc3fec06553a | note | ACTION (Hold, Monitor, Witness) - H
11423f8e-39da-5773-bd2c-9dd8504a75d1 | note | Detail - Locate and mark out all existing services
e06cf240-a595-51d5-8239-42848edfa82c | note | Frequency - Prior to any construction commencing
22b257c6-9f8a-559e-af02-e7c8f74ca6f0 | note | Conformance Criteria - B4u dig procedure - follow utility protocols
e62a868f-5874-5b51-9d06-54d774151995 | note | Records - B4u dig plans & GPR report attached
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Pre-Construction Sign Offs
9a8ba019-eb5b-51bf-adf5-5b4817d5d0b4 | note | ACTION (Hold, Monitor, Witness) - H
591aba36-4846-5522-8f01-7a8d66970108 | note | Detail - Sub-Contract and Supplier Agreements
18b4a46a-42dc-5b31-ad35-6f24da7eb33b | note | Frequency - Prior to commencement.
8e46aae8-8a38-5809-8126-3790d2245274 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
50d159f8-f4f8-57dd-b2c6-a2a313338169 | note | Conformance Criteria - Sub-Contract and Supplier Agreements to be agreed and signed
436b3f9a-8071-586c-9518-c23d71b8f424 | note | Records - Subcontract and Supplier Agreements
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Design
4d814cf0-9c57-586f-8cc5-f3690ffe9e6b | note | ACTION (Hold, Monitor, Witness) - H
ec4be3d7-a54b-5b06-939d-737d6ac04136 | note | Detail - Design is approved and Drawings are of the latest revision.
1857180d-696a-5414-82e5-90a7bb088df8 | note | Frequency - Prior to commencement.
1c23c984-1f11-5065-8713-a8552db3c08f | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
5ecf5e44-f50b-5de2-8deb-310c907e222c | note | Conformance Criteria - Ensure that Design is approved and Drawings are of the latest revision.
b2c9aa87-15dd-522a-b5f3-37edf5c3d5e1 | note | • Drawings to be 'ISSUED FOR CONSTRUCTION' status.
cea50518-1c48-5758-8054-93b22874158e | note | • HOLD POINT of not issued to IFC.
8f63773b-4a49-52ad-889a-09e4a318d029 | note | Records - Drawing Register.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Survey Set out
c87a080f-e09f-51ee-ada0-d4d806532dfb | note | ACTION (Hold, Monitor, Witness) - H
620ffd51-7466-50ad-9a81-967ac1330a14 | note | Detail - Set out Pipe Alignment and Service Locations with inlet & outlet points and inverts as required to construct to design
021e4a18-dcd4-527d-bfbb-eff6250257a7 | note | Frequency - Prior to commencement.
d2ef42eb-5980-55de-87fa-2cff63ff59a6 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Survey
27e8e321-90ba-5d69-9927-2bff79a2fee7 | note | Conformance Criteria - As per BlueBarn Engineering Drawings: 02237.17-T-400 & Set out files
e006f6c7-9597-5cce-bc1c-bb7f528c52ee | note | Records - Survey Receipt.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Pipe and Manhole Material Compliance
2d130bbe-b3f5-5a34-8d92-19e591514178 | note | ACTION (Hold, Monitor, Witness) - H
da6b54d5-9400-5995-ad3a-6f0b34adfdf2 | note | Detail - Cesspit, Manhole and Pipe shall comply with relevant AT/TDM standards
81ed7602-30aa-5750-b01e-ae6721629dd8 | note | Frequency - Prior to commencement.
3191564a-0e3b-5130-a09e-d174a30a2ebf | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review, Visual Inspection
54244494-ee7a-566c-967e-0368d0284ae1 | note | Conformance Criteria - Pipe shall be
972dbc5d-f0c6-5099-8808-75a700f3433d | note | • Check for freshly formed pipes and return if required
45e00685-7134-5ff4-9437-086077b9bc97 | note | 1) DN225 Class 4 RCRRJ pipes AS/NZS 4058
5b9c7d58-2de6-56d6-a72e-4c27ed4b260f | note | 2). All Concrete RCRRJ pipes to be fitted with Rubber rings
88b563db-1b60-5a01-8392-fcf0f377ec7c | note | 3). Pipes shall have product certification (ISO Type 5) to AS/NZS 4058
97a9680f-7f7a-5a02-a90d-d7a340e4f218 | note | Prefabricated concrete Manhole shall be in accordance with TDM Standards & AC COP
4e8cca62-f77a-5092-ae45-3e960f53d1aa | note | Records - Manufacturers Data Sheets, Delivery Dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Locate Existing Services by Hand Digging / Hydro Vac
aac41f62-f32a-52d1-941d-1bb991731847 | note | ACTION (Hold, Monitor, Witness) - H
97167f8f-6914-55f2-88ee-620ff933ee07 | note | Detail - Ensure all services conflicting with the line of trench have been exposed by hand digging.
7b5bfb12-b0fb-5db0-a40c-3e10e37f10d1 | note | Frequency - Prior to commencement.
077413eb-8617-5567-83ce-ec2559f7e7af | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Potholing / Survey
fc0144e0-ad34-5d67-a0bf-a803ed01d150 | note | Conformance Criteria - All conflicts have been located. New services and / or conflicts to be advised to Project Manager.
0a08eef6-0f56-5871-bfbb-a5ec84133a49 | note | Records - As-built Drawings. Doc. Review
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Trenching & Excavation
122ba340-9748-55e9-990f-c13099f45122 | note | ACTION (Hold, Monitor, Witness) - H
f5b32caa-848e-5070-9aa8-367e1b2ee380 | note | Detail - Excavation methodology
607e265e-c6b2-5b90-9696-491980a263a0 | note | Frequency - Daily
8d780982-d8c3-5c9f-89c3-265d02f4b6d4 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Prestart review
979b9c0c-60f7-5aea-b3b8-9a470f06dfd7 | note | Conformance Criteria - The excavation, benching and shoring requirements shall be in accordance with Worksafe Excavation safety guidelines (2016)
16c388c9-ee52-573b-b9f5-24d97c8dedcf | note | Records - Prestart RCP
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Trenching & Excavation (2)
9c12ded6-63fe-5c01-8869-6f098a12b55c | note | ACTION (Hold, Monitor, Witness) - M
34ae6c6d-0894-5384-b6e9-1700cda1f9a5 | note | Detail - Trench Profile - Width
9bf6d40d-3f67-5623-bf9c-e7ff09880105 | note | Frequency - Daily / as trenching takes place. Different depth methodology
86531590-629f-54c0-a2d3-784fed82eb37 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection, Excavation methodology
8d0a468c-1b64-5f96-a2f6-68ee2483224f | note | Conformance Criteria - Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing
dac30131-b0ff-5d98-bb4a-708f6e687a8d | note | Records - Construction Photos
| checkpoint | 7 - Trenching & Excavation (3)
ce1df771-04fb-59d5-8ae3-be9897d8ba9c | note | ACTION (Hold, Monitor, Witness) - W
5a91fda8-df67-5be1-b6ad-b9588ae0a84c | note | Detail - Trench Profile - Depth
0afb0c41-2f2f-51d8-88f0-a4a0a30e3083 | note | Frequency - Daily / as trenching takes place.
4ade6378-3d57-5cfd-aa38-4b7e826b8097 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection, Measurement
0e6a44bd-67cb-53a0-9018-a2016dce9596 | note | Conformance Criteria - Trench depth varies according to long section and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings
c2c9a6b0-d3ac-560f-8c0a-1a5b31a6b6a8 | note | Records - FH Drainage Line Record / Construction Photos
| checkpoint | 8 - Bedding for Concrete Pipe Laying & Manhole & Cesspit
6aec941a-c42b-5f0d-b9e7-667839a42467 | note | ACTION (Hold, Monitor, Witness) - W
66c90076-1126-5dd0-8c1c-a1be97900974 | note | Detail - Placing and compaction of Bedding Material.
96c0a495-0b68-5e4b-9d65-8b27d7ce9418 | note | Frequency - Inspected continuously during placing and compaction of Bedding Material.
4dbcbfd2-9df9-5a9e-a93b-d460f064d129 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
e76a0a15-7b9c-5ad8-923f-584ead095ead | note | Conformance Criteria - Bedding & Pipe surround material to be GAP7 or GAP 20 (Stevenson Quarry) or alternate material that complies with AS/NZS 3725
7a60dea9-2744-52bc-9689-0c52b191e137 | note | Records - FH Drainage Line Record / Construction Photos
| checkpoint | 9 - Pipe Position Tolerance
54339542-6acf-52dd-ab0b-0339687ca06f | note | ACTION (Hold, Monitor, Witness) - M
d6e69034-509e-5787-9eb5-03f73e3f0ba8 | note | Frequency - At any point of pipe
80201d0d-b6c0-59cb-8ba0-40ae97dce7b0 | note | Conformance Criteria - Position tolerance for pipe laying at any point along the length of the installation shall be within ±30 mm from the specified design.
2a5f1f5a-1cd7-5c37-b206-fa8d88ff3eeb | note | Records - FH Drainage Line Record, Survey Data.
| checkpoint | 10 - Trench Backfill - Placing & Compacting
7230837d-eb03-5aaf-8c40-29ec79191f9c | note | ACTION (Hold, Monitor, Witness) - M
4a2fdd52-7426-5a4c-a349-5d06052e8341 | note | Detail - Placing and compacting of Trench Backfill Material
cdb0cccb-62bc-5225-9b3f-93e11b25b32e | note | Frequency - Throughout Trench Backfilling operation.
5b28714a-b3ec-50bd-a531-4bc06dc58ee7 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
909bb25a-b6e5-5c77-8bc4-d5598936875b | note | Conformance Criteria - Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm
993d5ba0-7aad-507b-982b-76b2a53cbdac | note | Records - Construction Photos
| checkpoint | 11 - As-Built Drawings
e94ba7b0-e7ed-5ba6-99fb-f56e6f0d737a | note | ACTION (Hold, Monitor, Witness) - W
197616ef-4770-5cdb-a580-0812ac8bcbe4 | note | Detail - Red pen marked-up As-Built of every 'Issued for Construction' AT drawings
e1a502cf-f400-5493-8f00-b075d12d0491 | note | Frequency - Final As-Built Drawings to be completed within three months of the construction completion of the asset or infrastructure.
8178030a-ab43-50af-b832-37ee8d806382 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Drawings / Visual Inspection
a5ccfc48-43ea-536b-a699-ade058443589 | note | Conformance Criteria - As Built and GIS Data
52c6e871-460b-580b-a55e-1e8c7013c0d9 | note | Records - Redline As-Built Drawings, scanned as .pdf files.
| checklist | Halsey/Maich RAB - ITP - Traffic Islands |  | Traffic Islands | 5c82c55b-b7ff-42a9-ac1c-dc4f39c70863
| section | Materials
| checkpoint | 1 - Mountable Kerb
c800d1b3-d6b7-5a63-8f4d-ff8be7169d06 | note | VERIFICATION ACTIVITY - QA FORM
9ad55792-fd4c-5db0-907b-00edea5fd5bf | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002
bf76488c-644c-5c99-b68d-dfae56bba4b5 | note | FREQUENCY - Everysite
105b9e84-4283-50ad-afbb-041109314578 | note | ACCEPTANCE CRITERIA - Mountable Kerb to be laid using precast hand-laid and painted with two coats of reflective paint
ea4df31f-72be-5167-b500-5d7d1db63997 | note | Hold Point - Inprocess Inspection
b50817ff-88a5-5036-9c2a-b893eb2938a8 | note | Records - FH concrete QA sheet, photos.
bb03e056-bc2c-5f21-a0a6-10f618f8ce1a | note | Onsite Responsibility - Site Engineer
| section | Construction
| checkpoint | 2 - Survey Setout
ebd64959-9b56-5039-84b7-bb0b090e41a7 | note | VERIFICATION ACTIVITY - Survey
a5958117-5afd-5308-94c1-aa3e32e41ea7 | note | METHODS OR REFERENCE - Setout Kerb Alignment required to construct to design
4f6d6d9c-c75b-51dd-8075-b0bcb19bb5ff | note | FREQUENCY - Prior to commencement.
2e8ca6e2-8027-58ae-8bee-b328fd93f495 | note | ACCEPTANCE CRITERIA - Survey
ee5db7ce-2d1c-51d8-80a4-24717eb59984 | note | Hold Point - As per Construction Drawings
1599448c-4a4d-5df3-9606-8c35b582aee4 | note | Records - Survey Receipt.
cfa86b15-ff20-5793-acdb-763bad36f832 | note | Onsite Responsibility - Site Engineer
| checkpoint | 3 - Concrete Island
e80c084f-8407-59ef-a970-08a744636a4c | note | VERIFICATION ACTIVITY - QA FORM
c27373b2-4d9a-57c3-ace5-d62ffe84a14f | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002
35a4b4cf-355c-5e6f-87d2-27a1a7ef7206 | note | • TDM Technical Standards - IS0001 & IS0003
5681bce9-1608-5a86-afba-ddcac08ae41f | note | FREQUENCY - Each Site
7db028da-fb63-5a81-8784-d96c4367e458 | note | ACCEPTANCE CRITERIA - Kerbs to be haunced with 20MPa Concrete
b5bbb022-57c7-5e15-a79e-f596edbd2d4e | note | • Basecourse to be 150mm min thickness of GAP65
0bc2478c-8728-5eb7-8e92-00e4437c4bf5 | note | Hold Point - Inprocess Inspection
ed0003af-55a9-5c34-8a2c-d92f104ebac0 | note | Records - Photos
9ea066d8-a16d-59c8-bce3-67247149ddfe | note | Onsite Responsibility - Site Engineer
| checkpoint | 4 - Concrete Infil
3a9bc23e-58d3-50ec-85b2-181b1b581e21 | note | VERIFICATION ACTIVITY - QA FORM
96cf2507-1270-5163-9c7a-496729c5a94f | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002
468f7ad6-4b8f-5431-a729-61817e6c20e7 | note | FREQUENCY - Each Site
417b37f5-2cfe-51da-b474-ef024ca060e6 | note | ACCEPTANCE CRITERIA - 180mm depth of 20MPa broom finish unreinforced Concrete with 3 kg/m3 Red oxide
ebbba178-0c92-5e11-aec1-dc4733d0198c | note | • Cross Fall of 2% or max rise in centre of 180mm
fbb42999-6f18-5ed6-9afc-136a4e6fe96f | note | Hold Point - Inprocess Inspection
fe26499e-8dc8-5cd2-aa7d-35b720fece99 | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
b3af4af1-badc-5cd3-8ea6-13d4d6798219 | note | Onsite Responsibility - Site Engineer
| section | Asbuilts
| checkpoint | 5 - As built information
13e2a0c3-a849-5d40-b5ca-33f939f7106d | note | VERIFICATION ACTIVITY - Drawings
c6d437e7-44b1-55d7-98fd-e7c5c1345cc1 | note | FREQUENCY - Every Site
0740e22c-2546-59e5-b169-a53a5c912ff8 | note | ACCEPTANCE CRITERIA - As built drawings
3f220194-ec73-5843-8baa-8aa278f62bfe | note | Hold Point - In Process Inspection
1dbf76aa-ee77-574b-8caa-243891df1abf | note | Records - Asbuilt records
c6223c7e-47ec-5384-8db6-8a48524efdf9 | note | Onsite Responsibility - Supervisor and Engineer
| checkpoint | 6 - RAMM DATA
11e6bf04-7fe7-5116-9715-8f393588c4cf | note | VERIFICATION ACTIVITY - RAMM DATA SHEET
aaa7d0ee-862b-5c66-8e26-04fc524eb841 | note | FREQUENCY - Every Site
4d6c1e78-c91e-5b57-91ce-d52a0777a4ed | note | ACCEPTANCE CRITERIA - RAMM SHEET
446fafb5-dfbd-5840-8f45-878c481d6ed2 | note | Hold Point - In Process Inspection
38ceca14-2a85-5022-acab-538b958a6554 | note | Records - Asbuilt records
c1b48114-920a-5323-a91a-b04d0a4e7f9e | note | Onsite Responsibility - Supervisor and Engineer
| section | ITP APPROVAL
| checkpoint-no-value | ITP Approval
3737207c-3f03-55a4-8a56-7cf0d06652a3 | note | Prepared by: Yeswanth Vemula (1/05/2023)
812fed8c-d1d1-50c7-a222-3942c0ccac53 | note | Approving Delegate: Daniel Tat
| checklist | ITP - Great South Rd - Concrete Speedtable | itp | ITP - Great South Rd - Concrete Speedtable | 9de6de66-3314-4919-aaf1-0f72fc601e0c
| checkpoint | 1 - Permits
f550ff1f-5636-5bfd-b932-89b6fc3f36e0 | note | H
55432e5c-1e49-5c0d-a79d-c3d0f429e448 | note | Detail - Obtain Permits
da3ca0af-24b6-5009-9e1a-ab006379ddf4 | note | Frequency - As required
db524c0f-33af-5c43-ab7c-f251798cad17 | note | Inspection / Test Method - Document Review
9b7630c2-2d09-5daf-ab2e-41bc86619b68 | note | Conformance Criteria - Control Checklist - Fall Prevention (if applicable). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
44c8eaa9-a80e-5db9-a77d-c121ab9f2ee5 | note | Records - Permit attached or permit number noted
e1b20a5e-957e-5cd8-9d38-53bd747be466 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Pre-construction sign offs
be18408b-f6d0-55ce-8801-5be60d297841 | note | H
7772559b-7c17-54bd-a829-2740251e1bca | note | Detail - Ensure that Sub-Contract and Supplier Agreements are signed
bec1b30b-6ed0-5795-9dd1-8e723eaca179 | note | Frequency - Prior to commencement
314e7942-6b62-523c-a798-3c20d09f59dd | note | Inspection / Test Method - Document Review
79940248-5602-5717-ac09-0204e75ac143 | note | Conformance Criteria - Signed Subcontractor and Supplier Agreements
212ed970-bfd4-5add-8561-a07935c76fe4 | note | Records - Subcontract and Supplier Agreements
b131f942-1eb9-5e7f-8906-10b78b833776 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.1 -
502e8ed8-619c-5e55-9694-a183679719b0 | note | H
1e7a7476-7ba7-5ddd-8b89-b65184daa2bd | note | Detail - Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
b42a1666-13d4-5d42-a5a1-b4e3a1573406 | note | Frequency - Prior to commencement
b62f6491-8344-5628-a388-0dd4dafd2b2e | note | Inspection / Test Method - Document Review
74ecc02c-2e8a-519b-9efd-76d7225b2f1d | note | Conformance Criteria - TMP is approved by CAR manager for each site and works are only completed within the approved dates..
3b6487f3-1394-5e3b-abff-de3e9c69993c | note | Records - TMP on MyWorksites/On Site
b7615ef7-67bb-5355-984a-0940c696fe4b | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 -
0f693450-b78f-54dd-bc7c-f6bd9e77b811 | note | H
b6d854fd-d232-52ec-af3a-5269817379ba | note | Detail - Ensure all Sub-Contractors and Suppliers go through FH induction
32a7805d-9f39-55a9-b8d8-41323fb3e9fc | note | Frequency - On site daily
a0010d4b-a293-53f1-a66e-b8740a2fb7b9 | note | Inspection / Test Method - Induction
4337bdd9-f0e3-5f2b-9252-a6407c22ad07 | note | Conformance Criteria - Supplier's and Subcontractor's signatures on hazard ID and pre-start documentation
4713a8e0-94ac-5414-a8ca-ec496b78c40c | note | Records - Hazard ID and Pre-starts to safety team
e4fbaf1d-ebb2-556c-90d8-edf3386e83df | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Design
dd0ebb54-23fe-5915-b8a6-ca1eff5a6734 | note | H
2ad6cd11-665f-5c51-a15a-eb8a5b3979e3 | note | Detail - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
f2efb68c-492b-5480-ade6-1ed97026def1 | note | Frequency - Prior to commencement
2220deab-5e51-5945-810b-99a30587574f | note | Inspection / Test Method - Document Review
98ae35d8-c221-5ad6-afe9-569bebf5213b | note | Conformance Criteria - IFC drawings have been received by Contractor
19d6f32e-dd8b-5127-a89d-442a8da70290 | note | Records - Check Drawing Register
26a240e1-abe0-5747-bb78-67fded30b6dc | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Installation of Erosion and Sediment Controls
e817a21f-7220-5142-8120-3e679dde8563 | note | H
e0b78d21-20ac-5b17-8ee9-083fd72f8f03 | note | Detail - Ensure that Erosion & Sediment Control in place
b8827f1a-c85c-5600-a705-188c88fbdabd | note | Frequency - Prior to commencement
0eac7c1a-dd21-5c88-b944-cae6b6f5d05c | note | Inspection / Test Method - Visual Inspection
988d4d11-5c17-5810-a898-ed09a5bf2807 | note | Conformance Criteria - Territorial Authority has approved the asbuilts for the ESC controls constructed onsite and gives approval for construction to commence
5241572a-3375-5efb-b3cb-7a83f291270f | note | Records - Environmental Controls Audit
78006230-50ac-57cb-ba62-a4ce37535feb | note | FH Initials - Environmental Manager/Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Survey Setout
83e0c40a-a1fc-5df7-9c63-8d7e3317a037 | note | H
86f8c966-0f5e-5eec-b858-97cf9a652111 | note | Detail - Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations)
8623b793-d01c-593a-8ce1-d0f400fcd87a | note | Frequency - Prior to commencement
c0303fd4-41bc-5eeb-8222-47dbfdf54b77 | note | Inspection / Test Method - Survey + Smart Level
afebe1eb-66f7-5a60-a130-03c2de302020 | note | Conformance Criteria - Consistency with Construction Drawing
65b0385f-85f9-5408-af14-a1820f83714c | note | Records - Site Photos post surveying
7cace66d-7599-55c0-aa97-843972986b7c | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Locate Existing Services by Hand Digging
bba2684e-d959-5f2f-b936-181f372b1cd2 | note | H
c835b629-de21-5571-8aa7-9f44d710717d | note | Detail - Ensure all services conflicting with the line of trench has been exposed by hand digging
bac79441-06c0-5619-bb9f-3d2602927f35 | note | Frequency - Prior to commencement
0423c433-eead-5ae2-b483-66ef776ce4aa | note | Inspection / Test Method - Potholing
5e1e106c-ae9b-50ce-bb2d-dc152a53e3ec | note | Conformance Criteria - All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. Asbuilt all services
5c78ed4d-3e22-5ced-8e06-c149e59cc7cf | note | Records - Digging and excavation checklist, service planes,As-Built Drawings Doc. Review
bd9bfbe4-0310-5d8e-b469-c953a5a93c2e | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Material Compliance
e1c353cd-cd02-56a4-aa03-55d8156b05db | note | H
c17b9b84-4eab-5921-b224-3309284b2e92 | note | Detail - LESA dowels to be used at all construction joints at 600mm clearance
73524019-394e-53c6-a520-3307eae607c2 | note | Frequency - Prior to pouring concrete
764b285a-baa1-538c-9f2b-a9c498d62e67 | note | Inspection / Test Method - Document Review
6a39ffe8-99b3-553c-a343-98168b9e5efb | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
15704476-1951-5d8f-9340-bed65b7df9f7 | note | Records - Delivery Dockets / Photos
6858fb57-94e3-5656-9c26-5ac54f52bfcd | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.1 -
90cbbc93-bc48-5bd7-8696-157ba0af59e9 | note | H
fb7d9d66-3926-5f0d-b605-48d00d4d38fd | note | Detail - 0.25mm polythene layer placed across all surface area at bottom of raised table
a311ca4d-6889-5f0e-ae41-a211cc3fd537 | note | Frequency - Prior to pouring concrete
ccdf5bfd-654f-5f12-83ca-668a1d58f826 | note | Inspection / Test Method - Visual Inspection, Document Review
4aa8183b-71b7-5859-b072-8a1968ae9f55 | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
2f78eaaa-77e8-5eb5-870f-05ef29f1e678 | note | Records - Delivery Dockets / Photos
d4a8dd91-1e97-542e-9034-769faf632585 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.2 -
0a9edd1e-78be-5a9f-a3fc-96f2a6b14b74 | note | H
2a0a7625-8ae1-5fe3-92f7-e04794342435 | note | Detail - 50mm thick compacted layer of AP20 aggregate placed underneath polyethene layer.
fa272419-2c9a-5840-a310-5e361b633795 | note | Frequency - Prior to pouring concrete
314b65e2-ed68-5000-ac22-d8eb3662c5a7 | note | Inspection / Test Method - Visual Inspection
f791a781-8859-5330-9342-1be946494503 | note | Conformance Criteria - CIV >15
68791d72-efa9-51e1-9acf-8eaa3cdc29e4 | note | Records - Delivery Dockets
c0dd1a70-eb85-50b9-9f45-90f5e5e4489e | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.3 -
c2f6b355-f9c7-569c-9f9b-9b922a2da859 | note | H
0e941f4f-7f6c-5e0d-b36d-7c2abd15cbae | note | Detail - Two layers of 663 mesh 50mm cover from top and bottom to be placed inside with 70mm plastic chairs seperating.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.4 -
c2c44325-19b0-5d93-aad5-5bc61e7c5faf | note | H
91037283-f5d1-592a-8465-a7fe402ddbc1 | note | Detail - All concrete delivered to site shall have 50MPa 28 day compressive strength with 4kg/m3 of Black Oxide Powder
f164bf24-450e-5b96-b724-7670bec583c3 | note | Frequency - Prior to pouring concrete
f253dc2d-b2be-5a04-b205-57bbb4b17aa9 | note | Inspection / Test Method - Concrete Delivery Dockets
68270bb5-1ab5-588d-b5e8-a996ae98141c | note | Conformance Criteria - Delivery Docket added to QA folder
ed99c571-1d37-5701-8675-75bdbe95ab3a | note | Records - Concrete Delivery Dockets
be92b6ff-c327-5f5f-aaa8-72657b23c488 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8 - Temporary Works (Formwork)
29468734-bab6-527f-96a1-5080dc879c58 | note | W
6014d553-b2f4-57b2-91fe-36809b45de68 | note | Detail - Formwork to be set to correct line and level
93e1c190-80d6-5ce7-a514-ec8e02906609 | note | Frequency - Prior to pouring concrete
3aa05717-349d-576c-85fb-397ce006540d | note | Inspection / Test Method - Visual inspection
cba5360e-e2e2-5e76-8248-7b5801c6fb33 | note | Conformance Criteria - Concrete Inspection Record
cec06d44-19c2-5f2a-b1f8-087d9e6603ea | note | Records - Concrete Formwork Checklist
02c7e0e3-a322-551c-866d-ab6d1f026bd2 | note | FH Initials - Site Engineer
| checkpoint | 8.1 -
fe640a5b-d601-57c4-82b0-81fcdb907191 | note | H
86803252-f5d5-592a-a2f5-ba24f334a5bc | note | Detail - Raised table formwork to be 75mm above existing road level and be 300mm in depth and gradients respectively of entry (1:15) and exit ramps (1:40)
b722e98e-642a-51dd-bb23-d9f9d428361f | note | Frequency - Prior to pouring concrete
b55b6ab0-6eb7-5652-a1bf-1e3adc976791 | note | Inspection / Test Method - Measurement
3d3789d5-4421-5302-b590-5944f9025bc4 | note | Conformance Criteria - Designer to inspect formation level
15b4100a-8a87-5243-9446-c6107cdb7df1 | note | Records - Site photos
78854638-40f0-532f-b2b7-6b5684cd478f | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8.2 -
57289f7a-87c1-5fc1-81f9-8aedc070c624 | note | H
58313634-f754-5c8e-b6e7-48b071eeb139 | note | Detail - Raised Table ramps to have 250mm depth at entry point and tie into 300mm depth to meet raised table
a16e078c-89af-5eea-8293-8d1b878458b8 | note | Frequency - Prior to pouring concrete
93fa93b6-7060-5a8f-90fe-70a67f94418c | note | Inspection / Test Method - Measurement
532a59e5-8362-5eed-b1e5-a1976397fd76 | note | Conformance Criteria - Designer to inspect formation level
0b86215c-7aa6-5641-b433-dfbff10f1235 | note | Records - Site photos
ebc69f63-2baa-5e16-9bfd-25f50f32d259 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8.3 -
2e77ae31-5ecd-5668-9f1d-97411698b01e | note | H
5c73dd18-dcd7-5928-8bc8-72b3d41a3aaf | note | Detail - Raised Table ramps to be 1.125m across for entry and 3m for departure ramp.Toe to be 0.5 to 1m across for both entry and departure with 50mm asphaltic wearing course
6fe25786-1945-59ea-b964-3d50ab56761b | note | Frequency - Prior to pouring concrete
a28b96c6-b118-54d6-a5c0-aa1b4b9893f9 | note | Inspection / Test Method - Measurement
34aad87c-5903-5a16-9499-750ab7f5f8a2 | note | Conformance Criteria - Designer to inspect formation level
d1295208-20b7-5db5-af38-6fea9e36687c | note | Records - Site photos
5dee4285-9188-5d87-bfc3-d45984b0b10b | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8.4 -
95a58e27-70d8-5003-9e7c-f3e25c005ec3 | note | H
c53bf86b-e5fe-50af-9615-8f977d560d6c | note | Detail - Raised Table ramps to be 1:15 gradient for ramps at entry and exit ramps to be 1:40 relative to the road
bb1ebdb2-b673-5265-a52c-a87b498bc7e3 | note | Frequency - Prior to pouring concrete
bf57b67a-0886-5726-b00e-a321ea4265bc | note | Inspection / Test Method - Measurement
43bcb80e-10cb-53ff-bda6-ff6e0f0c8888 | note | Conformance Criteria - Designer to inspect gradient level
0cd93cb1-fcb0-518f-9f32-adc5d2678116 | note | Records - Site photos / Concrete Formwork Checklist
6032cc10-10cc-5db6-8316-aefb2fcc5100 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8.5 -
d6618948-0274-5da4-8dba-4dc7ac441ca9 | note | H
135b7bad-efea-5396-a589-d25b3c7a8f1b | note | Detail - The Site Engineer and MSQA Engineer must sign off the formwork prior to concrete being poured
6af60905-e0f8-5e1d-94d4-58bc71d2c715 | note | Frequency - Prior to concrete pour
73849a83-5059-5e2f-a130-1ce2a1c8a862 | note | Inspection / Test Method - Visual inspection
9a5d0a34-cfdb-5d9b-b11c-8bbd30a1d5c3 | note | Conformance Criteria - Concrete Inspection Record
e972cd11-9936-5e8e-9118-e003c9f76a77 | note | Records - Concrete Formwork Checklist
e4545aa3-8d88-5b6b-8ae3-fb5d3038d5c6 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Reinforcing
a6e771d1-ab0a-5a78-9b4d-7ec3ba700581 | note | H
9ed10509-ee75-5b84-b2f0-0fd9f1085045 | note | Detail - All construction joints are to contain 2 rows of LESA dowels or similar approved dowels .Dowell system 50mm w/ Black 300*50*6mm plates @400 centres placed across the construction joint
48c76fef-c4a0-52d7-87a5-a4f2b6fee84a | note | Frequency - Prior to pouring concrete
b27a8e2d-cb36-54da-ba87-4c6968f25bab | note | Inspection / Test Method - Measurement
0229bfd1-51dd-5b5c-baf0-0c112e8f5436 | note | Conformance Criteria - Concrete Inspection Record
8db99e67-5bda-5730-b47e-afd173587bb9 | note | Records - Site photos/Concrete Formwork Checklist
b56f0592-33d8-5976-b32c-480a21d0d4e5 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10 - Concreting
a36de7b9-d1ba-5186-b983-210bfdec3e7f | note | H
900de51f-0202-55e8-b1f2-94f4728642d6 | note | Detail - The MSQA Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required
8b78756b-e33d-52e9-88f4-e04da799626e | note | Frequency - Prior to concrete pour
82ea2631-841d-5612-9c68-cd36511b1178 | note | Inspection / Test Method - Visual inspection
2b636ec4-c39c-562d-b922-188dd662f530 | note | Conformance Criteria - Engineer will be notified via email/SMS at least 24 hours before required for inspection
f2ead7bc-4eae-5ab5-b32e-2633c3a6227b | note | Records - Email / SMS
1a72009e-0dd3-5d0f-b741-b4d5ad439fa5 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10.1 -
615c8e02-5d0f-58d9-bf26-9e108b896ee5 | note | W
80e0b8a4-2f3f-5d1e-bba9-482ac03c08fc | note | Detail - Vibrator to be used throughout concrete pour
430d67a7-81f2-561d-bfc2-d450eaa37e30 | note | Frequency - When pouring concrete
9df060c1-7b9d-5bfb-af77-46c2a287aa72 | note | Inspection / Test Method - Visual Inspection
21e47812-cef7-5b81-ab7b-93470a7f172d | note | Conformance Criteria - Concrete Inspection Record
bf18c7e5-61b6-57e0-a32d-f7149b175978 | note | Records - Concrete Formwork Checklist
1645865d-f29c-561d-9723-b46b8fdfc31d | note | FH Initials - Site Engineer
| checkpoint | 10.2 -
95809d09-74b6-5ccd-baa9-0c95c5caf7c9 | note | H
98459f51-3d10-5761-afd4-d1c5873fe5a0 | note | Detail - Concrete surfaces shall be U5 broomed finish for ramps, and exposed aggregate finish for table top.
cf131987-3cab-5d79-b048-cd087e2a20ea | note | Frequency - At completion of pour
9f00c831-1d6d-5a03-9e8f-1c023fed1803 | note | Inspection / Test Method - Visual inspection
af8e2339-22fe-5711-a8da-f86a7395d9ef | note | Conformance Criteria - Concrete Inspection Record
01012ef3-a448-55dd-b809-87261ed2bcc0 | note | Records - Concrete Formwork Checklist
f84d5fdb-c097-568b-9280-bd5e4fcfbd67 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 11 - Curing
35f35d0d-8c33-504e-848f-fe9693e520e9 | note | M
5003a2b4-6951-5c0d-9ba4-264ebbc585b3 | note | Detail - Concrete will be left for 48 hours minimum to cure before traffic is allowed on it.
8a999cfb-6b30-5119-ae71-f1e255744e3e | note | Frequency - Post Pour
40aff075-3f19-5820-8f1a-04a0dda011f7 | note | Inspection / Test Method - Monitoring the time allowed for curing
52db9a40-bc9d-5551-8493-22a41f31a1f7 | note | Conformance Criteria - 48 hours minimum have passed
65ddc714-4034-595f-97b0-de6f267bc241 | note | Records - Concrete Formwork Checklist
2fb03544-1107-5d29-a1b9-284445ce33ca | note | FH Initials - Site Engineer
| checkpoint | 12 - Remove formwork
45401c47-cb40-5c07-a5c6-00a9dc594510 | note | W
8530b4a1-288e-5526-8ff1-8a3e553f6dfe | note | Detail - Remove formwork after 48 hours
9efa64fb-7576-5f03-ae8f-0ef80d9df9fd | note | Frequency - Post Curing
83a55c1b-1da7-57bf-88b1-c53e440a09df | note | Inspection / Test Method - Visual inspection
e7c2eb5c-842b-5976-aa8f-4266befb3791 | note | Conformance Criteria - Concrete Inspection Record
e3a6e09b-6661-5c24-b86c-2601b7f58b40 | note | Records - Concrete Formwork Checklist
07fe5c54-472d-57b8-9bac-50de2c10dd2e | note | FH Initials - Site Engineer
| checkpoint | 13 - Asphalt- Concrete extension slab/ Toe
54879025-7f69-5326-95e4-8ec528024d15 | note | H
23124509-de8f-5148-8749-2e67923666f0 | note | Detail - Two rows of Lesa diamond placed mid depth @600 C/C along construction joint as per TDM TC003
c3355572-63e3-5e9c-a4de-f52ce4d2151b | note | Frequency - Prior to pouring concrete
f71c9af4-3362-5681-8328-06d3c4bb9ede | note | Inspection / Test Method - Measurement
09751505-1a51-5210-a33b-a02b4485aa61 | note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
4b237c44-752b-5e5a-b387-fbb7abb70c79 | note | Records - Site photos,delivery dockets
28095584-a74f-5bae-a7b3-2297aec07415 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 13.1 -
afa18491-b7e0-5719-b36d-cbd8f59f69df | note | H
20a7b738-608f-5f9d-9632-98df6e543caf | note | Detail - 200mm thick 50MPa Concrete with two layers of 663 mesh
c2768067-45a7-5b9f-ab0d-daa39f761546 | note | Frequency - Prior to pouring concrete
7a0ee243-72e5-5ee9-ae75-c01a62fc9de4 | note | Inspection / Test Method - Measurement
f39f06d2-267f-5716-a8f5-191e12b1a3e0 | note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
37d7e1cf-9377-5798-a68b-ccf2c4693ae8 | note | Records - Site photos,delivery dockets
0534d447-4c43-5fb9-bbc7-a94dab98a138 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 13.2 -
37c4f5e4-a465-54df-952a-df12c318136e | note | W
07380a0c-053c-5ee7-9fc1-41397891df5a | note | Detail - Tack Coat between AC and Concrete slab
fef25fa0-30f2-5f2f-a0cd-6b15aee63a43 | note | Frequency - Post Curing
ac3c293b-9d5b-568d-a821-a4a7c1ce382f | note | Inspection / Test Method - Visual inspection
5c07aa33-4efc-5276-a41b-7a9abbbdf585 | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
2c25aab5-ab74-5976-9c39-d1fa42bd4129 | note | Records - Site photos
3e6fcd94-ec9f-5392-9bc5-1d93a027e58c | note | FH Initials - Site Engineer
| checkpoint | 13.3 -
fb1ef56a-f633-54f9-891c-7d2cbd03e933 | note | W
47754c52-94db-5258-8124-a632902ea59f | note | Detail - 50mm thick DG10 / Mix 7
5bcef5de-9018-50ff-bc13-298756792a0e | note | Frequency - Post Curing
c39ddf49-60c2-5875-9d78-eb4a1abe4449 | note | Inspection / Test Method - Measurement
e0ef947c-e240-59bb-8cfe-6cbc3105f10a | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
eb92afce-9816-5f2c-be4c-34142c0517a7 | note | Records - Site photos,delivery dockets
d8bf6787-2a29-52cf-9ab4-ef3b671fb3b5 | note | FH Initials - Site Engineer
| checkpoint | 14 - Lot Number QA File
94f29e45-ad09-59ad-b949-8ca267d684ca | note | W
025cfff7-fc69-5722-86e5-9edce0e61232 | note | Detail - Ensure all QA Records,site photos and incident cases (OFIs) are closed and included within QA file
40bca27a-d6d1-5fc5-9309-5b2f428b5687 | note | Frequency - At completion of Lot
02ddce0f-0a4c-5807-a1cd-d12bc1ff5984 | note | Inspection / Test Method - Document Review
7cbf1c74-8997-55cf-822b-6b4470f63456 | note | Conformance Criteria - All QA files compiled and sumbitted to client
6851c9f1-1e88-5904-91d5-115165ad2d44 | note | Records - QA records
f788bce2-80fa-56db-8926-65e7f3d6b70f | note | FH Initials - Site Engineer
| checkpoint | 14.1 -
229b56a6-56b5-5c18-b9a6-c480e96f10bd | note | W
25ec0b22-65d4-57d5-95fa-de55a6b2bc0a | note | Detail - Delivery Dockets to be included in QA file
e557213c-69ea-5002-8f45-16ea2b72814c | note | Frequency - At completion of Lot
a9f08bd8-715b-5bca-91db-598019d9f202 | note | Inspection / Test Method - Document Review
2df827b5-1b4c-549d-ab1a-d6bff0dd1688 | note | Conformance Criteria - Delivery Dockets to be included in QA file
e495b6ab-2801-5773-bc9e-a3ff4af105df | note | Records - QA records
7acd9509-bf18-5b79-ba36-a93695bcec55 | note | FH Initials - Site Engineer
| checkpoint | 15 - As-builts
7b6e4dd9-19f8-514a-9fb8-6c796ee25070 | note | H
e318cb7a-0dae-54bf-993a-cf3298fe3b29 | note | Detail - Red pen mark up drawings to be included in QA file
2eb36e88-989f-56a1-8e7d-6981eac96808 | note | Frequency - At the completion of the Lot of work
0f53729b-5b06-5eaa-a35c-f10858f1fc82 | note | Inspection / Test Method - Drawings
ac2666b8-c45d-5a96-8117-59ce3f5d416f | note | Records - Asbuilt Drawing
0cadf6f9-6688-53f0-8e5e-db38a9646429 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checklist | ITP - Great South Rd - Enabling Works | itp | ITP - Great South Rd - Enabling Works | 73bbe34e-4ece-4ad8-8628-f2a61c715d41
| section | Site Set Out
| checkpoint | 1 - Site Set out
5eae14dc-b408-5d3c-9d2c-b04b0835e9ae | note | VERIFICATION ACTIVITY - Surveyor
fcc9d8f1-1a4f-5bcd-b233-428c6c248e47 | note | METHODS OR REFERENCE - Surveyor
2b2ca28c-629e-516a-9e39-8ef050ddd25a | note | Frequency - Everysite
d5e440ff-ec77-563b-afec-6ec2393cd3b5 | note | ACCEPTANCE CRITERIA - Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criterea is acceptable.
bb92998a-b0a9-5848-a17b-60caaa00fffb | note | Hold Point - Mandatory HOLD POINT -
531f5f41-471d-5c9d-a251-fec63c643b57 | note | Records - Onsite records/photos
1ad67a61-d3d3-5692-9ddd-ec07b356873d | note | Onsite Responsibility - Site Engineer
| section | Materials
| checkpoint | 2 - Kerb & Channel
cbc1db41-ca55-59ca-ba45-7dd9ca57ec81 | note | VERIFICATION ACTIVITY - QA FORM
49ee2e6d-176b-56b6-b987-6bfb579fbf24 | note | METHODS OR REFERENCE - TDM Technical Standards - KC0001
0776bfc8-d86e-5345-bb7a-c5b20fce8c81 | note | Frequency - Everysite
dde84042-4251-536b-8d76-058adb03a8d4 | note | ACCEPTANCE CRITERIA - Kerb & Channel to be laid using precast hand-laid. On compacted GAP40. Concrete 20MPa @28 Days on 100mm GAP40 with the subgrade CBR>5
c41c85e2-1379-5476-b063-5bb5b82d0839 | note | Hold Point - Inprocess Inspection
c0a79302-d6e1-5d67-ae1b-3e44eeb71d91 | note | Records - FH concrete QA sheet, photos. Concrete Plant Docket
57c98571-6344-5a7d-a679-7820b9bc28fc | note | Onsite Responsibility - Site Engineer
| checkpoint | 3 - Channel Level
5871bb79-a7e4-5d3b-9dc2-22921f6059d6 | note | VERIFICATION ACTIVITY - QA FORM
8d4c4059-6b43-521e-ab35-3ae738e371b9 | note | METHODS OR REFERENCE - TDM Technical Standards - KC0001
939f4117-d970-55eb-9acf-df6d6935b7f5 | note | Frequency - Everysite
535731cb-d647-5f8a-9330-65c897f8a8b3 | note | ACCEPTANCE CRITERIA - Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
e86eca70-04d2-53ad-8d1b-a5e14b30695a | note | Hold Point - Inprocess Inspection
3b6679f5-2349-5cb8-8d84-3d7483afa4e1 | note | Records - FH concrete QA sheet
a8f174b2-b0f8-598e-aee3-8f9bf4c99dd7 | note | Onsite Responsibility - Site Engineer
| section | CIVIL WORKS
| checkpoint | 4 - Concrete Footpaths
8a4bcf08-ca80-52f6-994e-e9482aa0f1f0 | note | VERIFICATION ACTIVITY - QA FORM
9d2faa96-57d3-59d4-9620-c06f1764a7ed | note | METHODS OR REFERENCE - TDM Technical Standards - FP0001
c5327c34-0bc1-583e-b44e-5840fb5dedce | note | Frequency - 10m Intervals
1c685a2b-a1d0-54a6-8403-00c988eb99db | note | ACCEPTANCE CRITERIA - Subgrade -(CBR > 3) Basecourse - 100mm min. thickness GAP40 Clegg CIV > 12 Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with exposed finish
b9be1382-d072-5557-bf6e-7d51ba4ce5a0 | note | Hold Point - Inprocess Inspection
25e828ca-4aad-5da4-a74a-815947b46c65 | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
d0a92fe3-0f03-5d93-a837-ad605dcffcba | note | Onsite Responsibility - Site Engineer
| checkpoint | 5 - AC Footpaths
d53706f3-3d09-5793-beca-162635fbfa09 | note | VERIFICATION ACTIVITY - QA FORM
ec6e4f43-654c-5a0a-9b0a-eecafac5bbd1 | note | METHODS OR REFERENCE - TDM Technical Standards - FP0001
4f94c76a-22a1-5429-bc79-63361d4bb1c8 | note | Frequency - 10m Intervals
c45bf35a-588b-5b24-9c6e-dd051c8789d6 | note | ACCEPTANCE CRITERIA - Subgrade -(CBR > 3) Basecourse - 100mm min. thickness GAP40 Clegg CIV > 13 DG10/Fine asphalt mix used
4f175555-1a0a-5280-bb80-dca2e0e5f9f1 | note | Hold Point - Inprocess Inspection
c0ac7a74-7321-5e35-83cf-998206145654 | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
b866075f-e6f1-5af9-83ea-ded97134782b | note | Onsite Responsibility - Site Engineer
| checkpoint | 6 -
6e4705e6-1824-5ba3-a4ba-0c430f604ed0 | note | METHODS OR REFERENCE - TDM Technical Standards - FP0010
ed4619d5-4f99-53f3-960d-fd1a4a702446 | note | Frequency - Each PX
75a93ecc-bc7b-5038-8551-c41fac0f2907 | note | ACCEPTANCE CRITERIA - Warning TGSI tiles should have 100mm concrete slab underneath
d0690f84-c7cb-5a1c-b3b3-41d5e981a199 | note | Hold Point - Inprocess Inspection, Measurement
ff597f46-653a-5233-9602-4f09f8c6a466 | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
7b9f3ae3-d055-56cc-955e-c6078ff4f423 | note | Onsite Responsibility - Site Engineer
| checkpoint | 7 - Tactiles
2baee133-ea73-587d-a324-ee0396645350 | note | VERIFICATION ACTIVITY - Visual
178b44f3-02f7-5d62-86a6-ce0496b3fe1b | note | METHODS OR REFERENCE - NZTA RTS Guidelines for facilities for blind and vision impared pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
6d70b911-560c-572c-866a-8df57bfed342 | note | Frequency - Everysite
a803ae83-70be-5b65-8f6f-058832fe7038 | note | ACCEPTANCE CRITERIA - Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
d65f5680-9f93-5983-a672-72ca69162597 | note | Hold Point - Inprocess Inspection
aa2ff71d-be75-5563-a721-08cfca9eda13 | note | Records - Photos
1f6d4121-5380-5ad4-b498-120b2417372f | note | Onsite Responsibility - Site Engineer
| checkpoint | 7.1 -
8a9c9608-bba5-5faf-88e2-a789a7167b34 | note | METHODS OR REFERENCE - AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
a87bd221-3d19-501f-8048-b97f9ba2d4c4 | note | Frequency - Everysite
6c5bd917-0deb-5494-8724-30dcd6851f25 | note | ACCEPTANCE CRITERIA - Edge of warning indicators to set back 300mm from the face of the kerb or lane, extend the full width of ramp and be 600mm deep.
132c87e6-2e47-5174-8cd0-2b2752391708 | note | Hold Point - Inprocess Inspection
4a20fbac-7dc9-581a-8276-4e2347e1ebf7 | note | Records - Photos
2c26aa0b-e8d9-5e50-bb13-63a02e74c2b7 | note | Onsite Responsibility - Site Engineer
| checkpoint | 7.2 -
826a9828-498a-5842-a593-3ddb15171199 | note | METHODS OR REFERENCE - AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
c3e8bbcd-f6ff-5762-ac87-8d82c860fda2 | note | Frequency - Everysite
55b9be87-0372-5f88-b522-f780febcfbd8 | note | ACCEPTANCE CRITERIA - TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
872a1646-c388-5ed6-a347-d06cc248d430 | note | Hold Point - Inprocess Inspection
0489acb6-328d-58bb-b4cd-8e075dee6b04 | note | Records - Photos
f7c66119-bbfb-57df-93b0-be29b74d89e1 | note | Onsite Responsibility - Site Engineer
| section | RAMM DATA
| checkpoint | 8 - As built information
e12c6822-2530-5655-aecf-b10e6f65ede0 | note | VERIFICATION ACTIVITY - RAMM DATA SHEET
ff03c488-d36e-59ad-8b8a-6e8a333c5d5f | note | Frequency - Every Site
4c817798-9502-5586-8a18-139e6fba70b5 | note | ACCEPTANCE CRITERIA - As built drawings and Ramm Sheets Completed
42a54f78-dd74-5e88-b23e-bc427e2ee48a | note | Hold Point - In Process Inspection
afa39854-d253-5f67-99ca-1d118f6d2f6a | note | Records - Asbuilt records
0e28baef-e3b5-5ae6-aa76-4c33a5411650 | note | Onsite Responsibility - Supervisor and Engineer
| checkpoint | Final Inspection
4abdb529-5cdf-5b89-8c43-8e26d2a557ca | textbox | Comments:
3ad6746b-9d7b-5957-aba6-1b9780c60945 | textbox | Position:
28e07d81-9442-5203-ac63-9dbd3948e535 | textbox | Print Name:
29c1bbe1-4e6a-5b7d-b03e-1c0bd97927b7 | textbox | Date Completed:
| signoff | Add Signature
| checkpoint | Final Inspection
aad2ef4c-df2f-5e83-a15a-014d83d11c82 | textbox | Comments:
5f90d200-dfad-5450-8f5b-fc76b676254e | textbox | Position:
96b4d151-5422-5f35-96d4-e8724d626816 | textbox | Print Name:
34c833ef-eaff-5384-befd-3845f1d23bf0 | textbox | Date Completed:
| signoff | Add Signature
| checklist | ITP - Great South Rd - Island | itp | ITP - Great South Rd - Island | a8450d00-925d-40cf-92cf-4539f1147269
| section | Materials
| checkpoint | 1 - Mountable Kerb
db1594cb-b2b2-5aba-954a-bc73713241a7 | note | VERIFICATION ACTIVITY - QA FORM
7edffe87-ffc0-579e-a668-74b55d1161aa | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002
127ae372-3bb2-5ba8-a0d8-0bd5656bfb3f | note | Frequency - Everysite
4ee5251e-eb99-585e-9412-d9199e20569d | note | ACCEPTANCE CRITERIA - Mountable Kerb to be laid using precast hand-laid and painted with two coats of reflective paint
d2b5af73-db1b-5743-a231-660b03a5c70b | note | Inprocess Inspection
b738d43f-afd4-521d-adf2-a9a6c4f74040 | note | Records - FH concrete QA sheet, photos.
2598351d-f11e-5de1-b1a0-5b9207037174 | note | Onsite Responsibility - Site Engineer
| section | Construction
| checkpoint | 2 - Survey Setout
f9041311-7a29-5aae-ac87-c37e4f2929ad | note | VERIFICATION ACTIVITY - Survey
88ebbd61-6c55-5593-9415-6f661d08cdc8 | note | METHODS OR REFERENCE - Setout Kerb Alignment required to construct to design
01e4ad39-2bb7-5738-a82e-95f185ff0690 | note | Frequency - Prior to commencement.
589ba7d6-7b95-5a85-8fdc-91fef9334af5 | note | ACCEPTANCE CRITERIA - Survey
6aba0267-4f64-52e9-8f17-acfd1b4c2fdc | note | As per Construction Drawings
6274f45a-5fe6-52d7-ab85-db6194c04f30 | note | Records - Survey Receipt.
fd4e524d-c0d4-5e2c-ac2b-75a078c5a1a1 | note | Onsite Responsibility - Site Engineer
| checkpoint | 3 - Concrete Island
36cccbdc-9747-5800-b9d8-f233ae0593b7 | note | VERIFICATION ACTIVITY - QA FORM
9dbcd368-9760-5261-b39d-d4d8f3f30e31 | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002
411956a7-7786-5eb3-9597-9c392944993d | note | Frequency - Each Site
5ee9a501-9c28-54de-8edc-016232809ad5 | note | ACCEPTANCE CRITERIA - Kerbs to be haunced with 20MPa Concrete
80d8fd09-4b7d-5d7b-9870-1377e7be4c8e | note | Inprocess Inspection
df60216d-21cd-55bd-893f-e7f26118cf67 | note | Records - Photos
f91a5272-aed2-5f60-8985-04f3ba2ccf9d | note | Onsite Responsibility - Site Engineer
| checkpoint | 3.1 - Concrete Island
6dd0d13d-8e86-5c63-990e-bff9fc209265 | note | VERIFICATION ACTIVITY - QA FORM
e26ac361-91fd-5ae5-a0de-98f6ab5fcd7b | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0003
af5b0b74-5ffb-5497-8bca-4843ba324dac | note | Frequency - Each Site
d6267ee1-bea8-5acf-ac88-fd52434260b6 | note | ACCEPTANCE CRITERIA - Basecourse to be 150mm min thickness of GAP65
e53f3794-562c-55e8-a3b3-6f16d8c8310b | note | Inprocess Inspection
e829f4fb-3a4c-56f8-9f8e-5b72121eaf32 | note | Records - Photos
c2bbf2d3-f770-586d-93b3-44f929fbdb40 | note | Onsite Responsibility - Site Engineer
| checkpoint | 4 - Concrete Infil
6b9c21e4-107d-55d6-b9e2-313b513a0b09 | note | VERIFICATION ACTIVITY - QA FORM
9e5a42cc-9598-5c21-aa05-a74da3d351b7 | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002
b5f98983-cc73-5b20-87da-c9fd8f196840 | note | Frequency - Each Site
0468b890-335d-5167-933d-2ce2e63376b6 | note | ACCEPTANCE CRITERIA - 180mm depth of 20MPa broom finish unreinforced Concrete with 4kg/m3 black oxide Cross Fall of 2% or max rise in centre of 180mm
473a759b-a07a-54c1-b90e-7f7c64575922 | note | Inprocess Inspection
68e76f9a-841e-5bd3-bfbf-64001d19371f | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
29750445-7275-55d1-9d81-861b3ecbe81d | note | Onsite Responsibility - Site Engineer
| section | Asbuilts
| checkpoint | 5 - As built information
e00fc8b6-7b70-5d49-a43b-1dc5706f04e4 | note | VERIFICATION ACTIVITY - Drawings
275b9df0-24df-5a4a-8093-a7af650db9fb | note | Frequency - Every Site
3dc114e7-d466-5005-8512-eb19febc0b82 | note | ACCEPTANCE CRITERIA - As built drawings
43528038-24af-5fd0-bf72-d8d38bdd000e | note | In Process Inspection
3d52557a-d596-54cf-a973-ee585d939ab1 | note | Records - Asbuilt records
03558890-0b5e-5e6e-bcd3-218f5c083fa0 | note | Onsite Responsibility - Supervisor and Engineer
| checkpoint | 6 - RAMM DATA
836c2205-4bfc-5535-9efa-e4b96e179e26 | note | VERIFICATION ACTIVITY - RAMM DATA SHEET
5ac8c17c-dc9a-504a-9ad3-5b545cbd1b85 | note | Frequency - Every Site
2c227797-4e9a-5d40-bcd6-89690b5ba871 | note | ACCEPTANCE CRITERIA - RAMM SHEET
51b5a1b3-b243-5cb3-80ba-237dec6a095a | note | In Process Inspection
3702f566-787a-5d58-b7a0-5a1dd32def8b | note | Records - Asbuilt records
6c64faba-aef5-506a-b837-891164715a41 | note | Onsite Responsibility - Supervisor and Engineer
| checklist | ITP - Great South Rd - Stormwater | itp | ITP - Great South Rd - Stormwater | 05807317-f0cd-462e-a864-954933b6cc25
| checkpoint | 1 - Permits & Services
c5067ef9-be49-5a79-92a1-ceeee44ba2bc | note | H
2ffd7ec4-51d7-5836-937c-1b1f48c7cf99 | note | Detail - Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
c897153d-3e20-56b4-b00a-3a2aa4366bf1 | note | Frequency - Prior to any construction commencing
7c0586ca-bcc1-5e35-a926-1ada4f4ae046 | note | Inspection / Test Method - Document Review
07ee5ce3-fa36-5895-a0c4-13526372519e | note | Conformance Criteria - Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority
818477f9-b7ef-5bf3-82e0-2f18bd392ccf | note | Records - Permit attached or permit number noted.
614964fc-9fec-5611-9e11-c3f3d9ce38eb | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.1 - Permits & Services
e768d2f5-be32-5796-8ba3-6930dcc6a04d | note | H
d4d0fb19-39f2-572b-8ca9-d2c48cdf3e5b | note | Detail - Locate and mark out all existing services
48577eec-90fb-5f64-a9df-53d2bb0bfeb9 | note | Frequency - Prior to any construction commencing
f9fb7307-b688-5628-864d-1539fd007296 | note | Conformance Criteria - B4u dig procedure - follow utility protocols
28003981-50d7-5c89-92e0-6fc1c324ac13 | note | Records - B4u dig plans & GPR report attached
97ac85ea-91b2-590c-9800-6aed7fcee3ad | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Pre-Construction Sign Offs
dde33f81-d3af-5e52-8a9f-4b61ed6fc250 | note | H
1a09703d-d5fe-5ba9-9ffc-5086329b9bfd | note | Detail - Sub-Contract and Supplier Agreements
32c5e375-395e-5efc-be29-45f7ccc4efa1 | note | Frequency - Prior to commencement.
4672cb3c-d671-51da-9e4c-a3b2af35cd24 | note | Inspection / Test Method - Document Review
cd9fb1f8-2cb8-5f3c-b00d-8f864b7bff52 | note | Conformance Criteria - Sub-Contract and Supplier Agreements to be agreed and signed
3bcf88f4-25b1-5b10-810a-944ca3938682 | note | Records - Subcontract and Supplier Agreements
4fae1e9a-b41b-5ce4-974a-a8f5a378042a | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Design
f082222d-5835-5420-802b-c7dd1885cd63 | note | H
44353dc3-21b0-518f-8c3b-e5c580bcb30d | note | Detail - Design is approved and Drawings are of the latest revision.
7a25c8c3-d1f1-5631-9ac6-129a63641c4a | note | Frequency - Prior to commencement.
4fd3888f-5c8e-58a6-83a1-9ded22ecc6d3 | note | Inspection / Test Method - Document Review
382a5edc-2366-552b-ab6b-b3f124b7b7f2 | note | Conformance Criteria - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
975b859f-b781-53a6-bd62-3b80c5e3ef4b | note | Records - Drawing Register.
f403a5d0-4741-5c62-94bc-139d384ea9f2 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Survey Setout
edf07bee-a88d-5d61-9a9e-ee8b122392f5 | note | H
ffd16b89-d8b9-5cec-b0a2-77cba2fbba28 | note | Detail - Setout Pipe Alignment and Service Locations with inlet & outlet points and inverts as required to construct to design
77679b99-ea02-5bb1-947a-a957d3d8a591 | note | Frequency - Prior to commencement.
228f07eb-668d-5900-9f2b-0e2f8269e29c | note | Inspection / Test Method - Survey
49a191f7-1759-578e-8324-903fe5f6b90a | note | Conformance Criteria - As per Blue Barn Consulting Engineering Drawings: 02188-T-400 & Setout files
9c3da98d-cada-5584-bc9b-0fb9f4544783 | note | Records - Survey Receipt.
df3e730a-6b26-5098-8194-318605999820 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Pipe and Manhole Material Compliance
69661c04-8a6e-58f2-876e-767664fb8e04 | note | H
7134b16e-b8ef-5df3-9ef7-df58ed42254a | note | Detail - Cesspit, Manhole and Pipe shall comply with relevant AT/TDM standards
e7f4f295-66fd-50e8-bec3-03415e211cdc | note | Frequency - Prior to commencement.
1097a9d7-e792-5049-aa61-2943e4e8f931 | note | Inspection / Test Method - Document Review, Visual Inspection
fd5e43f3-ddff-5533-a485-d4411a6fffe8 | note | Conformance Criteria - Pipe shall be Check for freshyly formed pipes and return if required 1) DN225 Class 4 RCRRJ pipes AS/NZS 4058 2). All Concrete RCRRJ pipes to be fitted with Rubber rings 3). Pipes shall have product certification (ISO Type 5) to AS/NZS 4058 Prefabricated concrete Manhole shall be in accordance with TDM Standards & AC COP
e451caf7-9551-517a-8956-2a572c0a9afb | note | Records - Manufacturers Data Sheets, Delivery Dockets
4bf4cd33-d85a-5393-ad57-842a735c4ac1 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Locate Existing Services by Hand Digging / Hydro Vac
20693165-ce62-5855-bc20-cd68d4b57623 | note | H
97bc53d2-73b5-5d94-b4ee-af6847eb748a | note | Detail - Ensure all services conflicting with the line of trench have been exposed by hand digging.
93b16d05-e8d2-5216-98ea-cdf30a5da039 | note | Frequency - Prior to commencement.
8066038a-a288-555c-911a-37f089c12d67 | note | Inspection / Test Method - Potholing / Survey
fd82a11c-713f-54dc-b708-c64179cee1b4 | note | Conformance Criteria - All conflicts have been located. New services and / or conflicts to be advised to Project Manager.
388445bd-bcd1-58a1-b3ac-ddef13e714ba | note | Records - As-built Drawings. Doc. Review
7baeecc1-a789-535f-9164-e7f56a22ad05 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Trenching & Excavation
44f570d5-b629-5d24-8418-735f7f9d3b16 | note | H
27122c98-abf2-5937-a2ec-d4991db8d8b4 | note | Detail - Excavation methodology
57dc1a0d-8220-5441-9e0b-7ff352dac274 | note | Frequency - Daily
f3314c42-e56b-544c-8fb1-3effb17182b8 | note | Inspection / Test Method - Prestart review
9f57b1f2-b199-57e3-93fc-93ee3e1daaab | note | Conformance Criteria - The excavation, benching and shoring requirements shall be in accordance with Worksafe Excavation safety guidelines (2016)
c6a81bf5-bd15-5640-8f42-15fc2b84dd08 | note | Records - Prestart RCP
803118b8-a15b-5cfa-ad7e-99c0a70b01fd | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.1 - Trenching & Excavation
3468451a-5fe5-506e-adc8-8dabc2768145 | note | M
68f11d91-a23d-5dbc-ad1d-c4d70d1e0cf3 | note | Detail - Trench Profile - Width
114892fd-2c23-502e-af87-c201aa042481 | note | Frequency - Daily / as trenching takes place. Different depth methodology
cd64d331-5b33-5427-bc2e-a738b6fae867 | note | Inspection / Test Method - Visual Inspection, Excavation methdology
845026d6-5b84-5ce1-985c-f78a97d5b0f7 | note | Conformance Criteria - Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing
69197fd4-b089-5c2a-9b7d-60c142b3dd2e | note | Records - Construction Photos
be8016ea-e976-5303-a5cb-5fc6826a4a86 | note | FH Initials - Site Engineer
| checkpoint | 7.2 - Trenching & Excavation
39b5ff3f-04ce-59e6-9202-b26acfc65cc2 | note | W
a486e986-602a-56d2-8d92-8a9c8345159a | note | Detail - Trench Profile - Depth
79afbf11-3792-5514-aad4-ab8df1b3d05e | note | Frequency - Daily / as trenching takes place.
b0f5bd33-e839-5b35-a23a-8469f37d0b8f | note | Inspection / Test Method - Visual Inspection, Measurement
55dd8611-a385-58c1-8fbf-edbb884978b6 | note | Conformance Criteria - Trench depth varies according to longsection and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings
0fe3b387-2cb2-5967-bb82-fb3c56f1dd0a | note | Records - FH Drainage Line Record / Construction Photos
2158225e-641b-5323-a0dc-eb3a4ddaa41a | note | FH Initials - Site Engineer
| checkpoint | 8 - Bedding for Concrete Pipe Laying & Manhole & Cesspit
f93d3666-f1d4-569e-bbec-23db491d2827 | note | W
6b4a9c33-3d6e-5db0-bb7f-4c0dffee211d | note | Detail - Placing and compaction of Bedding Material.
260a51d5-89d9-5c63-b376-961e627b7466 | note | Frequency - Inspected continuously during placing and compaction of Bedding Material.
a5b5aef7-d4b3-5b11-84a9-38f7186fc623 | note | Inspection / Test Method - Visual Inspection
8dcbc703-1afe-54a5-ab9c-8a79946abc93 | note | Conformance Criteria - Bedding & Pipe surround material to be GAP7 or GAP 20 (Stevenson Quarry) or alternate material that complies with AS/NZS 3725
a8030bfa-964d-5121-8a3a-824074d1460b | note | Records - FH Drainage Line Record / Construction Photos
233fd5f2-ae70-52a6-a219-4b8ced80ee1d | note | FH Initials - Site Engineer
| checkpoint | 9 - Pipe Position Tolerance
3e6b3e88-6d1e-5ded-ae76-7077132c51d9 | note | M
ff0c3c0e-1db4-5686-bb07-f8d84bb55ec1 | note | Frequency - At any point of pipe
eb5fa07b-83cc-5234-a87e-4ccaa14464e8 | note | Conformance Criteria - Position tolerance for pipe laying at any point along the length of the installation shall be within ±30 mm from the specified design.
cd57e1f6-4447-5f5f-9698-caa98fcce5ac | note | Records - FH Drainage Line Record, Survey Data.
66064578-149d-5290-a1bf-0c7be22e5566 | note | FH Initials - Site Engineer
| checkpoint | 10 - Trench Backfill - Placing & Compacting
664dd556-4acc-59d6-b31a-9bed92493af2 | note | M
f5aa13e0-6080-5e88-9435-91fed1c9e735 | note | Detail - Placing and compacting of Trench Backfill Material
7ea5bad9-82b7-5ec7-b311-ca234096d086 | note | Frequency - Throughout Trench Backfilling operation.
097d9da1-bc58-5e1c-877e-9c8a174416ee | note | Inspection / Test Method - Visual Inspection
a8f7a827-9968-5ec4-9aaa-cd7cc9c483a3 | note | Conformance Criteria - Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm
30ddc257-3a79-5374-9bbc-b13d70422d8c | note | Records - Construction Photos
8b666aa4-e984-511b-b8eb-d80d7014b38c | note | FH Initials - Site Engineer
| checkpoint | 11 - As-Built Drawings
dbb16b58-9546-5e87-8e26-60f8859157a0 | note | W
255ed7d8-2093-56d6-abce-be23dc107bb4 | note | Detail - Red pen marked-up As-Builts of every 'Issued for Construction' AT drawings
8c89e7a7-3dca-5a43-857c-cbd34ab4d171 | note | Frequency - Final As-Built Drawings to be completed within three months of the construction completion of the asset or infrastructure.
eb1e678e-36c0-56e6-89b9-799924a8c756 | note | Inspection / Test Method - Drawings / Visual Inspection
3f7b8500-c4cf-5d37-beef-f44ef1f54620 | note | Conformance Criteria - As Built and GIS Data
a54c8491-54f4-5661-89ba-ee7fc2380c47 | note | Records - Redline As-Built Drawings, scanned as .pdf files.
c8de229d-5177-5e67-acfb-549b8fb25fd5 | note | FH Initials - Site Engineer
| checklist | ITP - Griffen Park / Hillsborough Rd - Footpath, Kerb and channel | itp | Footpath, Kerb and channel | 10588cb3-57b9-456a-b0fe-6fdb07b4d72c
| section | Site Set Out
| checkpoint | 1 - Site Set out
9cb7f9d0-f4fd-573f-bc43-9d65ce94de01 | note | Verification Activity - Surveyor
07b38422-c2c4-5b64-b973-795a28a8f9a8 | note | Methods Or Reference - Surveyor
2b7857c2-d1b4-5510-b4a5-8ceab34073d8 | note | Frequency - Every Site
0ca28e5c-9b48-5f02-9f76-9171a2de072c | note | Acceptance Criteria - Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
fc394b66-1e71-54fb-9b75-0b4d8eb7061f | note | Mandatory HOLD POINT -
007458b3-e4ac-5419-a29e-487c93afbfe6 | note | Records - Survey Receipt
91f3e4e0-cb79-50fc-ac40-29802c803daf | note | Onsite Responsibility - Site Engineer
| signoff | Mandatory HOLD POINT
| section | Materials
| checkpoint | 2 - Kerb & Channel
f8100e9a-84fe-5c98-9d2c-46672f6dda7c | note | Verification Activity - QA FORM
d1dec625-c940-5264-a0ce-c2c27ffc6040 | note | Methods Or Reference - TDM Technical Standards - KC0001
b0f1c951-02ee-5ac1-baca-8d4f2b787ff5 | note | Frequency - Every site
14c10331-f505-5098-be5e-f30a6281654d | note | Acceptance Criteria - Kerb & Channel to be precast hand-laid. Kerbing laid on 300mm min GAP 65 subbase in roads and 100mm GAP 40 in footpaths. (CBR>5).Concrete 20MPa @28 Days
3ee46141-84be-5d60-a195-11cfe558c576 | note | Hold Point - In Process Inspection
7949b657-d517-5834-b62b-a48b6469d661 | note | Records - FH concrete QA sheet, photos. Concrete Plant Docket
65bbcca0-4bd1-56ee-92d4-87f34162c94e | note | Onsite Responsibility - Site Engineer
| checkpoint | 3 - Channel Level
0784d71c-0127-523c-a2a8-44fbe48f3255 | note | Verification Activity - QA FORM
de1f98b6-b3f6-53c2-91e2-dc6462a7a27b | note | Methods Or Reference - TDM Technical Standards - KC0001
12eae072-ebee-5deb-b262-07bd87350c5a | note | Frequency - Every site
37b02556-4af7-55d7-a2fa-84a3df63efb9 | note | Acceptance Criteria - Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
ad9032f9-e4b5-54c4-ab2b-28db9cd5d1ad | note | Hold Point - In Process Inspection
1baa0027-45a9-5d98-8410-27f0c934d089 | note | Records - FH concrete QA sheet
cc67d6d1-45f2-5dc8-a6f8-356e208dcfba | note | Onsite Responsibility - Site Engineer
| section | Construction
| checkpoint | 4 - Concrete Footpaths
f91f665b-0ce5-59a0-ac60-a1502ca11e63 | note | Verification Activity - QA FORM
1cfca176-04ed-5f87-bf04-92ad4dba2b7b | note | Methods Or Reference - TDM Technical Standards - FP0001
6fb2008e-3263-5ac8-bc3d-0cf294f644a3 | note | Frequency - 10m Intervals
c9bf13e6-b449-522e-8e0f-4b3acde7d83f | note | Acceptance Criteria - Subgrade -(CBR > 3) Base course - 100mm min. thickness GAP40 Clegg CIV > 12 Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 black oxide Exposed Finish
3719710d-1554-525b-8784-3f46b3ce469b | note | Hold Point - In Process Inspection
9e1ed6b3-cd63-57ed-be65-4e9f79c1302e | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
efd061dd-54ed-581f-810b-68c4ff5c662e | note | Onsite Responsibility - Site Engineer
| checkpoint | 5 - Grass Berms
b59e9b8d-6589-5b5d-bbbe-5de0c5e8a31d | note | Verification Activity - Visual
42897cd8-8a69-5629-a092-633a14c14b71 | note | Methods Or Reference - ATCOP Section 12 Footpaths and Pedestrian Facilities
ef4cc5b3-0032-518c-8446-27eb004e2368 | note | Frequency - 10m Intervals
56e241c3-a765-5d13-a7c9-9e00b3866489 | note | Acceptance Criteria - 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
d911584f-6c03-54ec-9fb0-4209142d9a3d | note | Hold Point - In Process Inspection
162bab1a-8c85-5ca3-83ad-9e5e3f8b7f03 | note | Records - Photos
83fa8a0b-f0d3-53cd-8eef-1766fb73efdf | note | Onsite Responsibility - Site Engineer
| checkpoint | 6 - Tactiles
b37b7ab2-6a2f-5a7f-b3d5-3e9979a67ef3 | note | Verification Activity - Visual
33c3bc13-0ccf-54ed-a048-a870f90eede6 | note | Methods Or Reference - NZTA RTS Guidelines for facilities for blind and vision impaired pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
3b5bc17b-d9e9-585e-b0ef-443502b7befb | note | Frequency - Every Site
73c57123-5031-5db4-a187-e8e5ba91093b | note | Acceptance Criteria - Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
aecab37d-f22c-55df-ad79-817ae19de02d | note | Hold Point - In Process Inspection
5be76b05-3726-592e-90bc-facbc35a01c6 | note | Records - Photos
4f3110e0-dfff-5d53-98a3-28715aa79da8 | note | Onsite Responsibility - Site Engineer
| section | As Builts
| checkpoint | 8 - As built information
7b0808c8-c738-56e1-8545-4328cfa497b6 | note | Verification Activity - RAMM DATA SHEET
4072d864-c50f-58d1-8698-cb54c98eeebe | note | Methods Or Reference -
91581691-59c4-527c-b82b-ec96eea1934a | note | Frequency - Every Site
0f721d55-721c-59c9-b982-3df05778cb22 | note | Acceptance Criteria - As built drawings and Ramm Sheets Completed
4a50ee88-3f7f-5123-b0bd-54bcd33ebaa9 | note | In Process Inspection
16d925e7-3018-5706-bf01-f3520daaa758 | note | Records - As Built records
a553d09a-a1b6-5a9f-8e5e-fb9366bc3db7 | note | Onsite Responsibility - Supervisor and Engineer
| checkpoint | Final Inspection
9211ba56-12b2-553d-9bb6-03f6938f65b0 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
53f6b9cb-5dec-5bd7-bf46-da070ca6195a | textbox | Print Name:
143dc8dc-d53c-5636-b385-b5909073fd51 | textbox | Position:
ad1f1e6b-2fcf-53c6-9dd2-59ad4e7d8ead | textbox | Date:
| checklist | ITP - Griffen Park / Hillsborough Rd - Pavement Construction | itp | Pavement Construction | b6aae83f-309d-4f90-a1eb-c1b43d19bc87
| section | Precom
| checkpoint | 1 - Permits & Services
62e9973d-2985-52e5-8fd3-ca26d5cf0154 | note | ACTION (Hold, Monitor, Witness) - H
5d0e4bf9-9527-5947-ab77-9c33fe9dfb2c | note | Detail - Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
b5f7d7b8-dcc0-54ff-a987-f1480610f3a9 | note | Frequency - Prior to any construction commencing
4d9937b9-ff35-5e72-9191-0aa49282da91 | note | Inspection / Test Method - Document Review
0419ed67-41bd-5b2d-9853-026f608de7b5 | note | Conformance Criteria - Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority
34a417ec-8853-5e73-8e55-18e6635957a1 | note | Records - Permit attached or permit number noted.
28596e92-587c-5b02-9919-2bd156748883 | note | FH Initials - Site Engineer
619d35b7-45ad-5328-aac0-e2185c34101b | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
a6fa1bcb-b095-5963-901d-4a9aaf28678d | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 1.1 - Permits & Services
08e11552-d49a-57e3-b947-62e77bf4b8b5 | note | ACTION (Hold, Monitor, Witness) - H
7f08386a-5ab7-5b83-80a1-b2d648e395e1 | note | Detail - Locate and mark out all existing services
7334d9be-1a65-54c3-a76c-8520b68914d7 | note | Frequency - Prior to any construction commencing
b55fd00c-8349-57a0-81e1-6cc0d312eb1e | note | Conformance Criteria - B4u dig procedure - follow utility protocols
6d7238b4-0658-5b61-8b18-db5ef17d8d5f | note | Records - B4u dig plans
5b559521-d19c-5ba3-9c62-c55b4b7feddb | note | FH Initials - Site Engineer
bb856e89-5355-5d00-a05d-3d04a1033979 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
8a8bdd00-cbe6-536e-a914-d72d364bfdaa | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 1.2 - Permits & Services
db6b4c36-ebfc-59a8-980e-8498bd04dfdd | note | ACTION (Hold, Monitor, Witness) - H
2cdcb174-a35a-5438-96ce-f99a748148da | note | Detail - Approved TMP
7dbd59cf-ad94-5f02-b10b-9adacdaa0061 | note | Frequency - Prior to any construction commencing
92928bf1-dc10-5ab9-90a2-4b881ba8dd23 | note | Conformance Criteria - Approved TMP and WAP onsite before establishing traffic management
3fa7ba7e-c0a2-5c04-a99a-7f4dbb994513 | note | Records - TMP Plans
feb5b156-a39b-58d5-881e-9a520c69df1c | note | FH Initials - Site Engineer
8e766ea6-f3c3-5fe5-80ce-9479538b7906 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
6e7c5e90-d6fb-597c-bcc5-b8a543da04c3 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 2 - Pre-Construction Sign Offs
cfcd0342-b448-54f2-ab73-9b0459077e09 | note | ACTION (Hold, Monitor, Witness) - H
27e0d633-aa76-5c2b-b021-c56264880693 | note | Detail - Sub-Contract and Supplier Agreements
54fb54be-9512-5b43-ba97-a354d2640fcd | note | Frequency - Prior to commencement.
09c419e5-5edd-5000-853f-7505195cf9a6 | note | Inspection / Test Method - Document Review
dd265cf7-634c-568f-8039-1e8c5816738b | note | Conformance Criteria - Sub-Contract and Supplier Agreements to be agreed and signed
6b7ee0d8-a284-533c-8ab1-6a32307ebd2f | note | Records - Subcontract and Supplier Agreements
e4783062-ce5c-5837-9e07-0c8bd737b3b8 | note | FH Initials - Site Engineer
2f116d7f-3701-5ea0-bb10-4ceddd1a2f18 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
6af2bc42-7efc-5c88-8aea-796b61a5a150 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 3 - Design
d6cd7bfa-37ef-5e81-b201-6ba113ffe3ba | note | ACTION (Hold, Monitor, Witness) - H
3be2259e-5dca-5745-9dae-4b14d4151871 | note | Detail - Design is approved and Drawings are of the latest revision.
9aee4f63-cee9-5716-9d02-8bc2e0771f9a | note | Frequency - Prior to commencement.
ea583c1f-1fa5-5524-a416-cd26b5392c1d | note | Inspection / Test Method - Document Review
fdcde257-310a-5b68-bffb-00260c47d876 | note | Conformance Criteria - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
c9ff9232-4af1-5290-bd54-3a2bac63637f | note | Records - Drawing Register.
0b1113ea-e101-50e8-a409-e7370171592f | note | FH Initials - Site Engineer
d497e045-3cb1-54ad-9d90-fb9d587fda7a | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - Engineers Rep.
ce68d538-b3fe-56ae-97a0-cf484ea27e85 | textbox | Date Completed:
| signoff | HOLDPOINT
| section | SAC Pavement & Surfacing
| checkpoint | 4 - Bitumen
429347cf-d5f3-553b-9a2b-fd96022fa33a | note | ACTION (Hold, Monitor, Witness) - H
2781e25b-f19d-5e2e-9147-a88639f5dad8 | note | Detail - NZTA M/1
16f2a62d-ea3f-589a-a598-69139f3b88b1 | note | Frequency - Passing all tests listed in Table 1 of NZTA M/1
c908ae02-dcfb-5dfd-ac3c-51e1b02d6e4c | note | Inspection / Test Method - Testing
9a0fdfe2-416d-5c99-9603-c82d87897930 | note | Conformance Criteria - Passing all tests listed in Table 1 of NZTA M/1
c2ae3dee-e55a-5821-96a5-9ecfaef97c58 | note | Records - IANZ Lab results
611535d9-dc35-5766-84bf-e58e44ff36bb | note | FH Initials - Site Engineer
da06984a-f3bf-5c27-8040-a729c9022cd8 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
acd83318-13fe-55f3-97ce-3a59012a4cd5 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 5 - Asphalt Mix Design
6f6280e5-9bfa-5cb9-a878-0eded63ff960 | note | ACTION (Hold, Monitor, Witness) - H
ed2e50ac-aed9-5d82-8a16-6d05dc4e4678 | note | Detail - JMF approved
53bffc8e-be36-5954-9e3c-4fdb797eee88 | note | Inspection / Test Method - Review
d3fe68b5-7d6a-50a7-87bb-6ea4f55bb884 | note | Conformance Criteria - AUSTROADS
80a96a9c-1c33-5322-938c-0c74c4fb0a45 | note | FH Initials - Site Engineer
2b8eb1c7-f5d6-52d0-acd2-ec1abffb05bc | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
382b27d6-06d3-5372-875b-be6ee983efe2 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 6 - Production Tests
b626332f-5b71-5fec-b846-5675a4d01a71 | note | ACTION (Hold, Monitor, Witness) - M
8ab83956-0a65-5547-aa2c-05b5b7776a89 | note | Detail - NAS 2004 & TNZ sup to NAS 2006 TNZ P/9P (M/10 Table 5.1)/
36f99a93-a83d-5fb1-87db-032abd082739 | note | Frequency - 1 set every 300t
1170b6b3-7899-5b96-b5b3-bf883f0cf1fb | note | Inspection / Test Method - Review
ed2dd645-1dd5-591b-bd8d-60edc214645d | note | Conformance Criteria - NAS 2004 & TNZ sup to NAS 2006 TNZ P/9P or NZTA M/10 - Grading, Binder content, Max Density, Temperature
1e03b675-d1cb-55d7-96eb-5865313f0c27 | note | Records - IANZ Lab results
dcab5ae3-5897-5c49-86d9-37cfcd6d99d0 | note | FH Initials - Site Engineer
9d9a5560-33b7-5c40-9edb-c3720b81babb | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
e106788d-5ac3-5718-8674-6f6990b0f9c0 | textbox | Date Completed:
| checkpoint | 7 - Check Weather Reports
1fd64a46-2df3-5c17-a385-cfdd4ee9ce17 | note | ACTION (Hold, Monitor, Witness) - W
adb096e4-c008-5c55-9f6d-5303c4bd3b3f | note | Detail - No fog, rain or wet surface. Base temp greater or equal to 7 degree celcius
9627214b-308f-5f58-b592-7701bc47ab46 | note | Frequency - Weather call the day before
b06013e1-e74a-5372-b5ff-987d5fd5c4c0 | note | Inspection / Test Method - Visual
261246ab-0820-5e22-868d-2591706b79fc | note | Conformance Criteria - Forecast and thermometer
54be454d-455d-5495-8ecb-5b77b92f3b13 | note | Records - Radar and Asphalt QA
a332f882-6058-5b97-b71b-49b36d43801a | note | FH Initials - Site Engineer
6e91370b-a5fb-54eb-a0c4-79dc2f7decbc | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - Design Engineer
f23790eb-022f-59d2-876e-0f1b50bb2eb5 | textbox | Date Completed:
| checkpoint | 8 - Pre-Seal Inspection
b432d070-ba6c-56c8-a245-297d8965141f | note | ACTION (Hold, Monitor, Witness) - H
9d810e9a-42c7-538e-8626-dacbf651befa | note | Detail - Surface finish
e6d6e0ce-f8db-5d29-93dd-8c430ba4ea5f | note | Frequency - Continuous
4713723d-d27a-5fee-bf93-9a414786cdee | note | Inspection / Test Method - Visual
a9c35315-900e-5d6f-a920-045871524926 | note | Conformance Criteria - The surface must be clear of deleterious material and not choked with fines. The basecourse surface must present a stone mosaic surface with larger aggregates protruding and not appear damp
4286fcd7-acfe-506c-a92b-747d6d7abe4b | note | Records - Sealing QA
d754f4bd-7f76-5ecd-8334-1ecace206a15 | note | FH Initials - Site Engineer
9544ff27-61de-5dbd-ada1-204372bf2414 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
06fcb880-bf0e-53d2-b78e-24ccd720be32 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 9 - Tack Coat
348fe02d-0d0a-5953-928a-e28955ce4006 | note | ACTION (Hold, Monitor, Witness) - M
c90352fa-eac4-5414-a7d3-1f19a16d1b32 | note | Detail - Minimum residual binder application of 0.3l/m2
16bf9594-906c-5f36-a6ed-24b657c664ff | note | Frequency - Each Run
bb34cf32-90de-5de3-9cab-f8df6abc6d14 | note | Inspection / Test Method - Testing & Visual
3a148a16-dbdf-5ac9-92f2-50f789827f5d | note | Conformance Criteria - Each spray of bitumen
972aa670-195c-5432-aa51-7581d90e3171 | note | Records - Asphalt QA
06af291c-45d3-5629-83de-3c0f8df6177c | note | FH Initials - Site Engineer
ed999465-ddd5-589d-8daf-41826f928829 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
83ce7160-443b-5223-a114-f62883391626 | textbox | Date Completed:
| checkpoint | 10 - Construct 200mm AC14
c2bb42a1-5a8b-51c3-9fbc-c7aeb660686f | note | ACTION (Hold, Monitor, Witness) - M
a0223181-e810-53f0-8ae4-9463c7a36358 | note | Detail - NZTA M/10 NDM and Stringline
95d8cb58-f2ad-5e16-928b-92290731150b | note | Frequency - Each Run
488dfbc2-3e93-53bc-998d-295c83fa83e0 | note | Inspection / Test Method - Visual
a91f098e-b44b-5c80-81ef-6975f361fdda | note | Conformance Criteria - Construct 200mm AC14 in 4 layers
ef18f913-cf3b-5e54-818a-e05fc085b632 | note | Records - Asphalt QA
dd320178-354a-50e6-91af-53d6536c8116 | note | FH Initials - Site Engineer
753517e4-72e3-5a29-a352-8c2ba41a7d46 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
630311d2-af89-5e9a-b309-53431d99407a | textbox | Date Completed:
| checkpoint | 11 - Construct 135mm AC14
0c399d57-7df4-5fa8-8115-7dd064376cfb | note | ACTION (Hold, Monitor, Witness) - M
864bdfc4-9572-5369-ad60-d0dbd285951a | note | Detail - NZTA M/10 NDM and Stringline
3976ec94-5be4-549f-b239-04c959152463 | note | Frequency - Each Run
a7db12a0-e2aa-5e96-85f4-e6ceac8e9a0b | note | Inspection / Test Method - Visual
64b80b23-c00f-598b-933d-e0b9c9d85490 | note | Conformance Criteria - Construct 135mm AC14 (75mm bottom and 60mm top)
c4328220-26a4-5536-98ac-8670a37496de | note | Records - Asphalt QA
ed751680-9288-5d74-827b-4ec002ada401 | note | FH Initials - Site Engineer
80c486dd-80b9-5ffa-81fa-80f0a5c9e5f9 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
40d10487-6bed-55ca-a7c4-11e513b4fdae | textbox | Date Completed:
| checkpoint | 12 - Two coat Grade 3/5 racked -in seal Grade 4 Membrane
4fa95990-acc7-51a4-9cd8-8923ba02c28f | note | ACTION (Hold, Monitor, Witness) - M
e2d18a0b-42a6-500f-bc71-6f8dd5bd157e | note | Detail - Construct a two-coat Grade 3/5 racked in seal or G4 membrane (min residual bitumen application rate of 1l/m2)
15828872-e20b-5496-bc34-39ecfcd3d953 | note | Frequency - Continuous
9d41d0a5-794b-552e-9996-e0483e78c968 | note | Inspection / Test Method - Testing & Visual
51875954-4a2d-5be0-93ca-a4fafa890f9b | note | Conformance Criteria - Tank dip tests before and after application to confirm application rate. Additional PTR rolling to imbed the aggregates into the bitumen
5c516500-f7e4-5242-8cbc-a940335b97f1 | note | Records - Chipseal QA Photos
28a5bbb5-4b79-5112-96a8-efe1efb5f5a7 | note | FH Initials - Site Engineer
44a94569-4045-5834-8e63-d047323bc444 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
ad4b66de-c995-57ba-bb67-22e00bcab5a4 | textbox | Date Completed:
| checkpoint | 16 - Construct 40mm SMA 10
d47e389e-3c23-58d1-a3a5-8c62eaa35d5c | note | ACTION (Hold, Monitor, Witness) - M
00e20e68-3bcb-5ef9-b3d9-e44b9e5b1344 | note | Detail - NZTA M/10 NDM and Stringline
b19a3f63-9dff-587c-9439-2b02763b8fcf | note | Frequency - Each Run
ce9e4326-ae0d-5780-9a96-469761fd4962 | note | Inspection / Test Method - Testing & Visual
b6007f04-b757-5040-8c55-921b3b7f5d6a | note | Conformance Criteria - Construct 40mm SMA10. - Design air voids 4% and level tolerance of +10mm, 0mm. NDM testing undertaken in accordance with NZTA M/10
5105e4e2-ad44-50a5-8880-d879d191956f | note | Records - Asphalt QA
87d532b0-192a-577c-ac12-7ef5855b33bf | note | FH Initials - Site Engineer
765ccc82-cf67-5651-bf4e-c077478dfc37 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
63a3e579-65ea-54ee-9191-13f87840b7e3 | textbox | Date Completed:
| checkpoint | 17 - Surface Finish
83401896-2264-5311-813e-3199fb955892 | note | ACTION (Hold, Monitor, Witness) - W
5f29f441-fe54-5bf9-a48f-b8d9c3da26e2 | note | Detail - TNZ P/9P
a42267c8-2f35-5c72-95fc-0b77338671f5 | note | Frequency - Each Lot
1f42c0fb-a205-542d-a095-dd3b234be638 | note | Inspection / Test Method - Visual
48fa1917-4a75-5a39-b30f-276f8c242263 | note | Conformance Criteria - Inspection: Uniform texture, no roller marks, no bleeding, cracking or shoving, no crushing of the aggregate
1603aa22-60ac-53b4-a0f5-2e5b16c33666 | note | Records - Photos
b676c852-4338-51a0-b93b-923cf60bf03c | note | FH Initials - Site Engineer
e11ce0cb-05a6-5474-bdd2-6f82e61cfe63 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
6918319f-02ba-5cef-92b1-df876da9dcd9 | textbox | Date Completed:
| checkpoint | 18 - Reinstatement of Line Marking and RRPM's
22c08cc3-059a-5ff3-bae6-7f1612d19eb8 | note | ACTION (Hold, Monitor, Witness) - M
a71ce275-6bd4-5dac-b031-7b38b443ec08 | note | Detail - NZTA M7 approved (Class B or C as required for anticipated traffic level)
c56baa27-8df9-5561-8d76-d6873331aa1f | note | Frequency - Every site
51fa94da-e2e5-545f-a297-027642a052c4 | note | Inspection / Test Method - Visual
d8be3409-69fd-5a61-8df5-9257724756f2 | note | Conformance Criteria - *Carried out within 12 hours of each shift completed and as per the existing markings * Suitable Traffic Control to remain in place until pavement markings have been reinstated
275b96c4-1d47-5737-84fc-ecb4f5527172 | note | Records - Photos
03443722-84a0-51fa-81af-6b7ca4469afe | note | FH Initials - Site Engineer
02b4dc73-acfa-5ccc-bbc8-dff36e72dd8d | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
920766ce-0978-568b-8674-42623f51410b | textbox | Date Completed:
| checkpoint | Final Inspection
d37828da-8ce1-573d-8ba4-676da562c458 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
dc20f5ea-9fa1-59c9-944f-fac4c939c7ac | textbox | Print Name:
c2be89c4-fd59-537f-9c00-508557019143 | textbox | Position:
53df3eae-668c-55de-9fa2-3bc499e15ab6 | textbox | Date:
| checklist | ITP - Griffen Park / Hillsborough Rd - Raised Pedestrian Crossing | itp | Raised Pedestrian Crossing | 675ee30c-c74a-4b2a-ab55-b8dcda36facf
| checkpoint | 1 - Permits
743f394e-1f78-52f6-aec0-910b3b43ae95 | note | ACTION (Hold, Monitor, Witness) - H
998a48d4-e80b-5f20-b631-1aada1adee71 | note | Detail - Obtain Permits
666a9c98-f835-5152-b5cd-3535630d0f3f | note | Frequency - As required
08cc6d70-9440-5e20-be3f-858ef4791eb7 | note | Inspection / Test Method - Document Review
e3434a21-35cb-50b1-980c-1212617e96e4 | note | Conformance Criteria - Control Checklist - Fall Prevention (if applicable). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
7f2b3bd0-3b89-50d0-9f59-85a0042830c9 | note | Records - Permit attached or permit number noted
37be8491-7d5c-5783-ad10-a6613d94c74f | note | FH Initials - Site Engineer
22c54d89-f7a7-51e0-a959-6bb77cf59392 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
b4233b3f-cccd-5ffd-81a3-01734d1e5cde | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 2 - Pre-construction sign offs
bae3bc52-53bb-58c5-b721-e32484f3fcb1 | note | ACTION (Hold, Monitor, Witness) - H
e73a868a-5f84-5fbd-a302-4a01654cece4 | note | Detail - Ensure that Sub-Contract and Supplier Agreements are signed
f4858514-89b9-5705-9826-62259ffa32f0 | note | Frequency - Prior to commencement
7593d285-e993-5888-8f51-a48d1ce69fbd | note | Inspection / Test Method - Document Review
e9bc0ac2-6dea-58e5-a341-88b8f894db41 | note | Conformance Criteria - Signed Subcontractor and Supplier Agreements
e60ac412-5583-5ba8-bcda-9d47c699c761 | note | Records - Subcontract and Supplier Agreements
155ddd22-b381-51ca-b2a0-b68de21f0c6b | note | FH Initials - Site Engineer
1c295914-e24d-5149-8570-c70064bff2ed | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
ce13ab75-88c3-5e28-b262-6d2757d3c569 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 2.1 -
f0e02900-ec89-5628-9463-fe3f66092844 | note | ACTION (Hold, Monitor, Witness) - H
fe1c8a81-835d-5c06-a045-5b3ce1d75a5a | note | Detail - Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
a6ae0a51-5c98-5c0d-987d-10d83cb3adb2 | note | Frequency - Prior to commencement
8ee6724a-715b-569e-b795-b327637b50e2 | note | Inspection / Test Method - Document Review
5562b31c-ad0e-561c-a818-fb5a8b83a209 | note | Conformance Criteria - TMP is approved by CAR manager for each site and works are only completed within the approved dates..
4bcd5265-2caf-5433-a334-e53ac3315d12 | note | Records - TMP on MyWorksites/On Site
f27849e2-bbfd-55f5-a961-412800913f1a | note | FH Initials - Site Engineer
3cd47e45-27a5-5a2c-8e6f-e2567892c8fe | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
9716d3b4-c05e-56fc-906e-326d23fa1ab4 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 2.2 -
e0b5672f-03f5-5293-ab99-7edfabcb79db | note | ACTION (Hold, Monitor, Witness) - H
fae9c712-bc53-512d-a687-21d76b1a4180 | note | Detail - Ensure all Subcontractors and Suppliers go through FH induction
26d22db6-16be-5b70-8ab0-a17b466635e0 | note | Frequency - On site daily
46fc0b1e-610f-5a5e-a455-90db7773cb94 | note | Inspection / Test Method - Induction
f90789be-4801-5635-add3-8229fffa2220 | note | Conformance Criteria - Supplier's and Subcontractor's signatures on hazard ID and pre-start documentation
e98a67d6-24f1-56cd-a776-e3f33797ba19 | note | Records - Hazard ID and Pre-starts to safety team
67409f98-7cf2-567e-a6f0-68d33ce8690b | note | FH Initials - Site Engineer
d317fa52-7f67-597b-aa30-dc19fee6355a | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
d5accf4e-bf41-50ac-86b9-312907b1af66 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 3 - Design
63ed5a53-6cff-5f1b-9518-397d19daeda4 | note | ACTION (Hold, Monitor, Witness) - H
10fdabf0-0457-5679-abb9-be76e4406cc9 | note | Detail - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
abe54447-b43f-512b-9e21-3d57c1c17862 | note | Frequency - Prior to commencement
70c8fca8-976c-5afc-8a8f-c4b06bc34678 | note | Inspection / Test Method - Document Review
bf8e9e1b-3d9d-57ec-9494-ba83b1d7bb49 | note | Conformance Criteria - IFC drawings have been received by Contractor
ed1bb690-ba26-51a7-8dcd-96b9ba536a0d | note | Records - Check Drawing Register
de3cc23b-0627-564e-b3ba-9c5b22bf7ea8 | note | FH Initials - Site Engineer
33676ce8-9858-5568-b52b-3d4d161870db | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - Design Engineer
c0dc5b1b-c807-5e35-8be6-de9bfe818b75 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 3.1 -
25705437-c9bd-539a-bba9-9c41c2c2fc15 | note | ACTION (Hold, Monitor, Witness) - H
d276058a-4003-5645-8f10-730da7af6688 | note | Detail - Crossing to comply with AT TDM chapter Traffic Calming and TDM TC0023
5cdcdfa2-83b2-557a-8e63-2a2ae65b9346 | note | Frequency - Prior to commencement
65365f6a-a024-549b-a37a-a16017974cfd | note | Inspection / Test Method - Document Review
bbec4002-7056-57e1-a5a9-4d8d9ac9214c | note | Conformance Criteria - IFC drawings have been received by Contractor
79c1235f-3b66-5e8a-8cf0-3896e92727e3 | note | Records - Check Drawing Register
55ccca84-e61c-566e-bd27-b1f431235e35 | note | FH Initials - Site Engineer
1a21cdb2-3771-51b6-a43b-9be59677ce5a | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - Design Engineer
7dffd69e-c453-5a50-bcf9-4eb26cf779bf | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 4 - Installation of Erosion and Sediment Controls
53972ef7-c899-558c-8397-dfd33197bc0c | note | ACTION (Hold, Monitor, Witness) - H
f8ec7f47-5847-5b6e-842e-7e8797d1a052 | note | Detail - Ensure that Erosion & Sediment Control in place
a38f7384-eb9e-5be1-88c1-afeaa5f70803 | note | Frequency - Prior to commencement
0ebf44ac-9405-5e3b-8bba-1548b2b69542 | note | Inspection / Test Method - Visual Inspection
7c66ad45-0c4a-5507-8258-eb5c320f9bef | note | Conformance Criteria - Cesspit Covered
dc991284-dfb7-59eb-9c18-464c37c3aeb4 | note | Records - Environmental Controls Audit
fd557d8d-b5a4-5a1f-9a10-eb75bfa9121a | note | FH Initials - Environmental Manager/Site Engineer
6e9f03f2-b28d-5747-8c1e-5e45cdd8d75f | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
6fc3f89a-798c-537f-b545-1a2fa587f1fc | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 5 - Survey Setout
305137f4-5c59-5b03-88ee-b856a54bfe25 | note | ACTION (Hold, Monitor, Witness) - H
e640d3ce-1028-5076-9e03-c81e213a67ae | note | Detail - Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations)
377190c7-dd4e-5cc4-9f84-3b61f7a92b3d | note | Frequency - Prior to commencement
2288be0c-7e60-5cf5-858c-1d4c4831a4ce | note | Inspection / Test Method - Survey + Smart Level
b2bee5c4-8611-533a-999f-1c130d740a8a | note | Conformance Criteria - Consistency with Construction Drawing
0282cf09-3fd1-5da4-b265-29152ed97b3a | note | Records - Site Photos post surveying
5a887695-d842-51b8-9208-a8be1a9d4520 | note | FH Initials - Site Engineer
b973ab93-add5-5141-8167-998dba3f619f | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
75a5911f-2ba2-5602-aa5f-8bcac3138b41 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 6 - Locate Existing Services by Hand Digging
191a74cb-5de3-5d42-845b-7dd535283257 | note | ACTION (Hold, Monitor, Witness) - H
d0fad140-2a9b-5dd6-b9b8-a23332a5db20 | note | Detail - Ensure all services conflicting with the line of trench has been exposed by hand digging
384b1d8e-7fe3-552d-93a3-27ef3d6cffd3 | note | Frequency - Prior to commencement
a0e260cc-2e80-53a7-8e7e-54e4abe1ce9f | note | Inspection / Test Method - Potholing
e2f73abc-4c62-5a57-8632-bf21d785d311 | note | Conformance Criteria - All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. As Built all services
28088d3b-7fd7-525e-8bb7-cebeb569cfb9 | note | Records - Digging and excavation checklist, service planes,As-Built Drawings Doc. Review
c68377d7-135b-5703-8e57-cc35ba2eb278 | note | FH Initials - Site Engineer
ae55524e-d959-5c7f-8b95-8e6e00dcdc55 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
f3e3c667-0585-5484-9333-d698758d938a | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 7 - Material Compliance
0ff5e9ad-1521-591b-b50f-291a45260d02 | note | ACTION (Hold, Monitor, Witness) - H
1bcdbf6a-0751-5061-be6b-15ab6d9c40d6 | note | Detail - LESA dowels to be used at all construction joints
3dc19584-4eda-5c30-adcb-109a7350d7d9 | note | Frequency - Prior to pouring concrete
ca43555c-b3e0-5bb9-89f5-ea1e0c6c8621 | note | Inspection / Test Method - Document Review
bc1b6618-6779-55b4-9f8e-594ab61e2189 | note | Conformance Criteria - Photos + Delivery Docket added to QA folder , TDM Standards TC0023
13a10bf1-ab5d-52ca-8e37-ac475c72db9a | note | Records - Delivery Dockets / Photos
6379e5ab-379a-5b1b-b5bd-376880d11d21 | note | FH Initials - Site Engineer
d2bcb7c2-30db-5388-b573-1cc3aea6b81b | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
948e68fb-6de6-581c-8193-29ab87a9bfe9 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 7.1 -
bd59d219-fa02-5776-8649-142c5e8a5789 | note | ACTION (Hold, Monitor, Witness) - H
4a250757-3fd5-5ffc-b80a-3aa3b5a8d072 | note | Detail - 0.25mm polythene layer placed across all surface area at bottom of raised table
a804a868-fce1-5d12-a726-bc08563986e4 | note | Frequency - Prior to pouring concrete
19bf6d34-e8e9-5791-986f-1f9eb5187842 | note | Inspection / Test Method - Visual Inspection, Document Review
17e7739d-43d0-5a34-b2b3-9f2d0c26267c | note | Conformance Criteria - Photos + Delivery Docket added to QA folder , TDM Standards TC0023
29d1f7fa-c96f-548d-9fa5-bbb7995bc5be | note | Records - Delivery Dockets / Photos
f8b13bb7-086e-50a7-bee2-c5dc4418bc14 | note | FH Initials - Site Engineer
110c62d9-c3b6-5047-b88d-1418975a325b | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
6ad95c36-1d7d-5f21-8606-e968d4fc47b0 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 7.2 -
71f92665-8b3a-533e-9618-e6448a2373df | note | ACTION (Hold, Monitor, Witness) - H
fd7dfe30-703c-58e9-9339-ac9f5d138ec1 | note | Detail - 30mm thick compacted layer of AP20 aggregate placed underneath polyethene layer.
3a9e850c-4adb-5bdf-8f33-b7eda8d298e2 | note | Frequency - Prior to pouring concrete
55bcfa59-608c-5b54-a5e4-0dc9e1763ab6 | note | Inspection / Test Method - Visual Inspection
0582f9cd-308d-5e1b-8eee-417f712ae3a7 | note | Conformance Criteria - CIV >15
0a0e7215-cb9c-5714-8025-c71a843532b6 | note | Records - Delivery Dockets
ec369f97-e4aa-5fb1-9b0d-d6ca2b8c7dd1 | note | FH Initials - Site Engineer
91be0faa-dac3-5d95-bd2c-696c40fc1948 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
af6dbaba-36de-52f6-a7ad-49ad1c842c68 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 7.3 -
1e5338d9-3bfa-5279-89a8-fe703970d03a | note | ACTION (Hold, Monitor, Witness) - H
9c3ca01b-8f8f-59ca-9578-926110b2992a | note | Detail - Two layers of 663 mesh 50mm cover from top and bottom to be placed inside with 70mm plastic chairs separating.
fe4fa732-483b-53cb-97cc-a0406f431937 | note | Frequency - Prior to pouring concrete
dde606a0-2300-5938-8ed5-7b42d0133a07 | note | Inspection / Test Method - Visual Inspection
1df720ab-e3dd-5cf3-a476-793a1181c593 | note | Conformance Criteria - Photos + Delivery Docket added to QA folder , TDM Standards TC0023
86856948-e7d7-57d9-99a2-c59f32954e00 | note | Records - Delivery Dockets / Photos
8b1d09ab-8860-5673-878f-e60c6ed2e64d | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 7.4 -
3f26db56-e3e5-595a-bc01-8c7ecfd7e630 | note | ACTION (Hold, Monitor, Witness) - H
3009b2b9-7220-5e26-bfc5-2023896048d9 | note | Detail - All concrete delivered to site shall have 40MPa 28 day compressive strength with 4kg/m3 of Black Oxide Powder
91a1d8f6-eab9-5daf-aa48-513bb075f872 | note | Frequency - Prior to pouring concrete
ab2ac2cb-4ffb-5f28-87d4-4c6cb592e68e | note | Inspection / Test Method - Concrete Delivery Dockets
ec9c1931-d912-5069-bfb7-add9d74ae8cd | note | Conformance Criteria - Delivery Docket added to QA folder, TDM Standards TC0023
3c35015f-79cf-509e-a794-3ed1670a4f35 | note | Records - Concrete Delivery Dockets
1d28e43f-7eae-5b4b-affd-9e74959a0b4f | note | FH Initials - Site Engineer
066a4953-90ab-5678-b3e9-22b4060d215e | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
1a97805a-0b49-5cd6-8dc3-b6e9a440d4b8 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 8 - Temporary Works (Formwork)
87c1b134-d5c9-5c3b-a42c-cd92ca3337b2 | note | ACTION (Hold, Monitor, Witness) - W
71f242ab-1bbf-5b9c-854e-58ce58f7a011 | note | Detail - Formwork to be set to correct line and level
1a38cd38-a690-5de6-bafb-c6366a2c8e52 | note | Frequency - Prior to pouring concrete
49ff6c72-6b6e-5865-a9b2-750e07c42ad5 | note | Inspection / Test Method - Visual Inspection
5a1f82a8-d4c6-5611-b00c-a78fdc793b26 | note | Conformance Criteria - Concrete Inspection Record
06e3a4f4-79e0-5dc8-8eeb-c65117c42f52 | note | Records - Concrete Formwork Checklist
ddb5e725-f1cb-5aa7-8fa2-d98ab3b91d8b | note | FH Initials - Site Engineer
8e0fa104-690e-55d7-be16-cee604a76bdc | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
9c7152a8-697b-502c-9440-5971d9561e06 | textbox | Date Completed:
| checkpoint | 8.1 -
c62b26f2-d091-509c-b942-8616cd4eefb7 | note | ACTION (Hold, Monitor, Witness) - H
22273b0c-c6f4-5422-9359-6405067ed7be | note | Detail - Raised table formwork to be 75mm above existing road level and be 300mm in depth and gradients respectively of entry and exit ramps
d0efd942-ce5a-5212-826a-70f3bcc4c164 | note | Frequency - Prior to pouring concrete
6f3103a0-3e7c-5492-8d62-1b62032b0806 | note | Inspection / Test Method - Measurement
19e3e988-cb4a-52a5-a6ed-b0789d5eaae4 | note | Conformance Criteria - Designer to inspect formation level
269c91e7-9322-5b90-a6a3-f04a881cb1a4 | note | Records - Site photos
3c577486-4b8f-546e-8b31-b3d1028560a5 | note | FH Initials - Site Engineer
b2e3e3b0-1b3c-51c1-9411-7bb1fffc5e99 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
5c91497a-2cac-53db-94aa-dc21fa742b0d | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 8.2 -
b1d12a44-ca5b-516c-a58c-a71f33bdc255 | note | ACTION (Hold, Monitor, Witness) - H
9a3e3591-eb15-5cc1-bd92-990820b88704 | note | Detail - Raised Table ramps to have 200mm depth at entry point and tie into 300mm depth to meet raised table
5c129969-97b0-5178-bd1b-cf149595f9b6 | note | Frequency - Prior to pouring concrete
60750d07-dd68-50ed-bda4-f1104cf8462f | note | Inspection / Test Method - Measurement
d469926a-86e4-5e0b-888b-ada55a52fb02 | note | Conformance Criteria - Designer to inspect formation level
4c616c76-c41d-5fd1-a115-03ff487cfe6b | note | Records - Site photos
4b809eee-57f3-549c-95ae-2bba693d5d06 | note | FH Initials - Site Engineer
2ee74086-09f8-5106-bf37-abf4eba01fe9 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
07abe915-c43f-5e32-870f-c13c01994773 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 8.3 -
44d50171-35a5-5695-993a-e00fb93f8f98 | note | ACTION (Hold, Monitor, Witness) - H
e24e550e-20b4-52f6-bf3c-c6f260e10e60 | note | Detail - Raised Table ramps to be 0.75m across for entry and 0.75m for departure ramp.Toe to be 0.5m across for both entry and departure.
70574e7a-9aae-5680-bd36-97ad03965059 | note | Frequency - Prior to pouring concrete
1713efd0-8f10-5983-b2d4-563219ce1ed4 | note | Inspection / Test Method - Measurement
b601970d-15fa-5c93-9f00-00f8ac952aac | note | Conformance Criteria - Designer to inspect formation level
d2150279-31e9-5a8f-975b-58c669a43c86 | note | Records - Site photos
820740d0-3aea-5e1e-b430-cedd5d5fb833 | note | FH Initials - Site Engineer
0cd0c48c-5fc6-5842-b3c8-eff4084f3f4e | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
f95ebe8f-4aa7-57c5-89a2-7c2b916d2ad4 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 8.4 -
1078e69c-6c7f-5d25-b5da-c6924faf4c92 | note | ACTION (Hold, Monitor, Witness) - H
3979e85a-5acf-589b-b455-3720b9675e31 | note | Detail - Raised Table ramps to be 1:10 gradient for ramps
1653c6c8-d44a-5c8d-91e2-a9194b76f3bf | note | Frequency - Prior to pouring concrete
38fcc4c2-f175-5f49-b253-cef8d13e58d2 | note | Inspection / Test Method - Measurement
6bf6ae18-a16f-5ec5-a92b-aed2544e163a | note | Conformance Criteria - Designer to inspect gradient level
3f3ad05c-78ba-5370-b036-bb5a4046dbb0 | note | Records - Site photos / Concrete Formwork Checklist
e1e3a7d9-2dbd-54f0-babf-9252e8f24820 | note | FH Initials - Site Engineer
cd580057-d419-53c0-a1c5-370c940b25be | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
2d7ce3d3-acc4-536a-b63d-4fc9d7b293d0 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 8.5 -
1e56cbdf-b19c-54fe-a09c-c78dea2fa1e9 | note | ACTION (Hold, Monitor, Witness) - H
0e84f1d4-cf27-5a66-97ad-215e00dc6d81 | note | Detail - The Site Engineer and MSQA Engineer must sign off the formwork prior to concrete being poured
216edd0e-b45c-58ef-8b6d-6eadd63de2c2 | note | Frequency - Prior to concrete pour
b376dae0-2cb8-5563-a525-fdb35d449609 | note | Inspection / Test Method - Visual Inspection
97f60df9-ad87-5395-841c-f4577a648683 | note | Conformance Criteria - Concrete Inspection Record
3d2c51af-fcd3-58d1-a3c4-e598b12c272a | note | Records - Concrete Formwork Checklist
dfd4d08f-8f5f-5760-85f0-fc3a17cfe282 | note | FH Initials - Site Engineer
f413907a-a41a-56f9-985c-59a00d51b851 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
00841943-1307-5d0f-9a07-c7a916517572 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 9 - Reinforcing
d2358297-f736-567c-b800-e3e61f8dc0f1 | note | ACTION (Hold, Monitor, Witness) - H
9030bec8-48f9-5271-99b3-2dd72e17fc04 | note | Detail - Construction joints on speed table to ramps are to contain 2 rows of LESA dowels or similar approved dowels . Dominator dowell system 50mm w/ Black 300*50*6mm plates @600 centres placed across the construction joint and for joints from ramps to toe slab @400mm centers
68bef280-9c04-5157-8ff4-6d6dcdcd3ee9 | note | Frequency - Prior to pouring concrete
b31272ac-1b6f-58b3-9d54-371b280dfc1a | note | Inspection / Test Method - Measurement
e52acfd2-93fc-5164-9dca-d1b4c2bbc951 | note | Conformance Criteria - Concrete Inspection Record
75cb88dc-06b6-51b9-b3b0-ea6d87546b4f | note | Records - Site photos/Concrete Formwork Checklist
4baabccb-becb-5fba-ae6c-5f696f625138 | note | FH Initials - Site Engineer
fe9c1b92-4bb6-567a-acfe-a491697f85fd | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
aa60d608-cb15-5521-a5af-840729d038fa | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 10 - Concreting
a8654745-5d38-50fa-83a2-9e0dc1b49650 | note | ACTION (Hold, Monitor, Witness) - H
9190573e-f479-50b7-ad2e-f50099aa57a6 | note | Detail - The MSQA Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required
ab3ddc60-e747-56ca-8f7b-acf067cc2722 | note | Frequency - Prior to concrete pour
c9aec916-bff7-52e2-bf69-7d814c7a4e5c | note | Inspection / Test Method - Visual Inspection
446a8326-24a1-542a-8b2b-1ca8d8a72110 | note | Conformance Criteria - Engineer will be notified via email/SMS at least 24 hours before required for inspection
fc2b2a4c-3c50-5c32-a635-d188fab8536a | note | Records - Email / SMS
37ed9620-c762-5f0d-b3e1-0a3830e4eaa2 | note | FH Initials - Site Engineer
3234fc09-7b3f-552b-a378-3b3724343547 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
fb028f1a-c1ad-5626-9711-85974414290c | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 10.1 -
c8672506-cfca-5ea9-b353-353334e80701 | note | ACTION (Hold, Monitor, Witness) - W
9cd26314-2106-5e19-9467-f6050175eac8 | note | Detail - Vibrator to be used throughout concrete pour
096aa3cc-eb79-5079-9821-a68b2b2f4099 | note | Frequency - When pouring concrete
730b24fd-9284-5354-bdc0-43944e0c0a7c | note | Inspection / Test Method - Visual Inspection
72b00502-e1e4-543b-b61b-20d39ee4f847 | note | Conformance Criteria - Concrete Inspection Record
0c77912a-9c6b-52ea-8c27-e76dd689d861 | note | Records - Concrete Formwork Checklist
244197ee-d62a-5310-8b6c-e8ecc44b856d | note | FH Initials - Site Engineer
deaecb95-7aab-53cf-8593-e44dca6a7dcd | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
147e47b6-dca5-5368-8106-03b8933bceaf | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 10.2 -
0c7d36d6-128f-5db7-9c77-e0b12ca3adcf | note | ACTION (Hold, Monitor, Witness) - H
1e5f49a7-5b3b-5468-9a14-9dd7d0c698b9 | note | Detail - Concrete ramps surfaces shall be U5 broomed finish and speed table top exposed finish
dcdd8eb1-3830-515f-b7f2-8aa2b5b1efd3 | note | Frequency - At completion of pour
6472bda0-73c5-5a22-9420-6707de200973 | note | Inspection / Test Method - Visual Inspection
0b0d6e42-a3e1-59fd-88b7-7038053c0c88 | note | Conformance Criteria - Concrete Inspection Record
e4f39354-9f56-52b5-90ad-a2e9a09bd14e | note | Records - Concrete Formwork Checklist
bf66e0ca-dad5-5507-b9d0-0534bd1d8db6 | note | FH Initials - Site Engineer
c3f42d56-86c8-58f6-b44e-caea1f600b62 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
08f0bbcc-2a33-56eb-96d0-3cb7655e2589 | textbox | Date Completed:
| checkpoint | 11 - Curing
fe16bba1-2860-58f8-a181-0a1eee75562d | note | ACTION (Hold, Monitor, Witness) - M
effc93a3-b19e-53c2-9fd5-7c30ebbb0e31 | note | Detail - Concrete will be left for 48 hours minimum to cure before traffic is allowed on it.
4d0dd5b8-3b3b-57e1-a824-2ed54d7e8140 | note | Frequency - Post Pour
90a65e24-6cb0-5074-a10a-bacdc616e4a7 | note | Inspection / Test Method - Monitoring the time allowed for curing
0282aeb9-e2f3-5660-b8fc-413ed3ee36a2 | note | Conformance Criteria - 48 hours minimum have passed
1f19ed44-c2f8-5d93-9a81-3780ce585553 | note | Records - Concrete Formwork Checklist
ba39398e-d06c-5c2b-9f7c-f10f8722593f | note | FH Initials - Site Engineer
e819dcd7-b8e9-5bdd-84cd-a329578c0267 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
c0c7d883-a40d-5b09-9886-6971187305ca | textbox | Date Completed:
| checkpoint | 12 - Remove formwork
7342e5be-5981-5e25-9afb-c0090b3891d6 | note | ACTION (Hold, Monitor, Witness) - W
1feef54b-6fc7-5dfe-9d70-fe4774e60ca9 | note | Detail - Remove formwork after 48 hours
669e77e1-1c5a-572c-a1e8-6cef521b83c8 | note | Frequency - Post Curing
35371291-d25d-5848-9001-fa1de1e8841c | note | Inspection / Test Method - Visual Inspection
f3dbefd4-6da7-5e80-85fb-73b67f28a3d9 | note | Conformance Criteria - Concrete Inspection Record
77f2201c-4d6d-5863-b661-06204ee0eae0 | note | Records - Concrete Formwork Checklist
dd0988de-7bcc-5fda-9ace-4aff4c865b7d | note | FH Initials - Site Engineer
e3d05c8c-a136-54f3-b7ca-5cd2f991fe3f | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
3d0ec4f1-33d8-5a6c-8d2a-26126422e13e | textbox | Date Completed:
| checkpoint | 13 - Asphalt- Concrete extension slab/ Toe
cb545052-c194-5378-8677-b04cceced7ce | note | ACTION (Hold, Monitor, Witness) - H
cd118236-9a0a-5031-b7a2-59748e2f2196 | note | Detail - One row of Lesa diamond placed mid depth @600 C/C along construction joint placed at 75mm as per TDM TC0023
6e4a2f94-df33-520e-80ab-a64caaf336b2 | note | Frequency - Prior to pouring concrete
07fb6e8a-3964-56b3-aeb2-db3733193f02 | note | Inspection / Test Method - Measurement
f02f57b3-66e5-57b1-89c2-dda55b64b823 | note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
5fac1a7c-9f96-559b-8490-62dfc7917cb0 | note | Records - Site photos,delivery dockets
fd11530e-0d8c-5e4e-8488-93cc068df69f | note | FH Initials - Site Engineer
285e6ee3-84b7-5950-bf50-58c1380fc6a2 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
7a97f842-4040-5928-ae7c-39890324c605 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 13.1 -
5d2e404f-b8a3-5c55-9766-d1007f71e03e | note | ACTION (Hold, Monitor, Witness) - H
7277d1c6-60c4-5d5d-b3ae-db0f64757e69 | note | Detail - 200mm thick 40Mpa Concrete and 4kg/m3 Black Oxide with one layer of 663 mesh
137f4a50-b9ad-5141-89cc-96d75afb2e84 | note | Frequency - Prior to pouring concrete
4a896d15-7e27-54ba-bdfb-1966c0d7efe2 | note | Inspection / Test Method - Measurement
72e37624-e501-50fa-b637-85b2048f91d9 | note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
3fd06662-caef-540b-8eea-585541a30d43 | note | Records - Site photos,delivery dockets
d21710af-3659-5464-84f5-6128e69a40c4 | note | FH Initials - Site Engineer
6888c2de-2607-5310-82bd-2784ee400071 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
e3e0b89c-49ad-5b9d-a7b2-48b542c26d5d | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 13.2
a97fbcce-0c97-5d9d-a209-9cdaad391d62 | note | ACTION (Hold, Monitor, Witness) - W
5d03ff69-2148-5de1-b299-45d23bfec7db | note | Detail - Ramp to have relative gradients
c52fc280-0c01-573e-bf2a-cb935c8a9897 | note | Frequency - Post Curing
3e0d71d5-0727-5c35-81e1-c04c358c44aa | note | Inspection / Test Method - Visual Inspection
28c97675-b76a-5ae3-ab7c-54561c6becf4 | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
f6292383-7e01-5466-923d-7cb5127dc48e | note | Records - Site photos
e9944dc6-66f3-51ca-92bf-cb7901cde027 | note | FH Initials - Site Engineer
c27ca429-1c60-59e4-a67f-293ae8c36f71 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
779978f2-ebcf-5ed6-b8cd-e8d95d6e84c3 | textbox | Date Completed:
| checkpoint | 13.3
f42206af-07ce-5009-b3ca-744e358661f1 | note | ACTION (Hold, Monitor, Witness) - W
8722b95a-9725-5026-8348-6aadb781790b | note | Detail - 150mm thick AC14 and 4kg/m3 Black Oxide
5fdf6db8-12ec-5634-bcc3-2e8e0c12fe37 | note | Frequency - Post Curing
4b542863-e36e-5910-9895-ad570d2a020b | note | Inspection / Test Method - Measurement
74f77d05-8c77-563a-ad64-27ba0b1c6711 | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
c0389ace-417b-5ba0-a88d-ed79428a6c99 | note | Records - Site photos,delivery dockets
b3aa290e-57b7-57b0-a063-1ed4ba453c32 | note | FH Initials - Site Engineer
e50fe992-bfa7-5a4f-bcd4-3c326a284d65 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
2f3d17d9-7057-5f97-8419-cd9aae59a9d6 | textbox | Date Completed:
| checkpoint | 14 - Lot Number QA File
d8206635-15f1-5fe1-be38-c33177ad0bf8 | note | ACTION (Hold, Monitor, Witness) - W
17d37a13-bed5-5a49-8f51-55af8bb34fe1 | note | Detail - Ensure all QA Records,site photos and incident cases (OFIs) are closed and included within QA file
37598047-d5d3-5a04-82eb-976d5987ec3f | note | Frequency - At completion of Lot
aaacd99f-6c10-59fb-b67a-65cbc9b9d6e3 | note | Inspection / Test Method - Document Review
e7bc4a3d-a565-52f1-b26f-a4a3eb5d801b | note | Conformance Criteria - All QA files compiled and submitted to client
056004df-1dc6-5f77-b9fd-96c7ff834cdf | note | Records - QA records
d1d66302-67ca-5fe7-b6e4-b45d2808d7c0 | note | FH Initials - Site Engineer
71befdb4-af2d-5925-982f-1ea4a7c45d66 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
a484d16f-0cf5-5195-99c9-526787af5ae5 | textbox | Date Completed:
| checkpoint | 14.1 -
84adbfc3-ea0a-56ab-aead-f7be0cc86217 | note | ACTION (Hold, Monitor, Witness) - W
e692b458-926a-5aba-98ae-aabcfc3d66db | note | Detail - Delivery Dockets to be included in QA file
9cee4bfd-3efe-585f-b51c-d2db46395277 | note | Frequency - At completion of Lot
c33034f1-7934-58ae-8910-cb59493e9012 | note | Inspection / Test Method - Document Review
ec9da1f2-4be9-5c53-9e9e-f3c5515636a0 | note | Conformance Criteria - Delivery Dockets to be included in QA file
9a645740-c1d9-50af-ad47-de2010f4f5b0 | note | Records - QA records
3fbae257-baf9-5678-9783-aeaa40890809 | note | FH Initials - Site Engineer
20a587ca-87f5-51f6-90cd-0697306be048 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
dc2a0fa9-a27c-52b6-ab94-8187ff40303b | textbox | Date Completed:
| checkpoint | 15 - As-builts
88653977-ca8b-5572-bcd4-ff8fc95dfa62 | note | ACTION (Hold, Monitor, Witness) - H
28fed422-7123-58f1-abbf-583ca78ab54b | note | Detail - Red pen mark up drawings to be included in QA file
916aa532-76c8-5135-b090-f49291c6d24e | note | Frequency - At the completion of the Lot of work
4c6b9d25-2fa6-5543-b4bb-4dabdcc84ac8 | note | Inspection / Test Method - Drawings
468f919f-0e6e-5ff3-982a-b0f0627d4196 | note | Conformance Criteria -
10032ae9-f60f-546c-b430-7c5f76330637 | note | Records - As Built Drawing
8bff1634-7746-5dd6-8d68-53c42a7d0832 | note | FH Initials - Site Engineer
94f967fa-4b74-522f-9544-531392d18048 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
e8f2286d-9859-5b75-b74b-c8d41f4a2956 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | Final Inspection
e5e49220-39c1-5777-a54f-9de73d26a9db | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
5a5f3dc0-763c-5527-a5b2-db9d8c094daa | textbox | Print Name:
97ce6320-1154-5bc9-9412-de09a9e40e6b | textbox | Position:
b8bb8922-6702-5b8f-98f6-e85f4dfe4774 | textbox | Date:
| checklist | ITP - Griffen Park / Hillsborough Rd - Roundabout | itp | Roundabout | 5ca33d7b-bb25-40b7-b938-13194976a59c
| section | Construction
| checkpoint | 1 - Survey Setout
fcaf3a0f-7a82-5c9c-9d50-6266cc92232e | note | Verification Activity - Survey
49aa9515-cf7c-514d-a796-56913f95fb9c | note | Methods Or Reference - Setout Kerb Alignment required to construct to design
ab996802-d8b1-54ba-b84c-a73347024b5b | note | Frequency - Prior to commencement.
2836b637-5fa6-53aa-9086-7eefb9948bfe | note | Acceptance Criteria - Survey
fb7b7838-7a06-5104-8fba-34da2f4a0d94 | note | Hold Point - As per Drawings 3822001-400-CA-1050
365e1c18-221d-56ab-a59e-8ab82c661d07 | note | Records - Survey Receipt.
7c008b5c-2a37-5943-bac1-4826ba2ebb11 | note | Onsite Responsibility - Site Engineer
| checkpoint | 2 - Concrete Roundabout - Central Island
9abcb676-5610-5601-8e1f-4bde47d16575 | note | Verification Activity - QA FORM/ Drawings
aebd3161-928c-58da-9852-28e049c3fe78 | note | Methods Or Reference - Construction Drawings
87a9aecf-ec0e-5f76-a57c-93988c8c2036 | note | Frequency - Each Site
427adb12-b34a-538f-b929-1e675ef280ef | note | Acceptance Criteria - Standard precast kerb to be hand-laid with 100mm reveal. Diameter to varies across with 2% cross fall.Kerbs to be sitted on 300mm Min AP40 Sub Base Course , with CBR>5
efb934e4-bb41-5f1e-8db7-1d9466525385 | note | Hold Point - In Process Inspection
4fa64fc3-6f06-5e77-a85e-f7f463bcded8 | note | Records - Photos
98255a33-d5e1-5ad1-a1be-cc8ed88e2f18 | note | Onsite Responsibility - Site Engineer
| checkpoint | 2.1 - Concrete Roundabout - Central Island
db10050d-ffa6-5ef6-9ed8-ee1f7a950781 | note | Verification Activity - QA FORM/ Drawings
9baf05a8-e1c3-5f4e-bd98-5ead105a5e0e | note | Methods Or Reference - Construction Drawings
1ad0be1b-eb08-5c50-8206-1681728cd9fc | note | Frequency - Each Site
712c4e87-c7c7-5a34-8e4b-1e05d9e8a493 | note | Acceptance Criteria - Central island to have 100mm GAP 65 Granular base course on removed pavement surface.
9ba6979d-0856-582d-96fd-7624d571dbcc | note | Hold Point - In Process Inspection
916d6a5f-692e-5f18-8f53-dca2bd2157e8 | note | Records - Photos
3d1b3d31-6c49-5528-924e-aa485d65bb75 | note | Onsite Responsibility - Site Engineer
| checkpoint | 3 - Concrete Infill - Central Island
a99d5bde-26b3-53f5-bd11-a98c8f06379e | note | Verification Activity - QA FORM
2743fe32-8578-5ca6-9674-3332dd4ff3f8 | note | Methods Or Reference - Construction Drawings
99a9fc31-804f-5317-a1db-772a541f3d02 | note | Frequency - Each Site
df25a28f-3567-5b6e-9a23-2d414c25949b | note | Acceptance Criteria - 100mm depth of 20MPa Unreinforced exposed Mcacallum chip Concrete with 3kg/m3 red oxide
41fc0a35-8098-507a-a603-9fa876a0b93f | note | Hold Point - In Process Inspection
f71a5dd3-b56b-5fbc-99f7-681e560a43d4 | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
4a0c037b-28b9-525b-8a4a-288290930190 | note | Onsite Responsibility - Site Engineer
| checkpoint | 4 - Apron
49586d1e-fd76-5ab8-ad2b-b1e86a76c8ad | note | Verification Activity - QA FORM/ Drawings
11cc5fb7-c793-586c-b09b-f7811a85bbb8 | note | Methods Or Reference - Construction Drawings
27b1f82c-073f-5bb7-81e7-46ef4d9d3df4 | note | Frequency - Each Site
4333d288-87b5-5a99-b000-0cfa3216824b | note | Acceptance Criteria - Slip formed 25Mpa fibre reinforced concrete for roundabout edging OR Mountable Precast kerb for corner overrun
d6b6681a-7d98-5687-ab88-dafb5effe8c5 | note | Hold Point - In Process Inspection
809af522-0344-539b-82dd-f121e1b19c18 | note | Records - Photos
a478a2e6-065a-5bc8-af03-0d7e45054b73 | note | Onsite Responsibility - Site Engineer
| checkpoint | 4.1 - Apron
4455a0dd-9daf-5008-9434-d5df26afc02a | note | Verification Activity - QA FORM/ Drawings
4e2d6d71-b0b9-5a98-a7f8-a97c4c551d6f | note | Methods Or Reference - TDM Technical Standards - IS0007
2775bb03-93e3-53df-a658-fac9751d26b5 | note | Frequency - Each Site
b8d6c445-40a1-5ad7-9c5f-a712ce3e0833 | note | Acceptance Criteria - Kerbs to be sitted on 300mm Min AP40 Sub Base Course , with CBR>5
f40effac-566b-52c3-bd8a-f450597fff89 | note | Hold Point - In Process Inspection
d888e89e-47fe-59f3-aec9-2d26bb3ae1d3 | note | Records - Photos of smart level/ As Builts
7c983d7a-fa14-5e52-8868-7f9ccb8cadd7 | note | Onsite Responsibility - Site Engineer
| checkpoint | 4.2 - Apron
5e122c1c-949c-50af-a672-90702a76f2f0 | note | Verification Activity - QA FORM/ Drawings
5928d03a-cb24-5f9b-9ed5-36a13800d14f | note | Methods Or Reference - Construction Drawings
df83cc02-3e70-5328-81be-2bbce0023579 | note | Frequency - Each Site
935036f8-facc-5462-a0c3-ac581a603620 | note | Acceptance Criteria - Apron to have 2% min fall towards the road and 2 m wide throughout.
91e95d34-3d7e-57ee-84f3-dde7ad085070 | note | Hold Point - In Process Inspection
9dc0f8cc-a918-5de5-8414-d543d2ffe693 | note | Records - Photos of smart level/ As Builts
490b8934-0fe0-58e7-8179-a0962eaaebed | note | Onsite Responsibility - Site Engineer
| checkpoint | 4.3 - Apron
b1f1b013-d327-52ad-a82e-1efb832ca999 | note | Verification Activity - QA FORM/ Drawings
a57905c0-77f8-585e-8ea4-daa42d5589a1 | note | Methods Or Reference - TDM Technical Standards - IS0007
306d3a2c-3d4b-57e4-87d3-03383ca1b5c5 | note | Frequency - Each Site
758dbbee-5e55-5786-8ae7-9d758c716e11 | note | Acceptance Criteria - Apron to have 30mm thick AP20 layer with 0.25mm Polythene layer on top below concrete
12231ef8-d1af-59ed-8447-b5ca61422260 | note | Hold Point - In Process Inspection
da6c7660-99f5-5a06-9597-92d3c92c6821 | note | Records - Photos of smart level/ As Builts
ac1624a9-dd94-5be8-939b-3abd5355a9fe | note | Onsite Responsibility - Site Engineer
| checkpoint | 4.4 - Apron
206e1fc8-68aa-55da-b355-69e804219dc5 | note | Verification Activity - Concrete Dockets
b0be2bdb-31f0-53bc-920f-55974f3d8df0 | note | Methods Or Reference - Construction Drawings
983d8468-b8f8-505e-9255-ed146023d643 | note | Frequency - Each Site
865720d5-73b0-562f-b535-07b5b5054503 | note | Acceptance Criteria - 200mm depth of 40 Mpa concrete with exposed aggregate finish with 4kg/m3 Black oxide.
ec995946-d074-55c0-8fe4-dbfdb170d1db | note | Hold Point - In Process Inspection
18c454ce-42fd-57ec-b76a-42b81edc1d1b | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
cbe98764-f37c-5310-9399-7905eae57de3 | note | Onsite Responsibility - Site Engineer
| checkpoint | As Builts
| checkpoint | 7 - As built information
9b524f9f-1a99-5a94-9620-1301281da8c2 | note | Verification Activity - Drawings
465f8f2c-3d20-5af1-a6b3-332e616ccbc1 | note | Frequency - Every Site
0c38c801-19c3-5bc3-98b9-f0a5d51bb071 | note | Acceptance Criteria - As built drawings
7e2bc475-b480-5999-bc18-68ddd06d58ff | note | Hold Point - In Process Inspection
27535478-bcc5-5948-a698-bf587a96e4db | note | Records - As Built records
da7f5f4c-7d91-5039-8f48-cae42ccaf465 | note | Onsite Responsibility - Supervisor and Engineer
| checkpoint | 7 - RAMM DATA
3509ef01-2562-5b05-946f-c22901dd6eb0 | note | Verification Activity - RAMM DATA SHEET
117cf0ee-aab0-5832-9dd1-f3d13956cdae | note | Frequency - Every Site
287a85ab-772a-5213-a9f0-54812fc7121f | note | Acceptance Criteria - RAMM SHEET
c26f0c5e-2279-5f43-bc8c-b69bea107e7f | note | Hold Point - In Process Inspection
495a5a04-8048-599c-9aa0-1bdf1fddaa5f | note | Records - As Built records
d5eb24af-fc48-5166-bc19-ec4d6ba98159 | note | Onsite Responsibility - Supervisor and Engineer
| section | ITP APPROVAL
| checkpoint | Final Inspection
46597b5f-248a-5466-ad30-8f1578783769 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
1c4cf797-f1bf-55d0-897f-7d61774f27d4 | textbox | Print Name:
3b11cb3b-16a5-5e89-b430-b5fb1f0442ad | textbox | Position:
892da696-b29b-59ec-b3ca-9be69d71b31d | textbox | Date:
| checklist | ITP - Griffen Park / Hillsborough Rd - Stormwater Drainage | itp | Stormwater Drainage | fde6d96f-8169-4528-81a7-d05a77d59960
| checkpoint | 1 - Permits & Services
f6f3d7bb-cac7-5076-be67-68f956c83385 | note | ACTION (Hold, Monitor, Witness) - H
534fd5d6-69d0-554e-b910-b5c2b2c1f35a | note | Detail - Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
e207af83-3236-5ce9-b123-cd3204629252 | note | Frequency - Prior to any construction commencing
06e35948-cf86-5bbd-b6ac-90b0b662fad0 | note | Inspection / Test Method - Document Review
569f6a3b-f70d-54f6-b238-7a2e6ce6dd11 | note | Conformance Criteria - Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority
1523d8d3-c7e6-58bc-b858-486c05080fc7 | note | Records - Permit attached or permit number noted.
93d1d344-ccab-5906-9584-8b692726fd35 | note | FH Initials - Site Engineer
2e396cfe-cee0-5c99-ab1c-f7802b51a48b | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
7c0fde4d-7fcc-5661-8a17-3209d513c5fa | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 1.1 - Permits & Services
573ac577-f997-50b4-8ef9-cc63c1f64208 | note | ACTION (Hold, Monitor, Witness) - H
8f0f3258-1670-5423-98a5-2751a678aa53 | note | Detail - Locate and mark out all existing services
36a580e2-568b-5dbb-8199-3b4db282cf08 | note | Frequency - Prior to any construction commencing
5d457417-65d5-53d4-b373-9bba10b2b60b | note | Conformance Criteria - B4u dig procedure - follow utility protocols
a7cd2493-1da9-5d7a-96f8-de41d30f34cd | note | Records - B4u dig plans & GPR report attached
a2008a79-919c-5096-b378-e6fd9f9add06 | note | FH Initials - Site Engineer
07588169-732a-56e2-a30f-0675e4824e82 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
c4e8d32c-35b9-53ed-bc35-19b340bdb159 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 2 - Pre-Construction Sign Offs
32d78f6a-97c9-5c6d-b468-de7558c019aa | note | ACTION (Hold, Monitor, Witness) - H
08db983c-1888-5e87-9523-808afd0f527f | note | Detail - Sub-Contract and Supplier Agreements
6d8fb180-37c8-55ea-bbbe-d83f3ec085dc | note | Frequency - Prior to commencement.
6f6f78d5-8880-5c89-94f0-d97abfc95a69 | note | Inspection / Test Method - Document Review
e8be5a7b-ddbd-5c64-a5eb-31ae5a79fa05 | note | Conformance Criteria - Sub-Contract and Supplier Agreements to be agreed and signed
4c9a0faa-8b54-5958-b273-2e7ff88a218f | note | Records - Subcontract and Supplier Agreements
3b4eafa9-7756-555f-8188-e4e9ca0fafb8 | note | FH Initials - Site Engineer
e3fda1d2-6a86-5199-9db4-cad566717398 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
917ce5b0-e2b5-5499-a04c-186d3b4f9c46 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 3 - Design
4ad37f39-4b2b-5e0a-af27-0f758177aa92 | note | ACTION (Hold, Monitor, Witness) - H
7db3fddd-30fe-5bc2-9c2e-bc320294f06c | note | Detail - Design is approved and Drawings are of the latest revision.
c3b15ff9-6a20-582e-bb65-2b4e1f1dc8a3 | note | Frequency - Prior to commencement.
476256c7-3b46-5a39-827f-7cd132e99aba | note | Inspection / Test Method - Document Review
da39513a-01a7-5942-8da2-a0c3cc7f2a14 | note | Conformance Criteria - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
7bad854a-79db-5cf0-a6e6-cd03315a5284 | note | Records - Drawing Register.
acea18fc-7b7c-5f60-9d7d-9366f7b85105 | note | FH Initials - Site Engineer
6f30af95-40a6-5043-bc2b-667b3622ceb2 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - Engineers Rep.
b0934bc4-71ee-598f-af40-d70028cac3a5 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 4 - Survey Setout
4dd6f742-bc24-50d0-910c-6bc5d2a19b2c | note | ACTION (Hold, Monitor, Witness) - H
43a42e2d-16ed-5255-a60e-c816fcdc9af6 | note | Detail - Setout Pipe Alignment and Service Locations with inlet & outlet points and inverts as required to construct to design
b7770e91-f670-5e0c-83a3-b3567534d59b | note | Frequency - Prior to commencement.
cc237a79-bf42-5006-a259-2deb9ce34b00 | note | Inspection / Test Method - Survey
5812b88a-17f1-5cdd-806b-1137015ef340 | note | Conformance Criteria - As per Beca Engineering Drawings: Setout files
e8be8019-4799-54d5-b281-a807c5f9b421 | note | Records - Survey Receipt.
2fd08296-db22-5caf-b501-40baa38aadce | note | FH Initials - Site Engineer
b65d8c1f-2101-5f68-a476-de4f2c5be225 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
91f99d6d-9934-521e-a05b-6320983ab6e2 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 5 - Pipe and Manhole Material Compliance
492b7202-4526-52ae-a458-9e4b7ad73fa0 | note | ACTION (Hold, Monitor, Witness) - H
39fe7d61-5053-5b0b-a806-991d79c8a437 | note | Detail - Cesspit, Manhole and Pipe shall comply with relevant AT/TDM standards
556fb5b3-3f68-5d8f-812f-5d97b0edc695 | note | Frequency - Prior to commencement.
40b5fd14-50be-5366-b428-d664276085fe | note | Inspection / Test Method - Document Review, Visual Inspection
16882568-b173-5ba8-8f3c-c0d7cccefdef | note | Conformance Criteria - Pipe shall be Check for freshly formed pipes and return if required 1) DN225 Class 4 RCRRJ pipes AS/NZS 4058 2). All Concrete RCRRJ pipes to be fitted with Rubber rings 3). Pipes shall have product certification (ISO Type 5) to AS/NZS 4058 Prefabricated concrete Manhole shall be in accordance with TDM Standards & AC COP
03ccc8b6-d69f-51af-b9b2-d00a81cbeb1b | note | Records - Manufacturers Data Sheets, Delivery Dockets
a13c221c-b22f-566c-9b20-55370572c78f | note | FH Initials - Site Engineer
4577469a-d34a-5af5-8a99-b54e3c0ef544 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
c225aead-fad2-5612-8762-8f369065874c | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 6 - Locate Existing Services by Hand Digging / Hydro Vac
f72b28b2-d963-51cf-9646-943ffe61d225 | note | ACTION (Hold, Monitor, Witness) - H
a91648a3-e431-5911-be83-177cdf8a4b7b | note | Detail - Ensure all services conflicting with the line of trench have been exposed by hand digging.
09243b8a-2482-5077-8b1f-f3b780789f4c | note | Frequency - Prior to commencement.
94586221-1597-53df-ba5b-ddf2a8306c91 | note | Inspection / Test Method - Potholing / Survey
178fa21b-ca79-5611-9538-aa171eb49c5f | note | Conformance Criteria - All conflicts have been located. New services and / or conflicts to be advised to Project Manager.
c66ed31d-2b41-569e-ad2e-e4a74d460403 | note | Records - As-built Drawings. Doc. Review
fbf06b21-c28e-595a-a936-d30cdb984e6c | note | FH Initials - Site Engineer
7f4a4ebc-f197-57de-b065-221a07ca5760 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
a0cfdcb6-509f-5f3c-961a-45b553cb408f | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 7 - Trenching & Excavation
aa691113-1663-533d-b327-fb77fba8d19c | note | ACTION (Hold, Monitor, Witness) - H
82823301-bf3f-5233-a475-ca6dd2bb4542 | note | Detail - Excavation methodology
e312fa65-c96c-59d0-a71d-48d10903621b | note | Frequency - Daily
3c065082-8abc-5a66-85cb-6267dda079e2 | note | Inspection / Test Method - Pre Start review
968d0340-b4ec-5bbc-ab1d-a3a0a6fc0911 | note | Conformance Criteria - The excavation, benching and shoring requirements shall be in accordance with Worksafe Excavation safety guidelines (2016)
959e0175-a77f-55ac-8485-3e54aff69888 | note | Records - Pre Start RCP
28af99d4-429e-5397-a4ac-fcbbcc1aec9f | note | FH Initials - Site Engineer
b5aad2e8-ba9d-54ea-acfa-20775e7aa00b | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
776d15a3-7a90-5224-8274-36dd06f75b51 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 7 - Trenching & Excavation
1bf85918-efcc-5d18-ab68-584eba68fce3 | note | ACTION (Hold, Monitor, Witness) - M
2a1c2112-5f09-56da-b129-63bd2d16316e | note | Detail - Trench Profile - Width
43832bf7-9236-56d4-b306-2573f68672c9 | note | Frequency - Daily / as trenching takes place. Different depth methodology
23b9fbff-03d5-5af7-b27b-78a7a69ef196 | note | Inspection / Test Method - Visual Inspection, Excavation methodology
422523b5-dfe9-5a38-a184-22c0534d7949 | note | Conformance Criteria - Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing
8ee9fc43-dafc-572d-89e4-23e8523a0e8b | note | Records - Construction Photos
1e36d163-f0be-5a33-b9a3-f1bd0246b5b6 | note | FH Initials - Site Engineer
911576bc-d62b-5328-8ee6-813874fee6b9 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
78615c3b-cc7c-592e-9075-7d1b85ffeaa1 | textbox | Date Completed:
| checkpoint | 7 - Trenching & Excavation
af795caa-c4ce-59db-902d-a03281d9e5b8 | note | ACTION (Hold, Monitor, Witness) - W
e0c4426b-8c3d-5b73-bebc-8607403a293f | note | Detail - Trench Profile - Depth
24db5940-b95e-5110-8659-611d205208e1 | note | Frequency - Daily / as trenching takes place.
f943fb4f-0e0f-5989-8338-963a873339ee | note | Inspection / Test Method - Visual Inspection, Measurement
e9321a89-b4cd-5e9b-8e97-444453b39301 | note | Conformance Criteria - Trench depth varies according to long section and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings
16d629df-5ed3-5626-8582-fd07d2232bfa | note | Records - FH Drainage Line Record / Construction Photos
1ad7b30b-8b91-5b6c-af85-e08cab6e774f | note | FH Initials - Site Engineer
a2a5ed65-5b5d-566a-b23b-fe69bd755669 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
66b91866-b8d7-5361-a631-0c8a41496c51 | textbox | Date Completed:
| checkpoint | 8 - Bedding for Concrete Pipe Laying & Manhole & Cesspit
5d509f6d-9d98-58ba-98d3-cbf387d83fb0 | note | ACTION (Hold, Monitor, Witness) - W
8dbf8c72-4e2d-5f15-adf6-f117050c0b66 | note | Detail - Placing and compaction of Bedding Material.
db3ba749-ecd2-58df-ab48-0631077b8d96 | note | Frequency - Inspected continuously during placing and compaction of Bedding Material.
050558c3-dc9c-53d4-91c4-b75c826526c4 | note | Inspection / Test Method - Visual Inspection
f08feebd-0095-5ad9-b4a9-d40229817233 | note | Conformance Criteria - Bedding & Pipe surround material to be GAP7 or GAP 20 (Stevenson Quarry) or alternate material that complies with AS/NZS 3725
3c75bcd7-25ab-5330-9d9b-f2982b55e79f | note | Records - FH Drainage Line Record / Construction Photos
b4508696-60d0-5109-8961-eef8356f8ca5 | note | FH Initials - Site Engineer
ef482a7e-986b-5f30-8aea-1dd113996441 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
e23ce1b4-7532-5679-81ed-679775b28985 | textbox | Date Completed:
| checkpoint | 9 - Pipe Position Tolerance
21aab0b4-ecdc-5979-8bd7-6d36214f8f90 | note | ACTION (Hold, Monitor, Witness) - M
7b247627-2056-5c93-9ad5-0e72603f9820 | note | Detail -
b446897c-9174-5e25-b5e2-690bcd4933b3 | note | Frequency - At any point of pipe
548a8c36-3d7f-55ce-a350-bb0b88ff39a8 | note | Inspection / Test Method -
7b6fd6a6-87e7-5b55-b9d7-e9057c04328d | note | Conformance Criteria - Position tolerance for pipe laying at any point along the length of the installation shall be within ±30 mm from the specified design.
198c14c6-895d-5cc2-bbf8-8bc5d61cd46f | note | Records - FH Drainage Line Record, Survey Data.
2e8fad5f-c02d-5996-8db1-848bc2b52e8f | note | FH Initials - Site Engineer
a2976253-0347-59e1-8305-59390f802cce | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
a30bf56b-0352-5994-a2f7-0387dc0b798e | textbox | Date Completed:
| checkpoint | 10 - Trench Backfill - Placing & Compacting
d857dda6-0c89-5622-871b-d9835b4b7e83 | note | ACTION (Hold, Monitor, Witness) - M
830b8234-fe9b-5063-b7fa-a7c8ec453ab0 | note | Detail - Placing and compacting of Trench Backfill Material
66719542-5fe3-5ebe-a37d-47d8eb2452a2 | note | Frequency - Throughout Trench Backfilling operation.
23f44e5f-3a25-58cf-9e77-9c578dd74bfb | note | Inspection / Test Method - Visual Inspection
ba05e284-4a1f-56b7-8e78-7991d502fa72 | note | Conformance Criteria - Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm
7917b3a1-04a4-51ff-a24e-5a883e91ffd9 | note | Records - Construction Photos
74a33021-ae9c-5d9b-be5c-5b6b6c4f945b | note | FH Initials - Site Engineer
31854e68-e949-569c-adbc-782ed1a676c7 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
0e14e433-22e3-54c4-b33b-837c200abc7a | textbox | Date Completed:
| checkpoint | 11 - As-Built Drawings
30a553e0-9496-5671-827f-bc7c3b8dda2e | note | ACTION (Hold, Monitor, Witness) - W
58c1af22-f92f-5d10-be6d-4bd82cd84247 | note | Detail - Red pen marked-up As-Builts of every 'Issued for Construction' AT drawings
7e0193ce-0dfa-5f0b-9d74-c04a603f730d | note | Frequency - Final As-Built Drawings to be completed within three months of the construction completion of the asset or infrastructure.
2e6097b3-d02d-5c35-b71b-8a7726c94ec7 | note | Inspection / Test Method - Drawings / Visual Inspection
558da3f4-3bd3-5a7e-af1b-93006a61d267 | note | Conformance Criteria - As Built and GIS Data
32703fb6-db9c-56c6-ac7c-00f84ab854a2 | note | Records - Redline As-Built Drawings, scanned as .pdf files.
5d45afd9-1c2a-5cef-b828-db39a03e2a8c | note | FH Initials - Site Engineer
2de70484-c626-5906-be94-013552eb50a9 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - Engineers Rep.
22c76171-6162-5d86-81de-5744632dc1f9 | textbox | Date Completed:
| checkpoint | Final Inspection
9aab3715-b8d0-59ea-a4f5-deccc9e8aabc | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
a5e2cf1c-d4f1-5cad-bbbd-b0708f98f3c3 | textbox | Print Name:
ef500c46-a20b-5cdc-9b7d-5188ec878ae8 | textbox | Position:
b158c023-ee2d-5668-a470-1cc8ec8898b1 | textbox | Date:
| checklist | ITP - Griffen Park / Hillsborough Rd - Traffic Island |  | Traffic Island | 2fa82182-47d7-4600-9547-6aabbf8ca275
| section | Materials
| checkpoint | 1 - Kerb
373d6f47-b2d6-5493-bb69-3b99ed8bc19b | note | Verification Activity - QA FORM
f703a319-4cd5-57e5-95d7-28a35bbfa150 | note | Methods Or Reference - TDM Technical Standards - IS0001 & IS0002
70845417-82a4-59a8-beb0-297aef76ea36 | note | Frequency - Every Site
c1e81402-aa26-54ba-9388-5f77f3cf8930 | note | Acceptance Criteria - Kerb to be laid using precast hand-laid
52c8c547-d598-55e3-ab2c-2d2e43d545d9 | note | Hold Point - In Process Inspection
1cccfa9b-8cc0-5fb2-910f-a1055e285c09 | note | Records - FH concrete QA sheet, photos.
3edb83b4-7039-528a-b9f1-967d99259681 | note | Onsite Responsibility - Site Engineer
| section | Construction
| checkpoint | 2 - Survey Setout
5024cbb9-6d74-5d42-9ff2-0ecfeae152bd | note | Verification Activity - Survey
dcbc3bc8-e67a-536f-b49e-e654127c31a1 | note | Methods Or Reference - Setout Kerb Alignment required to construct to design
efe51fad-7610-533c-8e83-b1a620435569 | note | Frequency - Prior to commencement.
b113aebc-737b-56ae-a973-291027c2b7c8 | note | Acceptance Criteria - Survey
99b056b9-ec59-538c-81dc-8e52d4785fc9 | note | Hold Point - As per Drawings 3822001-400-CA-1050
1a612227-cb81-509f-9be0-3d0bc1a389b3 | note | Records - Survey Receipt.
0474c193-7ec1-591b-bc9b-41bff48bacf0 | note | Onsite Responsibility - Site Engineer
| checkpoint | 3 - Concrete Island
0600e1ac-d3b5-5319-bc05-29fb81ac0617 | note | Verification Activity - QA FORM
743636b1-a550-5d0b-8d88-bd2d2167ac42 | note | Methods Or Reference - TDM Technical Standards - IS0001 & IS0002
76f20424-37d3-5955-afb2-e1c8c3ae4bb7 | note | Frequency - Each Site
53a1ddf2-f39d-5b73-b5b5-b408a2e7a09a | note | Acceptance Criteria - Kerb to be precast hand-laid. Kerbing laid on 150mm min GAP 65 subbase in roads. Concrete 20MPa @28 Days
3e7dec68-0fd1-5d56-a6ab-6725de645232 | note | Hold Point - In Process Inspection
0a3fed72-75b9-50a6-9753-71e617936935 | note | Records - Photos
6e6fa14c-a61e-50e5-9480-b36a650d71f2 | note | Onsite Responsibility - Site Engineer
| checkpoint | 4 - Concrete Infill
ea5ce623-459c-52b4-9907-df57a1ef6b1d | note | Verification Activity - QA FORM
5a3d5614-6554-5706-b7a5-f184e637797a | note | Methods Or Reference - TDM Technical Standards - IS0002
dd0600b2-67fb-56b0-a93c-6bdd78a17749 | note | Frequency - Each Site
390e57cd-8c76-5509-b804-81bbbc926740 | note | Acceptance Criteria - 180mm depth of 20MPa Broomed Concrete with 4kg/m3 red oxide Cross Fall of 2% or max rise in centre of 180mm
b207c490-6ff0-50d6-973b-00e186b58448 | note | Hold Point - In Process Inspection
8af0e31a-5ea8-5b8e-89d1-53acf2bbe8c6 | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
b9db5e3c-f48c-5003-bd44-96776279c46f | note | Onsite Responsibility - Site Engineer
| section | As Builts
| checkpoint | 7 - As built information
b3588df0-c52a-58e7-bbc0-be58e5d7d653 | note | Verification Activity - Drawings
2427f28e-1715-534b-8fb5-87d884ab1e70 | note | Frequency - Every Site
86ebd991-66ea-5a54-b4eb-c90e77c4fc1c | note | Acceptance Criteria - As built drawings
15f1f409-e46a-545a-97a9-f7a9b1407d03 | note | Hold Point - In Process Inspection
830d56ee-38ee-537c-9073-51ab9baeb67e | note | Records - As Built records
c04db015-2e04-57c7-9e3c-2831b8091a47 | note | Onsite Responsibility - Supervisor and Engineer
| checkpoint | 7 - RAMM DATA
e0bb4ad5-cbf4-52c2-824a-814846ed8756 | note | Verification Activity - RAMM DATA SHEET
a3e69262-bfd7-5ccc-b628-9123dd050833 | note | Frequency - Every Site
ea4df0ba-6d3c-5d6b-9da6-2d14751f8781 | note | Acceptance Criteria - RAMM SHEET
e8d1e7d4-3a77-5868-8b26-3cd8079a12d9 | note | Hold Point - In Process Inspection
ce962c3f-1538-542c-8f53-b68ab0faaf35 | note | Records - As Built records
09d6fc07-1696-5e65-bca7-3db28e2d9587 | note | Onsite Responsibility - Supervisor and Engineer
| section | ITP APPROVAL
| checkpoint | Final Inspection
adba1a61-4a78-564a-a9a9-b2e6c8fc50d0 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
d702b6fd-9e97-5863-b09e-68220c0f6fc4 | textbox | Print Name:
85eff86a-673c-5705-87e1-642af949356f | textbox | Position:
66263dc0-9832-56fa-a5ec-1183b23b3f77 | textbox | Date:
| checklist | ITP - Griffen Park / Hillsborough Rd - Vehicle Crossings | itp | Vehicle Crossings | 0b7de203-9895-4a01-9343-9f03cc04f07c
| section | Site Set Out
| checkpoint | 1 - Site Set out
af67e904-1238-54a1-ae49-f4867c4d37a4 | note | Verification Activity - Surveyor
f2e73f34-fd1d-545d-a897-54e81048ab18 | note | Methods Or Reference - Surveyor
12889f6b-0b3f-56a0-8741-8624fb40d738 | note | Frequency - Every Site
d7ac1cec-3747-5a45-9399-6fb3a4730dd5 | note | Acceptance Criteria - Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable. Alternatively like for like
5c577395-adcf-5aed-9129-0e2bd1582c1f | note | Mandatory HOLD POINT -
583cf055-2635-55c0-8bb7-5a898e1dad82 | note | Records - Survey Receipt
f041df5d-62c7-5d6a-a732-a1dafc56730e | note | Onsite Responsibility - Site Engineer
| signoff | Mandatory HOLD POINT
| section | Materials
| checkpoint | 2 - Channel Level
f2b12434-e847-528a-ba16-2ab57e09e0aa | note | Verification Activity - QA FORM
a9aa1a43-599e-5fab-bf4d-2b8ed5ae774f | note | Methods Or Reference - TDM Technical Standards - VX0000
1304c3c4-001a-530b-8bdc-e337fcdfac30 | note | Frequency - Every site
696c545f-c1f2-56d3-96ca-0795e007a017 | note | Acceptance Criteria - Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
010dbbbb-f733-534e-90d8-0722fbe3a835 | note | Hold Point - In Process Inspection
b4c1101a-1a22-56cc-8703-0604fafbb66d | note | Records - FH concrete QA sheet
a2e93316-edac-53b3-b182-64c60e29a6d2 | note | Onsite Responsibility - Site Engineer
| checkpoint | 3 - Mesh & Steel
0aa932e3-3f36-56de-9d4f-726daaa6422b | note | Verification Activity - QA FORM
b50007c6-ba7a-5108-adea-ba7289c68e6d | note | Methods Or Reference - TDM Technical Standards - VX0000
23353034-23f6-58eb-b660-d4d38ab10631 | note | Frequency - Every site
1387b935-54bf-55bf-a428-c3e9df5245ce | note | Acceptance Criteria - 661 Mesh and/or D12 Bars to be installed if 4> dwellings or commercial crossing
ef213588-dcf9-5f2a-a05c-302b82620e3f | note | Hold Point - Mandatory HOLD POINT -
0a96cd9e-51d3-5b47-b4b4-606629696dd3 | note | Records - FH concrete QA sheet Photos
b91b322e-203c-5e27-93b8-0aed65b8d590 | note | Onsite Responsibility - Site Engineer
| section | Construction
| checkpoint | 4a - Vehicle Crossing
b518d751-d7bf-5abc-9b2d-fbd51e4126e8 | note | Verification Activity - QA FORM
e915adfe-2508-5351-ab14-ba0a1a87f3e7 | note | Methods Or Reference - TDM Technical Standards - VX103
8d79b3d7-da5a-5139-8796-a1e628d1ee30 | note | Frequency - Each VX
376fd68a-e857-5d0c-993b-321637bd47ff | note | Acceptance Criteria - Subgrade -(CBR > 3) Base course - 100mm min. thickness GAP40 Clegg CIV > 12 Surfacing - Concrete 150mm and 20 MPa @ 28 days. 4kg/m3 black oxide Exposed Finish
7bbc2501-4d87-5f80-99fa-f74728c7e0d3 | note | Hold Point - In Process Inspection
78082180-491f-596d-8345-62d0b405b665 | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
8241a504-acd3-5528-93e9-392b3dc949dc | note | Onsite Responsibility - Site Engineer
| checkpoint | 4b - Commercial Crossing
ed62018e-c48b-5034-8ea8-e2b00c5ca58d | note | Verification Activity - QA FORM
ce868024-6dff-5927-a117-d9a360a970de | note | Methods Or Reference - TDM Technical Standards - VX0202
1f6003d8-8254-5b4b-9b40-9e94fe123e4f | note | Frequency - Each VX
ad7e8893-59ec-5a97-92a5-ec1b10a42f11 | note | Acceptance Criteria - Subgrade -(CBR > 3) Base course - 100mm min. thickness GAP40 Clegg CIV > 12 Surfacing - Concrete 200mm and 20 MPa @ 28 days. 4kg/m3 black oxide Exposed Finish
502f9d67-5977-5de6-b079-bc806bba367f | note | Hold Point - In Process Inspection
e0a59f75-47a6-51ef-aa30-25378f63e6fd | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
c0a47870-c702-513d-996e-4d873479cb3f | note | Onsite Responsibility - Site Engineer
| checkpoint | 5 - Grass Berms
a85a5388-cd4a-5a7c-9561-b193fe0a2c3b | note | Verification Activity - Visual
242b7ad1-301e-5d8a-b3c8-3a7cab642af8 | note | Methods Or Reference - ATCOP Section 12 Footpaths and Pedestrian Facilities
f3861b2a-0a39-5347-b0cc-067be61abb7d | note | Frequency - 10m Intervals
6c38db2a-35bc-5d2f-abe7-5053f7cd73f0 | note | Acceptance Criteria - 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
5769288c-b21f-5e8d-8a7e-02135b6f798b | note | Hold Point - In Process Inspection
e325eb99-fdd0-55a3-b7d1-7461493810dc | note | Records - Photos
2e278576-c454-5a6f-9991-aa8899e8e38a | note | Onsite Responsibility - Site Engineer
| section | As Builts
| checkpoint | 6 - As built information
c16bc260-e4e2-5a07-8910-688fe1792331 | note | Verification Activity - RAMM DATA SHEET
d2677c0f-ce22-54b7-99ef-d5e4f492004d | note | Methods Or Reference -
7976a2c5-16a3-5c4b-a11c-f8e031af4ee1 | note | Frequency - Every Site
20c10e26-532f-5904-8c97-f96d076a7a89 | note | Acceptance Criteria - As built drawings and Ramm Sheets Completed
b1b3ef4b-495d-5e0c-9af5-e8a036855444 | note | Hold Point - In Process Inspection
d842274f-b913-5585-8716-f426e22da32f | note | Records - As Built records
493fdebb-7170-5548-af55-ffb8fd471ea3 | note | Onsite Responsibility - Supervisor and Engineer
| checkpoint | Final Inspection
f90d2067-54b5-5992-9c3b-6e4bd97228a7 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
60375904-1289-599d-a109-e941b0aa8e93 | textbox | Print Name:
7499af58-b1e1-5840-a6d5-292a13d97374 | textbox | Position:
9563a6e2-e91a-5d07-874c-273094bab3e5 | textbox | Date:
| checklist | ITP - Massey Road - Aspalt Speedtable |  | ITP - Massey Road - Aspalt Speedtable | ad987a36-0b4f-4ff8-a4e6-8c12b1f3529a
| section | Precom
| checkpoint | 1 - Permits & Services
59069545-4c38-5a14-8e0a-81d0d8f289c5 | note | H
45d52460-a8e4-5398-a265-ba7d8854df30 | note | Detail - Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
2c14ff3b-fd83-5d2d-b20f-d69aba5742ce | note | Frequency - Prior to any construction commencing
d8c24edf-3d98-537a-88c2-3a130e929d64 | note | Inspection / Test Method - Document Review,PHOTOS
1ae97dac-f938-50f3-ad78-d381cc7d11e2 | note | Conformance Criteria - Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority
a8603eca-8ca9-50a6-b1d0-ed9df083d3f6 | note | Records - Permit attached or permit number noted.
e2bffd4b-937b-5a69-9ea2-fa9c1bfdf225 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.1 - Permits & Services
6b14a192-d944-5b54-81be-48e1a28eb891 | note | H
bf871c2c-b797-5188-b0b5-6d1f0032efcd | note | Detail - Locate and mark out all existing services
dc8bef5a-47fe-54df-9ad0-2791d8c4e99d | note | Frequency - Prior to any construction commencing
31aa8a2f-e4ea-57c0-b0f6-24d1a833675c | note | Inspection / Test Method - photos
b74436f8-4be4-5501-9cbf-bc298ccff63e | note | Conformance Criteria - B4u dig procedure - follow utility protocols
f5401272-f202-532e-b597-e7014b157eac | note | Records - B4u dig plans
cc96ffdc-5b19-5128-894c-6c09cccc2b99 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.2 - Permits & Services
9d0c4c69-f3ca-5f23-933b-fbe6182c7588 | note | H
a30d0324-6fd3-552d-8209-155db7118f96 | note | Detail - Approved TMP
5e2a6120-5e6a-51b2-aeae-ff13a4f59426 | note | Frequency - Prior to any construction commencing
0b095af5-73e7-5cc6-86ec-bce24b04ad77 | note | Conformance Criteria - Approved TMP and WAP onsite befor establishing traffic management
06ebe721-b161-546c-9a57-d242f4439616 | note | Records - TMP Plans
21eab813-e89e-5a26-abe6-54f1e31196c3 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Pre-Construction Sign Offs
b97d409a-b449-5b3c-88b0-b0bc68899561 | note | H
4bc8b001-9b07-5d9c-9bac-766ebcf2bc02 | note | Detail - Sub-Contract and Supplier Agreements
2a87847b-0f0f-50f1-82d1-214babb0b5a4 | note | Frequency - Prior to commencement.
036afda7-3dac-5b33-b895-fa8d04d8ba47 | note | Inspection / Test Method - Document Review
2445047c-438b-54ec-9366-ed77d77f4f70 | note | Conformance Criteria - Sub-Contract and Supplier Agreements to be agreed and signed
fa07fb0e-1172-529a-8c83-472f798c5dfe | note | Records - Subcontract and Supplier Agreements
47467cac-6e65-51b1-bb28-4f5e91b00ce1 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Design
1a870aaa-1d78-5a7d-9c04-4db8b05369ac | note | H
97ca1ae9-612e-51e4-9dde-87fa51e7826a | note | Detail - Design is approved and Drawings are of the latest revision.
5770a4d9-2101-5a57-9f6c-56c3c75f8ad5 | note | Frequency - Prior to commencement.
9febaf9a-88d2-5d86-a8fe-05b87ff995d1 | note | Inspection / Test Method - Document Review
6be31ac1-2cb2-5a05-aa89-5550d9672132 | note | Conformance Criteria - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
dee80fea-2d7d-5fbf-8a60-3d5355ed74c3 | note | Records - Drawing Register.
85bbeb92-674c-5fdb-9b15-e82d19d294b0 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| section | Milling
| checkpoint | 4 - Milling Depth (up to 75mm)
09367b90-7f09-55dd-b54d-96564c8efe44 | note | M
9d72e033-5f5a-54b2-9125-6a5ae24e2238 | note | Detail - AT Contract Specification 4414
03a438ef-203a-550f-9f4a-11bc4a75a0d6 | note | Frequency - Every site
8cad0830-5586-5bea-81da-fcdbdf9a5261 | note | Inspection / Test Method - Review,photos
0ef2b8c5-7439-52e8-870c-2c3f09da05e0 | note | Conformance Criteria - Surface preparation shall be in accordance with NZTA Specification M10,The Contractor shall mill the existing surface to the minimum depth required to place the specified AC surfacing layer and provide a “key in” between the new and existing surfacing.The milling depth shall be carefully controlled to ensure that the finished milled depth and level within + / - 5mm of the specified levels or specified layer depths.
c341a132-2add-5817-94d6-e83896bde448 | note | Records - Milling Records
f712b2e4-07b4-5dd4-a067-f96b477fd149 | note | FH Initials - Supervisor
| section | Aggregate Quality and Lab Test
| checkpoint | 5 - Temprature Limitation
1a6e15f9-cd5b-5b03-be74-9486476872b9 | note | W
39f2c928-60d2-5ce9-9b42-e1f91e7073fc | note | Detail - Contract Spec /M10 Spec
b1884833-6c1b-51d4-8802-3630b1a225e4 | note | Frequency - Every site
ae5d66da-4734-5e0b-9fa6-006bfaa17e1b | note | Inspection / Test Method - Review
9cebe2a0-719b-5160-aa96-1edcfa40e84b | note | Conformance Criteria - Asphalt not to be paved when foggy or raining, or placed on a wet surface or when temprature is below 120 degree
be3dde64-bab7-5d4a-9d49-4f16d6072f6c | note | Records - Asphalt QA
05f30679-934e-56db-8b98-343c0693ac96 | note | FH Initials - Site Engineer
| checkpoint | 6 - Check Weather Reports
1e9f9b70-259e-5dd0-b175-cd5358f51496 | note | W
75ab4ad7-5bc0-5625-ab67-cb12004dc112 | note | Detail - No fog, rain or wet surface. Base temp greater or equal to 7 degrees celcius
cf005d22-5b31-5895-b81e-4be20b24f2ac | note | Frequency - Weather call 2pm on the day
3207d280-67b0-5146-9e78-17dd62510128 | note | Inspection / Test Method - Visual
dbdcc902-b6be-5119-a462-19c76b42c9e3 | note | Conformance Criteria - Forecast and thermometer
aaa5a6ff-fcd4-5789-9cd1-9c74c45eb45a | note | Records - Radar and Asphalt QA
1049f3d9-090b-5a2c-94ef-8e88536f8b67 | note | FH Initials - Site Engineer
| checkpoint | 7 - Pre-Seal Inspection
1f84140b-33d3-506c-94a3-97ef26976a57 | note | H
25c01a0c-af9c-544f-8976-b3816a203a01 | note | Detail - Surface finish
b228d666-821f-5e35-938c-50b92ad11fc7 | note | Frequency - Continuous
3ae23385-b83a-542a-bebd-6466d57ed21d | note | Inspection / Test Method - Visual
e963b703-d375-5143-a93e-313f5161ae9d | note | Conformance Criteria - The surface must be clear of deleterious material and not chocked with fines. The basecourse surface must present a stone mosaic surface with larger aggregates protruding and not appear damp
ba64602d-1dcf-54e1-a587-6d92ae37e099 | note | Records - Sealing QA
1e1d8213-25e0-5b7d-baaa-17d859467911 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.1 - Pre-Seal Inspection
c1761e91-5c39-5aef-a48c-3cb7fb378d08 | note | H
c175b68c-147e-5e23-bb23-d0721640115a | note | Detail - Basecourse Compaction
701a2626-b311-5d40-9920-bce8150bfe34 | note | Frequency - Everysite
72311480-4b4f-5b0e-8bc6-98b049748c6a | note | Inspection / Test Method - Testing
d2fb85ae-0226-5f7b-83ab-7ffc7b3670ef | note | Conformance Criteria - Clegg CIV >25
e7aaaa61-1c21-5ab7-b44c-7897275940ee | note | Records - Asphalt QA
6fec3f62-048d-5b46-8a1f-dfaef6b4564c | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8 - Tack Coat
1630dd84-550f-568e-92d9-773033dfbe52 | note | M
47934fa4-36c2-5468-924c-257f22b28b8f | note | Detail - NZTA M10 Spec
02954c30-5aaa-5a26-9281-58d1aebd83a2 | note | Frequency - Ensure heavy coat of emulsion is applied before on each layer of Asphalt mix
5b4aed35-2416-5095-b734-920af9f1777c | note | Inspection / Test Method - Testing
f0fefc06-5cf1-569f-a0a5-8574855bbf6b | note | Conformance Criteria - minimum of 1 L/m2 is required on each spray run
1dcfe227-f1d8-5835-8549-ed98d269b065 | note | Records - Asphalt QA
573360fe-1e68-506f-ace2-1032e55082ad | note | FH Initials - Site Engineer
| checkpoint | 9 - Construct AC20 Layer
73b96cd3-ef51-5e6f-abd8-c9e615b26260 | note | M
18c1575c-49b9-5a2c-9d69-75038fdc0d9d | note | Detail - NZTA M/10 NDM and Stringline
9c1db619-6e02-537d-a880-6157fde56a45 | note | Frequency - Each Run
20904000-a523-565f-8a42-b421df14b263 | note | Inspection / Test Method - Testing & Visual
b44a4918-0d2c-5273-8861-2df7d8637855 | note | Conformance Criteria - Construct 100mm AC20 layer. Design air voids 2-7% and level tolerance of +10mm, 0mm. NDM testing undertaken in accordance with NZTA M/10
c16a08df-8229-5880-aec5-b13ac2a723ab | note | Records - Asphalt QA
394953ab-596a-57bb-bbcc-1976825ef9f6 | note | FH Initials - Site Engineer
| checkpoint | 10 - Construct DG10 Layer
3c4147d1-b282-5749-b437-df7ca33f1e56 | note | M
3a17168f-7d79-5748-b6b9-c7930b03e3f5 | note | Detail - NZTA M/10 NDM and Stringline
0042b6a8-cf25-5b6e-adfc-cfcd9143b0e3 | note | Frequency - Each Run
227f8c9c-a6ee-5d1e-89d2-cc1c3b13231e | note | Inspection / Test Method - Testing & Visual
617b0d51-04e0-5ace-a9aa-3d8d1074b9a6 | note | Conformance Criteria - Construct 50mm DG10 surface layer. - Design air voids 2-7% and level tolerance of +10mm, 0mm. NDM testing undertaken in accordance with NZTA M/10
3fa5f0e4-2bd7-5961-b330-3fd5c8f25ab9 | note | Records - Asphalt QA
6085f4f2-0702-5e09-8e72-773a68dfb648 | note | FH Initials - Site Engineer
| checkpoint | 11 - Surface Finish
23364588-2fd5-5e97-8e3c-6c8f718eb909 | note | W
f70d5763-f69b-5bba-8b3c-0232d63d03c1 | note | Detail - TNZ P/9P
a4bf1fc3-1528-5f4e-ae29-ef26096ecf8a | note | Frequency - Each Lot
131a01d3-9697-52bd-9517-8c264b90937c | note | Inspection / Test Method - Visual
25c8909c-d448-523d-b3c6-7e64d5559436 | note | Conformance Criteria - Inspection: Uniform texture, no roller marks, no bleeding, cracking or shoving, no crushing of the aggregate
bb0d450d-3c16-5203-be7a-f9977a8d91cc | note | Records - Photos
03aa2b48-5f31-50d0-9355-49654607ff31 | note | FH Initials - Site Engineer
| checkpoint | 12 - Reinstatement of Linemarking
0073652f-19a7-51b3-9562-5300a677cc42 | note | M
531113cf-7ecc-5a17-a5cd-463f22f82bc4 | note | Detail - NZTA M7 approved (Class B or C as required for anticipated traffic level)
c0d1dec3-b198-5d9c-8362-7cf24023e073 | note | Frequency - Every site
cb49703b-8f45-5224-ad8b-8dd94be4a0e4 | note | Inspection / Test Method - Visual
3375d22e-5cb7-5a7b-a75e-e12b2b123b1d | note | Conformance Criteria - *Carried out within 12 hours of each shift completed and as per the existing markings * Suitable Traffic Control to remain in place until pavement markings have been reinstated
c8145bdc-1c83-55ae-94cd-41e244cfe75e | note | Records - Photos
26c6987d-067c-54c4-a5b3-1b01873371c1 | note | FH Initials - Site Engineer
| checkpoint | QA checked by Quality Manager
fb8d1bf3-4839-5bbb-ab8b-e6b769f8a1ec | textbox | Comments:
3850712d-5b1f-5e34-baad-a5d340160bec | textbox | Print Name
cd75fbf3-caca-53f9-80d2-036a74e8ea65 | textbox | Position:
0cb41a6c-0bb3-5537-b0c9-0a06e00e2237 | textbox | Date Completed
| signoff | Add Signature
| checkpoint | Accepted by Engineers Rep
8bfc4a94-278b-54e4-9d0a-dfad7cc8c737 | textbox | Comments:
75c8f285-1237-5298-810a-ca3e5ad75e85 | textbox | Print Name
c9db85b3-d509-5863-883a-1589e775f94e | textbox | Position:
f33040d5-bc9b-56ab-b662-8bb18186bdce | textbox | Date Completed
| signoff | Add Signature
| checklist | ITP - Massey Road - Concrete Speedtable |  | ITP - Massey Road - Concrete Speedtable | c683d624-3111-4a62-a2ec-d73196c9aa76
| checkpoint | 1 - Permits
0f4d6064-1620-51aa-bf55-ad93be71ed5f | note | H
47027443-d8e2-526a-8840-c1a2d3f3fd1b | note | Detail - Obtain Permits
7f6598d0-7a80-52d7-b0a2-39eb32ef0fba | note | Frequency - As required
0ee197a6-64e8-527a-86f3-7e55fe6c00e5 | note | Inspection / Test Method - Document Review
4ecbe8f0-136a-5f30-be19-fbda87600cec | note | Conformance Criteria - Control Checklist - Fall Prevention (if applicable). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
35539426-54c0-55bc-992a-e9482824a43e | note | Records - Permit attached or permit number noted
4b4d2b8b-1a48-55fe-bfc5-13b1e2902687 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Pre-construction sign offs
ffce3f97-7c06-5547-aa12-9057aa51ab5d | note | H
58ce06af-59ec-5978-8e1a-f2bb30a20015 | note | Detail - Ensure that Sub-Contract and Supplier Agreements are signed
00f61ceb-6d05-5094-abbc-5cfc936c9719 | note | Frequency - Prior to commencement
c0d8db66-fc7e-5ffc-a599-ac3959557064 | note | Inspection / Test Method - Document Review
7f395d0e-84c1-5621-99bc-492a0148a93e | note | Conformance Criteria - Signed Subcontractor and Supplier Agreements
8c124e0c-e6c7-5821-92d3-eec8af920cc1 | note | Records - Subcontract and Supplier Agreements
7b1c6681-3d05-501e-8cd8-bcb0b9d02b72 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.1 - Pre-construction sign offs
6cd90d37-bfdb-508a-a553-c3169234e669 | note | H
3c91dada-2d65-517a-886f-3fc9d314c9cd | note | Detail - Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
cfcf895f-4bdc-55e7-a6b3-d3086e3f6aa9 | note | Frequency - Prior to commencement
fddcaf72-e911-572a-afda-342b322b7964 | note | Inspection / Test Method - Document Review
f1ac1315-7430-5cc8-a093-c114668d7376 | note | Conformance Criteria - TMP is approved by CAR manager for each site and works are only completed within the approved dates..
d58707cf-a3e9-5fd5-b8ca-f6bbac18bd39 | note | Records - TMP on MyWorksites/On Site
90be97c4-ec5e-504e-9851-f1a4dbf63f59 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Pre-construction sign offs
4fe36c84-677e-5618-a0ff-c4af521dafc7 | note | H
05ca568c-96e3-5274-bae1-a590ca17317a | note | Detail - Ensure all Sub-Contractors and Suppliers go through FH induction
5fa8114f-fac6-5a42-bc39-03dbf027b979 | note | Frequency - On site daily
68fd3c0a-dd63-50db-a6d4-5945d9db8484 | note | Inspection / Test Method - Induction
d0c66501-c14b-50a6-bdd0-3fae06ef8e30 | note | Conformance Criteria - Supplier's and Subcontractor's signatures on hazard ID and pre-start documentation
1613d336-4618-5a66-b479-68b61b9f7e1e | note | Records - Hazard ID and Pre-starts to safety team
6b0e0903-a5ff-540a-81f3-3c0af7dd0c24 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Design
387c0396-e7bb-5b7d-899d-d33f41db257e | note | H
7b11064f-ce46-5d01-bab4-7b4ffdbfef82 | note | Detail - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
eec7288f-0756-5ff2-9bc9-de79ce6c230b | note | Frequency - Prior to commencement
799196d1-2273-5c4c-ac66-e8c01e48d0b4 | note | Inspection / Test Method - Document Review
feced328-22b5-5dd1-a628-0c38f2bfd011 | note | Conformance Criteria - IFC drawings have been received by Contractor
c262ebd3-ab97-5aba-a7b6-c503fc8cd69a | note | Records - Check Drawing Register
912486fe-5c2f-5983-9700-39bbf490f3b8 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Installation of Erosion and Sediment Controls
c16a3d2c-66d3-53b4-9296-811888617760 | note | H
3769329e-dd4d-56b1-9c2d-73e65ecfde62 | note | Detail - Ensure that Erosion & Sediment Control in place
a66b0bcb-9e2a-5e30-8a0c-156c79181afe | note | Frequency - Prior to commencement
a447b4aa-f32c-5fc6-bc0e-fdb41040db19 | note | Inspection / Test Method - Visual Inspection
f4f03a57-abee-5cf0-86aa-91b1dd458583 | note | Conformance Criteria - Territorial Authority has approved the asbuilts for the ESC controls constructed onsite and gives approval for construction to commence
9ee8cafc-cdd3-5e7a-a6a9-631be8a69493 | note | Records - Environmental Controls Audit
41d95662-04c7-5bd1-9712-21e61c219cc5 | note | FH Initials - Environmental Manager/Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Survey Setout
499a3ecb-fb65-5751-8c23-f65749069d2e | note | H
85895ce8-7384-5c15-9df2-4f54e924db0d | note | Detail - Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations)
234cd4ab-2086-5f29-bbf0-e810c1305214 | note | Frequency - Prior to commencement
74e4adef-b619-58e6-a8aa-c5a01968df0b | note | Inspection / Test Method - Survey + Smart Level
e4f4fb33-acb8-5383-beee-19578a9ed4a6 | note | Conformance Criteria - Consistency with Construction Drawing
b59a900e-1239-5349-a4bb-4282d3f6d237 | note | Records - Site Photos post surveying
44a1198c-aaa8-58a7-8c49-c4cc6f75eca2 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Locate Existing Services by Hand Digging
990567fc-0000-5ca6-8049-cbe0b10dc257 | note | H
029f7459-61da-585b-9d07-547a4dec6886 | note | Detail - Ensure all services conflicting with the line of trench has been exposed by hand digging
eecc81ea-62ba-5de9-8d0d-05a1930ee2a0 | note | Frequency - Prior to commencement
80dea0c3-a11b-56d8-9340-761890dcee86 | note | Inspection / Test Method - Potholing
00006604-a559-5bda-8f00-bf6c7281466f | note | Conformance Criteria - All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. Asbuilt all services
1356178b-4ad9-57b5-9f35-f80ec22e1bbd | note | Records - Digging and excavation checklist, service planes,As-Built Drawings Doc. Review
eded3ebc-0136-5711-a562-440328e789d5 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Material Compliance
ad774b40-8edd-54f1-bb43-737e10ce0e32 | note | H
10f70683-c825-5179-acf1-4fbaeadde4ab | note | Detail - LESA dowels to be used at all construction joints at 600mm clearance
1bc4b32d-3258-58bd-9386-7be0fc6ee84d | note | Frequency - Prior to pouring concrete
f2607b06-b70a-5125-a7ae-2ec50a788a78 | note | Inspection / Test Method - Document Review
215093c6-c408-5a29-b839-89dd4da69d25 | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
aca146bb-2524-5e70-9737-3727e64eaa4c | note | Records - Delivery Dockets / Photos
6b20e2bc-1173-5b84-be83-137ff0b37e1a | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.1 - Material Compliance
c54beaac-0ad9-55db-bbe3-e454d8baaaf0 | note | H
5299856b-c399-520a-a9cd-7b2dc5b42dbe | note | Detail - 0.25mm polythene layer placed across all surface area at bottom of raised table
f165bd20-9cf2-508f-93c6-6999210007a6 | note | Frequency - Prior to pouring concrete
f30e8b75-a657-5c36-abec-55a9471d37ce | note | Inspection / Test Method - Visual Inspection, Document Review
aa4ef2a9-f1d2-552c-892f-a7f51f466614 | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
43de80e7-996d-5b58-b46f-ae82ffdf4e44 | note | Records - Delivery Dockets / Photos
2f748119-0023-5138-bda5-919bbb14f3c5 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.2 - Material Compliance
5f789206-f37b-5089-bd72-cd5777b39c8c | note | H
69d3228e-083a-5e08-8520-0501150d4486 | note | Detail - 50mm thick compacted layer of AP20 aggregate placed underneath polyethene layer.
0d9922e2-e881-55cd-9217-5ae53a2c187c | note | Frequency - Prior to pouring concrete
9446104e-f66a-5537-8cf1-ad6872041c78 | note | Inspection / Test Method - Visual Inspection
38469cb4-3d32-5ac6-8de6-64d443f28470 | note | Conformance Criteria - CIV >15
41d1bd30-2112-5491-a468-6a58d48746d8 | note | Records - Delivery Dockets
e16f8bce-4c13-5640-af8d-a00183e20802 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.3 - Material Compliance
4818dadf-2988-549c-9b40-343f3c874d0d | note | H
9ab047e8-6e0c-533e-82ed-00e97a431883 | note | Detail - Two layers of 663 mesh 50mm cover from top and bottom to be placed inside with 70mm plastic chairs seperating.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.4 - Material Compliance
b552c48b-39d1-51e0-81d6-ffaa6a894b3f | note | H
ee8f0140-1a16-581d-a6cb-c851e10fea7a | note | Detail - All concrete delivered to site shall have 50MPa 28 day compressive strength with 4kg/m3 of Black Oxide Powder
fbad5aac-2378-5e7f-8f15-db72cd51e60d | note | Frequency - Prior to pouring concrete
33469e0b-d663-572a-ad07-86ade5bb3b31 | note | Inspection / Test Method - Concrete Delivery Dockets
cc77c5cd-a561-50ca-a997-a63b0d35fc30 | note | Conformance Criteria - Delivery Docket added to QA folder
61e60dc6-f265-51ca-bf7d-b7ed94aebce5 | note | Records - Concrete Delivery Dockets
8e455699-faae-58b8-b9b8-9ca9b721ca4e | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8 - Temporary Works (Formwork)
b95fb1e4-f50b-5e13-8948-d87bfeefc766 | note | W
5ded7b26-7f79-5d51-bcb6-d212ff2120d2 | note | Detail - Formwork to be set to correct line and level
47fdc6d1-a306-5edd-a48c-d1e32d754c57 | note | Frequency - Prior to pouring concrete
7dec3bac-63f6-5a63-9939-758855bcdb3f | note | Inspection / Test Method - Visual inspection
41edbbee-427b-53f2-8cf4-e980aa82105b | note | Conformance Criteria - Concrete Inspection Record
926f99b9-2805-57d8-a552-7e31c6de57d5 | note | Records - Concrete Formwork Checklist
e37a48e1-8aa7-556c-a6dd-0dbbabd6df23 | note | FH Initials - Site Engineer
| checkpoint | 8.1 - Temporary Works (Formwork)
f76b1282-532c-529a-bd3d-528c7948665f | note | H
68e83ad2-eee8-578f-b223-63823e96e836 | note | Detail - Raised table formwork to be 75mm above existing road level and be 300mm in depth and gradients respectively of entry (1:15) and exit ramps (1:40)
2089a776-6244-58ee-8ea9-06cf3654cd2c | note | Frequency - Prior to pouring concrete
fccc4f4e-97ac-5bec-9c8e-4e72b49400c0 | note | Inspection / Test Method - Measurement
c385d31b-de73-5b15-8a88-8178e1b3fd18 | note | Conformance Criteria - Designer to inspect formation level
08d6ae13-d853-58a4-bbbe-3502248290a0 | note | Records - Site photos
149c43d5-a28a-5e96-80ef-7d2b61a0a17b | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8.2 - Temporary Works (Formwork)
78feef78-a58c-5e1e-a978-721237d8f2bf | note | H
beac5227-1ada-50f1-8342-8ae138d5046f | note | Detail - Raised Table ramps to have 250mm depth at entry point and tie into 300mm depth to meet raised table
f2517eb8-ffaf-5811-9416-a5d5a8662460 | note | Frequency - Prior to pouring concrete
0f3e3991-5086-58f6-ada5-601690cb3691 | note | Inspection / Test Method - Measurement
f9400cbf-7306-527f-beda-4131c796b09c | note | Conformance Criteria - Designer to inspect formation level
9658c7c4-60a5-50ee-a26f-d37431e8066d | note | Records - Site photos
37a0331a-1713-5015-bfe4-74a2fc318ce9 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8.3 - Temporary Works (Formwork)
55f8cca9-6269-5037-b295-20e7ed3c7159 | note | H
19179e9a-e789-531c-a1d1-478b0f778526 | note | Detail - Raised Table ramps to be 1.125m across for entry and 3m for departure ramp.Toe to be 0.5 to 1m across for both entry and departure with 50mm asphaltic wearing course
8bd07545-790f-5a60-84a1-406a229b155e | note | Frequency - Prior to pouring concrete
57cdafbb-caab-53ce-8fa0-fc320e33aa3a | note | Inspection / Test Method - Measurement
080e16fe-01a7-57c9-a275-937a5ab50f76 | note | Conformance Criteria - Designer to inspect formation level
fd19f098-e1ac-59d7-a09a-23681785afb6 | note | Records - Site photos
98b28352-405a-5570-aa59-968495017e54 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8.4 - Temporary Works (Formwork)
2c68fcc8-4469-50d4-a7d6-bdf1277e19cf | note | H
0bbfd7ef-633b-5724-9c13-af89fc8360c2 | note | Detail - Raised Table ramps to be 1:15 gradient for ramps at entry and exit ramps to be 1:40 relative to the road
f28ebe09-8876-5309-a2c9-e4749f1890bf | note | Frequency - Prior to pouring concrete
81e112b7-ba11-5c34-9dc6-ed9e8d6ab203 | note | Inspection / Test Method - Measurement
17eca3c2-32e2-5b5b-9d71-667d81c033bf | note | Conformance Criteria - Designer to inspect gradient level
c78be967-02f2-59c9-bacd-4e6e3f2dcb23 | note | Records - Site photos / Concrete Formwork Checklist
3288e6b2-b2c6-555f-a841-14bb42c2e65c | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8.5 - Temporary Works (Formwork)
48218fa4-b097-536f-91de-26a527497872 | note | H
a3f00042-eb48-5d2f-9acb-d810f9a9fbcd | note | Detail - The Site Engineer and MSQA Engineer must sign off the formwork prior to concrete being poured
d38874b4-c0e6-56a9-a709-a1925a3cf4e2 | note | Frequency - Prior to concrete pour
73f2f102-f3a1-5046-a6d4-e6d52ddb6c51 | note | Inspection / Test Method - Visual inspection
a91e1374-791d-58ce-b9c4-a7831bfef6a6 | note | Conformance Criteria - Concrete Inspection Record
8dbd82ea-402c-567c-9784-73b040d38afc | note | Records - Concrete Formwork Checklist
2e7755a7-d37f-55d6-9a8b-2dea1ce9b4aa | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Reinforcing
2840ba86-f67e-528b-a06d-2902f3649ba7 | note | H
eaa9d176-b8b0-5bfe-aadf-ece31bba38a9 | note | Detail - All construction joints are to contain 2 rows of LESA dowels or similar approved dowels .Dowell system 50mm w/ Black 300*50*6mm plates @400 centres placed across the construction joint
f299b4f1-3ebf-59b9-81d1-4ad43592e741 | note | Frequency - Prior to pouring concrete
5bd6f5e0-241c-58f5-90b8-3f85b380059e | note | Inspection / Test Method - Measurement
8c1cd58c-e49d-554f-87b7-9df5906eb0fb | note | Conformance Criteria - Concrete Inspection Record
11a058f0-3838-5722-9f60-8e6fab8657ae | note | Records - Site photos/Concrete Formwork Checklist
631ca45d-86c0-5019-9042-6264c89769a0 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10 - Concreting
117dc37e-51a7-50ff-85b5-35c60dc7d688 | note | H
69018828-cdd9-57f6-b352-4e245105c7a3 | note | Detail - The MSQA Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required
2ed95d1b-c428-52ad-ab85-d4432bc6f619 | note | Frequency - Prior to concrete pour
f5108f52-11aa-5d5a-9ad1-e4ca419b19ae | note | Inspection / Test Method - Visual inspection
e6ce21d7-83e9-587a-914e-dd4dfbc171e1 | note | Conformance Criteria - Engineer will be notified via email/SMS at least 24 hours before required for inspection
dfef2d05-0f1a-5e89-aa1c-fa07f4531f5d | note | Records - Email / SMS
f122a913-2e33-5bb3-a067-9f260e7ccbed | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10.1 - Concreting
34be1a9a-a917-5f48-a62f-79b6c4fab4c9 | note | W
bc58a866-d889-5284-9a82-c3bd46788329 | note | Detail - Vibrator to be used throughout concrete pour
cf52789a-f377-534e-b60b-23de42381468 | note | Frequency - When pouring concrete
260f281f-4b22-5426-a5fd-29bfe9bf78e0 | note | Inspection / Test Method - Visual Inspection
28883e40-f2c1-54e2-8656-562e0cecf13b | note | Conformance Criteria - Concrete Inspection Record
80e5bcfa-25da-5593-99b1-51ed94e957c5 | note | Records - Concrete Formwork Checklist
6d12907d-bfe6-5814-8ca9-d0005fc178f5 | note | FH Initials - Site Engineer
| checkpoint | 10.2 - Concreting
f7d2df1b-a8a8-59a1-a772-a17db52e0049 | note | H
45c73e1a-6619-5db2-bb77-f25fdacd6b67 | note | Detail - Concrete surfaces shall be U5 broomed finish for ramps, and exposed aggregate finish for table top.
bddb1747-4a88-5580-b98b-c9e2f3d827a4 | note | Frequency - At completion of pour
5de21843-a826-50e9-a344-195f8d3bf3bd | note | Inspection / Test Method - Visual inspection
ec1d3784-a6c6-5e3d-9f5c-01da6669016a | note | Conformance Criteria - Concrete Inspection Record
6c920759-c721-561d-8697-d757f55965ec | note | Records - Concrete Formwork Checklist
f9b5bd9d-302f-540c-8ad0-1a0fbac94f51 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 11 - Curing
7af45420-4d31-5561-9a3b-198d8e3eb605 | note | M
1bc11787-46e0-5da2-819a-220bef1c7338 | note | Detail - Concrete will be left for 48 hours minimum to cure before traffic is allowed on it.
cce22517-65b5-597f-8d84-08a78a3c5de1 | note | Frequency - Post Pour
32d2015a-9c0d-52ef-8644-576e87aab836 | note | Inspection / Test Method - Monitoring the time allowed for curing
594b4a3f-dab6-5637-b551-9eb183fabf15 | note | Conformance Criteria - 48 hours minimum have passed
23e3fcf3-2f44-5633-9cb4-cd782e7e9c21 | note | Records - Concrete Formwork Checklist
71b6bb6e-3dab-5ef4-88d2-cd00559e69cf | note | FH Initials - Site Engineer
| checkpoint | 12 - Remove formwork
fa01c4b1-2f3c-5c31-998e-b5b797852773 | note | W
343a09ac-cf9a-57d0-b371-13ddffc9892d | note | Detail - Remove formwork after 48 hours
78696a15-4037-527c-b05e-17133764d97a | note | Frequency - Post Curing
2c6014dc-4c2c-5551-b3b9-3be9dd92b866 | note | Inspection / Test Method - Visual inspection
ebd734e3-f7af-5c5a-bf77-feb5db5619f4 | note | Conformance Criteria - Concrete Inspection Record
efd21a9c-a633-5f37-8e96-6f746bd8bdca | note | Records - Concrete Formwork Checklist
fc97511b-0b74-5520-928a-42ee66284224 | note | FH Initials - Site Engineer
| checkpoint | 13 - Asphalt- Concrete extension slab/ Toe
1718446f-5885-5108-a6b5-36459b135fe5 | note | H
862698ab-7128-50b1-9fa1-a2df69cff95a | note | Detail - Two rows of Lesa diamond placed mid depth @600 C/C along construction joint as per TDM TC003
8b48170f-42fb-598b-80b8-fd45c20a2e50 | note | Frequency - Prior to pouring concrete
f47c8879-c242-5881-95b9-79474ef14b2b | note | Inspection / Test Method - Measurement
f5148ed9-3400-590b-b5fc-dcc942f7492a | note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
a632ef94-7c25-5b22-b660-aceed8888408 | note | Records - Site photos,delivery dockets
c2b0ae29-2f58-5d4a-b8a0-ae1c8ad15a57 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 13.1 - Asphalt- Concrete extension slab/ Toe
5573c8bd-4092-5ea5-aa8d-dad41a95173e | note | H
213a958c-317f-52f4-819a-96d919c40c00 | note | Detail - 200mm thick 50MPa Concrete with two layers of 663 mesh
08d9e0bd-5c52-50bb-aaae-37336611bb39 | note | Frequency - Prior to pouring concrete
d7a6095b-3b56-5518-a333-064caf99c5af | note | Inspection / Test Method - Measurement
a21e0186-a353-593c-927f-62fe93a8235a | note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
e9552771-19e4-50bc-b5d4-5c603587af85 | note | Records - Site photos,delivery dockets
f5851840-ff4c-5da0-bcc3-eb4de4ba49d7 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 13.2 - Asphalt- Concrete extension slab/ Toe
c3272865-fa17-5a09-8611-2dc77eb71aec | note | W
b4c35e9e-8a77-5d41-8d9d-caeff69384a4 | note | Detail - Tack Coat between AC and Concrete slab
3f851fbf-9a97-50e9-8e09-47dc32b5a64a | note | Frequency - Post Curing
f9063739-8d2d-5109-85ae-02534e1220e2 | note | Inspection / Test Method - Visual inspection
5db1dca2-b438-5457-b0cf-c55b73566e44 | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
80b55f22-9f89-5970-91e3-ccb2301c6051 | note | Records - Site photos
8a882f0f-2d26-52f6-8f2f-5ee9ea45b861 | note | FH Initials - Site Engineer
| checkpoint | 13.3 - Asphalt- Concrete extension slab/ Toe
637ee4ad-cad5-5dff-a310-1b4a1f611551 | note | W
a423ccd9-f12f-53e6-8c0b-f4529ef6f067 | note | Detail - 50mm thick DG10 / Mix 7
a4436f06-c33c-5f96-a3bb-dd2f45379caa | note | Frequency - Post Curing
34c886c8-c55a-5561-bfe2-08b279a3e1d9 | note | Inspection / Test Method - Measurement
b377205d-3b62-5f8d-b405-e2435fbffe89 | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
9b3e6a67-a1d2-51c2-a520-2a1bba5e9758 | note | Records - Site photos,delivery dockets
3efbd145-8ba5-5b22-8628-c69cd50e3100 | note | FH Initials - Site Engineer
| checkpoint | 14 - Lot Number QA File
bdcb2868-da6a-556c-b4b6-6a7eb0a4276b | note | W
679d987e-d33c-5f7b-97ec-e2edbd3633c8 | note | Detail - Ensure all QA Records,site photos and incident cases (OFIs) are closed and included within QA file
6e1d9664-76a2-54d5-b4aa-3900bf7d41eb | note | Frequency - At completion of Lot
e092abbd-5ac8-5339-9119-3850afa32f2b | note | Inspection / Test Method - Document Review
0cc05428-edc2-5949-87da-abb689913190 | note | Conformance Criteria - All QA files compiled and sumbitted to client
b6a7522f-f120-51a6-9431-b508b5906dd2 | note | Records - QA records
23ac1799-a1c3-5052-8ad0-ef0fc8d696e2 | note | FH Initials - Site Engineer
| checkpoint | 14.1 - Lot Number QA File
47f9a892-46da-5c2d-81f2-a169d7e5fbf5 | note | W
78c71332-c880-5931-a817-3b3f603ab7a3 | note | Detail - Delivery Dockets to be included in QA file
94849429-7261-502f-ae9c-4e088d74d36e | note | Frequency - At completion of Lot
38b26994-f2f6-517b-b2a5-0cbe29068ff1 | note | Inspection / Test Method - Document Review
d2d98d1a-de4d-54cd-a260-16c4b0b012f9 | note | Conformance Criteria - Delivery Dockets to be included in QA file
e5524f37-1b54-5d6f-89a3-d8fc002ac2cb | note | Records - QA records
8faa7480-976d-59de-8f12-381024e40bd1 | note | FH Initials - Site Engineer
| checkpoint | 15 - As-builts
de83c686-dde8-51ce-907d-b993402fb4c2 | note | H
d51f0e5f-234a-5ea8-bc11-af14c55b6531 | note | Detail - Red pen mark up drawings to be included in QA file
a546573a-2e86-594f-9805-e26533113004 | note | Frequency - At the completion of the Lot of work
90e38ad5-a4cb-55cd-861f-31d949b6689f | note | Inspection / Test Method - Drawings
44c7f70a-7fee-574e-901f-63a2a63a41cd | note | Records - Asbuilt Drawing
5e7a36e7-5dc4-52fb-8974-d23bdb9aa2d2 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checklist | ITP - Massey Road - Enabling Works |  | ITP - Massey Road - Enabling Works | 34998639-8d25-4621-8f2b-91be9c99aa88
| section | Site Set Out
| checkpoint | 1 - Site Set out
9155c6a7-5d09-5a73-b388-b9277c99c38e | note | VERIFICATION ACTIVITY - Surveyor
9573b97c-6575-5bf0-a13e-ed2de3bf4a0d | note | METHODS OR REFERENCE - Surveyor
1c9d9c11-fc82-5dcf-b2a7-899225e911ca | note | Frequency - Everysite
2748bb4b-c7f1-58a6-bd05-e9d9fe1c20c6 | note | ACCEPTANCE CRITERIA - Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criterea is acceptable.
18586efe-26e4-52dd-b89a-2f98a1e505b0 | note | Mandatory HOLD POINT -
a7b4269c-f329-5b0e-97c5-b74f1fee0ec6 | note | Records - Onsite records/photos
4ce8fc28-313a-597e-ba50-b9dab4eab221 | note | Onsite Responsibility - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| section | Materials
| checkpoint | 2 - Kerb & Channel
c6637c69-bc79-5fb7-aac9-993e8c4921b8 | note | VERIFICATION ACTIVITY - QA FORM
1d93cb49-cb1d-5799-a49b-851dfc27ce05 | note | METHODS OR REFERENCE - TDM Technical Standards - KC0001
9e7939ce-e43b-57b9-a106-8fba8cb2c406 | note | Frequency - Everysite
aa4d25a1-e4ce-53da-9263-77f5bd60f6b5 | note | ACCEPTANCE CRITERIA - Kerb & Channel to be laid using precast hand-laid. On compacted GAP40. Concrete 20MPa @28 Days on 100mm GAP40 with the subgrade CBR>5
05b62f31-d290-5536-832b-a067fccbede6 | note | Inprocess Inspection
067c9b78-2f07-5e2d-bdb7-0d187b36e8ec | note | Records - FH concrete QA sheet, photos. Concrete Plant Docket
08ef3b0b-5f36-5786-b928-ca559a08d4da | note | Onsite Responsibility - Site Engineer
| checkpoint | 3 - Channel Level
4a769b49-d3c6-5259-a255-343b0962fd0e | note | VERIFICATION ACTIVITY - QA FORM
e8a94b1b-19bc-52c4-9429-7ff10f48736d | note | METHODS OR REFERENCE - TDM Technical Standards - KC0001
e852a434-5ef6-5c2c-b9ac-47e830cb70b7 | note | Frequency - Everysite
69d4dc2e-588a-53d8-aa4d-b4d3c3ce0b57 | note | ACCEPTANCE CRITERIA - Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
b4ff52e3-a527-5d72-988c-46a3eec9bce1 | note | Inprocess Inspection
775a7c5f-77b6-5235-a5e6-d617767f8af0 | note | Records - FH concrete QA sheet
36700016-a72e-5763-899c-1eda087a07cc | note | Onsite Responsibility - Site Engineer
| section | CIVIL WORKS
| checkpoint | 4 - Concrete Footpaths
d88ba717-52ee-51ca-95d4-f73496b55bb2 | note | VERIFICATION ACTIVITY - QA FORM
27166f9b-94a0-5d13-9cd7-2c55dc08a5db | note | METHODS OR REFERENCE - TDM Technical Standards - FP0001
78e0f4ea-f6d3-53e2-a482-81100faae26b | note | Frequency - 10m Intervals
6d004f96-7801-5f56-8d6a-f1f72242d959 | note | ACCEPTANCE CRITERIA - Subgrade -(CBR > 3) Basecourse - 100mm min. thickness GAP40 Clegg CIV > 15 Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish
add7cb81-be84-519a-8274-65ff39858af1 | note | Inprocess Inspection
187975e0-bea8-5d33-9fbb-953dff2e6c66 | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
b683068e-72f4-51b1-9a2c-7ef3b9afabf1 | note | Onsite Responsibility - Site Engineer
| checkpoint | 5 - Concrete Footpaths
7c564fcc-2eca-5773-bc3d-2dfd94dc7fb9 | note | METHODS OR REFERENCE - TDM Technical Standards - FP0010
d857c43a-37b3-5548-bfd2-2382fc758695 | note | Frequency - Each PX
ec3db974-9dfa-5295-9662-5507b0e3ba8b | note | ACCEPTANCE CRITERIA - Warning TGSI tiles should have 100mm concrete slab underneath
5d41e326-85f5-5122-a13c-c8a265c8bb6d | note | Inprocess Inspection, Measurement
0dff9dc3-f262-5bd6-8bed-0af2586228c3 | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
1f2aa361-3b53-5a61-828b-5274c1973713 | note | Onsite Responsibility - Site Engineer
| checkpoint | 6 - Tactiles
29670cc4-3be3-567e-83de-83d2cc4c301c | note | VERIFICATION ACTIVITY - Visual
92debe81-7eea-5dca-9886-7c401d0d3d37 | note | METHODS OR REFERENCE - NZTA RTS Guidelines for facilities for blind and vision impared pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
a25c3f13-fe63-599a-b031-a9bb35906ce9 | note | Frequency - Everysite
20457c5a-0583-57e4-b61d-ed465b25cfc6 | note | ACCEPTANCE CRITERIA - Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
a1df43b9-e925-5ab9-85fc-355b6b9e6664 | note | Inprocess Inspection
de0aadb3-bf94-529f-b18f-1d39f05614bd | note | Records - Photos
bf6b77f6-062f-5581-9e44-b1a26c96b35c | note | Onsite Responsibility - Site Engineer
| checkpoint | 6.1 - Tactiles
8971a2f5-bb13-5d42-8aec-67031873b392 | note | METHODS OR REFERENCE - AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
4930a5d8-1504-58b5-a6ae-227b8a960e67 | note | Frequency - Everysite
a66bd602-c95b-5ebb-b09d-724b1ce8ec58 | note | ACCEPTANCE CRITERIA - Edge of warning indicators to set back 300mm from the face of the kerb or lane, extend the full width of ramp and be 600mm deep.
e45a8bb6-b2e0-5c43-aa04-7044e66a093c | note | Inprocess Inspection
91693cb8-1eb5-502c-983e-091ddf8cdd0f | note | Records - Photos
e5e4bdf4-e6ba-5c17-840e-a749075c3cdf | note | Onsite Responsibility - Site Engineer
| checkpoint | 6.2 - Tactiles
a79fd993-8fac-5734-81ed-2f67cacc3632 | note | METHODS OR REFERENCE - AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
fa0f7d15-68bb-521e-b451-2ccbb60ba758 | note | Frequency - Everysite
3ff55ba9-3907-55f9-8aa6-489034704380 | note | ACCEPTANCE CRITERIA - TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
ac99d625-3e52-5d04-99db-d6b1a4375a95 | note | Inprocess Inspection
58402bbf-5419-5b1a-aa0f-9c05b8502954 | note | Records - Photos
791c8c5e-72aa-57c0-84bc-41132ca47fbb | note | Onsite Responsibility - Site Engineer
| section | RAMM DATA
| checkpoint | 7 - As built information
8901cea0-5e11-5b6c-aeb6-6729ba0a34f4 | note | VERIFICATION ACTIVITY - RAMM DATA SHEET
eeee5a1e-797e-5f84-932a-eb4062831349 | note | Frequency - Every Site
b0e274ce-ab14-5457-ad04-b050346328c4 | note | ACCEPTANCE CRITERIA - As built drawings and Ramm Sheets Completed
ea8d0b36-ad77-5706-bd4a-8a7b0f55de1c | note | In Process Inspection
0932f658-5f19-5557-85b6-8f14d1794e80 | note | Records - Asbuilt records
0dc5f6ba-3f18-5ae5-993c-b23bab282b33 | note | Onsite Responsibility - Supervisor and Engineer
| checklist | ITP - Massey Road - Stormwater |  | ITP - Massey Road - Stormwater | 5f0cd92d-fc0a-4279-b9e8-4dd2f9d4b2cc
| checkpoint | 1 - Permits & Services
da9a1cdc-6c1f-5556-8907-38b6dc499e1a | note | H
32f678d7-8096-5cc4-8017-6f3a433df101 | note | Detail - Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
79f687ae-cdf9-5201-b0e8-994997500e36 | note | Frequency - Prior to any construction commencing
e75c336f-e7da-511e-9cf6-0f6586a937a2 | note | Inspection / Test Method - Document Review
9e4ba9e5-8c1f-5993-b368-0e9325d27b92 | note | Conformance Criteria - Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority
6bc12c23-1b02-562a-822c-322dc82d9154 | note | Records - Permit attached or permit number noted.
41827695-8816-52ae-ab0d-f4c366d9ad06 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.1 - Permits & Services
e22f5f41-3e42-5bd5-9b9d-ae8c85b29dcc | note | H
445ee068-7598-551d-a1e2-2f4b93f94194 | note | Detail - Locate and mark out all existing services
c4a8c0bd-024c-5b56-9633-3a03855bbd7e | note | Frequency - Prior to any construction commencing
5849b6e8-cccd-54a5-8439-2670e06b656b | note | Conformance Criteria - B4u dig procedure - follow utility protocols
ec2063f1-c7c1-5959-bf75-8f905ffaa973 | note | Records - B4u dig plans & GPR report attached
3692e9a1-b90d-54ad-939f-4d7d5004e74b | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Pre-Construction Sign Offs
12e4bb6e-6fc1-5923-926b-8f33853e6b82 | note | H
83bf1cdc-63e3-5564-8542-2d599b767638 | note | Detail - Sub-Contract and Supplier Agreements
c81ad7b2-a9c6-510f-a4ef-c6af7837f27f | note | Frequency - Prior to commencement.
c5a2a09a-48ce-55e5-8a41-e803155aa502 | note | Inspection / Test Method - Document Review
459eab4c-6609-5990-8555-6f5231a9e345 | note | Conformance Criteria - Sub-Contract and Supplier Agreements to be agreed and signed
a79d8348-e84f-5a67-a40d-5db039cb2748 | note | Records - Subcontract and Supplier Agreements
b28ef0fe-7449-555f-a8d3-907f63f857a6 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Design
f4b9c151-f656-582a-9fc5-f26a5fb51169 | note | H
70102531-642e-54bd-ad21-fc9d42797059 | note | Detail - Design is approved and Drawings are of the latest revision.
d1421314-c561-5268-842e-d774acab378e | note | Frequency - Prior to commencement.
55ef32a0-c955-5f13-9310-aca13060c4a1 | note | Inspection / Test Method - Document Review
418e5eb3-b440-563a-9232-ed15db2d5c18 | note | Conformance Criteria - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
984024bc-22c8-5f9d-a4bd-189c9998c861 | note | Records - Drawing Register.
0bdc89a4-279b-5dfb-89ae-dde27fe62c31 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Survey Setout
e29abc16-e4f5-52b1-83ea-4e9cb11f79ec | note | H
1b096634-9eca-5c04-a10e-a97e981f13fb | note | Detail - Setout Pipe Alignment and Service Locations with inlet & outlet points and inverts as required to construct to design
d6a29dbd-c225-5db6-808a-ea4bccde54a6 | note | Frequency - Prior to commencement.
81c8331a-a98c-5a58-b468-d87283d9c42b | note | Inspection / Test Method - Survey
3e039cb1-5c37-5b06-9617-65126cd5fae9 | note | Conformance Criteria - As per Blue Barn Consulting Engineering Drawings: 02188-T-400 & Setout files
6f01aeb3-82b6-529f-a22c-dd0ebeca0363 | note | Records - Survey Receipt.
8ad63546-a270-563b-bde3-6fbf3989a498 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Pipe and Manhole Material Compliance
ef5de62b-8dc8-5a86-9315-83cc55fa4f48 | note | H
9f3a7e59-6d82-5d10-80b0-5fe658d0b729 | note | Detail - Cesspit, Manhole and Pipe shall comply with relevant AT/TDM standards
0a7c9f94-c52e-54f6-b027-46a305d85a77 | note | Frequency - Prior to commencement.
a7b8120b-8cd3-523e-a8e9-260e3aae858d | note | Inspection / Test Method - Document Review, Visual Inspection
ec0600c4-dc7e-5fe0-9908-82a92e9d1837 | note | Conformance Criteria - Pipe shall be Check for freshyly formed pipes and return if required 1) DN225 Class 4 RCRRJ pipes AS/NZS 4058 2). All Concrete RCRRJ pipes to be fitted with Rubber rings 3). Pipes shall have product certification (ISO Type 5) to AS/NZS 4058 Prefabricated concrete Manhole shall be in accordance with TDM Standards & AC COP
4d539b6d-1aca-5405-9e4c-a948f33c437e | note | Records - Manufacturers Data Sheets, Delivery Dockets
c7576ca6-5303-5814-9f59-27b8324ffdd9 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Locate Existing Services by Hand Digging / Hydro Vac
6d43233a-48b6-519c-b55c-26e6d8631a7e | note | H
abc5c343-ca8f-51d0-a5c5-a71693da004f | note | Detail - Ensure all services conflicting with the line of trench have been exposed by hand digging.
8dc594d3-a8d2-5424-8740-b5318611380f | note | Frequency - Prior to commencement.
a6c075f1-d06a-53f9-bdb5-ddc3f413569f | note | Inspection / Test Method - Potholing / Survey
5a241202-7d14-5fae-a7bb-cd3e77c55ae3 | note | Conformance Criteria - All conflicts have been located. New services and / or conflicts to be advised to Project Manager.
fb64f3a4-0c76-51cd-90f6-8219e8499b8d | note | Records - As-built Drawings. Doc. Review
789e265a-e607-5dac-b15c-0cb989b1f2d1 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Trenching & Excavation
2e5943f4-e991-5313-af71-6d879d83c872 | note | H
7f07e75d-2bb9-50f7-8888-f12a389b90f6 | note | Detail - Excavation methodology
6e7cba23-3af0-508d-bc79-80dcbf43ba45 | note | Frequency - Daily
7afdc185-8e2b-54c6-9356-1cb2110604cd | note | Inspection / Test Method - Prestart review
33a61db8-e1c9-58b8-8752-4e6f190f2ca9 | note | Conformance Criteria - The excavation, benching and shoring requirements shall be in accordance with Worksafe Excavation safety guidelines (2016)
a1c53b32-c9e2-5421-9498-50f491240cc7 | note | Records - Prestart RCP
92a7596a-c6b6-588e-8cfd-bdee3bf8dba3 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.1 - Trenching & Excavation
661699ba-1adf-55fb-9a1a-05796d65ba50 | note | M
df868bdc-d0d1-56c7-bf2b-8bbc37364056 | note | Detail - Trench Profile - Width
86e8a564-c52b-51a4-9d2a-0957be7b4ee0 | note | Frequency - Daily / as trenching takes place. Different depth methodology
873d4b1c-5275-5337-b360-8000b25f3919 | note | Inspection / Test Method - Visual Inspection, Excavation methdology
31495fce-cc10-5f9e-9812-e3af3b838a47 | note | Conformance Criteria - Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing
932e14d9-e91c-5f60-a7e1-f18c19103f1a | note | Records - Construction Photos
88c66b21-d027-5671-a4ed-a892f90f61c0 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.2 - Trenching & Excavation
a984476a-5fc5-51c3-8bfa-7087557b0dbf | note | W
06b40d93-7b7f-53c4-98bc-c2ca7623d6b8 | note | Detail - Trench Profile - Depth
1e72f5ab-4a8e-5020-91b8-bc43716a3912 | note | Frequency - Daily / as trenching takes place.
ba24aa2f-5cfa-5a87-ba21-23f060355329 | note | Inspection / Test Method - Visual Inspection, Measurement
336e696d-0b54-50a3-be1a-e6c7ef780b9d | note | Conformance Criteria - Trench depth varies according to longsection and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings
14910930-9fb2-5012-bc5d-019e4c9b2d10 | note | Records - FH Drainage Line Record / Construction Photos
72aede44-6995-558a-81c1-c7a30b31147b | note | FH Initials - Site Engineer
| checkpoint | 8 - Bedding for Concrete Pipe Laying & Manhole & Cesspit
a189bbaf-3ad4-5401-aa5a-f189666f315b | note | W
126f28f3-7528-5991-a2c6-1ee65c9ccdad | note | Detail - Placing and compaction of Bedding Material.
f33a6db6-19e3-57b9-90b2-bb1d16164a5b | note | Frequency - Inspected continuously during placing and compaction of Bedding Material.
5daa61ce-74ad-571c-8d1b-9690f7a8ecc2 | note | Inspection / Test Method - Visual Inspection
a132a581-5955-536a-a23f-768857fb121a | note | Conformance Criteria - Bedding & Pipe surround material to be GAP7 or GAP 20 (Stevenson Quarry) or alternate material that complies with AS/NZS 3725
55a80541-5b9e-58ef-be74-e8a22438a048 | note | Records - FH Drainage Line Record / Construction Photos
a3af7893-b0fd-52fa-bed8-29d9a246fd50 | note | FH Initials - Site Engineer
| checkpoint | 9 - Pipe Position Tolerance
035709c7-774a-5914-8866-3c6fc76a9866 | note | M
0295fc89-d9c1-5087-a48c-0c814780e03b | note | Frequency - At any point of pipe
7ea57b09-786f-59f2-8916-0e0889654288 | note | Conformance Criteria - Position tolerance for pipe laying at any point along the length of the installation shall be within ±30 mm from the specified design.
ddf8df00-5c32-57ae-b7fa-136e7e859f4d | note | Records - FH Drainage Line Record, Survey Data.
5e888913-294f-504a-bddd-36787dff78d4 | note | FH Initials - Site Engineer
| checkpoint | 10 - Trench Backfill - Placing & Compacting
a807fd23-591c-52ff-9db9-fc3c730a7a69 | note | M
bdfbe66d-22ef-5041-a2f9-d52f5aee2cf3 | note | Detail - Placing and compacting of Trench Backfill Material
ae56d4a2-5720-5014-8c48-7748944415f0 | note | Frequency - Throughout Trench Backfilling operation.
99f8d3c4-9018-5f08-af77-bcdcb6d1a684 | note | Inspection / Test Method - Visual Inspection
4f81b30f-5754-510e-b3de-807464567e2e | note | Conformance Criteria - Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm
03ade187-40b2-520f-8e63-ef97df61308f | note | Records - Construction Photos
8b541cc4-f754-532e-8eeb-ad42689387a4 | note | FH Initials - Site Engineer
| checkpoint | 11 - As-Built Drawings
aa993bcd-8b99-5aab-a889-7eef9653cd97 | note | W
fc4a3097-3584-585f-9af4-7fadac94bb2d | note | Detail - Red pen marked-up As-Builts of every 'Issued for Construction' AT drawings
f0aeb9a3-b78c-5db5-88f9-0d63755ce112 | note | Frequency - Final As-Built Drawings to be completed within three months of the construction completion of the asset or infrastructure.
60ebce65-f69f-5dff-bf2f-ff1d3ac1d127 | note | Inspection / Test Method - Drawings / Visual Inspection
7e94ad03-66dc-57be-8bb1-aed889b0a096 | note | Conformance Criteria - As Built and GIS Data
ac681d74-f676-5934-9b14-c6ed9ab17916 | note | Records - Redline As-Built Drawings, scanned as .pdf files.
84d37e59-cd1b-5b40-86fd-93bce685688f | note | FH Initials - Site Engineer
| checkpoint | QA checked by Quality Manager
37d7cd3c-582b-57b9-9103-0539a866bc50 | textbox | Comments:
ca801cb8-b363-5c45-8aa2-7081e108fba7 | textbox | Print Name
7222339c-7d05-5969-9307-fb3e4dd78e2a | textbox | Position:
9c500253-e438-5871-b91a-3c9a5acfd269 | textbox | Date Completed
| signoff | Add Signature
| checkpoint | Accepted by Engineers Rep
781938b3-8c7f-5e3a-93b5-246a8b3f5d7f | textbox | Comments:
2ac0df82-909d-52b5-b0e0-248faaa5aa6b | textbox | Print Name
dc8bfc55-9c40-5198-8b96-3906d5dcc042 | textbox | Position:
0edd4d1b-b6cc-5831-8fc0-8e2821617295 | textbox | Date Completed
| signoff | Add Signature
| checklist | ITP - Massey Road - Traffic Islands |  | ITP - Massey Road - Traffic Islands | a2d3282b-ee56-4b2f-b7ba-274e815f50df
| section | Materials
| checkpoint | 1 - Mountable Kerb
f09e6aab-0a80-533e-8ad6-dc496370ea2d | note | VERIFICATION ACTIVITY - QA FORM
32836d5a-eb3a-5e5d-b021-99094e68eaeb | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002
0b942c98-0f1e-5e08-84a9-5ac8c3fde6a4 | note | Frequency - Everysite
adc61bf7-a6ff-582f-831a-ff67bd5364ba | note | ACCEPTANCE CRITERIA - Mountable Kerb to be laid using precast hand-laid and painted with two coats of reflective paint
61c7cfbc-c2ee-59f5-b76e-0f3838974132 | note | Inprocess Inspection
691dcf5b-6d5c-5958-9bed-0efd108989bd | note | Records - FH concrete QA sheet, photos.
68d4399e-9170-522a-b380-a052f3e97d74 | note | Onsite Responsibility - Site Engineer
| section | Construction
| checkpoint | 2 - Survey Setout
9a3066b6-a122-56f7-b3f5-6b25b42f9d03 | note | VERIFICATION ACTIVITY - Survey
e8101845-2cc8-5995-8ea1-b4bd52277eb9 | note | METHODS OR REFERENCE - Setout Kerb Alignment required to construct to design
1d1ae9b7-ded4-52bc-9c6b-7c1d5c83ac27 | note | Frequency - Prior to commencement.
e317a022-12c0-5948-a1eb-64f82b4db154 | note | ACCEPTANCE CRITERIA - Survey
61838f99-c3f5-5e16-90f5-bcbfa445ffca | note | As per Construction Drawings
2b96f036-2cf5-58a8-bc26-36d616b912d7 | note | Records - Survey Receipt.
942b1a30-235e-5435-bf85-829ee438863d | note | Onsite Responsibility - Site Engineer
| checkpoint | 3 - Concrete Island
0c8aafa9-435b-5e44-94bd-a55a47f01d43 | note | VERIFICATION ACTIVITY - QA FORM
8c41222c-5c2d-5e86-9f04-77a7f00894eb | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002
32467ee5-62b2-594d-9ea2-6dc2213765cd | note | Frequency - Each Site
bda3af89-2d99-5002-a7b1-75403c2afc86 | note | ACCEPTANCE CRITERIA - Kerbs to be haunced with 20MPa Concrete
e46ca91f-3ca3-52cc-8220-c769689c268f | note | Inprocess Inspection
f07cd934-989f-582f-84ea-4e98e4f7373c | note | Records - Photos
a9a5780d-9f86-5153-92e7-033d16bedde6 | note | Onsite Responsibility - Site Engineer
| checkpoint | 3.1 - Concrete Island
73c1c391-38ac-5421-aa8d-7b2866686b7f | note | VERIFICATION ACTIVITY - QA FORM
ded2b8ee-e273-5acd-9ce2-19d96888c6cb | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0003
64668834-faa6-5641-b382-3df0227e5145 | note | Frequency - Each Site
e3744d99-6c06-59a6-ba4b-42cd3d052faf | note | ACCEPTANCE CRITERIA - Basecourse to be 150mm min thickness of GAP65
2ce6deb1-7ab9-5984-a994-3d7536fc33bf | note | Inprocess Inspection
c4be895d-f36b-5eff-b988-4c77a134cb87 | note | Records - Photos
bec1a210-c2bc-511d-b44e-f7a6a9b75a24 | note | Onsite Responsibility - Site Engineer
| checkpoint | 4 - Concrete Infil
f543ee26-4356-5560-b3a8-12f683bedfcc | note | VERIFICATION ACTIVITY - QA FORM
771e3a36-bc99-541b-a14c-dcbfd8098a3d | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002
ab887746-b6af-55da-8656-8430cf4f97d1 | note | Frequency - Each Site
2b05d846-e6e1-56ae-ba04-29bd2ae8030c | note | ACCEPTANCE CRITERIA - 180mm depth of 20MPa broom finish unreinforced Concrete with 4kg/m3 black oxide Cross Fall of 2% or max rise in centre of 180mm
c89dcf6c-6c90-5937-b319-0b0675c304a8 | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
959defd7-c866-547c-bc44-44563ee6347d | note | Onsite Responsibility - Site Engineer
| section | Asbuilts
| checkpoint | 5 - As built information
0c5f9250-04b6-551a-854a-e04f0255c0df | note | VERIFICATION ACTIVITY - Drawings
2c4d402b-5d0c-55d1-b6a9-2816c7216811 | note | Frequency - Every Site
760cd9d8-1fc7-508f-b5c9-37bfb57cadbb | note | ACCEPTANCE CRITERIA - As built drawings
f8d213c5-72c3-54f0-ad75-193f76ce826f | note | Inprocess Inspection
9e525868-0b18-5696-80d6-d352ffc4ca51 | note | Records - Asbuilt records
790cb7d3-2c64-577f-99f0-41ccc21dd6dd | note | Onsite Responsibility - Supervisor and Engineer
| checkpoint | 6 - RAMM DATA
997d90b1-6615-50d1-a51e-509a66fddc73 | note | VERIFICATION ACTIVITY - RAMM DATA SHEET
b657d427-30b9-5d2a-b145-0e2418c98123 | note | Frequency - Every Site
110252e8-e8e9-5b02-afa1-90afc3d2c249 | note | ACCEPTANCE CRITERIA - RAMM SHEET
1462f469-0207-52f4-8fd5-bbfe29650d20 | note | In Process Inspection
42c08529-40aa-562e-a80b-c9c658ae6b53 | note | Records - Asbuilt records
c7f0b99e-e486-541e-9d50-fa849aca33c5 | note | Onsite Responsibility - Supervisor and Engineer
| checklist | ITP - Mckenzie Road - Concrete Speedtable | itp | ITP - Mckenzie Road - Concrete Speedtable | 64ea5210-3072-45cb-acfa-fc2ed7e956ce
| checkpoint | 1 - Permits
22698320-e06a-5234-bff8-505f6cccc384 | note | H
a030f5ac-3fd0-58d8-bdfd-a6cf7753deec | note | Detail - Obtain Permits
d19a66ee-56c1-5b11-9e0b-bad8e7a7a193 | note | Frequency - As required
f1483c1e-5895-599f-a2a7-020b7801cb9d | note | Inspection / Test Method - Document Review
8c53fcf4-7b0f-5ea0-a895-3be35a3bb048 | note | Conformance Criteria - Control Checklist - Fall Prevention (if applicable). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
2d65f655-40ff-502a-93af-f59a559f51dd | note | Records - Permit attached or permit number noted
2a9e3b6c-04a3-50c8-87c0-42bdd0972b2c | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Pre-construction sign offs
3cc88b9b-10d8-5efa-b386-55e87c9085b2 | note | H
71c3aa7c-73a2-57c6-a5e8-ca347bf15f23 | note | Detail - Ensure that Sub-Contract and Supplier Agreements are signed
53927a1f-f372-5f6a-b8ac-72a5658a6ca9 | note | Frequency - Prior to commencement
7cedbe9a-470e-5705-8947-95a2dc525e9b | note | Inspection / Test Method - Document Review
bbceb787-5d3f-5328-a281-4b257d7f3f36 | note | Conformance Criteria - Signed Subcontractor and Supplier Agreements
f2d3923b-a313-5a59-9774-1c18acdfe4aa | note | Records - Subcontract and Supplier Agreements
923055be-7c22-5531-b244-322b2926e812 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.1 - Pre-construction sign offs
047448e5-ddc0-5f1e-964d-2bd9c03adf9d | note | H
63a6e514-31c8-50be-a21c-e31b5024f663 | note | Detail - Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
23ca171e-5205-5852-8196-703a53115503 | note | Frequency - Prior to commencement
d6a3473d-2ad8-5e8c-929c-2dc1150478ac | note | Inspection / Test Method - Document Review
327b2efb-9833-5fce-a1be-cd6b12ff14f0 | note | Conformance Criteria - TMP is approved by CAR manager for each site and works are only completed within the approved dates..
d64b9d18-ebd6-55f4-a3ea-c858fd2816e9 | note | Records - TMP on MyWorksites/On Site
f1b201ef-3559-59f2-8b32-5ba91180ee1f | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Pre-construction sign offs
3232a107-1fa7-5d09-bb82-67ff20792531 | note | H
017b1417-ace2-5af7-be75-75e914e95f7c | note | Detail - Ensure all Sub-Contractors and Suppliers go through FH induction
8b1e106e-23aa-5976-9777-d90cead98d92 | note | Frequency - On site daily
9a6345f8-fb9a-5b05-a60a-b18549a4aae2 | note | Inspection / Test Method - Induction
5b300b8a-cee6-563d-9f0a-a40e38ef5f26 | note | Conformance Criteria - Supplier's and Subcontractor's signatures on hazard ID and pre-start documentation
1bcb3b1c-803c-53df-ba85-69a14402e351 | note | Records - Hazard ID and Pre-starts to safety team
3c7f8f51-7cc4-5426-9b4a-42ca86d89295 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Design
e82c77b9-276a-5985-b7de-34de01be03f2 | note | H
9f2fc21e-dba2-5c13-a90e-977394cd1a35 | note | Detail - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
179a88e3-a9a2-5858-9ab0-20e412015632 | note | Frequency - Prior to commencement
43c0b2e0-e71a-59d0-bc45-37a9783fe11e | note | Inspection / Test Method - Document Review
75ac6eb8-a903-5661-ac86-5f316b2f727b | note | Conformance Criteria - IFC drawings have been received by Contractor
a383978e-4038-5e94-a830-e5db01034e97 | note | Records - Check Drawing Register
a56a7ebb-0d87-5d0d-949c-b26a7b436118 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Installation of Erosion and Sediment Controls
775da63f-2017-5cce-b3fe-e75eb5739150 | note | H
73be6a73-3bab-5ee1-b809-831b4e234906 | note | Detail - Ensure that Erosion & Sediment Control in place
fa9b1fe6-f8bd-580b-a058-11c77eb5db14 | note | Frequency - Prior to commencement
43bafe5c-155f-57b3-9beb-790b23d7e4bf | note | Inspection / Test Method - Visual Inspection
1c25607e-5234-5f27-8306-35b01fc0865f | note | Conformance Criteria - Territorial Authority has approved the asbuilts for the ESC controls constructed onsite and gives approval for construction to commence
ac97b141-107e-5e24-91ab-08b8c6986ba4 | note | Records - Environmental Controls Audit
16b7ac13-7454-54a5-b0a3-83d649fa2db0 | note | FH Initials - Environmental Manager/Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Survey Setout
7c037a27-df20-5b86-ac57-d404a87810b8 | note | H
d5205825-3c09-5026-90bb-20b046aeadd2 | note | Detail - Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations)
eab338fc-de9b-56eb-9517-550e30e82d89 | note | Frequency - Prior to commencement
5f102c93-53b0-5af3-a5e5-e92087c9f163 | note | Inspection / Test Method - Survey + Smart Level
f9d5107a-ff4d-5ec3-b3fa-b36de6125d42 | note | Conformance Criteria - Consistency with Construction Drawing
39a12409-2707-5b28-8648-019d8bcdcf74 | note | Records - Site Photos post surveying
46fbae8d-e477-5da2-a5f6-21f6b388d7d5 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Locate Existing Services by Hand Digging
33872b73-a217-5ee6-a206-0fb702da9e89 | note | H
7c59b55d-f534-5b75-92e5-748221d81c6d | note | Detail - Ensure all services conflicting with the line of trench has been exposed by hand digging
c03c9a75-0ce9-58a0-804c-36962bbf53e6 | note | Frequency - Prior to commencement
64a35a42-8da3-52b5-b58c-ad1616ec3cfa | note | Inspection / Test Method - Potholing
9ca766b1-2d50-587c-acc2-32887c449f28 | note | Conformance Criteria - All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. Asbuilt all services
8c07dccc-0e1c-5949-b60f-473031170d5c | note | Records - Digging and excavation checklist, service planes,As-Built Drawings Doc. Review
8e6c6103-8e86-51f2-bbf5-9a44cb9ca7bb | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Material Compliance
56cb89ef-7c4d-5d42-942a-c1601e9bd753 | note | H
2fc4a401-b8b5-52f2-bfa9-eabb3a35913f | note | Detail - LESA dowels to be used at all construction joints at 600mm clearance
df376724-10ef-5926-93d8-3731dfd08071 | note | Frequency - Prior to pouring concrete
bad98a8e-ee93-5523-9fe3-7a0e56349036 | note | Inspection / Test Method - Document Review
604a8015-533c-508c-9d10-5b5f04c16ddd | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
a8eb8ea0-e396-5037-950b-0c3184361f31 | note | Records - Delivery Dockets / Photos
7cdc6a3f-fb52-5dd0-be67-010204d95d38 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.1 - Material Compliance
cfe7971c-7039-5592-8800-198bbea291c2 | note | H
8d8b874f-62d2-5798-9555-4aacaaeaa70f | note | Detail - 0.25mm polythene layer placed across all surface area at bottom of raised table
26b67a34-9fb8-53a4-a224-e684f74d4740 | note | Frequency - Prior to pouring concrete
f6d5cdaf-e549-5ef5-99d4-64123f7b3ceb | note | Inspection / Test Method - Visual Inspection, Document Review
6d34aa3c-ff4d-5788-b984-27665e7ce67e | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
0404bd68-a9e9-5b4b-92a2-b6bdb4c77552 | note | Records - Delivery Dockets / Photos
4e3663da-1863-5d30-be56-1e6209816b66 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.2 - Material Compliance
9b36012d-0e96-59ca-8614-b7667836ea95 | note | H
859f6bb6-37d9-5393-9039-bd046d8bff1e | note | Detail - 50mm thick compacted layer of AP20 aggregate placed underneath polyethene layer.
3e5cc72c-c8bc-5813-b018-4ac12a6ac325 | note | Frequency - Prior to pouring concrete
a140d6e4-47be-54c4-99dd-061e047963cb | note | Inspection / Test Method - Visual Inspection
86ba3ea2-97dc-571c-bb6e-1fd30946d9e9 | note | Conformance Criteria - CIV >15
a9861ba9-3647-597c-8615-c62cd6e02adb | note | Records - Delivery Dockets
7c7b2c50-6d9b-5048-89ea-126228178d56 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.3 - Material Compliance
fe834df4-f64e-5110-821f-693b3a474d82 | note | H
1f08c481-f55d-5a07-9ad8-c4880969af1d | note | Detail - Two layers of 663 mesh 50mm cover from top and bottom to be placed inside with 70mm plastic chairs seperating.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.4 - Material Compliance
31fba32f-57fa-5519-a099-1f56dbad659c | note | H
7caaee7d-4293-5728-a4e1-d3c1fd09b004 | note | Detail - All concrete delivered to site shall have 40MPa 28 day compressive strength with 4kg/m3 of Black Oxide Powder
7187f6a1-3645-5785-a762-6760f70f9fdb | note | Frequency - Prior to pouring concrete
0989eef4-8c56-53b8-9ff2-7ddf766f35ca | note | Inspection / Test Method - Concrete Delivery Dockets
ecfc66a6-aae0-5699-8a18-a22bb40074a9 | note | Conformance Criteria - Delivery Docket added to QA folder
05902d86-a74b-5207-aa15-4cde41bab402 | note | Records - Concrete Delivery Dockets
fd4db05c-2e39-50fa-b379-d7daaede18e0 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8 - Temporary Works (Formwork)
5f19daf8-8777-5755-a1ce-4eb1163efdfc | note | W
1aa6e783-5aa1-5e8b-944e-349c94dd2bca | note | Detail - Formwork to be set to correct line and level
2c3f7717-e470-595c-8002-b2df673f8b08 | note | Frequency - Prior to pouring concrete
abd5ad05-a806-5ba2-ad5b-6442a347f8dd | note | Inspection / Test Method - Visual inspection
1ca79612-1178-5de6-ab4d-c96e04bed3dc | note | Conformance Criteria - Concrete Inspection Record
62ce8cb4-6453-5513-a9ae-080ea4925ea8 | note | Records - Concrete Formwork Checklist
d43aa353-daff-5a62-bd28-f86cc906182a | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8.1 - Temporary Works (Formwork)
1d5c171b-55a6-50cd-b571-0bcda90b18bc | note | H
0474cfca-3c76-543e-acb7-7c80e85bc0fe | note | Detail - Raised table formwork to be 75mm above existing road level and be 300mm in depth and gradients respectively of entry (1:15) and exit ramps (1:40)
2973174c-4e31-5328-807b-58e23c75470b | note | Frequency - Prior to pouring concrete
c518bce8-6c27-5b4c-afef-483a74e32d14 | note | Inspection / Test Method - Measurement
89873118-2e8c-5eeb-a9cd-1fc115174e75 | note | Conformance Criteria - Designer to inspect formation level
c16c6ab1-b822-54a5-8372-2fa00d40c02d | note | Records - Site photos
80df969f-539e-5bca-ab9a-d503f9d36cd7 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8.2 - Temporary Works (Formwork)
3c616156-f5c2-5dc5-9027-9bea4f278238 | note | H
05e3c8b5-9348-5eb6-a836-dbf11bece5ac | note | Detail - Raised Table ramps to have 250mm depth at entry point and tie into 300mm depth to meet raised table
3dd4652d-a71c-58ce-8392-b70544c1366c | note | Frequency - Prior to pouring concrete
4f57c0c3-ff91-5adb-bd88-83ee3a0b1faf | note | Inspection / Test Method - Measurement
4fba598d-221b-5845-8fcb-66fb81a628c1 | note | Conformance Criteria - Designer to inspect formation level
3f21297c-61df-5647-894c-c165908a02d4 | note | Records - Site photos
1ef5536d-cd3a-513f-a1fc-212262e4e392 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8.3 - Temporary Works (Formwork)
2687741b-ea0b-501d-9432-ec273ead52c4 | note | H
887c0da3-3cba-5e0c-a755-f9d792ee45d2 | note | Detail - Raised Table ramps to be 1.125m across for entry and 3m for departure ramp.Toe to be 0.5 to 1m across for both entry and departure with 50mm asphaltic wearing course
6540c282-1cc3-568e-8819-f427ff76eb6a | note | Frequency - Prior to pouring concrete
bc1b276b-bfd1-58fb-bc31-965d0dbf55c6 | note | Inspection / Test Method - Measurement
117d5138-ee94-507c-b549-6cb0e551693d | note | Conformance Criteria - Designer to inspect formation level
3d2ada5c-70bd-5005-b3b2-9dd8181ffbd6 | note | Records - Site photos
5213b7a8-f356-5d0e-987a-9fefe61b30b6 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8.4 - Temporary Works (Formwork)
2f20462c-f27a-57a3-a85c-3aef3517a7e5 | note | H
17d64d8a-8c76-575e-8aba-f6dea60a1266 | note | Detail - Raised Table ramps to be 1:15 gradient for ramps at entry and exit ramps to be 1:40 relative to the road
6e2ea8ac-f689-58e6-8ad5-6da15b8f3cb9 | note | Frequency - Prior to pouring concrete
0ed8dbd7-50ee-5bc5-9d6f-5b0768738bf2 | note | Inspection / Test Method - Measurement
5dc30fd7-9f90-5b1e-b51e-361c83c8be9e | note | Conformance Criteria - Designer to inspect gradient level
93a51531-f904-5f78-9826-85159da09eb2 | note | Records - Site photos / Concrete Formwork Checklist
f43e9928-8ee0-569d-ae53-e172d836275b | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8.5 - Temporary Works (Formwork)
530f0b30-5a59-57e1-b5ee-018de1b7396c | note | H
8cd975b7-4799-5065-9c12-4316c8c645fc | note | Detail - The Site Engineer and MSQA Engineer must sign off the formwork prior to concrete being poured
0d8b83ec-302b-5987-bbb3-1b6151c01617 | note | Frequency - Prior to concrete pour
62b43909-3616-5a3b-85cc-0d18d8090bf7 | note | Inspection / Test Method - Visual inspection
0ba30b78-cd80-5a3c-a7a0-97e79270b562 | note | Conformance Criteria - Concrete Inspection Record
fb246751-aedd-51d4-9a09-965079bd337c | note | Records - Concrete Formwork Checklist
d23375a4-bb6a-5a3c-8c5a-6fa4caf30bb3 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Reinforcing
ecaacbc0-5602-52bb-984a-45d7509049d1 | note | H
563333f1-b114-5b26-a586-c2a5f66dfcc2 | note | Detail - All construction joints are to contain 2 rows of LESA dowels or similar approved dowels .Dowell system 50mm w/ Black 300*50*6mm plates @400 centres placed across the construction joint
e39b84c1-e5c7-593a-9e32-7df9022046a2 | note | Frequency - Prior to pouring concrete
e69e8f91-5ec5-56a9-b0d3-7b36af3f1308 | note | Inspection / Test Method - Measurement
18439974-c34a-58e9-be35-0021fac63b10 | note | Conformance Criteria - Concrete Inspection Record
88914a87-dab8-5241-9b4b-e6003e0843ec | note | Records - Site photos/Concrete Formwork Checklist
4753ab3b-b986-5534-93cf-ce0df4481400 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10 - Concreting
9eef57b5-fff9-52e1-bb74-004055b26a53 | note | H
c762f50d-12af-5868-bd76-ff633654371f | note | Detail - The MSQA Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required
bd093200-27a0-57dd-9fee-41a4cf031567 | note | Frequency - Prior to concrete pour
d4fcff40-1773-549b-9cc3-2d024a801ae8 | note | Inspection / Test Method - Visual inspection
9f2d581a-1b6a-5ffc-ae03-8aa8b7c45b7a | note | Conformance Criteria - Engineer will be notified via email/SMS at least 24 hours before required for inspection
6e94321b-2dd8-5a4f-8263-260442bd3110 | note | Records - Email / SMS
810f95a1-ee53-5a0a-bbf8-139399a46297 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10.1 - Concreting
3fe364f9-5404-5e29-9e83-6886ebe44305 | note | W
7ca04055-171d-54c1-92c0-7d2b5be121bf | note | Detail - Vibrator to be used throughout concrete pour
f1ac0871-d453-57d1-a363-558f031dc187 | note | Frequency - When pouring concrete
283e7d58-fa8a-553c-817f-37520e16f468 | note | Inspection / Test Method - Visual Inspection
13ea0ecd-bdf6-5ffd-9c3e-05e25d650f50 | note | Conformance Criteria - Concrete Inspection Record
d00e4c0e-363e-5d55-aaf1-96ea21d9b554 | note | Records - Concrete Formwork Checklist
dc10ba80-f474-5e6a-8e4c-77051c6bbf2d | note | FH Initials - Site Engineer
| checkpoint | 10.2 - Concreting
a5396a8c-d1ba-58b4-95ef-c49212e0e73e | note | H
dad2750f-757f-510a-a91b-8b8cc6c6fc09 | note | Detail - Concrete surfaces shall be U5 broomed finish for ramps, and exposed aggregate finish for table top.
26983dfe-e539-5f80-a0be-ba65b4c175de | note | Frequency - At completion of pour
a51d8be6-a4db-593d-b4bf-f39fc150d70e | note | Inspection / Test Method - Visual inspection
adb7c33e-693f-5d30-bb39-74bad1d1ab5d | note | Conformance Criteria - Concrete Inspection Record
a0abec19-a091-5c2e-b439-d3068d277114 | note | Records - Concrete Formwork Checklist
edaacbbb-8f48-5b50-93db-855c5f3e6cb8 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 11 - Curing
4c36ab38-6662-529a-bafc-4b502306704c | note | M
5121ebfd-26f1-597f-b5cd-0cc780f79b9d | note | Detail - Concrete will be left for 48 hours minimum to cure before traffic is allowed on it.
e4609059-c7a3-523d-8a32-ff7fcde70184 | note | Frequency - Post Pour
604a852d-2789-584a-9007-dce3ab40ded9 | note | Inspection / Test Method - Monitoring the time allowed for curing
da7007f0-3aac-5b36-9e72-a912cb8f14c0 | note | Conformance Criteria - 48 hours minimum have passed
8bfdef14-030c-55a5-be8d-106bf6048329 | note | Records - Concrete Formwork Checklist
25adbdbd-532e-5ad6-a1ad-ab1119824ea8 | note | FH Initials - Site Engineer
| checkpoint | 12 - Remove formwork
05ed22ab-b8d4-5d6e-a2ea-236c34ec588f | note | W
fb2f12d2-ed34-5016-8498-eda86805d1aa | note | Detail - Remove formwork after 48 hours
91f155b7-5eff-5be9-9255-0eb0ee81bcbb | note | Frequency - Post Curing
5c922b1d-7725-5fc5-989c-01a00fa1c3d7 | note | Inspection / Test Method - Visual inspection
ed1c3af7-43f9-5fff-b2f1-9a00331c8b3a | note | Conformance Criteria - Concrete Inspection Record
6d0eeb0c-4dfc-51fb-b474-af24a1e8a249 | note | Records - Concrete Formwork Checklist
5f17a232-e162-5069-a0f4-d764cae2f6df | note | FH Initials - Site Engineer
| checkpoint | 13 - Asphalt- Concrete extension slab/ Toe
c53b3f68-e3c6-5fdb-aa8c-7b5f61343c11 | note | H
ecaffd08-ccae-5304-8d75-ea85fd8b8f57 | note | Detail - Two rows of Lesa diamond placed mid depth @600 C/C along construction joint as per TDM TC003
e7d2268c-502f-5afc-8985-54efeef22e67 | note | Frequency - Prior to pouring concrete
cbba3cbb-c80f-510d-b82a-4c94eb28ecb0 | note | Inspection / Test Method - Measurement
a599a3f5-c94f-5689-b5ab-0321db5ac16e | note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
3efd0d4d-59d3-53d9-8570-619b6cb74066 | note | Records - Site photos,delivery dockets
57612fe4-c988-55eb-afc5-e6bf64410152 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 13.1 - Asphalt- Concrete extension slab/ Toe
fc1607e3-3568-5b6e-b0f1-1ab6ab0575b0 | note | H
8462da4b-af82-5f6d-bcc7-9f738333c861 | note | Detail - 200mm thick 50MPa Concrete with two layers of 663 mesh
99bd7d39-e354-5419-b341-8907444cca02 | note | Frequency - Prior to pouring concrete
44de4a56-5667-5620-9251-5b16e85c218f | note | Inspection / Test Method - Measurement
9dce2d72-5a9b-5a5e-ac14-2a7b2d825092 | note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
b7dee4a6-5d27-5662-8067-d756921de230 | note | Records - Site photos,delivery dockets
03184c93-b85e-56fd-b50f-410c358dc0a6 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 13.2 - Asphalt- Concrete extension slab/ Toe
8626adbc-7dfd-560d-b5cf-b98876c263f4 | note | W
38c64070-ee61-589a-95f6-8285e1f0a22a | note | Detail - Tack Coat between AC and Concrete slab
00b9535c-4b85-56ed-9728-6bbb661c98b3 | note | Frequency - Post Curing
562995c1-b33a-5081-8931-0c3dc0463141 | note | Inspection / Test Method - Visual inspection
bd61c180-060c-5bb1-b5ed-681c3c03dc28 | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
0af383f8-bcea-53c4-a461-6ac463eb7a29 | note | Records - Site photos
9f11b011-31a0-5e24-9df4-e3a042315ea0 | note | FH Initials - Site Engineer
| checkpoint | 13.3 - Asphalt- Concrete extension slab/ Toe
a598124e-78cc-53ba-87f8-8d36f4989952 | note | W
36047350-6030-5bd5-af15-0a65c957c255 | note | Detail - 50mm thick DG10 / Mix 7
0d532fc9-18f7-5936-b91f-03f242f923cb | note | Frequency - Post Curing
2400a4d2-aa0b-5f50-97d4-744956d818e3 | note | Inspection / Test Method - Measurement
3e1de7f2-b2cc-5a8a-b32c-0cbe218f67c0 | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
64355c9a-dda6-52ae-95d3-06a6f4c27ea5 | note | Records - Site photos,delivery dockets
6061f092-edc1-5f37-aef3-886716e6e92a | note | FH Initials - Site Engineer
| checkpoint | 14 - Lot Number QA File
71445b41-0ca2-5f5f-9594-69a5a139146d | note | W
f9e28319-3137-5808-940c-27eef065e5dd | note | Detail - Ensure all QA Records,site photos and incident cases (OFIs) are closed and included within QA file
d5e078a2-059e-5504-accd-f9a82be54c64 | note | Frequency - At completion of Lot
22a8247e-ba31-5128-acac-676287ca0fdb | note | Inspection / Test Method - Document Review
2d81317d-2599-5129-9e5c-6ff7db3673a0 | note | Conformance Criteria - All QA files compiled and sumbitted to client
37100ac3-58ff-560c-ac18-99abcf9b4e2d | note | Records - QA records
89427e26-f47b-5fcc-b2f4-6d5421ddf84f | note | FH Initials - Site Engineer
| checkpoint | 14.1 - Lot Number QA File
92bc1807-8247-5dd2-a771-59d5b2bfe82f | note | W
fd755b33-ecbc-56c7-922b-8b0d3dd294f1 | note | Detail - Delivery Dockets to be included in QA file
5f656f5d-feda-5cc8-9af7-bd7058b650a4 | note | Frequency - At completion of Lot
592020fd-feda-5285-8d1a-4182fa9c2087 | note | Inspection / Test Method - Document Review
05db922e-9f86-5e29-82be-524518c5c771 | note | Conformance Criteria - Delivery Dockets to be included in QA file
7d2de638-3e65-5245-bf6d-37c4863de1bc | note | Records - QA records
ba9b0dc2-42e7-5092-889e-d77f38f14932 | note | FH Initials - Site Engineer
| checkpoint | 15 - As-builts
f877b04c-05b6-58b7-beb2-042e920bc1ce | note | H
75fce9dd-efa9-581c-bb17-f087d5f42d59 | note | Detail - Red pen mark up drawings to be included in QA file
4fc7c330-0557-5c4f-b0ca-1721af0cfc4b | note | Frequency - At the completion of the Lot of work
5fcc970e-0623-50d5-9360-cefa1391583c | note | Inspection / Test Method - Drawings
5cdf80d8-e8b6-5391-a4d9-3e2fe11b48f0 | note | Records - Asbuilt Drawing
367e8532-69b5-5384-a190-e8ce0f21d499 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checklist | ITP - Mckenzie Road - Enabling Works | itp | ITP - Mckenzie Road - Enabling Works | c9f0fcf8-5059-4b99-b6b8-0836fc7fe957
| section | Site Set Out
| checkpoint | 1 - Site Set out
439422f2-2c65-58e4-82f9-d707ee6f717a | note | VERIFICATION ACTIVITY - Surveyor
74253c76-5cb4-59b3-aa0b-cda5769e4c35 | note | METHODS OR REFERENCE - Surveyor
7a39e8e9-2b14-5cc1-b42b-6dc106657636 | note | Frequency - Everysite
6833c819-3c7e-50a7-a315-2042a706ea86 | note | ACCEPTANCE CRITERIA - Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criterea is acceptable.
f0f0b2b3-da17-565e-9a14-68dcecfa3afa | note | Mandatory HOLD POINT -
83e04af4-81d1-50da-a302-beda8fcbd470 | note | Records - Onsite records/photos
b3233770-065e-5c02-bed3-f127b70ee55a | note | Onsite Responsibility - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| section | Materials
| checkpoint | 2 - Kerb & Channel
c5743425-7d8e-59ae-b212-ca2bf2e0c7ab | note | VERIFICATION ACTIVITY - QA FORM
a96d3300-262b-5c58-b24e-7403c24008e9 | note | METHODS OR REFERENCE - TDM Technical Standards - KC0001
6092a0c1-7c4b-5c3c-9371-391ab7a26a7c | note | Frequency - Everysite
8a8b924b-4f38-544f-b101-00392ed216f3 | note | ACCEPTANCE CRITERIA - Kerb & Channel to be laid using precast hand-laid. On compacted GAP40. Concrete 20MPa @28 Days on 100mm GAP40 with the subgrade CBR>5
e196b0b6-6bc7-527e-9f37-44b6cb660c14 | note | Inprocess Inspection
ff5619e0-83fc-5dfa-95f6-6cbe08703c97 | note | Records - FH concrete QA sheet, photos. Concrete Plant Docket
2f91bef5-b2ba-55db-84c0-af489b1dd3ab | note | Onsite Responsibility - Site Engineer
| checkpoint | 3 - Channel Level
09ab135e-af17-5501-b3b3-6c26b8445398 | note | VERIFICATION ACTIVITY - QA FORM
829cac3e-09af-567a-b1cf-fc1f3c28e4ed | note | METHODS OR REFERENCE - TDM Technical Standards - KC0001
c2ab4cae-ffd0-5d1e-ab6d-8c64bebadaf8 | note | Frequency - Everysite
75e97bf6-04f9-5865-8abd-3009d119b570 | note | ACCEPTANCE CRITERIA - Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
bda627e4-899d-5215-a8b6-619c2114fda8 | note | Inprocess Inspection
549d1dcb-eeca-5aa8-a3dc-a0ab226ba548 | note | Records - FH concrete QA sheet
df1bf82e-4d25-5fb9-94a5-a66bb448dc1e | note | Onsite Responsibility - Site Engineer
| section | CIVIL WORKS
| checkpoint | 4 - Concrete Footpaths
cfb4ccbd-254d-539f-aafd-7a745f405324 | note | VERIFICATION ACTIVITY - QA FORM
1654db99-b2a0-58f0-af3d-32e58b4b2862 | note | METHODS OR REFERENCE - TDM Technical Standards - FP0001
574d5174-04f6-582a-9c69-7a25801f615f | note | Frequency - 10m Intervals
b7754a23-9ba2-54bc-916b-de79c07221f1 | note | ACCEPTANCE CRITERIA - Subgrade -(CBR > 3) Basecourse - 100mm min. thickness GAP40 Clegg CIV > 12 Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish
6522b40f-d64b-59dd-941d-ec333f895f20 | note | Inprocess Inspection
474da51e-632c-5151-985a-a8ca5d4aa53b | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
714aed54-a5ac-54c7-9427-240ef32b4a6a | note | Onsite Responsibility - Site Engineer
| checkpoint | 5 - Concrete Footpaths
45800dca-e5fd-564c-ba68-e3867f609c88 | note | METHODS OR REFERENCE - TDM Technical Standards - FP0010
23ff0886-3367-5f3c-81d9-334b1e840b69 | note | Frequency - Each PX
1e4ea2da-a3c6-5001-b1dc-09e00df219e5 | note | ACCEPTANCE CRITERIA - Warning TGSI tiles should have 100mm concrete slab underneath
d8578279-7668-528e-bbb7-93fd00d24070 | note | Inprocess Inspection, Measurement
dc7ae81d-29ff-5c4b-a277-3f9bf2042ca7 | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
6ec6c717-c885-5929-9abc-484c033d4a0d | note | Onsite Responsibility - Site Engineer
| checkpoint | 6 - Tactiles
b41fcf97-3426-5beb-81c5-4f52f5588ef7 | note | VERIFICATION ACTIVITY - Visual
87efeafb-35ae-5633-816b-2c9f75ce2408 | note | METHODS OR REFERENCE - NZTA RTS Guidelines for facilities for blind and vision impared pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
701b4689-b6b9-5883-ac05-8f404bac611c | note | Frequency - Everysite
a9718bb5-35ec-5a01-99b9-d1fefeeaf218 | note | ACCEPTANCE CRITERIA - Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
09cb9a96-6b04-5402-94c1-3bdc3ac19489 | note | Inprocess Inspection
8c3b0e8e-7e6c-57ab-845f-32449b49f50a | note | Records - Photos
04789e70-9f7f-56e8-9965-d74b639cc3da | note | Onsite Responsibility - Site Engineer
| checkpoint | 6.1 - Tactiles
9b367b77-378b-57d4-be85-23222e30578d | note | METHODS OR REFERENCE - AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
38509ada-5593-52be-9c7d-30413cbc30b4 | note | Frequency - Everysite
afe9e313-2c71-5a9d-9f7d-dc1643d171d8 | note | ACCEPTANCE CRITERIA - Edge of warning indicators to set back 300mm from the face of the kerb or lane, extend the full width of ramp and be 600mm deep.
fbfcbe44-6ecc-5dd1-8d2b-d9166d3c379b | note | Inprocess Inspection
9f667a29-7e6e-514d-a258-42666b1dd89e | note | Records - Photos
4010b5ad-1fac-5a0d-8266-df92c96ea2dd | note | Onsite Responsibility - Site Engineer
| checkpoint | 6.2 - Tactiles
9c36eea6-6a47-58c8-8d52-267128a0bcfd | note | METHODS OR REFERENCE - AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
93f3b718-fda0-5281-8bf8-0992de6f56ce | note | Frequency - Everysite
ec3e83a0-0e0b-5a04-9baa-1f52eb166111 | note | ACCEPTANCE CRITERIA - TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
48139960-530b-5a53-a3f7-f0fde34ef3b0 | note | Inprocess Inspection
888b36f2-756c-5571-9a14-609b73280956 | note | Records - Photos
e8a96466-e202-5175-8fb6-9d9fb9c85988 | note | Onsite Responsibility - Site Engineer
| section | RAMM DATA
| checkpoint | 7 - As built information
8d793f95-8342-5e5d-9925-768d10f0579d | note | VERIFICATION ACTIVITY - RAMM DATA SHEET
f2c76af5-4137-598d-88de-4e058d945a74 | note | Frequency - Every Site
d0b881b1-54f2-5e77-98fe-90c424c920c1 | note | ACCEPTANCE CRITERIA - As built drawings and Ramm Sheets Completed
4b755307-fbc7-5cae-8680-e0028cdf13aa | note | In Process Inspection
a8953299-5066-503b-8cac-05c2a7dbeecb | note | Records - Asbuilt records
3f265431-cfad-5bf0-b22a-287068e9d41f | note | Onsite Responsibility - Supervisor and Engineer
| checklist | ITP - Mckenzie Road - Istands | itp | ITP - Mckenzie Road - Istands | c893bfa6-3050-4922-803b-1267c55783a3
| section | Materials
| checkpoint | 1 - Mountable Kerb
b5b29231-6dbd-5f2a-a6e8-362c7dc22159 | note | VERIFICATION ACTIVITY - QA FORM
ecbf6ae6-bd11-5b41-b94e-15c714787622 | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002
59545849-38c3-53d8-bf1a-1474cf6c1df9 | note | Frequency - Everysite
e3481414-55ed-590e-9f0d-59a841c72ffc | note | ACCEPTANCE CRITERIA - Mountable Kerb to be laid using precast hand-laid and painted with two coats of reflective paint
e99e213b-fa15-5e77-a9bb-e3d25e9def41 | note | Inprocess Inspection
19abb039-a9c8-5ca1-b05c-fa7cad8ef99e | note | Records - FH concrete QA sheet, photos.
5dd78786-4cb7-55b7-b004-7090d79aa702 | note | Onsite Responsibility - Site Engineer
| section | Construction
| checkpoint | 2 - Survey Setout
0a5c58e4-10be-52f3-9540-7af022a2cec3 | note | VERIFICATION ACTIVITY - Survey
cfce74f1-1328-55ef-9148-c3d5a7d6b836 | note | METHODS OR REFERENCE - Setout Kerb Alignment required to construct to design
239d0a59-52a1-560e-8de6-06cc70950f35 | note | Frequency - Prior to commencement.
b0fa0657-b135-50f6-8de7-3b6dc13c70d7 | note | ACCEPTANCE CRITERIA - Survey
4b50244a-88be-5498-8f5d-e8647c2e2b51 | note | As per Construction Drawings
7a841d36-a2ca-5348-8c72-e4b478af8f84 | note | Records - Survey Receipt.
86ccae4e-3657-5abb-b7a2-a1b93f6ca539 | note | Onsite Responsibility - Site Engineer
| checkpoint | 3 - Concrete Island
4a74169c-ebbb-52a0-8141-fc4fb3e79b64 | note | VERIFICATION ACTIVITY - QA FORM
fbb090f6-6ae3-52b1-adde-99ae865a9b70 | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002
315ea323-337d-51a5-8407-554c2a1d11d2 | note | Frequency - Each Site
d0320fa8-4620-561a-9f0c-a273ff63faad | note | ACCEPTANCE CRITERIA - Kerbs to be haunced with 20MPa Concrete
dcb15982-1e2f-5573-93c5-8261d48fe7b2 | note | Inprocess Inspection
4f4fea3b-7f83-5fa0-b2b8-1f13ce358722 | note | Records - Photos
298f4900-53f4-5223-b249-bfcfe6d1ace4 | note | Onsite Responsibility - Site Engineer
| checkpoint | 3.1 - Concrete Island
e0ae9b25-73fc-5b8d-918d-87cd670676eb | note | VERIFICATION ACTIVITY - QA FORM
28c83f0e-7165-58e8-9c90-55d4c8bc6df7 | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0003
eda69262-cd49-5d44-958e-df1bfd1d264f | note | Frequency - Each Site
c636587c-5b01-5a00-814e-0190b3454327 | note | ACCEPTANCE CRITERIA - Basecourse to be 150mm min thickness of GAP65
122a3ce4-60e7-564d-8e28-377d4e25e697 | note | Inprocess Inspection
79654a07-8837-5f0c-bad6-23170986e0b4 | note | Records - Photos
5352c20d-4a3e-5f8c-a3f6-212d55069d88 | note | Onsite Responsibility - Site Engineer
| checkpoint | 4 - Concrete Infil
3318be48-2ef8-5887-b6e0-00454711bc67 | note | VERIFICATION ACTIVITY - QA FORM
fb8b9f11-7cbc-50a3-bb8c-eb118d8ebb7d | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002
897736fd-2410-527f-80cc-de5da7d759a6 | note | Frequency - Each Site
ba8906fd-ff48-5543-bfc2-6d0cbf4fb1e1 | note | ACCEPTANCE CRITERIA - 180mm depth of 20MPa broom finish unreinforced Concrete with 4kg/m3 black oxide Cross Fall of 2% or max rise in centre of 180mm
a0803486-6431-52c3-a5ee-9aee9afca9c9 | note | Inprocess Inspection
126bb5c9-acaa-54fc-9618-99e8e201b529 | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
2f132c15-ea38-5f3e-bf74-cd4fde0e23ac | note | Onsite Responsibility - Site Engineer
| section | Asbuilts
| checkpoint | 5 - As built information
c8dd1ba8-975a-54cf-b1ed-a1c22ac7883d | note | VERIFICATION ACTIVITY - Drawings
9e4170b7-e428-5c6e-87c8-ea5713ba3f50 | note | Frequency - Every Site
d7b44af1-e174-50ff-ae43-9a45ef43c851 | note | ACCEPTANCE CRITERIA - As built drawings
7dd495bc-dc07-5baa-8039-1068addd84e7 | note | In Process Inspection
0ebbc3fb-fc32-5ca7-bba6-ca85bbe9f03f | note | Records - Asbuilt records
fc2239ab-ee3b-5f3e-b77d-4dd166958db0 | note | Onsite Responsibility - Supervisor and Engineer
| checkpoint | 6 - RAMM DATA
9cb46067-41b5-5f6d-ab4b-756bffb8374d | note | VERIFICATION ACTIVITY - RAMM DATA SHEET
c627eae4-3992-5601-b243-8fc6be1837b1 | note | Frequency - Every Site
5f7b3300-29e1-590c-a9cb-bfb565d6bb5b | note | ACCEPTANCE CRITERIA - RAMM SHEET
d0d4d1de-3c96-5463-8195-4eba3cfea856 | note | In Process Inspection
8e9b7c88-5631-580e-b278-18a8aef89ddd | note | Records - Asbuilt records
33e9f869-7c48-58da-a354-dda3a0c82384 | note | Onsite Responsibility - Supervisor and Engineer
| checklist | ITP - Mckenzie Road - Stormwater | itp | ITP - Mckenzie Road - Stormwater | 228a9126-e706-4432-b4f3-73509589e99a
| checkpoint | 1 - Permits & Services
b3c8c11d-0570-5b9a-837c-60829a365dc5 | note | H
db73867a-f690-5750-b776-c14f4305ca20 | note | Detail - Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
89c5c254-bf9a-53bb-a3e4-625c0b4175b4 | note | Frequency - Prior to any construction commencing
cfe8a350-2923-572e-bd99-28e6208aadb0 | note | Inspection / Test Method - Document Review
3e2612ea-2c8c-556e-822c-d6f9dcf646e8 | note | Conformance Criteria - Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority
2a17082b-df4d-5c88-8122-df1ebe8a4d5c | note | Records - Permit attached or permit number noted.
3c5f172b-bf02-586f-825b-5257cb7daadf | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.1 - Permits & Services
9b997897-d645-57b7-b383-776f1eb4e813 | note | H
60118bbc-2173-5a6a-a038-b487c3c77f0e | note | Detail - Locate and mark out all existing services
3ab37d60-93a5-5e5f-9305-b10ad3999254 | note | Frequency - Prior to any construction commencing
20d63fd2-7e3f-5322-9d77-29125d7f8b38 | note | Conformance Criteria - B4u dig procedure - follow utility protocols
18ec3010-c0e2-58e6-a287-b8929c909ddd | note | Records - B4u dig plans & GPR report attached
3286740d-a263-564c-b94f-c383e39dc97e | note | FH Initials - Site Engineer
| checkpoint | 2 - Pre-Construction Sign Offs
a1ef1c96-6ee8-5e80-b035-9c6d293dc228 | note | H
8a09eb05-7d57-5bab-afbd-44ecd6d987a4 | note | Detail - Sub-Contract and Supplier Agreements
9c2233dc-f874-52b6-935e-46cd35a1f81d | note | Frequency - Prior to commencement.
abed3b43-cef6-5055-bbb2-c8e74fd7cd76 | note | Inspection / Test Method - Document Review
7c94a290-8113-5232-8cb4-644bd2bd5afe | note | Conformance Criteria - Sub-Contract and Supplier Agreements to be agreed and signed
4b27aa68-b2c9-5421-9e54-a71684018048 | note | Records - Subcontract and Supplier Agreements
9930c7f1-67d9-5281-ba6c-bf7818318939 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Design
20eda8fa-b8e2-5e3d-a719-17130c053f00 | note | H
98224550-804d-5e4c-ab9b-e32262e7097a | note | Detail - Design is approved and Drawings are of the latest revision.
835b07c9-f854-59e7-a35e-ae41057ca6cb | note | Frequency - Prior to commencement.
963be0fc-9b1b-50b0-8a5c-ec9646ac8391 | note | Inspection / Test Method - Document Review
e2310d52-ec02-5570-9c3e-a22b2dd5a76b | note | Conformance Criteria - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
a6905315-b75d-5502-a8a6-ffa426610bb9 | note | Records - Drawing Register.
3529bd02-3244-559f-819c-dc1da2bf89fa | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Survey Setout
51e1e441-8166-5611-bc11-3c65ef834ef7 | note | H
2acda9b6-c6f8-5ab0-9fa3-9dc59d9ed38b | note | Detail - Setout Pipe Alignment and Service Locations with inlet & outlet points and inverts as required to construct to design
3a136266-6231-5f31-a40d-8642240340d5 | note | Frequency - Prior to commencement.
957b17c5-3498-5d7b-8983-f8253cc987c3 | note | Inspection / Test Method - Survey
b2309e1f-ca86-55ec-a022-1b06667e9a8b | note | Conformance Criteria - As per Blue Barn Consulting Engineering Drawings: 02188-T-400 & Setout files
3669fc66-099c-593c-8736-4bed6e1b871d | note | Records - Survey Receipt.
228a1ff9-9b00-5128-afc1-7682bb5d967f | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Pipe and Manhole Material Compliance
796e578e-eac9-5671-9f1b-de28f2ecc630 | note | H
6a27a81a-6f00-5e07-8871-f30c70186fae | note | Detail - Cesspit, Manhole and Pipe shall comply with relevant AT/TDM standards
75d6bee9-b1ba-57cd-8a26-81d69c9fb226 | note | Frequency - Prior to commencement.
b941233e-dc6e-508e-a534-b04527352e0d | note | Inspection / Test Method - Document Review, Visual Inspection
84508024-0b62-5970-bfde-0509fa68b040 | note | Conformance Criteria - Pipe shall be Check for freshyly formed pipes and return if required 1) DN225 Class 4 RCRRJ pipes AS/NZS 4058 2). All Concrete RCRRJ pipes to be fitted with Rubber rings 3). Pipes shall have product certification (ISO Type 5) to AS/NZS 4058 Prefabricated concrete Manhole shall be in accordance with TDM Standards & AC COP
ff1983f4-2ca6-5916-8f48-9431eaa22bfd | note | Records - Manufacturers Data Sheets, Delivery Dockets
a8fe8bff-3368-5179-b437-ed587662948c | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Locate Existing Services by Hand Digging / Hydro Vac
c94fd055-dfd0-5250-923f-72545f2e85c3 | note | H
b95faa82-b611-596f-92fe-c7c912669ee1 | note | Detail - Ensure all services conflicting with the line of trench have been exposed by hand digging.
59e7aa6c-1ca6-5e1b-a840-610807b21885 | note | Frequency - Prior to commencement.
1417e805-474f-5731-8bad-dd1362924173 | note | Inspection / Test Method - Potholing / Survey
4f504c55-31f7-5e66-8d6f-9baf25c53f02 | note | Conformance Criteria - All conflicts have been located. New services and / or conflicts to be advised to Project Manager.
a1e3640d-8f6d-54b0-9025-3cb05f48c0fd | note | Records - As-built Drawings. Doc. Review
38279db4-7839-5553-9aaf-4fd9d86a1cdd | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Trenching & Excavation
b6c51101-8136-5a8e-8735-611ea4a63988 | note | H
2ed85907-7923-5421-867d-350620c68275 | note | Detail - Excavation methodology
8879aa28-9d0b-534f-b628-466fa0da1c6b | note | Frequency - Daily
b6b2a99a-fe52-5fe4-8e52-2b4ba131ae14 | note | Inspection / Test Method - Prestart review
49d622ff-21e6-5b31-8c88-6e2a0abe5a0e | note | Conformance Criteria - The excavation, benching and shoring requirements shall be in accordance with Worksafe Excavation safety guidelines (2016)
5f66d6ca-a5bb-5a24-9b7b-7d4eb2771ea1 | note | Records - Prestart RCP
3dbaddf2-d6c7-53d7-92d6-5722723b511d | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.1 - Trenching & Excavation
d7d5b9be-c7cb-51d6-b906-f4c5f8840c88 | note | M
694cb0b1-ebd9-5947-82e9-fe4632479f17 | note | Detail - Trench Profile - Width
fe218245-d419-582c-a087-2fdc73745bec | note | Frequency - Daily / as trenching takes place. Different depth methodology
4d8bd7ac-a991-5378-a575-3e809af03fd3 | note | Inspection / Test Method - Visual Inspection, Excavation methdology
a473c00a-f888-5587-bd8b-cee7826fface | note | Conformance Criteria - Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing
e1d12c95-b206-5fb2-82ea-b29eb70389f0 | note | Records - Construction Photos
ea155010-b14e-5b88-b8b4-403de875e7b8 | note | FH Initials - Site Engineer
| checkpoint | 7.2 - Trenching & Excavation
4d06fddc-e0a2-5b29-97a3-1723b978088d | note | W
2f27b1e0-5c67-5b68-91b6-0d8a39fd6bf9 | note | Detail - Trench Profile - Depth
a632fa0b-0dc8-514a-ab2f-d1f460513c37 | note | Frequency - Daily / as trenching takes place.
f1cef5ce-dd12-534b-b3cc-cce489d3ee65 | note | Inspection / Test Method - Visual Inspection, Measurement
48c812b3-8043-519d-8df1-f8977e591406 | note | Conformance Criteria - Trench depth varies according to longsection and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings
fda3b1b8-fd14-573c-8d3f-9688ee8fd41e | note | Records - FH Drainage Line Record / Construction Photos
4c6d3097-136c-5736-9e5e-e27e39558b33 | note | FH Initials - Site Engineer
| checkpoint | 8 - Bedding for Concrete Pipe Laying & Manhole & Cesspit
2038fe24-220c-5810-a7b6-dc9328132959 | note | W
b915eb3c-ae78-56ba-b68e-e2aa56dd5f2a | note | Detail - Placing and compaction of Bedding Material.
140e0023-edef-5086-aba5-34b6cd91e23f | note | Frequency - Inspected continuously during placing and compaction of Bedding Material.
ebd78c54-9c28-573b-9257-beb4423204f0 | note | Inspection / Test Method - Visual Inspection
e09085f3-03a9-53bf-b1d5-ee3bd8136d71 | note | Conformance Criteria - Bedding & Pipe surround material to be GAP7 or GAP 20 (Stevenson Quarry) or alternate material that complies with AS/NZS 3725
cc02cdf2-c39b-5a37-99f8-3b8f00f24889 | note | Records - FH Drainage Line Record / Construction Photos
e5fa5ac4-57e9-58bd-822b-ed8206add4a2 | note | FH Initials - Site Engineer
| checkpoint | 9 - Pipe Position Tolerance
9b7c8ea9-6bf2-5987-8cb7-871f673fbb3d | note | M
432f1247-e98b-5f50-b7d1-a1502a72a068 | note | Frequency - At any point of pipe
d9f4b05f-c276-5d66-8772-6146bbd253f9 | note | Conformance Criteria - Position tolerance for pipe laying at any point along the length of the installation shall be within ±30 mm from the specified design.
01ee827f-9432-5514-9dac-40a0d77bfe2a | note | Records - FH Drainage Line Record, Survey Data.
b3663a9b-5fca-5b14-b11c-78ab514ac727 | note | FH Initials - Site Engineer
| checkpoint | 10 - Trench Backfill - Placing & Compacting
5b4cb190-0093-5f80-996d-3b5fa18f2195 | note | M
71acf6a2-eb7a-5cdc-8ed8-161f527f7ad6 | note | Detail - Placing and compacting of Trench Backfill Material
263c44f7-29d2-58bf-9ff7-4d8e5d90a22a | note | Frequency - Throughout Trench Backfilling operation.
982c6878-5648-5397-80b0-799763d70957 | note | Inspection / Test Method - Visual Inspection
9080e7de-b030-546f-9547-2b1b94f6cf7d | note | Conformance Criteria - Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm
c638b0b8-b610-530b-adcb-4d4406877470 | note | Records - Construction Photos
eb982cfb-8c16-5c35-932c-36c31471c5a7 | note | FH Initials - Site Engineer
| checkpoint | 11 - As-Built Drawings
71088f1a-0d93-5e59-926e-b28aac487268 | note | W
5fb34dcb-d753-5fca-a2fd-970a57cf45dd | note | Detail - Red pen marked-up As-Builts of every 'Issued for Construction' AT drawings
aa0638c4-cb64-5b0a-a16b-f16e10680d8a | note | Frequency - Final As-Built Drawings to be completed within three months of the construction completion of the asset or infrastructure.
d0873973-b02c-5d67-a93c-cb5cbcdc44e7 | note | Inspection / Test Method - Drawings / Visual Inspection
599bab6e-07ab-549d-ab6e-d030f6440106 | note | Conformance Criteria - As Built and GIS Data
b4d4f1a2-ab46-59f8-be2f-c9b8008113b8 | note | Records - Redline As-Built Drawings, scanned as .pdf files.
7a9cbf5d-f347-595b-b84c-e240e7dd24c2 | note | FH Initials - Site Engineer
| checkpoint | Final Inspection
89a4ac5e-ee22-5437-9900-d6f530cb656d | textbox | Comments:
12180c07-0d98-5697-853d-aaa77ea3c3cf | textbox | Position:
29ef09ff-bf6d-5fe5-bbec-88883e8dc29a | textbox | Print Name:
af5a2481-1af1-50d0-8e45-6ec1eede196f | textbox | Date Completed:
| signoff | Add Signature
| checkpoint | Final Inspection
ad71bb4b-76ce-5ac5-9926-848383051b5a | textbox | Comments:
89e79747-ba41-560a-99e3-03f13575c638 | textbox | Position:
c185dfa5-10c3-545b-8227-44e2ae39ece6 | textbox | Print Name:
b4dc7a17-8626-596a-8e23-25a43a0ef083 | textbox | Date Completed:
| signoff | Add Signature
| checklist | ITP - Motatau - Enabling Works - Footpath, Kerb and channel | itp | ITP - Motatau - Enabling Works - Footpath, Kerb and channel | 0b0ce88c-8bab-4293-adf8-2c22de0a6f78
| section | Site Set Out
| checkpoint | 1 - Site Set out
b377bbe4-1ee8-5eb6-ab3c-205dd0796142 | note | VERIFICATION ACTIVITY - Surveyor
308766d9-ca1c-5e7c-9816-f93d0afd4c1e | note | METHODS OR REFERENCE - Surveyor
bb7e148f-be2b-5479-b917-fd4bb50856ab | note | FREQUENCY - Everysite
fc7ecbb7-b9d0-5e64-a049-c1365b120a30 | note | ACCEPTANCE CRITERIA - Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
2383df50-53ba-5a50-953b-72cacea43cc9 | note | Mandatory HOLD POINT -
543d658e-5384-5c8f-9e02-0097b4cea8a2 | note | Records - Onsite records/photos
9aec90fd-c4fe-5af8-9ad1-c9098247dcee | note | Onsite Responsibility - Site Engineer
| signoff | HOLDPOINT
| section | Materials
| checkpoint | 2 - Kerb & Channel
d34ff5f9-e226-5051-b97c-9ba6c8479f11 | note | VERIFICATION ACTIVITY - QA FORM
8bb928a6-d5b3-5cd8-96ac-cab585777b30 | note | METHODS OR REFERENCE - TDM Technical Standards - KC0001
f752e9ae-58b4-5a46-b5af-b6020cce9228 | note | FREQUENCY - Everysite
20166a57-eb46-5064-bdc2-b4bedcf590ce | note | ACCEPTANCE CRITERIA - Kerb & Channel to be laid using precast hand-laid. On compacted GAP40. Concrete 20MPa @28 Days on 100mm GAP40 with the subgrade CBR>5
64f71289-335d-509e-8d97-b3a1cf7bfcc6 | note | In Process Inspection
f1c973f8-ba81-533b-864b-118f8fa8d6f0 | note | Records - FH concrete QA sheet, photos. Concrete Plant Docket
43fa1f31-be3c-5b02-818b-14e09869272a | note | Onsite Responsibility - Site Engineer
| checkpoint | 3 - Channel Level
754a1258-81ed-5cb8-a092-bffe15405670 | note | VERIFICATION ACTIVITY - QA FORM
7e4ef6e8-e31c-568b-8ba7-f21f3ea64339 | note | METHODS OR REFERENCE - TDM Technical Standards - KC0001
1d23ad8c-6458-53db-9ccd-28bb1d084c31 | note | FREQUENCY - Everysite
1566ff77-a5a5-56d7-8df8-002a4378bd33 | note | ACCEPTANCE CRITERIA - Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
1b3b6b2b-5d74-5b38-b957-07decf75ac5c | note | In Process Inspection
2e6294fe-523d-5b8c-a3b3-08214c098fd4 | note | Records - FH concrete QA sheet
9da16371-6826-52e5-9bc3-5751a3f7885a | note | Onsite Responsibility - Site Engineer
| section | CIVIL WORKS
| checkpoint | 4 - Concrete Footpaths
1fc25aef-45dd-5ab4-82f8-df31d09dc5d6 | note | VERIFICATION ACTIVITY - QA FORM
c34dbe4b-b211-5358-9f8e-5e380759664e | note | METHODS OR REFERENCE - TDM Technical Standards - FP0001
84965f98-e752-542a-ba5c-21d6e109e047 | note | FREQUENCY - 10m Intervals
2dc56669-6c77-54d0-864b-07a91e9b5ae9 | note | ACCEPTANCE CRITERIA - Subgrade -(CBR > 3) Basecourse - 100mm min. thickness GAP40 Clegg CIV > 15 Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish
92bed86c-4a2c-5e24-a8a8-d0299d74402a | note | In Process Inspection
dccb1358-e16c-5f18-83a9-027fc0adf27f | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
d8e35bdc-2d87-5c90-8b07-d33bb0ee4aea | note | Onsite Responsibility - Site Engineer
| checkpoint | 5 -
8da034d9-102c-5ce8-8493-873d5abc22e9 | note | VERIFICATION ACTIVITY -
f539d8f7-3f85-59bf-b84b-d1989fbbf679 | note | METHODS OR REFERENCE - TDM Technical Standards - FP0010
bf7eac0a-96f6-516f-8e32-ef682384ef7a | note | FREQUENCY - Each PX
4da1a97d-c24c-5d4e-b13d-aac396817f5f | note | ACCEPTANCE CRITERIA - Warning TGSI tiles should have 100mm concrete slab underneath
87b9d5dd-e4e3-597c-9f43-6e41dfc4cf90 | note | In Process Inspection, Measurement
b23bcc1f-4473-5bd1-a1af-9425dd2c7b42 | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
35399437-f256-59ef-a706-b99eef92430d | note | Onsite Responsibility - Site Engineer
| checkpoint | 6 - Tactiles
e9a3e3a9-84b3-50ed-9e58-17dfba5be1dd | note | VERIFICATION ACTIVITY - Visual
421276ff-4d6e-528d-b371-be5a73c38114 | note | METHODS OR REFERENCE - NZTA RTS Guidelines for facilities for blind and vision impaired pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
f8302dff-b509-54c8-94b6-6f3c59017f73 | note | FREQUENCY - Everysite
c35678ab-dfc0-5743-881e-54a63b81fb17 | note | ACCEPTANCE CRITERIA - Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
c23caff3-c4c0-5403-bcce-3390707d837f | note | In Process Inspection
93e7e4d5-8394-55f2-b88e-bb5969f31250 | note | Records - Photos
18fd543a-c4b0-5b90-92ee-e43139129ea6 | note | Onsite Responsibility - Site Engineer
| checkpoint | 6.1
75101633-9f5b-5f46-bda8-77ba0535712c | note | METHODS OR REFERENCE - AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
6875bdf5-12e1-5b80-909f-af78408d8748 | note | FREQUENCY - Everysite
e0d16ca4-aebe-5da8-b62e-59e0267d95c8 | note | ACCEPTANCE CRITERIA - Edge of warning indicators to set back 300mm from the face of the kerb or lane, extend the full width of ramp and be 600mm deep.
4d988dd7-5dca-587f-8d35-f6d81dd3330e | note | In Process Inspection
bcdaaf4a-5a6d-5e2e-bec6-25b66f08ef92 | note | Records - Photos
8284e885-e0fa-58bc-8424-3b7f1df5fb57 | note | Onsite Responsibility - Site Engineer
| checkpoint | 6.2 -
bf090a04-a7cb-5a69-a837-8b38c29bafda | note | METHODS OR REFERENCE - AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
fa56cfaa-9056-5a89-b921-a3c44bac908e | note | FREQUENCY - Everysite
dfc6f2f6-53c6-527d-b255-9d9224b4b9d0 | note | ACCEPTANCE CRITERIA - TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
785a813a-e0ce-5a25-a64f-26fb4e16d895 | note | In Process Inspection
77a6e76e-bdce-5c8c-8e08-78a626847f68 | note | Records - Photos
b9347766-9233-5b7c-8240-e61aa340c94e | note | Onsite Responsibility - Site Engineer
| section | RAMM DATA
| checkpoint | 7 - As built information
d3b20655-5388-5e4f-b885-6b11a4862ee4 | note | VERIFICATION ACTIVITY - RAMM DATA SHEET
11df1193-ef13-5d9e-b16d-39f78c05fc81 | note | FREQUENCY - Every Site
af13b132-00ae-5025-9ea5-0d948f70cc24 | note | ACCEPTANCE CRITERIA - As built drawings and Ramm Sheets Completed
b2f70539-e287-5e2d-a9bc-043d749a65cc | note | In Process Inspection
2926804d-9776-5509-a0bf-7bfc9cfcd008 | note | Records - Asbuilt records
5b68a23e-5e94-50d3-90a4-619860afe7b7 | note | Onsite Responsibility - Supervisor and Engineer
| signoff | HOLDPOINT
| checkpoint | Final Inspection
01553db6-4b5d-54aa-9914-30f60a4a7e59 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
7868b7ef-a43f-5546-b34a-0ebfbbf7c9d2 | textbox | Print Name:
5fc66f33-411c-5880-88c1-644ddf5fbeb9 | textbox | Position:
c97a6e8c-0ef0-51b6-ba7c-373105f6ea19 | textbox | Date:
| checklist | ITP - Motatau - Raised Pedestrian Crossing | itp | ITP - Motatau - Raised Pedestrian Crossing | 0f23c9f8-15f9-41a0-a1ab-04521a54f1cb
| checkpoint | 1 - Permits
7b0028f9-3e88-52c6-9ff7-07dacd0ea8fb | note | Inspection / Test Point - Permits
779a4841-5d06-5e1d-9ea4-5106b99b9bb4 | note | H
9d885ca0-05b4-5599-a7ee-75223754da6e | note | Detail - Obtain Permits
77a3a2fe-2aa3-511d-817d-46146158b4c0 | note | Frequency - As required
2be1df03-1595-5220-b9cc-572acb82996a | note | Inspection / Test Method - Document Review
f20958d8-8694-5dd5-8208-3232a807bc9d | note | Conformance Criteria - Control Checklist - Fall Prevention (if applicable). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
60ea0f57-c3da-5188-b6d5-b16a61ff918f | note | Records - Permit attached or permit number noted
1a851cae-1ffd-5335-b5ca-ce2308338083 | note | FH Initials - Site Engineer
c070139d-c94b-511f-86eb-d1c8e5c1288c | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
b1f0963e-7831-551d-8e1b-87f716c57c0a | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 2 - Pre-construction sign offs
407f2b83-f048-5b75-a8b8-94a1c04cf32e | note | Inspection / Test Point - Pre-construction sign offs
78642a49-91fe-5bd7-9186-b6bb97ac2501 | note | H
2a6c575e-52aa-54c0-967a-6cce503b887d | note | Detail - Ensure that Sub-Contract and Supplier Agreements are signed
a6baae4b-634c-5859-956f-335bdffba412 | note | Frequency - Prior to commencement
74cccef6-ab2c-546d-b5df-2252526fc879 | note | Inspection / Test Method - Document Review
70e2a45a-a7ce-5d22-b87b-edd22975ba61 | note | Conformance Criteria - Signed Subcontractor and Supplier Agreements
89db8905-a845-5d87-acfb-c4ecc48c0fc0 | note | Records - Subcontract and Supplier Agreements
42eac125-579e-5abd-83fa-dddb53217453 | note | FH Initials - Site Engineer
1e7fca19-8eb6-563d-ac70-8d2fa9343bdf | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
48a16b1c-86fe-5675-a950-882fa39242dd | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 2.1 -
65926df1-2c30-52ae-9438-f71c370176fc | note | H
325e1eea-32e3-5e5e-8e28-538fe80b815a | note | Detail - Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
60e1e170-7aea-59f4-b1d8-7d01c77a0b3f | note | Frequency - Prior to commencement
c58bc202-c3e1-5396-b91a-f1acf063e576 | note | Inspection / Test Method - Document Review
7a68444f-6530-5d55-b2c8-4f780f543af8 | note | Conformance Criteria - TMP is approved by CAR manager for each site and works are only completed within the approved dates..
75adb8ca-5d17-55e7-b240-aac2704b7dd8 | note | Records - TMP on MyWorksites/On Site
1c0b88b7-ee0c-51e0-95f9-020282f8a6a7 | note | FH Initials - Site Engineer
87fe1bf4-ebfb-55a9-851b-547aaa8e243a | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
f82b86ea-e9f7-57e9-af0c-c1505d07ad40 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 2.2 -
c37c1415-5a3f-59ed-ba80-5c081a611b02 | note | H
c604a69c-535a-56ef-a3d1-ba791a1462d4 | note | Detail - Ensure all Subcontractors and Suppliers go through FH induction
39339d7e-da93-55af-beef-cd799c1fa305 | note | Frequency - On site daily
e9bfcd73-7050-5276-b8f9-55a5b0ca8721 | note | Inspection / Test Method - Induction
72fe06a3-3a9e-53e3-ab2d-1e7f9672600a | note | Conformance Criteria - Supplier's and Subcontractor's signatures on hazard ID and pre-start documentation
047c3a2b-c311-5a3c-9209-7f64f935bebf | note | Records - Hazard ID and Pre-starts to safety team
ce3bf458-666b-5816-a131-3811d6019f19 | note | FH Initials - Site Engineer
1441fc49-b3d7-54ee-aca8-bfa9cf743de5 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
a492f091-740f-5dd1-a19d-f2b16cfd9fa0 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 3 - Design
528d4ea3-eb59-512c-b03a-c8b6ebf9ba02 | note | Inspection / Test Point - Design
f4df5bbd-8a43-5516-ac8d-d99c4ac17a7a | note | H
03732459-2203-54dc-8397-ba8ea8b3563c | note | Detail - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
b1a1f647-cf00-5f5c-9d7e-c274905b88a1 | note | Frequency - Prior to commencement
e3013bb4-f90e-532f-b80d-f5a64eff6793 | note | Inspection / Test Method - Document Review
f76f7085-9359-58d5-b788-742df513206d | note | Conformance Criteria - IFC drawings have been received by Contractor
61517d27-31d1-5779-b003-8fb2d780b834 | note | Records - Check Drawing Register
20d579b3-885a-5567-b1bf-b3ca7cb25d65 | note | FH Initials - Site Engineer
7134e44b-03bc-5cb3-801b-dc9ce6281888 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - Design Engineer
a170bb95-8e39-57ab-947c-e360512818e0 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 3 - Design
151cdd9b-b7dd-5940-ae23-e5098ae9e8e6 | note | Inspection / Test Point - Design
3560f4a6-df01-5b85-8e09-e86812155359 | note | H
bc757ac8-f99a-5d0f-880e-12625d015a33 | note | Detail - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
9b3bd54a-466a-5ba4-aaa6-7e7dd4961a0a | note | Frequency - Prior to commencement
01c0ba29-d17d-5731-81fb-57e4e75f1d2c | note | Inspection / Test Method - Document Review
e9d32c82-5ab8-5260-bf91-c68764b701f2 | note | Conformance Criteria - IFC drawings have been received by Contractor
24750298-2b49-503c-8ebe-2dabfaa5d0cb | note | Records - Check Drawing Register
c77c1ecb-23da-51a8-b0b7-594f0ae01be3 | note | FH Initials - Site Engineer
b3d73973-9558-59cf-86d3-f6171a7b1fde | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - Design Engineer
a652c732-db4e-5922-b8e9-e039820f0aa8 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 3.1 -
fe2adb42-95bd-5747-8de5-ffb76d32b270 | note | H
bd83926c-8bfb-58da-afc8-ba8edf4f0641 | note | Detail - Crossing to comply with AT TDM chapter Traffic Calming and TDM TC0003
86c14bde-f592-5cdc-81be-48924cbda74d | note | Frequency - Prior to commencement
b9ce5523-93d7-59f8-a30c-9c1060cf537e | note | Inspection / Test Method - Document Review
8ec78370-9d4f-5b9a-a9d4-9eae2c74dd66 | note | Conformance Criteria - IFC drawings have been received by Contractor
8a5be461-fd7c-5cdf-8ee4-6fd1dda3ee32 | note | Records - Check Drawing Register
ad92de46-38ac-5aeb-9ad8-afc4266c1263 | note | FH Initials - Site Engineer
f0044af3-5236-56af-b02b-8379c56ae6c5 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - Design Engineer
0008120a-a29b-5212-86ff-dd62f0f2ae85 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 4 - Installation of Erosion and Sediment Controls
b303f1f2-2998-5f22-ba19-16865a69032b | note | Inspection / Test Point - Installation of Erosion and Sediment Controls
cb9d9754-a963-560d-905e-1b3e93714df3 | note | H
c4bf12fa-254c-5aea-8bc8-008e32faa08e | note | Detail - Ensure that Erosion & Sediment Control in place
1946020f-222a-5ecf-a450-8b1242d16bc0 | note | Frequency - Prior to commencement
ba6d9079-6dac-533d-a267-a6f21d755da9 | note | Inspection / Test Method - Visual Inspection
d53a6fa5-1a3a-5735-8773-6d087854c1e7 | note | Conformance Criteria - Cesspit Covered
6db3cb39-4e63-5348-996f-a915442df182 | note | Records - Environmental Controls Audit
e27e41df-8892-56cb-8870-6a8aa66c54fc | note | FH Initials - Environmental Manager/Site Engineer
19241d3d-ab31-52d4-84e2-82f49b96d52a | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
8ea0bd11-27da-5bb4-b6d6-9b0a69e1f958 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 5 - Survey Setout
43df6592-f91a-58f1-82f6-13b9938c3897 | note | Inspection / Test Point - Survey Setout
0fb802f5-9614-5f04-be5f-0a10c0318bfd | note | H
28589810-13c3-5223-9650-2fd536cac406 | note | Detail - Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations)
4b96eeb5-aad0-5906-9b25-1c631192b28b | note | Frequency - Prior to commencement
81082cc0-b4ca-5a64-9d36-b97d15748a4c | note | Inspection / Test Method - Survey + Smart Level
5d050d99-999f-5373-9c9c-a3a87f93b408 | note | Conformance Criteria - Consistency with Construction Drawing
8edbc766-3f7e-5134-afbd-247a99fbe083 | note | Records - Site Photos post surveying
be594eeb-4b64-50d4-997c-a6e1ffb479c3 | note | FH Initials - Site Engineer
f990ca2e-821f-509e-91ce-2abf0da248cd | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
9afa59d2-7789-5378-ace7-1ec374f7f355 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 6 - Locate Existing Services by Hand Digging
3d4793b2-a88d-5af6-a77f-86ab740ecc39 | note | Inspection / Test Point - Locate Existing Services by Hand Digging
7d139feb-31db-58e7-87d2-756137b7e3ce | note | H
2ec100b2-4908-5bb8-b0aa-a057f8cc5460 | note | Detail - Ensure all services conflicting with the line of trench has been exposed by hand digging
ee6452f0-53e3-5dee-8dee-51fd15b37763 | note | Frequency - Prior to commencement
11598fe2-a8e5-5af0-9379-38928d55b681 | note | Inspection / Test Method - Potholing
1eb1e037-2f0b-50dd-be29-f8e5789c1101 | note | Conformance Criteria - All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. Asbuilt all services
5c1ee194-23b2-5af7-861a-7ed3d8d16c36 | note | Records - Digging and excavation checklist, service planes,As-Built Drawings Doc. Review
70ce3867-b603-57fc-9cf4-aed9adbb2576 | note | FH Initials - Site Engineer
161725cc-0b32-59db-a2a1-c45474a3ae00 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
2ac755d9-dc1a-5260-8f93-ddb3d8cc9a22 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 7 - Material Compliance
dcd177b2-9ff3-5163-bfa5-02a3c20e22c7 | note | Inspection / Test Point - Material Compliance
444e0ec8-cdae-5814-b8c7-3e4c7590f1ba | note | H
fabd4cbd-692a-5d02-b8be-7e08d2e21d81 | note | Detail - LESA dowels to be used at all construction joints
c997abe2-7eaf-5ef7-adc3-7c7f359a5427 | note | Frequency - Prior to pouring concrete
d7b3acb3-c44f-53da-a6c3-73b6556881ae | note | Inspection / Test Method - Document Review
41f76aef-2afb-570c-8309-2be405d733ce | note | Conformance Criteria - Photos + Delivery Docket added to QA folder , TDM Standards TC0003
531af653-a678-5539-9d65-af84169e7c69 | note | Records - Delivery Dockets / Photos
060677df-2fe0-5aec-880f-32f54c303597 | note | FH Initials - Site Engineer
5af1dc6c-9cb4-51d4-9c51-0064c240217c | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
c43388a3-f145-5433-96a1-76a9df411053 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 7.1 -
f56ecaee-bdfb-5841-ac25-e6eba30d4728 | note | Inspection / Test Point -
05d1f89f-5842-5ab0-9e2c-9cdd5f024f10 | note | H
0b9019c1-430d-547c-9d14-df63a5eb31bf | note | Detail - 0.25mm polythene layer placed across all surface area at bottom of raised table
6663da2c-ab9b-521b-bbd2-b53e64f58f89 | note | Frequency - Prior to pouring concrete
79d40f8a-9a9e-52ce-b4e7-e0555d7b338e | note | Inspection / Test Method - Visual Inspection, Document Review
80b2ede0-b184-5b9a-968c-2b0ada861c4e | note | Conformance Criteria - Photos + Delivery Docket added to QA folder , TDM Standards TC0003
42092201-7554-5030-8ac7-4ac959cfcab8 | note | Records - Delivery Dockets / Photos
83dd9617-0473-5da7-99eb-389d40a46a40 | note | FH Initials - Site Engineer
f4c52dce-b3e4-5372-8f80-bc92cf03dd68 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
ec7faec5-c724-5fe0-83d3-b7b9229483ce | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 7.2 -
0da137b9-4a1c-5871-8e22-f2604c21346f | note | H
ba8eb469-e30a-5f10-87f3-adf945541fb3 | note | Detail - 30mm thick compacted layer of AP20 aggregate placed underneath polyethene layer.
eb122a44-4749-59cc-970f-2a08dc524009 | note | Frequency - Prior to pouring concrete
09dd558d-919a-56db-ba6f-32beb36f2e00 | note | Inspection / Test Method - Visual Inspection
5030378a-df49-5005-b3df-58ac9f758ade | note | Conformance Criteria - CIV >15
91f3c11e-71de-5529-956c-d924c1cc9794 | note | Records - Delivery Dockets
5aac750a-9762-5405-8d52-252476fef465 | note | FH Initials - Site Engineer
f76b6896-aa3c-5d74-a43d-2633e64b4b2b | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
7918ca64-8a5f-509b-b3bb-4c2e19bf1850 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 7.3
1efb58e0-5803-594d-832f-fdffe4a7e22c | note | H
edd13270-f03c-5278-bd43-53c3fa8778c7 | note | Detail - Two layers of 663 mesh 50mm cover from top and bottom to be placed inside with 70mm plastic chairs separating.
3fa18440-a26a-59cd-a981-080a3a1a65ca | note | Frequency - Prior to pouring concrete
c992ac30-60f5-5bf1-8198-16cb3f502205 | note | Inspection / Test Method - Visual Inspection
87207011-f40e-5b1e-bcc7-d9509f1bfaf8 | note | Conformance Criteria - Photos + Delivery Docket added to QA folder , TDM Standards TC0003
25881189-1d7d-5d0f-9a3a-6c0a928cdf3b | note | Records - Delivery Dockets / Photos
2fbe5ae7-7721-5ad6-8037-a2857f554a21 | note | FH Initials -
4377d169-fd95-59b2-b607-da9455bdcd52 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
24b313b5-f3b8-5fcd-98c0-2e66ccc881cd | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 7.3
fef6426a-81de-5c35-9a74-a988cedb2910 | note | H
ca032549-e5a3-5a29-a74a-240a9a498cc7 | note | Detail - Two layers of 663 mesh 50mm cover from top and bottom to be placed inside with 70mm plastic chairs separating.
00a1b008-2393-565d-b421-d5d785ca342a | note | Frequency - Prior to pouring concrete
aa611a5a-2ce3-5dad-865b-c59d08f74080 | note | Inspection / Test Method - Visual Inspection
4c3d3890-c9a8-52b8-8272-c43803895aad | note | Conformance Criteria - Photos + Delivery Docket added to QA folder , TDM Standards TC0003
986f8ce9-591c-5835-999c-de47c3d62753 | note | Records - Delivery Dockets / Photos
60b5737d-ad90-5932-b4c0-c2a50fa35a1d | note | FH Initials -
da47d768-b521-51e5-9857-0359a5b68db8 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
3fcdc0d0-4b80-5f91-853d-a8e1fb83da42 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 8 - Temporary Works (Formwork)
60bd759a-3919-5b5f-9a4c-a4cbfd5494ec | note | Inspection / Test Point - Temporary Works (Formwork)
27d158e6-90dc-5bfe-ba97-84d05f0e4e91 | note | W
f1bdc64c-464d-5ded-a216-2feed55102a2 | note | Detail - Formwork to be set to correct line and level
ec5c1394-fac6-58a0-a8d4-bb06cb7e274b | note | Frequency - Prior to pouring concrete
95d85476-ec59-5abb-bcda-d9c826294a8f | note | Inspection / Test Method - Visual inspection
47dd4ee9-4c57-500c-9e7c-2357376de3c8 | note | Conformance Criteria - Concrete Inspection Record
1e135c76-9b0c-58cb-9ba9-a6457de710b9 | note | Records - Concrete Formwork Checklist
d3ce7315-bb95-5d79-a842-15e24c244fff | note | FH Initials - Site Engineer
f6893d46-ccac-52f4-98f4-5c983977392f | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
92775ebb-3437-52ce-9094-d279a35ea5a6 | textbox | Date Completed:
| checkpoint | 8.1
b9924f3d-68d1-5d06-bb7b-e0215f0ef3fd | note | Inspection / Test Point -
cf8066a6-1fc1-5c44-9ab7-aa700d373615 | note | H
921148c1-2bf2-5abd-8b7e-521eb10fdfa6 | note | Detail - Raised table formwork to be 100mm above existing road level and be 300mm in depth and gradients respectively of entry and exit ramps
fa8c73d5-956a-5571-8c2d-5157cac6e911 | note | Frequency - Prior to pouring concrete
33591ce6-f905-5de4-b73f-845623079b49 | note | Inspection / Test Method - Measurement
fa32654b-7f5c-5db6-a42c-2a94f9a50f9f | note | Conformance Criteria - Designer to inspect formation level
fc4dd88a-d3cd-561f-b6cd-33dbc2f58d8c | note | Records - Site photos
5f288949-8aef-541e-b11a-3aed608ed13e | note | FH Initials - Site Engineer
f190dacc-a35d-5d63-99f9-710c2651fae1 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
bf92e1c1-574a-51c6-8d1a-dc81de1921d3 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 8.2
74bde3db-773e-5bc8-b2f5-07061534a3d2 | note | H
8c4612ca-c6d5-50c7-946a-599befc41867 | note | Detail - Raised Table ramps to have 200mm depth at entry point and tie into 300mm depth to meet raised table
6af6babb-347e-5d6d-ad59-b4d4e4fca80b | note | Frequency - Prior to pouring concrete
df679403-31b4-5d18-b17f-0dbecca84281 | note | Inspection / Test Method - Measurement
dd09a0ef-717b-5f91-a45f-4a9ff36d03ba | note | Conformance Criteria - Designer to inspect formation level
b16a992b-12f9-50ac-be62-927eb9d1dfe5 | note | Records - Site photos
783f83a7-33dc-5d70-84fe-ba3172ed5961 | note | FH Initials - Site Engineer
2bbcef77-63a7-5b95-9071-81490d6f536e | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
afd9b504-3d15-5a01-818e-1df45e61f1a2 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 8.3
d056fc59-ca24-5bb6-b7fe-9f101a06df4d | note | H
9fabc04c-83c2-5a52-adaa-8249825d5556 | note | Detail - Raised Table ramps to be 1m across for entry and 1m for departure ramp.Toe to be 1m across for both entry and departure.
d8f55c6f-1246-5e69-ac26-d15540ca63a2 | note | Frequency - Prior to pouring concrete
de444bdb-168e-5a4b-90e9-559569e4af7e | note | Inspection / Test Method - Measurement
4394cace-1800-583d-bc40-6c978d7747e6 | note | Conformance Criteria - Designer to inspect formation level
affd67ba-9b3b-58b2-9ee8-29dd5855658e | note | Records - Site photos
26395ba4-8d3a-53e9-bcb0-c8afb8eb3abe | note | FH Initials - Site Engineer
66ee0879-ccdd-5870-806f-462fb412f7ad | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
8c093768-f372-5851-9ff8-5fc1f54c8c78 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 8.4
acf3b6a4-fd5c-55b6-87ce-cebd4eea3be8 | note | H
6a7355e5-2e85-5145-a047-a3becaf596d2 | note | Detail - Raised Table ramps to be 1:10 gradient for ramps - As per Relative gradients provided in Construction drawing 1-A8258.07
3d8fec77-6f40-564a-abc6-0bc3938eda67 | note | Frequency - Prior to pouring concrete
eade9d80-04f6-57af-8a54-3beaf0780080 | note | Inspection / Test Method - Measurement
57b157d0-8714-55d9-bd26-75e33edaa2ff | note | Conformance Criteria - Designer to inspect gradient level
16fe0f58-96ea-5ee8-bf7f-7201bbda62d0 | note | Records - Site photos / Concrete Formwork Checklist
b3ed132d-76b9-5306-b4d0-bf3443103152 | note | FH Initials - Site Engineer
2ba40501-4ddb-581c-8991-b9b92ed0a514 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
62409ff1-d603-5a7a-af34-3864f0fbe0ce | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 8.5
f333a730-7a16-5767-8360-ccc162419485 | note | H
c504bf49-ba65-58bf-adb9-a64f800326cb | note | Detail - The Site Engineer and MSQA Engineer must sign off the formwork prior to concrete being poured
e137b390-2cd0-573a-bcec-bb030e53a6dd | note | Frequency - Prior to concrete pour
05cf89cd-9bce-5275-9fe4-50f86973e6f1 | note | Inspection / Test Method - Visual inspection
f3813cb0-ecc5-54bf-9416-a895a35bf5e0 | note | Conformance Criteria - Concrete Inspection Record
d82a54fa-ed19-5cc0-9b0a-b1ed8ba1298f | note | Records - Concrete Formwork Checklist
6f97ac8a-ee16-59e3-87b8-f27b56286dd2 | note | FH Initials - Site Engineer
03c6a2eb-e6c8-5b06-b7e3-7d67daff3de2 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
b885a951-ae80-507d-95d8-f10813999598 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 9 - Reinforcing
0dc0edad-7621-55b0-aac8-b4c11700d09f | note | Inspection / Test Point - Reinforcing
ad81cc7c-fa30-5cf7-bfa2-bf3e14bd423f | note | H
6d5aebd3-79bc-5d95-97aa-9c4f04987227 | note | Detail - Construction joints on speed table to ramps are to contain 2 rows of LESA dowels or similar approved dowels . Dominator dowell system 50mm w/ Black 300*50*6mm plates @600 centres placed across the construction joint and for joints from ramps to toe slab @400mm centers
20d845d3-2145-5ad7-82af-e5f3b0ad1a97 | note | Frequency - Prior to pouring concrete
3d40cb4e-d15a-58b8-b1fd-81c9cca0e1b2 | note | Inspection / Test Method - Measurement
6d10c05f-f6e4-5c65-b897-3b447213e04d | note | Conformance Criteria - Concrete Inspection Record
0983b670-5972-5fb0-88cb-cf1082e0f5f6 | note | Records - Site photos/Concrete Formwork Checklist
e06c5097-9c85-5a9e-88f9-f0ebfb6f0282 | note | FH Initials - Site Engineer
7a77ca76-b03b-577a-9735-97a3b0975e68 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
863fb193-3818-534f-b62f-cca1b3b2840c | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 10 - Concreting
412c4ca3-591b-516c-aef2-d14a5051d233 | note | Inspection / Test Point - Concreting
600cd65b-5875-5473-9a1d-399167244e02 | note | H
5884a2df-bb68-5c07-84cf-0e3e95782ad7 | note | Detail - The MSQA Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required
6d12c41c-ef8c-5564-b19e-ef92dd30f6c9 | note | Frequency - Prior to concrete pour
201679b4-ae96-5815-82ce-9a04e8afb7d0 | note | Inspection / Test Method - Visual inspection
3e9f2e75-627e-5384-9e85-9ae609902fd6 | note | Conformance Criteria - Engineer will be notified via email/SMS at least 24 hours before required for inspection
9e644737-b7c8-56f9-9c3b-aa0db27dfb21 | note | Records - Email / SMS
1d4218d3-96ea-578a-8823-985050e3cea3 | note | FH Initials - Site Engineer
882fc9a3-e619-5ac8-82ac-a3904d67634b | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
dca7f290-3232-59ad-b1e7-63c33505ac1d | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 10.1
9550175d-307f-5ee6-8902-f502cc72e3fe | note | Inspection / Test Point -
6b352042-c179-55c8-bb6f-41769a53acfa | note | W
1d6044b7-8439-5af1-9746-e77fc6911f48 | note | Detail - Vibrator to be used throughout concrete pour
bb4b9913-6606-5a69-8bd0-680430d2302c | note | Frequency - When pouring concrete
1a3d39d2-a0ca-5797-ad99-966ad5a49e01 | note | Inspection / Test Method - Visual Inspection
cc46ad92-fe6f-55b8-8a4c-43c4cefa8c17 | note | Conformance Criteria - Concrete Inspection Record
b331fb4b-4287-5fd1-9f72-c5c4e388264b | note | Records - Concrete Formwork Checklist
5a5d79d3-7d51-5485-b1c7-de934ef9094b | note | FH Initials - Site Engineer
40c39c98-f973-5aed-9847-96e7229285fc | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
1ff04f3b-c77c-5470-8cc8-7b35f75816e0 | textbox | Date Completed:
| checkpoint | 10.2 -
2cac6664-c634-5a44-ab5e-4fcaa8f123f9 | note | Inspection / Test Point -
d3242fe3-638b-5c5c-a1b8-968bfa1d9cc4 | note | H
323c7d64-4a9b-54d9-88a3-95b8daacc33d | note | Detail - Concrete ramps surfaces shall be U5 broomed finish and speed table top exposed finish
7ef7b2e9-35da-539d-8fed-1e4fd1f525df | note | Frequency - At completion of pour
4b74c89b-4e84-55ed-af68-613579a34ab7 | note | Inspection / Test Method - Visual inspection
6d731f1d-5571-5dd2-b89a-9cf193528ca5 | note | Conformance Criteria - Concrete Inspection Record
98b23739-5375-52d1-96d0-c406aaa3b3d3 | note | Records - Concrete Formwork Checklist
6e309454-545f-583c-8bd2-d3f4ae5674fe | note | FH Initials - Site Engineer
add512aa-3b7e-5744-9332-0fdbc3efa48a | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
db400842-8465-5d49-9b35-4eb884eab220 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 11 - Curing
35ca422c-e3ec-5418-9e4d-ec95fe0c7783 | note | Inspection / Test Point - Curing
f8522d1e-9451-556f-a8d3-d78680e90a51 | note | M
1bd7692b-9ea9-5d8e-8cd0-e743952bdba4 | note | Detail - Concrete will be left for 48 hours minimum to cure before traffic is allowed on it.
5196e70c-5421-56bd-945b-e0a4048ef8ee | note | Frequency - Post Pour
bc536d69-9a57-5ba5-bfa0-e253edc82859 | note | Inspection / Test Method - Monitoring the time allowed for curing
feb36d07-a3a6-55b0-bc1d-d8d0b2899c06 | note | Conformance Criteria - 48 hours minimum have passed
3835f72c-04d3-5498-898e-ac061ac5203a | note | Records - Concrete Formwork Checklist
0b4ef566-21ca-51dc-be0c-5f275458d466 | note | FH Initials - Site Engineer
f81834d6-ae7c-5ce2-a5cc-3d0e8fc835bb | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
ada61b36-7f6c-554f-b443-9730384d918a | textbox | Date Completed:
| checkpoint | 12 - Remove formwork
8aa4d09b-987b-5d6d-b848-73e8015edbf2 | note | Inspection / Test Point - Remove formwork
46397704-591c-5446-bfea-43d0972aa1ba | note | W
7d9e5ca1-17e4-5635-8cb6-ae7923bffe3a | note | Detail - Remove formwork after 48 hours
18127f48-dc3f-5edb-99b9-b2ecd6aa549b | note | Frequency - Post Curing
85de1519-2ea7-5079-aaa0-1d7170eab871 | note | Inspection / Test Method - Visual inspection
b3913e40-4c8e-59e9-99e4-8c1ad41f743e | note | Conformance Criteria - Concrete Inspection Record
b45544b5-1a8c-5506-9ffd-2813c11b6384 | note | Records - Concrete Formwork Checklist
aea86b7c-c9e0-557a-935a-4c2081bf5131 | note | FH Initials - Site Engineer
cf5867c6-0874-5f6e-975e-f47368e755b8 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
fa8163f4-8480-51d8-ac41-a43dfa00a711 | textbox | Date Completed:
| checkpoint | 13 - Asphalt- Concrete extension slab/ Toe
caeb0207-c280-5dfc-a568-a07a47889e24 | note | Inspection / Test Point - Asphalt- Concrete extension slab/ Toe
d90b40ba-4cf1-5d9e-97a5-5fdee49ecc3a | note | H
4cdfc0ff-67dc-5041-9b23-044e5b40b715 | note | Detail - One row of Lesa diamond placed mid depth @400 C/C along construction joint placed at 75mm as per TDM TC0010
3c02342a-7b8a-5307-89c7-6059162eb47c | note | Frequency - Prior to pouring concrete
e009f36e-a9dd-53c6-97c0-c916261791fb | note | Inspection / Test Method - Measurement
9d6528be-9920-5663-aed4-7d05e26860f6 | note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
a6a46e30-b715-5c6b-97db-c83c93e7f459 | note | Records - Site photos,delivery dockets
bcbe936b-9fb5-565c-aa9b-16b26eae5d08 | note | FH Initials - Site Engineer
55fb5ff3-52cd-50f6-b97d-7104134dd93b | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
3015ef1f-2fb5-5baa-b92e-016c01c428eb | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 13.1 -
920575b3-3f27-53d6-b0b2-d510a04aeb44 | note | H
c5b2e95f-dfd0-5159-978d-89dcdc1ac8ac | note | Detail - 250mm thick 40Mpa Concrete and 4kg/m3 Black Oxide with one layer of 663 mesh
d2d39d4f-7844-5ec3-95f9-05bf171196ee | note | Frequency - Prior to pouring concrete
058e3602-90ff-5947-9190-de24d1ed325f | note | Inspection / Test Method - Measurement
231d11c1-2358-5a31-8f92-ad11e8220a9b | note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
98f1c7d5-b006-564c-9d9f-54b09cb11396 | note | Records - Site photos,delivery dockets
8f1fb4f2-6913-55a8-9fe6-bf78b5f447d3 | note | FH Initials - Site Engineer
573f7281-8d47-572b-ba95-ac05967eeca2 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
0ee28acb-5fad-5e7b-8b72-a31627958c2e | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 13.1 -
261545a1-b6d0-5d1a-8073-054ecd0f74bb | note | W
1a780835-a7dd-59e1-a3bc-11441c4c2891 | note | Detail - Ramp to have relative gradients as per Construction Drawing 1-A8258.07
8370fa5a-a3ce-5e80-a371-7e7392439ff5 | note | Frequency - Post Curing
4b54a290-a0d9-5c5d-8f08-a309113d88cc | note | Inspection / Test Method - Visual inspection
4e9c4670-8296-50a4-86da-928d77534d42 | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
96756de8-88f4-575f-8a6c-2de5a3270d98 | note | Records - Site photos
a1e48776-d1f8-51b1-bc73-a707cf5b3b2b | note | FH Initials - Site Engineer
569aca92-803e-5ae8-9fe0-ccdd0dfb7d4e | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
5b76cacc-7c20-59ff-af3c-ed7e8d317aae | textbox | Date Completed:
| checkpoint | 13.1 -
7cf7c597-6e88-5da6-a214-e9093b93d50e | note | W
c98d5799-3994-5665-a5e9-8796605ef962 | note | Detail - 50mm thick AC14 and 4kg/m3 Black Oxide
c505d1f8-72c9-5dfe-a6cf-d1e59c95727a | note | Frequency - Post Curing
85a1042f-4d12-5d56-86fe-372896aab0d0 | note | Inspection / Test Method - Measurement
b1713d98-9966-5407-b4ab-ec7529b52ee1 | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
f1c7eea3-0580-572f-8315-8525416ba75d | note | Records - Site photos,delivery dockets
3bc5a1ff-4ffb-5eaf-8bba-5f2ffef21f59 | note | FH Initials - Site Engineer
1372c979-a5a4-5b67-8b9e-f8cfadb534d2 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
56ba6b02-deff-5db7-9993-b435090dd752 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 14 - Lot Number QA File
02610332-342c-5269-9e21-3c68062e589b | note | Inspection / Test Point - Lot Number QA File
cb19982c-9986-5cbb-9759-5f16dcadc0fa | note | W
798ec3d1-2cfa-548d-81c0-879f7e796db3 | note | Detail - Ensure all QA Records,site photos and incident cases (OFIs) are closed and included within QA file
5db34cc9-7570-5f0e-9f50-677ac471fede | note | Frequency - At completion of Lot
41bad3ad-a86c-584d-944e-38e5bb24286b | note | Inspection / Test Method - Document Review
a5daeec2-3afc-5e1f-9a0b-aa3540a13dcf | note | Conformance Criteria - All QA files compiled and submitted to client
ca1482e2-6bac-5735-b41f-01ccc7758d8c | note | Records - QA records
b4d7292a-2c21-580a-b7e7-73455b91a4d6 | note | FH Initials - Site Engineer
5875e69c-8cb5-5438-88e6-a6552bbe4b8d | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
7c9f2616-be92-5659-83ba-971d63cbdbfe | textbox | Date Completed:
| checkpoint | 14.1
f4dd43b7-0008-5e36-8b40-6efd8e2522b2 | note | W
c7d2bf03-37f5-545f-aaec-a8efeb7c4159 | note | Detail - Delivery Dockets to be included in QA file
3a98077e-6c7d-5f4c-b707-71546ac32aaa | note | Frequency - At completion of Lot
129671b7-e192-52d3-82d8-70d84f73f759 | note | Inspection / Test Method - Document Review
f333395e-d16f-515d-9e5f-7310df566b55 | note | Conformance Criteria - Delivery Dockets to be included in QA file
2717f42a-671e-56b2-8472-da0c97e822d8 | note | Records - QA records
a70eecd9-5ba6-5639-9130-93cbb12719e6 | note | FH Initials - Site Engineer
243c232c-48fb-57e3-b2ff-936e3f07f3fb | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
78fa3861-3d95-5165-beb7-648bf410407e | textbox | Date Completed:
| checkpoint | 15 - As-builts
e59f09c2-47e7-5f43-80f9-3e3ffe863452 | note | Inspection / Test Point - As-builts
faf778dd-f549-5cc2-af47-22c265cc7176 | note | H
def1beea-bbaa-5a9d-b98e-64b032483b39 | note | Detail - Red pen mark up drawings to be included in QA file
982a6d77-c086-57e1-859e-e608a1ae589b | note | Frequency - At the completion of the Lot of work
a75e807d-3c0a-560b-972f-94d9f2ae873e | note | Inspection / Test Method - Drawings
22cb79d3-24b8-5c9d-8825-ecff615eea90 | note | Conformance Criteria -
755eb350-f28e-5390-8272-51ac13674f6a | note | Records - Asbuilt Drawing
f79b3cd8-428b-5307-b9d9-ec841c99961b | note | FH Initials - Site Engineer
64e936ef-56f7-5926-9227-82affd77b4e5 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
a8ab0bcb-0632-53f8-9715-905f832d71c2 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | Final Inspection
148709b3-c6cf-5e80-affd-7d4867be5b8c | textbox | Comments:
adfed1dc-35c8-5de6-82a9-d8ead9ee78f2 | textbox | IFC Drawings used for Construction incl. Rev numbers:
4cc48a11-c97d-5566-80de-0519de6b334e | textbox | Reference Documentation (Notices/OFIs etc.):
7292e76d-58a4-57f5-aab8-7768f1cd74e5 | textbox | QA Compiled By :
6e0fad8e-3c78-5479-a6ec-bc803393f3fe | textbox | QA checked By Discipline Manager:
3b164237-452e-5f09-855f-f0a6f974a3c9 | textbox | QA checked By Quality Manager:
f2050995-ed85-588a-85c7-95d74c733f8a | textbox | Accepted By Design Engineer:
| checklist | ITP - Rockfield Road - Enabling Works - Footpath, Kerb and channel | itp | ITP - Rockfield Road - Enabling Works - Footpath, Kerb and channel | fb655810-416c-4e57-8417-79c43865c027
| section | Site Set Out
| checkpoint | 1 - Site Set out
07ecd051-4d0a-584b-a15e-609d51d224c2 | note | VERIFICATION ACTIVITY - Surveyor
fdf7d0d7-4a7b-53be-b546-4c396bee803a | note | METHODS OR REFERENCE - Surveyor
8e167f3e-f89d-5aab-8cc1-21c28ade0b30 | note | FREQUENCY - Every site
56d8a5a0-da62-536d-98ea-edb654e1135f | note | ACCEPTANCE CRITERIA - Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
0aa25e34-ef58-588e-a2cf-4072d1d7ab69 | note | Mandatory HOLD POINT -
10f67d2e-6381-556b-b23d-1f5fd6146282 | note | Records - Onsite records/photos
11ceba2f-ac5d-545c-92c0-7868a1d83b25 | note | Onsite Responsibility - Site Engineer
| signoff | HOLDPOINT
| section | Materials
| checkpoint | 2 - Kerb & Channel
ad13f4aa-4830-5cf3-ac4e-3d45a6be39ea | note | VERIFICATION ACTIVITY - QA FORM
12102165-c59c-57e2-9b58-8cfc3b833ae3 | note | METHODS OR REFERENCE - TDM Technical Standards - KC0001
d99599a6-b2f7-5e3c-a9e0-ffbf24dd0f27 | note | FREQUENCY - Every site
96d4a49b-bf7a-5360-ac4b-8c01be1cf8d1 | note | ACCEPTANCE CRITERIA - Kerb & Channel to be precast hand-laid. Kerbing laid on 300mm min GAP65 sub-base in roads and 100mm GAP40 in footpaths (CBR>5).Concrete 20MPa @28 Days
60430459-dbb8-5036-b3de-df9b9561f7f0 | note | In Process Inspection
212ffff4-7808-5102-9c89-ef6dc6d4b16a | note | Records - FH concrete QA sheet, photos. Concrete Plant Docket
c41e0cfe-c387-54ae-8933-b14c6184731c | note | Onsite Responsibility - Site Engineer
| checkpoint | 3 - Channel Level
1226f12b-0f68-57c1-921c-c603e64489e8 | note | VERIFICATION ACTIVITY - QA FORM
0d9f097e-449c-5d96-97ca-5e6590616687 | note | METHODS OR REFERENCE - TDM Technical Standards - KC0001
ad39818b-7bd0-5211-9337-0aa65113d288 | note | FREQUENCY - Every site
1e3c3bb4-7175-5f74-a44d-21e19a30d14a | note | ACCEPTANCE CRITERIA - Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
bec9ae8f-240c-5f63-8428-d57efdf9a3c1 | note | In Process Inspection
2f99a405-169a-5799-9ad9-1cbb7bfbb7a3 | note | Records - FH concrete QA sheet
549a3264-c9ef-5467-b36a-2e9a8aac5ded | note | Onsite Responsibility - Site Engineer
| checkpoint | 4 - Concrete Footpaths
1c1977e7-e4fd-586c-950b-f86502d81ac9 | note | VERIFICATION ACTIVITY - QA FORM
d2063b68-6577-5cee-9393-a47e96fb9b26 | note | METHODS OR REFERENCE - TDM Technical Standards - FP0001
8f49be11-cc9c-53e0-a4b0-1fb604935020 | note | FREQUENCY - 10m Intervals
c8d02b63-fbfd-5111-830c-3b7b6ac76467 | note | ACCEPTANCE CRITERIA - Subgrade - (CBR > 3) Basecourse - 100mm min. GAP40 thickness Clegg CIV > 15 Surfacing - Concrete 150mm and 20 Map @ 28 days. 4kg/m3 black oxide with broom finish Concrete surface finish must comply with 3114 and S/NZ 4663 Slip resistance of pedestrian surface
2fadb520-3e96-5a4e-a94f-fb380275f28a | note | In Process Inspection
2f7a0af6-d5d8-53ef-8bd4-a02a8bcec8f3 | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
fd633a63-c488-5d43-92fb-32df404746b7 | note | Onsite Responsibility - Site Engineer
| checkpoint | 4 - Concrete Footpaths
76d320f0-62f5-5928-a05a-b4eff835176a | note | VERIFICATION ACTIVITY - QA FORM
496b584a-8761-51ab-ad18-bb9997768e54 | note | METHODS OR REFERENCE - TDM Technical Standards - FP0006
55dff54e-da03-5d61-ae2c-56c275c3233c | note | FREQUENCY - Each PX
2646c073-04d9-5d73-95f8-7fd5f2e18110 | note | ACCEPTANCE CRITERIA - Warning TGSI tiles should have 100mm concrete slab underneath
18383a18-d505-5024-af67-19ea89f7fcbd | note | In Process Inspection
462016da-a4f5-57fc-b34b-a3a4a485e7ea | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
7142c647-e078-5ec5-b481-2c1ac4fec461 | note | Onsite Responsibility - Site Engineer
| checkpoint | 5 - Side Islands
3561c5a2-2988-5dea-810d-21c5676b7c6c | note | VERIFICATION ACTIVITY - QA FORM
347a9a84-5c6d-5618-adef-d112c5c74f67 | note | METHODS OR REFERENCE - TDM Technical Standards - IS0003 A
5de4643c-aeaf-5d9c-afb4-72d18acdf2ee | note | FREQUENCY - Each site
94973d1d-8d8f-51e4-8a6e-667f87d80838 | note | ACCEPTANCE CRITERIA - Tapered Edge line with 1:10, 180mm thick 20 MPa Unreinforced Re-chip and -YUK concrete with 4kg/m3 Black Oxide and Exposed aggregate finish , base course to be 150mm min GAP65
4ae4b976-9e48-544a-849f-f4636e52f706 | note | In Process Inspection
2f901828-7b58-5c40-a7ac-3b212b779202 | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
b049a821-0983-5d0c-99b4-fade2e8ad81b | note | Onsite Responsibility - Site Engineer
| checkpoint | 6 - Tactiles
00477da1-6e1a-5d7f-b5f8-8f2db720b88d | note | VERIFICATION ACTIVITY - Visual
a2e1afa5-e3a4-54f0-ab77-85f0f269aa74 | note | METHODS OR REFERENCE - NZTA RTS Guidelines for facilities for blind and vision impaired pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
ed064f6b-fe74-52a4-b9fc-53887c99505d | note | FREQUENCY - Every site
87eefd18-a4bb-551e-9d35-807275f1a0d5 | note | ACCEPTANCE CRITERIA - Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
223631f6-9eeb-5fe3-b0f3-ba1670729357 | note | In Process Inspection
66569026-79da-5e80-9d27-c9a2c5eb636c | note | Records - Photos
4ba15f9b-53d1-59b4-982e-d700de38b22a | note | Onsite Responsibility - Site Engineer
| checkpoint | 6.1
b5f44351-08a9-5399-b2bf-256bac251439 | note | VERIFICATION ACTIVITY - Visual
bc4c8807-ae7e-526a-8e51-e9eb51807cc5 | note | METHODS OR REFERENCE - AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
437cb9cc-fd13-5da2-8de7-715303ae6f03 | note | FREQUENCY - Every site
7cc92249-babc-55a4-bee1-c9573a2e1717 | note | ACCEPTANCE CRITERIA - Edge of warning indicators to set back 300mm from the face of the kerb or lane, extend the full width of ramp and be 600mm deep.
3f0a6a92-c36b-57b1-a9b9-262e0afbaec0 | note | In Process Inspection
c8b076e9-77c4-5275-afb3-81141028d26f | note | Records - Photos
47d56cef-d94d-5c8d-ae30-dacaea5df74c | note | Onsite Responsibility - Site Engineer
| checkpoint | 6.2
2b3dc35d-d3a8-5db8-a747-703e64ae4c8a | note | VERIFICATION ACTIVITY - Visual
aab0bed5-a300-5f0d-a713-31ade6878e7d | note | METHODS OR REFERENCE - AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
9195fa0d-db1e-580f-be0e-51e25421aec4 | note | FREQUENCY - Everysite
9764f275-9f2a-57c6-9fdf-8f8debf6c1a0 | note | ACCEPTANCE CRITERIA - TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
2ba7e5d2-ecb0-5f8f-acda-564ebd53c771 | note | In Process Inspection
3b5c0f90-7894-58e6-b2dd-74ed9f1f25b6 | note | Records - Photos
f5ff9c58-8d1d-505f-a899-4f9f1a33f9ec | note | Onsite Responsibility - Site Engineer
| checkpoint | 7 - As built information
a137bde0-3ccd-5003-8d14-7c8655203034 | note | VERIFICATION ACTIVITY - RAMM DATA SHEET
ee7d6b39-0f92-56a9-9322-0f5d33fd1280 | note | METHODS OR REFERENCE -
4c00058f-21ce-52ca-8e1e-708cc24a452d | note | FREQUENCY - Every Site
0543586b-39a4-5c1f-b3bc-c8d5812eae7c | note | ACCEPTANCE CRITERIA - As built drawings and Ramm Sheets Completed
e2a378a1-5510-5da1-8c06-61f088ccb9f4 | note | In Process Inspection
168ac0cd-0bf9-5a47-9754-85413dae4d25 | note | Records - Asbuilt records
86fd4aa3-205c-5e0f-be54-d2879cb6de42 | note | Onsite Responsibility - Supervisor and Engineer
| checkpoint | Final Inspection
d6d39d37-a63d-54b1-924b-fe7cff086935 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
0c029be1-5391-5d0b-8e3d-90c3fa0ec8b8 | textbox | Print Name:
73f4fac0-218a-509b-b1b2-3e91bdb9da1a | textbox | Position:
49d0c257-5eeb-5a68-bb2a-155e78ad798a | textbox | Date:
| checklist | ITP - Rockfield Road - Enabling Works - Stormwater Drainage | itp | ITP - Rockfield Road - Enabling Works - Stormwater Drainage | eb4aed92-0783-4eaa-bafd-282432715c0f
| checkpoint | 1 - Permits
00ab1127-64db-53f1-b06a-8386d2091f76 | note | Inspection / Test Point - Permits
183207a2-c4a2-5b25-ba31-e077240507ae | note | H
45d42828-a59e-56c4-bd1c-6039f7ab7f84 | note | Detail - Obtain Permits
4d0e3c67-a4b5-5bab-97c0-4e51d121709d | note | Frequency - As required
4f8dd11f-9a7e-51d7-bf8e-7f9183854783 | note | Inspection / Test Method - Document Review
e54ae6b7-2ad4-5420-81e2-abd82bf75d53 | note | Conformance Criteria - Control Checklist - Fall Prevention (if applicable). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
6f5c365c-704b-59b8-b5ce-c8d5a774a56b | note | Records - Permit attached or permit number noted
90fff355-5441-5cb6-be89-b25c2ea169e8 | note | FH Initials - Site Engineer
3b4af23a-f2db-537c-baea-dfe6f79e478f | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
e2917f26-2837-53a7-8c00-622204662221 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 1 - Permits
d9eff987-140c-5f9b-ab2a-fb5a4af01f92 | note | Inspection / Test Point - H
a7182667-5948-5d12-9dfb-e14f8c826df3 | note | Locate and mark out all existing services
cd6c20fb-1d52-51c1-85ed-49bd21cbeaf0 | note | Detail - Prior to any construction commencing
2e50eda7-7f52-5979-9bb7-b3146ba52154 | note | Frequency -
a3976806-c072-5351-849c-34a05c140275 | note | Inspection / Test Method - B4u dig procedure - follow utility protocols
c358754a-530b-582f-80d0-aadb18266120 | note | Conformance Criteria - B4u dig plans & GPR report attached
ac5871c8-41fd-5217-88dc-615ea0d46952 | note | Records - Site Engineer
10306186-907b-576c-9cda-6c516b2e4d99 | note | FH Initials -
1f796ce9-2d26-58da-a964-fe082d2e19ae | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
60c55d7f-956c-5047-a0a7-610bc8b35c77 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 2 - Pre-Construction Sign Offs
2cfd2342-9352-5445-93d6-63b02827b67a | note | Inspection / Test Point - Pre-Construction Sign Offs
f45c78b1-8457-5854-b2c4-bfda7bea61e5 | note | H
f590fd14-26b6-593a-acf9-6ef0906dfac0 | note | Detail - Sub-Contract and Supplier Agreements
380f2010-6243-5f3a-b712-8c4e2a7af689 | note | Frequency - Prior to commencement.
4da38d81-c6a9-5d39-9843-44db4841bef8 | note | Inspection / Test Method - Document Review
5a720d2a-4756-5f28-aebe-cd3e07830813 | note | Conformance Criteria - Sub-Contract and Supplier Agreements to be agreed and signed
4dcbfc85-d9ff-5cab-83ab-5ba7c252debe | note | Records - Subcontract and Supplier Agreements
79b8a1c4-812f-5475-a39f-397bf841747d | note | FH Initials - Site Engineer
6a312967-7841-584e-89a6-f21deafd659e | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
096219ae-df0b-5948-a7a7-dfbdb717eb97 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 3 - Design
ef055e25-107f-5eb7-9df9-520d29fa57b1 | note | Inspection / Test Point - Design
776d2937-a836-5bd2-89b1-f525d3dc55f4 | note | H
b22adb27-a549-5052-bb15-045c00f26f40 | note | Detail - Design is approved and Drawings are of the latest revision.
54d7e38e-d7da-5207-8431-94b6138f2e16 | note | Frequency - Prior to commencement.
bc54c608-5e06-5b31-adfb-67bc7ca89b0b | note | Inspection / Test Method - Document Review
16a785b5-e32f-59ca-9c59-d517297b0c6d | note | Conformance Criteria - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
a08330fb-d43a-5547-97b8-04132170623b | note | Records - Drawing Register.
22641290-3009-568d-9baa-ecd45ae7f3ff | note | FH Initials - Site Engineer
dbe137ca-027c-5f3c-bf1e-a60babd58240 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - Engineers Rep.
705ec862-c821-5f74-a539-7a1dcf79f1dc | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 4 - Survey Setout
5a77ffe0-31e1-579a-9094-fb239edda13b | note | Inspection / Test Point - Survey Setout
20992feb-ed35-5d55-8c59-f42ccaede359 | note | H
eb7333cf-5809-594a-a8cd-ce568131b5da | note | Detail - Setout Pipe Alignment and Service Locations with inlet & outlet points and inverts as required to construct to design
7cbd2ce0-662e-5cee-bfac-f5d95b743ace | note | Frequency - Prior to commencement.
515fb95d-a31c-545e-b9de-5208dce65968 | note | Inspection / Test Method - Survey
9a478b80-4991-5749-9957-42e1d92f1d05 | note | Conformance Criteria - As per Stellar Consulting Engineering Drawings: 2789-C6060 & Setout files
325c93a9-fd23-529f-a469-3b691a11cb67 | note | Records - Survey Receipt.
8b3c9c1b-c16c-5877-ab0e-bbb1aa543a69 | note | FH Initials - Site Engineer
a9954120-aad9-5ab9-8dd8-37f1b94d5290 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
b6e5c9da-6954-58d4-92db-314f997bb3a2 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 5 - Pipe and Manhole Material Compliance
bbc362a8-d0b6-5304-aac6-cdf923dd22fc | note | Inspection / Test Point - Pipe and Manhole Material Compliance
ba2244a6-f42b-5aa4-a9d1-121913f91d64 | note | H
6aa1c130-a0dd-5879-9f17-cc880669f8d5 | note | Detail - Cesspit, Manhole and Pipe shall comply with relevant AT/TDM standards
9b793455-7ff3-5cc8-9725-fe042711f90c | note | Frequency - Prior to commencement.
24570b8d-2a52-5d16-be39-57410f4ab3a7 | note | Inspection / Test Method - Document Review, Visual Inspection
fd759d90-01df-55fe-bb0d-de23852c700d | note | Conformance Criteria - Pipe shall be Check for freshly formed pipes and return if required 1) DN225 Class 4 RCRRJ pipes AS/NZS 4058 2). All Concrete RCRRJ pipes to be fitted with Rubber rings 3). Pipes shall have product certification (ISO Type 5) to AS/NZS 4058 Prefabricated concrete Manhole shall be in accordance with TDM Standards & AC COP
4ef40135-8168-55f1-a07f-e5cb78b85bd1 | note | Records - Manufacturers Data Sheets, Delivery Dockets
1e219da9-0e10-5352-88e9-06f4bf19afa4 | note | FH Initials - Site Engineer
b5087c28-09d4-58d4-b1b6-0514974e3f9f | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
b1bb2e5b-8c71-5cdf-bda2-3ea13f35fa95 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 6 - Locate Existing Services by Hand Digging / Hydro Vac
ea978183-d339-52bf-8c91-fb379112a06d | note | Inspection / Test Point - Locate Existing Services by Hand Digging / Hydro Vac
ac0c34b9-d701-576a-9e05-c55743a8faec | note | H
e5dad906-e39f-5eb7-ac56-66d4e27f2b7c | note | Detail - Ensure all services conflicting with the line of trench have been exposed by hand digging.
1d711993-f8cf-5bff-8009-e10b7059bdae | note | Frequency - Prior to commencement.
b3e6e46a-5d8c-5d26-964d-136bd6369b71 | note | Inspection / Test Method - Potholing / Survey
02951b00-10a9-5ed6-9cf4-3dfa9b00127e | note | Conformance Criteria - All conflicts have been located. New services and / or conflicts to be advised to Project Manager.
12c2eed7-7b76-529a-a1eb-cd409f65eaff | note | Records - As-built Drawings. Doc. Review
16eec84f-4812-544f-b363-94d7c879d9c6 | note | FH Initials - Site Engineer
5f6bad4b-811e-5958-900e-6f64c4dd944e | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
45bea89f-ba16-5304-8af9-c722de8d3183 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 7 - Trenching & Excavation
d8dc85b3-3c74-57e9-ac3c-f9e77123dcce | note | Inspection / Test Point - Trenching & Excavation
3a88def5-a13a-5084-b783-4b30509e387f | note | H
fc1b353b-e1af-57b8-8a48-df842474dfee | note | Detail - Excavation methodology
b2cc4087-1c4e-5f39-bd59-438a1abb31d5 | note | Frequency - Daily
61eaecb0-6f8a-5cf3-8e7f-60b97dd5db51 | note | Inspection / Test Method - Prestart review
2374ff9e-74e0-55d0-9a00-e1998b65d1fd | note | Conformance Criteria - The excavation, benching and shoring requirements shall be in accordance with Worksafe Excavation safety guidelines (2016)
8f03f228-525b-5411-8f50-830570960dc7 | note | Records - Prestart RCP
1eb07f1e-0d25-5b1b-b0f5-e83d236b9af2 | note | FH Initials - Site Engineer
cf093af4-5d81-5f54-aa1b-0612d4216e97 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
036cd03e-91df-57b1-8143-dcfde3b77e19 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 7 - Trenching & Excavation
48a1871c-12cd-57a2-a279-f34b8f4c4d24 | note | Inspection / Test Point - Trenching & Excavation
7dd5df56-b64d-5291-9d82-1892a36f942a | note | M
eb95f2d7-eba3-5c05-8a66-2b9b2933ef36 | note | Detail - Trench Profile - Width
3f260c86-cf98-5186-9a75-e9a1fc213813 | note | Frequency - Daily / as trenching takes place. Different depth methodology
bcb4453d-d9e6-526c-9842-fd99bd178ff8 | note | Inspection / Test Method - Visual Inspection, Excavation methodology
8a380b5b-fa6d-507c-8895-70a8b2c58320 | note | Conformance Criteria - Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing
2918e044-6d34-552b-ab09-d087510c6280 | note | Records - Construction Photos
526fab03-d78c-59b9-9d90-de38465eca52 | note | FH Initials - Site Engineer
d6cc68e9-d625-5a48-9c10-018bf465e685 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
8bb14a8b-26c8-5d58-801d-afcbcc9691c8 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 7 - Trenching & Excavation
8c16cbc4-e2e1-5fae-b309-74d805cde984 | note | Inspection / Test Point - Trenching & Excavation
834531f7-9502-5099-b474-ec19c6085652 | note | W
f473227f-ce6a-5615-a6b5-10cbb75b9e4f | note | Detail - Trench Profile - Depth
5e5d12a0-da15-58b7-8a69-f6294ca43149 | note | Frequency - Daily / as trenching takes place.
b3405ea5-dd2b-556a-ae2b-d7e0941292ba | note | Inspection / Test Method - Visual Inspection, Measurement
b2a899f0-9d21-59f1-80a3-ba61bf3e2d14 | note | Conformance Criteria - Trench depth varies according to long section and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings
206eb8b0-21b5-527d-8fb5-15d0111a5a62 | note | Records - FH Drainage Line Record / Construction Photos
23355709-ead6-587d-b2ac-e311b9900da8 | note | FH Initials - Site Engineer
e0eb54b5-a2d6-54f9-ac28-22f3e6a3dccc | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
abeb11c7-aacf-5bf8-9d8a-e3dd0a9084dc | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 8 - Bedding for Concrete Pipe Laying & Manhole & Cesspit
ff7153c1-3698-5401-a4d6-a72e8ebaff59 | note | Inspection / Test Point - Bedding for Concrete Pipe Laying & Manhole & Cesspit
8ef0ca36-170f-500b-a1e8-4c00cc6dc213 | note | W
382b3550-f106-516a-8ac8-5c4245380483 | note | Detail - Placing and compaction of Bedding Material.
e2d1cb8a-eaff-5bc6-b738-0add764cfe5f | note | Frequency - Inspected continuously during placing and compaction of Bedding Material.
221d2a77-4e6d-53fa-8085-59affa61e555 | note | Inspection / Test Method - Visual Inspection
3a9b15ae-1bb7-52fd-af11-c6172d74078c | note | Conformance Criteria - Bedding & Pipe surround material to be GAP7 or GAP 20 (Stevenson Quarry) or alternate material that complies with AS/NZS 3725
f44c34df-0c47-53b2-92af-1c10db23ca06 | note | Records - FH Drainage Line Record / Construction Photos
0e76d346-3e71-5b61-93b6-15872693d91a | note | FH Initials - Site Engineer
0718b3e2-3ff8-5218-ade1-192cc4a97534 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
a2021d28-6633-5017-a05f-bf020bbcd2ce | textbox | Date Completed:
| checkpoint | 9 - Pipe Position Tolerance
7bb8f8e1-320a-5a99-ae4e-46fb9a630498 | note | Inspection / Test Point - Pipe Position Tolerance
a381ebf8-0a09-5cd6-8222-4328d5943171 | note | M
148760e5-c377-5973-8c35-155b247410d7 | note | Frequency - At any point of pipe
55f15f5f-035b-532d-881c-a11a78d19f21 | note | Inspection / Test Method -
e4042748-7a8a-5e23-ba7d-8355036837f2 | note | Conformance Criteria - Position tolerance for pipe laying at any point along the length of the installation shall be within ±30 mm from the specified design.
7645d288-060c-5f08-a122-281148f352af | note | Records - FH Drainage Line Record, Survey Data.
bf7c8cb1-2dd7-5ac6-b06d-9ef83265c6e6 | note | FH Initials - Site Engineer
6d98a35f-4695-5bd7-98db-313774a4d35e | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
8c9a4c37-efc1-5a4c-93b1-390badef206c | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 10 - Trench Backfill - Placing & Compacting
513b3ef0-aa39-5338-be2e-cd925b0111f9 | note | Inspection / Test Point - Trench Backfill - Placing & Compacting
5c804624-1367-5ab1-acb2-63b858dc4ada | note | M
4c9cd90f-e6d6-5111-84d3-e329d940e3a6 | note | Detail - Placing and compacting of Trench Backfill Material
7dc12623-7022-59e0-af08-837e83951a78 | note | Frequency - Throughout Trench Backfilling operation.
1fc567f5-1209-5a51-9c66-74adf845b92d | note | Inspection / Test Method - Visual Inspection
f9ef99c6-b55d-5089-8fe5-d594551aa8ee | note | Conformance Criteria - Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm
2258e5bf-4d0b-56dd-a661-2ec250346aaf | note | Records - Construction Photos
b942e9c1-75ab-59e2-bb5a-09fa7ccd237f | note | FH Initials - Site Engineer
07f2b529-770b-589e-b88d-f7639b0cd6bb | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
7b114328-0ef3-5fbb-b345-f5d46cfc8423 | textbox | Date Completed:
| checkpoint | 11 - As-Built Drawings
f4efdd73-4070-5ea3-8a4c-693869ac793e | note | Inspection / Test Point - As-Built Drawings
2cf6a1d0-0605-5276-9552-434f3543a960 | note | W
362f7d48-d471-56e2-986c-12bbaf186392 | note | Detail - Red pen marked-up As-Builts of every 'Issued for Construction' AT drawings
386db64e-80ad-5c69-a562-20f1b1133c4f | note | Frequency - Final As-Built Drawings to be completed within three months of the construction completion of the asset or infrastructure.
c8193fca-db22-516a-9b13-1008517003f7 | note | Inspection / Test Method - Drawings / Visual Inspection
93ea2e6c-0da2-59b0-9638-666fa747c9c6 | note | Conformance Criteria - As Built and GIS Data
300c80a0-77ae-5dcc-bcda-ec6324397d00 | note | Records - Redline As-Built Drawings, scanned as .pdf files.
74dbf3d8-5415-5495-8f36-57dae8e24fb3 | note | FH Initials - Site Engineer
0d65d4f4-7aa6-5815-bace-0d824c2dfeb8 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - Engineers Rep.
f377021a-5d3f-5e28-af0e-493ff298f606 | textbox | Date Completed:
| checkpoint | Final Inspection
5b0dd77f-1059-515a-b705-725ea3d463a1 | textbox | QA checked By Quality Manager:
02062df2-46f6-5328-84fd-3bddf0081edd | textbox | Accepted By Engineers Rep:
| checklist | ITP - Rockfield Road - Raised Pedestrian Crossing | itp | ITP - Rockfield Road - Raised Pedestrian Crossing | f01d1022-1eb8-4698-8faa-f19ddd078051
| checkpoint | 1 - Permits
05cbec80-0e79-5278-a9b8-27b99151278c | note | Inspection / Test Point - Permits
e0acf17d-d11a-55fd-9f3b-51774b04507f | note | H
820bd8bf-ef4e-5e38-99e3-1551ba54b812 | note | Detail - Obtain Permits
beae4c90-cc33-5469-89d3-a39d65fbb2f3 | note | Frequency - As required
2cacb85b-52bf-51a3-b684-a4d7da722da0 | note | Inspection / Test Method - Document Review
55740fef-9b09-5f6d-9601-e20abe1921e5 | note | Conformance Criteria - Control Checklist - Fall Prevention (if applicable). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
e944414f-42f1-5966-9d50-54eb281252b7 | note | Records - Permit attached or permit number noted
0ffe3f4c-4caa-5602-b48d-5b3f8670a17a | note | FH Initials - Site Engineer
44b7c84e-a64c-5896-a893-025ba7d70c26 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 2 - Pre-construction sign offs
f6a59d11-ec34-58c2-8117-0a17c3784e58 | note | Inspection / Test Point - Pre-construction sign offs
88aab39d-809e-5afd-a87f-c80b4229d69e | note | H
83a2899f-a486-5c8f-a947-939575c3c10b | note | Detail - Ensure that Sub-Contract and Supplier Agreements are signed
6b219e0f-2399-5cab-8275-df2328f6b797 | note | Frequency - Prior to commencement
b84297ee-c7be-5075-bd09-780a69730909 | note | Inspection / Test Method - Document Review
7c7393d5-44c4-5486-abec-d06d734f73cc | note | Conformance Criteria - Signed Subcontractor and Supplier Agreements
873264c5-437f-5685-81f6-90e5b7586b41 | note | Records - Subcontract and Supplier Agreements
374e328d-ff73-55f7-a973-e61e0dbc98dd | note | FH Initials - Site Engineer
0c978cf7-adb7-5c4e-982e-7a3c61b1fe5b | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 2.1 -
3d51b5f1-a6a2-552f-8085-a36ba30b02fd | note | Inspection / Test Point -
450296d5-d0b4-5570-8fc9-ec0342cfab6b | note | H
66842f7f-82af-5041-b3a6-e94eed6264bc | note | Detail - Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
6e8ab7de-01c4-5903-b3a9-8d812040214a | note | Frequency - Prior to commencement
add673bc-ccc0-5508-9b14-29d3baba1582 | note | Inspection / Test Method - Document Review
c2037626-a474-5b37-ac29-923a429e8f8b | note | Conformance Criteria - TMP is approved by CAR manager for each site and works are only completed within the approved dates..
16877900-9e46-55c2-aec5-c6aa470f337f | note | Records - TMP on MyWorksites/On Site
9ef8750c-b3f2-54a6-a0ec-efd437f544ad | note | FH Initials - Site Engineer
7ad330a0-c603-59a1-8dc9-4c6b41e82058 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 2.2 -
af3705bc-3285-582f-827a-85f956f49002 | note | Inspection / Test Point -
cd9659e8-ea34-5d1c-be3c-52447874804a | note | H
2d38d2d6-db26-597f-9a09-68063998e881 | note | Detail - Ensure all Subcontractors and Suppliers go through FH induction
a1570447-19dd-5ea4-a4fb-6f8b2332893a | note | Frequency - On site daily
68999fe1-221c-5b1a-9248-773d25bfffb7 | note | Inspection / Test Method - Induction
bb0b55b4-1789-5ec8-9f6b-494b0bd20846 | note | Conformance Criteria - Supplier's and Subcontractor's signatures on hazard ID and pre-start documentation
c1a31d49-33f7-56f2-b001-a3be07b42d4c | note | Records - Hazard ID and Pre-starts to safety team
9ab58790-a056-5aa8-b1e5-e3ac305e5fe9 | note | FH Initials - Site Engineer
6081fdb6-fb11-54a5-bcb6-c1f98f3c3ca1 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 3 - Design
3c9d7258-8fcf-5943-90d9-389cb2449e37 | note | Inspection / Test Point - Design
edf74a9f-2d7a-59ac-bcff-04fd7e37eb5f | note | H
bc715568-e106-501a-a59d-bca1373b1a48 | note | Detail - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
3328e18e-f6a3-55e4-908e-b8dd7a14d53a | note | Frequency - Prior to commencement
d915f0d1-9d40-5f63-a720-4650cb4baf88 | note | Inspection / Test Method - Document Review
f858f55f-ef85-5be8-9e0f-ec8c58cf7c34 | note | Conformance Criteria - IFC drawings have been received by Contractor
5507bc0d-2fc9-5b31-84b5-cd740801dac6 | note | Records - Check Drawing Register
b711aa63-8e66-557b-8342-5d8439937596 | note | FH Initials - Site Engineer
6ca126e2-65a6-5096-a259-afd9c6d44780 | note | Design Engineer/MSQA Engineer Initials - Design Engineer
7610a12b-e1e7-5091-a17b-a6c264c364e8 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 4 - Installation of Erosion and Sediment Controls
b54d64da-a211-5327-8e14-2ec7c9e5354e | note | Inspection / Test Point - Installation of Erosion and Sediment Controls
05dd4647-bef9-5a89-9a6d-271ed8297738 | note | H
ecd92957-8a36-5863-8a02-9df8b7292823 | note | Detail - Ensure that Erosion & Sediment Control in place
dbe11fb8-9b78-5d8d-9792-bec6685cca82 | note | Frequency - Prior to commencement
692e41c9-4cff-5528-8e20-9240c8062a00 | note | Inspection / Test Method - Visual Inspection
ba7f1958-87c3-5e2d-86de-2d63305a85b3 | note | Conformance Criteria - Territorial Authority has approved the asbuilts for the ESC controls constructed onsite and gives approval for construction to commence
e73d306e-fada-545a-99c3-9d04a73ba238 | note | Records - Environmental Controls Audit
9d286478-8eb4-5d0b-878b-18be120d99c2 | note | FH Initials - Environmental Manager/Site Engineer
e265a897-2e7b-5a1f-82e4-8f363abdb1fe | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 5 - Survey Setout
7090de7c-7732-546f-80ac-41f57ceb3248 | note | Inspection / Test Point - Survey Setout
588bdd70-1124-5f58-82cc-eb2b4ef0ae39 | note | H
0d8459f4-2c52-552e-a87b-400738f3b57b | note | Detail - Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations)
c45a35e0-d659-5bd3-90db-4d98d42dc3b3 | note | Frequency - Prior to commencement
8594f82d-41bd-5685-92b1-9d226f3ef996 | note | Inspection / Test Method - Survey + Smart Level
de677f0a-a856-5016-bf23-9a4d37377fab | note | Conformance Criteria - Consistency with Construction Drawing
d7e5e77e-8ec6-5b87-bce6-24c546d77e53 | note | Records - Site Photos post surveying
2deae77b-622e-5c74-be17-760582c104ba | note | FH Initials - Site Engineer
58a16dc2-fbd9-5d52-84a3-89efc8608cdc | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 6 - Locate Existing Services by Hand Digging
ee5d5d08-ee62-588d-816b-674e0e8c88f5 | note | Inspection / Test Point - Locate Existing Services by Hand Digging
70942ef1-9a1a-5ee5-ad7a-abc50ab14e17 | note | H
31ab2c4a-c406-5384-8081-885c590cc249 | note | Detail - Ensure all services conflicting with the line of trench has been exposed by hand digging
e7f2c366-6a45-5f5f-8ffd-4018da659e78 | note | Frequency - Prior to commencement
1129c76a-4ce3-5e94-818d-39175258b004 | note | Inspection / Test Method - Potholing
1e5a9a32-a739-570e-a768-a1f03c25b878 | note | Conformance Criteria - All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. Asbuilt all services
f5ebdadd-1b77-514f-ba6f-19ff1152919a | note | Records - Digging and excavation checklist, service planes, As-Built Drawings Doc. Review
4ac98b18-af9a-5086-b486-8e41dc6f330e | note | FH Initials - Site Engineer
1f7693c9-3cae-5f92-a60c-6e82238227f8 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 7 - Material Compliance
725807d1-d5c5-50a0-a919-60765d38ae25 | note | Inspection / Test Point - Material Compliance
35fa9cd5-becc-5adb-9a3c-2d030e0816ff | note | H
35d1f776-52e7-52b3-a2a8-5ce12a611412 | note | Detail - LESA dowels to be used at all construction joints
2c42273c-250f-594f-bc1f-9384bb2f3958 | note | Frequency - Prior to pouring concrete
419e6323-037d-5d28-9f6a-6ab663086a1d | note | Inspection / Test Method - Document Review
c3eb137e-65c2-56d5-b81f-5ca06f88021f | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
3c36e38d-f7e3-5150-ac62-5969f1e9d055 | note | Records - Delivery Dockets / Photos
3e380ad2-bfe2-5e88-aef5-5368aad5b397 | note | FH Initials - Site Engineer
322532a2-fb21-5f3f-89aa-dcb1fc853789 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 7.1 -
8f7e8deb-7876-5ad6-a881-d7fc66d1da56 | note | Inspection / Test Point -
fc2ce230-6e38-5c1b-84f7-d49845df89a5 | note | H
ea3cd11b-c2b1-5a37-912a-fe1986e0b5d4 | note | Detail - 0.25mm polythene layer placed across all surface area at bottom of raised table
1ddf18cd-e7f8-59d7-a23b-211aa60872c1 | note | Frequency - Prior to pouring concrete
77860391-908c-5ad1-af05-9c60c0698f0e | note | Inspection / Test Method - Visual Inspection, Document Review
cbccec42-d6b3-50e1-8a3a-f5c0092b7bf1 | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
7602b08f-fb11-5f6e-b4fa-174be874945c | note | Records - Delivery Dockets / Photos
a8b0f701-ff6a-5091-a266-5d8eb054d8e1 | note | FH Initials - Site Engineer
249921a9-a37a-50ed-b065-37afe86753a1 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 7.2 -
2cb04413-514e-5eea-b75a-3cdaf5a9d681 | note | Inspection / Test Point -
7fd493e3-9b90-573a-8110-81bd7e4b18b6 | note | H
944e2271-b1d0-5d8e-af05-739cbfba04f4 | note | Detail - 50mm thick compacted layer of AP20 aggregate placed underneath polyethene layer.
601182fa-4be7-5b27-b466-0f371367cb01 | note | Frequency - Prior to pouring concrete
07ba3819-b2d8-5463-a688-abdf4d7e3e26 | note | Inspection / Test Method - Visual Inspection
704c97d8-6cde-52bd-8466-c6c733544080 | note | Conformance Criteria - CIV >15
b8ef0332-e935-5f16-8dc7-e66b4dde96f3 | note | Records - Delivery Dockets
cd0da887-e456-5470-b323-607dfe49b212 | note | FH Initials - Site Engineer
275b7b55-a0f5-5d19-b292-92ee4af87781 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 7.3 -
95c9c422-d041-5811-9614-4888c96a6f4c | note | Inspection / Test Point -
2916f9ca-f1cb-5401-bcc6-8d37de94940a | note | H
9a505cde-6ea7-5a6d-9174-774fe16bd285 | note | Detail - Two layers of 663 mesh to be placed inside with plastic chairs separating.
a1c9c413-c842-5ae6-b558-13ae0aa00629 | note | Frequency - Prior to pouring concrete
c6106c54-b39e-56d6-9490-35ad36e3a146 | note | Inspection / Test Method - Visual inspection
2c5ed789-bd26-57e1-b51f-a6bf7e4419ef | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
f68e0a3f-2d24-5caa-a5a7-f6df4c49668b | note | Records - Delivery Dockets / Photos
72bd08ab-d71e-5e06-a3a0-767db0f9c1a7 | note | FH Initials - Site Engineer
c66107a3-ec68-5ca8-bb55-7439032f0021 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 7.4 -
0d71ee37-22b0-57b6-870d-2f887facfcd4 | note | Inspection / Test Point -
b4ba1bc6-a2b7-5b0f-b062-2117d2db1fe3 | note | H
5dc0f403-0732-543f-9d1d-f7fa2e481557 | note | Detail - All concrete delivered to site shall have 40MPa 28 day compressive strength with 4kg/m3 of Black Oxide Powder and 13mm aggregate chip size
37d8b1d1-e726-5956-93ea-5813526ab5d0 | note | Frequency - Prior to pouring concrete
4f74487f-5291-5fca-964d-127d1e32bc81 | note | Inspection / Test Method - Concrete Delivery Dockets
651570f1-2fe9-506e-ba3d-a55369e3bf74 | note | Conformance Criteria - Delivery Docket added to QA folder
e34b61f8-081a-50ad-9b51-4974c544f6fa | note | Records - Concrete Delivery Dockets
469d149e-1ce1-57c6-97b3-245e7a364923 | note | FH Initials - Site Engineer
d62df1dc-a46d-5a17-bd0d-46c8adb22441 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 7.5 -
89a9b857-d4a3-56eb-9c8f-0d1a12390bd6 | note | Inspection / Test Point -
f537b313-40a1-5631-8051-373e625e20b3 | note | H
b950baf6-53ab-5c10-ac9d-98b750f5e7ba | note | Detail - Steel chequer plate cover powder coated skid resistant yellow connecting kerb to kerb bolted on
3f3c35ca-0828-5d18-abe7-3414fc74622e | note | Frequency - Prior to pouring concrete
384872a0-5e79-50e9-9fc3-f27d2f8a1659 | note | Inspection / Test Method - Visual inspection
856f8d00-2b1a-5229-9567-a81dce416a23 | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
1c0e11ab-7d64-5847-8627-1744341eef69 | note | Records - Delivery Dockets / Photos
26d3a297-5480-5f3a-92e7-75763d0d46bd | note | FH Initials - Site Engineer
d96652df-27c8-54e3-9ca8-338e64511ed6 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 8 - Temporary Works (Formwork)
2e400c34-b05d-56dd-b3eb-1432731ad06a | note | Inspection / Test Point - Temporary Works (Formwork)
0d768aa3-2368-59f5-8c7c-da3c0f4cd440 | note | W
cb4ebbed-c619-58d8-a14a-6c500f30890a | note | Detail - Formwork to be set to correct line and level
4d618890-5115-59b0-a271-86a8812ea9bc | note | Frequency - Prior to pouring concrete
623014ef-0269-54ba-a098-db4b44d1efb9 | note | Inspection / Test Method - Visual inspection
1778ec95-a31b-53a4-bc99-c486c9d6e33b | note | Conformance Criteria - Concrete Inspection Record
3169c781-8a2b-501d-94f9-d3019424cde0 | note | Records - Concrete Formwork Checklist
fde13eb7-0bf3-5618-b8e6-32d8b7e67944 | note | FH Initials - Site Engineer
0f31d380-7352-509e-b204-279d75d692a3 | note | Design Engineer/MSQA Engineer Initials - MSQA Engineer
9f7d0a19-c266-5b3c-bea0-298a8973873a | textbox | Date Completed:
| checkpoint | 8.1 -
2e2f9cf7-1a5e-5726-b0a1-3ac911c41f73 | note | Inspection / Test Point -
5c917d1a-38a0-5e26-8b7f-a3cf729f3e41 | note | H
511c9b0d-98a5-50cf-9421-19804fc63f25 | note | Detail - Raised table formwork to be 100mm above existing road level and be 300mm in depth and gradients respectively of entry and exit ramps
dd7ba0f1-1c8a-53c7-83e3-95ccf105c104 | note | Frequency - Prior to pouring concrete
90168591-b495-5e18-9068-2eb2b655a3fc | note | Inspection / Test Method - Measurement
a9f0c13b-ea05-577b-9049-ed5bcb38653b | note | Conformance Criteria - Designer to inspect formation level
49248cf6-1ff0-5d9a-be0c-25e7fc986c85 | note | Records - Site photos
26efac4b-0b8b-557f-8b7f-7d75a141f2e9 | note | FH Initials - Site Engineer
af388441-2658-5175-b26b-581d8d2d9176 | note | Design Engineer/MSQA Engineer Initials - MSQA Engineer
7520e2c4-1cd2-5c7d-aa74-198fa9976d8e | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 8.2 -
817aec67-63de-58b9-a53e-99e691a2c383 | note | Inspection / Test Point -
0e39bdaf-3557-5bec-99c1-df80226c66dc | note | H
b73e8d63-c299-5a5b-bbd8-9b018b1e987b | note | Detail - Raised Table ramps to have 200mm depth at entry point and tie into 300mm depth to meet raised table
62b5c8e4-b860-587b-86b6-6dc9b5e33fe1 | note | Frequency - Prior to pouring concrete
a3b92258-d6b6-5346-89e3-2de4d1e8f9d0 | note | Inspection / Test Method - Measurement
42c0896e-52cb-57d3-b177-5f891bcf8589 | note | Conformance Criteria - Designer to inspect formation level
00cf9ce7-fae0-5d26-9d0c-a88f159fbb3d | note | Records - Site photos
4f5f5d54-c2c5-5cc3-bc15-3a441c048742 | note | FH Initials - Site Engineer
dace20b0-f72d-57d8-9a77-06860e26a9a1 | note | Design Engineer/MSQA Engineer Initials - MSQA Engineer
559695be-c4ce-5609-9626-1d70b4f3cdc6 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 8.3 -
b9c5c145-9370-523e-8125-45b8a0949bf1 | note | Inspection / Test Point -
75510f12-7aa2-578c-b248-e81555b2d0a4 | note | H
caf40323-ad83-5816-abac-7e44b432832e | note | Detail - Raised Table ramps to be 1m across for entry and 1m for departure ramp. Toe to be 1m across for both entry and departure with asphaltic wearing course
b47b0dd5-6c5c-5b58-81ce-cfe0554816da | note | Frequency - Prior to pouring concrete
12334108-527e-54a5-aa0d-53379a7a1795 | note | Inspection / Test Method - Measurement
b1d2c378-f9a9-5247-88b2-c00adbe83ed4 | note | Conformance Criteria - Designer to inspect formation level
a22d485f-4d78-5bda-9374-9920cb6edc88 | note | Records - Site photos
ea15c6bc-8895-52ed-a609-561d4245ba9e | note | FH Initials - Site Engineer
07232781-b115-52ca-a7b3-b549d75b3a65 | note | Design Engineer/MSQA Engineer Initials - MSQA Engineer
7ca9b55d-3e30-571f-9ae4-3b0eccb59833 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 8.4 -
c8034f61-e52b-5a5f-82cb-6b0eebe923db | note | Inspection / Test Point -
3994f072-0b04-522a-acf7-1d3feb138ca1 | note | H
718e6eba-f98f-592a-acef-994ba948c4a2 | note | Detail - Raised Table ramps to be 1:10 gradient for ramps
38311fe5-5209-5701-b961-66c5d2feedf0 | note | Frequency - Prior to pouring concrete
b43405fc-487c-5c70-a3f9-8244e14cbe49 | note | Inspection / Test Method - Measurement
3c8c01f8-b069-5e4b-a06f-7d361627d7d8 | note | Conformance Criteria - Designer to inspect gradient level
fcb1ea13-2a55-52d8-9e89-4487701dd7fe | note | Records - Site photos / Concrete Formwork Checklist
ba30032d-2f08-5d04-a0c7-639af18ca3bd | note | FH Initials - Site Engineer
82039416-27c3-57a7-b1c9-5a54a8636b18 | note | Design Engineer/MSQA Engineer Initials - MSQA Engineer
ea7f7fe4-24ff-5349-ad2e-78c96a8f4a39 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 8.5 -
ec8c8d55-f144-575b-84cb-e9f80a7c0e49 | note | Inspection / Test Point -
46455d9c-2a8c-5754-bcdb-4522f73537b7 | note | H
4076ca26-5b08-5e6d-b549-14fcbeaa46d2 | note | Detail - The Site Engineer and MSQA Engineer must sign off the formwork prior to concrete being poured
32da3cea-0a7c-5469-902f-0e2dcbdc9891 | note | Frequency - Prior to concrete pour
53434348-0009-55f8-99e3-9f5c8001d5e6 | note | Inspection / Test Method - Visual inspection
45af18bd-521b-5be0-9f59-71b684faf1fa | note | Conformance Criteria - Concrete Inspection Record
993970b3-34df-575f-8aec-0738da14c7d9 | note | Records - Concrete Formwork Checklist
c122dd8f-14b5-506b-89ce-1e5aa8933446 | note | FH Initials - Site Engineer
edf67f0d-b97a-5538-980a-3937679ad618 | note | Design Engineer/MSQA Engineer Initials - MSQA Engineer
361af112-825c-52c6-b0e0-baeef8c78be4 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 9 - Reinforcing
2caf267d-4898-59c6-a18b-1b6a0a8e511a | note | Inspection / Test Point - Reinforcing
7cf9e9da-0f8a-5980-b964-ff611bbea450 | note | H
349a6ea8-555d-57e3-b77f-c3d5a0126183 | note | Detail - All construction joints are to contain 2 rows of LESA dowels or similar approved dowels . Speed basket system 50mm w/ Black 300*50*6mm plates @400 centres placed across the construction joint
9b498cc7-89d2-5987-8865-b6918031d17c | note | Frequency - Prior to pouring concrete
e5335527-afc7-5c2a-a4c0-7abc8148ced7 | note | Inspection / Test Method - Measurement
7dd6396c-d0fe-5855-aa70-cbf8bf5c57ac | note | Conformance Criteria - Concrete Inspection Record
a2a19c69-1086-5762-af10-99839fe185ce | note | Records - Site photos/Concrete Formwork Checklist
00b09ec9-b9eb-5339-a3bd-4405d4d96318 | note | FH Initials - Site Engineer
ddf07baf-5743-5cc3-8292-1e68a803aee3 | note | Design Engineer/MSQA Engineer Initials - MSQA Engineer
beee2acf-9497-5eba-8181-5ce812847419 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 10 - Concreting
632436b2-c02d-553f-8dc2-fd079228d00e | note | Inspection / Test Point - Concreting
c948e372-bafa-5714-b640-094a435f463d | note | H
1c1540ad-e769-5461-b250-64abb96aab5a | note | Detail - The MSQA Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required
963cfaff-c9ab-530c-a8e2-82000115958e | note | Frequency - Prior to concrete pour
edcacaf8-c057-5489-807f-1b8b3695c64a | note | Inspection / Test Method - Visual inspection
0e83e389-6295-57f2-821b-2b578f31aae9 | note | Conformance Criteria - Engineer will be notified via email/SMS at least 24 hours before required for inspection
22c8ef53-7418-5f4a-99e6-a13127694fe9 | note | Records - Email / SMS
aceec6f9-e27c-5223-ab4d-263861b96619 | note | FH Initials - Site Engineer
42262de0-6ea7-50ef-aded-d8ad20033422 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 10.1 -
2c56ea6a-2fb6-5ac0-844a-b8e47ccbddcf | note | Inspection / Test Point -
20286f18-db82-52a7-8e2b-58a0595b9ab8 | note | W
bace855d-3ffc-524c-afbb-789a6a8bb874 | note | Detail - Vibrator to be used throughout concrete pour
04186972-2adc-527c-820a-a0bfb8ec0175 | note | Frequency - When pouring concrete
3ae7e579-b665-5350-bad9-96269c028d20 | note | Inspection / Test Method - Visual Inspection
24394b2b-4e02-5040-9693-9437f4feb4b6 | note | Conformance Criteria - Concrete Inspection Record
a5520cf9-62f6-5b99-a64b-1ef51844f9b8 | note | Records - Concrete Formwork Checklist
6c7522c3-c4ba-5015-b7d6-1b1469f345cd | note | FH Initials - Site Engineer
f82cb3f5-db9e-560d-9246-e4e96623caf5 | textbox | Date Completed:
| checkpoint | 10.2 -
bccfd351-21a7-575e-a947-246a5c035348 | note | Inspection / Test Point -
e48ce5f5-439d-5642-bf89-ac1cdce1beca | note | H
be633215-234d-5d91-9c56-38ba448c32a0 | note | Detail - Concrete surfaces shall be U5 broom finish for ramps, and exposed aggregate finish for table top.
b3e4cabf-e7a5-5219-b968-4b5506a2b075 | note | Frequency - At completion of pour
650fa4b8-e748-5929-87b5-94ceb7692936 | note | Inspection / Test Method - Visual inspection
5502497a-0832-5442-9b69-390b8d5edaa3 | note | Conformance Criteria - Concrete Inspection Record
22ec5c40-619c-5dde-a87a-ef69780f1fe2 | note | Records - Concrete Formwork Checklist
6404d0bd-2561-5b6e-9a6e-dcb661853b13 | note | FH Initials - Site Engineer
8afaa1fc-81ab-5ec4-8700-a4034a90257b | note | Design Engineer/MSQA Engineer Initials - MSQA Engineer
61b54244-69b1-51d0-949c-f0e0fec87305 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 11 - Curing
93c5ffb0-7412-5491-9e91-938a880e6fec | note | Inspection / Test Point - Curing
a3f3896e-a51e-521c-9bf5-58d4d1f4cbf0 | note | M
4e7adff6-6e27-5cdf-8b81-f9ff702ae6f2 | note | Detail - Concrete will be left for 48 hours minimum to cure before traffic is allowed on it.
ec1b5aa6-8f6f-5033-af9f-c1f2c901bf1b | note | Frequency - Post Pour
faa49a7b-864a-56b5-a497-9c777993a765 | note | Inspection / Test Method - Monitoring the time allowed for curing
44887ec4-94e9-5530-8318-69f34991ae31 | note | Conformance Criteria - 48 hours minimum have passed
a3d8a987-3682-5fbe-a0ab-06b416f65e6a | note | Records - Concrete Formwork Checklist
2e4905f2-a99c-583a-aeb5-575223eed83b | note | FH Initials - Site Engineer
dd4949ef-31e0-5f06-89d9-a68668a10eef | textbox | Date Completed:
| checkpoint | 12 - Remove formwork
19400316-74ee-5874-9f96-b918b64e4aa8 | note | Inspection / Test Point - Remove formwork
c97af875-16a7-55d6-abf7-e7da1d145269 | note | W
6c594a86-bd83-5538-9b4b-8f30b5bb6479 | note | Detail - Remove formwork after 48 hours
74e90f37-113e-54f5-a69a-6b334652b873 | note | Frequency - Post Curing
cee20364-5503-5421-975d-3075f6760eca | note | Inspection / Test Method - Visual inspection
adea6d84-71ad-5790-a38b-59e23cb0f843 | note | Conformance Criteria - Concrete Inspection Record
5b9782d5-e748-574d-8397-5e59a6f2bf9d | note | Records - Concrete Formwork Checklist
38d6b186-f90c-507a-b57f-c0f317e9c7ff | note | FH Initials - Site Engineer
a2c4dd0f-ca1d-5813-b069-94c6ff7bd1cd | textbox | Date Completed:
| checkpoint | 13 - Asphalt- Concrete extension slab/ Toe
4b04f28e-659b-56a3-8268-f47178c68e15 | note | Inspection / Test Point - Asphalt- Concrete extension slab/ Toe
e8b7dedd-3f51-52c3-8b07-10cc8858f7f3 | note | H
6659e328-71c4-5557-9990-056088e19ea1 | note | Detail - Two rows of Lesa diamond placed mid depth @400 C/C along construction joint as per 2789-C6500
159decb3-9784-5e54-b485-d61e3f93a845 | note | Frequency - Prior to pouring concrete
eea4bb89-2e82-5f18-a488-c9497d5407c7 | note | Inspection / Test Method - Measurement
13b7029d-956f-541a-9577-40333664e919 | note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
8050366c-b834-546f-8084-b03cd6e1412a | note | Records - Site photos, delivery dockets
ae3f41b2-3fa9-5ed4-a333-a5e24471dec6 | note | FH Initials - Site Engineer
dddb5520-17e5-5e29-8608-e0e52d2d44dd | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 13.1 -
868d8cdf-bb0a-58de-a036-098c8d74f13c | note | Inspection / Test Point -
370847f7-031b-59ff-9c96-4e4a3db1dcaa | note | H
87ac80a2-dc16-5a34-bc76-d75dc64bce33 | note | Detail - 150mm thick 40MPa Concrete with two layers of 663 mesh
51763886-8c4c-556d-9347-7616435ec232 | note | Frequency - Prior to pouring concrete
9a2e1a76-005f-54b3-9575-6c8791435be3 | note | Inspection / Test Method - Measurement
e083d65d-6b4d-571b-b2b7-9ae6ba746249 | note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
2035b63d-ff97-59e4-8a03-aa05041063a5 | note | Records - Site photos, delivery dockets
91c367b8-0bd2-53cd-bdb1-1f61953dcbe8 | note | FH Initials - Site Engineer
a7c08cbb-135a-570c-ac33-f2cd20db6495 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 13.2 -
328e5297-9ab8-5172-96b1-9a66f1b61b8a | note | Inspection / Test Point -
e365e014-e8a9-5823-90a4-c4223340b11b | note | W
6d459a30-bb2e-5744-b198-9d3a6c74e118 | note | Detail - Tack Coat between AC and Concrete slab
1c67a132-d2c6-53a2-b934-9e13acc83216 | note | Frequency - Post Curing
5b030bdf-9782-5c23-9e3a-7904a1bf742a | note | Inspection / Test Method - Visual inspection
53a4bfae-2978-5c7b-b353-8c5f3b3d7fad | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
25572adb-ace6-5f65-a26d-04fc79e79ef3 | note | Records - Site photos
ef4dea5c-d31f-5076-820c-d9f66c4e7ad0 | note | FH Initials - Site Engineer
86dbda62-616c-5045-a0f2-dd630d119d49 | textbox | Date Completed:
| checkpoint | 13.3 -
6bed3770-4b66-53ac-a8c9-864165eca01e | note | Inspection / Test Point -
cbfcd288-152a-5998-ab64-65896ab5121e | note | W
06e0a4ed-ff08-5704-9912-6123ed6a6230 | note | Detail - 50mm thick DG10/Mix 7
73ce9a89-5deb-5c42-8105-7869c9933c95 | note | Frequency - Post Curing
c6f599e0-80b5-54a7-ab56-fbcdb176e6ae | note | Inspection / Test Method - Measurement
8ee57864-aee9-5a4f-924a-3e4fa098d577 | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
12ace640-3442-58c4-bb4f-e257036e2cf1 | note | Records - Site photos, delivery dockets
e4b16ab2-d06d-5b3f-b608-f2520e85c838 | note | FH Initials - Site Engineer
d3a4e18c-5de7-5e36-b53d-6d03c4acbe1c | textbox | Date Completed:
| checkpoint | 14 - Lot Number QA File
bd2b47aa-a80e-5c54-b123-240d0c9608a7 | note | Inspection / Test Point - Lot Number QA File
6c8591b7-9628-57ad-8b16-adc7a06ab7db | note | W
397a3720-b65d-5d4d-96d0-3561e22194e3 | note | Detail - Ensure all QA Records, site photos and incident cases (OFIs) are closed and included within QA file
7210877a-1748-5ce7-9f3a-d3029a9c7e59 | note | Frequency - At completion of Lot
df51271b-0637-5fcb-beda-658d1c84b923 | note | Inspection / Test Method - Document Review
ae415392-6b8b-5a83-97e1-c45ebbcf4481 | note | Conformance Criteria - All QA files compiled and submitted to client
65af2ce3-1125-512a-9f68-b0778cb62e0e | note | Records - QA records
48c9ccb2-1b8a-575c-840e-01dc27607cac | note | FH Initials - Site Engineer
2f75e48a-7b4e-596c-b63d-eb81f99b31b7 | textbox | Date Completed:
| checkpoint | 14.1 -
38ddffc4-6ad0-5174-b8c4-2ecd127a14ec | note | Inspection / Test Point -
f981d0e1-ec05-5933-8b15-184f91bbbf2f | note | W
2d505d36-a0a5-560b-bb25-eca2f31b6fc6 | note | Detail - Delivery Dockets to be included in QA file
cc82254a-7a9f-51b3-824d-62ce55ab28ee | note | Frequency - At completion of Lot
b7e579b0-a29e-55da-8c48-4b5718831486 | note | Inspection / Test Method - Document Review
862838fb-0568-5bf5-9914-69e36ec1b175 | note | Conformance Criteria - Delivery Dockets to be included in QA file
6f221d5a-1771-56b2-932f-0b64a4e0535e | note | Records - QA records
a705f408-6ebf-5b50-944c-8204f9876a00 | note | FH Initials - Site Engineer
5844dc61-a36a-5784-9806-25f253e4b55a | textbox | Date Completed:
| checkpoint | 15 - As-builts
ae680f74-b222-5a0a-80a0-41fb21c2be54 | note | Inspection / Test Point - As-builts
a1517fce-eb7b-5b8e-bb8d-6b5f9c6a1f18 | note | H
e093927a-549c-5dba-92d5-9ff8b15fc888 | note | Detail - Red pen mark up drawings to be included in QA file
8445d1af-357c-5deb-9686-01ddcb7f0203 | note | Frequency - At the completion of the Lot of work
7328d362-b87c-561e-bfff-77c972a1c681 | note | Inspection / Test Method - Drawings
485f43ab-8756-5f12-bf71-c4def112c5aa | note | Conformance Criteria -
9ae87ba0-7401-56a9-add8-ea43cc7c8047 | note | Records - Asbuilt Drawing
1931cb71-8ffc-50c2-acd3-a46b07fbab10 | note | FH Initials - Site Engineer
7cd667b3-3e9b-5244-bbe8-0cfdf68c943e | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | Final Inspection
42675938-bf9f-58dd-9ea8-4c0de3756ee2 | textbox | Comments:
cdfb682a-67af-5d0a-8f0c-d14183aa06fd | textbox | IFC Drawings used for Construction incl. Rev numbers:
9b3121f1-079c-59ab-8139-9016a7fde799 | textbox | Reference Documentation (Notices/OFIs etc.):
88c6352c-529d-58c2-acac-e8f3e4b78f17 | textbox | QA Compiled By :
5e6faef5-9b97-55ce-b1bd-c4016f6dcbe9 | textbox | QA checked By Discipline Manager:
6953f4d2-489f-5e3a-a51b-9e2531068a13 | textbox | QA checked By Quality Manager:
fd076df9-63f6-52cc-99e5-15d4e88976a6 | textbox | Accepted By Design Engineer:
| checklist | ITP - St Lukes Road/Morningside Drive intersection - ACO Drain |  | ITP - St Lukes Road/Morningside Drive intersection - ACO Drain | 5efec312-69d8-4545-907a-61b438f80ebf
| section | Site Set Out
| checkpoint | 1 - Site Set out
8d2cb990-d643-54e4-81c7-2eb64701ec28 | note | VERIFICATION ACTIVITY - Surveyor
a163aa42-ee57-5a45-abf0-8f2a1086352e | note | METHODS OR REFERENCE - Surveyor
4996eb01-0caf-560c-9622-5009cc71c06d | note | FREQUENCY - Everysite
b397f755-1e45-5a08-9c1d-f32aace6121a | note | ACCEPTANCE CRITERIA - Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable. Alternatively like for like
3886774e-4365-539b-9db5-17c146df85b3 | note | Hold Point - Mandatory HOLD POINT -
c54b5da8-d6c3-55bc-8c9f-c157e186260b | note | Records - Survey Receipt
8d354d04-0c52-529a-a231-b857b760b210 | note | Onsite Responsibility - Site Engineer
| section | Materials
| checkpoint | 2 - Aco Drain K300
2019d5e1-bab3-5546-83cb-6be0a19ab6b3 | note | VERIFICATION ACTIVITY - QA FORM
c0d24776-74b0-5e71-83c5-09c3e17f87cd | note | METHODS OR REFERENCE - TDM Technical Standards
be4ba5b2-db72-548f-9e0c-3ec3d3a71432 | note | FREQUENCY - Every site
a6b9e3f2-85b5-58e3-8621-541688a849c1 | note | ACCEPTANCE CRITERIA - All the block and the grate should be inspected before installation.
1be8310b-7573-5f61-aac7-d9453064bf16 | note | Hold Point - Inprocess Inspection
35aa8ee4-47ae-579d-a831-1647eb0af817 | note | Records - Dockets
627935ab-00ec-5b5c-9449-a6ba764ed2e2 | note | Onsite Responsibility - Site Engineer
| section | Construction
| checkpoint | 3 - Prep and Level Check
a24eccd3-6ecc-59ee-9df8-74a565d942e7 | note | VERIFICATION ACTIVITY - QA FORM
5c7aa7cf-6d79-52a0-9553-3ad91bf4caae | note | METHODS OR REFERENCE - TDM Technical Standards
4a848d28-6759-5c4c-9e89-834e3c03650a | note | FREQUENCY - Each block
aa67d21f-b7fc-57ae-bac6-31090f0dc4d6 | note | ACCEPTANCE CRITERIA - Subgrade -(CBR > 3) Base course - 100mm min. thickness GAP40 Clegg CIV > 12 water flow check
8adbd7c8-cd7a-56de-be80-f2913bd283ea | note | Hold Point - Inprocess Inspection - Engnieer to check
b887f8ed-a852-5121-afbc-c3982d25dac1 | note | Records - Depth check photos, fall check photos
ac9d0316-9531-5036-9f5d-3f8c10802baa | note | Onsite Responsibility - Site Engineer
| checkpoint | 4 - Lay Kerb Drain
b5a4273d-16ed-5b80-b7a5-80f4cb40d546 | note | VERIFICATION ACTIVITY - QA FORM
d3cba88f-bbdc-5682-bb47-b388f081efc7 | note | METHODS OR REFERENCE - TDM Technical Standards
ff9a9474-cff4-5099-8b5d-5bd778101c14 | note | FREQUENCY - Each Block
b93716a8-ce3e-519c-85bc-41420a4b94a0 | note | ACCEPTANCE CRITERIA - Boxing to be done along the aco drain Surfacing - Concrete 150mm and 25 MPa @ 28 days. Side Haunching for 150mm thickness Vibrator to be used to avoid voids Finished level of concrete to match with the grate
c32f0af1-9101-51f0-9413-471bfda118f8 | note | Hold Point - Inprocess Inspection - Engnieer to check
d6e5fe0f-7387-5d68-9d48-42a42792a41b | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record Photos
204999e8-7444-52f1-b72a-3cab8cd24521 | note | Onsite Responsibility - Site Engineer
| section | Asbuilts
| checkpoint | 5 - As built information
4fb58146-3b2c-5539-b8db-ace20155720d | note | VERIFICATION ACTIVITY - RAMM DATA SHEET
6298cf22-5493-5cdb-bfbb-68fd43443ab0 | note | FREQUENCY - Every Site
3d8aab18-82c0-5dad-bdaf-222d08a55cd1 | note | ACCEPTANCE CRITERIA - As built drawings and Ramm Sheets Completed
d002737a-0616-59e4-a872-4f70729a052c | note | Hold Point - In Process Inspection
3467b14a-7435-5c5c-8593-1fe47caa147f | note | Records - Asbuilt records
5063ca62-6a79-5008-8faa-a6057e59afdb | note | Onsite Responsibility - Supervisor and Engineer
| checklist | ITP - St Lukes Road/Morningside Drive intersection - Concrete Speedtable |  | ITP - St Lukes Road/Morningside Drive intersection - Concrete Speedtable | 3af1a026-2d05-4b11-9b24-e1bc18bea14f
| checkpoint | 1 - Permits
e6f3aff5-0470-5358-97c8-75890da90e52 | note | H
fd02a609-4748-5423-ba94-1a6b32646d70 | note | Detail - Obtain Permits
41c4671b-bb58-5b70-aa26-e1a780c100b3 | note | Frequency - As required
7db272a8-e8c4-5088-9f49-da3af3ecf3fe | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
aef79d54-2ba2-5701-a532-b6cf2877725c | note | Conformance Criteria - Control Checklist - Fall Prevention (if applicable). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
2d1d7724-90d0-5e6e-b5a5-7bd51ee9c1fd | note | Records - Permit attached or permit number noted
78448a1f-755e-58a6-8b1e-33e96a5413f0 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Pre-construction sign offs
7e1d353d-199b-57ee-8b0f-4e7a26094cf4 | note | H
5956bcf0-ea6a-5c49-a143-79d31231b1e3 | note | Detail - Ensure that Sub-Contract and Supplier Agreements are signed
f9fd521d-b8a0-5d3c-afe9-258481c68823 | note | Frequency - Prior to commencement
d10a92e7-412a-558c-a5c3-aec4cad342dc | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
cfb16333-1272-509c-b8d5-b998d425500b | note | Conformance Criteria - Signed Subcontractor and Supplier Agreements
fb205010-5e0d-5dd3-b6f1-3f1cf8f0343d | note | Records - Subcontract and Supplier Agreements
1648a4e1-9348-5fab-9592-71a9dee2914f | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.1 -
acf1a44a-6857-51fd-98f0-7ac93157d55d | note | H
c30b5540-3280-5e88-9483-c305ece1a499 | note | Detail - Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
d8e74fb9-d412-54a0-9a07-a5a4e3ea144b | note | Frequency - Prior to commencement
a5244250-5b36-5ef0-9353-52ceb8470648 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
5129e841-6de8-52aa-ac5e-4ee8b02a301b | note | Conformance Criteria - TMP is approved by CAR manager for each site and works are only completed within the approved dates..
b353e649-e78a-50f2-8f10-104adcf353e9 | note | Records - TMP on MyWorksites/On Site
55d40d2d-7193-50ab-871d-cc94fb4664a8 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 -
aadab849-959b-5f46-9336-a7ada69d3a81 | note | H
48927965-f30e-5139-909f-e17b8a07e769 | note | Detail - Ensure all Sub-Contractors and Suppliers go through FH induction
65bf89c4-fc85-5746-905a-037e14adb4a4 | note | Frequency - On site daily
8c1558f2-0bdc-5a20-9122-a5d273ddd1e5 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Induction
d3be0450-fce1-56a1-96be-6d6a681057ef | note | Conformance Criteria - Supplier's and Subcontractor's signatures on hazard ID and pre-start documentation
892b25f5-6d32-5c78-b567-b82c8134967a | note | Records - Hazard ID and Pre-starts to safety team
99ceaf5d-5b06-5abe-8c20-3b32679e46e9 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Design
5c2baddc-bc2d-5ce8-acb9-9c0fdc5460c6 | note | H
af531e0f-36c0-5e7c-af68-f96bfab78a58 | note | Detail - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
b9724924-6cc8-553b-b0ff-44298cc90cee | note | Frequency - Prior to commencement
1bbb7d5c-8dbc-5e20-b2a2-9ae2f95bf771 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
c3c15c7f-7c66-5650-b978-d77d94c5ae43 | note | Conformance Criteria - IFC drawings have been received by Contractor
889a8405-bebc-5df6-8394-4c873d9c629c | note | Records - Check Drawing Register
dd80d9e4-7f37-56f2-951f-fdd807a08871 | note | FH Initials - Site Engineer
cc56dd9a-7d83-5ae4-b822-5bfd353ac45e | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - Design Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Installation of Erosion and Sediment Controls
8758f403-b4d7-566a-9ee2-e21b6edb2b2b | note | H
55f4d2f3-1214-56bd-acd5-4ceb5b8a0dfb | note | Detail - Ensure that Erosion & Sediment Control in place
3d4e8182-66a9-5fd6-bb4a-bc6e60cb6d06 | note | Frequency - Prior to commencement
75fc6e28-9ac1-5286-a8fb-62380cc2e08c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
828d9487-4f43-58c1-bb63-e66771bbba79 | note | Conformance Criteria - Territorial Authority has approved the asbuilts for the ESC controls constructed onsite and gives approval for construction to commence
2de43f08-14e6-5a4e-84a7-9f83c33a4132 | note | Records - Environmental Controls Audit
d61a3d8e-7042-5f82-a49a-7aed4a72a44e | note | FH Initials - Environmental Manager/Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Survey Setout
4fe38ba4-17ce-5b8e-95a1-06caffc5e200 | note | H
f7726095-63be-5714-bee4-c3a99a88156a | note | Detail - Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations)
846065df-2d51-5384-a886-903b0b9eada3 | note | Frequency - Prior to commencement
de5c25bb-b83d-5cc8-a4ca-4dca07b288b6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey + Smart Level
47caa804-391f-50a5-bae3-9f78cbb6fd1a | note | Conformance Criteria - Consistency with Construction Drawing
babb074b-ad66-5d8c-9121-ae0a15c77bcb | note | Records - Site Photos post surveying
55b8d5b7-0749-5509-9fcb-f792d435ea49 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Locate Existing Services by Hand Digging
0768858f-dd07-52ce-9583-50fa9cadd59a | note | H
5399135f-2013-5aaf-b3cc-aba95f5f73d5 | note | Detail - Ensure all services conflicting with the line of trench has been exposed by hand digging
2c1ba671-5d31-59d0-b3a4-cc5de88a9a0c | note | Frequency - Prior to commencement
2b147023-e2f8-5077-a138-09faa8f45313 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Potholing
01ba10b2-5ef5-58ea-97de-8172cc73e709 | note | Conformance Criteria - All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. Asbuilt all services
9039067d-fd1b-5412-a5df-8f580b2fa6dc | note | Records - Digging and excavation checklist, service planes,As-Built Drawings Doc. Review
99a9ef7b-fa0a-5c74-a499-3770228c0bdc | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Material Compliance
6aab4d36-20bd-5d9a-931a-a88ceb1e7a04 | note | H
15301909-8be2-52ca-805f-6de5f31dfdf8 | note | Detail - LESA dowels to be used at all construction joints at 600mm clearance
74747b08-34aa-52ed-bbb4-30f51eaeb748 | note | Frequency - Prior to pouring concrete
bcb0cf01-b73b-5bec-8afd-177c92e2afc9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
a98fa5e4-f3af-51e0-b147-a0620c2be4ce | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
dac2ce38-5301-5742-8989-2f28af4a3044 | note | Records - Delivery Dockets / Photos
20825d9e-a563-5edb-914e-b237f168e543 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.1 -
9613c092-9e7b-54c2-8a6b-d09c6c30e099 | note | H
8e81ee63-23e3-5a49-aefc-0fa9ff286568 | note | Detail - 0.25mm polythene layer placed across all surface area at bottom of raised table
20a79c14-bf80-56a5-a431-cc1f4844af3f | note | Frequency - Prior to pouring concrete
2e05a09b-0f25-58cf-8c3d-69ec1ff45151 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, Document Review
5cc318d4-c501-5cdd-8886-b5b49e6baafc | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
2bd2f254-a3e2-54d0-8065-6496f9aff4fd | note | Records - Delivery Dockets / Photos
ec232d54-0057-55a8-9eaf-362920f33086 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.2 -
bf88917e-1075-50ff-85b0-51617eba3628 | note | H
69ea281d-0d1c-5581-bc76-b47dae8d500e | note | Detail - 30mm thick compacted layer of AP20 aggregate placed underneath polyethene layer.
2e88c977-22d6-50ba-807e-09a1822bc3b1 | note | Frequency - Prior to pouring concrete
fe1cbf54-e33b-5fc3-98fd-fde4731cc756 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
0e31f1b1-7dc1-5ffa-a9e0-5655349db1b4 | note | Conformance Criteria - CIV >15
9ce8d69b-ed89-5653-aae1-60fd203091e8 | note | Records - Delivery Dockets
8cf5391b-af65-5663-9bf1-31dd87ca1574 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.3 -
32fb9b68-3c17-58dd-8d4d-b7c0bdce39af | note | H
0f50a400-a0df-565f-8879-99ea41c2faba | note | Detail - Two layers of 663 mesh 50mm cover from top and bottom to be placed inside with 70mm plastic chairs seperating.
344c4a77-4136-59d9-b8d5-9812aaf329f4 | note | Frequency - Prior to pouring concrete
6f1ecc3c-1309-5e25-a24b-4fab0c66f24a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
6fd498e0-dd39-5cb6-b1fc-cf6c52515808 | note | Records - Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.4 -
c8e99f56-9bd0-5ccc-8fc2-82eb053ed0fc | note | H
1ef8b20b-0ba0-5be8-b5cb-d8f711154344 | note | Detail - All concrete delivered to site shall have 40MPa 28 day compressive strength.
ac9eb8d2-f5fb-5c7f-8c92-8b4a32f5b31b | note | Frequency - Prior to pouring concrete
90641c57-a546-54f4-8573-14cdce4be2ad | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Concrete Delivery Dockets
b826276c-75f4-522c-bed5-cb9318c25cad | note | Conformance Criteria - Delivery Docket added to QA folder
48ffc458-5d15-522c-9410-95eed908b2eb | note | Records - Concrete Delivery Dockets
62d8de6a-b2fb-522d-9a4a-3825a8891408 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8 - Temporary Works (Formwork)
19fb0c70-de13-56b5-881c-ebf509261ae3 | note | W
4b0b7756-09f0-5a5e-9570-7dda8de66338 | note | Detail - Formwork to be set to correct line and level
235b5018-8e92-510b-bf48-bc9a225c7c22 | note | Frequency - Prior to pouring concrete
46e419be-1691-56d9-a7c8-fffa0bab293a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
618f5b3c-3620-5995-a816-a88e27392178 | note | Conformance Criteria - Concrete Inspection Record
6458be77-4888-53cd-8f00-857591f5a1b8 | note | Records - Concrete Formwork Checklist
afc49c63-875f-58fa-a70d-15d60d073cb7 | note | FH Initials - Site Engineer
e73de57b-b4c6-543a-932e-906097bc8694 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
| checkpoint | 8.1 -
b62795d2-5f19-5eb3-ba01-990f6c4142aa | note | H
7e65f452-12a5-5d4c-bd9d-562056143ad7 | note | Detail - Raised table formwork to be 75mm above existing road level and be 300mm in depth and gradients respectively of entry (1:15) and exit ramps (1:20)
89384c74-ec92-5fa2-8a60-c7c1397078b4 | note | Frequency - Prior to pouring concrete
611d3844-9b16-5174-a47c-8e0b9dc18f1f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
b33b2625-706e-5256-a533-3eb27149844b | note | Conformance Criteria - Designer to inspect formation level
acf8d60e-8452-5ce4-aed9-ff6f1f3a779f | note | Records - Site photos
a8b366d6-dc55-5068-b9d5-092edbea97f1 | note | FH Initials - Site Engineer
5dc13e63-6ba7-5f09-802b-0f9150b5720a | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8.2 -
e088c2b2-93ae-5404-8227-c0fc00a45efa | note | H
6bf786d1-f3be-59c9-9c55-fed1f7ca77a3 | note | Detail - Raised Table ramps to have 225mm depth at entry point and tie into 300mm depth to meet raised table
925d3092-880d-5e9e-9643-229fd50dd7da | note | Frequency - Prior to pouring concrete
af01d05e-ac06-5efc-98b9-9c93f364a131 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
86d13bc5-f144-5fdf-b3fd-95a183c01d56 | note | Conformance Criteria - Designer to inspect formation level
57e48085-dc26-51e8-99b8-7156bbdf8efe | note | Records - Site photos
89282ea8-5565-5d21-9443-59a39f194aab | note | FH Initials - Site Engineer
c138f05c-b530-53be-a9bd-589e920b266c | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8.3 -
658c4e45-1ae8-5f60-ba65-ad5b739bea00 | note | H
ebed6b8b-9d91-5747-8278-7c2953074c09 | note | Detail - Raised Table ramps to be 1.125m across for entry and 1.5m for departure ramp.Toe to be 500mm across for both entry and departure with 50mm asphaltic wearing course
d53c5757-d3a5-5b5b-8241-0f0a3c138763 | note | Frequency - Prior to pouring concrete
fb23081c-1f45-55e6-af23-02df0db1bfcd | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
1d153967-6f52-5523-adad-f6501c4a5c9a | note | Conformance Criteria - Designer to inspect formation level
98138558-644d-52fe-9a40-aa2f29081a69 | note | Records - Site photos
b08af23a-c1f2-5231-98d5-a797430bfabf | note | FH Initials - Site Engineer
3ee05bb4-24b3-52a8-a3da-7afc2838da01 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8.4 -
c3ec490e-e4d7-57ed-9972-c07366d35bf5 | note | H
63255b5c-d8d9-54a7-b3f6-392f9fea4c8f | note | Detail - Raised Table ramps to be 1:15 gradient for ramps at entry and exit ramps to be 1:20 relative to the road
22b523f8-1727-5bb3-85c1-e0186e428fe1 | note | Frequency - Prior to pouring concrete
18fc7162-42ce-5879-ac36-6977af3144cc | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
cbc61997-42d6-5634-8145-22519694257c | note | Conformance Criteria - Designer to inspect gradient level
15350c10-1822-53bc-b9aa-c320f697a964 | note | Records - Site photos / Concrete Formwork Checklist
4d5f8669-9fd6-5893-b615-4280b0ead012 | note | FH Initials - Site Engineer
9a7e44cb-a942-5641-b3a2-fcdce6571248 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8.5 -
0c026ec0-6032-566a-8165-d9406a28c649 | note | H
f1f0c425-7173-5b93-8ece-9d929bead5a2 | note | Detail - The Site Engineer and MSQA Engineer must sign off the formwork prior to concrete being poured
c4461c77-8bf2-5b4d-bd0a-ade97502b11d | note | Frequency - Prior to concrete pour
fe2df19e-ff74-5e46-8a56-1859e647add9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
6e7ad922-b5c2-5b3a-a37b-d95fc5dac8c7 | note | Conformance Criteria - Concrete Inspection Record
cb2384eb-3300-5704-915e-8ccc2a9d074c | note | Records - Concrete Formwork Checklist
3e09a072-0054-596a-a693-3ea8006974f6 | note | FH Initials - Site Engineer
b2d1615d-a442-51cf-8071-ca4e4ee6befa | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Reinforcing
ee7cb76e-0755-5508-aa1c-22772563fd2f | note | H
a7539c49-67f3-5e26-aeb5-98800590c9ad | note | Detail - All construction joints are to contain 2 rows of LESA dowels or similar approved dowels .Dowell system 50mm w/ Black 300*50*6mm plates @400 centres placed across the construction joint
45b5f670-6e28-50d7-a29e-8f7cf4c5cfb5 | note | Frequency - Prior to pouring concrete
71dc8be3-8949-55e9-ac63-25e50897a7d6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
a706aaef-4448-58fb-9f47-fd2f041e34d7 | note | Conformance Criteria - Concrete Inspection Record
338d6aca-1efd-5d2f-8855-cce3d267d26f | note | Records - Site photos/Concrete Formwork Checklist
d3f8b6fc-2a16-5380-b2f2-91b44895b9f9 | note | FH Initials - Site Engineer
33f82467-7e4d-5b86-9ae1-ada41f59e9a8 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10 - Concreting
4237f0ca-9fba-5299-a315-826db45fe10a | note | H
07238b6a-bbd6-58f2-a5e0-1a311dfda13a | note | Detail - The MSQA Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required
f7561ab4-76c1-522b-9ae6-8f88fdf68624 | note | Frequency - Prior to concrete pour
67694c03-e3b3-5fd7-bab1-5ef7395adb96 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
1bb43b39-4a52-58e1-9f50-b6cddb67929e | note | Conformance Criteria - Engineer will be notified via email/SMS at least 24 hours before required for inspection
6aaa7dd5-b949-5f7d-b997-a7d791d72309 | note | Records - Email / SMS
d45ff984-706a-516d-84e2-5aa0ea7d0c11 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10.1 -
08708b46-4ce6-5093-911a-3fff77e9b2bc | note | W
15392a1d-20d7-5fa0-8a57-50b73e9cb5c1 | note | Detail - Vibrator to be used throughout concrete pour
e45c2447-5d21-5b6c-9b17-355c0ff633c4 | note | Frequency - When pouring concrete
5123d0d9-b129-5ee7-8900-a0827975e273 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
c9dfdd7e-0f47-5e6b-9f12-cfd5b08e5d42 | note | Conformance Criteria - Concrete Inspection Record
f6a2731e-1b7b-5e6b-b48c-d57925ced47e | note | Records - Concrete Formwork Checklist
470562a4-ea32-518f-b87e-e9b09731e355 | note | FH Initials - Site Engineer
| checkpoint | 10.2 -
0c7364dc-4740-52af-9f38-ccc88a98a805 | note | H
b1aa4c65-59cd-502e-9d69-98ce98fed5b2 | note | Detail - Concrete surfaces shall be U5 broomed finish for ramps, and Broom finish for table top.
a3823129-0cb2-512a-a694-3c16cdbbc008 | note | Frequency - At completion of pour
cec0da1c-4f81-561c-b6d3-f83c7f7f986f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
d99d4e14-19c0-5b3a-9564-6dad85581a37 | note | Conformance Criteria - Concrete Inspection Record
5d396126-f539-5fa0-817e-282145cb57d9 | note | Records - Concrete Formwork Checklist
83566065-4aa0-5f65-9b52-90ba5b17c9e4 | note | FH Initials - Site Engineer
3f5209d6-a04d-5cb0-bcbf-2209c14746f4 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 11 - Curing
54bf2699-e56f-5300-99e3-abf4c4c44df6 | note | M
c628a77f-aac6-5149-ad95-380e0b24d733 | note | Detail - Concrete will be left for 48 hours minimum to cure before traffic is allowed on it.
185a26e4-2e29-52cf-87c5-27b1f04f9f3e | note | Frequency - Post Pour
3e775228-a562-586a-ac6d-c8cef29beb42 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Monitoring the time allowed for curing
45566ceb-329e-53c5-9e6b-8d95805d2db4 | note | Conformance Criteria - 48 hours minimum have passed
ff195f01-c20c-5007-b2ae-3a75b65d484c | note | Records - Concrete Formwork Checklist
2803c909-ed76-5088-950e-9a319f20048d | note | FH Initials - Site Engineer
| checkpoint | 12 - Remove formwork
cba53c53-3958-5503-a12b-750022c97f10 | note | W
c43720b2-1313-5970-b519-46f4375b16a5 | note | Detail - Remove formwork after 48 hours
e12a7676-81a8-56e5-8d5e-2f4f80bf32db | note | Frequency - Post Curing
ea2a5b97-3052-5f3d-a644-e6a7b3ca970c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
09a64a2b-de22-5141-b457-d6e4237c03db | note | Conformance Criteria - Concrete Inspection Record
6d195efd-4c18-5e6d-9e6b-100a4b4f454b | note | Records - Concrete Formwork Checklist
7ace8843-6191-559b-8ad6-3d9cd4a5717c | note | FH Initials - Site Engineer
| checkpoint | 13 - Asphalt- Concrete extension slab/ Toe
728b3958-9730-513e-86bf-072e0745352c | note | H
0007bfed-7a22-5dd1-8ec4-ca38c899f902 | note | Detail - Two rows of Lesa diamond placed mid depth @600 C/C along construction joint as per TDM TC003
3a1b2b50-4d59-59aa-aefe-1aea13f71797 | note | Frequency - Prior to pouring concrete
1c97043e-0b87-5dad-9f2e-7ee52fb2397f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
d191a1fc-6d3a-54f1-9f1b-0f3665f0c95a | note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
04583b29-af3e-5cd3-b68d-c47d85fb5c5d | note | Records - Site photos,delivery dockets
faecba07-e2e3-5301-b81f-e875ee02320d | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 13.1 -
4dd0113d-32b7-5bf8-af24-616ebbb4fc1b | note | H
be579026-2dbc-59a6-b588-0fa93285c761 | note | Detail - 200mm thick 40MPa Concrete with two layers of 663 mesh
f75fe17f-430e-5d4f-89b1-05988bf46faa | note | Frequency - Prior to pouring concrete
d27c2678-c1bc-566a-abde-933c21bdc8c1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
5b8f58cd-62b2-57ed-9d44-fdadb48b3f4d | note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
f9c4a930-94ff-56bb-a2d8-093b466f5b19 | note | Records - Site photos,delivery dockets
b10c4419-fddd-5c09-9622-c8f1584d4ae8 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 13.2 -
b84b0889-635f-59c4-9e9b-b65e9d687c62 | note | W
180ce1a1-f9fa-57dd-8dce-935d7fdd1ec2 | note | Detail - Tack Coat between AC and Concrete slab
811f987c-29cb-5acb-bd4e-6f4480ca5d22 | note | Frequency - Post Curing
b982c650-16ef-5e11-9ace-71dc57b459e4 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
788d8abe-28ab-572e-92e8-3c640d078b07 | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
b9fa4499-f84a-519b-ac98-e5b6cbf46a76 | note | Records - Site photos
e8a9c97b-2542-59a7-8d23-16cadb754ddf | note | FH Initials - Site Engineer
| checkpoint | 13.3 -
736ecd61-052d-537f-bdbe-f897cc973e38 | note | W
d7d6a4b6-a53b-5e9a-9160-403386cb59d0 | note | Detail - 50mm thick DG10 / Mix 7
c5fe3ecf-7b0a-504c-ad89-08cafe555091 | note | Frequency - Post Curing
ced5b99a-c3f7-5b9a-b886-5b86d237b029 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
16365f84-6ba2-5534-99ad-aef348077c03 | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
6ff5cb27-9172-5563-a314-281add39b653 | note | Records - Site photos,delivery dockets
6466cb25-b9d7-5fce-8ecc-39dc57c296b5 | note | FH Initials - Site Engineer
| checkpoint | 14 - Lot Number QA File
e542647e-5a17-5bde-aa78-d7e59362697b | note | W
6e62f79b-d4b0-5c6d-aed8-cdf6c62825d5 | note | Detail - Ensure all QA Records,site photos and incident cases (OFIs) are closed and included within QA file
f6f68ff5-c3f6-5d03-ba66-074b754b3f4c | note | Frequency - At completion of Lot
9d19ff42-9c5c-5ac1-a77d-01e4ea481410 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
3867f0ff-7ab8-58aa-848b-8e9acfbc3dc0 | note | Conformance Criteria - All QA files compiled and sumbitted to client
9b7fc674-e8dc-5429-aab9-14673b1b34e0 | note | Records - QA records
de1b14c8-618c-5638-bb2b-21fbb0d1b9a6 | note | FH Initials - Site Engineer
| checkpoint | 14.1 -
3bab4240-c0e2-5d8f-a991-34657fb8dc9a | note | W
6dd47010-c19d-5797-a343-adb8c706c5ab | note | Detail - Delivery Dockets to be included in QA file
7f1dabf3-843e-50f3-948c-a94dff54319c | note | Frequency - At completion of Lot
7f0f1af6-e4b3-5373-909f-f62dcf2eab9e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
901be100-0e14-5288-b6f9-b7a70b41052c | note | Conformance Criteria - Delivery Dockets to be included in QA file
d6dfa4e6-4e14-54c9-a1dc-3be456c0a9f6 | note | Records - QA records
55b2c9ce-9030-5a6c-b8f5-c9251c401644 | note | FH Initials - Site Engineer
| checkpoint | 15 - As-builts
645ac489-8462-5816-b897-a6644a947282 | note | H
10f5a458-1da2-5967-a35b-04a912d9ac78 | note | Detail - Red pen mark up drawings to be included in QA file
788cfc91-9402-51c0-91cb-f6699845b650 | note | Frequency - At the completion of the Lot of work
885c344d-1b68-5582-be45-7c78ef12d7ec | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
c6acc0fd-8a1f-5ae7-b29f-29d5d532fac5 | note | Records - Asbuilt Drawing
f7e536f5-ef2c-5781-87d8-2ef8dee989bf | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checklist | ITP - St Lukes Road/Morningside Drive intersection - Ducting and Traffic Signals |  | ITP - St Lukes Road/Morningside Drive intersection - Ducting and Traffic Signals | 7bb84262-77d7-4f23-aed7-583aede981cb
| checkpoint | 1 - Permits
0dbda8ec-8192-5215-913d-b2dea554d575 | note | H
b385fa9a-c611-5c5c-b79c-fdc0ae82e288 | note | Detail - Obtain Permits
68690731-2a9d-583c-9058-9ecd4043bb5e | note | Frequency - As required
78b2f275-1b97-5882-a67c-b112e9494344 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
891fc5e6-1853-5976-827c-a7bd3eff8419 | note | Conformance Criteria - Authorisation to work, dig permit and service provider permits
6a375b8d-b99e-567f-89e2-6a00bfd03e31 | note | Records - This ITP signed
fb4bec80-553f-5a97-a895-c702a37be096 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Design
02a5dd1e-c5f8-5789-8306-c77147ec4825 | note | H
aa82a5ad-8d52-5a09-80ca-b138bbcfd62e | note | Detail - Ensure that Design is approved and Drawings are of the latest revision
80293d04-49eb-503b-a9c8-abfec31e792c | note | Frequency - Prior to commencement
3f7670a4-666f-51fe-bc0b-0b92bbd68de2 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
d5d38af4-0a72-5ac4-b567-354d4a0e3057 | note | Records - Check Drawing Register
1c7ab305-0bbd-564f-9fa5-7c8eaaae2fa7 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Survey Setout
99d325ec-88b7-5599-b676-e622bec21978 | note | H
94d5caf0-824f-5fa9-9051-9ca0ef722246 | note | Detail - Setout ducting alignment and EOS FL depths. Setout and mark all known services along the cable corridor.
2abb7ac6-5030-545e-a04e-5877e6cf2bb0 | note | Frequency - Prior to commencement
b7d825d1-4b7a-5982-9db8-84c5034c3bc6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
02ca3c88-a356-5606-bd3c-f7f36a5185c2 | note | Conformance Criteria - Consistency with Drawings and Specifiactions
20355a79-bbfc-5cb7-a2e8-96ab3ca9a3cc | note | Records - Survey Records
2924250c-646e-5ac3-aae8-4e7bee3c51db | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.1 -
20325858-977a-501e-bdb4-4cd7c869b4b6 | note | H
695870cb-c805-5368-bc5a-dd1491b1682e | note | Detail - Confirm with Engineer on site the exact location of all posts, foundations, signs, cable chambers, cable ducts, loops and loop termination boxes( Toby boxes) before installation.
24fcabb1-a922-53ac-b5dd-9bcf841e6d82 | note | Frequency - Prior to commencement
c326c170-0753-5a5c-9734-2e794f23a912 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
57fda63f-1953-5796-b9df-1e45f38c2c16 | note | Conformance Criteria - Consistency with Drawings and Specifiactions
4b818b60-434a-5226-8fb2-2e655626c9e3 | note | Records - Photos / Engineers approval documentation
c871b1ee-344d-5d8e-8e62-9ce755478635 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Locate existing services by hand digging/ hydrovac
0a928b5d-3461-5110-943d-293395412c5d | note | W
faab604f-bb8c-5459-93fc-1a78b15e8efe | note | Detail - Ensure all services conflicting with the line of trench has been exposed by hand digging or hydro excavation
8b1e7543-bd00-59f5-add9-a7f307322aee | note | Frequency - Prior to Installation
84510f17-f227-5c84-8085-2ae932111367 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Potholing
9c0a1073-36b1-5418-9b8d-9f899c6caad6 | note | Conformance Criteria - All conflicts have been located and survey as built recorded
10955384-6f2b-5535-9628-09b4392bee73 | note | Records - Digging/Excavating Control Checklist
18618755-ee21-5fb0-9d15-775d5ca2535b | note | FH Initials - Site Engineer
| checkpoint | 5 - Material Compliance
53708f7d-4c93-526c-bd4b-e78dd708ad4a | note | H
acbd41b5-92b3-5b25-b911-4f5b6d7f02dd | note | Detail - Ensure duct pipes and poles are as per drawings and specification
91defa86-d48c-5068-bd74-03d6956850d6 | note | Frequency - Upon delivery to site
73530c3a-1b22-59c0-afca-d04eef59c057 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure delivery docket matches materials
d5290b6c-0fde-5bb6-b931-9a88ba743b25 | note | Records - Delivery Docket
d00ed5ee-5442-59fc-a8d7-16e61f8f78da | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.1 -
441083b6-5402-59f4-9a53-106b2a1bbbd2 | note | H
e9447a42-5991-5d6d-8008-2bcfc3395bef | note | Detail - Ensure all concrete used is 20MPa mix
e2726646-bafb-5014-a763-8dba6d96b7fe | note | Frequency - Upon delivery to site
81bcfe7a-3622-5812-beaa-b1134903bfb6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure delivery docket matches materials
77c52bc8-229e-5ef0-8f59-7a5127b261ed | note | Records - Delivery Docket
4075b066-21de-5167-b8a7-483ff51e4d31 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Trenching
97233f15-208a-5f50-86a9-6f76d73dc11f | note | H
6e3e5e2b-515b-5eb9-8865-86b11a9c42cd | note | Detail - Inspect trench profile to ensure walls vertical, widths is 300mm max (single ducts). Ensure trench depth is sufficient to provide 600mm cover to duct when under berm (900mm cover when under road crossing)
b0a1b664-1148-5f04-ac37-4d5851c033f9 | note | Frequency - 10m Intervals
dffd4d4a-63ae-5b43-ba2a-a97f5eef3fe8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
10498978-e958-545a-9d14-beb51fe2bb6b | note | Conformance Criteria - Consistency with Drawings and Specifiactions
c5df66b6-2f3e-5594-822d-848ecb1acaf7 | note | Records - Photos
6e48c9b9-d33a-5ab8-8560-aa91a77ba4a8 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.1 -
0ecd6be6-f6bf-51c0-9dc8-56934f33c95e | note | H
8c0324ad-468f-5c23-adab-314f8c057828 | note | Detail - Ensure trench is cut in a manner that will ensure ducts are layed at correct depths,grades and alignment as per design dwgs
742c37d1-786f-5a8e-bbb2-4e3ffde4a6e5 | note | Frequency - 10m Intervals
edc45adb-b844-5732-82e6-c62b3247e0e0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
e3556d84-cbdc-5a9e-9f02-83dec1d281d5 | note | Conformance Criteria - Ensure trench alignment and levels match the design drawings
2aa853bc-4c50-5a53-870a-b3240425f69e | note | Records - Dipsheet & Photos
9dfbb667-d2cd-5327-8ae7-7fa08f14af8f | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Duct Installation
c788c966-6897-522c-8575-7b1921841d07 | note | W
d9480362-043e-5a8a-8457-9deb67bd2da8 | note | Detail - Place proposed ducts in locations where required. Draw wire tapes required and cap ducts where required to prevent ingress of material into duct.
16c5f36e-c8fa-56cd-b456-adb6c934161b | note | Frequency - Prior to Installation
4bcc660d-a596-590a-ac56-d8edda325a9f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
42436d63-791b-59da-aea3-6380ebd338b2 | note | Conformance Criteria - Consistency with Drawings and Specifiactions
d1a03167-e434-537f-91e0-e8c9f9bdc4c3 | note | Records - Photos
6e6ba1e1-6001-555b-95b3-5a6e9e91ba7b | note | FH Initials - Site Engineer
| checkpoint | 7.1 -
1fa27fe2-7669-50c5-ad73-4ce9595b7d98 | note | H
8455aec0-a705-50f3-a7f6-5f43783b29eb | note | Detail - Ensure minimum spacing of ducts requirements are met as per design dwgs and ATCop min spacing tables
037b6608-45b9-5844-8749-d97a9c387da6 | note | Frequency - 10m Intervals
26678e06-1e3e-50ba-9147-8b27688b0f58 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
e136b7f4-b080-55bb-8f62-d8b56fe1b138 | note | Conformance Criteria - Consistency with Drawings and Specifiactions
1db0b8a1-3ab5-575c-9eb0-7ff6cdf4b5cc | note | Records - Photos
d00afd94-d63f-5482-bc47-bea95e19d1f5 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.2 -
6ad6f9c6-f2dd-5c2e-98ac-75e20eafc936 | note | H
01afd926-d1be-5fdc-84c1-3caf89939a98 | note | Detail - Asbuilt Survey
cad4082c-81f4-56ec-81ea-8b2a4ef8b50f | note | Frequency - 20m Intervals
c63976c1-f2f8-5e7e-8ff7-b500e89c9a0b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
9ea0b595-c52c-521f-8c3e-1a1bb1ce9c9e | note | Conformance Criteria - Consistency with Drawings and Specifiactions
2e2960ed-5a66-5656-b5f9-8de97971e125 | note | Records - Survey Records
189b5593-1207-5ceb-93d3-88063dafdcb0 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8 - Bedding
c5c740b5-e620-5234-bfa8-28707170c705 | note | H
be263c04-482e-5896-b91d-fc9122ae790e | note | Detail - Lay min. 150mm gap20 or finer for bedding and haunching
045bc1fa-3977-530f-9225-662f1b7ba8d8 | note | Frequency - 10m Intervals
66bc4061-758b-5391-9ceb-d98da839ea9f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
f88fc1a8-bc4c-5865-bd21-c5c461111724 | note | Conformance Criteria - Consistency with Drawings and Specifiactions
cf11a8d2-c31b-57d6-b8ba-dec15bd2cf5e | note | Records - Photos
d189f4ac-6313-5f2b-89ef-ff464856595b | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Warning Tape
28403db6-f2f5-5e3d-86a3-035fdb55ef13 | note | H
4326c4df-9f80-5971-8dac-12a1a8d2b2f2 | note | Detail - Ensure warning tape gets installed 300mm above duct pipe for all new ducting lines.
fc432140-7c43-5604-a166-746b565b28a1 | note | Frequency - 10m Intervals
0426047f-bbe0-513c-a339-c8e110ab1a99 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
6020c0e9-4ad8-5bf6-9544-279b9db6038a | note | Conformance Criteria - Consistency with Drawings and Specifiactions
4b0ef066-a9d5-5c4c-ab8e-2bda22065ddd | note | Records - Photos
7b0bc941-5255-5bda-ac20-efda5affa614 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10 - Traffic signal pole erection
ac6fc405-2865-5d5d-8182-1671017bfb39 | note | H
3b4ad816-7431-54d2-a5b3-92b3e4d85762 | note | Detail - Ensure Design engineer as inspected pole locations prior to proceeding
5ff7ec55-bc40-568f-b7a9-d0f37ac8c2ee | note | Frequency - Per pole
c38cd927-0563-5bf8-b415-944188af6241 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
6a45c387-1ca8-588e-ad36-fa213d1abb07 | note | Conformance Criteria - Sign off by design engineer
60283c80-0612-5945-be7d-7ffabec025f3 | note | Records - Engineer sign off
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10.1 -
9f96e30f-7133-5c2a-997f-27e77de316c2 | note | H
e3cfc64c-b759-556a-ad8a-e8ce7674f335 | note | Detail - Ensure Pot hole is as per design with required depths and widths
7a35eb44-0d81-541d-be9c-a6630cd77f4a | note | Frequency - Per pole
1d0bfd7b-b75b-5ca4-8f65-80ad0530b7ba | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
5db37a51-b02d-5d6c-b051-671f6836dbf0 | note | Conformance Criteria - Consistency with Drawings and Specifiactions
433837d3-8c12-5287-9cb8-e93b0b7ac5d9 | note | Records - Dipsheet & Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10.2 -
316e6476-a885-5aa7-bab9-5076466ca6e2 | note | H
c49c61a7-3640-5d20-ba2e-0d02aa657d59 | note | Detail - Ensure Poles are plumb and within design tolerances
e3d3f04b-c3a2-51c2-9f8e-2975e197a6bf | note | Frequency - Per pole
fd72661f-b5eb-57d6-9a8f-70a05e113a22 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
57901caf-e71a-508b-a57a-9a403798ba6a | note | Conformance Criteria - Consistency with Drawings and Specifiactions
1b0f928e-1dd0-5220-b295-91b2db20bb5f | note | Records - Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 11 - As-builts & C&I Diagram
45f04c27-e8fd-5a8e-a64f-26ff8f5f7972 | note | H
2dc01e22-3aa3-5c99-a5ba-6fc1960192e9 | note | Detail - As-built as per ATOC requirements
8bc56203-117e-511a-a888-3b5e975eaa4f | note | Frequency - At the completion of the Lot of work
8c27b4a1-0b65-5169-845b-781fb167bf5c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
abbd5240-3101-5870-bae7-95897eebc7a5 | note | Conformance Criteria - As-built as per ATOC requirements
19d8f7d3-36a0-5e7d-a92a-5f29bf052e6d | note | Records - Asbuilt Drawing
c66c393e-e81c-5de1-b3b2-fecca0254e5d | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Final Inspection
9fac1df9-b2f9-5f4f-b5a4-1f98694af7ab | textbox | Comments:
9421a839-f1b0-54be-bc74-97d37fa7c410 | textbox | Drawings used for Construction incl. Rev numbers:
96abca97-e999-5cd1-8923-a7820740b09a | textbox | Reference Documentation (Notices/OFIs etc):
| checkpoint | QA Compiled By :
5d3a407e-bc23-5b3e-a620-b53a7af6986d | textbox | Name:
389ef883-2d6d-5325-88e9-20e2aa49f3af | textbox | Date Completed:
| signoff | Sign ITP
| checkpoint | QA checked By Project manager
4837ea63-d4d1-5053-942b-ba1f12497949 | textbox | Name:
b029d27d-d608-5cdc-a6bd-c428e0b637d7 | textbox | Date Completed:
| signoff | Sign ITP
| checkpoint | QA checked By Contract Manager:
b803dfe0-f7be-552f-936d-623ce882784f | textbox | Name:
57a56fc1-ad6b-57d5-8cf5-b31cea92f292 | textbox | Date Completed:
| signoff | Sign ITP
| checkpoint | Accepted By Design/AT Engineer:
e8b948ab-81ab-5927-b527-831cb17e8b5f | textbox | Name:
4bf0dfa5-7030-5f97-b0ec-109ae6a6aae6 | textbox | Date Completed:
| signoff | Sign ITP
| checklist | ITP - St Lukes Road/Morningside Drive intersection - Enabling Works |  | ITP - St Lukes Road/Morningside Drive intersection - Enabling Works | 1460a8bf-f3e5-4a2e-bfb1-541a875808c4
| section | Site Set Out
| checkpoint | 1 - Site Set out
3fa204e0-6c56-5877-9400-6981f4e56ed7 | note | VERIFICATION ACTIVITY - Surveyor
fa2cf24b-2206-50a9-854d-0355d47b59b1 | note | METHODS OR REFERENCE - Surveyor
a4ee13bf-c54e-5c91-a93c-2b959c623d12 | note | FREQUENCY - Everysite
3c23fe9a-d52f-5a1e-b9ef-b1a8983317be | note | ACCEPTANCE CRITERIA - Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criterea is acceptable.
c6d039fc-799f-542f-b091-d4375d30bfce | note | Hold Point - Mandatory HOLD POINT -
e30ab4f6-b762-5b2a-96aa-b9a4fc408d45 | note | Records - Onsite records/photos
e62e4119-5a10-5238-a3cb-9283616c3785 | note | Onsite Responsibility - Site Engineer
| section | Materials
| checkpoint | 2 - Kerb & Channel
5f053929-d24b-5c23-b6ca-ebb8fda2a9ed | note | VERIFICATION ACTIVITY - QA FORM
d13d10c2-6076-5378-8a12-6da46bf23287 | note | METHODS OR REFERENCE - TDM Technical Standards - KC0001
a77781df-f09f-57e4-87c8-320b79f86084 | note | FREQUENCY - Everysite
f45e0929-bfd6-569f-9122-e52f415ce019 | note | ACCEPTANCE CRITERIA - Kerb & Channel to be laid using precast hand-laid. On compacted GAP40. Concrete 20MPa @28 Days on 100mm GAP40
abb888ef-42ea-5756-8d4a-55a28d1cba35 | note | Hold Point - Inprocess Inspection - Engineer to check the Stringline Set out
cff46914-789e-5f56-9fde-a43d5d31606e | note | Records - FH concrete QA sheet, photos. Concrete Plant Docket
2f1c9aa4-e308-5a65-aa6f-b5386d987d22 | note | Onsite Responsibility - Site Engineer
| checkpoint | 3 - Channel Level
9eec518c-b38e-59f8-b8fe-c416b4611c85 | note | VERIFICATION ACTIVITY - QA FORM
0284548a-0d7a-5857-9d25-92aee3802de5 | note | METHODS OR REFERENCE - TDM Technical Standards - KC0001
22bf52cc-f90c-5a06-b72a-15d27f56c1c2 | note | FREQUENCY - Everysite
6e330781-23a3-5294-8d36-eab45ceac98c | note | ACCEPTANCE CRITERIA - Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
7c15a896-45b3-5a37-acdb-675d497fa611 | note | Hold Point - Inprocess Inspection
2668baf6-b154-58ad-9727-e134f145e9ba | note | Records - FH concrete QA sheet, Photos
70aa9bdd-6dbf-53d5-8c8c-488da2353a6d | note | Onsite Responsibility - Site Engineer
| section | CIVIL WORKS
| checkpoint | 4 - Concrete Footpaths and Pram Crossings
864a98f9-462c-5bac-8e44-89672107edae | note | VERIFICATION ACTIVITY - QA FORM
9f389bbb-0b0d-5491-9ab2-212d3af4f9a6 | note | METHODS OR REFERENCE - TDM Technical Standards - FP0001
97385b6f-adfd-564d-8764-2d3a3d1b9992 | note | FREQUENCY - 10m Intervals
948ae407-5a12-5a4f-a93c-eb0d9d7fe778 | note | ACCEPTANCE CRITERIA - Basecourse - 100mm min. thickness GAP40 Clegg CIV > 12 Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish Expansion Joint cut for every 3m interval Pram crossing to have 600mm flare from kerb; Minmum 1.5m deep and wide.
b413eff3-2d3f-5de0-bc7d-d12af3995c57 | note | Hold Point - Inprocess Inspection
f8930dd0-59b0-5f00-9258-fb4f29d2c49a | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
3c199721-d082-59ca-9944-f5fc316fedde | note | Onsite Responsibility - Site Engineer
| checkpoint | 5 - Tactiles
163d1000-bc8f-52a7-be71-d8ba917be288 | note | METHODS OR REFERENCE - TDM Technical Standards - FP0010
ea88d39f-6eb3-548f-ac4a-b86685337f3c | note | FREQUENCY - Each PX
932b3af6-09a5-5e66-9ad9-f196f335fa07 | note | ACCEPTANCE CRITERIA - Tile set out position to be agreed with ATOC and Engineer. Warning TGSI tiles should have 100mm concrete slab underneath
5fcffc9c-1bad-5580-a967-7b491af69e47 | note | Hold Point - Inprocess Inspection, Measurement
2fe6e17d-e6f3-5376-9d54-d5a52a48a4a1 | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
7b434978-2a96-5b5a-9fbc-ecde381d6f05 | note | Onsite Responsibility - Site Engineer
| checkpoint | 5.1 -
776acee2-9c7c-555a-9fe7-926d2eeabd47 | note | VERIFICATION ACTIVITY - Visual
9b3c791f-3755-5892-8a57-9c81578f3e3c | note | METHODS OR REFERENCE - NZTA RTS Guidelines for facilities for blind and vision impared pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
c5620cce-4395-5257-8098-38db602e0baf | note | FREQUENCY - Everysite
96b8d901-cf51-53c1-81db-74379cf5062d | note | ACCEPTANCE CRITERIA - Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
0a54a911-3c20-5ebc-8350-b00df1967d2e | note | Hold Point - Inprocess Inspection
a68da3ad-5f9a-585a-a60d-c7becfc346dc | note | Records - Photos
cd539025-4d05-5062-9959-c32691c0e1c3 | note | Onsite Responsibility - Site Engineer
| checkpoint | 5.2 -
88e328ab-81ee-5b9b-adaf-36b9694c3fde | note | METHODS OR REFERENCE - AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
6f74d62d-d13e-5c4f-8e02-1472d5094404 | note | FREQUENCY - Everysite
4408617a-d616-590a-80d4-8390714a98a4 | note | ACCEPTANCE CRITERIA - Edge of warning indicators to set back 300mm from the face of the kerb or lane.
28e8d335-f290-506b-8110-4480f9785656 | note | Hold Point - Inprocess Inspection
6fd984a6-bf6f-5e28-9516-b8619cc48841 | note | Records - Photos
ce649c9e-3345-5843-b837-5b479c2fd783 | note | Onsite Responsibility - Site Engineer
| checkpoint | 5.3 -
8f9b4420-26fc-5f15-b3cb-84e8615feaa0 | note | METHODS OR REFERENCE - AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
43adbe42-d996-5289-8ab7-6beac5792a96 | note | FREQUENCY - Everysite
98acf081-63d6-5d2d-a43e-81d8b11e4841 | note | ACCEPTANCE CRITERIA - TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
e3ca0919-97d6-5680-a815-486641d28d19 | note | Hold Point - Inprocess Inspection
9807626f-b33a-5a3d-94d8-083a631dba01 | note | Records - Materials Dockets
fac150d0-95fa-5726-9896-375842d5c91c | note | Onsite Responsibility - Site Engineer
| section | 6
| checkpoint | 7 - As built information
5d385da7-98ca-5c6b-9933-3adb3f05a002 | note | VERIFICATION ACTIVITY - RAMM DATA SHEET
e6b4bced-337d-5015-95d4-fd4527ac114e | note | FREQUENCY - Every Site
03f84d4f-faff-5484-9c44-499b5d27b8d1 | note | ACCEPTANCE CRITERIA - As built drawings and Ramm Sheets Completed
0b0922af-956c-52b6-88f1-dc23c3323298 | note | Hold Point - In Process Inspection
2ff9ae31-3d95-5960-a8c4-051d971f65d0 | note | Records - Asbuilt records
0237d10f-c05c-55b6-beb4-2d8bca9c88b5 | note | Onsite Responsibility - Supervisor and Engineer
| checklist | ITP - St Lukes Road/Morningside Drive intersection - Pavement |  | ITP - St Lukes Road/Morningside Drive intersection - Pavement | 9e03a0ba-1bce-444d-8169-d1e6269bbf49
| section | Precom
| checkpoint | 1 - Permits & Services
a547c869-ceb8-542e-9edf-c0d7ed364856 | note | H
dc480b7e-b99a-5963-a02a-b5f91eaaae7a | note | Detail - Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
681346b3-043d-5396-b56f-b3473eba2002 | note | Frequency - Prior to any construction commencing
cc359c74-6ea6-50cc-bdb0-db6a42a4ab16 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
58cf89eb-2c11-5243-a61d-bfbb337f556a | note | Conformance Criteria - Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority
09590a3b-fa80-596d-a1d7-6e2dae62aa83 | note | Records - Permit attached or permit number noted.
e537a223-010e-5140-9da8-a1e78ebc90d5 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.1 -
88b44506-5613-581b-97a3-6216f7ed0642 | note | H
8f30a418-1fc6-59b5-bbc0-2b50ef72ed42 | note | Detail - Locate and mark out all existing services
a5ef34af-37f2-53d9-944a-678627a17b2e | note | Frequency - Prior to any construction commencing
93cfede8-3a5d-59a6-b7d4-b8056c994f9b | note | Conformance Criteria - B4u dig procedure - follow utility protocols
6f211677-54d6-5fc0-9ae7-52f817a4e67f | note | Records - B4u dig plans
be404e9c-1fb7-5e23-b454-016b251ceec0 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.2 -
076db791-04ab-5fa5-bbbb-3c8ae18f7887 | note | H
45ac6910-2532-5000-b721-ac49d289fb2f | note | Detail - Approved TMP
745c753d-ef27-5086-9022-0b286df9d2d1 | note | Frequency - Prior to any construction commencing
b5987be0-8a76-53df-b85a-9cb93290954d | note | Conformance Criteria - Approved TMP and WAP onsite befor establishing traffic management
fb9e5311-4dc8-58a3-a792-b3bf16d2f632 | note | Records - TMP Plans
391bd7d2-ff6f-5ea4-886b-d001c75014a6 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Pre-Construction Sign Offs
5d874ee6-a728-530c-85aa-91fe5b9c2c9b | note | H
675276f7-766e-5743-bb09-8f062a2be5ac | note | Detail - Sub-Contract and Supplier Agreements
0a826bf0-5358-5c25-a5e0-96ce267dd5ba | note | Frequency - Prior to commencement.
5a0c6ce0-82ce-523a-b02a-27cce1774fa6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
c2e1ab0a-b4b3-542a-b37d-0912522951d4 | note | Conformance Criteria - Sub-Contract and Supplier Agreements to be agreed and signed
b168b648-2456-524b-9776-ce6c09d8e4f2 | note | Records - Subcontract and Supplier Agreements
98e15ee1-4260-55fc-856d-83b5d0b72c2e | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Design
e8747c0b-f85a-5039-bce3-60fde721f191 | note | H
1cb99e0e-66c7-56ac-be04-4fbe72ec45ba | note | Detail - Design is approved and Drawings are of the latest revision.
f24f5c0f-144f-57b9-a0d8-31cd761b7ebb | note | Frequency - Prior to commencement.
bb4e2128-5be0-58ff-966b-c39be4614acd | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
2815ce56-72a6-5e6a-9a6f-743abce12dff | note | Conformance Criteria - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
2114bbec-1442-540d-8b75-6a07377ace68 | note | Records - Drawing Register.
36ab87ce-3ca4-5fa9-8802-7f548e3338ef | note | FH Initials - Site Engineer
38ff6649-e6f3-5120-8ac6-fdb4e011c817 | note | Design Engineer Initials - Engineers Rep.
| signoff | AUTHORITY HOLDPOINT
| section | SAC Pavement & Surfacing
| checkpoint | 4 - Bitumen
4242ce10-a054-5d14-9ca5-729ac11b8879 | note | H
4e468300-c7ae-5e87-822d-84b7b86f0127 | note | Detail - NZTA M/1
87ecb1ca-12a6-520f-99e5-9dc7b17f70af | note | Frequency - Passing all tests listed in Table 1 of NZTA M/1
e1dcaa23-fb4b-531c-8eab-50fd539d0996 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
f3db14b1-57bc-58d0-9a34-f35ad83c6093 | note | Conformance Criteria - Passing all tests listed in Table 1 of NZTA M/1
d8aceb28-de29-5eeb-9577-86b561f310d8 | note | Records - IANZ Lab results
f89b700d-cb0f-5867-9ed9-e59fe477b71a | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Asphalt Mix Design
20de2d57-7b10-5de0-8a7d-6f726a04db26 | note | H
d16d7cd4-df14-5091-938d-d3bcb3b075e3 | note | Detail - JMF approved
d056816a-cc32-57f5-9464-a339cf1b2d8d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
b9fa35c7-47ba-5885-afbf-42984e0ef2a3 | note | Conformance Criteria - AUSTROADS
4d7f9ad0-efe2-58d5-922e-d65a9031fdb4 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Production Tests
4c2426f2-e8bf-5e0e-beaf-c629002f9261 | note | M
1c6f0ea0-03e9-5c99-b28d-355de3132b04 | note | Detail - NAS 2004 & TNZ sup to NAS 2006 TNZ P/9P (M/10 Table 5.1)/
38772f34-8d43-586c-bf09-1b131a17ad7d | note | Frequency - 1 set every 300t
37f82546-0958-5a6d-ba3f-047312842f95 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
ea1ddd11-3f99-5a07-981f-31a99d9af8f7 | note | Conformance Criteria - NAS 2004 & TNZ sup to NAS 2006 TNZ P/9P or NZTA M/10 - Grading, Binder content, Max Density, Temprature
2748c3a4-c90b-5b3b-8d03-16b60d624c5d | note | Records - IANZ Lab results
610f0729-db76-5c6f-b48f-b0ed3144cb6c | note | FH Initials - Site Engineer
| checkpoint | 7 - Check Weather Reports
7f4469b9-32fb-52e8-bf6e-a0e46593ddbe | note | W
4ea8865f-77fd-574e-b0b4-408bfc05a723 | note | Detail - No fog, rain or wet surface. Base temp greater or equal to 7 deg celcius
aa63bfa6-adf5-508e-9819-0e17cbb6507b | note | Frequency - Weather call the day before
907949a0-89cb-57d1-8f83-58f55b4031bd | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
5eb42e2d-8a7c-55a4-a0f4-468d7d935407 | note | Conformance Criteria - Forecast and thermometer
1ccb75cc-8694-52fd-9d96-e2742242f405 | note | Records - Radar and Asphalt QA
e29270eb-b9b5-52bc-ae4d-c192ada7cb65 | note | FH Initials - Site Engineer
2792df9b-3d8e-584e-a4c1-a879cb8c624e | note | Design Engineer Initials - Design Engineer
| checkpoint | 9 - Tack Coat
4b453fc3-0edc-531a-b939-c709fe0a1bcb | note | M
30161253-a269-5f93-8da9-384641f8c229 | note | Detail - Minimum residual binder application of 0.3l/m2
c7984740-7b1d-5647-bfaf-12bbe2ca7569 | note | Frequency - Each Run
7a3910d3-a0d1-5bd4-a90a-e49b04453f72 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing & Visual
4e3583ef-d0e1-5b1c-a990-9c9e278cc4ce | note | Conformance Criteria - Each spray of bitumen
409ee545-cb7a-511c-9ff1-5da2207225be | note | Records - Asphalt QA
56b36e0f-268f-5e35-906f-d9deee90ef3b | note | FH Initials - Site Engineer
| checkpoint | 10 - Construct 70mm AC14
d5e597bf-a946-5555-b452-328c0b2b5f9a | note | M
975d3ae3-e586-540d-b195-76ce37dc0300 | note | Detail - NZTA M/10 NDM and Stringline
8cd26b3c-f6fd-58a2-87ab-f45bd3a743db | note | Frequency - Each Run
22e0b6f8-ffd0-5683-a04a-1b1533dbd481 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
f4ef0af4-6f0d-5dbd-825f-4882042807e6 | note | Conformance Criteria - Construct 55mm AC14, Depth check and Stringline check
484489bb-3ca2-5b1c-9c66-9a1e97d23301 | note | Records - Asphalt QA
9239ae94-24bc-5f80-ad10-668a54f35bc4 | note | FH Initials - Site Engineer
| checkpoint | 11 - Construct 70mm AC14
35f70a70-b427-52a0-95dc-c6a9cf6d0cd0 | note | M
f7afbc3b-5019-51b1-8915-329c88dfaca8 | note | Detail - NZTA M/10 NDM and Stringline
3e880c48-cbc3-5af4-970e-72861617e426 | note | Frequency - Each Run
433a936a-dfac-5565-85fe-0acc037c8b66 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
abb33e3e-f185-5283-9418-86b9a69123f0 | note | Conformance Criteria - Construct 55mm AC14, Paving and compaction using roller. Well compacted to avoid air voids.
13993704-ab14-5c97-8dc8-08ce86bf42cc | note | Records - Asphalt QA
bada7d06-c4b9-5975-b00b-212ea7baa81c | note | FH Initials - Site Engineer
| checkpoint | 17 - Surface Finish - 3mm Calcined Bauxite
aafdd697-bd49-5084-95c3-d12a30b1155e | note | W
0a6787f7-f33a-54ad-b4cc-2641c35fa83f | note | Detail - TNZ P/9P
0f91cb44-986d-5dbf-9abd-b5810f50ec83 | note | Frequency - Each Lot
d3f691ce-de14-541b-bc1d-af2eba6fdb2a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
dbb0a957-e55c-50a3-a465-2a56761c5da5 | note | Conformance Criteria - Inspection: Uniform texture, no roller marks, no bleeding, cracking or shoving, no crushing of the aggregate
7a9dd9af-1b77-5bd6-81ba-dd27a0e62430 | note | Records - Photos
8d10667e-c3d3-5292-85ab-09d86aa9f916 | note | FH Initials - Site Engineer
| checkpoint | 18 - Reinstatement of Linemarking and RRPM's
48aa1e25-2713-5e5c-abb0-dbf4cfdf2dff | note | M
2bce6e8b-f6c0-5fdc-8ac2-6902bbc0483c | note | Detail - NZTA M7 approved (Class B or C as required for anticipated traffic level)
4b2f4a1a-d99f-52bf-9b4b-3e5f96aae92f | note | Frequency - Every site
c95738cb-2a37-5a9e-8df1-9e579d6e30cc | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
5aa6c52a-c929-50c5-afdc-5cf6f28dbe2c | note | Conformance Criteria - *Carried out within 12 hours of each shift completed and as per the existing markings * Suitable Traffic Control to remain in place until pavement markings have been reinstated
17b5dac9-d3a8-5c98-9347-0530e6eac927 | note | Records - Photos
4e755823-1e2d-5a7c-8c0a-87707ff6605e | note | FH Initials - Site Engineer
| checkpoint | Final Inspection
75b69a99-87eb-5963-8437-19ee5652aeb2 | textbox | Comments:
| checkpoint | QA checked By Quality Manager:
8f8e6c32-0169-575d-a9e2-23b038112694 | textbox | Name:
b5e8b4b2-3c4a-5eb1-a6e7-f779e52c37cf | textbox | Date Completed:
| signoff | Sign ITP
| checkpoint | Accepted By Engineers Rep:
70cbfec6-2158-5867-a0c9-b2469ff4cec2 | textbox | Name:
16948960-0071-5bd5-a54d-6047294a3c76 | textbox | Date Completed:
| signoff | Sign ITP
| checklist | ITP - St Lukes Road/Morningside Drive intersection - Signage |  | ITP - St Lukes Road/Morningside Drive intersection - Signage | d23c3f41-5ebf-4e92-bdcf-0cfbd2cbcb58
| section | Site Set Out
| checkpoint | 1 - Site Set out
6c30b96f-cc76-519f-939e-65b0f3e5c4cd | note | VERIFICATION ACTIVITY - Surveyor
9b419a34-fba2-5517-9907-219ca93c82d5 | note | METHODS OR REFERENCE - Surveyor
e42cb435-a1c6-5350-83ac-6fb6f0ad65c8 | note | FREQUENCY - Everysite
47ad77de-9b70-5d3a-b658-18efd2884a3a | note | ACCEPTANCE CRITERIA - Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable. Alternatively like for like
6211c931-97fe-5441-bfaf-5c1b4f077a32 | note | Hold Point - Mandatory HOLD POINT -
002256ce-4831-54fb-b1dd-2c9da066d919 | note | Records - Survey Receipt
c8d7f9d8-518c-5ffc-9a43-cbdbf125f219 | note | Onsite Responsibility - Site Engineer
| section | Materials
| checkpoint | 2 - Signs/Belisha Disk
8cdd2313-0161-59fe-8093-052cb1f5301b | note | VERIFICATION ACTIVITY - QA FORM
c4d84a2e-15fb-54af-96db-7c1833ed6265 | note | METHODS OR REFERENCE - TDM Technical Standards
37345873-2bc6-59a7-9035-907fa0413645 | note | FREQUENCY - Every site
0521424b-fb14-5431-9e1a-1152938aef17 | note | ACCEPTANCE CRITERIA - All signs to looking in excellent condition. Signs to have good reflection and visibility. NO scratches or markings. All signs to match with construction drawings provided by designers.
83748288-3989-5fa1-9833-c04d82a14bd4 | note | Hold Point - Inprocess Inspection
42e796ce-dcac-528c-a7ae-e3a1b33be1b9 | note | Records - Dockets/Photos
29acf428-061c-5156-858f-c6de95849ec0 | note | Onsite Responsibility - Site Engineer
| checkpoint | 3 - Pole, Impact recovery post and Ground Socket
296976d6-d5e8-595d-b5b2-50dc4ffee59d | note | VERIFICATION ACTIVITY - QA FORM
8d6137a6-185b-5522-90b1-9d740df4acef | note | METHODS OR REFERENCE - TDM Technical Standards
1e728bde-734e-5710-b930-078fe7bef29a | note | FREQUENCY - Every site
e3871b77-d62a-5d88-bc18-b4eecb2fbd73 | note | ACCEPTANCE CRITERIA - Check for underground service before installtion. All poles and post to be looking in excellent conditon with end caps - 3m long. Ground socket to be 60mm dia, 600mm deep with grouted screw or pins. For Black and white pole 76mm dia and 600mm deep
3447d9bb-043b-5e28-ba49-617582a2cf01 | note | Hold Point - Inprocess Inspection
7ad56af7-7ec7-551e-b0f8-302e60ead007 | note | Records - Dockets/Photos
c700c196-3d59-5e66-b19d-76d5f1a8eadf | note | Onsite Responsibility - Site Engineer
| section | Construction
| checkpoint | 4a - Ground Socket
0f6392cf-8473-5e9f-b5d8-af6217ccbc09 | note | VERIFICATION ACTIVITY - QA FORM
510b353f-bdbc-531f-a96f-e8235d22b0af | note | METHODS OR REFERENCE - TDM Technical Standards
4798ef22-c4b9-5401-965b-d64985b2e237 | note | FREQUENCY - Each Socket
983488b5-4601-5662-88d7-6e4fd9b69540 | note | ACCEPTANCE CRITERIA - The dug out hole to be 300mm wide and 600mm deep. 20Mpa concrete with 50mm cover at bottom to be used for installing socket. The sockets to have 50mm reveal at top and smooth finish of concrete around the socket.
b7c63dba-23fa-552c-84fb-8fd9628a1ae6 | note | Hold Point - Inprocess Inspection
84a50fb8-bc2a-520c-8634-3ccc1a92b795 | note | Records - Dockets/Photos with tape measurement
1e4e988f-b75d-581c-a865-2ededf737d06 | note | Onsite Responsibility - Site Engineer
| checkpoint | 4b - Pole and Impact recovery post
20aeae10-a04e-5e10-b7f3-8107e26de1d6 | note | VERIFICATION ACTIVITY - QA FORM
b9e329cc-5f86-563d-92d2-afa297d06b34 | note | METHODS OR REFERENCE - TDM Technical Standards
f93094dd-b717-5876-b0b6-5247a5bfbc8c | note | FREQUENCY - Each Post or pole
f47116f7-d0cb-5020-a94a-bb16a528f1c3 | note | ACCEPTANCE CRITERIA - All poles to inserted into the socket after the concrete curing. And, the screw or pins to be used to prevent thr pole rotation. The impact recovery post installed on the island infill surface after curing period by drilling and using Dyna bolts. The bolts are tightned sufficent to prevent rotation
9de63f0b-21f4-58c8-9c65-1cc2c6283a2e | note | Hold Point - Inprocess Inspection
049bb299-122d-5d4f-ab4a-e72a958499f8 | note | Records - Dockets/Photos
926f7564-5b2c-5121-889a-43f1bfac7dca | note | Onsite Responsibility - Site Engineer
| checkpoint | 5 - Signs/Belisha Disk
b7d83355-5457-53f3-8c1d-2bdbf85d9f5e | note | VERIFICATION ACTIVITY - QA FORM
ba49d362-fa68-5c4f-b490-69e62068626b | note | METHODS OR REFERENCE - TDM Technical Standards
0e6081a6-2ba4-560f-8509-0b50b7d8c90b | note | FREQUENCY - Each Sign
d56be1eb-edab-58a5-b197-ab34849ca520 | note | ACCEPTANCE CRITERIA - All the sign/Belisha disk to be fixed with the pole or post with ARC brackets and tightened adequately.
603fa05e-bd93-502c-8827-857da99065be | note | Hold Point - Inprocess Inspection
a9e43cdd-8af0-5735-a2c5-15c16b55eb9d | note | Records - Dockets/Photos
5add1126-f2fc-5e15-a157-0fc0f2742caf | note | Onsite Responsibility - Site Engineer
| section | Asbuilts
| checkpoint | 6 - As built information
99a91e13-8947-5a23-b685-0c676da900d3 | note | VERIFICATION ACTIVITY - RAMM DATA SHEET
fa120b3c-bf78-5142-a3bb-ca4abf97d1dd | note | FREQUENCY - Every Site
ade2b428-fa03-5ffe-a873-8e2f73ed2d8e | note | ACCEPTANCE CRITERIA - As built drawings and Ramm Sheets Completed
9d1982a3-8173-5079-a968-b305c1b1fe4f | note | Hold Point - In Process Inspection
4421d5e1-b755-5c41-9c17-9996a259cca1 | note | Records - Asbuilt records
bc715876-077a-5c0e-99f4-657ed47aff0d | note | Onsite Responsibility - Supervisor and Engineer
| checklist | ITP - St Lukes Road/Morningside Drive intersection - Traffic Islands |  | ITP - St Lukes Road/Morningside Drive intersection - Traffic Islands | 95a5edbe-bdc8-4d84-af64-42178e0cf019
| section | Materials
| checkpoint | 1 - Mountable Kerb
79509ee2-9992-5080-95a1-907ecd75694d | note | VERIFICATION ACTIVITY - QA FORM
3602ea0e-9ef8-53a9-9eac-a72e641a2bf0 | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002
c9d1d70c-bf93-59eb-98e6-38c9bf6a58d9 | note | FREQUENCY - Everysite
94aa37df-99e5-576e-9c64-9bc1eb19b8ef | note | ACCEPTANCE CRITERIA - Mountable Kerb to be laid using precast hand-laid and painted with two coats of reflective paint
aaebfe9a-f55d-5647-a2e1-bf1f007859d9 | note | Hold Point - Inprocess Inspection - Engineer to check kerb stringline before laying
730c90b1-7485-5e90-9f07-8c214fdeba91 | note | Records - FH concrete QA sheet, photos.
9b7e2630-30f4-5190-9157-fffb9372b3c5 | note | Onsite Responsibility - Site Engineer
| section | Construction
| checkpoint | 2 - Survey Setout
2e7db3d3-7814-5a50-b38a-416ed385fc90 | note | VERIFICATION ACTIVITY - Survey
95f8b96c-d70b-5471-99c3-2f2fc68021b7 | note | METHODS OR REFERENCE - Setout Kerb Alignment required to construct to design
d4b55126-122e-54be-a806-21034e672beb | note | FREQUENCY - Prior to commencement.
d0ec2e42-0dad-53b4-ab5d-45b65dd894b0 | note | ACCEPTANCE CRITERIA - Survey
75443599-c0b1-5b86-85b5-1de4cb8c3252 | note | Hold Point - As per Construction Drawings
6626cc67-0344-5547-819a-b4ec4ce93ae3 | note | Records - Survey Receipt.
e519d6fc-90c4-5625-8484-ca2a05f1cd85 | note | Onsite Responsibility - Site Engineer
| checkpoint | 3 - Concrete Island
286affee-7fbf-5888-b545-864fee92c437 | note | VERIFICATION ACTIVITY - QA FORM
e40e4b9c-fc71-542c-9647-1cb869d8a408 | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002
1dcd3e4a-77c6-555c-af7a-ea12b1baf50f | note | FREQUENCY - Each Site
a0251d64-0393-5bea-a716-2238774e67ad | note | ACCEPTANCE CRITERIA - Kerbs to be haunced with 20MPa Concrete
3c970695-aa2d-51c2-9c03-1a6d45e6854d | note | Hold Point - Inprocess Inspection
f0b8de19-b198-5f55-bbc2-b832a69c982b | note | Records - Photos
619a0e3a-a3eb-5ae4-818f-bd72fb8724bd | note | Onsite Responsibility - Site Engineer
| checkpoint | 3.1 -
18f55fb2-aa0e-53b3-b05b-03abbbf26614 | note | VERIFICATION ACTIVITY - QA FORM
e963e0d0-792c-51ae-a37b-19ff10654ec8 | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0003
09b0b187-e57f-5000-8cc2-b02dc84ae33c | note | FREQUENCY - Each Site
3887ef26-29d1-5dbc-a571-4060571eb320 | note | ACCEPTANCE CRITERIA - Basecourse to be 150mm min thickness of GAP65
d7df43de-59d8-5125-a6b1-d9ac672b51e5 | note | Hold Point - Inprocess Inspection
07eae6eb-6038-5136-8aa5-73eb4409083f | note | Records - Photos
f1ed8115-436c-5cbc-bcb4-1b36bb8ceae5 | note | Onsite Responsibility - Site Engineer
| checkpoint | 4 - Concrete Infil
dc18fc34-884f-59b6-90bb-3623ecd85405 | note | VERIFICATION ACTIVITY - QA FORM
18b8e3b8-ba7c-5036-9b8d-17a487828fef | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002
e7a98d69-8265-58e5-95fe-6ac24118d4ec | note | FREQUENCY - Each Site
f76df45e-b219-5b14-bad6-39030ac6776a | note | ACCEPTANCE CRITERIA - 180mm depth of 20MPa Broom finish, unreinforced Concrete with 6kg/m3 Red oxide Cross Fall of 2% or max rise in centre of 180mm
31fe5456-aea6-5147-8d68-c88df289eb4e | note | Hold Point - Inprocess Inspection
0a45d5f3-cd67-5ec3-a6cf-6df5181f6d1d | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
69bfb2af-be34-5321-a558-5f791bf28f51 | note | Onsite Responsibility - Site Engineer
| section | Asbuilts
| checkpoint | 5 - As built information
2ee5eddc-52fb-5a9b-b1ca-746f8bbd450c | note | VERIFICATION ACTIVITY - Drawings
c0db60f3-7796-53dd-997e-19c98e33daf7 | note | FREQUENCY - Every Site
9e11fc4e-9ca1-5e9e-be5e-b3c134676ca0 | note | ACCEPTANCE CRITERIA - As built drawings
9407cab5-f376-5c3d-b329-2f8493c0706b | note | Hold Point - In Process Inspection
aa9f5964-32bd-51dc-90ee-5fb9bd05f644 | note | Records - Asbuilt records
26b4dc9a-afc2-5270-b766-270414ec5115 | note | Onsite Responsibility - Supervisor and Engineer
| checkpoint | 6 - RAMM DATA
4ed14ebd-905e-5026-801e-def4d49d1e12 | note | VERIFICATION ACTIVITY - RAMM DATA SHEET
28f985bd-7c76-5a30-af99-14a5099ba274 | note | FREQUENCY - Every Site
433a0e2e-c73a-53dd-8b64-256bd0b859d1 | note | ACCEPTANCE CRITERIA - RAMM SHEET
d712ddad-76e5-5228-8d7e-63afe95676f0 | note | Hold Point - In Process Inspection
bbb2d025-167f-564d-912b-80c59b454ff3 | note | Records - Asbuilt records
20ec48ef-b6c3-5b0a-ba21-27465a70a18c | note | Onsite Responsibility - Supervisor and Engineer
| checklist | ITP - St Lukes Road/Morningside Drive intersection - Vehicle Crossings |  | ITP - St Lukes Road/Morningside Drive intersection - Enabling Works - Vehicle Crossings | 4ddffb21-af98-4ef7-a1b5-6cab60e93eb6
| section | Site Set Out
| checkpoint | 1 - Site Set out
13eede79-6a0c-5aff-b87e-5faacdb3149a | note | VERIFICATION ACTIVITY - Surveyor
d8e9600c-bc8e-59fa-9fa9-77ccd3b1d9f2 | note | METHODS OR REFERENCE - Surveyor
7187d19f-9068-5ff6-a556-85ce9e1af59f | note | FREQUENCY - Everysite
1ab46364-a64e-50b4-9caf-d66cc1e95f1e | note | ACCEPTANCE CRITERIA - Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable. Alternatively like for like
f159afb4-700d-5e75-9838-453cb51c5a68 | note | Hold Point - Mandatory HOLD POINT -
d5e4fbde-50bc-56ef-9984-26576b76e23d | note | Records - Survey Receipt
e0d5caf8-a243-54b2-980f-5e733fcfc4cd | note | Onsite Responsibility - Site Engineer
| section | Materials
| checkpoint | 2 - Channel Level
262c860a-f654-5027-ad1f-7d3ee7b0a7fa | note | VERIFICATION ACTIVITY - QA FORM
274b2ce0-facd-5a04-b893-b51f04497b17 | note | METHODS OR REFERENCE - TDM Technical Standards - VX0000
d1b8ac98-c28e-59a5-aaf4-e2e6fd9c5bfe | note | FREQUENCY - Every site
c87a5cc2-f087-5bca-b2a6-9a74ab7a08ad | note | ACCEPTANCE CRITERIA - Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
dab6ec5f-6828-566b-93ad-4510ef6fdb45 | note | Hold Point - Inprocess Inspection
fe08b551-a53b-5468-ba8f-683f8710700c | note | Records - FH concrete QA sheet
3e589c9a-b27c-5249-b701-9b8900790e85 | note | Onsite Responsibility - Site Engineer
| checkpoint | 3 - Mesh & Steel
3eef1fd6-f7ae-5a95-ba1d-c95678433dd4 | note | VERIFICATION ACTIVITY - QA FORM
cd437d5f-5c8f-5b58-86d0-6d635f659287 | note | METHODS OR REFERENCE - TDM Technical Standards - VX0000
a981eab8-11d9-5149-b63a-5b98efcd56c6 | note | FREQUENCY - Every site
05ad95ef-b26c-5ced-8ce0-8360d5a82e5a | note | ACCEPTANCE CRITERIA - 661 Mesh and/or D12 Bars to be installed if 4> dwellings or commercial crossing
0f563cc1-6e42-51cb-855e-ba43c8335b70 | note | Hold Point - Mandatory HOLD POINT -
60274585-ae52-5130-9b1e-213faaa080f0 | note | Records - FH concrete QA sheet Photos
0b059164-504c-5c09-91d0-3f2041a6aa70 | note | Onsite Responsibility - Site Engineer
| section | Construction
| checkpoint | 4a - Vehicle Crossing
78169538-a5af-50e9-bc11-d6a0f4b2f927 | note | VERIFICATION ACTIVITY - QA FORM
66f1dd70-1f42-59a7-bdd5-ed9e7abf7993 | note | METHODS OR REFERENCE - TDM Technical Standards - VX103
bed0f8aa-b81a-522c-9105-6795ea02052f | note | FREQUENCY - Each VX
df23bae4-5919-5cdd-b929-c94d4c9c742b | note | ACCEPTANCE CRITERIA - Subgrade -(CBR > 3) Base course - 100mm min. thickness GAP40 Clegg CIV > 12 Surfacing - Concrete 150mm and 20 MPa @ 28 days. 4kg/m3 black oxide Exposed Finish
bca3cde6-5d1f-529b-a650-801d54777b89 | note | Hold Point - Inprocess Inspection
f8d1cbe6-c9d5-5c65-a704-32b438bcc038 | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
a6a96826-7a07-5839-b494-e097ff4bd140 | note | Onsite Responsibility - Site Engineer
| checkpoint | 4b - Commercial Crossing
70b4a8b2-468d-5dbc-8237-ac90bb914735 | note | VERIFICATION ACTIVITY - QA FORM
3a530c93-085e-5b9d-a6d1-c261fa40faca | note | METHODS OR REFERENCE - TDM Technical Standards - VX0202
e5142beb-5eac-50a5-a842-7dd64eaacea9 | note | FREQUENCY - Each VX
c5d9ca11-6c44-526f-baea-8a7b3217e677 | note | ACCEPTANCE CRITERIA - Subgrade -(CBR > 3) Base course - 100mm min. thickness GAP40 Clegg CIV > 12 Surfacing - Concrete 200mm and 20 MPa @ 28 days. 4kg/m3 black oxide Exposed Finish
0df90ba2-967d-5346-b2ea-881123f4686a | note | Hold Point - Inprocess Inspection
7679114a-9b63-5a0b-ba74-a5e4d1af0265 | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
e5d1c2d4-a6d1-5f9d-9537-80c1ac8a7aae | note | Onsite Responsibility - Site Engineer
| checkpoint | 5 - Grass Berms
473bcd99-5e22-5768-8307-a2fc3681c087 | note | VERIFICATION ACTIVITY - Visual
4b06b878-69bd-5c75-bc8b-503e25b0976e | note | METHODS OR REFERENCE - ATCOP Section 12 Footpaths and Pedestrian Facilities
6e5d50db-f499-5443-bfd9-8ea70c5e9552 | note | FREQUENCY - 10m Intervals
c3cbb398-d719-5903-86fb-ddc7e1b55451 | note | ACCEPTANCE CRITERIA - 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
34ae55ed-b856-5aca-a52c-803d5b5fc794 | note | Hold Point - Inprocess Inspection
53687c47-15bd-52fc-80d8-191a1e1682f7 | note | Records - Photos
a41c9939-680e-5fc4-8205-3e39599fec16 | note | Onsite Responsibility - Site Engineer
| section | Asbuilts
| checkpoint | 6 - As built information
a19dbdc4-370f-5360-b30f-6c54126211fe | note | VERIFICATION ACTIVITY - RAMM DATA SHEET
7eaf69d3-90ad-50e5-a122-e5a9fa3dd33c | note | FREQUENCY - Every Site
5e3dfe17-4ccb-5d4b-9574-e1b95fb15894 | note | ACCEPTANCE CRITERIA - As built drawings and Ramm Sheets Completed
f2dd2386-e211-5ebe-997b-adc8793361cf | note | Hold Point - In Process Inspection
e9bf6627-b87b-5a44-bca3-1b0bca90e99d | note | Records - Asbuilt records
30370cd9-d9c0-5222-8040-b13ad1fee61f | note | Onsite Responsibility - Supervisor and Engineer
| section | ITP APPROVAL
5c4c40ff-6bfa-44a1-a90b-fedd762b37eb | checklist | ITP - Triangle Road - Enabling Works - Footpath, Kerb and Channel | itp | ITP - Triangle Road - Enabling Works - Footpath, Kerb and Channel | 4ab59945-e553-4975-bf49-a768af26d4ac
3bd0d3bb-a0ad-4811-a550-d170fb4b9f8d | section | Kerb and Channel
8446f066-f0d8-4764-9d96-a1e4530b799c | checkpoint | 1.a - Type 1 kerb & Channel
e742e7a4-c5e4-56a0-abc5-6fefed3c40a8 | note | VERIFICATION ACTIVITY - QA FORM
77c00003-9c08-53c3-be93-6ffd9193f168 | note | METHODS OR REFERENCE - TDM Technical Standards - KC0001
3b5bd26d-214a-5cf8-a6d5-025a4aae6c08 | note | FREQUENCY - Every Site
17143717-5dfe-5838-9b0d-7e2503d8c807 | note | ACCEPTANCE CRITERIA - Kerb & Channel to be laid using precast hand-laid on compacted minimum 300mm GAP65 sub base with CIV > 25. Concrete 20MPa @28 Days
53a4c040-54bd-5d7d-91d5-594e910dac98 | note | Hold Point - In Process Inspection
ccfba4dc-0cae-5626-8221-11eceac478d8 | note | Records - Clegg Sheet, photos. Concrete Plant Docket
6cf9dd2d-b204-51bb-a4c9-7a3d0d22fdff | note | Onsite Responsibility - Site Engineer
f29a63d4-4fdd-4f80-b143-008681f0ea1d | checkpoint | 1.b - Type 10 kerb and stub
f1662441-2ef2-5391-84b0-ea43366dbed1 | note | VERIFICATION ACTIVITY - QA FORM
e94a2449-1794-5826-93d2-bf75af23b247 | note | METHODS OR REFERENCE - TDM Technical Standards - KC0003
abdfda78-9957-51bb-a1e7-7271e63cc0a0 | note | FREQUENCY - Every Site
bfdf5c40-48dc-566b-8b73-55254a646760 | note | ACCEPTANCE CRITERIA - Kerb & Channel to be laid using precast hand-laid on compacted minimum 300mm GAP65 sub base. Concrete 20MPa @28 Days
de3a9ef4-ca00-59ab-a4da-049376a0961d | note | Hold Point - In Process Inspection
a67a7616-0f68-5e5f-b781-a46a19f0bd05 | note | Records - Clegg Sheet, photos. Concrete Plant Docket
c6d8dd39-26fc-55ae-a655-146bc03d1769 | note | Onsite Responsibility - Site Engineer
21a73b46-7335-4bfd-b16b-fd2a628bb664 | checkpoint | 1.c - Kassel kerb
22d9a28b-438b-52c2-b579-5ac3ad62e856 | note | VERIFICATION ACTIVITY - QA FORM
f7d5929e-17cc-51ee-b7b5-c9ae96d4d7e2 | note | METHODS OR REFERENCE - TDM Technical Standards - KC0030 and KC0031
b768392f-7cfc-5aca-a171-8f5a01b9a15a | note | FREQUENCY - Every Site
3cfa3bf5-c76d-5c72-93d0-45a7e7d3db1e | note | ACCEPTANCE CRITERIA - Kerbs must be laid on a 200mm thick 800mm wide concrete base (15MPa min)
58ac0a12-bc84-5311-886a-e03ce89a70bf | note | Hold Point - In Process Inspection
6c221354-c4b1-5324-9ca3-98369f906a23 | note | Records - Clegg Sheet, photos. Concrete Plant Docket
f9633942-f39a-55e2-9279-4ff5bda06109 | note | Onsite Responsibility - Site Engineer
561a659a-c2d1-474f-85c1-8c56f4b10f62 | checkpoint | 2 - Channel Level
f9ac0e6f-c625-5789-96b6-f651d2c973b4 | note | VERIFICATION ACTIVITY - QA FORM
e3ec4183-1ec7-5e67-8102-11656b3a049a | note | METHODS OR REFERENCE - TDM Technical Standards - KC0001
4927704d-1104-54b0-ae06-1842a71e13a4 | note | FREQUENCY - Every Site
361805de-42e5-5d8f-99c5-ea0a39243228 | note | ACCEPTANCE CRITERIA - Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match new road level. Channel grade to follow long-sections provided in IFC set.
68098497-45ab-50a8-a58c-8d2e8b34ca43 | note | Hold Point - In Process Inspection
7cb0f16f-53fa-5218-bb5a-d224c1dcdd8a | note | Records - FH channel QA sheet/photos
383bcc99-5db5-550b-8c52-b4e73beef65c | note | Onsite Responsibility - Site Engineer
3fce105c-5d74-4bfe-a488-66fd5589a761 | checkpoint | 3 - Dish channel
c19d910d-a025-5b54-90a1-111470738cca | note | VERIFICATION ACTIVITY - QA FORM
de736946-af76-5f18-a742-56fccd364da2 | note | METHODS OR REFERENCE - TDM Technical Standards - KC0004
f894e51c-8d32-50cb-99e9-f8161b014cb7 | note | FREQUENCY - Every Site
df762c9a-6b3b-5404-b8d5-718cf301b17a | note | ACCEPTANCE CRITERIA - 30mm deep V shape dish 3 of D12 rebar within 60mm cover within 200mm thick, 600mm wide concrete (unless otherwise specified)
3de59429-ce9e-57d0-a921-63ec50d42cdf | note | Hold Point - In Process Inspection
716d2d9e-76d9-5880-b7da-a217d463355a | note | Records - Photos
2fe89147-5e7a-515e-a76c-e112bf5765b1 | note | Onsite Responsibility - Site Engineer
32ad265c-96ad-4250-a356-00a532dbf78f | section | Footpath
12df649b-1fb9-49d7-bde0-77ad0fe709f3 | checkpoint | 4.a - Concrete Footpaths
9e3779a8-47bb-5673-a129-5ef67ebb1567 | note | VERIFICATION ACTIVITY - QA FORM
c1c0b332-ef3b-541f-8929-cd2afbdcf030 | note | METHODS OR REFERENCE - TDM Technical Standards - FP0001
a09ccd66-975c-5424-b770-e0d43465d835 | note | FREQUENCY - 10m Intervals
9e3d43c6-2c70-5301-bef0-706ba9b20286 | note | ACCEPTANCE CRITERIA - Basecourse - 100mm min. thickness Clegg CIV > 12 (frequency every 3m or minimum 4 spots per pour - excluding PX) Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 black oxide with broom finish
2aa47156-280b-5f43-ac62-9f9f912bcad9 | note | Hold Point - In Process Inspection
0f82c2be-1071-5056-a57a-9211b78da4ca | note | Records - Clegg Sheet, photos. Concrete Plant Docket
308101fe-6692-5dd3-84b0-e8c608429a91 | note | Onsite Responsibility - Site Engineer
4e2370d3-5096-43af-b6b3-d77fc4ca94a2 | checkpoint | 4.b - Asphalt Footpaths/Cycle Lane
84541f8d-7bf9-5ea9-b328-c605d15c82e9 | note | VERIFICATION ACTIVITY - QA FORM
32668dd1-86f8-5afb-b0bc-b574ae4c5008 | note | METHODS OR REFERENCE - TDM Technical Standards - FP0003
4567d99e-d833-5fa0-abc6-107763cea7da | note | FREQUENCY - 10m Intervals
90ed61a7-d638-524a-b174-8578fc290b08 | note | ACCEPTANCE CRITERIA - Basecourse - 150mm min. thickness Clegg CIV > 27 (frequency every 3m or minimum 4 spots per pour - excluding PX) Surfacing -25mm mix 10 (TNZ M-10 spec) black asphaltic concrete
38d8c6f2-36c8-514c-a7ac-7d4f9cef4ca9 | note | Hold Point - In Process Inspection
6079dd1c-d21e-5254-8c8c-4343074ea194 | note | Records - Clegg Sheet, photos. Asphalt plant Docket
1c07b99a-c75c-5fd0-9d54-abac8f1440c8 | note | Onsite Responsibility - Site Engineer
0e5bcbcd-3b56-429d-9756-2ca8153130a4 | section | Vehicle Crossings
05536984-b6ff-4616-8d98-bc0474fae614 | checkpoint | 5.a - Concrete Residential Vehicle Crossings (VX)
b4d8a103-28f9-590a-ad3a-a231fc21f3a9 | note | VERIFICATION ACTIVITY - QA FORM
a55907c9-168d-5310-b87b-9dd12aceaee5 | note | METHODS OR REFERENCE - TDM Technical Standards - VX0102
f3b608c0-a1cb-5565-8185-7d16ed0a0655 | note | FREQUENCY - Each VX
d2b85d3f-b296-5377-b81c-b78232db8985 | note | ACCEPTANCE CRITERIA - Basecourse -100mm min. thickness Clegg CIV > 12 as per TDM Single layer of 665 mesh when joining to more than 4 dwellings Mesh to be above re-bars Surfacing - 150mm thick concrete and 20 MPa @ 28 days. 4kg/m3 black oxide and broom finish
757ff385-dfdb-56bb-8a3a-03b0bfa5bcf0 | note | Hold Point - In Process Inspection
b70466cc-13c9-5566-8817-bb3c235e2c98 | note | Records - Clegg Sheet, photos. Concrete Plant Docket
791fa203-d78b-5161-87ac-36f964c02077 | note | Onsite Responsibility - Site Engineer
f7c29134-4a5c-42ad-be44-bde606b052af | checkpoint | 5.b - Concrete Residential Vehicle Crossings (VX) through a swale
0db84cf5-b529-51ee-abd8-ffb5d52cd82a | note | VERIFICATION ACTIVITY - QA FORM
11530373-a76c-5caa-8a3e-c376aef354ea | note | METHODS OR REFERENCE - TDM Technical Standards - VX0105
8c671cc2-cd8d-5af0-ae9e-d72d5ee81331 | note | FREQUENCY - Each VX
af277d8c-43ba-503d-8982-2b67ca7998a3 | note | ACCEPTANCE CRITERIA - Basecourse -100mm min. thickness Clegg CIV > 12 Surfacing - 150mm thick concrete and 20 MPa @ 28 days. 4kg/m3 black oxide and broom finish
aa6cc1c6-dc97-51e8-a9d5-5057a0347556 | note | Hold Point - In Process Inspection
5205f1ff-e424-5dab-9d15-532c811a1cf6 | note | Records - Clegg Sheet, photos. Concrete Plant Docket
e6cad844-c302-56ec-973f-878a4e544d14 | note | Onsite Responsibility - Site Engineer
eb9686d3-9c5e-4c32-8ee6-3f2f5410aa83 | checkpoint | 6 - Concrete Commercial Vehicle Crossings (VX)
cd0ef041-ab04-5da4-acd3-da3ed3289b91 | note | VERIFICATION ACTIVITY - QA FORM
548af24c-1818-50ba-bba7-19ff2e630a99 | note | METHODS OR REFERENCE - TDM Technical Standards - VX0201 - VX0204
7a547672-f5d2-597f-a9ba-9a1d206657db | note | FREQUENCY - Each VX
10f747c6-b1e5-5562-8d02-026c3098a202 | note | ACCEPTANCE CRITERIA - Basecourse -100mm min. thickness Clegg CIV > 12 as per TDM Single Layer of 661 Mesh Mesh to be above re-bars Surfacing - 200mm thick concrete and 20 MPa @ 28 days. 4kg/m3 black oxide and broom finish
b9c4439a-7568-5874-b420-5fc60618a0ea | note | Hold Point - In Process Inspection
5322d300-12c5-53ee-98ef-f100e8a3b55c | note | Records - Clegg Sheet, photos. Concrete Plant Docket
ce36b158-83ff-5a6f-a444-de8a970ce366 | note | Onsite Responsibility - Site Engineer
a809d2ae-ce99-47ac-8dbf-a045d5424b02 | section | Pram Crossing
7fdf0b18-9dfc-4c50-a757-b692eb699947 | checkpoint | 7 - Pram Crossing
aefbcf70-75d6-539b-9cb3-cb52575499b4 | note | VERIFICATION ACTIVITY - Visual
6f908bf2-edb5-527a-9abb-c1317e7885d7 | note | METHODS OR REFERENCE - TDM Technical Standards - FP006
e129a66a-8f9f-5fc1-93bf-0f65948ee021 | note | FREQUENCY - Each Crossing
782555c0-39c7-50fe-803d-94a39e2bf39b | note | ACCEPTANCE CRITERIA - Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing. Tactiles Directional & warning - 60mm; 600mm flares;width as per design; Slope no greater than 1:12 where practicably possible Clegg CIV > 12
49f2e5f8-5e81-55ba-a93b-9847e6f4f6d9 | note | Hold Point - In Process Inspection
16976b9f-82c7-5f59-9bdd-186c95f11a62 | note | Records - Photos
9dcfe126-ee9c-5015-9362-7bc584741342 | note | Onsite Responsibility - Site Engineer
a23d8072-9e1a-4402-81d2-0ff167e5a546 | section | Other
6ea2c627-be1e-4946-a1e9-e303f0b52d1f | checkpoint | 8 - Service Covers and Street Furniture
dface10a-31fb-5f59-a7d0-c731cf85b3fb | note | VERIFICATION ACTIVITY - Visual
0c52fa1e-8d11-526c-a21e-45daf123a7c3 | note | METHODS OR REFERENCE - AT Contract Specification 14000
a748072b-b605-56c5-88f2-306a772348d8 | note | FREQUENCY - Every Site
830d7336-9cf6-5e36-ade1-fd1094831f00 | note | ACCEPTANCE CRITERIA - Service covers to be adjusted to new surface levels. Ensure no damage is done to street furniture in the vicinity while carrying out works.
268acfcb-2c4b-5e2e-8b55-01e76b38b604 | note | Hold Point - In Process Inspection
f292b511-63b6-5aae-8732-63b9f14bae03 | note | Records - Nil
d5ca7aa7-dde7-590c-b5fd-938661df0184 | note | Onsite Responsibility - Site Engineer
f5d3e513-d524-4129-b693-1ef7de6d48fa | checkpoint | 10 - As built information
8e3cd2a0-fe99-573e-9d7d-9baf92aa2d7a | note | VERIFICATION ACTIVITY - Drawings
3f070acd-ec0d-5849-b8a9-1e365b793608 | note | FREQUENCY - Every Site
c678bd88-d817-5bae-9004-885728c32f73 | note | ACCEPTANCE CRITERIA - As built drawings
53b8eebf-4efe-5efe-bc65-c314765cc11e | note | Hold Point - In Process Inspection
21f188aa-fe76-565b-82c7-b6cbc3cc161b | note | Records - Asbuilt records
b108e721-8b1a-5129-a629-03d792394d36 | note | Onsite Responsibility - Site Engineer & PM
6d0f2144-099c-4911-a7bb-9759bd8a6bb9 | checkpoint | 11 - RAMM DATA
d5276721-4120-55bb-a302-0bbbb070c5a4 | note | VERIFICATION ACTIVITY - RAMM DATA SHEET
127a3420-66e6-5124-b7a2-665adc188c5a | note | FREQUENCY - Every Site
4e89ee07-92fb-5fbf-b7e3-566cd4e00793 | note | ACCEPTANCE CRITERIA - RAMM SHEET
cf9b3e76-82c3-516e-9e06-c7aa90daef46 | note | Hold Point - In Process Inspection
54ca7b19-ba0e-5f65-a770-16037cb84f09 | note | Records - RAMM Sheet
3943de9c-3342-510c-a5df-33c6ed26b331 | note | Onsite Responsibility - Site Engineer & PM
c167bb15-34b9-4b0c-9055-558e23b508ab | checklist | ITP - Triangle Road - Stormwater Drainage | itp | ITP - Triangle Road - Stormwater Drainage | 9fec3bb7-5382-4289-bd8c-b2a8b77aecd1
614b0090-a3dd-42e7-875a-d6e7e90bd9f7 | section | Design
00119f1e-d34a-4a98-83ab-3fe1c00568eb | checkpoint | 1 - Design
89913d85-35f7-5995-949b-6d65c0737ed5 | note | VERIFICATION ACTIVITY - Survey Setout
4a3e847c-4b4b-5f69-80ff-818ffb55f048 | note | METHODS OR REFERENCE - As per IFC
982aad0b-dafd-5c39-b525-fcda3b6b7341 | note | FREQUENCY - Each site
cb293444-282a-5d8e-9e4d-0d19c7d3de58 | note | ACCEPTANCE CRITERIA - Setout Pipe Alignment and cesspit locations and with inlet & outlet points and inverts as required to construct to design
c04c9267-dcbf-50b2-a325-40bcda756d44 | note | Hold Point - In Process Inspection
d2fa39bb-4247-565d-b139-ad6c76767487 | note | Records - IFC Drawings
6e3394e4-966a-5852-8170-3da95613091c | note | Onsite Responsibility - Site Engineer
17027eb0-7304-4607-b0ef-2fc28db3acec | section | Material Compliance
fd0c92ac-021a-406c-ad43-6080861dc378 | checkpoint | 2.1 - Material Compliance - Pipe
a2d2774d-2e96-5ac7-bd3c-cbdca0266b2c | note | VERIFICATION ACTIVITY - Visual Inspection
e7ce18dd-8efc-58dd-a302-c5792d93bb74 | note | METHODS OR REFERENCE - TES drawing No: L-001 - L-003
ba19c0f1-e7f8-5d2c-99cf-57b870a065e2 | note | FREQUENCY - Prior to construction
e57ed3a2-ba1d-5f86-a003-e34d0f1b227f | note | ACCEPTANCE CRITERIA - Pipe shall be Check for freshly formed pipes and return if required 1) DN225 Class 4 RCRRJ pipes AS/NZS 4058 2) DN300 Class 4 RCRRJ pipes AS/NZS 4058 3) DN375 Class 4 RCRRJ pipes AS/NZS 4058 4) DN400 Class 4 RCRRJ pipes AS/NZS 4058 5) DN600 Class 4 RCRRJ pipes AS/NZS 4058 2). All Concrete RCRRJ pipes to be fitted with Rubber rings 3). Pipes shall have product certification (ISO Type 5) to AS/NZS 4058 4) Prefabricated concrete Manhole/cesspit shall be in accordance with TDM Standards/SWCOP
472af864-16c2-5dd6-ba36-26f11e8449bf | note | Hold Point - In Process Inspection
37791cee-88a9-5ee1-970b-aa160f65ee9e | note | Records - Photos
5bfe4279-ace8-5aa9-8654-fc8cc72d1833 | note | Onsite Responsibility - Site Engineer
9bdb9422-4b23-495f-b09c-a7b2ef7ca7d5 | checkpoint | 2.2 - Subsoil Pipes
77c7cc4c-1d4f-5322-91ad-764044b96f1e | note | VERIFICATION ACTIVITY - Visual Inspection
1811771c-7968-5d3a-adc8-91963eb9b31f | note | METHODS OR REFERENCE - TDM Technical Standards - RD0010
a4a0cdfe-e29a-52c8-b360-d808c7fa1999 | note | FREQUENCY - Prior to construction
8b71742b-0246-57c6-9fb4-562bf3c00128 | note | ACCEPTANCE CRITERIA - Subsoil pipe should have 100mm internal diameter, punched holes and filtersok Depth to be 375mm from subgrade level to invert of pipe or as possible to achieve invert of subsoil pipe to be above soffit level of outlet pipe in the downstream cesspit. 50mm bedding. Trench backfill shall be approved 30/10 scoria or similar if filter sock provided
22cbaa1a-0c32-5829-83c3-b5e102eabeb9 | note | Hold Point - In Process Inspection
f7712612-c672-5793-a20f-da5be9127282 | note | Records - Photos/Dockets
6693e6c3-c94c-5f58-a32a-907eb3acf69c | note | Onsite Responsibility - Site Engineer
bb6aea75-42dd-4545-a40a-6fffe9c6a7b8 | checkpoint | 2.3 - Catchpits
1842fe65-c3e5-546a-a782-5bb260cdc7c3 | note | VERIFICATION ACTIVITY - Visual Inspection
fcd99dd1-5ce7-5187-8946-5a72e3488c5a | note | METHODS OR REFERENCE - TDM Technical Standards - RD0022, RD0023, RD0027, RD0028, RD0042 and SWCoP - drawing SW05 Revision 3
b94c769e-1604-59ab-974d-04e859bd8222 | note | FREQUENCY - Prior to construction
f319c397-30d2-5ce0-9af5-813ead5008e8 | note | ACCEPTANCE CRITERIA - No Damage or cracks- Material should compliance with TDM
720f8e94-36df-5bc0-9d1f-cde78b064545 | note | Hold Point - In Process Inspection
5e7707f0-00a2-5b66-b58d-63c995cc0b29 | note | Records - Photos/Dockets
4e4ae6c3-041f-5285-a2cb-b76d45995a37 | note | Onsite Responsibility - Site Engineer
384f4b25-0a72-47c7-930b-0879d2750967 | checkpoint | 2.4 - Manholes
5acb9c29-251e-5845-9c6e-dcdb8d444433 | note | VERIFICATION ACTIVITY - Visual Inspection
06512a8d-0405-5c95-9b84-a5b913ce4a83 | note | METHODS OR REFERENCE - SWCoP - drawing SW05 Revision 3
4c5a962e-bb81-5ba0-9296-f605f2aa7f2a | note | FREQUENCY - Prior to construction
0d4eb09c-ef9f-5ff1-9fa4-c47ea2581f17 | note | ACCEPTANCE CRITERIA - No Damage or cracks- Material should compliance with SWCoP
3f408401-c0f5-5fe5-b029-c02a739803d1 | note | Hold Point - In Process Inspection
1abc8d25-8bfd-5ed7-bbf8-b039e7e7444e | note | Records - Photos/Dockets
727db18f-d7cb-57d8-9e51-a86d4e56148b | note | Onsite Responsibility - Site Engineer
ce277666-3d19-480f-800c-6fda9451531b | section | Construction
1ecad15d-aa8d-4119-aad1-88e1b7c07343 | checkpoint | 3.1 - Construction
bf1efe90-bdc5-5fec-8c3e-e65bd651aeb2 | note | VERIFICATION ACTIVITY - Trench Profile - Width
8c02ef0f-d528-58bc-9b7c-1f16177237c2 | note | METHODS OR REFERENCE - SWCoP - drawing SW05 Revision 3
1ef71606-f747-5744-8138-79c94dc282fe | note | FREQUENCY - Daily / as trenching takes place. Different depth methodology
4ca9c5fa-a85b-576a-97ca-16280f04a69f | note | ACCEPTANCE CRITERIA - Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing. provide a minimum of 100mm bedding below each pipe
c71a8c60-3732-53bd-8fb4-aca222e0a9d6 | note | Hold Point - In Process Inspection
76377f55-2456-5a09-9a43-f8c6a68a58ca | note | Records - Visual Inspection, Measurement
cba3d9e6-9dc3-5dfd-9667-16c39129d0e5 | note | Onsite Responsibility - Site Engineer
db7ac690-fc7d-4f54-b901-6044ba24a71b | checkpoint | 3.2 - Construction
93c74ef3-26fb-569c-97b5-ccfd211659ad | note | VERIFICATION ACTIVITY - Bedding for Concrete Pipe Laying & Manhole & Cesspit
8969cdf3-c04d-5f99-b509-7e11f377f249 | note | METHODS OR REFERENCE - SWCoP - drawing SW05 Revision 3
b1f4e256-3a4b-52d2-944a-50a23fc2f8fd | note | FREQUENCY - Inspected continuously during placing and compaction of Bedding Material.
4999c36f-1706-5d69-a309-d5acd69a593e | note | ACCEPTANCE CRITERIA - Bedding & Pipe surround material to be GAP7 or GAP 20 or alternate material CIV>25 TDM Technical Standard RD0010, RD0025, RD0026, & RD0027 & SWCoP - Drawing SW05 Revision 3, to be followed
e0dc6af0-507c-53bd-8934-73825f6f8c9e | note | Hold Point - In Process Inspection
1b5ce8c8-9a4e-5ff8-b413-fee0e8b28af8 | note | Records - Visual Inspection Photos showing depths of trench and trench reinstatement Clegg Sheet
b02e2ac7-766b-5760-a340-cc9d6de0b7c5 | note | Onsite Responsibility - Site Engineer
5999226e-fe23-47ff-ae0c-fbdbec6bcd0e | checkpoint | 3.3 - Construction
d1092e2c-95d3-59d9-8a31-44da50dbb773 | note | VERIFICATION ACTIVITY - Trench Backfill - Placing & Compacting
120d957c-c764-58f0-ba7b-7dd28bed7474 | note | METHODS OR REFERENCE - SWCoP - drawing SW05 Revision 3
503f920d-fdcb-5620-b653-b36de602a2fe | note | FREQUENCY - Throughout Trench Backfilling operation.
eefe71ea-7208-5f75-95d4-0d75002d1799 | note | ACCEPTANCE CRITERIA - Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm TDM Technical Standard RD0010, RD0025, RD0026, & RD0027 & SWCoP - drawing SW05 Revision 3, to be followed
9a19a255-2c3c-5724-93df-5670358eaf68 | note | Hold Point - In Process Inspection
877a48d9-73fb-5437-b552-e025269dc0c7 | note | Records - Visual Inspection
a7f7c92d-9279-59fd-89f5-c36894c54374 | note | Onsite Responsibility - Site Engineer
96ac88c6-2f2f-47a9-8048-9d32509f7cca | checkpoint | 4 - Riprap
6a7b6d62-a154-5cca-af40-e54f5a60fdb4 | note | VERIFICATION ACTIVITY - As per IFC
e1c79c43-25c6-5619-9165-33ec1c966c3b | note | METHODS OR REFERENCE - As per IFC
be2fb410-4f22-5adb-947a-e4cdfceab63b | note | FREQUENCY - Every Site
40f13006-b106-5da4-babb-a120e3a60612 | note | ACCEPTANCE CRITERIA - Use 150mm-250mm Greywacke or basalt rock
47ce9561-013b-597b-af31-787072ae1fae | note | Hold Point - In Process Inspection
71988dcd-e788-5b13-a4b5-848dc44adadf | note | Records - Visual Inspection
a1f93308-f613-5b74-bd68-e72f793da94a | note | Onsite Responsibility - Site Engineer
cf612094-e59e-459f-aab0-4ad2eec3efa6 | checkpoint | 5.1 - As built information
8433ac90-69f0-54eb-9af6-d5f7577bdd3e | note | VERIFICATION ACTIVITY - Drawings
1d6785b9-8c56-5896-bdd7-aa39cc28ff30 | note | FREQUENCY - Every Site
632cf0e4-a395-5707-b9a0-cd0902e0623b | note | ACCEPTANCE CRITERIA - As built drawings
486acced-7d01-5f49-a147-d4858e857b20 | note | Hold Point - In Process Inspection
5f46a23b-7e4d-5a02-bd18-bfa8b0356e50 | note | Records - Asbuilt records
8ff503de-f2ea-56bf-aa58-ab1de6de9770 | note | Onsite Responsibility - Site Engineer & PM
569bd9f1-35f3-45f2-b38f-d9f1395de56d | checkpoint | 5.2 - RAMM DATA
02d9d2b5-846e-5908-9779-e8f27e313d7d | note | VERIFICATION ACTIVITY - RAMM DATA SHEET
5e806c93-a030-5fb8-b1e8-6bbdee7a9a32 | note | FREQUENCY - Every Site
b311b01a-d99f-5bd3-9d54-e0c6e1b2b76d | note | ACCEPTANCE CRITERIA - RAMM SHEET
d2119990-a35a-5b73-96d7-179102c0ad8f | note | Hold Point - In Process Inspection
d7d607fc-9673-5f10-8f2a-c64725ba9f2d | note | Records - RAMM Sheet
8162160c-0659-5618-901b-6b8221034799 | note | Onsite Responsibility - Site Engineer & PM
316dead4-348a-46e1-95b4-45803092ca42 | checklist | ITP - Triangle Road - Traffic Island | itp | ITP - Triangle Road - Traffic Island | 3150556e-980c-4758-a21f-bdfb5081d9ef
21a35a11-08de-4787-876e-b641213416fb | section | Survey - Set out
b041fd0a-b142-41d5-b3a1-65ec0347f7e4 | checkpoint | 1 - Survey Setout
40de36b6-5093-5a09-a65f-5dc849c0a87a | note | VERIFICATION ACTIVITY - Survey
cc13ee6c-cd94-5ab3-bcc0-fec91eafd69c | note | METHODS OR REFERENCE - Setout Kerb Alignment required to construct to design
46e14e97-6670-588b-956d-b3fb74dee8e2 | note | FREQUENCY - Prior to commencement
f394b5e6-268c-5329-a43b-2501ae8ababf | note | ACCEPTANCE CRITERIA - Survey
3b7d8d5e-f55e-5013-8a21-b3614b3477a4 | note | Records - Survey set-out
db6c2ff1-0bcc-5a93-bf48-6a64d1e3c517 | note | Onsite Responsibility - Site Engineer
b1c42071-d0b7-4309-9aee-18c1a675bc44 | section | Materials
d309e847-bbb0-43ad-b11f-97daddb503fb | checkpoint | 1 - Mountable Kerb - Traffic islands
caf004b0-223e-5c89-b919-1656114919c9 | note | VERIFICATION ACTIVITY - QA Form
0c9a6ec5-4221-552b-aee6-e902a1dd9347 | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 and IS0002
9e4fd33a-7bfe-58cf-93cb-c973e44a5252 | note | FREQUENCY - Every Site
5c21033b-3f4a-559d-bd24-ef30caab1411 | note | ACCEPTANCE CRITERIA - New Type 11 mountable kerb, 20Mpa concrete on Basecourse of 150mm Min thickness of GAP65 20Mpa concrete used for haunching. Kerbs to have 100mm reveal from ground road level
b5c86eaf-dd03-578a-8c74-d6aa0a54da00 | note | Hold Point - In Process Inspection
4fc040ef-77d3-5d8c-89ea-7217dc68e9bc | note | Records - Photos
b4690c3c-c0a1-5ec3-a771-391b638ad38f | note | Onsite Responsibility - Site Engineer
4bf144ef-c97b-4297-988e-37eff1e887fa | section | Construction
e6e5f5a0-c3e6-405e-923a-54b2abc8b4cd | checkpoint | 4 - Concrete Infill
a9dea845-176d-5e53-bd02-6553232c7bc1 | note | VERIFICATION ACTIVITY - QA Form
16c3d2ad-8875-5c4a-9482-3fcf061779d1 | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 and IS0002
e535d70c-587f-5614-8338-89a731aa7510 | note | FREQUENCY - Each Site
888ba195-ec05-52cf-9155-bff071ff7994 | note | ACCEPTANCE CRITERIA - 180mm depth of 20MPa Unreinforced concrete. 4kg/m3 red oxide. Exposed aggregate finish Clegg CIV > 12
bda90cbf-2dbc-5ec0-955f-503ef0415921 | note | Hold Point - In Process Inspection
b4432761-8fc8-5e8c-b2ef-02e1d3bca072 | note | Records - FH concrete QA sheet. Clegg Sheet, photos. Concrete Plant Docket
1d6bda30-91ca-50f2-9626-19ee27c65584 | note | Onsite Responsibility - Site Engineer
4b6e469a-6c87-456c-bd6e-b5c8bfa0a6fd | checkpoint | 6 - As built information
b8b0cc27-5d92-5007-b0b6-54a97a7dad2b | note | VERIFICATION ACTIVITY - Drawings
8d185b2d-32e7-5e36-8813-b2bdb1b78e65 | note | FREQUENCY - Every Site
044edf0d-35de-51d4-8de1-e93fc4476424 | note | ACCEPTANCE CRITERIA - As built drawings
34eab89f-1d53-5571-bdda-68e320b967e6 | note | Hold Point - In Process Inspection
918c8c49-d23f-53e4-bf87-47c6554c88d9 | note | Records - Asbuilt records
18d84b64-b095-5edc-baf6-24fe25c87650 | note | Onsite Responsibility - Supervisor and Engineer
d37bb4ae-7947-440b-9822-7817e9a31f8f | checkpoint | 7 - RAMM DATA
9c8645c1-6f2e-5a19-93a3-2d82f2057006 | note | VERIFICATION ACTIVITY - RAMM DATA SHEET
801c123c-bfa8-5e4b-99ff-3f72eea5609f | note | FREQUENCY - Every Site
f0a9003f-113b-5445-bf2d-7ab475c7c57b | note | ACCEPTANCE CRITERIA - RAMM SHEET
ecc15c3d-ee73-506a-af9d-2cc237ed08e2 | note | Hold Point - In Process Inspection
a2346424-2dcb-5a4f-80fc-32a8fb1092f7 | note | Records - Asbuilt records
1f12777f-467c-5162-b51f-a748d5eb20d6 | note | Onsite Responsibility - Supervisor and Engineer
| checklist | ITP - VRU Projects - AC Speed Table Rev 1 |  | ITP - VRU Projects - AC Speed Table Rev 1 | 73d3fd4d-6284-426e-9c84-e5e6f334532b
| section | Precom
| checkpoint | 1.1 - Permits & Services
f810c70d-383f-5c79-b4eb-ed507da167d2 | note | H
e01fa1bb-4740-50be-98bf-4405e7bcafdf | note | Detail - Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
af4743af-c6e9-56ab-8e62-14cfd7f0d8f4 | note | Frequency - Prior to any construction commencing
7931c006-c0f2-5d29-a35f-9474e8456576 | note | Inspection / Test Method - Document Review,PHOTOS
1cec9040-bd14-5695-8ce1-8d217c65878f | note | Conformance Criteria - Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority
c81e036b-01c5-55b3-8fb8-35eacadd3888 | note | Records - Permit attached or permit number noted.
61582d24-42f0-5956-9c47-e6463ea9ca38 | note | FH Initials - Site Engineer
e1855dc7-490c-5d2b-a611-71c40cdd0bad | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.2 - Permits & Services
715f2083-9c93-52a4-8578-45a9c786f121 | note | H
9343482e-a27c-5b8e-9299-af61b8e8e8d8 | note | Detail - Locate and mark out all existing services
82c15ecb-3eab-54c9-975e-a6d5c0a87509 | note | Frequency - Prior to any construction commencing
875ac0c7-c1a5-5953-8f05-d15570f751a1 | note | Inspection / Test Method - photos
7a518056-4059-5d3c-b72b-4573160dbf5b | note | Conformance Criteria - B4u dig procedure - follow utility protocols
b8ff000b-7d5d-58f7-8cbc-52c412a8709f | note | Records - B4u dig plans
7b439283-9a05-5e66-be22-b47bd2405d2f | note | FH Initials - Site Engineer
6bd5fce5-168e-5b75-8aff-ec393c308478 | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.3 - Permits & Services
8c14ef8a-d718-5b90-8127-32e3c4d4866e | note | H
a9292593-16ea-5ae9-a495-08a28099cff8 | note | Detail - Approved TMP
dc7cb66e-825f-5eaa-baac-1eaf51923d0b | note | Frequency - Prior to any construction commencing
76e95adb-5755-58a7-8b47-d64c7b8c1c0a | note | Conformance Criteria - Approved TMP and WAP onsite before establishing traffic management
ff97444d-8aa6-5da2-ac05-4ba62ef18d9b | note | Records - TMP Plans
3a334f0b-53f5-5a75-853b-291f89874d3d | note | FH Initials - Site Engineer
2a6b1789-8b4b-596c-b8aa-a1408d64d1ee | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Pre-Construction Sign Offs
0cf46d1b-4925-5695-9bb5-b00259710eb9 | note | H
41109273-9e95-5dc1-8838-f143c78646e6 | note | Detail - Sub-Contract and Supplier Agreements
e3932fd1-afee-5ebc-9ff5-b17c6eed4728 | note | Frequency - Prior to commencement.
d7908b34-42ba-503b-84e5-9f9343e92ff0 | note | Inspection / Test Method - Document Review
7d97ec24-b128-583b-833b-cba52586598b | note | Conformance Criteria - Sub-Contract and Supplier Agreements to be agreed and signed
e1a01ff3-c151-5c47-9889-efc10d5aa92a | note | Records - Subcontract and Supplier Agreements
dcae9d4d-56a9-5ba9-b8d4-340fcb9bcd3c | note | FH Initials - Site Engineer
ee74770d-fee3-5286-bd9d-adb617f39b8a | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Design
99a81368-3d67-541f-8fa3-93280ce0d4d4 | note | H
234eed94-df98-51d7-b43f-3d269491501d | note | Detail - Design is approved and Drawings are of the latest revision.
db6c7262-4551-5ba5-8624-68f54bbda07e | note | Frequency - Prior to commencement.
898e62b4-ce2a-5295-9f83-715a1215005a | note | Inspection / Test Method - Document Review
2dc639c7-f9a4-5f5a-9337-17a74a6d8f9c | note | Conformance Criteria - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
2945188f-f1e9-527f-882f-526ae364977b | note | Records - Drawing Register.
f9f027df-ab6e-5905-bf46-067298a39dda | note | FH Initials - Site Engineer
c155c062-c9ae-58c4-a1a8-b3660f46afd7 | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | Milling
| checkpoint | 4 - Milling Depth (up to 75mm)
bab6a5f0-fbdb-5388-9417-80d06c3f7265 | note | M
5bd39387-54a5-5870-b031-70956ca53d36 | note | Detail - AT Contract Specification 4414
93df934c-62cc-5359-9ae5-4009368e2bbb | note | Frequency - Every site
d27956da-053f-557b-bb65-fc6bb5803281 | note | Inspection / Test Method - Review,photos
9f81e6fb-7c97-5b17-836b-939a2aa083b2 | note | Conformance Criteria - Surface preparation shall be in accordance with NZTA Specification M10,The Contractor shall mill the existing surface to the minimum depth required to place the specified AC surfacing layer and provide a “key in” between the new and existing surfacing.The milling depth shall be carefully controlled to ensure that the finished milled depth and level within + / - 5mm of the specified levels or specified layer depths.
15c74856-6864-5826-969b-794eb91102cc | note | Records - Milling Records
a829c803-ddde-5885-9878-86c46704af7e | note | FH Initials - Supervisor
680b6623-54cd-5386-87d9-143e2b05384f | textbox | Date Completed:
| section | Aggregate Quality and Lab Test
| checkpoint | 4 - Temperature Limitation
5fe81162-d0de-5472-914f-18a3fcbe72ce | note | W
0e17273b-9a30-5816-8a96-e5759a2f8861 | note | Detail - Contract Spec /M10 Spec
fa6779c1-e9f0-5782-ad73-c2f4d4da202f | note | Frequency - Every site
aeb0652f-42a5-5e4d-a8d7-278f10e9414d | note | Inspection / Test Method - Review
95b02ea1-8594-5931-bb7f-44a66b8ebc70 | note | Conformance Criteria - Asphalt not to be paved when foggy or raining, or placed on a wet surface or when Temperature is below 120 degree
c868cd98-11df-55ae-b14e-69185ee7d88c | note | Records - Asphalt QA
98fd74a5-dd6e-5d13-a5e2-78e29ca2003a | note | FH Initials - Site Engineer
4df05634-fe9d-58f7-970e-d194d121fcdb | textbox | Date Completed:
| checkpoint | 5 - Check Weather Reports
ff12a44d-762c-5bfd-aef6-184a940d13ca | note | W
6c0fac29-29d2-5e71-a651-ccda63bec5dc | note | Detail - No fog, rain or wet surface. Base temp greater or equal to 7 degrees celsius
989a9580-cd1a-57ea-bc98-fc43f24f08cc | note | Frequency - Weather call 2pm on the day
9b537c69-3a39-52cf-9a6a-740fe37b769e | note | Inspection / Test Method - Visual
158b46c5-a4ee-5d48-8177-76df831ad14a | note | Conformance Criteria - Forecast and thermometer
d9112deb-c138-5d49-a7c6-1a4ec51a371b | note | Records - Radar and Asphalt QA
b0b3d147-c445-5720-bd48-1b446057e7f6 | note | FH Initials - Site Engineer
8922a259-8c80-51cb-86ed-c48e4a18429e | textbox | Date Completed:
| checkpoint | 6.1 - Pre-Seal Inspection
fa5c15ed-8f6e-5c07-b955-09b166d9e12e | note | H
903dac4c-5b8e-5768-a3e1-7fe371c6d01e | note | Detail - Surface finish
ddd39124-2820-58aa-b08e-5e8aa1c02922 | note | Frequency - Continuous
f8ae0ac5-75f4-593a-b1f5-db2ac85624ff | note | Inspection / Test Method - Visual
b04ba2f6-a928-542a-b58a-649ddc69afac | note | Conformance Criteria - The surface must be clear of deleterious material and not choked with fines. The basecourse surface must present a stone mosaic surface with larger aggregates protruding and not appear damp
cb8a2f50-7003-5610-885b-0c93a641f18a | note | Records - Sealing QA
387f7c4a-5918-511e-9ef9-79c7f95615f6 | note | FH Initials - Site Engineer
d49f77d8-2cd6-5315-9f47-0472b8edf8cc | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.2 - Pre-Seal Inspection
f956227b-c039-558d-baa4-d363f8fa783c | note | H
c63c135b-0da5-5dd5-b4ca-fb3ce8685744 | note | Detail - Basecourse Compaction
22173927-6692-5782-b97a-0c93aabb6b95 | note | Frequency - Everysite
8d24a420-0274-59c4-ad01-ac016f9f0797 | note | Inspection / Test Method - Testing
d506f472-9dd3-53b4-8030-6128bba69c2b | note | Conformance Criteria - Clegg CIV >25
295fda93-f502-513b-b25c-ae9a1d27c1f6 | note | Records - Asphalt QA
285fe3ee-e905-59d7-bb69-dedfd17fee34 | note | FH Initials - Site Engineer
5690eeb3-b576-5a4f-8234-4b69df3f9bb1 | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Tack Coat
70fd73d5-70f4-5fce-9e56-52135e808977 | note | M
a2a1f383-2eeb-5ea0-ac15-d7318e149623 | note | Detail - NZTA M10 Spec
4c0cb561-2dd6-5dc1-adda-56601a5ef652 | note | Frequency - Ensure heavy coat of emulsion is applied before on each layer of Asphalt mix
1f69e86a-34ab-5d08-a7a2-d9494fe15133 | note | Inspection / Test Method - Testing
4d024a5e-1fe9-5445-a454-44bf081a5e8c | note | Conformance Criteria - minimum of 1 L/m2 is required on each spray run
7a32a474-e345-59c7-9540-aa23d6e30a55 | note | Records - Asphalt QA
ff0c5328-d215-5bdf-8810-0051fb68a96c | note | FH Initials - Site Engineer
3afa390c-5961-5e64-a579-d73d7c075f9d | textbox | Date Completed:
| checkpoint | 8 - Construct AC20 Layer
0da78d0d-a935-5529-94d9-c8b9181de200 | note | M
eecf9bea-e75a-5c08-865d-7afc25babe4b | note | Detail - NZTA M/10 NDM and Stringline
bcafed82-4555-5dfb-b918-9c067201a9f4 | note | Frequency - Each Run
f439dcdc-a827-55eb-b6e4-7ce179f30b0e | note | Inspection / Test Method - Testing & Visual
8b6b133b-e047-56df-99f5-f00aeba65fd4 | note | Conformance Criteria - Construct 100mm AC20 layer. Design air voids 2-7% and level tolerance of +10mm, 0mm. NDM testing undertaken in accordance with NZTA M/10
9f4570af-a551-526b-8903-d479fb8fbef1 | note | Records - Asphalt QA
a1a55677-af5c-596a-a3c0-cf876045039d | note | FH Initials - Site Engineer
977b964c-eaa6-59ea-a504-cc2eca9660b1 | textbox | Date Completed:
| checkpoint | 9 - Construct DG10 Layer
078da525-2ebb-50f6-84e8-415f6a221a51 | note | M
2d2a83d0-26cb-5687-a3d7-f45e81ac1676 | note | Detail - NZTA M/10 NDM and Stringline
cf735ece-d592-59a8-a833-1c3e2faf5c82 | note | Frequency - Each Run
36fb9fc7-684c-5566-b64d-3676cca4f8ab | note | Inspection / Test Method - Testing & Visual
70df0424-2a63-5d46-8b8a-db106f989fd7 | note | Conformance Criteria - Construct 50mm DG10 surface layer. - Design air voids 2-7% and level tolerance of +10mm, 0mm. NDM testing undertaken in accordance with NZTA M/10
c67583ef-7023-5a84-b9bf-048ec0f65806 | note | Records - Asphalt QA
86bed40f-fb31-57f7-9168-de6e3208e734 | note | FH Initials - Site Engineer
b393ce11-4fe7-55bb-80ff-345fe5f77070 | textbox | Date Completed:
| checkpoint | 10 - Surface Finish
88ee9c94-57cb-5cf4-ac3b-89bb22481229 | note | W
203b7687-caf0-5ba5-b25e-b52169c05264 | note | Detail - TNZ P/9P
e99d5bf1-792d-512d-a835-c95dce141b72 | note | Frequency - Each Lot
b0490845-c6ab-5a43-9b8d-50b78c559dbb | note | Inspection / Test Method - Visual
3db640fe-d615-5d84-bfd2-b065dbdac024 | note | Conformance Criteria - Inspection: Uniform texture, no roller marks, no bleeding, cracking or shoving, no crushing of the aggregate
76279bac-640d-57f4-90b3-84aef2816eee | note | Records - Photos
701ae4c4-6027-5b43-a97c-a9fa49e6d7eb | note | FH Initials - Site Engineer
31668c14-82a8-59b3-b629-79c2bc8a45ff | textbox | Date Completed:
| checkpoint | 11 - Reinstatement of Linemarking
3d089f52-7e7e-5756-b8ed-1055adab1937 | note | M
fa38301c-c63d-509b-a004-f78086b62735 | note | Detail - NZTA M7 approved (Class B or C as required for anticipated traffic level)
6f181389-fa5f-5957-b886-7fa0358604db | note | Frequency - Every site
85e85662-0339-559c-82ec-af27d28e26f1 | note | Inspection / Test Method - Visual
2fdcfc60-c0b0-554f-bcc0-6ad51817fd91 | note | Conformance Criteria - *Carried out within 12 hours of each shift completed and as per the existing markings * Suitable Traffic Control to remain in place until pavement markings have been reinstated
8d02b67f-b3c4-557f-9bd2-fad1e6c3e5e3 | note | Records - Photos
d177a20f-fb3d-5c66-ae8b-f70e46bda120 | note | FH Initials - Site Engineer
a534f0e4-d219-5496-b8a5-df64d116c089 | textbox | Date Completed:
| checkpoint | Final Inspection
23cec3eb-e1aa-5c8b-84a8-ef9725a2a2dc | textbox | QA checked By Quality Manager:
0a95429b-3091-5333-ab1e-258d0a3e0e4d | textbox | Accepted By Engineers Rep:
| checklist | ITP - Willcott Street - Enabling Works - Footpath, Kerb and channel | itp | ITP - Willcott Street - Enabling Works - Footpath, Kerb and channel | 36c9094f-0450-4503-8b62-8d08388d94a0
| section | Site Set Out
| checkpoint | 1 - Site Set out
fe7669da-6274-5b82-9c62-da112ed2cd1c | note | VERIFICATION ACTIVITY - Surveyor
b37bfad9-b7ae-5023-a0a1-ff241dd63ff5 | note | METHODS OR REFERENCE - Surveyor
b859282d-955c-5bb8-834e-df34509706d7 | note | FREQUENCY - Everysite
44fcf706-2d78-5cce-8d91-3b085b537954 | note | ACCEPTANCE CRITERIA - Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
0347124a-7096-55d9-80a8-7f3485c23eb4 | note | Mandatory HOLD POINT -
16b60e06-4540-528a-aed2-f887ec671278 | note | Records - Onsite records/photos
f41ff7b4-6dd4-526c-917b-03c1bc96e0cb | note | Onsite Responsibility - Site Engineer
| signoff | HOLDPOINT
| section | Materials
| checkpoint | 2a - Kerb & Channel
374f0fb0-b379-5942-9ad1-1633879aec82 | note | VERIFICATION ACTIVITY - QA FORM
6699c17b-e0ce-5e7e-a822-7424e4abfbb9 | note | METHODS OR REFERENCE - TDM Technical Standards - KC0001
e1aa31e5-0229-50e2-851b-8929a596591d | note | FREQUENCY - Everysite
f7e9b4d2-bc6d-5b78-9c5e-f9ee8f173577 | note | ACCEPTANCE CRITERIA - Kerb & Channel to be precast hand-laid. Kerbing laid on 300mm min GAP65 sub base in roads and 100mm GAP 40 in footpaths (CBR>5).Concrete 20MPa @28 Days
b5530dcb-f3a7-56de-898f-c1eb31dce512 | note | In Process Inspection
d1810342-4360-505f-9885-8e438df2c2f4 | note | Records - FH concrete QA sheet, photos. Concrete Plant Docket
c621d01b-52a9-5474-a136-23fe513d4f37 | note | Onsite Responsibility - Site Engineer
| checkpoint | 2b - Traffic Island
bf9e3cda-f86b-53a2-b658-2f43111d2325 | note | VERIFICATION ACTIVITY - QA FORM
7c98590b-158f-5824-bdc3-f05030911108 | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001
3cca3033-6b1a-5a77-bdf0-da9d169efd76 | note | FREQUENCY - Everysite
04ad4b2d-7a2d-5141-b3d9-091129e8ccfb | note | ACCEPTANCE CRITERIA - Kerb to be laid using precast hand-laid
91896da4-e30d-5407-80f6-70f7f12e1ac1 | note | In Process Inspection
05096f82-99bc-5a16-9a83-d58de7e4aa5f | note | Records - FH concrete QA sheet, photos. Concrete Plant Docket
92cd9b5c-b94f-5f93-bc3a-530f20785de1 | note | Onsite Responsibility - Site Engineer
| checkpoint | 3 - Channel Level
b2964c88-8917-5e31-b1ad-2af80cc10e6a | note | VERIFICATION ACTIVITY - QA FORM
6a479bc4-0271-5a30-9406-c7faf0e1da3c | note | METHODS OR REFERENCE - TDM Technical Standards - KC0001
6431a47e-61e5-5541-9d87-7775c1c80228 | note | FREQUENCY - Everysite
81cd2ddf-1ba3-54a7-98ce-d63418437641 | note | ACCEPTANCE CRITERIA - Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
56e4988f-a3eb-5a06-a37c-770e2928bdb4 | note | In Process Inspection
e5b15406-0b6d-534a-92ca-3faec902862d | note | Records - FH concrete QA sheet
ce38894e-0375-5344-94aa-523dc8fb02c0 | note | Onsite Responsibility - Site Engineer
| section | CIVIL WORKS
| checkpoint | 4 - Concrete Footpaths
57312936-a7a2-5fc3-8bd9-1c8fea800aea | note | VERIFICATION ACTIVITY - QA FORM
2eeaa6b8-cc05-5019-b8ae-d1daeca3288a | note | METHODS OR REFERENCE - TDM Technical Standards - FP0001
d336ba70-3021-5339-94aa-4c3a7729bbde | note | FREQUENCY - 10m Intervals
2df84ce0-bb0f-526c-8d99-dcd780fc23e6 | note | ACCEPTANCE CRITERIA - Subgrade -(CBR > 3) Basecourse - 100mm min. thickness GAP40 Clegg CIV > 12 Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 black oxide with broom finish
b18515c9-6d4e-5c7c-b12c-d4927f0b7340 | note | In Process Inspection
54addf5a-7b35-5fec-8667-5d7c50d61409 | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
15f89bef-2f4e-502c-8e04-40fe1bbc2f99 | note | Onsite Responsibility - Site Engineer
| checkpoint | 4.1 -
51a57011-fe8d-55c1-a34f-703f3b079c9c | note | VERIFICATION ACTIVITY - QA FORM
0aa8ba4f-8375-5c02-a708-5c61255aa98b | note | METHODS OR REFERENCE - TDM Technical Standards - FP0006
9d3496a9-856e-5818-b907-f2ea586c6d54 | note | FREQUENCY - Each PX
2c4119e5-c627-5a88-abcb-5becec5aeb3a | note | ACCEPTANCE CRITERIA - Warning TGSI tiles should have 100mm concrete slab underneath
1210d743-66aa-5052-b06e-39b669a49666 | note | In Process Inspection, Measurement
757f38b5-0119-5e83-8a9c-68e90d0ba88a | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
30bc6166-11f3-57c6-9069-ba3d7f2fd6ee | note | Onsite Responsibility - Site Engineer
| checkpoint | 5 - Grass Berms
2d5c6772-c905-5ee3-ac35-2577a0adb8fb | note | VERIFICATION ACTIVITY - Visual
fbf0e3b4-c563-5621-84c8-1791d715d3fc | note | METHODS OR REFERENCE - ATCOP Section 12 Footpaths and Pedestrian Facilities
ce134998-1dde-53f9-9bc2-68a983aeab69 | note | FREQUENCY - 10m Intervals
19fd1c16-02a8-5905-b8d9-cd822ec8a296 | note | ACCEPTANCE CRITERIA - 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
5d95e54f-2749-5d62-9b5a-aec69a571b7b | note | In Process Inspection
8c78e1eb-6b54-57ac-bb5b-5126d97cafa8 | note | Records - Photos
ef27de54-2ac4-5973-a6b4-c7d1117c67b9 | note | Onsite Responsibility - Site Engineer
| checkpoint | 6 - Tactiles
716c917f-f1e5-5322-9c12-5be429857f5c | note | VERIFICATION ACTIVITY - Visual
756dc9b4-7322-5818-bc1c-51ae959156c0 | note | METHODS OR REFERENCE - NZTA RTS Guidelines for facilities for blind and vision impaired pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
f337673b-bac4-5254-9f81-dc9fb5e44ae0 | note | FREQUENCY - Everysite
814be53f-3171-5d86-87b1-da5fbfd6770c | note | ACCEPTANCE CRITERIA - Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
41a5e299-d5d4-5264-a616-09530a05f7e8 | note | In Process Inspection
b504a74b-cb26-5dd5-8835-52d2b43037f0 | note | Records - Photos
86f8ca93-5fa0-5ff5-8b0d-40da0536e334 | note | Onsite Responsibility - Site Engineer
| checkpoint | 6.1
0af71293-3ae1-54af-8957-0a090cf7df7c | note | VERIFICATION ACTIVITY -
f265ddc2-7b04-50f6-87ad-d3d8a4387f60 | note | METHODS OR REFERENCE - AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
dbdfcd9f-1798-57b4-b930-83c05b4fc39d | note | FREQUENCY - Everysite
8e9b88f3-05f1-5758-baef-e47e98ac6a28 | note | ACCEPTANCE CRITERIA - Edge of warning indicators to set back 300mm from the face of the kerb or lane, extend the full width of ramp and be 600mm deep.
4925ed03-24db-5b74-8336-eae5cc486b57 | note | In Process Inspection
6788a83b-1e90-56b2-b76b-3b5b4f441d86 | note | Records - Photos
15dee8aa-6c0f-5996-ab4b-4bb3daf2a0b1 | note | Onsite Responsibility - Site Engineer
| checkpoint | 6.2 -
6453ad1c-e5c6-53b7-837f-d327e508a40a | note | VERIFICATION ACTIVITY -
a303a267-0c97-5719-b2f6-6664acd6cb8b | note | METHODS OR REFERENCE - AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
9b18d9a2-0f29-5661-bfd8-c981df3a3560 | note | FREQUENCY - Everysite
62ef37da-3ee6-52f9-baa2-a6d869234368 | note | ACCEPTANCE CRITERIA - TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
5a1f6fe8-86d6-54e9-b66b-6a3ea8bfca94 | note | In Process Inspection
f9f7f835-702e-56f7-b9d1-f276a0d5c532 | note | Records - Photos
92b4fd07-56ea-5657-8b31-99b5303f69d2 | note | Onsite Responsibility - Site Engineer
| checkpoint | 7 - Concrete Island
74c08020-e07c-5f62-8374-b56bc6dc8195 | note | VERIFICATION ACTIVITY - QA FORM
442787e5-ce07-5e76-876e-584d8dd88a4f | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001
55f93f04-e4f3-5fc6-b520-3a7341243cf9 | note | FREQUENCY - Each Site
582b46ea-02b5-5a95-83fc-9988db55b7b4 | note | ACCEPTANCE CRITERIA - Kerb & Channel to be precast hand-laid. Kerbing laid on 150mm min GAP65 sub base in roads.Concrete 20MPa @28 Days
6fc68b79-92e6-5fe2-8120-936b9897839f | note | In Process Inspection
488c216e-56dd-505b-9254-ccd5894fd4b3 | note | Records - Photos
1975d59c-a4c3-5ebe-9137-52e1ba163d31 | note | Onsite Responsibility - Site Engineer
| checkpoint | 8 - Concrete Infil
c25b34fe-8518-5bad-a761-c781f26f5d5f | note | VERIFICATION ACTIVITY - QA FORM
81c3c65e-5e71-5323-a9a4-17ecf0e52b69 | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002
be5e38aa-6413-56c9-ba6e-0798ac37cc9c | note | FREQUENCY - Each Site
52551102-77ab-52da-a816-ad7a6cef95d7 | note | ACCEPTANCE CRITERIA - 180mm depth of 20MPa McCallum Chip with 3kg/m3 Red Oxide - Exposed Cross Fall of 10% or max rise in centre of 150mm
392c07ed-ad56-57a6-9e94-087241102cdf | note | In Process Inspection
35479df3-c323-54ea-a7d2-e8c0b3b62860 | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
f9e71482-ab9d-5528-866d-103941bb068b | note | Onsite Responsibility - Site Engineer
| section | RAMM DATA
| checkpoint | 9 - As built information
2344fac6-2d9c-5bcb-b718-5bef33a39292 | note | VERIFICATION ACTIVITY - RAMM DATA SHEET
e628f297-c1b5-50d6-86f9-67f992a25af5 | note | METHODS OR REFERENCE -
51799d8b-a6a6-5818-87d2-b017438d4d09 | note | FREQUENCY - Every Site
11a3066f-7a6e-5a0b-8496-f570a1040c65 | note | ACCEPTANCE CRITERIA - As built drawings and Ramm Sheets Completed
947d66f3-7cb8-5c2d-826b-2302bd07d551 | note | In Process Inspection
c5b931fe-0a03-52d3-b757-c1559d6e7676 | note | Records - Asbuilt records
84aa7768-5818-5f99-bf55-546181072b89 | note | Onsite Responsibility - Supervisor and Engineer
| checkpoint | Final Inspection
7746dbb7-329e-55a1-818e-7b229836e9d7 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
c7dce318-b7c9-586b-a80a-020bd21926dd | textbox | Print Name:
0250584b-af87-58a3-ad15-86fadd51163d | textbox | Position:
5bbb851c-b915-5dc4-a979-034ca9aabdd3 | textbox | Date:
| checklist | ITP - Willcott Street - Raised Pedestrian Crossing | itp | ITP - Willcott Street - Raised Pedestrian Crossing | 520c7346-591b-4b27-afba-93fabbfdd89f
| checkpoint | 1 - Permits
9ea38b37-c7ef-5b00-8a4d-d03cc6f8a52b | note | Inspection / Test Point - Permits
c1282c63-1a12-5c37-8091-3a0cd6f3d073 | note | H
44f66319-4d8c-57c3-9ab2-a646ff851a3e | note | Detail - Obtain Permits
fc29865d-bc61-5ffd-9437-30d1c06e62b2 | note | Frequency - As required
f775e562-d713-536e-975b-878a3113b865 | note | Inspection / Test Method - Document Review
6df016c7-b87a-5e80-8ea3-d183614323c6 | note | Conformance Criteria - Control Checklist - Fall Prevention (if applicable). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
82cea3bf-2195-57bc-a309-c97dc922ac67 | note | Records - Permit attached or permit number noted
a4b08d26-d7ae-599c-a016-59fe3a5cf9a1 | note | FH Initials - Site Engineer
6112658b-3a92-5cfc-9e7a-44e89fa34e66 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
3468e892-fc3a-5a06-b367-d10281922fe7 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 2 - Pre-construction sign offs
59d2a90e-6387-5a4b-8586-9a4a4e250581 | note | Inspection / Test Point - Pre-construction sign offs
d4ed20f1-39c6-54b8-93f2-0ddf9e0c4f1b | note | H
4db320f3-9639-5ff1-9a81-b7356bee1be9 | note | Detail - Ensure that Sub-Contract and Supplier Agreements are signed
89527ba0-6f1d-5199-907b-d872b155e9be | note | Frequency - Prior to commencement
5cd693e0-d923-5333-8d02-af06ed274345 | note | Inspection / Test Method - Document Review
936253dd-5390-51b9-9ebf-de81facc22fa | note | Conformance Criteria - Signed Subcontractor and Supplier Agreements
e646a8d3-bd2c-55b8-848d-7295ddbbc433 | note | Records - Subcontract and Supplier Agreements
d6a13a52-961b-54d8-a3fb-1592ac701596 | note | FH Initials - Site Engineer
1365bac9-c609-5f41-91a7-e0e8782bfe1f | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
63f1f980-6fa7-5222-ae43-11825f28d04d | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 2.1 -
3f1cb732-0bae-50a1-8e45-881afd257409 | note | Inspection / Test Point -
aa5f5a8a-a0f7-5d0f-8b34-208adbdbc1f4 | note | H
5c0b95b5-f7cf-55a9-b22c-6c8347ccd15a | note | Detail - Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
917d92d1-144b-551e-a7b6-774616641e6e | note | Frequency - Prior to commencement
ecea1d3e-0e25-5016-909d-4f5a929b6b08 | note | Inspection / Test Method - Document Review
69ae87f6-abb3-52bf-9d97-2973e8b85102 | note | Conformance Criteria - TMP is approved by CAR manager for each site and works are only completed within the approved dates..
eaf6a72c-9f7f-50dd-8994-35600d2de594 | note | Records - TMP on MyWorksites/On Site
14835e87-acdc-5eab-afd4-0db5682a8d09 | note | FH Initials - Site Engineer
1869d155-f1d9-523b-8ad3-a137859517e7 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
5ade7a0f-b6bb-5e90-b8bb-8db009d62236 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 2.2 -
d14f8c2a-25d6-5261-9838-cc4cdc481fc9 | note | Inspection / Test Point -
eca4b261-4e9a-587e-8c8b-7618378dd4de | note | H
14b68c2a-072f-5305-9ccd-2e19bc916387 | note | Detail - Ensure all Subcontractors and Suppliers go through FH induction
532b3327-b30b-5c05-9fd0-0934f886a21c | note | Frequency - On site daily
85bc6572-bf47-5440-9c5a-46d18f6982d7 | note | Inspection / Test Method - Induction
f656664b-238d-5ea1-bb1e-8642043e8a6e | note | Conformance Criteria - Supplier's and Subcontractor's signatures on hazard ID and pre-start documentation
7ac62e0f-6ad7-5335-85a3-5cb4ce49471a | note | Records - Hazard ID and Pre-starts to safety team
2a058390-9804-5c31-8bce-dc05827b0c34 | note | FH Initials - Site Engineer
2ad506a0-3256-5eb5-a414-5d93291c031e | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
d237988d-8210-55be-879c-166990837da8 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 3 - Design
8b13ed0a-fb5b-56b2-95ad-1f14f03733be | note | Inspection / Test Point - Design
09d7d22e-7a98-554d-a3d0-c3641530bd7c | note | H
71c6a09c-ddff-5a6f-8902-5632303b9722 | note | Detail - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
cd83fa49-15d3-59a6-94e6-1845a83b1f4c | note | Frequency - Prior to commencement
674b0b63-c0d5-5c1a-a6b3-88ddac033979 | note | Inspection / Test Method - Document Review
67b827b4-f751-5067-9a84-9c27a7b837dc | note | Conformance Criteria - IFC drawings have been received by Contractor
4b67b770-3f4c-5b37-beb0-b833fff180c9 | note | Records - Check Drawing Register
b17be013-5ff0-518c-99ad-a46648d33fa6 | note | FH Initials - Site Engineer
4d573b27-e856-56de-9990-d802c2253f88 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - Design Engineer
87a4de41-33c7-5bc6-a2c1-cf8505521fb7 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 3.1 -
05ce86e3-2acb-5765-9fd9-86f265c23c43 | note | Inspection / Test Point -
4624fd9c-7a0d-5a1a-a07e-8f15eef1f6f4 | note | H
1d910bf6-9d3d-5e13-9047-aaca99704b33 | note | Detail - Crossing to comply with AT TDM chapter Traffic Calming and TDM TC0010
27c71579-2310-5dd9-b8ee-afde6a665bdc | note | Frequency - Prior to commencement
930a2bd9-d32f-5c16-a4c1-9aad73b760a5 | note | Inspection / Test Method - Document Review
67fdd431-c631-540e-84be-f93de36f9c32 | note | Conformance Criteria - IFC drawings have been received by Contractor
ae5ebfb0-6b4a-5244-a3ef-6be5476282ab | note | Records - Check Drawing Register
3929c958-a50c-5b2c-be2c-47a0a6b35e7a | note | FH Initials - Site Engineer
cec81eda-d547-5bce-b054-2a80137c56de | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - Design Engineer
8d9a72bc-e746-5a19-83dc-05d3d5c7d1e1 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 4 - Installation of Erosion and Sediment Controls
e7c40dd7-06ba-55ea-bdba-06684de2986e | note | Inspection / Test Point - Installation of Erosion and Sediment Controls
376db85f-8b7d-58e7-a596-b04516412c78 | note | H
2d617f52-1260-50fc-ae1c-040369cb95a3 | note | Detail - Ensure that Erosion & Sediment Control in place
c70f2fd4-2228-54ee-93d2-baf8a57a9ff6 | note | Frequency - Prior to commencement
4b1745d3-3786-5afc-b013-0365429e6602 | note | Inspection / Test Method - Visual Inspection
b34a8589-7bc4-55e3-b93c-e7018df50ca1 | note | Conformance Criteria - Territorial Authority has approved the asbuilts for the ESC controls constructed onsite and gives approval for construction to commence
99ce2d0c-cf64-5af5-97de-8a9023ed688a | note | Records - Environmental Controls Audit
3d47b0b5-fde3-5645-ab61-af5862a0a233 | note | FH Initials - Environmental Manager/Site Engineer
daad7679-b347-5521-93fa-912031d2d05d | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
9222844a-320e-5ead-9d03-4ba1de2f56ce | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 5 - Survey Setout
8456fde2-1b33-5301-8a9b-f0beb926574e | note | Inspection / Test Point - Survey Setout
b272d8d1-00b3-56c7-b1d8-4307d41caf1d | note | H
20c801bf-d3fd-5a15-a456-8842c31d190c | note | Detail - Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations)
3bdb79c0-79fc-5e7e-8366-e862a1d26700 | note | Frequency - Prior to commencement
74411f0e-9230-596a-87a9-5aa0911be762 | note | Inspection / Test Method - Survey + Smart Level
fedafeaa-35ff-589b-aef4-73c599dce925 | note | Conformance Criteria - Consistency with Construction Drawing
4a95e150-11e4-54e4-bec6-c83b0eed9407 | note | Records - Site Photos post surveying
da16ea3b-b769-56af-a7de-c29f2067adab | note | FH Initials - Site Engineer
5c48fea3-f199-5bb1-bba6-5c0f69d3e9fe | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
b9ac8eb5-8812-5fb6-97e8-f388e7a34251 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 6 - Locate Existing Services by Hand Digging
75e159b3-5ad5-50cc-a765-148435bcf47f | note | Inspection / Test Point - Locate Existing Services by Hand Digging
58604264-591d-5c4c-b6d5-6be8716f3a0e | note | H
4f135f06-30e6-5f42-986b-87703aca7e03 | note | Detail - Ensure all services conflicting with the line of trench has been exposed by hand digging
695c5156-8b61-5db9-b6a5-8e46c59f019b | note | Frequency - Prior to commencement
206062bb-d37b-55bc-abe7-cf311929a4e3 | note | Inspection / Test Method - Potholing
49adf21d-84b8-5fd2-9f9f-56e7633a9439 | note | Conformance Criteria - All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. Asbuilt all services
ee2c81da-7d4c-507b-9623-ae3f1fdf41d5 | note | Records - Digging and excavation checklist, service planes,As-Built Drawings Doc. Review
3eeefec4-ea41-5989-bf89-2064eb5632af | note | FH Initials - Site Engineer
8dc86991-7992-5c30-baa3-9e964b137501 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
3da030e6-794e-5e2e-b2c5-64eb9b6b41e2 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 7 - Material Compliance
6e4ffa41-5d3e-58a9-bf2e-1dd2d8e8ca69 | note | Inspection / Test Point - Material Compliance
45878f46-54f9-592a-8d5e-84acc8e8d96a | note | H
549d120a-5358-5d4f-9de6-7f91cb813c0d | note | Detail - LESA dowels to be used at all construction joints
75187c3b-d570-51e3-aa7b-6f04d5260f96 | note | Frequency - Prior to pouring concrete
a3d611b6-abae-5f15-b2cf-f0019c4e5160 | note | Inspection / Test Method - Document Review
a4118dc2-3f18-5710-96e0-9b66695edd8b | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
1b86b5a8-3c60-5960-a677-d7003e18c200 | note | Records - Delivery Dockets / Photos
b3f771d4-57b5-524c-a149-d3dcf13c7db0 | note | FH Initials - Site Engineer
c69a1d97-29a6-507f-b487-d4aedcc9ab72 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
30046c68-398d-589c-b16a-568b3ebaa9d2 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 7.1 -
cd4a5b63-c94a-56c5-bbd4-ac88d772f4b7 | note | Inspection / Test Point -
0be2727e-f3a7-5133-9fe2-34171a5c8740 | note | H
44a7bfce-9bd9-5fea-9c13-d4e2bb337294 | note | Detail - 0.25mm polythene layer placed across all surface area at bottom of raised table
facb7868-465f-5f6f-8698-93bc8b726cdb | note | Frequency - Prior to pouring concrete
2ca7fb6d-bbe1-5879-b3f4-70338ee98e00 | note | Inspection / Test Method - Visual Inspection, Document Review
eb1a9eb8-f541-5162-bd93-ea3fba46ccad | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
9e6efb6a-9e5a-5a99-b401-f9c47bcc7ed3 | note | Records - Delivery Dockets / Photos
7a003432-d2f3-51f9-8366-701e2cd6b6dd | note | FH Initials - Site Engineer
997b7511-50e6-540e-a0c3-9c92ccf06e83 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
ea957ec8-87e3-5c0b-bdef-4dd6651e93c5 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 7.2 -
f3fd379d-54e5-5b77-8764-c331afbec601 | note | Inspection / Test Point -
593945a4-251a-5fc5-a7e7-03a7d555335c | note | H
a7bf6b27-a829-5b3a-bad3-e409d803a09b | note | Detail - 30mm thick compacted layer of AP20 aggregate placed underneath polyethene layer.
714afb87-54d0-5a95-acb8-59bfd2095085 | note | Frequency - Prior to pouring concrete
2279228b-c556-5c62-9a20-479d2c098f77 | note | Inspection / Test Method - Visual Inspection
975cca28-4c2e-52d2-9579-609c01342ec4 | note | Conformance Criteria - CIV >15
f6c97aab-4763-51f6-a96a-26f3d37efa75 | note | Records - Delivery Dockets
64f9fc2c-b56f-5924-998b-62a62819d5e9 | note | FH Initials - Site Engineer
d8b6acd0-a333-5754-baff-8ff46da20878 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
3089dd91-f5e8-5157-9af9-d2c8811046aa | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 7.3 -
6b1ad189-3faa-53e6-94de-f67672a43180 | note | Inspection / Test Point -
1dad9646-e43c-5ef9-91bb-0e849b20b166 | note | H
9b9c0685-0dc9-5c64-b2a0-d9929fa1f4d2 | note | Detail - Two layers of 663 mesh 50mm cover from top and bottom to be placed inside with 70mm plastic chairs separating.
a03d9bc6-8c1a-5a41-87e4-61d78bf922d8 | note | Frequency - Prior to pouring concrete
f374d99d-ec1f-593b-9c06-c1b77ddc5637 | note | Inspection / Test Method - Visual Inspection
08589937-cd71-500e-9bb4-af4d977e7d12 | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
cb8a2201-18d7-5a19-8d3d-e0f98e0fe983 | note | Records - Delivery Dockets / Photos
18df4c89-ff9f-54e7-a275-90c32ebbe9a9 | note | FH Initials -
7f0c02f4-326e-5c3b-b3c8-52f44c72773b | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
e2854453-e6a5-5e77-a2fb-c6c2e69ebf6d | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 7.4 -
9cb7fd3b-7dd1-5021-860b-f2defd8753ad | note | Inspection / Test Point -
cae52284-9168-5b30-99d8-7964d328c731 | note | H
fd70d368-75c0-5cc0-82ea-6c9e5420a632 | note | Detail - All concrete delivered to site shall have 40MPa 28 day compressive strength
a62aed1e-962b-54d5-9ba5-fba7450856d2 | note | Frequency - Prior to pouring concrete
43ab89a3-c02c-5f9f-bcd0-ca7265fe46df | note | Inspection / Test Method - Concrete Delivery Dockets
9de14ebd-c0c8-5dd1-884e-2f9ab3612722 | note | Conformance Criteria - Delivery Docket added to QA folder
45082129-c10e-50fd-8a58-092d9e939841 | note | Records - Concrete Delivery Dockets
e2f07ee1-1686-550b-8dc3-6d3002346e0a | note | FH Initials - Site Engineer
9cc96a79-e3b3-54d3-a5ea-dc1d523a3f13 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
d987b4cc-01bd-53a3-a52d-d4821d777c62 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 8 - Temporary Works (Formwork)
e05cd40b-b69a-5e72-8b97-a722a7f45dc7 | note | Inspection / Test Point - Temporary Works (Formwork)
1535e89c-39f6-5bf6-a1a1-c83c97800888 | note | W
9efda194-fe7e-5378-b65b-7490fe9185ac | note | Detail - Formwork to be set to correct line and level
b2d0d512-aaba-538d-9076-b4ff85175357 | note | Frequency - Prior to pouring concrete
4cf717ad-9baf-5820-a03f-8a90fdbf921b | note | Inspection / Test Method - Visual inspection
467e43d6-ebd4-5537-840e-531972a7a626 | note | Conformance Criteria - Concrete Inspection Record
111cd02b-c901-59a1-802a-54ade19a22ec | note | Records - Concrete Formwork Checklist
b42a47fb-789d-5442-abc0-1d9eec47ebcd | note | FH Initials - Site Engineer
487b9350-5c1b-555c-ad13-c0dfc1e2554c | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
f3779bab-c2b3-56c3-a177-1f93ba93e190 | textbox | Date Completed:
| checkpoint | 8.1 -
031fbb7f-dfed-54c5-a038-309455cbbee9 | note | Inspection / Test Point -
144a1afc-e5af-5a21-beee-fa6df7ac1589 | note | H
f0c34de0-8e2b-5d63-9926-eeca1e103a65 | note | Detail - Raised table formwork to be 100mm above existing road level and be 300mm in depth and gradients respectively of entry and exit ramps
98b2ca8d-0e06-5159-a094-5c172f9580eb | note | Frequency - Prior to pouring concrete
773664dc-db51-5789-b6a1-3bb13cf7e2eb | note | Inspection / Test Method - Measurement
4c50c8d7-653e-5557-b569-2e27f265685c | note | Conformance Criteria - Designer to inspect formation level
ad7a396a-1da2-5165-93a2-9fb39796c2f8 | note | Records - Site photos
37993b71-4f34-5ba7-97ab-059553d5ebbb | note | FH Initials - Site Engineer
15585d10-e077-5ef9-91d0-cdba3c32fea7 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
d82eac6d-6493-56f2-b2ae-6c12758f5b63 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 8.2 -
2ac73215-a42e-5a84-9684-704df57bc548 | note | Inspection / Test Point -
c8779a4e-71b9-558c-9520-aa91d331e2e7 | note | H
aef1fb3d-c743-5c5b-a1c0-5c9fafdb86f8 | note | Detail - Raised Table ramps to have 200mm depth at entry point and tie into 300mm depth to meet raised table
b4dd87b3-ebe3-5416-8620-0b1f5f1202dc | note | Frequency - Prior to pouring concrete
ac922763-ef41-5f6e-8ee4-52dc17366674 | note | Inspection / Test Method - Measurement
06d10162-7262-50f6-ae5c-701b37d191ee | note | Conformance Criteria - Designer to inspect formation level
abee5aa0-5a97-545c-918d-9b6ddf8d7cd4 | note | Records - Site photos
2ffb97bb-2f91-57c1-a373-09fd34b722b7 | note | FH Initials - Site Engineer
f1b9308b-0cd4-53e4-b5ea-0057de2ca304 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
1cd91e7f-5280-550e-a9a8-08adc7a04cd8 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 8.3 -
cf7259db-8817-55fd-b095-0c73cf5cb493 | note | Inspection / Test Point -
cffbf74e-43da-5af8-a685-a5e860e632a0 | note | H
a575462e-2e66-5df8-bada-406f187b6fef | note | Detail - Raised Table ramps to be 1m across for entry and 1m for departure ramp.Toe to be 1m across for both entry and departure.
f526e8a4-9c0a-567a-a0c7-caf9514f02db | note | Frequency - Prior to pouring concrete
e128c77f-ea8d-5369-95b0-ceb1b9e0ed8b | note | Inspection / Test Method - Measurement
f822ae59-18ab-5cbb-b183-b8fe7b124dfb | note | Conformance Criteria - Designer to inspect formation level
5d841fad-5faf-5884-8201-a2f0339a0966 | note | Records - Site photos
9c064ee0-4687-5858-9922-2d4625266b7b | note | FH Initials - Site Engineer
d7141896-6b2e-5795-9693-b970db5797c0 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
cc2fa409-6cc1-5933-bff9-004143a6ba00 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 8.4 -
809acc86-0179-5be2-91cd-08f87e20497f | note | Inspection / Test Point -
523120a9-7eb7-51df-9210-803ce173b7b0 | note | H
a0103c76-e174-585b-9043-325f91d23e16 | note | Detail - Raised Table ramps to be 1:10 gradient for ramps - Relative gradient on West facing gradient -15.65% and opposite ramp to be 4.84% relative to the existing road.
077027c6-ae79-5430-b4f1-7aef1da900b8 | note | Frequency - Prior to pouring concrete
55794c87-4d91-5ecf-8f0b-2f7fd0a34cef | note | Inspection / Test Method - Measurement
ed27ac7c-8d27-5edc-b854-f921fe57af6a | note | Conformance Criteria - Designer to inspect gradient level
93ed3f34-6123-5fd6-af30-bb86ad2190f9 | note | Records - Site photos / Concrete Formwork Checklist
d01d2aa2-8731-5056-9768-0eb4c8824f45 | note | FH Initials - Site Engineer
6b177078-6788-5e8d-a3e7-c4f4661c50aa | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
8e44186b-426a-55f0-aa88-196449d1a658 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 8.5 -
bdfddb63-387c-50fc-a435-a4511a74d5b8 | note | Inspection / Test Point -
2c2b992a-b38e-52ae-a5e8-464671df82a9 | note | H
ad24e90a-221f-580e-90f8-2e3580cc4e9c | note | Detail - The Site Engineer and MSQA Engineer must sign off the formwork prior to concrete being poured
b940f216-4dde-576e-91a9-623911d2a6a4 | note | Frequency - Prior to concrete pour
f61cdf8e-d567-56d5-a741-d9943ca867cc | note | Inspection / Test Method - Visual inspection
880c62a5-966e-5007-94c9-cfba567e688f | note | Conformance Criteria - Concrete Inspection Record
fb5338e7-a6fa-5bbd-89a4-c5944f745e41 | note | Records - Concrete Formwork Checklist
447fc002-64fe-5827-8871-2787a9669a94 | note | FH Initials - Site Engineer
10d53eb2-184f-5965-b3ee-c0e14a0b7506 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
16c4d265-229b-5b53-94d3-efa08ee35046 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 9 - Reinforcing
43a8fea4-f4c4-5854-b81e-dad60b734755 | note | Inspection / Test Point - Reinforcing
b0f00231-d6c1-57d4-9502-84c23003faf1 | note | H
d3aab46e-c7d0-576f-b5e6-a34727f845e5 | note | Detail - All construction joints are to contain 2 rows of LESA dowels or similar approved dowels . Dominator dowell system 50mm w/ Black 300*50*6mm plates @600 centres placed across the construction joint
e2de17f4-8f75-538e-a850-1afafcb35e47 | note | Frequency - Prior to pouring concrete
e41cfc49-bf99-5918-bcc0-e6fc4468f1d8 | note | Inspection / Test Method - Measurement
e7d69dd7-ab32-5288-b091-49f2a46c1fc3 | note | Conformance Criteria - Concrete Inspection Record
df22f3b1-b55b-5e31-8317-1e89b10ca79c | note | Records - Site photos/Concrete Formwork Checklist
7a0cfa71-ae5e-546c-a063-7e4ddab9bcfe | note | FH Initials - Site Engineer
0d7e1b33-0389-59de-8df9-e80285e541d0 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
57af00e1-0fc1-5e33-ae4c-4eb013d1263c | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 10 - Concreting
99da54a5-ec62-549c-ac4e-9bd1271d5fe3 | note | Inspection / Test Point - Concreting
73c12378-9394-5cd4-9bd1-4be3829732ce | note | H
e9d24a95-a77f-5a9e-a65f-c2e22912bc74 | note | Detail - The MSQA Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required
134edb2b-a7ef-5e3b-ae1f-5cdb1e70445f | note | Frequency - Prior to concrete pour
ce6309c8-2325-53ba-9416-bd5637d1e8ba | note | Inspection / Test Method - Visual inspection
8dbb4216-c585-520a-b1ed-f133873bf611 | note | Conformance Criteria - Engineer will be notified via email/SMS at least 24 hours before required for inspection
f025e74b-00fc-5e79-8e74-6658c54f86fe | note | Records - Email / SMS
59535eb1-f107-567e-8b14-7a460ccc54e3 | note | FH Initials - Site Engineer
359cdf6b-8db2-5651-9c3c-6805b4198754 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
d3af23c8-12ba-5a51-b329-c55a201cdcd3 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 10.1 -
a5f5341d-e646-5023-8630-4bd95ff16993 | note | Inspection / Test Point -
2067b1ae-48b8-59b0-950b-12e8ef3a7812 | note | W
204abf4f-51d2-5807-9fc4-1467d743129f | note | Detail - Vibrator to be used throughout concrete pour
af0d849f-267e-5f66-98cc-964f5b2a0e95 | note | Frequency - When pouring concrete
0e62d0f4-41b8-5bdb-9cfa-94cf33023419 | note | Inspection / Test Method - Visual Inspection
7300680d-a550-5381-9e98-62f5d11ad4cc | note | Conformance Criteria - Concrete Inspection Record
c125c121-b1ae-5882-b8bc-35b894b643aa | note | Records - Concrete Formwork Checklist
a60f8b6d-7550-5d36-969e-5bb648a780bd | note | FH Initials - Site Engineer
38981dc9-67d4-5f7a-8318-aefe6b58e73b | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
e73e3e8b-9112-5589-af1d-4762471f6cb9 | textbox | Date Completed:
| checkpoint | 10.2 -
2cde7243-830a-5604-8f24-5471dbecd2f4 | note | Inspection / Test Point -
03521f9f-8494-5cd5-b964-541c851ce8dd | note | H
9d9931aa-a18c-5eed-8091-5c64bf67930b | note | Detail - Concrete surfaces shall be U5 broomed finish
c4ac6d3e-d75b-5d70-9ff5-149374df9d25 | note | Frequency - At completion of pour
77891a4e-5cfd-5146-83e6-56465b56f6d8 | note | Inspection / Test Method - Visual inspection
b55ced94-ac42-5c64-9656-e53185787f1b | note | Conformance Criteria - Concrete Inspection Record
93748e74-46f2-5479-a89e-eb2dc7269c66 | note | Records - Concrete Formwork Checklist
df8eec84-53af-54ab-9c4d-01656c537df8 | note | FH Initials - Site Engineer
00f6ed37-2764-54ce-8ff6-56f63f77b18b | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - MSQA Engineer
48866e52-6cbb-5baf-858a-9a085dd06f7d | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 11 - Curing
0cf6c877-d652-570d-bde2-b6a955ae191a | note | Inspection / Test Point - Curing
83155ea5-85b9-5084-a84f-6cd5b2025025 | note | M
0c46729c-f18a-50d9-b920-1466678f6725 | note | Detail - Concrete will be left for 48 hours minimum to cure before traffic is allowed on it.
a8ec689c-89d3-5e9b-80be-3c9dd421e17e | note | Frequency - Post Pour
5f4f41ec-56a8-5c1f-ad56-9d3d4700d47a | note | Inspection / Test Method - Monitoring the time allowed for curing
dfb8b72d-0231-5559-afc4-a029982a4a91 | note | Conformance Criteria - 48 hours minimum have passed
025216c1-58fc-5dec-9453-05ca8d74f793 | note | Records - Concrete Formwork Checklist
89383147-1a51-50d5-8e0e-1ebc842c9e1f | note | FH Initials - Site Engineer
b8f3d0c4-38dd-543d-a32d-2d9e47e9dfe9 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
9735d079-d9e2-54ab-8828-113e64145534 | textbox | Date Completed:
| checkpoint | 12 - Remove formwork
8997c4b5-ce79-5b2c-8706-550d45bdf1ef | note | Inspection / Test Point - Remove formwork
5b10b369-7e2b-5350-b421-8c30a03949ae | note | W
21c383a5-e117-59fc-b67d-8fea001524a8 | note | Detail - Remove formwork after 48 hours
b1bde4c8-738e-5fe7-b8fe-dafafc69f807 | note | Frequency - Post Curing
6dd9f1c0-7026-5835-af37-0157105f97d0 | note | Inspection / Test Method - Visual inspection
769ce260-43cc-5dfd-a802-7cccdbd46424 | note | Conformance Criteria - Concrete Inspection Record
5c53197b-cc78-56ef-9c70-f90dd46d2132 | note | Records - Concrete Formwork Checklist
4dbe64e4-cf13-5ce7-93c6-31dc417c771d | note | FH Initials - Site Engineer
d0193b0a-a38e-57a0-9900-d181dacda300 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
5f73c89a-d94a-55e9-9297-78a7f793c90b | textbox | Date Completed:
| checkpoint | 13 - Asphalt- Concrete extension slab/ Toe
01f8a909-bccb-555e-85d3-906dfa160b5f | note | Inspection / Test Point - Asphalt- Concrete extension slab/ Toe
0ae6706a-03d1-5965-a7be-81cafe7cbdeb | note | H
c13137fe-a397-5554-a158-be0cddb4a18c | note | Detail - One row of Lesa diamond placed mid depth @600 C/C along construction joint as per TDM TC003
fcae4168-d4ca-5958-8f58-5c42cc892939 | note | Frequency - Prior to pouring concrete
5452dcd8-9201-549d-808f-0aa7b71c723e | note | Inspection / Test Method - Measurement
a5ce4cec-9917-55d5-af40-5a3e6ab4129b | note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
2db35800-8810-57fe-bcca-3cd50b0e3ead | note | Records - Site photos,delivery dockets
52c750f0-f354-59c6-bc65-1d31779cbced | note | FH Initials - Site Engineer
6195829e-3bc6-56c6-bb70-739efdb70717 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
bcd09e8f-2094-5fea-a996-aa182c59ed89 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 13.1 -
46ed7292-aafc-5b62-9045-ca72934bfd36 | note | Inspection / Test Point -
df276c4e-9b95-5fe2-b7e8-f1caf7190594 | note | H
c72f2809-3f50-50ce-9af1-ca4e90cd443c | note | Detail - 150mm thick 40MPa Concrete with two layers of 663 mesh
444dd07d-6582-5843-9d7f-42e82fe14ac5 | note | Frequency - Prior to pouring concrete
62512584-4c5d-57f7-9fdb-97266230ee73 | note | Inspection / Test Method - Measurement
5fad9981-1280-58d9-8a0f-27b496041cc5 | note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
fd7ff8b7-11ae-5da1-9a65-1420cce51513 | note | Records - Site photos,delivery dockets
efa807c7-ed54-53fb-842a-600afdf13d69 | note | FH Initials - Site Engineer
6f7aef7d-b1bb-5ab7-95dc-2ced99cfeb79 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
9fd187b3-353a-5030-85f0-5433f902bb5e | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 13.2 -
4c482c4e-6c0e-52ad-9b35-4acc4c2dc3b6 | note | Inspection / Test Point -
1c001d78-24c6-5945-bbb7-92edd9d696fb | note | W
805ec9ba-938f-5d3f-ab5e-7ba5265bd01f | note | Detail - Tack Coat between DG10 and Concrete slab
1702fbbf-db15-542e-8838-cc9a00c8e4c4 | note | Frequency - Post Curing
295001fc-9922-50dd-937f-2bae9b21c80b | note | Inspection / Test Method - Visual inspection
1b1fac60-481d-51fe-a6e7-43645c5da5a6 | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
f23b5515-89cd-5aab-9db6-774798f094e1 | note | Records - Site photos
a30ef7a5-ed09-5767-ab67-171cb32e6fd9 | note | FH Initials - Site Engineer
28ba0be8-1591-5ea5-b605-038cff3a9dd4 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
642734a8-6112-5f7a-b51b-da4305a6ea6f | textbox | Date Completed:
| checkpoint | 13.3 -
49c18251-c39d-5b18-9b87-50cddd84fc24 | note | Inspection / Test Point -
fc68b62f-e706-537c-a215-d318f66dc9e3 | note | W
e5dd5797-3d6c-5c49-8bc5-7c6ae3b05800 | note | Detail - 50mm thick DG10
df15c467-be19-57ce-a8d8-f1fe75726e82 | note | Frequency - Post Curing
8c636bba-4785-5a05-98d5-4353d4f060d9 | note | Inspection / Test Method - Measurement
a43f4b16-0be9-5bf4-a617-9a97d20980fd | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
d760ccf3-d609-5e9d-9c64-3d0d5545df39 | note | Records - Site photos,delivery dockets
0bf0ecd2-330b-5c25-bf8c-a5e8205eebc3 | note | FH Initials - Site Engineer
142394f6-9f2c-5279-a31b-133015d4e595 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
32fe33e9-e317-547a-b679-4e9ad0953c3c | textbox | Date Completed:
| checkpoint | 14 - Lot Number QA File
dbe15c1d-70a3-5ae3-b87e-93565ab8987b | note | Inspection / Test Point - Lot Number QA File
a0adf221-1b22-5f9d-95ae-ef8aeb9ebf74 | note | W
9d64a391-3ecc-5efc-8559-993181bdeb86 | note | Detail - Ensure all QA Records,site photos and incident cases (OFIs) are closed and included within QA file
9d5ccd2a-fe55-5a5d-a100-acbb27da1cd7 | note | Frequency - At completion of Lot
144dafc4-468e-52a8-911b-e93e8f068d11 | note | Inspection / Test Method - Document Review
065b6eb3-169a-5e3c-90c7-a07a8a46ab4e | note | Conformance Criteria - All QA files compiled and submitted to client
bb1c226c-5a41-5ecf-8e4d-28422ee7de28 | note | Records - QA records
b93f1afa-fdfc-52a1-9ca4-78c71b544e11 | note | FH Initials - Site Engineer
8000dbb8-95e1-5401-873f-3b3e90c2b2d8 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
510655b2-9a09-5148-877d-5f2ed7e70f1a | textbox | Date Completed:
| checkpoint | 14.1 -
40129fc6-1726-5dd2-afbe-2edc41785bd2 | note | Inspection / Test Point -
961c54c5-5ff1-5247-824e-c463b184032b | note | W
62e446ee-6ac0-5322-b916-9d40a597c238 | note | Detail - Delivery Dockets to be included in QA file
106e14c7-a251-5289-a7ca-630ec9732850 | note | Frequency - At completion of Lot
c5e69c99-7864-5677-8621-c3aaf8276d01 | note | Inspection / Test Method - Document Review
e381093f-ab4b-54ff-8b2a-bfdaa2d89dff | note | Conformance Criteria - Delivery Dockets to be included in QA file
2246a588-8c70-56d5-a3d4-8887b0391b49 | note | Records - QA records
273dcf78-143a-55ff-8154-63cc1e2d5392 | note | FH Initials - Site Engineer
0cbd7be6-8f05-53b6-a5d9-82a68da6ae93 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
590467c2-6871-5315-988b-8875742c4eb5 | textbox | Date Completed:
| checkpoint | 15 - As-builts
a753e2fc-45f6-5401-a5bc-f172864e569e | note | Inspection / Test Point - As-builts
bac2e36b-6af5-5d91-adc5-68546ff8ebef | note | H
1211bc1d-1c80-5927-b408-cd1f81eb2a99 | note | Detail - Red pen mark up drawings to be included in QA file
404c61db-e3c6-5aac-bf68-151efb2da34c | note | Frequency - At the completion of the Lot of work
38b682fc-8bbf-5dca-ab29-b8cbe6b3ef1a | note | Inspection / Test Method - Drawings
f6b819fd-9576-5e26-9285-954156e5ae44 | note | Conformance Criteria -
7501d270-a329-5758-9c06-9385eedb66c6 | note | Records - Asbuilt Drawing
05822c9c-686e-5907-99f2-711d555e8269 | note | FH Initials - Site Engineer
053a1fbe-4bab-538f-ae38-ac5e4c21bef2 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
b33986f9-cd69-5b5d-862c-247aa2f96974 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | Final Inspection
3a3eca8a-5721-5ea2-9546-1a7cca8913e7 | textbox | Comments:
d639ff9d-2c96-5599-a916-90c7e6fd4e72 | textbox | IFC Drawings used for Construction incl. Rev numbers:
95715a9b-39bc-5bba-a3cb-92c23a03d1a6 | textbox | Reference Documentation (Notices/OFIs etc.):
e4bb9c68-6ad4-5af3-a853-aad2f173ecbe | textbox | QA Compiled By :
b20552cc-9ba2-569f-ac38-9376080cb5c7 | textbox | QA checked By Discipline Manager:
9b8f9114-0d47-5c5a-acc7-c95efe09a408 | textbox | QA checked By Quality Manager:
48d3184c-b4cd-5834-bd0c-f6333f7bde91 | textbox | Accepted By Design Engineer:
| checklist | ITP - Willcott Street - Stormwater Drainage | itp | ITP - Willcott Street - Stormwater Drainage | 0938e20a-9b2e-4040-bebe-b54f8425f7e1
| checkpoint | 1 - Permits & Services
9e1b1722-24ed-5f27-b99b-25ef6b7d34a5 | note | Inspection / Test Point - Permits & Services
bc7b8882-9ddb-55da-a406-be570fce41a4 | note | H
f7a337c2-b95a-5abd-9871-31fa3bc01c01 | note | Detail - Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
e6df2b6d-2d68-5088-be5d-1e6047df8d39 | note | Frequency - Prior to any construction commencing
6aa57308-ec1a-5d14-a816-f8e9ceffcdd4 | note | Inspection / Test Method - Document Review
c04286aa-1155-56cd-a13b-d4f8d746435b | note | Conformance Criteria - Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority
12eb20fe-6195-5b30-9bb0-60224ebe5d3b | note | Records - Permit attached or permit number noted.
be77751a-f2c8-5e4d-9aec-8bd8c68f8c40 | note | FH Initials - Site Engineer
d004627d-f6d1-5531-965f-efd5f4363c30 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
8f8ff762-8413-5e4d-be38-ea0e0fc0a3cf | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 1 - Permits & Services
c14d64d0-ddf8-52da-9bfa-d4ad7e234f19 | note | Inspection / Test Point - Permits & Services
e9a9c2ed-ac14-5c1b-a0e3-b42a0cd36a1a | note | H
68abfa43-3bc7-540c-a9ce-720b66b808a5 | note | Detail - Locate and mark out all existing services
c16acfe2-f079-5cec-8023-8a17e59e9b14 | note | Frequency - Prior to any construction commencing
899f65bc-4998-5bf3-a736-0cf6121eef44 | note | Inspection / Test Method -
f207972e-91a1-5ff2-9395-d455576263f1 | note | Conformance Criteria - B4u dig procedure - follow utility protocols
573758af-4f73-54dc-b60c-4fb6635d750b | note | Records - B4u dig plans & GPR report attached
4c6bccfd-a55f-5fd7-bacb-7779663cd2cb | note | FH Initials - Site Engineer
6edffc4a-4c84-5ded-a983-d6aa8a135a1f | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
ad022c03-8347-5e72-94c4-05d8de1aeedc | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 2 - Pre-Construction Sign Offs
adb38019-075f-5de3-af01-c036a7565b3e | note | Inspection / Test Point - Pre-Construction Sign Offs
2c351b6c-2d9d-57a2-864f-a068eb358f58 | note | H
3cf7088f-c1d1-5c62-91fc-ea6a220174d0 | note | Detail - Sub-Contract and Supplier Agreements
e5d922de-aba2-54d2-8fb1-c42bfc47ab15 | note | Frequency - Prior to commencement.
fd120b66-40e5-5847-81d6-028403edc031 | note | Inspection / Test Method - Document Review
ff5c9f64-4be3-53bf-83c0-f34a4b420159 | note | Conformance Criteria - Sub-Contract and Supplier Agreements to be agreed and signed
fccf0371-fcb5-5e06-8716-12b16370689c | note | Records - Subcontract and Supplier Agreements
21a1de00-0bb4-5db4-a3c4-63586e11d99a | note | FH Initials - Site Engineer
80f3d2eb-4852-5f10-970d-3c4d4793a622 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
98db86b0-e9c7-5e15-865a-f9f49baa5814 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 3 - Design
de2654f3-9828-5f58-877f-123abd60fa54 | note | Inspection / Test Point - Design
3b1eeb65-7d27-5354-a139-0602d1f0a93a | note | H
c808960b-8a13-57d4-84f7-38573a545de5 | note | Detail - Design is approved and Drawings are of the latest revision.
de8c7b82-260f-5c8d-b2c1-05351205b8f4 | note | Frequency - Prior to commencement.
79151b19-21ad-54e7-aeba-b9374768cfce | note | Inspection / Test Method - Document Review
2e3f7b10-cb2d-5863-b74e-96e6aa3e7fc4 | note | Conformance Criteria - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
9b21d522-91dc-5b43-8e3a-07a9f4c455de | note | Records - Drawing Register.
452c6809-38ac-5337-8ba9-082d9dd22e80 | note | FH Initials - Site Engineer
cb74b01c-c04b-51ed-8911-b942ddbb4ace | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - Engineers Rep.
37a8ed8c-7867-5435-b0ba-0b9603f5e060 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 4 - Survey Setout
7bff0a75-9c58-54c8-a9bb-004d7028c3f9 | note | Inspection / Test Point - Survey Setout
7497921f-b1eb-590a-97f1-5c381f5fe365 | note | H
994188ae-3c79-5b2b-a456-772eaf66b90c | note | Detail - Setout Pipe Alignment and Service Locations with inlet & outlet points and inverts as required to construct to design
36f4eba3-a495-5b0d-9759-ced13ff5d439 | note | Frequency - Prior to commencement.
f0047127-6078-5ec9-af65-e8158f54a961 | note | Inspection / Test Method - Survey
39294bfc-8d20-5e2f-a398-ecddeaf14e1f | note | Conformance Criteria - As per Blue Barn Consulting Engineering Drawings: 02088.02-T-700 & Setout files
5910ddc3-66bd-5a23-9243-ec4b68fd5175 | note | Records - Survey Receipt.
6904b18f-28dd-5ada-9586-eb35cb389e83 | note | FH Initials - Site Engineer
4cea45a0-0b26-5ee7-bd98-cb5f4be04b0e | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
84364298-f737-591d-a8e4-d203a0334180 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 5 - Pipe and Manhole Material Compliance
b0db6b6b-31e5-5aa7-8d8f-977fd256bddc | note | Inspection / Test Point - Pipe and Manhole Material Compliance
74c5ea15-c65d-58e4-b882-0d0e12cc7fa2 | note | H
df9b84a8-41a1-518f-b677-7d76f8822085 | note | Detail - Cesspit, Manhole and Pipe shall comply with relevant AT/TDM standards
aee9cee3-3300-568b-8ab3-55c8823085e9 | note | Frequency - Prior to commencement.
a9f5da16-6260-5ebd-8a78-8e85934997c2 | note | Inspection / Test Method - Document Review, Visual Inspection
edd01d42-aca4-5ab1-aa86-a0097c8668ca | note | Conformance Criteria - Pipe shall be Check for freshly formed pipes and return if required 1) DN225 Class 4 RCRRJ pipes AS/NZS 4058 2). All Concrete RCRRJ pipes to be fitted with Rubber rings 3). Pipes shall have product certification (ISO Type 5) to AS/NZS 4058 Prefabricated concrete Manhole shall be in accordance with TDM Standards & AC COP
cfebb0cb-33c4-5bff-ab21-5da568141b64 | note | Records - Manufacturers Data Sheets, Delivery Dockets
fddab239-2cff-5a91-b76f-1b7b7862026b | note | FH Initials - Site Engineer
4db5a58e-63c6-50d3-9d84-f73c1965c8c6 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
7a9f285f-9b51-59c0-95af-aae7a3cfb98f | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 6 - Locate Existing Services by Hand Digging / Hydro Vac
0c68d250-088c-5a3a-9eb5-9febd73f9442 | note | Inspection / Test Point - Locate Existing Services by Hand Digging / Hydro Vac
b3feb558-013c-5357-af5e-4edb543208db | note | H
c7e28837-8ce8-56b8-88f7-23469c0de7ca | note | Detail - Ensure all services conflicting with the line of trench have been exposed by hand digging.
54d159e8-2c47-5df1-aa74-71737121d72b | note | Frequency - Prior to commencement.
999ac2d1-39f5-5d1d-98e8-4e54e5e285cf | note | Inspection / Test Method - Potholing / Survey
ba4e9290-12b3-5406-8b94-eb4d19e6d374 | note | Conformance Criteria - All conflicts have been located. New services and / or conflicts to be advised to Project Manager.
3c6ea454-6cb3-536f-af9d-215e34806586 | note | Records - As-built Drawings. Doc. Review
14795dc3-c4e9-5345-befd-48c994b3882d | note | FH Initials - Site Engineer
37f4944a-d285-5078-a72e-966506de9ba9 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
219fa8e5-7cdc-52b1-956c-de6c3e7ed603 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 7 - Trenching & Excavation
e2600ae5-de24-5694-be2b-f7db8320a162 | note | Inspection / Test Point - Trenching & Excavation
1b2295d3-56db-50c9-890c-b8df90039216 | note | H
bfc006ef-5652-5c26-8bdb-219920a00324 | note | Detail - Excavation methodology
747002bf-f984-5059-96f4-d08564263abc | note | Frequency - Daily
2eb5a53c-2f08-579f-ad6a-a99372538be0 | note | Inspection / Test Method - Prestart review
d6f773f0-90d7-5952-897d-02fa9a687ad0 | note | Conformance Criteria - The excavation, benching and shoring requirements shall be in accordance with Worksafe Excavation safety guidelines (2016)
0901d3dc-cadf-5243-afad-39d52c74ba3a | note | Records - Prestart RCP
b86fcab1-c562-518b-9e99-a66f2932a4c5 | note | FH Initials - Site Engineer
201a30ac-25ac-5031-92e6-ebe95ddc76c2 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
2f73a44a-8708-5cec-aacf-1afec37ac514 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 7 - Trenching & Excavation
cb62c4d4-1e8f-5293-ac55-d08cb2be1d3b | note | Inspection / Test Point - Trenching & Excavation
bd525f13-8654-58dd-bd9f-0ae22ec1f07b | note | M
af259e3a-746c-5cf6-8238-6e1a32647943 | note | Detail - Trench Profile - Width
acd705ad-6c22-50c3-87a8-bf41ed3133da | note | Frequency - Daily / as trenching takes place. Different depth methodology
2275def1-fd64-5353-b640-c4c8cb6bdb76 | note | Inspection / Test Method - Visual Inspection, Excavation methodology
fc632835-60b8-5b11-917b-5ee784f2dcdb | note | Conformance Criteria - Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing
63c9b7e2-1b7e-534a-818f-057b03e6c56c | note | Records - Construction Photos
270e581d-5a83-5614-b42d-3f846062410f | note | FH Initials - Site Engineer
f031ede9-f427-5e7c-bb4b-7d66ef3679c6 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
51dcf10a-ff44-5b2e-908d-fb0808aaccab | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 7 - Trenching & Excavation
a08e2d36-92f8-5899-bd1c-b8d889837605 | note | Inspection / Test Point - Trenching & Excavation
f4ae7d03-c3a6-5281-aef6-dbb0a4b71f6f | note | W
141a230e-cc34-5719-a166-9e5b9b3e867e | note | Detail - Trench Profile - Depth
f71e327d-dfd8-5c87-be68-d91016412e6f | note | Frequency - Daily / as trenching takes place.
5fe27610-b649-5819-9a7f-d8231de1e6e1 | note | Inspection / Test Method - Visual Inspection, Measurement
82ff9485-590d-542a-b2d1-bcd1af06761d | note | Conformance Criteria - Trench depth varies according to long section and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings
b4eb2a39-8c5a-5047-918c-6552079ed09e | note | Records - FH Drainage Line Record / Construction Photos
6df3d911-8acc-58aa-891c-81d5882e7330 | note | FH Initials - Site Engineer
cf1e5fd4-8f1f-5b89-9367-1bf45236776d | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
51394ecd-a31e-5397-a377-82eacc1816f3 | textbox | Date Completed:
| signoff | HOLDPOINT
| checkpoint | 8 - Bedding for Concrete Pipe Laying & Manhole & Cesspit
4c7c9272-eff1-5acd-84f8-db1fab8aa947 | note | Inspection / Test Point - Bedding for Concrete Pipe Laying & Manhole & Cesspit
bec162cc-0751-5cc4-9a68-73544d33bcc5 | note | W
08e29c25-23bc-5a28-b4fe-15d8db09fd0e | note | Detail - Placing and compaction of Bedding Material.
9caeaa7a-6924-514e-bb7e-b48fae0192cd | note | Frequency - Inspected continuously during placing and compaction of Bedding Material.
fad4dd50-05b1-5e65-8a6a-03cff0ce3c1b | note | Inspection / Test Method - Visual Inspection
9c61de39-e419-5b43-b15e-c63285d694c0 | note | Conformance Criteria - Bedding & Pipe surround material to be GAP7 or GAP 20 (Stevenson Quarry) or alternate material that complies with AS/NZS 3725
cc8471da-0b39-5a48-9cbb-e6b865962cd9 | note | Records - FH Drainage Line Record / Construction Photos
9c7e7d83-9d37-5045-abf9-76ef3b218022 | note | FH Initials - Site Engineer
ea341e16-e689-524e-9ee3-d148e6d9c1e7 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
c5ce94ea-1031-5502-be30-2351bfe6dbc2 | textbox | Date Completed:
| checkpoint | 9 - Pipe Position Tolerance
b61c7a2f-5e32-5665-a911-198f7876c31c | note | Inspection / Test Point - Pipe Position Tolerance
59498faa-a625-542c-a08b-7999ccfc363a | note | M
717d24a3-77f6-5200-82a1-38fb4590ff17 | note | Detail -
c9f1f96c-ecc1-5387-99d9-eea95beea3c9 | note | Frequency - At any point of pipe
ec66905c-a760-5dd5-b416-f21827fe73be | note | Inspection / Test Method -
097d8156-ada1-5903-aa8a-b0bc46549e5e | note | Conformance Criteria - Position tolerance for pipe laying at any point along the length of the installation shall be within ±30 mm from the specified design.
fb66ddee-e05d-509f-9951-e324590582ca | note | Records - FH Drainage Line Record, Survey Data.
c065e9fb-4d58-5379-b3ef-f0fac625ea4e | note | FH Initials - Site Engineer
9ba6e7f1-eb57-5d12-9e8a-3fa7546d954c | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
e44ff11b-93f4-5ae2-8932-568bd3c2a0d1 | textbox | Date Completed:
| checkpoint | 10 - Trench Backfill - Placing & Compacting
40279805-6db7-558b-863b-ef9ff4807984 | note | Inspection / Test Point - Trench Backfill - Placing & Compacting
28595c35-e900-552b-bb71-190d647a3cf2 | note | M
40e557b8-18cf-5ab7-8215-e6b0c59d89ab | note | Detail - Placing and compacting of Trench Backfill Material
14c863ca-20ae-5c90-a282-1175340623e7 | note | Frequency - Throughout Trench Backfilling operation.
956d83d2-e052-55c1-94e4-61f78de3f3d9 | note | Inspection / Test Method - Visual Inspection
4b6d1b6a-11a8-5690-b01e-ba1c0b22f868 | note | Conformance Criteria - Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm
e6f2295b-f1f5-5ded-a024-7e33dbea923d | note | Records - Construction Photos
eec58562-4eb4-5641-b724-d5fa69f0d3b4 | note | FH Initials - Site Engineer
89f7a92a-0c58-541d-afa9-c7bf46340bc6 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) -
4a8196d3-f32e-5db3-8bda-6e9fb553b082 | textbox | Date Completed:
| checkpoint | 11 - As-Built Drawings
153b3e07-d166-5b34-a090-21110f60896e | note | Inspection / Test Point - As-Built Drawings
75b4f9ea-538c-5de6-9ee1-4b2de7e14a36 | note | W
52200537-2aaf-531c-a32f-8f9b37561499 | note | Detail - Red pen marked-up As-Builts of every 'Issued for Construction' AT drawings
a81ed0ad-6591-5a50-be47-28b2ac0ca206 | note | Frequency - Final As-Built Drawings to be completed within three months of the construction completion of the asset or infrastructure.
b3b19c22-5a72-550b-9173-c2c2052da737 | note | Inspection / Test Method - Drawings / Visual Inspection
a9eea2b3-842f-597a-8211-9519159d5d31 | note | Conformance Criteria - As Built and GIS Data
421920d2-fbd9-5925-bf08-538ecd381de0 | note | Records - Redline As-Built Drawings, scanned as .pdf files.
73de1352-3324-53da-9686-5b8e70c52ae6 | note | FH Initials - Site Engineer
d8de9881-1747-55dc-b4a5-5a662376d800 | note | Design Engineer/MSQA Engineer Initials (Grey if not required) - Engineers Rep.
03acaf1e-aca5-53c9-ba08-f3cc9a2968ea | textbox | Date Completed:
| checkpoint | Final Inspection
0c7fc7e2-33a0-5e85-9157-9b8548fa270c | textbox | QA checked By Quality Manager:
5399ef2b-ceae-536f-b388-2c123bfdd8ae | textbox | Accepted By Engineers Rep:
| checklist | Lincoln Rd - ITP - Enabling Works - Footpath, Kerb and Channel |  | Enabling Works - Footpath, Kerb and Channel | 7e5e2b31-8cdd-4039-9ad9-967092ba3af4
| section | Site Set Out
| checkpoint | 1 - Site Set out
2e35f882-56e7-54d1-9283-1563f8f1a17e | note | VERIFICATION ACTIVITY - Surveyor
475c69c9-d1e7-531f-91f7-89ae2ce9c946 | note | METHODS OR REFERENCE - Surveyor
774cde07-75d5-5655-839a-0abe5b16602e | note | FREQUENCY - Every site
89a654c9-b2bf-5ffc-b1be-754d3a233c06 | note | ACCEPTANCE CRITERIA - Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
0a50718b-be03-569c-967f-0f6510111d68 | note | Hold Point - Mandatory HOLD POINT -
72d885d4-a3bc-5904-8af7-f3e927a9d6f2 | note | Records - Onsite records/photos
fdc3dff4-ac01-5d41-9a50-961d4f2637dd | note | Onsite Responsibility - Site Engineer
| signoff | HOLD POINT
| section | Materials
| checkpoint | 2 - Kerb & Channel
f54ce2cc-8018-58b7-8832-2894068104b6 | note | VERIFICATION ACTIVITY - QA FORM
dbda9fbf-c76a-57d6-a542-f523b8677ce0 | note | METHODS OR REFERENCE - TDM Technical Standards - KC0001
a71a8742-f013-5247-aa8f-491163de8a7c | note | FREQUENCY - Every site
fdf10c90-4d18-5423-bd55-c18f850a5767 | note | ACCEPTANCE CRITERIA - Kerb & Channel to be laid using precast hand-laid. On compacted GAP40. Concrete 20MPa @28 Days on 100mm GAP40 with the subgrade CBR>5
e76866bb-4bd3-50d8-95c1-a717aed8c0b1 | note | Hold Point - In process Inspection
5f1a26a0-adcf-517b-86ec-4b29c7ab1bf7 | note | Records - FH concrete QA sheet, photos. Concrete Plant Docket
fce78c38-e944-579b-8c15-a2ea3d02f1f2 | note | Onsite Responsibility - Site Engineer
| checkpoint | 3 - Channel Level
7bf3b462-9e64-5978-a921-85e50f5d32e7 | note | VERIFICATION ACTIVITY - QA FORM
d40016a3-7248-5713-bbb8-0cc4cfd8f441 | note | METHODS OR REFERENCE - TDM Technical Standards - KC0001
76269370-a26d-5295-b50d-2800bdcb860e | note | FREQUENCY - Every site
30f23f60-7e85-5ed4-8e25-e169f0a12ed1 | note | ACCEPTANCE CRITERIA - Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
2bf76ca8-0280-546f-94e7-d654e7331c54 | note | Hold Point - In process Inspection
680fa24d-2def-52c4-baab-da6da7821303 | note | Records - FH concrete QA sheet
875b48d8-c840-50f2-b2f2-d085c748288e | note | Onsite Responsibility - Site Engineer
| section | CIVIL WORKS
| checkpoint | 4 - Concrete Footpaths
3f5a8f75-0b64-5139-a5ea-f5d956933882 | note | VERIFICATION ACTIVITY - QA FORM
333a8c8c-528f-5c98-8bf8-4cca8c8b6313 | note | METHODS OR REFERENCE - TDM Technical Standards - FP0001
6b586cc8-55eb-514a-94cf-78c429dd3343 | note | FREQUENCY - 10m Intervals
12009b88-c0c1-5840-9e9f-55dc28c3514b | note | ACCEPTANCE CRITERIA - Basecourse - 100mm min. thickness GAP40. Clegg CIV > 12. Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with room finish.
4156c2a8-2d4b-5e8d-a110-97923af4b26c | note | Hold Point - Inprocess Inspection
f2689e85-d22d-53d5-aad5-d4bedd4b07f2 | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
c533b5bd-65f9-5e34-9982-9348a8b92652 | note | Onsite Responsibility - Site Engineer
| checkpoint | 5 - Tactiles
919de33d-ec03-5810-8956-d3e86354eddf | note | VERIFICATION ACTIVITY - Visual
a83cefbd-85f6-59d3-ba3c-94641c0f1284 | note | METHODS OR REFERENCE - TDM Technical Standards - FP0010
0eeeb774-f3f9-5b76-9859-7259a87bd06e | note | FREQUENCY - Each PX
6bf5bd5f-2fba-5aea-b57b-1909abbdc082 | note | ACCEPTANCE CRITERIA - Warning TGSI tiles should have 100mm concrete slab underneath
7a623e1a-a0f0-5874-91b4-e7507d573a96 | note | Hold Point - Inprocess Inspection, Measurement
0b2ca55a-45c6-5ff1-9fea-f4038deb8018 | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
61769e94-1325-5007-9dfe-640dc9e5fbc4 | note | Onsite Responsibility - Site Engineer
| checkpoint | 5.1 - Tactiles
d1f30e31-a30e-530f-aaca-04c63430cf84 | note | VERIFICATION ACTIVITY - Visual
bcd181ab-e97b-56e2-b081-89a2c1acbeba | note | METHODS OR REFERENCE - NZTA RTS Guidelines for facilities for blind and vision impaired pedestrians. AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY.
5434909d-55f3-5b56-b012-dffa4cdf8846 | note | FREQUENCY - Every site
9742fa7d-a25c-55a9-84b4-35c5d67f47eb | note | ACCEPTANCE CRITERIA - Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
6d697790-5d69-50f8-9e0b-44bb62b212fe | note | Hold Point - In process Inspection
670e1200-869a-59e0-9a59-6dc52e015eb9 | note | Records - Photos
e2867df0-79b5-503f-a665-77e9ee8deca0 | note | Onsite Responsibility - Site Engineer
| checkpoint | 5.2 - Tactiles
6b488549-ff15-558e-a289-0b4a44de211c | note | VERIFICATION ACTIVITY - Visual
3377e19a-f09a-5cb4-9ad7-fe622accd60f | note | METHODS OR REFERENCE - AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
323b8586-7f27-5ab8-a547-052eae92afc2 | note | FREQUENCY - Every site
21356fe3-bc81-535e-8427-3c53fbf0e0fe | note | ACCEPTANCE CRITERIA - Edge of warning indicators to set back 300mm from the face of the kerb or lane, extend the full width of ramp and be 600mm deep.
0f718fca-7a1b-51b9-8487-7d654d685127 | note | Hold Point - In process Inspection
038aed7e-ea8b-5743-a239-3a863c84cac4 | note | Records - Photos
7a3efa74-8cce-54e9-8005-7fe4edd1bdc5 | note | Onsite Responsibility - Site Engineer
| checkpoint | 5.3 - Tactiles
448a340f-1899-5b0c-ba55-abbd522ed064 | note | VERIFICATION ACTIVITY - Visual
83fb59de-015c-540c-9fd1-79d4e645de02 | note | METHODS OR REFERENCE - AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
252564de-a286-50b3-95ce-58e955fb4a1d | note | FREQUENCY - Every site
00284487-ff6a-59aa-868b-45e7b3ea16c5 | note | ACCEPTANCE CRITERIA - TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
f2938a32-06ec-5ce6-9790-55e6afd0424f | note | Hold Point - In process Inspection
0e6e4058-9a21-588c-bf55-7b2e29584532 | note | Records - Photos
ce2ebc47-b760-5992-8d64-2909694c78cd | note | Onsite Responsibility - Site Engineer
| section | RAMM DATA
| checkpoint | 6 - As built information
6078c959-809c-501b-82c2-1208ec6ccbf1 | note | VERIFICATION ACTIVITY - RAMM DATA SHEET
9f0cec53-2afc-5cd3-8bc0-981779ad92d2 | note | FREQUENCY - Every Site
1751543c-2052-56a4-991e-a570a9163edc | note | ACCEPTANCE CRITERIA - As built drawings and Ramm Sheets Completed
256049e7-17df-512d-a207-2d62d9059873 | note | Hold Point - In Process Inspection
8c41a3a3-3e54-5881-ba4b-46513078b97e | note | Records - As built records
bb1b74b7-607b-5cc6-bdad-64d0303628d1 | note | Onsite Responsibility - Supervisor and Engineer
| checklist | Lincoln Rd - ITP - Raised Speed Table |  | Raised Speed Table | adde6438-a4bc-480d-80f6-ca9b1311a5aa
| checkpoint | 1 - Permits
0b17c15a-e2fc-58fd-a090-405db2507f13 | note | ACTION (Hold, Monitor, Witness) - H
cb22230f-f5a9-5448-9cfb-b534867dd34e | note | Detail - Obtain Permits
e0cd0d3d-31cc-5bb6-8bcd-51e586a60731 | note | Frequency - As required
00848616-cd65-5091-aca5-db4e1b5a8ebe | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
d8826d91-8afe-5f46-90bb-1cfd6f9943f4 | note | Conformance Criteria - Control Checklist - Fall Prevention (if applicable). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
001624fc-314d-5e45-8b76-eb37161a2d15 | note | Records - Permit attached or permit number noted
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Pre-construction sign offs
99b559fd-e190-5130-817b-e903441f75af | note | ACTION (Hold, Monitor, Witness) - H
5335d82f-28c6-52a1-a790-46f76e278370 | note | Detail - Ensure that Sub-Contract and Supplier Agreements are signed
a579be57-93c0-59e9-b086-2b18f831438a | note | Frequency - Prior to commencement
c0e5dc7a-b0f4-5fff-af74-d41794a0e1f8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
a6aa690a-7979-5ab6-9fc9-4d96e04dd34c | note | Conformance Criteria - Signed Subcontractor and Supplier Agreements
f1598841-5355-5913-bcf7-bc5f1d9802cb | note | Records - Subcontract and Supplier Agreements
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.1 -
a3487056-cbd1-5fa9-9d7d-472fb18a3774 | note | ACTION (Hold, Monitor, Witness) - H
ae5cd449-0910-5d48-93ab-9eab6880b5ca | note | Detail - Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
7d3582e3-c492-5404-aeb5-eb2c54344b68 | note | Frequency - Prior to commencement
30df5552-d8fa-5bdf-beef-058987533ed3 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
59bbd26d-4ff3-50d3-9843-bdd9a8d57ee6 | note | Conformance Criteria - TMP is approved by CAR manager for each site and works are only completed within the approved dates..
08d4e121-0811-582a-8579-6db3c4176092 | note | Records - TMP on MyWorksites/On Site
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 -
8936fd45-7179-5600-a5e3-86ffd06631bb | note | ACTION (Hold, Monitor, Witness) - H
fe990939-c4d0-5e45-a351-2595c3f6f812 | note | Detail - Ensure all Sub-Contractors and Suppliers go through FH induction
c5fdcd37-3db1-50ae-b297-52b9eb84e7eb | note | Frequency - On site daily
60a458bf-01fa-5b8d-b748-3bdca79e96c3 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Induction
f82d215e-da02-5f07-9c60-d11774d8c18e | note | Conformance Criteria - Supplier's and Subcontractor's signatures on hazard ID and pre-start documentation
6e74de83-65dc-5ff4-9731-fcabcda039f5 | note | Records - Hazard ID and Pre-starts to safety team
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Design
2e5e053b-3a02-54c4-820d-79bc51558ca3 | note | ACTION (Hold, Monitor, Witness) - H
928d7937-21e5-5b98-841c-3d7cdf65e49d | note | Detail - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
d51a6327-8c29-5fcb-b6f8-2be5b9222ba4 | note | Frequency - Prior to commencement
33717db3-d0c8-5e55-816f-be3bc07a5321 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
1c69df19-1e49-50f1-807d-7fa7a063dbb0 | note | Conformance Criteria - IFC drawings have been received by Contractor
c5695ee8-1008-5024-b346-239c1d7a2979 | note | Records - Check Drawing Register
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Installation of Erosion and Sediment Controls
1b8f0b41-84b3-5d37-8072-df2e0edac0c7 | note | ACTION (Hold, Monitor, Witness) - H
f344a6aa-e41b-57aa-b1c5-c6bc96c9f261 | note | Detail - Ensure that Erosion & Sediment Control in place
945cf361-5867-5a18-8f00-9d56c0d52213 | note | Frequency - Prior to commencement
9c26580d-5060-5371-86ce-029659e66bfd | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
a275bece-a054-50fc-886c-7d7c17126efa | note | Conformance Criteria - Territorial Authority has approved the asbuilts for the ESC controls constructed onsite and gives approval for construction to commence
541bbe28-af1f-5099-a959-dce30697c0f8 | note | Records - Environmental Controls Audit
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Survey Setout
fe31c89d-2041-57c4-95d7-544325d55135 | note | ACTION (Hold, Monitor, Witness) - H
3927b6cd-5368-50b3-8043-62448b1b8378 | note | Detail - Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations)
f9373efe-7200-5932-84bb-3b6e5a6e7857 | note | Frequency - Prior to commencement
536edf3b-309e-544c-824c-1600586bd8a9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey + Smart Level
aa9c15ca-8dea-5a32-b8c4-e23c9bdddddb | note | Conformance Criteria - Consistency with Construction Drawing
99f47c4d-f6a5-5ad7-9a8a-9d27b3687922 | note | Records - Site Photos post surveying
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Locate Existing Services by Hand Digging
bc2ff83e-1c66-5b4d-ad1b-8314c2d3f7b4 | note | ACTION (Hold, Monitor, Witness) - H
0362dae0-cf58-5d1c-b46d-01c6f2fa9b4a | note | Detail - Ensure all services conflicting with the line of trench has been exposed by hand digging
6fe85a17-d167-5155-9362-4b9775ffd918 | note | Frequency - Prior to commencement
620ad2cb-2e4a-5efd-a96a-0003485dc27d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Potholing
589912da-6a1d-53a9-893f-806ffc42aad6 | note | Conformance Criteria - All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. Asbuilt all services
4959e6b8-b668-53b3-9272-a502bff8fb56 | note | Records - Digging and excavation checklist, service planes,As-Built Drawings Doc. Review
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Material Compliance
e304e9f5-2f9c-53de-bb2e-8f8cdcfd32b6 | note | ACTION (Hold, Monitor, Witness) - H
40cad960-2f48-58c0-bf6a-dcd40bd4226f | note | Detail - LESA dowels to be used at all construction joints at 600mm clearance
50e0b6b2-10c3-5685-8eba-585c3dbc3c7d | note | Frequency - Prior to pouring concrete
ff80a3a8-293e-50bc-935b-056a47e4220e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
a397d2f9-ddba-56ef-b635-de77d6f97559 | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
580ccee6-7a14-5d5b-8808-2acb7bce19e5 | note | Records - Delivery Dockets / Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.1 -
eae10ba9-c12f-5f9c-be54-093311958968 | note | ACTION (Hold, Monitor, Witness) - H
ab050cec-a525-57d2-bcd1-b030337d3bba | note | Detail - 0.25mm polythene layer placed across all surface area at bottom of raised table
1738a058-ea8e-5752-98ec-233084efb0c8 | note | Frequency - Prior to pouring concrete
aaacfc3d-4a77-5dc0-a15d-354e35383e12 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, Document Review
da64c509-f578-594d-b27d-e5501d25e79c | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
e415cbae-11cf-509f-8bcb-3b86e35bd5c3 | note | Records - Delivery Dockets / Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.2 -
9472d0bc-5136-5c8a-b738-269b871c3a22 | note | ACTION (Hold, Monitor, Witness) - H
524ef8e0-bd8e-5be8-af5c-fea4283a251e | note | Detail - 30mm thick compacted layer of AP20 aggregate placed underneath polyethene layer.
9dd97ed7-6104-5b91-a744-d274edfa907c | note | Frequency - Prior to pouring concrete
1e10b23b-9857-58b3-a836-5fd973a9f906 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
b54d129d-b926-5874-b8c1-ee35f63d050e | note | Conformance Criteria - CIV >15
dcbc5cf1-6b92-571d-9ccd-846dccd47850 | note | Records - Delivery Dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.3 -
077d82f9-89c1-52ab-a56a-377fbcde6b4c | note | ACTION (Hold, Monitor, Witness) - H
778c7e92-52aa-5d7d-8dc7-393b2a715f76 | note | Detail - Two layers of 663 mesh 50mm cover from top and bottom to be placed inside with 70mm plastic chairs seperating.
b8fee512-448a-5e64-bd81-45d3b085e277 | note | Frequency - Prior to pouring concrete
36051e0b-d396-534a-aebf-c63f272a046e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
9ce92d6e-299f-57ee-836a-4f9457ab1b83 | note | Conformance Criteria - Photos
ab546afc-0a5f-5fce-b76b-e225b0d73cb6 | note | Records - Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.4 -
b95f88cf-cf7c-5366-aa54-7fbd39eace45 | note | ACTION (Hold, Monitor, Witness) - H
6357d308-c43f-5e35-ace0-e37f0fa37e07 | note | Detail - All concrete delivered to site shall have 50MPa 28 day compressive strength with 4kg/m3 of Black Oxide Powder
c9f286c2-61ff-5a8e-b570-0c8954162c52 | note | Frequency - Prior to pouring concrete
07c46df9-83a1-5f36-b6b0-86e151675a08 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Concrete Delivery Dockets
fc4e426b-2fd1-5a23-920c-49cb385c1b4d | note | Conformance Criteria - Delivery Docket added to QA folder
fe78e50d-f723-5571-9d3b-304f28920fe3 | note | Records - Concrete Delivery Dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8 - Temporary Works (Formwork)
fa4d64b6-4982-544c-9a2e-f9c866c2749b | note | ACTION (Hold, Monitor, Witness) - W
d5bf2c64-1340-5dec-bf64-9ee5ca00e0e4 | note | Detail - Formwork to be set to correct line and level
8cedd9f8-279a-5d78-8a10-640fcfd0309b | note | Frequency - Prior to pouring concrete
8220bc1b-674d-58c9-a1d9-f34e756bc099 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
c4f78bbf-9611-50e0-9781-eb22fcbfe503 | note | Conformance Criteria - Concrete Inspection Record
8f554579-85f0-5fb0-93b6-e4467bc0850e | note | Records - Concrete Formwork Checklist
| checkpoint | 8.1 -
349b9296-4100-5467-8d2c-1498632cb7b2 | note | ACTION (Hold, Monitor, Witness) - H
602af4c5-9e45-5dea-b5fd-fc0b5b8d3597 | note | Detail - Raised table formwork to be 100mm above existing road level and be 300mm in depth and gradients respectively of entry (1:10) and exit ramps (1:40)
ba67efa2-76d6-57d1-909b-9a43288afa47 | note | Frequency - Prior to pouring concrete
5185db27-a933-5033-b200-41d7893b4e3d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
d9783b0e-111d-56d1-a09c-d4dfdbccc026 | note | Conformance Criteria - Designer to inspect formation level
948996b5-9653-5ca9-938c-db49745bcf08 | note | Records - Site photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8.2 -
cb07691e-470b-5964-87ff-517880b04733 | note | ACTION (Hold, Monitor, Witness) - H
42e2b67a-a817-52b5-b696-81f2acb921ea | note | Detail - Raised Table ramps to have 200mm depth at entry point and tie into 300mm depth to meet raised table
6999890c-ecb9-5480-8e31-9e5a38c98a53 | note | Frequency - Prior to pouring concrete
03577304-a901-587e-a258-99d2cbfe6a2e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
30bba654-c0cb-56fb-aa4c-861b9b5289c4 | note | Conformance Criteria - Designer to inspect formation level
fed24be2-4704-52b1-bff3-439270e9f5b2 | note | Records - Site photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8.3 -
4e139e0f-0ef4-5b28-9cc7-6570a50d3bb6 | note | ACTION (Hold, Monitor, Witness) - H
5a489d07-18b0-5cd8-8a84-fd020f65d7b7 | note | Detail - Raised Table ramps to be 1m across for entry and 4m for departure ramp.Toe to be 0.5m to 1m across for both entry and departure with 50mm asphaltic wearing course
c054ba66-e3cb-58da-86a1-5b1eba7ce6a2 | note | Frequency - Prior to pouring concrete
b2458f32-4c3d-5421-b2e1-db099e31c2a6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
8c687849-5762-57e6-a487-50f4f71f2aaa | note | Conformance Criteria - Designer to inspect formation level
b31d6af8-ca43-5643-a220-832cac1ae422 | note | Records - Site photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8.4 -
b134c657-7717-5851-867f-f45b206b1907 | note | ACTION (Hold, Monitor, Witness) - H
eab0721e-118d-5a9c-ac0d-dfab4979bd7b | note | Detail - Raised Table ramps to be 1:10 gradient for ramps at entry and exit ramps to be 1:40 relative to the road
902c03bf-a44a-5235-8339-d8de080aecc0 | note | Frequency - Prior to pouring concrete
115165af-5a9c-541f-a566-cc12c1f23876 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
ac60535a-7a4d-583f-9845-805c63caa3b0 | note | Conformance Criteria - Designer to inspect gradient level
f0aba105-32b2-55af-afad-c2a77709d942 | note | Records - Site photos / Concrete Formwork Checklist
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8.5 -
35e35051-7199-50ff-9698-42df90a235e7 | note | ACTION (Hold, Monitor, Witness) - H
819630de-18cc-5709-b96c-826ffe5d6ba7 | note | Detail - The Site Engineer and MSQA Engineer must sign off the formwork prior to concrete being poured
b28586e4-be01-590d-8c23-4d15b566df26 | note | Frequency - Prior to concrete pour
6b43fe12-d10b-51fe-96cf-26e7dc4c58f6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
b5ce0672-523c-5bc6-8bb0-fbfb2d5d04ac | note | Conformance Criteria - Concrete Inspection Record
5819468f-12df-58ff-b52b-3f5f45010024 | note | Records - Concrete Formwork Checklist
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Reinforcing
766d95be-e9a1-5137-87e3-029d412ec425 | note | ACTION (Hold, Monitor, Witness) - H
a2dcd3e8-9175-5256-9df6-095ec20e4c32 | note | Detail - All construction joints are to contain 2 rows of LESA dowels or similar approved dowels .Dowell system 50mm w/ Black 300*50*6mm plates @600mm centres placed across the construction joint
c69badd4-2590-5fa2-93df-b1109434daea | note | Frequency - Prior to pouring concrete
de0ad842-7737-53b0-b908-d367229e6f14 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
95439931-f1da-566d-8ddf-5226a8ff6303 | note | Conformance Criteria - Concrete Inspection Record
e363a1a0-3e0f-5fd2-9641-3abda7bbcb60 | note | Records - Site photos/Concrete Formwork Checklist
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10 - Concreting
c6dfbace-89ad-5ebd-b722-aa815c974d2a | note | ACTION (Hold, Monitor, Witness) - H
2a9f864b-a1be-5223-8572-5622a2ac641e | note | Detail - The MSQA Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required
85fa27fe-bd2f-56f2-b9c1-d2a2612ec538 | note | Frequency - Prior to concrete pour
6b5c799b-844b-536e-9dd6-c0fe055a5cae | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
e8d7de7e-d322-5633-9291-da8b0aa13aa2 | note | Conformance Criteria - Engineer will be notified via email/SMS at least 24 hours before required for inspection
17df2213-b693-5a54-b4a8-70847ff82e82 | note | Records - Email / SMS
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10.1 -
2876db22-7207-5207-a0f4-dd18720172b0 | note | ACTION (Hold, Monitor, Witness) - W
76b31725-9411-5f78-93e9-6be1aaa8899e | note | Detail - Vibrator to be used throughout concrete pour
f136b8d4-530b-5fd1-b532-3a9f5bea14ce | note | Frequency - When pouring concrete
12f15384-432c-5b68-bdbb-8b5504da6eb4 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
5cc74d85-fb7d-5c1d-8631-e77de3f4dcec | note | Conformance Criteria - Concrete Inspection Record
aaa0e6e1-b613-521b-967b-41b3efb1fa29 | note | Records - Concrete Formwork Checklist
| checkpoint | 10.2 -
da901c74-4707-5edc-a5ad-be9cd43edfed | note | ACTION (Hold, Monitor, Witness) - H
ab3dff82-7468-5bc8-bd26-d21282ff0642 | note | Detail - Concrete surfaces shall be U5 broomed finish for ramps, and exposed aggregate finish for table top.
ef263e41-4304-5ad0-9701-871a9df794b2 | note | Frequency - At completion of pour
761e83c2-2789-532e-b5a3-52f35c0a5b0b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
209479ad-bd6b-5b3c-a820-747e3b0db236 | note | Conformance Criteria - Concrete Inspection Record
1e84ca6d-73a3-5264-9b40-395642ca10a6 | note | Records - Concrete Formwork Checklist
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 11 - Curing
91551e83-7794-57b5-bbbe-ed42c2b38aef | note | ACTION (Hold, Monitor, Witness) - M
4e380a02-4dd7-5001-a4c6-0a8a9e7c2f21 | note | Detail - Concrete will be left for 48 hours minimum to cure before traffic is allowed on it.
7a587172-77c4-5d85-b18c-4ae749755a42 | note | Frequency - Post Pour
d5b12ba9-d7bf-553c-9ed7-eb24bbbb5711 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Monitoring the time allowed for curing
f431c284-d266-563a-87f7-65944c279098 | note | Conformance Criteria - 48 hours minimum have passed
966946b8-80c0-508c-9b5a-0c097ddede68 | note | Records - Concrete Formwork Checklist
| checkpoint | 12 - Remove formwork
b064d902-bae0-5134-9fdb-9497e648d4fe | note | ACTION (Hold, Monitor, Witness) - W
727bb6d0-33f1-540f-87ca-eb18f8e37fa6 | note | Detail - Remove formwork after 48 hours
790b8afe-0f3f-599b-89ac-45b82a558337 | note | Frequency - Post Curing
09797a3c-d43d-5d43-96b6-0ed4c4dfa3c2 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
78f234ee-0c62-5fa9-b1c3-7bc1f52e23b1 | note | Conformance Criteria - Concrete Inspection Record
c183d5a9-ff42-51b2-95ef-88586a0bb70e | note | Records - Concrete Formwork Checklist
| checkpoint | 13 - Asphalt- Concrete extension slab/ Toe
2682085b-ba7a-569e-bf69-753755f4ff80 | note | ACTION (Hold, Monitor, Witness) - H
e8cc5ef1-4540-5053-b4b2-5f9e745e09e7 | note | Detail - Two rows of Lesa diamond placed mid depth @600 C/C along construction joint as per TDM TC0022
c1c99226-cb01-57a5-b981-c7f5e0bd75a4 | note | Frequency - Prior to pouring concrete
1ba707f4-6bac-5710-b845-198b118594d8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
d895fe6e-89bf-540b-aebb-48813b6584dd | note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
48adff46-1088-5751-a781-9979f59d456f | note | Records - Site photos, delivery dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 13.1 -
0dd0d5f4-fe33-5e2f-8449-6a82e42fc102 | note | ACTION (Hold, Monitor, Witness) - H
378d778b-bd5a-5583-ad7b-422458a70f10 | note | Detail - 200mm thick 50MPa Concrete with two layers of 663 mesh
33b687a7-54f6-5774-ae82-38e86e51d32c | note | Frequency - Prior to pouring concrete
708c47b6-a355-5e2a-8931-c34e5c12294a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
8e129a86-0e9a-5f56-bc58-afc74cd1718a | note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
2247b6f4-2e98-542b-97e6-d3446f5d0f0d | note | Records - Site photos, delivery dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 13.2 -
16034f66-5eb8-59db-bc31-4203a308b5b8 | note | ACTION (Hold, Monitor, Witness) - W
860d29bf-26a3-55c5-81cd-d55cc1480cb7 | note | Detail - Tack Coat between AC and Concrete slab
51c0afb7-c9cc-5128-bbd1-ac705c17ea9f | note | Frequency - Post Curing
356e61c8-3eb4-520a-b02e-2e8c4c8ff0ac | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
7b8e326b-7e64-5455-becb-b8195cb22075 | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
1f1c3d3d-e71e-51ca-8720-c32d91f752ee | note | Records - Site photos
| checkpoint | 13.3 -
70846590-b134-5b15-9352-8200f5f3ddd5 | note | ACTION (Hold, Monitor, Witness) - W
ea9b1939-d759-540c-a0f9-b80066c15f81 | note | Detail - 50mm thick DG10 / Mix 7
729c5d5a-4e72-5554-ae66-3b621e408635 | note | Frequency - Post Curing
fd54ced5-edf9-5ad5-ad78-770467be417c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
5c3ff950-4209-5c6c-8c7b-136f9a78ad4d | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
ce02f1c0-f11e-5150-a495-308543ddfbd3 | note | Records - Site photos, delivery dockets
| checkpoint | 14 - Lot Number QA File
2d7094d3-0f96-5952-8bc3-984db2446349 | note | ACTION (Hold, Monitor, Witness) - W
fae0a722-817d-54c4-a9f0-e0363db0ec0c | note | Detail - Ensure all QA Records,site photos and incident cases (OFIs) are closed and included within QA file
16c941e6-5829-57a0-ae1f-5e401f9fdfbe | note | Frequency - At completion of Lot
f47357db-2d5d-5281-bd14-d888dd3b1653 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
053f3057-0a38-53ff-a1fe-3b071ee236f8 | note | Conformance Criteria - All QA files compiled and sumbitted to client
1b5b54a9-765d-55c8-85fd-e6bb2f04bcf3 | note | Records - QA records
| checkpoint | 14.1 -
f75ac87c-5afb-5420-ba1d-30cfa801cbaa | note | ACTION (Hold, Monitor, Witness) - W
39e4ce73-c6c0-5b76-89f2-9c8df58fdb66 | note | Detail - Delivery Dockets to be included in QA file
750b30bb-d7de-5f9d-ad82-2cdbf31d86e4 | note | Frequency - At completion of Lot
3187deeb-2712-5707-8251-3d72bece79c1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
99266f15-62e7-5603-9111-9d34a7901362 | note | Conformance Criteria - Delivery Dockets to be included in QA file
76f1dbfa-add7-504b-a494-511ba2544b79 | note | Records - QA records
| checkpoint | 15 - As-builts
b20f41b4-845c-5c25-8fb5-15887e29d2c4 | note | ACTION (Hold, Monitor, Witness) - H
f5f7f782-604d-5534-afdc-607e8cd15b22 | note | Detail - Red pen mark up drawings to be included in QA file
152b8f2a-395c-5bd4-a1ba-e235f85f5ed1 | note | Frequency - At the completion of the Lot of work
0e025228-5d0d-5ad2-92fd-4f607b1e9b8f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
90a2a424-8589-5001-94aa-f13311069fb4 | note | Records - Asbuilt Drawing
| signoff | AUTHORITY HOLDPOINT
| checklist | Lincoln Rd - ITP - Stormwater Drainage |  | Stormwater Drainage | a9e8a0df-bfb2-4dae-9c04-463c9e72ce96
| checkpoint | 1 - Permits & Services
040ed495-8f6d-5b8d-b19f-dd9a1dd54ec0 | note | ACTION (Hold, Monitor, Witness) - H
c0615b2a-2e3d-5af7-847f-11c57d6c3f66 | note | Detail - Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
6fe946f6-9ed6-536d-8fc3-1a01eacfc7f6 | note | Frequency - Prior to any construction commencing
d48b5fb1-ece5-5472-b789-43beab4ac787 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
252d30d1-e742-5b5e-abe6-cff7095bd569 | note | Conformance Criteria - Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority.
44e54988-97d4-50f4-af93-384e5dd8ee14 | note | Records - Permit attached or permit number noted.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1 - Permits & Services (2)
d9652ce1-28ea-50a6-bdee-252d63be39ac | note | ACTION (Hold, Monitor, Witness) - H
cde4b71d-caa2-5e6d-83c5-92b8fb3d4734 | note | Detail - Excavation methodology, Trench Profile - Width, Trench Profile - Locate and mark out all existing services
68b5ce5e-0a73-5e09-89cb-ae6c1d39f8aa | note | Frequency - Prior to any construction commencing
d20baaa5-a7aa-5075-8adb-63f9eee03bc8 | note | Conformance Criteria - B4u dig procedure - follow utility protocols
a65ff0d2-e7e6-5aff-8ecb-18e38f0bde18 | note | Records - B4u dig plans & GPR report attached
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Pre-Construction Sign Offs
4b4cda06-67fd-548f-852c-ef2e75b33f92 | note | ACTION (Hold, Monitor, Witness) - H
15f13df4-c3af-58ae-a87a-e303e23f59aa | note | Detail - Sub-Contract and Supplier Agreements
97f9d318-26f2-53ff-8bb0-46ff0189ec36 | note | Frequency - Prior to commencement.
150ccf96-d639-5600-a460-f4f88f4a3098 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
456745ca-3110-5c9d-b17f-0ffb4d048dd1 | note | Conformance Criteria - Sub-Contract and Supplier Agreements to be agreed and signed
797b04b8-4d59-5f71-a5f8-3b38cec49144 | note | Records - Subcontract and Supplier Agreements
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Design
22eb0b82-d397-5191-9cbc-9854dc4cdac0 | note | ACTION (Hold, Monitor, Witness) - H
f33aded7-4185-5577-90cd-abb985e38c2a | note | Detail - Design is approved and Drawings are of the latest revision.
30eb8138-586f-584d-b5c1-30c0f67195b4 | note | Frequency - Prior to commencement.
e5d307b6-6dfc-5302-a028-f696bc9bbad4 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
e29f5dbc-4bfd-5f35-8be1-242ea1e87fc2 | note | Conformance Criteria - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
5f0be9bf-8339-5cca-bff8-ae7255769236 | note | Records - Drawing Register.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Survey Set out
775f75fb-712c-53bb-ad47-6372b550ab12 | note | ACTION (Hold, Monitor, Witness) - H
0c4c5a5c-107c-573b-b944-140be5722fdf | note | Detail - Set out Pipe Alignment and Service Locations with inlet & outlet points and inverts as required to construct to design
f0f5aff5-8cb5-5be2-b6b4-eb74b09b6629 | note | Frequency - Prior to commencement.
979c4fe2-9103-5a7c-931d-c2c422441f0b | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Survey
d5c22d21-0318-5d4b-accf-bd4d18bd0746 | note | Conformance Criteria - As per HARRISON GRIERSON ENGINEERING DRAWING: 1040-A2110796 & Set out files
f8d70d44-f94d-5db7-8966-7865a20498d1 | note | Records - Survey Receipt.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Pipe and Manhole Material Compliance
60edd31a-6b92-5ec9-8034-74ea9c619298 | note | ACTION (Hold, Monitor, Witness) - H
a7917a46-098d-5a58-97f8-30cbd5a087a3 | note | Detail - Cesspit, Manhole and Pipe shall comply with relevant AT/TDM standards
c2fae21e-baea-52d5-a36f-09347dedcdb9 | note | Frequency - Prior to commencement.
6819accb-2bba-55e2-ba34-d245d5dc8cf7 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review, Visual Inspection
ec010da9-e0a9-52ac-9213-3a34e733aa11 | note | Conformance Criteria - Pipe shall be
0202043b-2174-563a-a6df-5eec02188e84 | note | • Check for freshly formed pipes and return if required
898cbf2a-9934-5093-ac8d-f61a2cea55af | note | 1) DN300 Class 4 RCRRJ pipes AS/NZS 4058
091eb62f-601a-50e1-b67e-16db5dd107a5 | note | 2) All Concrete RCRRJ pipes to be fitted with Rubber rings
1dcec963-97ef-55cd-9ae4-72e3d55120c4 | note | 3) Pipes shall have product certification (ISO Type 5) to AS/NZS 4058
ed8b428d-fa6f-5b00-ac46-75a5d677b186 | note | • Prefabricated concrete Manhole shall be in accordance with TDM Standards & AC COP
408f7a9c-d0cd-5631-9d10-be51c9a193b4 | note | Records - Manufacturers Data Sheets, Delivery Dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Locate Existing Services by Hand Digging / Hydro Vac
c095967e-0964-5906-9a98-1b2266674ca7 | note | ACTION (Hold, Monitor, Witness) - H
d7dfcf29-56f2-598e-b0fe-8f1550788b3c | note | Detail - Ensure all services conflicting with the line of trench have been exposed by hand digging.
ac623e15-243b-5413-831a-2f756f36baec | note | Frequency - Prior to commencement.
880537fb-3f45-592b-8123-90f7dd325b73 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Potholing / Survey
f5584e0a-b512-5198-ad8a-e03bb5fb8aad | note | Conformance Criteria - All conflicts have been located. New services and / or conflicts to be advised to Project Manager.
1dd64751-9487-5c5d-900b-e4275dc12265 | note | Records - As-built Drawings. Doc. Review
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Trenching & Excavation
7f3c4fc1-d21f-542b-8f81-b6b623fe2f4d | note | ACTION (Hold, Monitor, Witness) - H
54b3aa15-9c83-50c8-80ef-1a26c1adab62 | note | Detail - Excavation methodology
2af1f5b2-db59-5b2e-a387-4c7d8bc5e3e4 | note | Frequency - Daily
54e48f66-0f10-5a92-b180-82a373f49a4f | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Prestart review
6e967ab8-54d4-5426-9fcf-52dfe8597992 | note | Conformance Criteria - The excavation, benching and shoring requirements shall be in accordance with Worksafe Excavation safety guidelines (2016)
cd0ab290-c424-528b-b10e-28d4b7b9a131 | note | Records - Prestart RCP
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Trenching & Excavation (2)
d42d7dd3-d573-5cc0-8da0-8a14c07f10e0 | note | ACTION (Hold, Monitor, Witness) - M
c44810ba-de20-5e67-b1db-de8264d94a81 | note | Detail - Trench Profile - Width
4560a46d-eddf-52a8-a841-ec825e2387ca | note | Frequency - Daily / as trenching takes place. Different depth methodology
07fd1a89-c83d-576c-ad27-5727f3983cd7 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection, Excavation methodology
d70c624e-cd0b-55f8-aad5-89a69ffee236 | note | Conformance Criteria - Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing
4684cb7a-dadd-58fc-9add-04e61136531c | note | Records - Construction Photos
| checkpoint | 7 - Trenching & Excavation (3)
aeed73ec-7774-5a18-93e1-d168330ea022 | note | ACTION (Hold, Monitor, Witness) - W
dc495293-4f75-5ddb-857b-29062e8e509a | note | Detail - Trench Profile - Depth
4ba3a1a5-f53d-55ae-8d1c-0eff7ada1e6c | note | Frequency - Daily / as trenching takes place.
a254387a-d7b0-50a4-9e34-94787e8fd41c | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection, Measurement
a4892c9c-586f-5041-aebf-f494feefdfc6 | note | Conformance Criteria - Trench depth varies according to long section and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings
ba38ec53-1aa5-5d07-9599-b5fcf9a723f2 | note | Records - FH Drainage Line Record / Construction Photos
| checkpoint | 8 - Bedding for Concrete Pipe Laying & Manhole & Cesspit
fdb6d4c2-3c6a-5a71-9aa7-690d44cf7fb2 | note | ACTION (Hold, Monitor, Witness) - W
1fe62f1d-0132-53a7-83ed-45dfbb13f93d | note | Detail - Placing and compaction of Bedding Material.
39dc9489-98e4-5f26-9e10-f79f7f62f06b | note | Frequency - Inspected continuously during placing and compaction of Bedding Material.
3b28e1f2-d0cf-5a41-8885-0bc7e94ec8c4 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
9e1ae739-d3ce-5af9-bc73-9e64a4323ada | note | Conformance Criteria - Bedding & Pipe surround material to be GAP7 or GAP 20 (Stevenson Quarry) or alternate material that complies with AS/NZS 3725
77247505-20de-50f3-baaa-4af7bc29a49c | note | Records - FH Drainage Line Record / Construction Photos
| checkpoint | 9 - Pipe Position Tolerance
4225e651-21d5-56fb-95b9-f9ce3835ba22 | note | ACTION (Hold, Monitor, Witness) - M
a579fb61-d8a8-53d6-af6d-8df2fe64d23f | note | Frequency - At any point of pipe
e08525bb-a760-5a7b-9805-eeece2cd6d01 | note | Conformance Criteria - Position tolerance for pipe laying at any point along the length of the installation shall be within ±30 mm from the specified design.
040f570f-dfb7-5f4f-af75-4d14e60723e7 | note | Records - FH Drainage Line Record, Survey Data.
| checkpoint | 10 - Trench Backfill - Placing & Compacting
f28e99ef-8d6a-5908-af85-041dd4f55c3f | note | ACTION (Hold, Monitor, Witness) - M
b34e2209-45c6-55c0-8038-02253f0a3cb0 | note | Detail - Placing and compacting of Trench Backfill Material
af4e311e-5415-5167-823b-5475e89276c5 | note | Frequency - Throughout Trench Backfilling operation.
75410ce5-9df6-5575-9c1a-f3859571117c | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
2ebe445c-c6e6-5ff6-85f5-ddbd2b80b5a8 | note | Conformance Criteria - Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm
9d70c2ee-dd3f-51e8-bb47-6799be65a5c8 | note | Records - Construction Photos
| checkpoint | 11 - As-Built Drawings
13ef79d4-e96c-5163-af6b-b0d1ca392e5c | note | ACTION (Hold, Monitor, Witness) - W
92042e1f-5436-527c-8e38-45e012449abe | note | Detail - Red pen marked-up As-Built of every 'Issued for Construction' AT drawings
c8425110-bad9-5c23-99ed-36ee1ec32ca7 | note | Frequency - Final As-Built Drawings to be completed within three months of the construction completion of the asset or infrastructure.
ecbc9e13-96da-5b31-9073-af65d4794cfe | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Drawings / Visual Inspection
e652bb46-485d-5a8f-8dc7-c0093eb4b757 | note | Conformance Criteria - As Built and GIS Data
ff1183cd-7fa3-5945-a022-89ceddd9dca6 | note | Records - Redline As-Built Drawings, scanned as .pdf files.
| checklist | Lincoln Rd - ITP - Traffic Islands |  | Traffic Islands | 4d35d55c-22a5-4e41-8a48-80fa4b5b784a
| section | Materials
| checkpoint | 1 - Mountable Kerb
50caf296-8759-5bea-a82b-d7a584404a52 | note | VERIFICATION ACTIVITY - QA FORM
ee2083b1-70ca-58e1-b8a8-889fdb308413 | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002
72e99e2b-c9e9-504a-9eec-d6b2debe9d41 | note | FREQUENCY - Everysite
0da700b3-5c76-519a-bcd5-ad2d62e16dd9 | note | ACCEPTANCE CRITERIA - Mountable Kerb to be laid using precast hand-laid and painted with two coats of reflective paint
58c7329a-c872-55fd-bf8a-54e485e3b346 | note | Hold Point - Inprocess Inspection
dfc695aa-1661-5123-921d-af3f1093d3d4 | note | Records - FH concrete QA sheet, photos.
d977b9b6-6c79-5f72-939b-f51e7741fef0 | note | Onsite Responsibility - Site Engineer
| section | Construction
| checkpoint | 2 - Survey Setout
9b342c7f-110f-53c4-942b-6cabff4ce6a4 | note | VERIFICATION ACTIVITY - Survey
6958e2fa-d417-5dae-a07a-530090326b3e | note | METHODS OR REFERENCE - Setout Kerb Alignment required to construct to design
d17ab768-db32-5747-a4dc-77c0e171f4d1 | note | FREQUENCY - Prior to commencement.
18beed1b-d21e-530f-b877-e78109e8a824 | note | ACCEPTANCE CRITERIA - Survey
15cc8603-760a-5b1d-b77f-61d3d7d35040 | note | Hold Point - As per Construction Drawings
0846f4b7-be8c-55a0-be1e-233c48df96e2 | note | Records - Survey Receipt.
3303d262-93f0-5f8c-915f-6a3b33899f39 | note | Onsite Responsibility - Site Engineer
| checkpoint | 3 - Concrete Island
7ddd13a0-94fd-55a8-bc21-3a8467029078 | note | VERIFICATION ACTIVITY - QA FORM
fac71c91-9f54-5c20-93b7-809d401442f9 | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002, TDM Technical Standards - IS0001 & IS0003
f61b9337-47f5-5733-b77b-90782d44b69a | note | FREQUENCY - Each Site
0bc8c048-dd20-5f0b-8ed8-b415eb142c80 | note | ACCEPTANCE CRITERIA - Kerbs to be haunced with 20MPa Concrete, Basecourse to be 150mm min thickness of GAP65
046be29f-ff30-562e-a2fb-d58f4f96bff6 | note | Hold Point - Inprocess Inspection
a18db03d-7cd2-5ed4-9fd3-5347f014daef | note | Records - Photos
56cde3ef-6b41-5407-beea-3768ad7e6825 | note | Onsite Responsibility - Site Engineer
| checkpoint | 4 - Concrete Infil
323c9eda-5969-5d34-b3ae-e61d65539c15 | note | VERIFICATION ACTIVITY - QA FORM
30d4db14-864a-514a-afc4-e45ff0c86144 | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002
c7142697-39ee-50c8-95d3-8aab5e3635ab | note | FREQUENCY - Each Site
428b11e7-e1b0-5d36-aa56-d0ecebaf5e55 | note | ACCEPTANCE CRITERIA - 180mm depth of 20MPa broom finish unreinforced Concrete with 4kg/m3 red oxide, Cross Fall of 2% or max rise in centre of 180mm
57677d74-7fe4-56a5-9cbd-0cf50f13828d | note | Hold Point - Inprocess Inspection
221214c3-23e5-5697-825b-56fbbcad711f | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
ada237b8-32be-5d8b-8965-f2951a1d7e3f | note | Onsite Responsibility - Site Engineer
| section | Asbuilts
| checkpoint | 5 - As built information
73bbd57f-52b6-55fc-8f50-72881243a6cb | note | VERIFICATION ACTIVITY - Drawings
96b057f4-0162-56bd-88f2-f80b07d204b0 | note | FREQUENCY - Every Site
48713b47-11c4-5cf2-887c-4451532d0b6e | note | ACCEPTANCE CRITERIA - As built drawings
9f6442ce-e2b7-5376-8e06-5f7c3668bfc8 | note | Hold Point - In Process Inspection
d58783dc-4ad0-5013-86b4-2e024bd2a602 | note | Records - Asbuilt records
426a6f61-4b9f-547c-b485-ec6b5f86325f | note | Onsite Responsibility - Supervisor and Engineer
| checkpoint | 6 - RAMM DATA
b65eac69-ba43-530a-b70a-361908f2a03c | note | VERIFICATION ACTIVITY - RAMM DATA SHEET
4b31739e-1bb1-5577-955c-ced3e825bf69 | note | FREQUENCY - Every Site
ef406c0e-0a26-5e2d-92fd-4a4f16235686 | note | ACCEPTANCE CRITERIA - RAMM SHEET
84c306af-adef-50ad-a1d1-69bd1855f07e | note | Hold Point - In Process Inspection
390f8d25-2ca2-595e-b21f-6ce17abe6524 | note | Records - Asbuilt records
bcb4daf8-b2da-5c67-83d3-7008ad54d5f1 | note | Onsite Responsibility - Supervisor and Engineer
| checklist | New North Road and Sandringham Road - ITP - Enabling Works - Footpath, Kerb and channel | itp | ITP - Enabling Works - Footpath, Kerb and channel | b7e4fcd9-920a-46fd-a835-28e4212af8be
| section | Site Set Out
| checkpoint | 1 - Site Set out
2fe52a0e-5782-5ecf-ad33-e4399c4168a7 | note | Verification Activity: Surveyor
5bb0d8c4-4409-5ed7-8c17-2d46a6d229b3 | note | Methods or Reference: Surveyor
bc0b38cc-b4af-5139-b458-2653709d26ac | note | Frequency: Everysite
b6e5efa5-a7a5-5f7c-89d5-69118eb9a354 | note | Acceptance Criteria: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
8f5a390b-aba9-5c26-a31f-c9f2dec6a3b7 | note | Hold Point: Mandatory HOLD POINT -
bef4c8fb-53d2-5e4f-96a9-df56aa4e8545 | note | Records: Onsite records/photos
31024100-45b3-552b-9964-f568ac2244b6 | note | Onsite Responsibility: Site Engineer
| signoff | HOLD POINT
| section | Materials
| checkpoint | 2 - Kerb & Channel
078fa6b1-3159-5502-8da8-5a5646d1c14f | note | Verification Activity: QA FORM
228f584d-ee29-5b4d-8816-f6b841367cf8 | note | Methods or Reference: TDM Technical Standards - KC0001
2a085a6c-28de-514a-8172-8f3b855d8c95 | note | Frequency: Everysite
cbdbbb48-919d-5dbf-be71-d85fdad0a37c | note | Acceptance Criteria: Kerb & Channel to be laid using precast hand-laid. On compacted GAP40. Concrete 20MPa @28 Days on 100mm GAP40 with the subgrade CBR>5
b24288a8-bfef-527b-81b0-fc015d6845fb | note | Hold Point: Inprocess Inspection
32a715c2-43f6-5f05-82fc-ce65ccb96ec8 | note | Records: FH concrete QA sheet, photos. Concrete Plant Docket
460930f5-fb46-56f4-b02d-3417e7d036a1 | note | Onsite Responsibility: Site Engineer
| checkpoint | 3 - Channel Level
681d30b3-936b-5ceb-b9f3-14f7de0e351a | note | Verification Activity: QA FORM
13c42c4d-2497-567e-9397-b6df03b8cbab | note | Methods or Reference: TDM Technical Standards - KC0001
157c7e24-5e01-5ad1-b564-e00b21a3fb8f | note | Frequency: Everysite
79609dbb-8a55-510a-9609-b5f43edc2460 | note | Acceptance Criteria: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
1a6557ae-dba4-558a-80d3-72467ee717f0 | note | Hold Point: Inprocess Inspection
ff900087-afad-5790-bae9-4d1690581c61 | note | Records: FH concrete QA sheet
fb0bb90b-e4e4-515c-9c24-510379b067bb | note | Onsite Responsibility: Site Engineer
| section | Civil Works
| checkpoint | 4 - AC Footpath
383c73d4-9211-5eba-ae42-d228625b5d06 | note | Verification Activity: QA FORM
f6179225-d4c7-5fcc-9333-c62e2abbbc67 | note | Methods or Reference: TDM Technical Standards - FP0001
2fddae70-cb30-5901-90cc-40b7fa2888c4 | note | Frequency: 10m Intervals
1d4daf77-a529-519e-8818-24c509d79c65 | note | Acceptance Criteria: Subgrade -(CBR > 3) Basecourse - 100mm min. thickness GAP40 Clegg CIV > 13 DG7/ fine quality asphalt Mix used
42dc7d35-76c1-54de-867e-ec88c9e3a3cc | note | Hold Point: Inprocess Inspection
3ced6c52-a10f-5a18-ad5e-33e2257fdee0 | note | Records: FH concrete QA sheet. Concrete delivery Dockets kept as record
6b8664a0-ea65-5711-b2c5-716442cdb03b | note | Onsite Responsibility: Site Engineer
| checkpoint | 5
5ea8268d-ef66-54f6-b6a0-0101e631c22d | note | Methods or Reference: TDM Technical Standards - FP0010
a51db3b0-4255-56bc-b3a3-ce69f2dba6d7 | note | Frequency: Each PX
6a01c3dd-590f-5ffa-b429-ba5f2c702a36 | note | Acceptance Criteria: Warning TGSI tiles should have 100mm concrete slab underneath
952c1e9a-67c2-5ee5-9d3f-0f04a1de6dbc | note | Hold Point: Inprocess Inspection, Measurement
a4310b26-8a2e-5941-b436-9d0157c98f6a | note | Records: FH concrete QA sheet. Concrete delivery Dockets kept as record
22afbe54-d29f-5fb2-b300-0fe646b002da | note | Onsite Responsibility: Site Engineer
| checkpoint | 6 - Tactiles
5c1742fe-fdf1-5de6-a3ff-94f123696143 | note | Verification Activity: Visual
ecb78ade-dd87-59fa-89d4-1708cc3204d0 | note | Methods or Reference: NZTA RTS Guidelines for facilities for blind and vision impaired pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
5f501c64-7adf-5c06-a8f6-62f30d043311 | note | Frequency: Everysite
6c99a6be-120e-5aa1-99fc-196f85807a23 | note | Acceptance Criteria: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
8682c26b-16de-5421-ad80-3d00e2e10589 | note | Hold Point: Inprocess Inspection
ce483a10-69c9-5c00-add6-ec545c8989e7 | note | Records: Photos
07ed37d7-9876-522c-a768-a58fb0860c55 | note | Onsite Responsibility: Site Engineer
| checkpoint | 6.1
2f7edb57-0c1e-597f-a8f9-106e64be7172 | note | Methods or Reference: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
3fc0a4be-58ec-5e4f-af6a-85264be55f60 | note | Frequency: Everysite
0103229a-cc78-562f-8aad-74ec801bdd5f | note | Acceptance Criteria: Edge of warning indicators to set back 300mm from the face of the kerb or lane, extend the full width of ramp and be 600mm deep.
c04f5129-d843-5587-b942-f3ac0125dc38 | note | Hold Point: Inprocess Inspection
fbb92aec-70aa-563a-9633-6dfe5bd0ce75 | note | Records: Photos
2ebbb0f4-512f-5bcb-b3fa-3a720a927da8 | note | Onsite Responsibility: Site Engineer
| checkpoint | 6.2
9f83f315-a193-5771-943d-bd23cad6f00b | note | Methods or Reference: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
3fca48e3-ee2c-5d90-839d-dc6bd6ff9b3c | note | Frequency: Everysite
118b6a75-887d-5377-b317-4971bca41e0a | note | Acceptance Criteria: TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
2d6f708a-015a-5654-a0a8-785ae3817e79 | note | Hold Point: Inprocess Inspection
82420e0a-e1a0-57bb-bce9-9dc0842a3477 | note | Records: Photos
c08c5d7a-d40f-5873-9477-07e354e61201 | note | Onsite Responsibility: Site Engineer
| section | RAMM Data
| checkpoint | 7 - As built information
fd1e7b4d-facd-5407-be2a-8a5ee3b593e1 | note | Verification Activity: RAMM DATA SHEET
183be541-0f75-5b94-85b0-40b0be07a1ee | note | Methods or Reference:
01d52a67-9acd-5523-aef6-f1d93d5a2ef1 | note | Frequency: Every Site
c1bbc5ee-ea4d-5e7d-a023-9be6022ff567 | note | Acceptance Criteria: As built drawings and Ramm Sheets Completed
c4af4338-a2f9-51ee-9c7d-bb5fd7b06dbf | note | Hold Point: In Process Inspection
93cc5618-9c93-56ca-98db-e16ca2cf7f2c | note | Records: Asbuilt records
bb7e8046-ace2-5d9a-803b-1255210933f6 | note | Onsite Responsibility: Supervisor and Engineer
| checkpoint-no-value | ITP Approval
3bab6200-149e-5bf3-a523-b81df739c91e | note | Prepared by: Cimyona Vinbi (21/02/22)
32ea78b5-5037-5f8d-a407-3bee8c842876 | note | Approving Delegate: Daniel Tat (15/03/22)
| checklist | Ponsonby - ITP - Asphalt Surfacing |  | Asphalt Surfacing | 2552067b-c80c-4ee4-ba7d-c3e151fcf7ca
| checkpoint | 1 - Traffic Management
dbc90c64-93f1-53f0-a950-115314bca50d | note | ACTION (Hold, Monitor, Witness) - W
5aa0a1e3-bc53-5084-8bf1-49a074bb6ded | note | Detail - Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
e1fa7c8f-a553-5dd0-9f88-63e2564235d2 | note | Frequency - Prior to commencement
132d5f75-321a-5848-9bba-c3ee82bb96db | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
3decf82f-43fc-58dd-8adb-6ba19b88a24c | note | Conformance Criteria - TMP is approved by AT for the site and works are only completed within the approved dates
e493f906-5f3a-564f-9511-ef4d36fc9a87 | note | Records - TMP on MyWorksites/On Site
| checkpoint | 2 - Pre-construction sign offs
7b051d40-8545-512a-a90f-36d54c2b70c9 | note | ACTION (Hold, Monitor, Witness) - W
20f1373b-5788-5fd5-bdf8-1cf6f5a3f88f | note | Detail - Ensure that Sub-Contract and Supplier Agreements are signed, all Sub-Contractors and Suppliers are inducted to site
58897358-b764-5c90-a354-2f659131a98e | note | Frequency - Prior to commencement
88883261-7023-554d-aaa1-31945fb19168 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
b3ea49cc-99ad-536b-9e64-be3722abc1a8 | note | Conformance Criteria - Signed Subcontract and Supplier Agreements on M-Files and Induction Register updated
c4b01467-7384-5a52-924a-183d3b3c8abf | note | Records - Subcontract and Supplier Agreements, A & Updated Induction Register
| checkpoint | 3 - Base course sign off
00c45050-ecb1-57d9-9898-536d3987989e | note | ACTION (Hold, Monitor, Witness) - H
1df086a4-3c41-51f1-a027-8d32a5ed8919 | note | Detail - Ensure that base course checklist and QA records are signed by AT representative/Engineer
b681519c-825f-5b85-ab20-eb322636323d | note | Frequency - Prior to commencement
0abfa7ec-c9ae-5ba1-a3fe-30e11aae70ac | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
7215bf1d-8688-5081-b29c-6070a93fd563 | note | Conformance Criteria - Completion approved as per Pavement ITP
2be09cdf-3dde-5d63-8e55-2d283909ce03 | note | Records - Pavement Base course checklist signed
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Design
6940ef37-647c-5f5e-b0b7-c1d5d38f202d | note | ACTION (Hold, Monitor, Witness) - H
879959e1-6174-5b2f-bbce-20364712045d | note | Detail - Ensure that Design is approved and Drawings are of the latest revision
fc7e8172-7d75-55f4-b107-65edb8f988dc | note | Frequency - Prior to commencement
4a2398eb-5dc7-5ca1-8a04-d8c215985999 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
b295be90-541f-5908-bcf6-0eb5ece86c02 | note | Conformance Criteria - IFC Label on drawings
df00f56c-b55f-50b3-86a1-6df01c61d0d2 | note | Records - Check Drawing Register
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Material testing and control - AC
5970f11f-a64f-51ac-9a07-af31c30e6d53 | note | ACTION (Hold, Monitor, Witness) - H
fc0c08e1-98be-5f21-b13e-a591f47ddce0 | note | Detail - Asphalt mix design approval
8657b03b-06ed-5ec2-a755-c345b6b1342b | note | Frequency - Prior to commencement
e2ab9abb-c723-5f98-9561-6bd1688dd228 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Submission and review
9823fde0-666e-5d24-b065-75ea9bd9352e | note | Conformance Criteria - Accepted by AT representative/Engineer
0a45217e-2e7e-5a5c-a9a3-7d90d4e47229 | note | Records - Approval evidence
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Construction
6ac4cc56-6ffb-5bb2-9f0d-bbec87a13c7e | note | ACTION (Hold, Monitor, Witness) - M
359e7e7b-4989-5442-bb16-fdee7611ea82 | note | Detail - Check weather forecast and record weather
ba7ea2e0-80d6-5dc1-acbd-cb5e3b616277 | note | Frequency - Prior and during application
5b552ff5-ec73-5706-a6ae-45467666a9b7 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Monitor
bcc1d0a2-7f59-5b0b-83e4-0df9d3b3c1ba | note | Conformance Criteria - No foggy or raining or wet surface, base temperature > 7°
606f8265-689e-55b8-9789-cd6ed44677ca | note | Records - NA
| checkpoint | 6 - Construction (2)
1492c763-3cc5-538e-a01a-e33beca85cc5 | note | ACTION (Hold, Monitor, Witness) - M
9c84bd0e-402d-5fb4-9684-214019425d45 | note | Detail - Joints
9a91f0a6-47ff-53d8-9ba2-e715f22639fd | note | Frequency - Per joint of the road
68248642-ad94-50d2-89e4-aeb105f84b79 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
8215d42a-ff0d-54fb-ac2e-09e38f016934 | note | Conformance Criteria - Edges and joints to existing surfaces must be tapered to provide a smooth transition from the slurry to the adjacent surfaces
1e94090f-bdad-5a02-a1cb-c8ed880b1b05 | note | Records - Visual inspection
| checkpoint | 6 - Construction (3)
2121e838-c1ce-5ea5-9beb-368df758ad34 | note | ACTION (Hold, Monitor, Witness) - H
ccac6124-fffe-5cb2-ac4e-d8cefd1aac2a | note | Detail - Milling/surface preparation
0ec970be-f526-59f9-9622-06e2c79c2a7c | note | Frequency - Prior to emulsion application
d2087586-b4fc-557a-9dcb-ac3a3084c420 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection, survey
c847e093-4a5f-5528-b869-e1f5b83964cd | note | Conformance Criteria - If the surface is being milled and filled, surface levels and condition are to be inspected by the Engineer and confirmed acceptable before proceeding.
9b9008da-3691-597b-91d8-54f524a9cab4 | note | • Not applicable if pavement has been constructed under the Pavement ITP process.
b8db0ce7-1f72-5fa3-86c4-fa1c3551ccb9 | note | Records - Visual inspection, survey
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Construction (4)
b8791e45-6034-5d99-a850-5c6529f8314c | note | ACTION (Hold, Monitor, Witness) - M
71215991-b874-5faa-a546-913720111c43 | note | Detail - Surface finish
ba39af46-5c6a-5f58-957d-47400797f609 | note | Frequency - Per section of road
c5d9e00f-8420-5177-8b3d-afba886237ee | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inpsection
46f701c5-0274-598a-920a-180a768468e5 | note | Conformance Criteria - Uniform texture, no roller marks no bleeding, cracking, no crushing of aggregate
96ee411b-25e9-5fc9-97e5-9cdfe9faaf92 | note | Records - Visual inspection
| checkpoint | 6 - Construction (5)
dfb51867-b302-54c3-bab7-003c5aee0827 | note | ACTION (Hold, Monitor, Witness) - M
2835578c-2fad-59e9-8c09-655cd2204317 | note | Detail - Level
379de3e8-e0eb-5652-90e4-73f8b3591796 | note | Frequency - As required
31e91975-9e0a-5bb7-b3a3-272988ea31cf | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inpsection
4cc713d9-ff87-5cb7-82e1-a5d835b84fc3 | note | Conformance Criteria - Asphalt against kerb and channel, the surface of the edge shall be flush or no more than 5mm above the lip of channel
5226ced0-82da-53aa-99d3-98ca7c175f99 | note | • Any irregularities which vary more than 5mm under straight edge, longitudinally or transversely shall be corrected
f28e0c10-5160-5715-83e0-018316aacbdc | note | Records - Visual inspection
| checkpoint | 6 - Construction (6)
cba34c37-2624-5daf-8c32-e9b8e919f165 | note | ACTION (Hold, Monitor, Witness) - H
5ba26452-5ed1-5576-8e33-3d44f7f2ef93 | note | Detail - Compaction
2bc7c94d-de1f-505c-b899-43a04fea6fb9 | note | Frequency - As required
2b215ee2-f2f4-5ce4-b621-511d5016b33b | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Testing
58dec33e-aa1d-5a8d-aeed-8eb85812a790 | note | Conformance Criteria - Nuclear Densometer tests meet specified density
6bd0a1a0-ba5a-5e6f-b211-7907e1e3e7d3 | note | Records - Nuclear Densometer test results
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Post construction
6bb61f5c-355c-5726-9a12-52d2b93a034c | note | ACTION (Hold, Monitor, Witness) - H
5c9c51eb-be75-5cc1-bc11-412962eaf267 | note | Detail - Inspection/ joint inpsection
aa7fb47b-fb1b-5199-9221-1cc3bd8fb755 | note | Frequency - As required
0e4600db-8b1f-51d8-ae95-cb76fff2384a | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
7e28774e-fc0b-5e88-846d-55b873414f4d | note | Conformance Criteria - Asphalt joint sealing as per AT standard
6f6a14c6-6df9-5e66-8d58-bf9c4de6b738 | note | • Accepted by AT representative/Engineer
21487ba8-2621-5009-ad1c-3201f783bd3a | note | Records - Visual inspection
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8 - Linemarking
bd785911-42a7-514e-a41f-59fb8f09b29d | note | ACTION (Hold, Monitor, Witness) - W
5149de9c-dfa8-52ee-9825-722d90884e5a | note | Detail - Ensure that linemarking is set out and applied in the correct location and to the level of quality expected
c6249d76-546f-5aad-b55a-acbd697cb4f6 | note | Frequency - Before & after linemarking
67168a06-d2a9-572d-8549-d79c1ebbe88a | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection, survey
e3efafd2-012d-5ef7-984e-ca3fc146faf3 | note | Conformance Criteria - Linemarking adheres to design alignments and is of a good quality
a4b5ed61-731a-5fc7-994e-a5a4eb76014e | note | Records - Visual inspection, survey
| checklist | Ponsonby - ITP - Ducting and Streetlight Installation |  | Ducting and Streetlight Installation | 4c8bde4b-c69c-40be-9389-9e0c16e478a1
| checkpoint | 1 - Permits
4c4bfa8c-bdf0-5433-8691-c3c758442cca | note | ACTION (Hold, Monitor, Witness) - W
8ab709e9-bc11-5ec1-b9df-d7fbc4562260 | note | Detail - Obtain Permits
33066390-a338-5362-a03b-2a1c9335deb1 | note | Frequency - As required
cdcd0065-bacd-5f77-a039-a3399aac271e | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
c7dc63a8-d4ed-5a4f-a915-90a6394fb660 | note | Conformance Criteria - Control Checklist - Digging / Excavating (incl. marking out & potholing existing services).
79294616-de4e-541f-aa7e-519fc97d7e82 | note | • Notify Worksafe NZ if required.
dba8751c-c3fd-52e4-a069-e2b245b7def7 | note | • Ensure all necessary Permit to Works & Controlled Checklists are in place
7c14ffa9-eb96-5dfc-8656-a55eff2eb5cf | note | Records - Permit attached or permit number noted
| checkpoint | 2 - Traffic Management
bbf01c4a-b6cb-5e04-87f1-533cb13e9664 | note | ACTION (Hold, Monitor, Witness) - W
d5cd10af-93cb-5541-99c2-dcd422289369 | note | Detail - Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
78afbded-87d0-5e7a-b6da-f2971fd8fb33 | note | Frequency - Prior to commencement
e7917019-df03-5d82-8f49-fb9f8a4c3d3c | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
770bb316-ce95-5ab3-9c8e-c080115ec537 | note | Conformance Criteria - TMP is approved by AT for the site and works are completed within the approved dates
575c3b70-a85c-5adb-9d9d-f1147dc1c6f6 | note | Records - TMP on MyWorksites/ On Site
| checkpoint | 3 - Pre-construction sign offs
cb720230-15ae-5076-b4f6-4be3c184ce38 | note | ACTION (Hold, Monitor, Witness) - W
33da9770-a163-574e-8459-7c7c41b0570b | note | Detail - Ensure that Sub-Contract and Supplier Agreements are signed and that personnel have gone through the NWBI induction.
a23e6d32-0810-5fed-b41c-857b918f32e6 | note | Frequency - Prior to commencement
ee5e1cf5-d35b-5bab-958c-4b2ed04abe43 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
0028c6cf-3b3f-56e1-8bb6-9804b425a075 | note | Conformance Criteria - Signed subcontract & Supplier agreements. Issued induction stickers and number
ca920c5a-61a4-50b9-8e43-60da319ce2b3 | note | Records - Signed Agreements, Updated Induction Register
| checkpoint | 4 - Design
674f39bb-aaa0-5fe6-ba6c-8c732846fe83 | note | ACTION (Hold, Monitor, Witness) - H
f8b0a9c7-a592-5a8e-9c07-130448927477 | note | Detail - Ensure that Design is approved and Drawings are of the latest revision
48a7e1f3-0179-5062-b1dd-cb6ec302b0bb | note | Frequency - Prior to commencement
232145dd-0717-5bc6-99de-6bf95415e751 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
552ba200-df94-5c44-a61a-af7a12c982fb | note | Conformance Criteria - IFC label on drawings
007dfe12-9fad-5c0b-95e7-1fedf47013a7 | note | Records - Check Drawing Register
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Survey Setout
c816186d-6922-58a5-9561-22dda9f6b280 | note | ACTION (Hold, Monitor, Witness) - W
a8b83947-4053-5306-9537-83769885e4aa | note | Detail - Setout ducting alignment and Street light locations.
8ea6676c-d942-5716-a1e5-dff2d4a2ddcc | note | • Setout and mark all known services along the cable corridor.
908a3e98-eab2-5ff8-a6b3-8675dbbcdc23 | note | Frequency - Prior to commencement
215815d8-5084-536e-a69d-ec034782553b | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Survey
3d700e7d-1f8d-5791-a50c-3d1d952f34b3 | note | Records - Survey Records Services Ducting Checksheet
| checkpoint | 6 - Locate existing services by hand digging/ hydrovac
f1b3edf4-e2c6-515e-913e-ce91aef18a97 | note | ACTION (Hold, Monitor, Witness) - W
6dee9a57-f139-5fe7-b19b-fd7533cd91ae | note | Detail - Ensure all services conflicting with the line of trench has been exposed by hand digging
54ddf514-07b4-56de-8ffd-d0ec88e247c3 | note | Frequency - Prior to Installation
f7d0ec45-4b27-51bc-9559-d97bf659ea98 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Potholing
7029ce9b-320d-53be-ba92-506bff65c320 | note | Conformance Criteria - All conflicts have been located
89f845d5-0bab-5356-9b83-096076406693 | note | Records - Digging/Excavating Permit, Service Ducting Checksheet
| checkpoint | 7 - Material Compliance
6ae7a528-8b75-5f46-879e-9b4cde613623 | note | ACTION (Hold, Monitor, Witness) - H
002655ea-d6ba-588e-8d92-4eb3878e7b20 | note | Detail - Ensure bedding and cover material is as per vector specifications
9194b1fd-e5d6-5af6-84df-0f8eb3cbfec0 | note | Frequency - Prior to commencement
a7bfcd51-c75a-5205-8fed-66ccf2a16cdd | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
fbdb80a5-30fd-5ad1-bba2-6e23c399273c | note | Conformance Criteria - Crushing Resistance not less than 100kN. Maximum percentage of weight passing 0.075mm sieve shall not exceed 10%
40c4b3c8-5284-559e-9ae9-e322c6cc802b | note | Records - Test Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Material Compliance (2)
4bd33d5c-caeb-5da4-8482-fe1e3891d350 | note | ACTION (Hold, Monitor, Witness) - H
6f61357d-4078-5374-b827-214c6111e8f2 | note | Detail - Ensure duct pipes are as per drawings & spec.
3618548c-f07c-551e-9e30-5ba0a4e7a812 | note | Frequency - Upon delivery to site
0d189ce2-5b35-5177-b8a2-43eaa1bdd215 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Ensure delivery docket matches materials
a5c975f7-9d66-5092-804d-50b917af716d | note | Conformance Criteria - Vector requirements as per ESE303, EDE3020, EDE3024
7cdc0f58-f40a-5c33-b1ee-92bb6c4c98d3 | note | Records - Delivery Docket, Vector Specifications, Services Ducting Checksheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8 - Trenching
7132db6a-9a9d-5c72-bad5-b51925f6b1a4 | note | ACTION (Hold, Monitor, Witness) - M
b84a7aee-984a-5385-815d-f8f35d6ae956 | note | Detail - Inspect trench profile to ensure vertical depth and trench widths as per vector specifications EDE 3024 and EC-21-ACIP4-304 (900mm min cover and 650mm min. trench width for two ducts and 350mm min. trench width for singular ducts)
d76e513a-e779-52fb-a21c-d7a98be1eb16 | note | Frequency - 10m Intervals
40718bfe-0ca3-5ef6-8bbe-66b3fb0d6965 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
aca2f514-6d7d-5dd2-a7d8-84ca4fa67681 | note | Conformance Criteria - Ensure trench profiles conform with corresponding vector specifications EDE 3024 and EC-21-ACIP4-304
cc43fdfc-08ca-51a3-92e7-7fdf46289e7c | note | Records - Vector Specifications, Services Ducting Checksheet
| checkpoint | 9 - Bedding
8a41537e-a37d-5005-99e2-c300266bec46 | note | ACTION (Hold, Monitor, Witness) - H
2b00404c-9b07-5fa9-a57b-d9405e2688f1 | note | Detail - Bedding depths for Ducting as per vector specifications EDE 3024 and EC-21-ACIP4-304.
0e9ed09e-c47b-5859-a6a3-bab518252439 | note | Frequency - 10m Intervals
a30a0764-3caa-5e37-8a9a-83afe90def7a | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
990a39c1-2c19-5563-a83f-6d3ba1028bd1 | note | Conformance Criteria - As per vector specifications EDE 3024 and EC-21-ACIP4-304
615035cc-92a3-5a90-a352-8412d7efdf05 | note | Records - Vector Specifications, Site Photos, Services Ducting Checksheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10 - Warning Tape and Polymeric Slab
0b21826c-02c0-5b24-96db-e5eff8421dc4 | note | ACTION (Hold, Monitor, Witness) - H
748046d7-6d53-5a82-aca0-8ca178edfdc5 | note | Detail - Install Marker tape at 50% depth of duct cover or as per utility owners specification.
01c20d34-efd7-56f0-aada-d263e480e8cc | note | Frequency - 10m Intervals
29e4ff2e-a7a2-5ddd-a16b-b4f3f236987b | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
fc400aad-cd5e-5290-87b6-fc696d3fe061 | note | Conformance Criteria - Vector specifications as per EDE3021
7198a2ac-4049-5487-a87e-178d4b6dcc8b | note | Records - Vector Specifications, Site Photos, Services Ducting Checksheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 11 - Backfill/ Compaction (also refer to specific utility owners requirements)
25d53a27-e696-54e5-9919-5d9c6ccdc2c1 | note | ACTION (Hold, Monitor, Witness) - H
82167746-efb5-57c5-8fb3-be56bd9e2484 | note | Detail - Depth Range >1m
6bfee957-4490-5897-a8fc-493334215d44 | note | ○ Carriageway
d78186e1-695c-540e-8779-de0afe0a6235 | note | • GAP40, max. compaction layer 200 mm, as per TNZ B/2 Specification, CIV >=30
db638118-d0ef-5976-b2d0-4d83e8ad69b0 | note | ○ Depth Range >1m - outside 1m from Kerb
9053f45b-326d-5458-9761-ebaae2531097 | note | • Selected backfill, max. compaction layer 200mm, as per TNZ B/2 Specification, CIV >=20
aae1c49a-bdc4-55d5-9ec1-7cb02a12667b | note | Frequency - 10m Intervals
d50bb8b1-ac35-56d8-bd8f-3c64da0efba9 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Lab/ testing
848d7064-eb4a-5dc0-bd13-7b0b51bc8052 | note | Conformance Criteria - Pass Test Results
13e993a2-97b5-536a-a5c2-ffc974f7ebab | note | Records - Test Records/QA Sheets, Services Ducting Checksheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 12 - Assemble & Install Street Lighting Column
59e594fd-b6c9-5655-b91e-a40ff249c278 | note | ACTION (Hold, Monitor, Witness) - W
76ae8c6d-15b7-5f20-9a30-97ce755190bb | note | Detail - Confirm column type, height and outreach arm correct for location as per AS/NZS 1158
3ad8ea70-15df-54ac-8d54-5e30a250a921 | note | Frequency - Before Column Installed
7c242151-dda6-5c04-ae0a-675d10154943 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
3358057a-5d9b-5e8b-81d6-1a72847ce60a | note | Conformance Criteria - As per vector ATCoP Street Lighting
e36b9dd7-4086-58f9-8d3f-f736bfc78a54 | note | Records - This ITP
| checkpoint | 12 - Assemble & Install Street Lighting Column (2)
81d4305c-838d-5594-b707-ec59c4734e6c | note | ACTION (Hold, Monitor, Witness) - W
766fb380-d2ca-5cf5-b894-ffd93bfb0ee1 | note | Detail - Luminaire types as detailed on drawings
8cec5959-7dcf-519a-acb5-a028a9228050 | note | Frequency - Prior to supplying to site
f1310089-a463-5043-bb5e-744bfb937491 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document review
d59087b2-71c2-5eb6-957b-3c4663315798 | note | Conformance Criteria - Refer to IFC Streetlight Drawings
0041096c-ae39-546d-97a2-65241e9dcf94 | note | Records - Delivery dockets
| checkpoint | 12 - Assemble & Install Street Lighting Column (3)
aedd9018-404c-5f4d-a483-95ea6240a8a7 | note | ACTION (Hold, Monitor, Witness) - W
72de33d2-7d6a-5863-a7ed-09d9798c76cc | note | Detail - Streetlighting to be position no more than 1m away from face of kerb to face of column
075a6f41-f52a-5b4d-8406-1f296d55deee | note | Frequency - Column Installation
690b2117-7d7a-51c8-955d-7877bd0c6ec3 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
290cc2de-4f63-57a9-a1f2-86da0c11f088 | note | Conformance Criteria - As per vector ATCoP Street Lighting
4ad58473-070e-5e2e-a5f9-aead0f4d49ff | note | Records - This ITP
| checkpoint | 12 - Assemble & Install Street Lighting Column (4)
342b763e-d77d-5284-b61a-6368331d415b | note | ACTION (Hold, Monitor, Witness) - W
d87fc44e-527e-5e13-aacb-7f588295efae | note | Detail - Foundation to be excavated as per manufacturer specification for ground planted columns
34874517-fb29-5c48-86b6-df9c9a30bd57 | note | Frequency - Column Installation
cf3bd50e-bdb3-5631-b0bc-0ff4d1a364c7 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
6dce01f8-1428-5f09-97ea-615359c53706 | note | Conformance Criteria - As per vector ATCoP Street Lighting
85d73b4b-e7df-588e-aa35-28acb0bf01e9 | note | Records - This ITP
| checkpoint | 12 - Assemble & Install Street Lighting Column (5)
391d7d9c-704f-5496-bebe-65c29ba203e9 | note | ACTION (Hold, Monitor, Witness) - W
5f1f994a-19b7-5c1e-88b4-fea10c216863 | note | Detail - Backfilling with granular or concrete as per manufacturer specs
fe1d8a65-c881-5267-b56a-348e3718c6b3 | note | Frequency - Column Installation
c95b2a08-88eb-51bb-af9c-60cfddde2231 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
518a0976-77dd-55c5-97a8-6f61033e013f | note | Conformance Criteria - Refer to IFC Streetlight Drawings
22c27657-13a3-5b76-9471-3bd330edb70c | note | Records - This ITP
| checkpoint | 12 - Assemble & Install Street Lighting Column (6)
285c9d76-4395-5783-9b7e-4d94b100ca11 | note | ACTION (Hold, Monitor, Witness) - W
f0513133-05d1-5fec-808a-a145ef4db291 | note | Detail - Confirm column is bolted to base stub as per Manufacturer's Instructions
ab7919a9-6d3e-5aa0-83ff-0c070b5adde6 | note | Frequency - Column Installation
22e4afb7-f45b-5563-aa27-f70902185273 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
6e711e0b-035a-5a17-9fca-8750956e2e1c | note | Conformance Criteria - Refer to IFC Streetlight Drawings
144973c2-0cc6-58c5-b77c-67767b0fb6c0 | note | Records - This ITP
| checkpoint | 13 - Tud/Pit/Chamber Installation
9bd51fa4-f160-5713-a037-303bd440218d | note | ACTION (Hold, Monitor, Witness) - H
11abbce4-2bf9-5c6d-9fe9-9483233c1498 | note | Detail - Where needed, Ensure TUDs/pits and chambers are installed in the correct locations at asset owner's instruction to manufacturer and asset owner specifications
4063893c-78c9-563c-bc30-f0a19d8ba926 | note | Frequency - During Installation
988e581c-951c-5872-a8ab-1b9d80539406 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Site Inspection/Design Review
8716f0be-af8c-5bb7-962c-2907d25938ca | note | Conformance Criteria - Sign off and approval by asset owner/MSQA
f635b7eb-4dcc-5688-ba77-2fb1796ce1fd | note | Records - Site Photos/ Checksheets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 14 - Commisioning
ae31cde9-b3cd-5912-bb12-80db065ad1ef | note | ACTION (Hold, Monitor, Witness) - H
dc4ec3ff-2ba7-500b-bb48-006514db7d81 | note | Detail - Ensure that certification, testing and commissioning undertaken according to Utility Service Provider's guidelines. After livening a test sheet recording the measured voltage at each light and each circuit current is required.
3e2616ef-3e38-54c9-817e-4c09ce9369b7 | note | Frequency - Post Installation
108bf2b6-4fd9-566c-a9ba-ed35708ab3de | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
0e5d2298-5ba0-5c99-94bf-41be10f301a1 | note | Conformance Criteria - Commisioning completed by vector authorities for Certificate of Compliance and Record of Inspection before operational sign off
06b97400-d4e4-5c03-bf93-ae836731030e | note | Records - Test Certificates, COCs and ROIs
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 14 - Commisioning (2)
326a8fb2-eaf8-5d4c-86d7-07b35c13d0dd | note | ACTION (Hold, Monitor, Witness) - W
0f4534f9-e2b5-57dd-9174-211c17092824 | note | Detail - Equipment labels for Poles, Lighting Supply Boxes and internal equipment installed
e09f3bae-5ee5-55a6-86fb-b612b058281e | note | Frequency - Post Installation
9b9f4377-cff7-5648-b7e8-ab92a768f0ba | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
ed9db401-de8f-5464-ae73-16040d45e9fd | note | Conformance Criteria - All relevant labels placed
290860b3-fe5f-5f83-82a3-38a8501480ee | note | Records - Photos,This ITP
| checkpoint | 15 - As-builts
41dda943-c271-5513-b7d2-75577de67a16 | note | ACTION (Hold, Monitor, Witness) - H
274aa17f-c668-5088-9ebe-9bc2e993b86b | note | Detail - Cable installation records, Electrical test records, materials and equipment schedule, Survey As-Built
3c44c916-868c-5e38-a093-7695024df409 | note | Frequency - At the completion of the Lot of work
5cae95ab-4aa9-5bf3-84c2-35e29906cc3b | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Drawings/Documents
15ea2eda-c60f-5f05-b0e9-07112f0b54ea | note | Records - Survey Asbuilt Documents
| signoff | AUTHORITY HOLDPOINT
| checklist | Ponsonby - ITP - Earthworks and Retaining Wall |  | Earthworks and Retaining Wall | aa87a800-7060-4dfd-8977-fcfec0f414de
| checkpoint | 1 - Permits
476d18aa-e843-587e-bcb0-f4418e889dd2 | note | ACTION (Hold, Monitor, Witness) - W
4566bcfc-537a-55c2-8d6d-dc7199a38e4e | note | Detail - Obtain Permits
6ee160e2-2a1f-5b00-bd9d-3e0e0156598a | note | Frequency - As required
2e3c6da8-01e3-5e86-8b25-3dcee36cb066 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
662205c4-1987-59fb-be6c-859643243e27 | note | Conformance Criteria - Control Checklist - Digging / Excavating (incl. marking out & potholing existing services).
22f177fc-e14c-5fa4-8cf5-73e9722e7f34 | note | • Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
1f2473e7-3d3e-50a3-8c4d-6a7d737353b3 | note | Records - Permit attached or permit number noted
| checkpoint | 2 - Traffic Management
f5f0ca04-2bb6-50e0-aaf0-6f8e2bc43cf4 | note | ACTION (Hold, Monitor, Witness) - W
7cca0307-63e7-5572-9ca3-9f2f3fe77352 | note | Detail - Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
f3238d81-33e1-5a6b-b6a7-01d0b78c23b8 | note | Frequency - Prior to commencement
debc195f-3b57-563b-a879-836cd2f123be | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
46bdb85d-f3f6-5e81-a4d8-e8c77411ecd4 | note | Conformance Criteria - TMP is approved by AT for the site and works are only completed within the approved dates
eecebabc-07c0-54c0-9861-3cf2e0528470 | note | Records - TMP on MyWorksites/OnSite
| checkpoint | 3 - Pre-construction sign offs
bb078642-d4cc-56e0-8545-a233ad5795ab | note | ACTION (Hold, Monitor, Witness) - W
48692666-8b2c-5489-8282-52ecac10e587 | note | Detail - Ensure that Sub-Contract and Supplier Agreements are signed, all Sub-Contractors and Suppliers are inducted to site
123fd141-b838-5599-bd82-bf72526f4272 | note | Frequency - Prior to commencement
cc8ffa1e-bc5b-50bd-9b5b-6adfec2acd3f | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
2a3ce4eb-a142-5c29-8814-51c65f3af1d2 | note | Conformance Criteria - Signed Subcontract and Supplier Agreements on M-Files and Induction Register updated
c5c24693-e350-55f9-966b-05e8400d4cb3 | note | Records - Subcontract and Supplier Agreements, A & Updated Induction Register
| checkpoint | 4 - Design
40b9684f-402c-52cf-bc87-b6497bc5afea | note | ACTION (Hold, Monitor, Witness) - H
ac847999-83da-5e3c-829f-4c37847bc125 | note | Detail - Ensure that Design is approved and Drawings are of the latest revision
bc3cb441-955d-5baa-94db-5ba8f1d02dd9 | note | Frequency - Prior to commencement
7e8134ff-ff40-5e1e-ab9a-9554dfe92639 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
b87bb4ac-df66-582f-ad17-88c7296d04af | note | Conformance Criteria - IFC Label on drawings
809ed49b-da43-5bbb-8e32-9255711deb79 | note | Records - Check Drawing Register
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Material Compliance
fb997be0-0624-5660-908d-5a287068ab52 | note | ACTION (Hold, Monitor, Witness) - H
a606e9e7-dce8-5424-b709-a41c94d92069 | note | Detail - Granular Fill Material requirements
cb8dcd42-f59a-574c-af90-d094d036d6e2 | note | Frequency - Prior to commencement
8cde9b74-9036-5c71-ba94-4e6651440a64 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - As per TNZ F/1:1997
19939408-1e3c-5beb-93c2-8814bd8e29ab | note | Conformance Criteria - Maximum percenetage of weight passing 35% 0.0075m sieve shall not exceed 35% and has a sand equivalent greater than 20.
78ad7de1-5dc3-5bef-8379-67ca35533831 | note | Records - Test Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Survey Setout
2121ab9c-9de4-5d47-a08a-585bff3151f4 | note | ACTION (Hold, Monitor, Witness) - W
b1a8002a-e62a-587e-adb4-7ea9f6541732 | note | Detail - Setout cut/fill areas as required by to construct to design. Topographical surveys to be completed prior to starting, monthly and upon completion
3c724079-19f8-577f-80c6-3add44e2df15 | note | Frequency - Prior to commencement, monthly and at completion
f3ae3b25-7f23-5da2-8a76-0733efb12bd6 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Survey
619fd688-7c90-5646-ac83-c851815c0c21 | note | Records - Check Drawing Register
| checkpoint | 7 - Installation of Erosion and Sediment Controls where required
169cf02f-edc8-51a9-a2a5-4e9469f1b7d5 | note | ACTION (Hold, Monitor, Witness) - H
2087b8ee-ad62-54cb-a5ea-494620e109cf | note | Detail - Setout Environmental Controls and confirm location with Environmental Manager
d8298e1b-b3b5-583e-934b-6f579940a147 | note | Frequency - Prior to commencement
52aaf298-2e10-5738-9170-39817d18a1c4 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Review
219f31ce-6816-5bca-9c8a-082e4db691b0 | note | Conformance Criteria - Correct volume for area and setup to TP90: 1999
e5f4e055-0568-51e7-9adc-6aa0a30947fc | note | Records - Survey receipt
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Installation of Erosion and Sediment Controls where required (2)
7f1794de-c384-5bc8-8de6-74619711043d | note | ACTION (Hold, Monitor, Witness) - H
9e9e9791-d9d3-53c5-8800-a0a8810aea9c | note | Detail - Design Engineer Rep/ Client Rep to inspect controls after implementation
46026937-c312-5a49-afe4-b5a6dbb6bf31 | note | Frequency - Prior to commencement
286dc184-b0cb-5e02-97a4-7a5f49ed8c92 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Submission
7401e037-d2be-5d2d-92d3-305453e4e0b5 | note | Conformance Criteria - Correct volume for area and setup to TP90: 1999
c0691931-f29e-5b2f-ab0e-c76b5f4bcdc1 | note | Records - As-built
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Installation of Erosion and Sediment Controls where required (3)
58a815d7-f682-50a1-9281-c94cc845e825 | note | ACTION (Hold, Monitor, Witness) - M
b425ab10-1df2-5c30-b19c-bf48e6e0299c | note | Detail - Monitor sediments tracked out onto any roads and the generation of any Foreign objects and debris as well as dust generated
1bf68b71-1741-5bff-8030-34d8b1d06a7c | note | Frequency - Continuous monitoring
2334103c-63a8-580a-b26a-cdd71cf705cf | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
9c39b137-316a-5212-a5fe-cb597a2374aa | note | Conformance Criteria - Roads free of debris using watercart where required to minimise dust generation
d2396f7b-2684-5d3b-8ee9-5c65c090b254 | note | Records - This ITP
| checkpoint | 7 - Installation of Erosion and Sediment Controls where required (4)
1db8bc20-2042-5f22-bbde-1b66eeed6c3c | note | ACTION (Hold, Monitor, Witness) - M
86c476e8-9a66-50f9-9420-9949f808f304 | note | Detail - Monitor effectiveness of the ESCP Controls throughout the work
deb2f2a9-a4a9-5bb7-8609-637491f48a82 | note | Frequency - Continuous monitoring
63cc1d2a-4709-5bfb-9f20-14ed9a518fe9 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Measure
117cb6de-7977-5ddf-a89d-862ea2d74ec3 | note | Conformance Criteria - In accordance with Auckland Council TP90:1999
b1db12f3-2503-5a26-b983-92093395b14e | note | Records - Audits
| checkpoint | 8 - Site Clearing
89299c72-2c10-502b-9a52-4a2c5e27a292 | note | ACTION (Hold, Monitor, Witness) - W
548609c0-1c06-5eaa-863e-f81a1337d468 | note | Detail - Removal of pavement layers, vegetation, services and other objects
3302c992-bb5c-5ac6-9e61-e5541b03a261 | note | Frequency - During Physical Works
d5f2c338-8866-5ed9-99c6-fbf335a2d9cb | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
1ddb3baf-290d-569e-b10c-8dbd0352d5ad | note | Records - Photographic / Videography
| checkpoint | 9 - Stripping
d58fa683-6287-542c-abf8-08c57da9c9b6 | note | ACTION (Hold, Monitor, Witness) - W
08695874-4619-5375-8ac5-581eae4abed3 | note | Detail - Determine if topsoil suitable for respread after earthworks are complete
34663f0c-9cad-57fb-b4e8-d4fc7d508329 | note | Frequency - As required
3b5e2658-f08c-5104-8262-f1c39e55be04 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
3c988cd4-8f91-53f3-ae61-02107d8f8778 | note | Conformance Criteria - Stripping in accordance with TNZ F/1:1997
8e930301-2aaa-5c5d-b37e-1a1bf93cfa4d | note | Records - Photographic / Videography/ Checksheets
| checkpoint | 9 - Stripping (2)
fdee69fb-ff13-5991-a7d0-608b4ac578b1 | note | ACTION (Hold, Monitor, Witness) - H
a931da39-cb49-50f2-9bab-caec835b0b47 | note | Detail - Joint inspection with Engineers Rep and carry out topo survey
514e62ca-15b0-59b2-a7ba-030a4974105c | note | Frequency - On completion of stripping
19712ca7-f5fa-591e-9686-2c1c7b0752a3 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
9749bcff-bf08-56eb-89f2-d02c8942db1d | note | Conformance Criteria - Ensure topsoil stripping is complete and area is clear of organic material
7c57c59e-9510-58f9-a9af-ea39a85c4a68 | note | Records - Photographic / Videography/ Checksheets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10 - Stockpiling
1c80f65c-0716-561f-aead-4a7ddb08e0ed | note | ACTION (Hold, Monitor, Witness) - M
ad4a6a45-ae2e-5c73-9eca-69fe74f87e9b | note | Detail - Ensure stockpiles are separately stockpiled, exposed surfaces to be compacted sufficiently and away from runway, inlets and coastline
375496d8-8f44-55bb-a81d-8689b59221aa | note | Frequency - As required
64b5ade0-fc47-56ad-aa65-9edfe54edf95 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
9fb2e8b4-da15-5fd4-8458-0ee966107376 | note | Conformance Criteria - Stockpiling in accordance with TNZ F/1:1997. Stockpiles to be minimum 50m away from watercourses.
1ee528f7-0c9e-525f-8ec1-b46a4705ad1a | note | Records - Photographic / Videography
| checkpoint | 11 - Retaining Wall Foundations
be3c4f83-df40-5f7b-adef-9493cc67304a | note | ACTION (Hold, Monitor, Witness) - H
9ba376f0-67ce-5ffe-a834-fd5b661be6bc | note | Detail - Shear vane Strength
bdfa4193-9535-592f-8e63-c32a1570dfde | note | Frequency - 1 tests per 4m2
a2b040b3-ca19-5c31-b67a-3984443f044f | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Testing
8e403517-ffb9-52f5-87ec-5b73fcacdb11 | note | Conformance Criteria - Shear vane to exceed 80 Kpa or otherwise subgrade to be undercut and repalced by specfieid granular material at Deign Engineer's discretion
76d0a0e8-ffc0-58a5-a3ef-8952956ce36f | note | Records - Lab Test reports
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 12 - Cut Subgrade testing
a33ea9e2-fd91-5964-9fd2-e857e2a474a5 | note | ACTION (Hold, Monitor, Witness) - M
58d1a100-754e-5c9a-a96f-6f83c2c0978f | note | Detail - Subgrade Surface - Straight Edge
1aa63d75-6c9a-5706-b159-6ae571d3e698 | note | Frequency - During Construction
455d7ec5-b78c-5482-9f13-4ef63a8aa05e | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Survey
a094d7cb-96f5-5d4a-a3bf-a22f0bd1df27 | note | Conformance Criteria - As per TNZ F/1 clause 11.2.2 - All points within 30mm of true from a 3m straight edge laid parallel to centreline of road.
53689f3b-c483-5268-80c2-eb562d7516d6 | note | • The subgrade surface shall not pond water, where the design slope of the subgrade is 2% or steeper.
30795fb8-2205-5f54-860c-436a6590839a | note | Records - Survey receipt
| checkpoint | 12 - Cut Subgrade testing (2)
d9e210e4-8c07-549e-9f96-2cefd204dcd1 | note | ACTION (Hold, Monitor, Witness) - H
8caeb890-0d5d-5e4f-975f-c6f14f58d697 | note | Detail - Scala Penetrometer Testing
f4663ab3-af2e-5e7c-8eaa-f553c1ea458a | note | Frequency - 20m intervals to a depth of 1m at alternating wheel tracks
d72fd032-ac04-541f-a119-18750c899067 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Lab Testing
29e9dfa4-e569-50d1-ac00-3cc487a3995b | note | Conformance Criteria - Scala Penetrometer to a minimum depth of 1m and shall have no reading less than specified CBR of 3.5%, where Subgrade is gravel, Clegg hammer shall have no reading less than CIV 7.
3074eec4-f3eb-5141-87f9-2ba13bc490da | note | Records - QA Sheets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 13 - Bulk Fill Material Testing
3a9d98e1-8fc6-5f5d-99d9-cfd3f7daf4f6 | note | ACTION (Hold, Monitor, Witness) - H
a0974e03-dfd1-5253-8a2a-a4b6931d6b35 | note | Detail - Compaction shall be to TNZ F/1 with maximum layer thickness to not exceed 200mm
6c627c1c-9eb8-5480-ab12-7203e3471889 | note | Frequency - Every 200mm lift at/ 1 test per 4m2
7b4d85d5-b1e3-58d4-a1c5-f2ab3d6b2cff | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Lab Testing
5188d2e9-a5ea-503b-aa98-bf98b70ff500 | note | Conformance Criteria - CIV >= 25
8eb885bd-ac8c-594c-83ca-4c23144c0bf1 | note | Records - QA Sheets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 14 - Final Inspection
46b67b5d-a6a9-5e78-b95c-86cb7793efac | note | ACTION (Hold, Monitor, Witness) - H
bccebad1-97ae-5d51-a0e9-9a61a2445ca3 | note | Detail - Subgrade inspection by Engineer
16b5f509-817b-5152-860d-35beeeffacd4 | note | Frequency - Once per area
1847039a-7287-5ebe-a4a3-c27275061d24 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
3e0e175d-7f59-5986-9c96-dcc18d606e73 | note | Conformance Criteria - Final sign off of subgrade by Engineer.
e6bdfce6-e124-5dc9-8844-76aa510a5f5b | note | Records - Photographic / Videography
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 15 - Retaining Wall Construction
b6d40f0d-6585-55e1-9eac-daf9fe478b86 | note | ACTION (Hold, Monitor, Witness) - H
21547ee8-a77a-5267-b308-318985d6fc6a | note | Detail - Material Compliance
474e277b-7732-5c47-8b17-c69fd9f21937 | note | Frequency - During Construction
38145a09-9f9d-5e04-8ce8-fa7c3b33daa3 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document review
aa203fd7-7ef8-5bc7-9ceb-229c6ccceb73 | note | Conformance Criteria - High Density H6 treated Radiata poles to be used for construction unless specified other wise by Design Engineer H5 treated timber to be used as railings unless specified otherwise by Design Engineer
3477cd22-105e-537a-b919-ed7c08eabde4 | note | Records - Delivery Dockets/ Design Engineer Correspondence
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 15 - Retaining Wall Construction (2)
f358bbd1-7a76-51ed-bb67-795457ce4e05 | note | ACTION (Hold, Monitor, Witness) - M
5831e637-bcde-5567-9154-37b5d44e090d | note | Detail - Concrete Encasement
626a032c-27f4-5691-9d3c-9516f26aefe6 | note | Frequency - During Construction
3be9f0bc-616d-5e89-b9c2-66e1f9c68470 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
77f0f17d-a0ad-563a-95ed-0c62afce4f6e | note | Conformance Criteria - Concrete mix to be a minimum 17.5 Mpa, high slump mix, 10mm chip.
069fa1ca-1941-50d0-b023-90eaa6063fc7 | note | • Minimum of 100mm cover below timber poles
4cf00c01-e14a-5ec3-a51d-92dabcbf4250 | note | Records - Photgraphic / Videography / Delivery Dockets
| checkpoint | 15 - Retaining Wall Construction (3)
b0c5c961-2e22-5a88-9717-04192e320f5e | note | ACTION (Hold, Monitor, Witness) - H
c808ce02-3461-5051-8aff-b32a86b292b9 | note | Detail - Subsoil drainage
93fe06c5-3dc7-5959-8154-2e91a901710b | note | Frequency - During Construction
f1e3c1be-f28a-57f5-92bf-f66056771886 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
da30bc0f-b137-580c-8b8f-1918894bd4ca | note | Conformance Criteria - Subsoils to be 110mm preforated pipe with filter sleeve sock.
ffa7bd89-21a2-5f45-b3d9-510cd985cd5e | note | • Bidim A29 or approved geofabric to be placed between drainage material and surrounding ground.
6b39060c-b959-5b7e-b772-014f5f43e0d7 | note | • Drainage 40/20 freeflowing aggregate to be used as bedding and cover.
0b4c9fdc-b97f-5ba2-ad0c-1cbcd1165ae9 | note | Records - Photgraphic / Videography / Delivery Dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 16 - As-builts
79bd9c47-9108-59b0-a673-4f9f61c85575 | note | ACTION (Hold, Monitor, Witness) - H
db76e515-414a-57de-9199-548645c72530 | note | Detail - Red pen mark up drawings to be included in QA file
16e6d93c-8247-5c97-a95c-983937afeb1c | note | Frequency - At the completion of the Lot of work
1f1f476c-851c-543f-8522-35dc9bcebdcc | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Drawings
eb25bc3d-c6ef-551d-b157-afcc02d9bc3f | note | Records - Asbuilt Drawing
| signoff | AUTHORITY HOLDPOINT
| checklist | Ponsonby - ITP - Footpath Construction |  | Footpath Construction | b6ed7067-2f1c-4438-a6bc-692caf2b97f2
| checkpoint | 1 - Permits
0e5e4114-f77a-5340-a3d2-bc834619232e | note | ACTION (Hold, Monitor, Witness) - W
5e55b5ae-6a7a-5bd2-8206-129f19aeb630 | note | Detail - Obtain Permits
b99db9f8-1043-5e3b-a4a1-a82dc7f96f63 | note | Frequency - As required
f3372cf5-4ab4-556a-a6fd-132c2509bd4f | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
8761135e-19a6-5303-a248-07ed631c803c | note | Conformance Criteria - Control Checklist - Digging / Excavating (incl. marking out & potholing existing services). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
3fec396c-71a5-5026-808b-20df80e05afc | note | Records - Permit attached or permit number noted
| checkpoint | 2 - Traffic Management
5cddd236-4827-5d26-bdf2-47df66053f6f | note | ACTION (Hold, Monitor, Witness) - W
f77d0210-893e-5d7d-bd2b-ef04bb944559 | note | Detail - Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
6636b103-ff55-5fd5-8234-97a8d1b8da92 | note | Frequency - Prior to commencement
a4b1e451-7d0b-5de7-aa31-985fb0ba116f | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
81d6b8c1-4bec-55b9-9da5-785340edfd14 | note | Conformance Criteria - TMP is approved by AT for the site and works are completed within the approved dates
0f5ffd83-23fa-57d3-a66b-13ca0d7b3231 | note | Records - TMP on MyWorksites
| checkpoint | 3 - Pre-construction sign offs
638133d5-137f-5c74-9a6b-500e14f5fb23 | note | ACTION (Hold, Monitor, Witness) - W
196c4253-486d-5052-b4e1-f255e6cf5297 | note | Detail - Ensure that Sub-Contract and Supplier Agreements are signed, all Sub-Contractors and Suppliers are inducted to site
ed083a39-6d10-51e3-8079-ed7873696d21 | note | Frequency - Prior to commencement
8fb7599c-c8c9-59b9-8f6a-ed66b9e661ed | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
7d9eb675-53ce-5d1b-acd2-a8a5519c74f6 | note | Conformance Criteria - Signed Subcontract and Supplier Agreements and Induction Register updated
41dd2dc0-dc33-5499-941a-2f36462a28cc | note | Records - Subcontract and Supplier Agreements, & Updated Induction Register
| checkpoint | 4 - Design
e7cebae2-b2a0-531d-a646-0d38d463adf0 | note | ACTION (Hold, Monitor, Witness) - H
6cd3fee2-81b1-5b15-adf8-43b84db9eb05 | note | Detail - Ensure that Design is approved and Drawings are of the latest revision
4d04c102-2793-5cb8-9787-6621b0633737 | note | Frequency - Prior to commencement
b7caaf6a-e204-5a43-b881-ef723d36b0d7 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
d64cb15b-994a-5a65-9ac0-915bf863a53a | note | Conformance Criteria - IFC Label on drawings
c29b95eb-7e8b-525f-b33f-b9084b4c7003 | note | Records - Check Drawing Reegister
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Survey Setout
e12ed889-d3fe-5cb2-97bf-69d4c4eee536 | note | ACTION (Hold, Monitor, Witness) - W
203aec93-4233-5ff6-a2ae-daae5ce13350 | note | Detail - Set out pegs installed every 10m of the footpath showing the FL & giving indication of line, extra pegs required on curves or special features
29a94fd6-68a5-5d92-997b-ad2e753d68e8 | note | Frequency - Prior to commencement
2c5dc183-2877-5ac2-b7e3-c3234f42953d | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Survey
dcbda7df-924c-5af7-8abb-ea4bf52359b4 | note | Records - Visual Inspection
| checkpoint | 6 - Material Compliance
f509bd83-109b-5d4d-99f3-d3c585a7efed | note | ACTION (Hold, Monitor, Witness) - H
b23ffd78-9a62-5138-a02d-901447634b6b | note | Detail - GAP40 - Basecourse
15e672da-8c6b-52a9-9f32-407c59b56171 | note | Frequency - Prior to commencement
286f4d9b-9eb3-511a-9311-0f3e4c03657f | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Lab Testing
7f573dc9-c757-5afb-9125-7b4264ad39d8 | note | Conformance Criteria - Grading test only
8662cc24-35f5-5635-ad7d-70ab4f5783fc | note | Records - Lab Test Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Material Compliance (2)
50340e53-2e28-5737-8fb0-058a82ea01eb | note | ACTION (Hold, Monitor, Witness) - H
f47f8e6b-b25f-5818-affa-dce7219e1f07 | note | Detail - Concrete Mix Design at 20 Mpa in accordance with ATCoP
bff3bbb7-4208-535e-b3f7-e9d8018f306c | note | Frequency - Prior to commencement
a754b901-856f-544a-bfb3-a322b6960ef0 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
457107a8-4f24-5ef4-99b4-81fa85f57051 | note | Conformance Criteria - Mix Design is approved prior to any concrete being delivered to site by Design Engineer
437cc26e-2cc1-54ea-967b-f458c3396efd | note | Records - Mix Design Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Subgrade Compliance
e2b34986-f02d-5c67-a866-329e0d736898 | note | ACTION (Hold, Monitor, Witness) - H
05dabe9a-c85c-5326-a954-490dcefcf7f7 | note | Detail - If Existing Subgrade CBR<3% or CIV<7 (if granular), Base layer thickness can be increased by 100mm at Design Engineer's discretion
e2e2d744-2ee6-5868-9b65-cac2bf87f534 | note | Frequency - One test per 10 linear metres
427f83f8-d02d-50f5-a164-48bd22704a8e | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Design Engineer Inspection and Correspondence
17d857f8-bd58-568d-9104-370cfa58cb9e | note | Conformance Criteria - CBR> 3% or CIV>=7
7c5cd335-88c4-535c-84fb-9780db513259 | note | Records - QA Sheets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8 - Basecourse - GAP40
875ef245-e53e-52bf-9249-fd448a442b5b | note | ACTION (Hold, Monitor, Witness) - H
ca7be100-d1c7-55c6-b93d-a3880570a1ab | note | Detail - Compaction of GAP 40 with minimun 100mm thickness
169d7f93-93b2-5e66-9350-f9df176e9ce8 | note | Frequency - Upon Completion
2c1922cd-8270-5ea3-a84a-8364fefa056e | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Clegg Test
02262ea2-b476-5274-ad7d-04dc4afc36b2 | note | Conformance Criteria - ClV >= 12
783b357e-0b6d-58a3-8510-8e102354b7c0 | note | Records - QA Sheets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Concreting
b4bd46f2-1abf-5405-a9b4-6606f38f8e0d | note | ACTION (Hold, Monitor, Witness) - H
2a4062ae-8f5f-57b7-885a-e89e064e5ef4 | note | Detail - Before any concrete is poured a prepour inspection to be carried out
5adf0c27-b97a-5d9e-b3fb-47af394603d8 | note | Frequency - Pre-Pour
5d3766f3-f95a-5283-9be9-f51cb973c1ae | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
70ce195d-91ce-5818-89cd-341be4b015e3 | note | Conformance Criteria - Concrete pre-pour checksheet
f37e89cf-b116-5d21-9f3a-2bc30379ae78 | note | Records - Checksheets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Concreting (2)
ea977ed7-cfe4-5cd7-97ac-98580ae68ec6 | note | ACTION (Hold, Monitor, Witness) - W
2550ee62-6ede-5b1e-8838-2e84691eede1 | note | Detail - Ensure concrete type and finish is as per specifications & drawings. Concrete panels should be no longer than 3m.
3cdfb57c-a835-522f-8ad9-519e646eeffe | note | Frequency - Pre-Pour
163dd34e-bbc6-5f4d-8c4b-4895c124ce45 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
5400a180-0573-5049-a37b-4f7abaa9c8de | note | Conformance Criteria - U5 Broom Finish
1f8d1d42-b5bb-5065-a7ec-d6ab3ee0309f | note | Records - Concrete docket/ Photos
| checkpoint | 9 - Concreting (3)
2b97c00e-386e-50c2-9503-af99f1769ecc | note | ACTION (Hold, Monitor, Witness) - H
02506c10-c9f9-515e-81c8-88f5813ad2fd | note | Detail - Vehicle crossing basecourse to be of a minimum 100mm thickness of compacted GAP40
7e6d15e6-7b78-582a-88c5-3e1301e8b1f5 | note | Frequency - Pre-Pour
b4b90215-8d0c-54cf-9dda-bfbfaa7ca087 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Clegg Test
d00866ae-950d-5b3b-baf6-48df0814d4a2 | note | Conformance Criteria - CIV >= 25 as per ATCoP drawings
3d584a31-947b-5390-8f03-4c34d8838278 | note | Records - QA Sheets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Concreting (4)
5dd7ec35-837d-545d-90a4-42c05ea7e735 | note | ACTION (Hold, Monitor, Witness) - H
2ae0abde-c65b-5073-9b62-6ace6aad0574 | note | Detail - Bus Shelter Foundation Prep
869539eb-a0db-578c-9de7-a32dffcf419a | note | • Concrete thickness to be 2oomm
57b79189-f084-5293-91e2-0835f534f526 | note | • 100mm GAP40 Basecourse.
0c5b0364-8d5b-56df-b505-c2b6527ba6ee | note | • 2 layers of 665 mesh
f7fbeaf4-d424-5f96-85ed-80dbf464021b | note | Frequency - Pre-Pour
8fb9f7be-fbb8-5cbb-9445-019c3badccba | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Clegg Test
1530a748-c96b-586e-a6f2-35a30172b19f | note | Conformance Criteria - CIV >= 25 as per ATCoP drawings
2f198c14-6045-5685-b319-350abf699e6b | note | Records - QA Sheets/ Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Concreting (5)
29263ea1-5a8d-59b9-bca9-556e643288cc | note | ACTION (Hold, Monitor, Witness) - H
707043b9-ad05-5771-8d99-6a62663f83a6 | note | Detail - Tactile pavers are installed per drawings & specifications
83d16a0d-b38d-5820-a6fb-55ec077a1982 | note | Frequency - Pre-Pour
b0996d1d-1bc9-5646-a2c1-74b9b7ff1b81 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
3759e57f-27b3-5ff8-9759-d95939dd9325 | note | Conformance Criteria - As per drawing
7f3ca029-f9c5-54da-9192-54e55535b125 | note | Records - Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10 - Signage
800c266a-370a-5568-9544-4a04e8134c36 | note | ACTION (Hold, Monitor, Witness) - W
1c06e215-df35-5108-be47-85a8b30a7a86 | note | Detail - Signage sockets and signs are installed as per drawings and specification
e3e2e1bb-35d8-58ec-ada4-86ca02242886 | note | Frequency - Upon Completion
c855db46-8fa7-5c5d-8653-096c59996703 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
e61758c9-000c-52da-9989-4b523fdf8c0d | note | Conformance Criteria - As per drawings
7846f176-0a47-5823-a32e-34ad119bbfae | note | Records - Photos
| checkpoint | 11 - As-builts
e0d4ba0a-f459-5bec-872e-1495edb47faf | note | ACTION (Hold, Monitor, Witness) - H
0f785c88-d743-57c2-a44b-d23ca6e23029 | note | Detail - Red pen mark up drawings and RAMM to be included in QA file
52d45d93-dbab-5fd1-a1b4-311b2626c410 | note | Frequency - At the completion of the Lot of work
47e39675-3690-5d5f-81af-c383c6affe16 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Drawings
13837915-81c3-5a70-8c0a-3327e888198d | note | Records - Asbuilt Drawing
| signoff | AUTHORITY HOLDPOINT
| checklist | Ponsonby - ITP - Kerbs & Channel |  | Kerbs & Channel | bae55c6d-caf7-4f40-a26c-9a818cca6c92
| checkpoint | 1 - Permits
62e20d89-4479-5940-827a-6736dd6ee661 | note | ACTION (Hold, Monitor, Witness) - W
36403740-8a7a-5e5a-94e0-b2d1966ee4a4 | note | Detail - Obtain Permits
b86fe1c4-9814-5c8a-aa5e-2475975473c5 | note | Frequency - As required
7f4aaec4-6890-573e-bf5a-3c021b454b50 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
f2482cd8-5914-53cc-a6f3-55cb4f5f5811 | note | Conformance Criteria - Control Checklist - Digging / Excavating (incl. marking out & potholing existing services).
98cbc3c9-f101-5286-945b-bc6b21f293f3 | note | • Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
b9756b96-c191-5236-9d66-a0b95879cbda | note | Records - Permit number noted
| checkpoint | 2 - Traffic Management
5954f96f-bec2-5e46-bad0-71b73c821ff8 | note | ACTION (Hold, Monitor, Witness) - W
a8de58a6-1f6a-555a-bb64-41fd340d359e | note | Detail - Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
5828343d-8f7d-5011-8a86-008f90fb831d | note | Frequency - Prior to commencement
fa8acb75-f229-5f47-8eb3-50e6c56e1c35 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
b1a0d9d2-f8cb-5e5b-8b06-18f672019a4a | note | Conformance Criteria - TMP is approved by AT for the site and works are only completed within the approved dates
2800da23-c52c-5acd-94e2-bf5982474db2 | note | Records - TMP on MyWorksites/OnSite
| checkpoint | 3 - Pre-construction sign offs
4dc2c4de-06c9-520f-bd64-d5b741ba8f7a | note | ACTION (Hold, Monitor, Witness) - W
9570df9b-4058-5410-94a3-18e83ce18281 | note | Detail - Ensure that Sub-Contract and Supplier Agreements are signed, all Sub-Contractors and Suppliers are inducted to site
283d34be-cff7-59b3-ae68-c5d7609717eb | note | Frequency - Prior to commencement
4d430236-1e1c-542a-a1ab-65b737fe73e8 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
6e13620a-8786-5fe3-a6b2-c09dda948bbc | note | Conformance Criteria - Signed Subcontract and Supplier Agreements on M-Files and Induction Register updated
1284fa02-2a3d-5351-b1bc-b3d622d792df | note | Records - Subcontract and Supplier Agreements, A & Updated Induction Register
| checkpoint | 4 - Design
82f7cda9-c75c-5bbc-a865-d30f216fbb89 | note | ACTION (Hold, Monitor, Witness) - H
6c5d2ff3-b5e4-59e8-b258-f73189c979b7 | note | Detail - Ensure that Design is approved and Drawings are of the latest revision
f6919c83-fc72-548f-aada-2d63f91a6310 | note | Frequency - Prior to commencement
c4472227-fc70-521d-8c64-67443ad62f76 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
c43a3b0d-5714-598b-88ec-1cad87a5e3a0 | note | Conformance Criteria - IFC Label on drawings
773b7ad9-9f65-518f-8206-5d121fc83281 | note | Records - Check Drawing Register
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Survey Setout
24f3b716-9e2e-51f3-8fb5-7f2b10835fc8 | note | ACTION (Hold, Monitor, Witness) - W
543ca950-9978-5c9b-8b86-e764721c7a2a | note | Detail - Check constructed Sub base is within level tolerance.
e55b72fa-76db-55fe-968e-cfc5b58f7da4 | note | Frequency - Prior to commencement
2db4586b-b3cf-52a7-85bd-49906e11bb4e | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Survey
3b0d5dfe-4c11-5a62-b4c9-57b90ab9bf0c | note | Records - Survey receipt
| checkpoint | 5 - Survey Setout (2)
470024d7-aef4-59db-bec6-ac2ebdfd1b76 | note | ACTION (Hold, Monitor, Witness) - W
ea15472a-075b-5a98-8f1b-0bf922bca9b1 | note | Detail - Set out Vehicle Crossing transition points and Pedestrian Drop Downs.
0e231dd7-0836-5acd-818b-09b2fd03ecca | note | Frequency - Prior to commencement
83343ddc-8394-55ca-80fb-140448f4c535 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Survey, Measurement and Visual inspection
74cf5508-a82d-553d-b20b-a462202e9f6b | note | Conformance Criteria - Kerbing Specification and Geometrics Drawing
| checkpoint | 6 - Material Compliance
1ff9d53c-edc9-53b8-9f61-47d7f6c01455 | note | ACTION (Hold, Monitor, Witness) - W
4c11ae5d-4df8-5ba5-a91a-8499ab6ae769 | note | Detail - Mortar consist of two parts fine, sharp sand to one part of cement.
2d55d1b9-e7e1-5e62-ae6b-1ea247db145b | note | Frequency - Prior to commencement
95a0e50d-f5e5-5d45-a9fc-730eea20795f | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Delivery Docket
0e625ea0-f299-5ff7-a3ad-39743738ca3f | note | Conformance Criteria - Must be discarded if not used within 30mins of mixing
f93c2616-70e4-5873-ae27-8971b0f4e96a | note | Records - Delivery Dockets
| checkpoint | 6 - Material Compliance (2)
8edc2d4f-d1e2-5b49-8013-96296cc80eb1 | note | ACTION (Hold, Monitor, Witness) - H
7938ed94-2d11-5d33-94e6-82b301b4446c | note | Detail - Precast work shall be 20MPa concrete Concrete haunching to also be 20MPa in accordance with ATCoP
1e1b327a-fcfd-52b3-879a-8a160a751d72 | note | Frequency - Prior to commencement
df65d031-ea48-5c87-b553-2403a17a726b | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Delivery Docket
f158e992-9497-5e0f-8376-dadddcd37f38 | note | Conformance Criteria - Check product & dockets upon arrival onsite
e9acdbf3-4357-5e60-8212-1c6383729f0a | note | • Mix Design is approved prior to any concrete being delivered to site by Design Engineer
24bbbdd9-b5a3-53f6-9b5a-70f5893aa5d5 | note | Records - Delivery Dockets, Mix Design report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Material Compliance (3)
a30d3d51-ea4c-5000-ad5f-a9cc8669e208 | note | ACTION (Hold, Monitor, Witness) - H
2cda4c3a-8988-55ff-96da-d0260a59fb98 | note | Detail - GAP40 and GAP65 - Basecourse
0da70a3d-e22c-5668-abf8-eb54e346f2b6 | note | Frequency - Prior to commencement
6ddccac2-bb47-52f3-ad3c-c20121285de2 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Lab Testing
672dd558-c770-5c67-b68f-772b28d8a963 | note | Conformance Criteria - Grading test only
a8d0b009-c367-59ca-a61b-f352179f9a51 | note | Records - Lab Test Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Subsoils
5429b1fa-fd74-5a7b-a94e-ee9759ff687d | note | ACTION (Hold, Monitor, Witness) - W
50907c94-5c8d-5250-ac9f-22cf9060957f | note | Detail - Preforated filter sleeve Drain Pipe to be placed minimium 375mm below subgrade bedded and covered with F/2 sand
b26269e6-52d4-5417-84cb-649960826460 | note | Frequency - 10m
2f814d6f-97e7-5cc5-b423-7be65c7caeff | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Site Check
2e7578aa-491e-57f7-8b87-b931c01d5a76 | note | Conformance Criteria - As per TDM Technical standards RD0100
f1890775-fd25-5600-bc00-3b3ba552fb24 | note | Records - QA Sheets
| checkpoint | 8 - Precast kerb and channel
f52381ad-21b4-5dfb-a034-1466aff8bead | note | ACTION (Hold, Monitor, Witness) - M
f010f1e9-894b-5f2a-b20e-5827ffb7501e | note | Detail - All chamfer to be 20mm, kerb joints to be 10mm min cement mortared
2ff7112d-2c5e-565b-b556-f1647a0959cf | note | Frequency - Prior installation
9b90d289-ff95-5c0d-8941-3647b0a29103 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection and Measurement
960c9daf-9577-5a39-ae5a-288f302c63cb | note | Conformance Criteria - To ensure the correct kerb types are installed at the correct locations
4a318350-5eff-57b2-8864-309240764431 | note | Records - ATCOP, Photos
| checkpoint | 9 - Kerb and channel foundation
9c86595a-9641-516f-853b-71bb0d610965 | note | ACTION (Hold, Monitor, Witness) - H
497e1097-2414-5409-aac4-d303be38a727 | note | Detail - If Existing Subgrade <3% or CIV<7 (if granular), undercut required and bakcfilled with appropriate material and at depth for Design Engineer to specify.
763db92d-0f5e-54b3-9b16-6f943e57a89f | note | Frequency - 10m
4d326a86-544d-5f7e-bf21-a09443230f65 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Testing
58f8a288-0881-5e81-bd92-6ac95fe95172 | note | Conformance Criteria - Subgrade material >3%or CIV =>7
300c2699-068f-52e2-a62d-97aae737e7a9 | note | Records - QA Sheets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Kerb and channel foundation (2)
18bbf39f-f266-5a09-9d0e-cf147e2d818d | note | ACTION (Hold, Monitor, Witness) - H
5b7c499a-60ba-547b-967c-7a79ba00fce2 | note | Detail - Kerbing must be laid on 300mm min GAP 65 subbase in Road and 100mm GAP 40 on Footpaths.
ccaa38e4-3270-5717-89c7-dc14d8f63ddf | note | • The subbase for the K&C must be Clegg Tested with no CIV<30
b9d19e00-2bd2-5ca7-b839-41cd5485444c | note | • Concrete haunching must be done as per drawings.
ba2ab687-3cd9-5931-b629-3d30a8201c95 | note | Frequency - 10m
165f4544-a129-5ac7-8fea-1d95bfddcf48 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Testing
ced54f99-fb7c-5693-b237-f29bee6daf75 | note | Conformance Criteria - Pavement depth and type under the kerb varies depending on location. CIV for foundations >=30
0f1ecd67-36f1-547f-bd82-438f96fa328f | note | Records - QA Sheets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10 - Kassel Kerbs Foundation
85ad72bc-a6c5-5156-a77b-8c0ae8dad424 | note | ACTION (Hold, Monitor, Witness) - H
0bc5bfd2-57c8-59b7-82ce-384b75261f4b | note | Detail - If the existing Subgrade material <3% CBR or CIV<7 if granular, Undercut 300mm and backfill with Granular GAP 40. Design Engineer to Specify Depth.
0fe94b71-31ba-57e7-8faa-684595c16013 | note | Frequency - 10m
57e88f6a-baa4-5577-a6c7-2699fc4fabc5 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Testing
330679f3-041c-5477-9f2f-a96ac5459b3b | note | Conformance Criteria - Subgrade material =>3%or CIV =>7
a01a92ba-8e79-5e2d-a184-0580a6d8cf8b | note | Records - QA Sheets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10 - Kassel Kerbs Foundation (2)
40de9cc1-8131-56bb-ae3f-353e42f49f31 | note | ACTION (Hold, Monitor, Witness) - H
49b4fa27-30b6-59eb-99a0-dd5f53cf396e | note | Detail - The Kassel Kerbs must be laid on minimum 15 MPa Concrete at correct 200mm thickness on GAP65 subbase CIV >15
c75564a0-97e1-5706-8a3a-8e8b8a77ab8d | note | Frequency - 10m
923a80ae-79a0-5ad6-961f-afa486780dfe | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Test/Site Check
076c5766-a9de-53c5-8e2e-44e17b0802a6 | note | Conformance Criteria - As per Drawing: 2019-AT-017_G502
d4d6b132-c138-56f6-90d0-5561238e8697 | note | Records - QA Sheets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 11 - Island Infill
426a58e9-8059-5b60-8a3d-dbde2c5402f2 | note | ACTION (Hold, Monitor, Witness) - H
ebb79eb8-2522-56c4-9756-4bad5f36889f | note | Detail - If the existing Subgrade material <CBR 3% or CIV <7 (if granular), Increase base thickness by upto 100mm at the discretion of Design Engineer
681179e4-30e9-50ff-a7e8-b7daa5606e4b | note | Frequency - 10m
38995f6e-6b98-5b2c-8326-56761b2d67b6 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Lab/test
5cbe0241-d431-50fe-b297-3e295c567fdf | note | Conformance Criteria - Subgrade material >3% or CIV>= 7
45e82655-c398-567f-b5ed-b71eea3d5b68 | note | Records - QA Sheets, Design Engineer Correspondence
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 11 - Island Infill (2)
467a3505-fd85-5413-b572-f625cc574911 | note | ACTION (Hold, Monitor, Witness) - H
c5dc3c5a-0525-56ee-b902-3727c7508df9 | note | Detail - The sub-base must be GAP40 and must be clegg tested at every 10m intervals
f92ed24e-c8a9-58d5-ae5e-f081c0902dcf | note | Frequency - 10m
ab59ee90-fff3-59fb-8026-bf201f9570e1 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Lab/test
73100581-ae30-5156-b6c8-1f25c6d2b01b | note | Conformance Criteria - CIV >=30
824d6a4c-0e6b-5d66-9463-7257c696c6ea | note | Records - QA Sheets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 11 - Island Infill (3)
62db5c81-9996-5c9b-99d0-b46060af6cfb | note | ACTION (Hold, Monitor, Witness) - W
a9c215b0-91b0-5832-8792-8b3d28cea0f2 | note | Detail - Concrete must be minimum of 20 Mpa and must be of correct 150mm thickness
8d1173cd-dd8b-5c22-b78e-9a7d66d537b4 | note | Frequency - During Pour
179ab947-3fc1-5bdc-8913-1a4f83d51882 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
b36a66a8-ab6f-52ff-a3a9-7ce765946318 | note | Conformance Criteria - Exposed finish compliant with NZS3104 and constructed accordance with NZS3109
97deed65-4182-5902-a720-74b58bb29f87 | note | Records - Visual inspection
| checkpoint | 12 - Stringing for All Kerb Type
fa710601-7287-5970-b765-7e283b3e0853 | note | ACTION (Hold, Monitor, Witness) - H
39a57d63-d6ae-5d52-88be-baa6204cde27 | note | Detail - Kerbs laid out accurately to lines, gradients & levels shown in drawings.
87d7d37c-2a43-56ab-aeca-1da58ce18499 | note | Frequency - Prior to commencement
7485dbc5-af77-5712-ae5c-5ef3276b99c2 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection and Measurement
3f12473c-fb2c-5fa6-9206-ae1ae9121df5 | note | Conformance Criteria - Prior to laying, string lines or levels to be inspected by Engineers Rep.
2d2c1f04-c632-5bcc-be92-78213ca6c0aa | note | • When a 3 m straight edge is laid parallel to any surface of a pre-cast or bluestone kerb and channel there shall be no more than 5 mm variation from the straight edge, except at change of grades or curves
1753412d-7716-5970-a708-a438eed7020b | note | Records - ATCOP
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 13 - Dish Channels
02a01078-3c1a-5c28-983f-5908fa9d5f53 | note | ACTION (Hold, Monitor, Witness) - M
f5721ed0-e8b1-5033-b146-2d867b810374 | note | Detail - Contraction joints at a maximum of 3m intervals.
30373b0f-aa34-5ce6-8eff-cd885f94dbf9 | note | Frequency - During Slip forming
364292d5-8b05-59e8-8a60-11eb83c8314c | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection and Measurement
7c34bf72-ce13-5e42-8db9-3268ca411271 | note | Conformance Criteria - Kerbing Specification
c454c670-54cf-58f3-ab90-965200c952bf | note | Records - ATCOP
| checkpoint | 13 - Dish Channels (2)
c94e55af-9e36-5e3f-a380-1084eafe77c5 | note | ACTION (Hold, Monitor, Witness) - M
4dd589fe-f004-558f-b4af-cdf410bd4128 | note | Detail - Top surface to channels to be finished smooth and even with a trowel.
a333c96c-1e4d-5f92-bfdc-69aab1be89cc | note | Frequency - Prior to commencement
21415441-0a16-5a01-97ef-512e8e681c10 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
5ab04c66-6d4f-5773-b275-23d9fdd5e1ec | note | Conformance Criteria - Shall not pond any water.
8e5f92cf-1b58-5675-b72f-61ab749cbedb | note | Records - ATCOP
| checkpoint | 14 - Tie-in with pre-cast components
6371b36d-2417-5010-aa69-8c878303836c | note | ACTION (Hold, Monitor, Witness) - M
012374f6-af52-56ea-97b7-25f4a9f83636 | note | Detail - Ensure Kerb & channel to be cut and tied-in with pre-cast components by forming concrete aprons
4afddd3c-d717-55c3-8343-2ffa8eec494f | note | Frequency - During works
7e547f7b-6a55-529f-8e15-fd8066f33ac1 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
ea8bb5ed-ab6e-59be-bb8b-db0f82b95366 | note | Conformance Criteria - Consistency with Work Instruction
c46d5f47-eb74-55ff-a719-ffa0a84311ea | note | Records - ATCOP
| checkpoint | 14 - Tie-in with pre-cast components (2)
87143d53-5912-5dda-859b-4e8a8bf0894f | note | ACTION (Hold, Monitor, Witness) - M
d6901b3b-96d1-5716-b76d-72e69e247a74 | note | Detail - Channel joint material set flush with surfaces (ensure levels are within the tolerances).
8adcaa00-d509-586f-877f-db0d9ffa4819 | note | Frequency - During works
b82bde5a-3599-5a3a-81d5-727ae1afeceb | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
59125c42-5ba3-54d1-aa22-3071a4885971 | note | Conformance Criteria - Consistency with Channel Specifications
5f3923c6-5dd1-551c-9596-009e8bbb384b | note | Records - ATCOP
| checkpoint | 14 - Tie-in with pre-cast components (3)
1584af3a-9c54-558b-a527-a71da10adab5 | note | ACTION (Hold, Monitor, Witness) - M
257323de-9243-5fcf-a695-ac2cef17ffd7 | note | Detail - Catchpit frame, grating and back entry kerb installed at correct level
c0ebef10-5ccf-52c5-a069-a79db7a295f0 | note | Frequency - During Works
c08c2aaf-8dd9-5674-b3f7-0f7669d7f2bb | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document review visual inspection
75481d24-0b58-5a0a-9cfa-2dbc2ff547a9 | note | Conformance Criteria - Document review visual inspection
e373fe52-689b-5962-9805-1fec45543b2d | note | Records - ATCOP
| checkpoint | 15 - As-builts
ef8220e9-e076-5d37-8d46-f60350c45fba | note | ACTION (Hold, Monitor, Witness) - H
35f16065-570e-5a42-a95f-f3d6f4689673 | note | Detail - Red pen mark up drawings to be included in QA file
ce72d318-ab97-5067-b3d9-ed69c36aae1d | note | Frequency - At the completion of the Lot of work
127c3beb-3dcd-5246-8093-2a0d791c396d | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Drawings
34a77d37-b828-5508-a646-f94567190ec4 | note | Records - Asbuilt Drawing
| signoff | AUTHORITY HOLDPOINT
| checklist | Ponsonby - ITP - Road Pavement |  | Road Pavement | 4b125756-4eca-4bf5-b9df-7aab35427020
| checkpoint | 1 - Permits
650cb897-55e5-5744-ab2c-f95d3b8e85f6 | note | ACTION (Hold, Monitor, Witness) - W
d2fee65f-75f6-5fa2-b8b2-f8dcc508fdd3 | note | Detail - Obtain Permits
4d001545-e484-5543-ba38-8293ad2325b5 | note | Frequency - As required
2d06e13f-a177-5b70-94f5-0ab45aa7cead | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
be154133-028d-5a5b-8324-05e2af5a4e88 | note | Conformance Criteria - Control Checklist - Digging / Excavating (incl. marking out & potholing existing services).
092e0334-afa1-561e-a2f5-49b9016181de | note | • Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
cd1e8d5f-1332-5cf8-9eca-809f98ec4c7a | note | Records - Permit number noted
| checkpoint | 2 - Traffic Management
fd97452c-476c-579b-9352-a69cd1366501 | note | ACTION (Hold, Monitor, Witness) - W
f30925ac-1941-55b6-a1c6-5f722939121b | note | Detail - Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
1bebb46e-2998-5ed1-a5d4-67518d0c63e7 | note | Frequency - Prior to commencement
89f73add-3d40-59a1-b8a3-9bca5b73a148 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
b14294ad-884f-5db8-a4fa-bdce7898388f | note | Conformance Criteria - TMP is approved by AT for the site and works are only completed within the approved dates
ecd235c3-756d-5580-9015-fb655736521a | note | Records - TMP on MyWorksites/OnSite
| checkpoint | 3 - Pre-construction sign offs
f5506347-dd97-5a61-8a22-416c99a399e9 | note | ACTION (Hold, Monitor, Witness) - W
710eb364-3d46-5b39-bc0c-68fd955431f8 | note | Detail - Ensure that Sub-Contract and Supplier Agreements are signed, all Sub-Contractors and Suppliers are inducted to site
bc220d1e-ec4f-514a-b30a-16a79decbb1d | note | Frequency - Prior to commencement
6fee3de2-4e96-57bd-aade-3df6d9fa3cd0 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
aa1cd132-dfec-5696-b665-1e71d01d2b23 | note | Conformance Criteria - Signed Subcontract and Supplier Agreements on M-Files and Induction Register updated
71e8aa6f-272b-554d-ae4a-15a2b2884a4a | note | Records - Subcontract and Supplier Agreements, A & Updated Induction Register
| checkpoint | 4 - Design
e313c924-7ea7-534d-a83c-d7c3c2e73961 | note | ACTION (Hold, Monitor, Witness) - H
545f88ea-5c10-5785-a434-de95c1dace26 | note | Detail - Ensure that Design is approved and Drawings are of the latest revision
9b2d3b0e-f961-57cb-a88a-6fb8285e2539 | note | Frequency - Prior to commencement
d8c06c6f-27ff-5722-a606-2f288b0d7ac4 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
9ea6d8f7-7c20-50db-a3dc-78c45368209c | note | Conformance Criteria - IFC Label on drawings
d098c525-cf39-5777-9026-831d297dc82b | note | Records - Check Drawing Register
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Subgrade
6f75d136-4e2b-534c-914b-ef1c2ddf6175 | note | ACTION (Hold, Monitor, Witness) - H
93341fe2-2662-51ac-adcf-ab976cf9b5f3 | note | Detail - Subgrade Scala Penetrometer Testing (CBR) at 10m intervals in each traffic lane-staggered and /or stitch section - unless directed otherwise by engineer
8185976c-2e70-572a-8087-4135756eae64 | note | Frequency - 10m
9530531f-158d-5280-b7ae-eb8ff57dbe66 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Testing
9080c388-0534-5b7e-b2b5-ef59878d79f1 | note | Conformance Criteria - Accepted by or subgrade improvement instruction received from AT representative/Engineer
20e64fdb-67cd-5f99-8b7f-51dd05f860ae | note | Records - Testing records/ QA sheets if applicable
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Subgrade (2)
5db491f9-67bc-527c-88c6-8078582275e8 | note | ACTION (Hold, Monitor, Witness) - W
7d01d9ac-9d37-5ab7-bd55-02b5fb3c14b8 | note | Detail - Subgrade undercutting/improvement inpsection
4d851e2f-83b5-58a6-b325-40f34e0f56d7 | note | Frequency - Prior to commencement
0af71473-ff2e-52f7-996b-fc0caa8c7ace | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
952a6033-df89-5945-842c-9ed0f7409914 | note | Conformance Criteria - Accepted by or subgrade improvement instruction received from AT representative/Engineer
4f87ba6d-2ae7-5938-900d-18a1cca61768 | note | Records - Testing records/ QA sheets if applicable
| checkpoint | 5 - Subgrade (3)
bd8dea97-7c5c-542b-bc9b-5ef39de861d6 | note | ACTION (Hold, Monitor, Witness) - M
65568008-a85b-577b-89e9-cd2967d89e89 | note | Detail - Subgrade surfacing stringing
eebb6f52-6662-56a7-854a-79cd00185dd3 | note | Frequency - 1 in 10m
a8b01238-6d24-5bb6-a4fd-feec630336a7 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Measurement
f7341e31-288a-59c4-b035-76185ee12d08 | note | Conformance Criteria - Straight edge: ±30mm/3m
2ae9c82b-bf30-58ed-b84c-76da29b82c27 | note | Records - QA sheets
| checkpoint | 6 - Subbase-GAP65
264f38dd-db2f-5076-b4b1-60860cf480d6 | note | ACTION (Hold, Monitor, Witness) - M
1dc359b6-deb8-5648-bec5-73f8160b7fdd | note | Detail - Material source testing approved
1f726534-305e-516d-ac56-a46cb7a2903d | note | Frequency - Prior to commencement
18d72302-944d-59f3-bf55-feb37d652762 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Submission and review
b2da41a8-65b7-5889-ae1b-e8e005a9a530 | note | Conformance Criteria - Meets specified criteria and lab test report is recent within 6 months
6b02ecec-0df9-5611-b7c4-f6c6ad002c83 | note | Records - Lab Test Report
| checkpoint | 6 - Subbase-GAP65 (2)
c48ff0ac-464b-5542-9e5b-c704d95018b6 | note | ACTION (Hold, Monitor, Witness) - M
7f56ca0f-64a9-57e8-9e45-e76843382536 | note | Detail - Material delivery
fb7aa4bd-231e-5fdf-b3f6-8a455d333dba | note | Frequency - Prior to commencement
62184562-ffa4-5a36-aa47-d0b8c7615f5a | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
75611aed-e55a-556b-89ce-ec48dbde9d57 | note | Conformance Criteria - Check for quality of material
7744a49c-2dfe-5a1b-91b6-40be56fa01bb | note | Records - Visual inspection
| checkpoint | 6 - Subbase-GAP65 (3)
f7ef6801-17c0-58e8-aa58-1f8640c8737e | note | ACTION (Hold, Monitor, Witness) - H
4d4d3477-664c-5a18-b878-9f7603606fac | note | Detail - Surface shape-stringing line check
8b2f71fa-32f6-5cfd-97f0-9fa3f4a92ae9 | note | Frequency - 1 in 10m
58147e05-cf63-550b-b82c-22d1bb3dfc41 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Measurement
986b25dd-27d0-545d-8a72-53be8da10c79 | note | Conformance Criteria - Within tolerances, ±20mm
d05cf65a-4c36-543c-a9ad-8d9cd7341aee | note | • Crossfall no depart from exisitng crossfall or instruction from AT represenative/engineer
3b3965c6-2332-504f-8f9c-408cbbd443d9 | note | Records - QA sheets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Subbase-GAP65 (4)
bbff3bf3-0a13-57ad-88a2-989063b00544 | note | ACTION (Hold, Monitor, Witness) - H
544cb04f-395c-58b4-9bbc-71eb7041956a | note | Detail - Compaction-NDM tests
3cb76d59-408f-5515-bd3b-004dfabd6a27 | note | Frequency - 1 test per 30m of road per lane, staggered at 15m
f94adfc1-6b32-5fc5-966e-438c0ee2ad84 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Review
d9a970e4-0743-5cec-b780-8aaaa4df168a | note | Conformance Criteria - Mean >=95% of MDD
11c3225b-cab7-5a3f-a71b-1e1e5acaad42 | note | • Minimum>=92% of MDD
7f4a0e02-c70c-5f60-945b-ebcbd86d5d33 | note | Records - Testing records/
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Subbase-GAP65 (5)
a7371b43-1cd3-5660-871d-de3006091406 | note | ACTION (Hold, Monitor, Witness) - H
10226c7b-fe0f-5c8f-a1fe-b550a5b79679 | note | Detail - Benkelman Beam Deflection Test
278c3961-121a-5a92-a654-71d1aac8cfcb | note | Frequency - at 10m intervals in each traffic lane-staggered
e6532d5f-146f-5dc8-9283-88aa872e61ad | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Review
6f668a25-ebc6-5aaa-8082-88d32b38fbd9 | note | Conformance Criteria - <=1mm (or specified by AT representative/engineer)
013fef3b-15b7-50db-b12c-23002d3b4dfd | note | • Not applicable to stitch section
d0515114-0583-5a17-8f74-e3a8cd5beff7 | note | Records - Testing records/
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Basecourse-NZTA M/4 AP40
5b7e6249-28db-5369-a919-60b47724c437 | note | ACTION (Hold, Monitor, Witness) - M
ead9b31a-feaf-5328-9f16-7802e3d7971d | note | Detail - All chamfer to be 20mm, kerb joints to be 10mm min cement mortared
57272d77-7cd0-5fb6-9257-d10b94020561 | note | Frequency - Prior installation
c5557798-a4be-5905-8f11-837f44889cd1 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection and Measurement
7f95a97e-eebf-5c61-98c3-2928371972be | note | Conformance Criteria - To ensure the correct kerb types are installed at the correct locations
cce1e4de-6e72-5f88-a589-5ebd46a1825d | note | Records - ATCOP, Photos
| checkpoint | 7 - Basecourse-NZTA M/4 AP40 (2)
98830768-85f4-5f88-a82c-af97e1e13040 | note | ACTION (Hold, Monitor, Witness) - M
f7dc2b2e-021b-549b-9084-8e9eeaf494c4 | note | Detail - Material source testing approved
30747b26-8ef2-51de-97fe-337ab0f30599 | note | Frequency - Prior to commencement
a927b3b1-d111-5b5e-8f90-d4f8896d9e4b | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Submission and review
749c38ff-3d35-5340-93cf-9f0adadafd2b | note | Conformance Criteria - 1/ source and at least 1/6 months
39fa9d32-f613-58b1-a18f-7a8dc7b7a49f | note | Records - Lab Test Report
| checkpoint | 7 - Basecourse-NZTA M/4 AP40 (3)
7f618ef9-5e4b-5d9c-8b9a-9e90290fbeec | note | ACTION (Hold, Monitor, Witness) - M
53a5e55e-a29e-56ec-a8e2-7aa9a2dfd90a | note | Detail - Material delivery
6d4e866b-f2a8-5638-a9b3-52fcd321e30e | note | Frequency - Prior to commencement
99c88d04-f9be-5a7a-ad6d-9a79bfe789b6 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual inspection
d8813ca7-2614-588b-9d47-d512c2c8b035 | note | Conformance Criteria - Check for quality of material
f8caa4f6-6317-577f-a6db-2fbe1d734b83 | note | Records - Visual inspection
| checkpoint | 7 - Basecourse-NZTA M/4 AP40 (4)
c7f54511-18cc-5e42-b490-c640ad6fbecd | note | ACTION (Hold, Monitor, Witness) - H
6ea58cba-2cf1-529e-b76a-2ae26d81faff | note | Detail - Surface shape-stringing line check
12cb7e7f-f280-5013-9d15-82b910162b2a | note | Frequency - 1 in 10m
227df80f-fbe1-5fab-beee-7c0b67440a0c | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Measurement
66b53d96-2d7e-57ef-8fec-c4918152a999 | note | Conformance Criteria - Within tolerances, ±5mm
5d036741-4146-54a7-b660-5b9faa9e8149 | note | • Crossfall no depart from exisitng crossfall
e140ff16-6ead-5c35-b021-e67186bd0820 | note | Records - QA sheets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Basecourse-NZTA M/4 AP40 (5)
aad2e241-03b8-5642-9e16-1064cb89852b | note | ACTION (Hold, Monitor, Witness) - H
8fd9c2c4-a8cb-5c8d-a746-89621cc1c556 | note | Detail - Compaction-NDM tests
8c7fff9c-b8da-599e-8b23-adf66cfca0ff | note | Frequency - 1 test per 30m of road per lane, staggered at 15m
898be89c-7135-5e06-ae97-bb076251202d | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Review
209827e9-4c8f-525b-b0e0-2aea11048302 | note | Conformance Criteria - Mean >=98% of MDD
5d16cac5-529d-51ec-a21c-510471ed5202 | note | • Minimum>=95% of MDD
af5a1873-7014-55b4-be1f-539a33b6949e | note | Records - Testing records/
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Basecourse-NZTA M/4 AP40 (6)
5829199f-a0d7-5b61-8000-4fbcdda0fca1 | note | ACTION (Hold, Monitor, Witness) - H
ebe0dcd8-7bcc-58d7-973e-9b3cdbf0029a | note | Detail - Benkelman Beam Deflection Test
633514ab-1aaa-59a7-8256-9ab181cf6a90 | note | Frequency - at 10m intervals in each traffic lane-staggered
f11e1987-6fad-573c-af49-6230edaed7cb | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Review
d7a6d398-6814-5bb3-8979-97396726ba70 | note | Conformance Criteria - <=1mm (or specified by AT representative/engineer)
818b12a4-f50c-529c-82e8-e98b33cfe897 | note | • Not applicable to stitch section
60b60507-ab94-5802-9ea7-63c18078fa4d | note | Records - Testing records/
| signoff | AUTHORITY HOLDPOINT
| checklist | Ponsonby - ITP - Stormwater Drainage |  | Stormwater Drainage | af8a69a2-59b8-4331-8fb0-ff09ead039ac
| checkpoint | 1 - Permits
726ed22a-0265-5046-acfc-949718f2dc70 | note | ACTION (Hold, Monitor, Witness) - W
28575627-8e6c-554a-a62d-40d83fb15cec | note | Detail - Obtain Permits
02841cfc-e126-569a-b643-ef59fec31734 | note | Frequency - As required
0d187424-db09-5ece-980e-f51da078396e | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
35523236-36c1-5178-900a-1c5b7ae740aa | note | Conformance Criteria - Control Checklist - Digging / Excavating (incl. marking out & potholing existing services). Notify Worksafe NZ if required.
d9f61189-f6de-5384-ab9b-245329c84f29 | note | • Ensure all necessary Permit to Works & Controlled Checklists are in place
ece9c29c-c98a-595b-93d5-c694234de7ae | note | Records - Permit attached or permit number noted
| checkpoint | 2 - Traffic Management
c9682f06-c5f7-5b21-959a-3543e2f5f7ed | note | ACTION (Hold, Monitor, Witness) - W
81f35a0f-50a4-5a79-ba37-d09ba1d9b423 | note | Detail - Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
1810fb46-0df8-5070-afe9-ffdfd49a5057 | note | Frequency - Prior to commencement
b4eff5fb-55fa-5b34-bf6c-6f898a7e12c2 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
b7c1d525-26d2-54b2-b490-7f149f3494e3 | note | Conformance Criteria - TMP is approved by AT for the site and works are completed within the approved dates
3237be67-4881-56c6-9d91-02e3232f58b9 | note | Records - TMP on MyWorksites/ On Site
| checkpoint | 3 - Pre-construction sign offs
3860a3bf-88d5-5aeb-8d0e-dfdb735a954a | note | ACTION (Hold, Monitor, Witness) - W
4af12cb4-505b-54f3-ab85-e829fa100b2c | note | Detail - Ensure that Sub-Contract and Supplier Agreements are signed and that personnel have gone through the NWBI induction.
fd18da35-4bad-5f54-9f66-1d0f43ccb002 | note | Frequency - Prior to commencement
f28a843e-897c-5c69-9b4a-705bba0ac9e7 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
0f7c5f82-e8b6-580c-a388-b780accd8b05 | note | Conformance Criteria - Signed subcontract & Supplier agreements. Issued induction stickers and number
484f7217-8448-5fbd-9f52-08d0dd7aeaed | note | Records - Signed Agreements, Updated Induction Register
| checkpoint | 4 - Design
7ff3cc8b-6b24-5884-bece-c50e78b98859 | note | ACTION (Hold, Monitor, Witness) - H
a9992d1e-0d8a-5e12-acf4-ca8d1d77fe3a | note | Detail - Ensure that Design is approved and Drawings are of the latest revision
c7a9f118-18b4-52f3-9b79-17fa8bc2e786 | note | Frequency - Prior to commencement
967b3415-8c9a-5841-a521-54ed76654166 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
bffdf83c-e20f-54d9-9d91-68503f957094 | note | Conformance Criteria - IFC label on drawings
bc8462d7-9a0f-583f-814c-cf075538f770 | note | Records - Check Drawing Register
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Survey Setout
1c35d076-2b1a-5dc6-80ff-3da6adb04492 | note | ACTION (Hold, Monitor, Witness) - M
3633c25f-6285-5e4c-be08-f6807485f658 | note | Detail - Set out pegs installed every 10m of the footpath showing the FL.
2204aceb-edde-527f-b739-ff54ffc83f51 | note | Frequency - Prior to commencement
e055f37a-fe9b-58ec-b735-23039e6dfa0c | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Survey
b5c4e1c0-1dc4-5157-ad5b-f6decc3f85ef | note | Records - Visual Inspection
| checkpoint | 6 - Material Compliance
785d41be-f89f-53ae-8519-0a53e9567a20 | note | ACTION (Hold, Monitor, Witness) - H
480c9ccb-c11b-5e5e-ba54-5fea0f317aef | note | Detail - Bedding, Haunching and Backfill Material
ca09e1f1-ba23-5b53-b5a7-df8f796e6c7d | note | Frequency - Prior to commencement
6d08d101-05eb-515f-abf7-9c2500906429 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - AS/NZS 3725, AS/NZS 3500.3
0a46ddc1-e147-5a31-8c94-08a28b97da90 | note | Conformance Criteria - Crushing Resistance not less than 100kN. Maximum percentage of weight passing 0.075mm sieve shall not exceed 10%
118331d8-8a9a-5b88-a371-3e48473c7740 | note | Records - Test report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Pipes and Precast Units
d33772ff-6482-5f3f-9aa0-a85da90b98e8 | note | ACTION (Hold, Monitor, Witness) - M
bc6c4942-3cc1-522e-88f8-0e80786f2aaa | note | Detail - Confirm pipes diameter, class & jointing type as shown on the drawings, and that the pipes are correct and in good condition.
277f9d4f-a939-5f6e-9b11-d2bdebaeceec | note | Frequency - Delivery to site
c498f391-f90e-52ec-9da3-c079c0934b5f | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
46c4c061-1c9f-5b5e-9344-d270bb25c52f | note | Conformance Criteria - Pipe - Diameter & Class, Manholes, Catchpits as per SW CoP and AS/NZS 3725
85abe99f-eac1-5913-ba08-e0a185211b60 | note | Records - Delivery Dockets
| checkpoint | 8 - Trenching and Excavation
e186bfed-7927-5494-bfc6-de5087b3bc42 | note | ACTION (Hold, Monitor, Witness) - M
53c84240-4c6e-574b-97f6-61d7127e1614 | note | Detail - Inspect trench profile and ensure it is correct to lines and levels to design
c60527c7-b371-5e08-8545-5b3b6bf24422 | note | Frequency - Daily
648f4d4c-ef61-5fcb-9742-15ceef6daf7d | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual/Inspection
306d0647-fb43-569a-86af-db604d065b59 | note | Conformance Criteria - Line and level is correct
f070f8e5-2b83-59dd-9ced-e5c16331861c | note | Records - Checksheet
| checkpoint | 8 - Trenching and Excavation (2)
0aed77cd-19f1-5c71-87d0-2fffbc6ea6c4 | note | ACTION (Hold, Monitor, Witness) - M
e15bbb78-d7e0-5b81-81e1-ae2c51f19868 | note | Detail - Ensure trench width is sufficient as per AS/NZS 3725 namely 3x Diameter of Pipe
c1fa2a7a-e7df-51a8-ba72-063c43868dba | note | Frequency - Daily
eaa71966-ed55-56bf-8e8f-ddf95c81d2fc | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
86e64940-ec15-5e83-b566-d7e30bb03664 | note | Conformance Criteria - As per AS/NZS 3725
79d64fcb-2506-53ee-bdf0-a8caf5589984 | note | Records - Checksheet
| checkpoint | 9 - Foundation Compliance
99d880ae-db55-5f50-abe4-0785a6a48d56 | note | ACTION (Hold, Monitor, Witness) - H
c5ed77ae-f337-5fc0-9feb-c7c45702e880 | note | Detail - As per specification, Shear Vane <50 KPa 2%<CBR<3% Undercut 150mm, CBR<2% Seek Design Engineer's advice
ae198050-27be-5760-91ff-33727c2d58e5 | note | Frequency - 1 Test every 20m
e1a9ee19-9932-54d9-8973-16021fb8bea3 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Testing
21798ea5-ac50-57ce-9250-19b72d2da5a3 | note | Conformance Criteria - Shear Vane >50 Kpa, CBR > 3%
3df92bd4-befa-5301-8f4e-f3f36977f874 | note | Records - QA Sheets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10 - Undercut Backfill Material Compliance Testing
1c61b839-eda5-5c98-bb1e-3c45ef4958f8 | note | ACTION (Hold, Monitor, Witness) - H
752a161e-5374-53d4-8cda-8ab6c4f5aa4b | note | Detail - Undercut If subgrade fails testing requirements and replace with copmpacted GAP40 for depth of undercut
57e1f221-aaf7-50e8-b8c6-91147583d1fd | note | Frequency - 1 Test every 20m
240b3e64-2ae7-5320-81d4-6b665a23370a | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Testing
6aec1e21-9e6f-50b4-a789-fcc85d9a7759 | note | Conformance Criteria - CIV> 15
ae9f617f-4e73-50ee-a5ed-c86483ba55b0 | note | Records - QA Sheets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 11 - Pipe and Structure Bedding
da803391-8d18-5abe-8063-c133c0c0982a | note | ACTION (Hold, Monitor, Witness) - H
3bc39311-0a0d-58b3-b956-4567c9db2dbb | note | Detail - Specified Bedding Construction Material
6736174f-e90d-5bc6-b30e-d96171833c2a | note | • Pipe Diameter<300mm bedding, side and haunch zones to be 100mm
944d0532-ae38-5b8d-b049-5448515614ba | note | • Pipe Diameter >300mm bedding, side and Haunch zones to be 150mm
58817efa-5763-51c5-af59-3c33a850366a | note | • Stucture Bedding to comprise of a 75-100mm levelling course GAP20
6b0f43b8-f901-5e7b-b39b-caa56df657eb | note | Frequency - 1 Test every 20m
d43c5ac7-000d-5944-8f86-763ab59a4ef4 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Testing
a306334b-9a84-5bb6-96d2-4b5200438ba9 | note | Conformance Criteria - As per AS/NZS 3725 Minimum Bedding, Side and Haunch Zone CIV > 15
c5646731-c832-58b3-8021-27a777a1bf3b | note | Records - Checksheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 12 - Structure and Pipe Backfill
302740f7-b5de-504f-8190-0eb09d9dd0f2 | note | ACTION (Hold, Monitor, Witness) - H
469742c0-7288-5e6c-8471-bc3ee95b6aab | note | Detail - Backfill zone compacted in GAP40 layers no greater than 200mm .
b5505faa-d93a-5727-ba2c-af4f2bb43775 | note | Frequency - Test Per Structure
58accbe1-f6f9-53ce-9c69-d5e1108eb466 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
11868c7b-0db6-590f-8917-29b724ed1390 | note | Conformance Criteria - Compliance with requirements from Specifications and SW CoP.
54be1ad9-de52-5651-a93b-0b8c3a9dd6dd | note | ○ Under Carraigeway
1b36226a-82cc-5980-bcdc-9d974a766ac5 | note | • CIV >=32
a816191a-acf8-5286-b50b-b4758b7543c3 | note | ○ Under Footpath and Berm
b9f30c3e-a2f2-5a8a-a121-974bcc2ea2af | note | • CIV >=25
7c4f2eaf-16f3-5982-80ca-0c4d5d9053ad | note | Records - Checksheet
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 13 - Pipe Laying
58ba8f54-d8cf-568f-b168-9a7c785b7252 | note | ACTION (Hold, Monitor, Witness) - M
438fa695-f0dc-5494-a78d-44992e8b9570 | note | Detail - Inspect pipes prior to backfilling to ensure they have been installed correctly and the joints are in place and sealed.
efc0fa92-c20a-55a7-b384-bb6f70cdd23c | note | • Ensure Pipes do not exceed ±25 mm from design levels for any five metres of pipe
868b2ba5-5193-5532-8e60-9bb5843408e2 | note | Frequency - Prior to backfilling
509d6285-e8e0-597c-81f9-e0b754884c6c | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual/Inspection
1be76ef1-bb2f-5b26-b280-0485379c6fcd | note | Conformance Criteria - No defects/ gaps / pipes are aligned correctly. Compliance with the Stormwater Contract specification
1e88b06a-af70-59c0-8ad6-77a5caf697f9 | note | Records - Photos, Checksheet
| checkpoint | 13 - Pipe Laying (2)
61a37e10-47f8-5b61-9c86-dd0e5109dd54 | note | ACTION (Hold, Monitor, Witness) - M
36f28837-0dc9-5f71-9b3e-39851e599527 | note | Detail - As-built survey of pipes installed
dd82a445-5300-5c62-a106-a125634904a8 | note | Frequency - Once line is completed between 2 structures
b2dc19e7-0340-55a0-b423-fb669c69bb80 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Survey
d1f11e1b-54f1-51d9-8572-87a8435ec49f | note | Conformance Criteria - Survey Receipts
34fc100a-fcf5-5082-87c7-93cc431bd984 | note | Records - Checksheet
| checkpoint | 14 - Trench Overlay Zone
64a84133-95fa-5dd8-85fd-8f881940b57a | note | ACTION (Hold, Monitor, Witness) - M
d4d6ebd1-d558-536b-96c0-84898eda3191 | note | Detail - Ensure correct thickness of compacted overlay zone - 150mm overlay above top of pipe for Pipe Diameter between 300 and 1500mm
0075abd9-7e43-5c51-8e3e-1ecda5b0ce0a | note | Frequency - During Backflling
d5d5b995-0d15-540d-8014-f3ecc087b4b1 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
c434e2af-9399-544b-8455-caa5bc1fefd2 | note | Conformance Criteria - Compliance with the drawings . 150mm overlay above top of pipe. Refer to AS/NZS 3725
a77b9ef5-f635-59bb-b9b8-9f59bc835286 | note | Records - Checksheet
| checkpoint | 15 - Pipe Backfill Compliance
290a7d41-3a4c-5819-aabc-d8245296a839 | note | ACTION (Hold, Monitor, Witness) - M
da9d896b-e311-5c25-b99e-1e4b16ac5c1d | note | Detail - Backfill zone compacted in GAP40 layers no greater than 200mm . Requirements based on pipe location. Minimum cover 1200mm from top of pipe in carraigeway and 800mm in berm. If Cover cannot be achieveded seek advice from design engineer
67a1916f-01bb-54a0-860f-f1004fec7cd5 | note | Frequency - 1 Test every 20m
b0c27732-233c-5223-9b8d-7eceb0241279 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review & Testing
dc6fa5cb-7354-5c77-a198-1659b5eebeb3 | note | Conformance Criteria - Compliance with requirements from Specifications and SW CoP.
3cda05d3-e554-52ed-b106-b4aec41640dd | note | ○ Under Carraigeway
f91dc94a-6d37-5246-a629-c287a6131054 | note | • >=95% Compaction and CIV >=32
1601107c-9a65-5b30-be7f-50b80864b38a | note | ○ Under Footpath and Berm
7eeb8c22-973d-5f17-997d-16c6fc80ffb8 | note | • >=85% Compaction and CIV >=25
bc13c6e9-90d7-5ef3-a964-f79eb7a83495 | note | Records - Checksheet, Lab Report, QA Sheets
| checkpoint | 16 - Structure installation (Manhole, Catchpit)
a4526281-5ddf-5fb4-a0b3-6f5f58edaf9c | note | ACTION (Hold, Monitor, Witness) - W
35715d0f-186f-55b5-8c25-d7cb7ea1727c | note | Detail - Galvanised Step irons required in chambers over 1500mm deep
f5598ee4-9636-5781-bef9-490a249fa801 | note | Frequency - As required
fd74dadf-09e3-5c19-a7ee-183c5c912f6a | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual/Inspection
39a8aa61-9e3a-5957-a843-6bfdc3f5c755 | note | Conformance Criteria - Maximum 600mm from manhole frame to first rung. Maximum 300mm between rungs. As Per ATCoP
0552e1cc-8b49-5612-ad71-ba89e943acc4 | note | Records - Photos
| checkpoint | 16 - Structure installation (Manhole, Catchpit) (2)
292beeaa-763e-50e7-a31d-23ea0e6c8f92 | note | ACTION (Hold, Monitor, Witness) - W
4a678761-9448-592a-a82c-fcb374885abd | note | Detail - Structures to be installed to the design survey location and level
b9947eb6-3e46-505a-8bf6-233b80a684f2 | note | Frequency - During structure construction
e8e072f2-802f-55a6-a2f1-f46c5984d3b5 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual/Inspection
13ee374d-dc8d-5a5b-a3c7-2c45e95e3f22 | note | Conformance Criteria - Survey markouts for centre of structure and insatllment to be from centre of structure
dda8b98a-0f42-5ff5-958e-9801e7b5b6b1 | note | Records - Checksheet
| checkpoint | 16 - Structure installation (Manhole, Catchpit) (3)
c9ca57a4-4dd9-5edd-bb24-941a2df5b6ae | note | ACTION (Hold, Monitor, Witness) - W
8164eb88-d49f-591c-b79e-4c398800de08 | note | Detail - All joints are to be sealed including rungs and lids
cb414c0c-ed0a-5ad9-9601-09263b51faff | note | Frequency - During structure construction
d8c266a5-c406-58a2-ab98-2400d918c16b | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual/Inspection
3fc30eca-cb3b-5c37-b82f-382f91bec6cb | note | Conformance Criteria - 25 MPa concrete to be used for throat haunching and cradle around inlets an outlets
5b139abf-2550-542e-916c-cd8adc122b5d | note | Records - Photos
| checkpoint | 16 - Structure installation (Manhole, Catchpit) (4)
5a7f6bdd-68c2-573c-9227-00c3f14a4c29 | note | ACTION (Hold, Monitor, Witness) - W
a139d73a-748d-5fb8-ac3f-3d7662f1276c | note | Detail - Adjustment rings to ensure correct level and fall to cover
ebd23ceb-02c4-5933-9258-6b10103b9ca1 | note | Frequency - During structure construction
0e4e3bc2-9605-5a68-93d0-b7c1ab0956b1 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual/Inspection
d91ac48a-4a01-57d3-aed5-722f94317205 | note | Conformance Criteria - Maximum throat depth on manholes to be 450mm. Miminimum riser usage is required and minimum riser height to be 300mm. All Joints between risers must be epoxied
09ba41da-2d8a-5612-b97d-f2b371a87b83 | note | Records - Photos
| checkpoint | 16 - Structure installation (Manhole, Catchpit) (5)
5c248908-94c4-5ca7-9ff4-eec821c76e87 | note | ACTION (Hold, Monitor, Witness) - W
2648f60c-710a-5150-b0e9-17d9f086d815 | note | Detail - Concrete benching
4f29a29a-f30a-5f7c-8d97-1840060d9076 | note | Frequency - During structure construction
7700eed1-3820-5f6e-9bb0-f57b41005a67 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual/Inspection
8df839b4-b7e0-5bd9-8311-9be68525d305 | note | Conformance Criteria - Benching at base of Manhole shall be formed with 25 Mpa concrete.
b05e8268-76f3-5f15-a83d-791612088d40 | note | Records - Delivery Dockets
| checkpoint | 16 - Structure installation (Manhole, Catchpit) (6)
d5d1058b-3994-53ed-9f14-6e9626a8d7e3 | note | ACTION (Hold, Monitor, Witness) - W
3028937c-3797-54ab-b995-267a6f180945 | note | Detail - Manhole covers & frames set to correct level
80d6ccb7-aea9-5091-8ff0-c779841b22c6 | note | Frequency - During structure construction
19bd8857-7694-5214-93ae-6a3e7cf7c900 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual/Inspection/ Check
8dc16677-1e9c-58f4-843f-ee9784d42404 | note | Conformance Criteria - Heavy Duty Class E manhole covers required in trafficable areas as per AS 3996 400 KN rating
5ba306f8-8631-5abf-8409-ebfb61a96a89 | note | Records - Checksheet, Delivery Dockets, SW CoP
| checkpoint | 16 - Structure installation (Manhole, Catchpit) (7)
22cca6a2-36ba-5e16-8a0c-550c03099e7a | note | ACTION (Hold, Monitor, Witness) - W
2a537e3f-89df-560a-94da-8d404347e6e5 | note | Detail - Catchpit sump depth
92994a78-169d-5333-adff-8a2e8fb625cf | note | Frequency - During structure construction
74f1feea-bb5a-5699-b14a-83c1ddccf47f | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Measurement
d2f8b409-221e-5657-86e5-63644bb437c8 | note | Conformance Criteria - Minimum sump depth to 450mm as per AT CoP
9235ddd9-3853-533b-933b-1cbddc54af2e | note | Records - ATCOP
| checkpoint | 16 - Structure installation (Manhole, Catchpit) (8)
892a4937-85bd-582c-94e1-c70ddeb3323f | note | ACTION (Hold, Monitor, Witness) - W
39a5c023-a429-5a4f-8a47-4a9dbb922eb0 | note | Detail - Catchpit grate levels are set to correct level
380ba071-a1f7-59d5-99e5-548b436f241a | note | Frequency - During structure construction
c4136fd1-3888-51e3-b81c-26320833f27b | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual/Inspection/ Check
cb5ae1bf-8db7-5714-b70d-44bc77400ac8 | note | Conformance Criteria - Measure on site and must be Cycle friendly Class D lids as per AS/ 3996 rating 210 KN
2e4a26a9-b582-523f-a76f-da4c6e11cf5d | note | Records - Checksheet, Delivery Dockets, SW CoP
| checkpoint | 17 - CCTV
013d6f61-7cd1-54e3-b06d-1e6529d4407f | note | ACTION (Hold, Monitor, Witness) - H
56f9adde-5b53-5326-bc92-9002fe555db5 | note | Detail - CCTV record at completion of trench backfill and prior to final surfacing
283a3411-a2b7-57ef-a748-50017ba9b8cb | note | Frequency - At completion of the works
b0dad5a1-bdaf-5e8a-ba20-5e82d601177c | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection/ CCTV inspection
d72790f0-2dc0-5434-8d12-2662e3d49604 | note | Conformance Criteria - No Defects
7777035e-62ae-51b8-a971-5639ccf4b5f4 | note | Records - Inspection Report CCTV
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 18 - As-builts
676cb2b0-b61b-51a3-8185-c76a3f7780f7 | note | ACTION (Hold, Monitor, Witness) - H
c26332da-21f6-56aa-b391-93c03a944065 | note | Detail - Red pen mark up drawings to be included in QA file
ac679274-a20e-513b-a807-5572d1f8f9e3 | note | Frequency - At the completion of the Lot of work
9173295f-a55c-5b37-9c35-e7d152fae3ed | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Drawings
8513c80b-e85a-5293-b87a-6ab5447d4d0e | note | Records - Asbuilt Drawing
| signoff | AUTHORITY HOLDPOINT
| checklist | Portland Road - ITP - Enabling Works - Footpath, Kerb and Channel | itp | ITP - Enabling Works - Footpath, Kerb and Channel | fcdc189f-a663-487c-b749-ab79d0e983a3
| section | Site Set Out
| checkpoint | 1 Site Set out
6ba67fd0-fcf0-43e3-bdcc-ac4ef83dc0da | note | VERIFICATION ACTIVITY: Surveyor
1de5edcb-f93a-4490-9798-269251836005 | note | METHODS OR REFERENCE: Surveyor
0a184a6a-d6e9-49ee-be8e-f1f8afa340ff | note | FREQUENCY: Everysite
6d483f4f-7c63-49d8-83dc-eaf5cbf10da7 | note | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criterea is acceptable.
c90f04c8-92d0-4ca7-bb56-50c5250d21f0 | note | Hold Point: Mandatory HOLD POINT -
e1bc6caf-bf93-464b-a570-95575463b298 | note | Records: Onsite records/photos
f3428d77-5b9a-4921-865d-b9b8c520ab9d | note | Onsite Responsibility: Site Engineer
| signoff | HOLD POINT
| section | Materials
| checkpoint | 1 Kerb & Channel
e8631064-92fd-4a6b-acaa-f885fc11f8b8 | note | VERIFICATION ACTIVITY: QA FORM
e3ec6c60-83bd-4b18-ac0a-a539ed188ed8 | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
2a845afd-fbc3-4e46-befd-3a4215066a1c | note | FREQUENCY: Everysite
23969383-05b9-478c-8d61-ca12e4be6e1a | note | ACCEPTANCE CRITERIA: Kerb & Channel to be precast hand-laid. . Kerbing laid on 300mm min Gap 65 subbase in roads and 100mm GAP 40 in footpaths (CBR>5).Concrete 20mpa @28 Days
1a229d3a-9bd9-48ba-98c4-7b1186724fb9 | note | Hold Point: Inprocess Inspection
74afbda9-9cc4-49dd-a6dc-9e3039ff61d4 | note | Records: FH concrete QA sheet, photos. Concrete Plant Docket
db00f418-7008-4882-8a2d-fd7f3d2a22d7 | note | Onsite Responsibility: Site Engineer
| checkpoint | 2 Channel Level
32a1bd74-6845-44b4-ad5f-fc336e207cd3 | note | VERIFICATION ACTIVITY: QA FORM
e52a614c-f8ab-49b3-934c-59d387be3679 | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
27e4280a-8897-4e8d-b18f-b823294f0db6 | note | FREQUENCY: Everysite
16d28bc4-1a4e-4472-9b02-afa037a494af | note | ACCEPTANCE CRITERIA: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
246a92b5-6d96-447f-94dc-0fb98611f771 | note | Hold Point: Inprocess Inspection
d14acd82-cdc5-422e-b06a-04dcde86d64d | note | Records: FH concrete QA sheet
4d7d156f-c039-4060-81db-4dac1f4a50fe | note | Onsite Responsibility: Site Engineer
| section | Construction
| checkpoint | 3 Asphaltic Footpaths
24dded84-4a27-433d-a1b5-688e0fde4024 | note | VERIFICATION ACTIVITY: QA FORM
091a2f99-f6b9-4f8a-a5e4-0b7b3d4f29e6 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0003
0928d2e6-a294-4285-b19b-1effaa7f3a89 | note | FREQUENCY: 10m Intervals
0a85d0de-da51-4cdd-859c-14148ff40fac | note | ACCEPTANCE CRITERIA: Subgrade -(CBR > 3) Basecourse - 150mmmin. thickness of GAP 40 Clegg CIV > 15 Surfacing - 25mm MIX 10 (TNZ-M/10 SPEC BLACK ASPHALTIC CONCRETE) . 2% to 3% max. fall to carriageway.
eee93390-f3e5-46cd-8a39-dfb05cfe6d60 | note | Hold Point: Inprocess Inspection
9a662980-3254-41c2-b246-eaa5def7d9ef | note | Records: FH concrete QA sheet. Concrete delivery Dockets kept as record
3c7000e1-8057-4c52-b319-945619754bd9 | note | Onsite Responsibility: Site Engineer
| checkpoint | 4 Pram Crossings (PX)
b9bd9624-fa73-4eed-9a17-610550781a03 | note | VERIFICATION ACTIVITY: QA FORM
3c4f5a57-13cd-4c54-b1a5-cdc856f40d57 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0006
3627dc7b-53cb-4973-ada1-bee0f7027cdb | note | FREQUENCY: Each PX
2acead64-00c0-4e6f-aa82-964c852a42a3 | note | ACCEPTANCE CRITERIA: Subgrade -(CBR > 3) Basecourse - 150mmmin. thickness of GAP 40 Clegg CIV > 15 Surfacing - 25mm MIX 10 (TNZ-M/10 SPEC BLACK ASPHALTIC CONCRETE) . 2% to 3% max. fall to carriageway.
8b40f33d-aa21-44a2-b73d-7b270d3bfa78 | note | Hold Point: Inprocess Inspection
a8eacb49-4e88-4431-9a17-8171f9bc348d | note | Records: FH concrete QA sheet. Concrete delivery Dockets kept as record
83e7bb98-fde9-483a-b2b5-e81c9a8daf6c | note | Onsite Responsibility: Site Engineer
| checkpoint | 5 Grass Berms
dbd10f7f-782e-4693-89a9-ac511bad94c6 | note | VERIFICATION ACTIVITY: Visual
91e99469-84b4-49fc-83b8-ffaca0411950 | note | METHODS OR REFERENCE: ATCOP Section 12 Footpaths and Pedestrian Facilities
ab1ac7d3-3c92-419d-ad86-049c2952849c | note | FREQUENCY: 10m Intervals
0f7f4bf4-d3fa-47a7-b873-ae09682d7da2 | note | ACCEPTANCE CRITERIA: 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
13a7feff-1405-47ae-9e41-8ccf1e337970 | note | Hold Point: Inprocess Inspection
41d93eae-647a-4395-aa57-9a1947c4eb5d | note | Records: Photos
c2bd0d00-2c30-44a3-90a9-636a84466e28 | note | Onsite Responsibility: Site Engineer
| checkpoint | 6 Tactiles
a531284a-a145-4afb-88f8-6d3a0c07239b | note | VERIFICATION ACTIVITY: Visual
1765b4f4-aa4e-4f73-9277-ee68ef7bd77b | note | METHODS OR REFERENCE: NZTA RTS Guidelines for facilities for blind and vision impared pedestrians; AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
8d5787d1-4ded-4ab0-b7f7-1909b6eeb3f1 | note | FREQUENCY: Everysite
80684a7e-5421-4d7d-8183-99b521e79724 | note | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
8c52c2cb-6b52-4ee9-8506-81a7cc901c99 | note | Hold Point: Inprocess Inspection
13fca5cb-5164-4d1f-9058-d13865c122d4 | note | Records: Photos
c687bd6c-e374-420d-ab19-54ed6d343faa | note | Onsite Responsibility: Site Engineer
| section | Asbuilts
| checkpoint | 7 As built information
35c3599d-ff5b-429c-97ef-6b5b927d2c33 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
ec811bfb-ef07-46ba-984b-9f2eecd5824f | note | FREQUENCY: Every Site
39da1f8e-0951-4cda-ab9f-5e63d4057190 | note | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
7e627da2-7a5b-4566-ac21-6fb6568be03b | note | Hold Point: In Process Inspection
bd5215ab-23a6-4167-8cf3-1d96c42ac378 | note | Records: Asbuilt records
85e891f2-7ed9-4b1b-9a47-f5b00e62bbec | note | Onsite Responsibility: Supervisor and Engineer
| checklist | Portland Road - ITP - Raised Pedestrian Crossing | itp | ITP - Raised Pedestrian Crossing | b6ad0ece-275a-4bd3-8ac3-557e7df6c52e
| checkpoint | 1 Permits
f56bf502-9539-43da-af99-240cedc8574b | note | ACTION (Hold, Monitor, Witness): H
8c8cae44-7b04-4760-b242-28e78b1e91af | note | Detail: Obtain Permits
5cca4860-d4b2-473f-84ba-4dcb2cf17d37 | note | Frequency: As required
a70ebf2e-226f-4cc4-bc05-9c7a75f6a0a1 | note | Inspection / Test Method: Document Review
98d3c58c-fe02-48ed-98d1-382009002904 | note | Conformance Criteria: Control Checklist - Fall Prevention (if applicable). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
0d1e2c00-a658-445a-9944-98d933edf619 | note | Records: Permit attached or permit number noted
| signoff | HOLD POINT
| checkpoint | 2 Pre-construction sign offs
63e1c69b-5dff-4f3a-b80c-8e6b6d022cda | note | ACTION (Hold, Monitor, Witness): H
846d8f18-7be1-4b4b-a12d-05f3c8d35b01 | note | Detail: Ensure that Sub-Contract and Supplier Agreements are signed
bc049f9e-9edc-4d55-a27a-1c1d8d76c21b | note | Frequency: Prior to commencement
43b964ac-2843-45ad-aaa5-3ebba8767cec | note | Inspection / Test Method: Document Review
2dcad666-a16d-4eb2-a6c9-03654bf3fb3f | note | Conformance Criteria: Signed Subcontractor and Supplier Agreements
feda9ed1-ef13-407c-9507-2495ae1b2f8a | note | Records: Subcontract and Supplier Agreements
| signoff | HOLD POINT
| checkpoint | 2.1 Pre-construction sign offs
c2d8b032-697f-4c8b-8f92-7fc97f5861a6 | note | ACTION (Hold, Monitor, Witness): H
3b48c016-bc45-4e08-b531-ff83ed894f99 | note | Detail: Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
7e59723c-5785-4f32-9a98-d0d4fc557391 | note | Frequency: Prior to commencement
266a1d60-8f88-47af-882c-bea0b6666682 | note | Inspection / Test Method: Document Review
53fa9b9f-dcae-47e1-a339-6908f7207ec3 | note | Conformance Criteria: TMP is approved by CAR manager for each site and works are only completed within the approved dates..
6c0fa734-97eb-4124-a859-c8ccc846e342 | note | Records: TMP on MyWorksites/On Site
| signoff | HOLD POINT
| checkpoint | 2.2 Pre-construction sign offs
2f394cef-d478-40e4-8999-07a5d69378f1 | note | ACTION (Hold, Monitor, Witness): H
d5216ee6-4d21-429e-9bba-3e274b17764b | note | Detail: Ensure all Sub-Contractors and Suppliers go through FH induction
3747555d-333e-4770-bf72-a71d58938bda | note | Frequency: On site daily
0a0fe2b6-fe75-4438-bd51-4958634dc09a | note | Inspection / Test Method: Induction
01bfb892-6bc0-41cb-a63a-4439b2bc6a0b | note | Conformance Criteria: Supplier's and Subcontractor's signatures on hazard ID and pre-start documentation
a99e23fd-3b34-4b3c-b1de-ab851626f95a | note | Records: Hazard ID and Pre-starts to safety team
| signoff | HOLD POINT
| checkpoint | 3 Design
4179b8e7-d8b1-4164-91bf-60bf65910e20 | note | ACTION (Hold, Monitor, Witness): H
c91b510f-24f7-4866-8f63-9749eae62a85 | note | Detail: Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
0e0f64ed-4282-4621-b7a5-6e810af0181f | note | Frequency: Prior to commencement
49cc0497-fa7a-41b8-a4ae-bf968e01ce47 | note | Inspection / Test Method: Document Review
227e9ebf-5499-43b9-afb4-1c57778f6b47 | note | Conformance Criteria: IFC drawings have been received by Contractor
49be4b99-81e4-4f2e-9f0d-22ff0976bd8d | note | Records: Check Drawing Register
| signoff | HOLD POINT
| checkpoint | 4 Installation of Erosion and Sediment Controls
41eacb28-836f-48e4-880e-b86e651abcdc | note | ACTION (Hold, Monitor, Witness): H
0a724ba1-c386-4ce4-91a7-ade5f7dce03b | note | Detail: Ensure that Erosion & Sediment Control in place
b7e8f025-7514-41b4-addc-cea782daa1af | note | Frequency: Prior to commencement
c8731ebf-d732-452f-999f-0b3aff412fd3 | note | Inspection / Test Method: Visual Inspection
0f37c1e2-051f-45bd-b5f0-368486522016 | note | Conformance Criteria: Territorial Authority has approved the asbuilts for the ESC controls constructed onsite and gives approval for construction to commence
b1917bf5-47aa-4393-a1d2-58f6366f1643 | note | Records: Environmental Controls Audit
| signoff | HOLD POINT
| checkpoint | 5 Survey Setout
30eb8f63-f0a4-4785-8ade-74a9902eab44 | note | ACTION (Hold, Monitor, Witness): H
d35da8f5-25b7-4eac-ae6f-9d3560726b6c | note | Detail: Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations)
b7efc5a7-a4ea-4671-a1ea-93118d2cbf68 | note | Frequency: Prior to commencement
9f7091ff-5b51-4744-8d61-ea776ec21c1f | note | Inspection / Test Method: Survey + Smart Level
2b173680-e92d-4917-935a-2069c5d7d1c1 | note | Conformance Criteria: Consistency with Construction Drawing
6a381b4d-667c-48dc-89f0-e5fae3224665 | note | Records: Site Photos post surveying
| signoff | HOLD POINT
| checkpoint | 6 Locate Existing Services by Hand Digging
a432a95f-9f45-4a0d-8ad8-a9d503260c2c | note | ACTION (Hold, Monitor, Witness): H
d3e57843-347a-4dae-b71b-4d991a749317 | note | Detail: Ensure all services conflicting with the line of trench has been exposed by hand digging
84dc2db5-4e5d-4a9b-b308-0e756803db05 | note | Frequency: Prior to commencement
eb5ed185-6256-4f19-8882-409342504eed | note | Inspection / Test Method: Potholing
2c687a65-1e09-4b2a-8145-a0d149d853f8 | note | Conformance Criteria: All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. Asbuilt all services
a80908e6-d06d-440a-b590-c1834455a790 | note | Records: Digging and excavation checklist, service planes, As-Built Drawings Doc. Review
| signoff | HOLD POINT
| checkpoint | 7 Material Compliance
9dd79b85-75d2-42e4-ad59-d7085aaa5ca2 | note | ACTION (Hold, Monitor, Witness): H
e0ac73be-884e-4d09-8007-308961d46ae3 | note | Detail: LESA dowels to be used at all construction joints
bacdcc39-077e-46e3-8b85-0a9bd49dd2ca | note | Frequency: Prior to pouring concrete
b0e634a9-0de5-448a-922f-debce8e2e816 | note | Inspection / Test Method: Document Review
eeabc891-14b1-4260-a31a-e23b2b158028 | note | Conformance Criteria: Photos + Delivery Docket added to QA folder
fef0c3a2-30d7-4cf3-b210-02e765404eb1 | note | Records: Delivery Dockets / Photos
| signoff | HOLD POINT
| checkpoint | 7.1 Material Compliance
41372d2a-0a2d-4411-aca6-98d99f974c1e | note | ACTION (Hold, Monitor, Witness): H
e32e00ba-7337-4643-bd12-12682bfbf191 | note | Detail: 0.25mm polythene layer placed across all surface area at bottom of raised table
1cc8a188-0887-47bd-9136-784f4650a572 | note | Frequency: Prior to pouring concrete
bfd97af3-6e1f-4dd7-8ac4-3bd70d5d03fe | note | Inspection / Test Method: Visual Inspection, Document Review
c8d54b2f-2d9d-4f7e-a5e3-7cde4ac2a585 | note | Conformance Criteria: Photos + Delivery Docket added to QA folder
4e859543-5ef4-40d9-8be0-4ae5b3091aea | note | Records: Delivery Dockets / Photos
| signoff | HOLD POINT
| checkpoint | 7.2 Material Compliance
44cfe1e0-3710-452e-9341-053faa14b103 | note | ACTION (Hold, Monitor, Witness): H
b6c26eef-eaf1-4f25-8536-f37029f7d934 | note | Detail: 50mm thick compacted layer of AP20 aggregate placed underneath polyethene layer.
7459797f-2301-4702-a88d-371486ca0a56 | note | Frequency: Prior to pouring concrete
f4692c39-50f8-4733-963e-33ae9f6459c8 | note | Inspection / Test Method: Visual Inspection
e7c60162-49a6-4b14-92c9-548e9854ee0b | note | Conformance Criteria: CIV >15
cbf29821-ee45-454d-b144-746239a36f29 | note | Records: Delivery Dockets
| signoff | HOLD POINT
| checkpoint | 7.3 Material Compliance
0c3d736c-6522-40bd-af4d-0ea0f302e5a3 | note | ACTION (Hold, Monitor, Witness): H
effb3675-8a0f-497c-b57c-847a6991995f | note | Detail: All concrete delivered to site shall have 40MPa 28 day compressive strength with 4kg/m3 of Black Oxide Powder and 13mm aggregate chip size
49932543-1d07-473e-860c-5d742691d5cb | note | Frequency: Prior to pouring concrete
0b901848-68f1-491a-8371-e6cfc7f64044 | note | Inspection / Test Method: Concrete Delivery Dockets
9e54f103-affb-45c6-91d8-2a46a67923a5 | note | Conformance Criteria: Delivery Docket added to QA folder
dcce77ec-87f0-4a2b-8a38-fc3abb2be56e | note | Records: Concrete Delivery Dockets
| signoff | HOLD POINT
| checkpoint | 7.3.1 Material Compliance
1022789c-4fa2-4d4b-bd73-fc2ae9464396 | note | ACTION (Hold, Monitor, Witness): H
b1699f0e-eeae-4154-a937-2d6cd070a662 | note | Detail: Two layers of 663 steel mesh to be placed in the speed table with 50mm plastic chairs separating them.
c64f84ed-333d-48ab-b45f-8e606f2dc0e0 | note | Frequency: Prior to pouring concrete
1ff750a3-97f6-4585-94c7-64f0b11d857c | note | Inspection / Test Method: Visual Inspection
cf705f1d-7ad3-4abf-9158-c026e2595f4b | note | Conformance Criteria: Delivery Docket added to QA folder
1aa01731-7268-4fd7-867b-554494ae7784 | note | Records: Site photos
| signoff | HOLD POINT
| checkpoint | 8 Temporary Works (Formwork)
fe430fd1-7e14-4350-86d1-544149bf4c7e | note | ACTION (Hold, Monitor, Witness): W
251bb264-8ad2-410c-bbb0-d3691d814290 | note | Detail: Formwork to be set to correct line and level
4dd3e3bd-01be-4036-b280-5d655be7f08e | note | Frequency: Prior to pouring concrete
060f3c38-5966-46e7-a72b-ac9d7cf31c78 | note | Inspection / Test Method: Visual inspection
a37df524-7434-4d23-afa4-ea4d30e2efc3 | note | Conformance Criteria: Concrete Inspection Record
4ab35f2e-51b9-4041-a705-cda3df9b6410 | note | Records: Concrete Formwork Checklist
| checkpoint | 8.1 Temporary Works (Formwork)
201dee91-857e-4195-b737-f843e3d967ff | note | ACTION (Hold, Monitor, Witness): H
0f9128df-ee75-48d6-9322-9ac2f03c00b8 | note | Detail: Raised table formwork to be 100mm above existing road level and be 300mm in depth and gradients respectively of entry and exit ramps
1e27f38c-6ad6-459b-84fc-f83c98a7e85b | note | Frequency: Prior to pouring concrete
ea9ad903-0407-400c-bf63-ce78a28a5749 | note | Inspection / Test Method: Measurement
b9f59c01-ad72-4568-bf97-b9bfbe48ace9 | note | Conformance Criteria: Designer to inspect formation level
1e8ce9eb-1e89-4c6e-b8e5-637570a714b6 | note | Records: Site photos
| signoff | HOLD POINT
| checkpoint | 8.2 Temporary Works (Formwork)
767f2a4d-ec18-4d25-9b2c-c44d85d87543 | note | ACTION (Hold, Monitor, Witness): H
ea734fbc-a760-4a72-9903-a422cefef5c8 | note | Detail: Raised Table ramps to have 200mm depth at entry point and tie into 300mm depth to meet raised table
a2821ce0-d9eb-42c0-90a1-84d917bed137 | note | Frequency: Prior to pouring concrete
93defb24-6e36-4d4e-9fa5-af70bbf115cc | note | Inspection / Test Method: Measurement
d80a41c2-73ac-4668-b0aa-5554d41cebd5 | note | Conformance Criteria: Designer to inspect formation level
c2146b10-f582-4a48-86e0-967e85de32d2 | note | Records: Site photos
| signoff | HOLD POINT
| checkpoint | 8.3 Temporary Works (Formwork)
36f41995-74f9-4414-b20c-8631d4b529a2 | note | ACTION (Hold, Monitor, Witness): H
5f38a159-9fc5-491d-a50d-a40fe96a8144 | note | Detail: Raised Table ramps to be 1m across for entry and 1m for departure ramp. Toe to be 1m across for both entry and departure.
747a9554-3f61-47c2-8d78-6acb5fc18d96 | note | Frequency: Prior to pouring concrete
bae7a742-4497-4772-8eb4-44912cc3beea | note | Inspection / Test Method: Measurement
a6b765f6-1d43-4c08-8104-c4731f73f321 | note | Conformance Criteria: Designer to inspect formation level
f1716038-284a-4c27-a661-e633767ca5cc | note | Records: Site photos
| signoff | HOLD POINT
| checkpoint | 8.4 Temporary Works (Formwork)
b035d067-0d54-4eda-9e91-2eef8e585357 | note | ACTION (Hold, Monitor, Witness): H
b826856b-0444-4418-bfd6-70f181c8b634 | note | Detail: Raised Table ramps to be 1:10 gradient for ramps, with 2 layers of 663 mesh.
3c9f0291-6fcf-4db8-85d4-15cc3dbd6a31 | note | Frequency: Prior to pouring concrete
31fab920-624f-4851-9f64-29e55a6590f8 | note | Inspection / Test Method: Measurement
f7addfbd-80dc-4744-9ee6-12d788264204 | note | Conformance Criteria: Designer to inspect gradient level
998e5e88-098b-45ca-8aa4-a5ce9c928587 | note | Records: Site photos / Concrete Formwork Checklist
| signoff | HOLD POINT
| checkpoint | 8.5 Temporary Works (Formwork)
b3b82123-b6f4-499d-94be-5c81400e750b | note | ACTION (Hold, Monitor, Witness): H
f3a8060c-a195-4d97-8361-27be3751bcad | note | Detail: The Site Engineer and MSQA Engineer must sign off the formwork prior to concrete being poured
7442c626-8877-482c-9249-045459373cba | note | Frequency: Prior to concrete pour
20016f50-1d4c-4a15-9bc0-79cc30eeeaed | note | Inspection / Test Method: Visual inspection
4d080c3f-b33b-4c7e-a899-42c75bfcdf1b | note | Conformance Criteria: Concrete Inspection Record
115bcc5a-9e9f-4cb1-b96e-56b5db214212 | note | Records: Concrete Formwork Checklist
| signoff | HOLD POINT
| checkpoint | 9 Reinforcing
e5654b62-6b80-4be1-94bc-443759a953a3 | note | ACTION (Hold, Monitor, Witness): H
f5c770be-1e59-49da-ba43-c2e6686139e3 | note | Detail: All construction joints are to contain 2 rows of LESA dowels or similar approved dowels . Speed basket system 50mm w/ Black 300*50*6mm plates @400 centres placed across the construction joint
8e7156a9-907d-496f-809b-e99270d17c6c | note | Frequency: Prior to pouring concrete
9be5db5e-beb5-4d6c-9585-9e044f721f89 | note | Inspection / Test Method: Measurement
bdca7882-7498-4cdc-9c64-5c7f022433c2 | note | Conformance Criteria: Concrete Inspection Record
bb07d310-8fa8-43bf-80c0-fbd960310b6d | note | Records: Site photos/Concrete Formwork Checklist
| signoff | HOLD POINT
| checkpoint | 10 Concreting
b85302da-5165-40ea-8058-5434bf362cc7 | note | ACTION (Hold, Monitor, Witness): H
5c7778d9-ae39-42c7-a73b-da48b531a027 | note | Detail: The MSQA Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required
f5055c91-f968-4257-8fb4-1abebffa02bc | note | Frequency: Prior to concrete pour
c6d6ece4-3331-484e-8747-b4f04629d27f | note | Inspection / Test Method: Visual inspection
298678c2-880f-4fbd-a965-84c2cf98f534 | note | Conformance Criteria: Engineer will be notified via email/SMS at least 24 hours before required for inspection
04feae9c-1de3-441a-9014-57cdc50ffd77 | note | Records: Email / SMS
| signoff | HOLD POINT
| checkpoint | 10.1 Concreting
d7e69b08-ad9b-4bcb-8da8-fe35aafb43b4 | note | ACTION (Hold, Monitor, Witness): W
5ccdeeb8-35c9-4c5e-86e1-9e44c21e7e82 | note | Detail: Vibrator to be used throughout concrete pour
a77c287e-0028-4c39-b907-d783be6e4fc5 | note | Frequency: When pouring concrete
3c9365d3-3c07-4b41-a2a5-000759509644 | note | Inspection / Test Method: Visual Inspection
2b9f7f28-fa20-4c6f-bf23-0e89e71f34bd | note | Conformance Criteria: Concrete Inspection Record
a2a52200-478d-4f85-9a98-687760bd14f1 | note | Records: Concrete Formwork Checklist
| checkpoint | 10.2 Concreting
e3262b93-b302-4fbf-a395-4b234898aa65 | note | ACTION (Hold, Monitor, Witness): H
3129c15e-ae3f-4f46-b496-55f36c628c4b | note | Detail: Concrete surfaces on ramps shall be U5 broomed finish and speed table top to be exposed.
3f7f87ef-7b94-436a-8d6f-2d6aa624b4b0 | note | Frequency: At completion of pour
f70e81b1-96ce-4fa4-ae3c-50e5dc532557 | note | Inspection / Test Method: Visual inspection
aef894e4-5324-49ee-a415-f4bb5b0a2b3b | note | Conformance Criteria: Concrete Inspection Record
70e104f4-92c0-4779-94bf-e492c40e0dd8 | note | Records: Concrete Formwork Checklist
| signoff | HOLD POINT
| checkpoint | 11 Curing
def74f70-98c8-4b8e-b507-9b27939880a5 | note | ACTION (Hold, Monitor, Witness): M
e4a245ce-c1bb-4b15-80ea-e6e9e310b6fb | note | Detail: Concrete will be left for 48 hours minimum to cure before traffic is allowed on it.
1f0b0cac-6411-4857-b2df-fc3bd05e4a0d | note | Frequency: Post Pour
4bc577a4-a44d-46ce-849d-a275b59a2c05 | note | Inspection / Test Method: Monitoring the time allowed for curing
00a8cf94-3468-4e9e-b71b-13b1f1257a13 | note | Conformance Criteria: 48 hours minimum have passed
19cf7064-0b90-4d30-a351-7036fc4c3325 | note | Records: Concrete Formwork Checklist
| checkpoint | 12 Remove formwork
c80cffc2-19c5-4eb5-9a70-87336dba40a8 | note | ACTION (Hold, Monitor, Witness): W
4b367bd1-a46d-41fa-8e46-8e89f338a859 | note | Detail: Remove formwork after 48 hours
9160683f-c760-466e-924f-a457c0f96d8a | note | Frequency: Post Curing
caf4bf72-8636-485e-a125-4d33be178de2 | note | Inspection / Test Method: Visual inspection
fa795ffd-e07d-4859-803f-8e1d26f22cc3 | note | Conformance Criteria: Concrete Inspection Record
bffb310b-e8d2-45ef-a849-1c2c73201576 | note | Records: Concrete Formwork Checklist
| checkpoint | 13 Asphalt- Concrete extension slab/ Toe
f3f9dbd1-2e51-4c77-8bab-da88888c22f2 | note | ACTION (Hold, Monitor, Witness): H
47b35a2c-0e57-4978-b247-0cff52f67e1b | note | Detail: One row of Lesa diamond placed mid depth @400 C/C along construction joint as per TDM TC003
47cf3f2a-1945-4a6e-95c7-e581bdcae3ae | note | Frequency: Prior to pouring concrete
28a13716-b8e5-4453-a1d0-cacdb54d3272 | note | Inspection / Test Method: Measurement
27ed45a9-b531-49b8-811c-5ebbde781798 | note | Conformance Criteria: Pre pour Inspection Checklist, Concrete Inspection records
666ba1d8-450c-469c-82da-d6c675e3b709 | note | Records: Site photos, delivery dockets
| signoff | HOLD POINT
| checkpoint | 13.1 Asphalt- Concrete extension slab/ Toe
28453789-3d7e-49e0-927d-48c574fbea50 | note | ACTION (Hold, Monitor, Witness): H
d01f1aed-af62-4989-87a5-96b6928b9889 | note | Detail: 150mm thick 40Mpa Concrete with two layers of 663 mesh
6d5fdb82-6f47-4159-b973-5c7de4eabcb5 | note | Frequency: Prior to pouring concrete
f723a0e4-ca0c-4979-891d-9ba1225b9beb | note | Inspection / Test Method: Measurement
50bed6e0-752e-4a27-a3b8-36c92fc9b304 | note | Conformance Criteria: Pre pour Inspection Checklist, Concrete Inspection records
92abd2a4-4d4f-4f79-adeb-8dab485389dd | note | Records: Site photos, delivery dockets
| signoff | HOLD POINT
| checkpoint | 13.1 Asphalt- Concrete extension slab/ Toe
3c2aa981-0720-4efd-9a7b-bff6f958465a | note | ACTION (Hold, Monitor, Witness): W
6049aa86-766d-43d9-a47f-8bd856a634da | note | Detail: Tack Coat between AC14 and Concrete slab
729fe008-e918-4635-b22d-e8a1eb2e988d | note | Frequency: Post Curing
1bde3535-cf2d-4b69-8200-6336b62aaf33 | note | Inspection / Test Method: Visual inspection
3706bc0b-f2f9-4beb-8935-f1162c3d08bf | note | Conformance Criteria: Photos + Delivery Docket added to QA folder
cb29131a-1578-4b8a-b533-dd8df1c48ace | note | Records: Site photos
| checkpoint | 13.2 Asphalt- Concrete extension slab/ Toe
d8c507c8-0b5d-4b48-b5bf-36f850ec1c6b | note | ACTION (Hold, Monitor, Witness): W
3d3572a8-5e74-421b-b59e-987209855737 | note | Detail: Tack Coat between AC14 and Concrete slab
aabb8ae7-23a1-4449-b6ae-c0eda7936ecf | note | Frequency: Post Curing
4462193a-b23d-4013-a88f-3cdcfa20106b | note | Inspection / Test Method: Visual inspection
9bc10efc-8497-452d-9ed9-a42d71437a7f | note | Conformance Criteria: Photos + Delivery Docket added to QA folder
e57d7c03-315c-46eb-a95c-d7f62f50912b | note | Records: Site photos
| checkpoint | 13.3 Asphalt- Concrete extension slab/ Toe
54b43e21-64e5-43e2-af9a-f585c5de769b | note | ACTION (Hold, Monitor, Witness): W
13d5e5a4-1534-4b9f-b05b-e2884c53e591 | note | Detail: 50mm thick AC14
a15af5c9-224c-406e-a579-c660aa33d03d | note | Frequency: Post Curing
b49e9db7-fd0c-49c1-a8cc-6ece5df86cab | note | Inspection / Test Method: Measurement
8f9aa266-4fb8-41b8-85b6-a5e939680a12 | note | Conformance Criteria: Photos + Delivery Docket added to QA folder
e5d9f024-f507-4bb7-8582-92047875778e | note | Records: Site photos, delivery dockets
| checkpoint | 14 Lot Number QA File
363cffe8-3fc7-400d-9cd0-bdc30d131922 | note | ACTION (Hold, Monitor, Witness): W
417f20dd-9085-43d5-a234-237df66854bb | note | Detail: Ensure all QA Records, site photos and incident cases (OFIs) are closed and included within QA file
e8d1f1be-2656-4500-bf88-46ef4d6a4fdd | note | Frequency: At completion of Lot
dd6e03af-830c-455a-b82e-d884b2b6f93c | note | Inspection / Test Method: Document Review
15e876ea-1ceb-4710-a28a-7fe0a755d1fb | note | Conformance Criteria: All QA files compiled and submitted to client
ef70740f-9079-45f6-9ab4-39253935ecc0 | note | Records: QA records
| checkpoint | 14.1 Lot Number QA File
5de1c3f0-ff92-4f2b-9369-e9e235bfbea2 | note | ACTION (Hold, Monitor, Witness): W
4c633804-3e62-4a98-8c7d-a3061e9b8612 | note | Detail: Delivery Dockets to be included in QA file
4a475358-7073-4af5-b8b8-4cc7d40993cd | note | Frequency: At completion of Lot
85a5fcd6-59a4-4076-a6cf-6743feed3068 | note | Inspection / Test Method: Document Review
2068eea2-bb6d-4b93-b6cb-b51c28f5b911 | note | Conformance Criteria: Delivery Dockets to be included in QA file
654c45cc-bc14-46a7-b38d-0322c1b2bf9e | note | Records: QA records
| checkpoint | 15 As-builts
156b2c61-85be-4d45-8c7f-1ad046c65ecc | note | ACTION (Hold, Monitor, Witness): H
81615d11-d426-4cd0-badc-bf04b9ef4821 | note | Detail: Red pen mark up drawings to be included in QA file
661fa224-04b5-477f-a0a5-0332c993c94b | note | Frequency: At the completion of the Lot of work
97a1cd4e-6014-4a3a-be7b-5c0a94ff9aa1 | note | Inspection / Test Method: Drawings
bfc8153a-de96-4df5-88ec-4713e348fa6a | note | Conformance Criteria:
451d9bf6-a748-4220-b154-a1ef7ed7c5d5 | note | Records: Asbuilt Drawing
| signoff | HOLD POINT
| checkpoint | ITP Completion
53888654-1392-46a6-a780-cd3f25a76094 | textbox | IFC Drawings used for Construction incl. Rev numbers:
7ed63d06-c5ef-4951-a4a9-6f552795f6b1 | textbox | Reference Documentation (Notices/OFIs etc.):
73ba3f5d-d6bb-4244-8c05-e799d7ca7df5 | textbox | QA Compiled By :
b4a70f36-e41e-43d0-9c1d-ddcdb8402df7 | textbox | QA checked By Discipline Manager:
e247471a-2360-4e00-9e71-a9e48d74d621 | textbox | QA checked By Quality Manager:
993bd705-f7b3-4d77-b81b-ba5f6631ba9f | textbox | Accepted By Design Engineer:
| checklist | Portland Road - ITP - Stormwater Drainage | itp | ITP - Stormwater Drainage | d4312cd7-8b9f-4547-bc46-b4502ec27505
| checkpoint | 1 Permits & Services
c2885d90-a291-4ed8-bc40-0501071d0479 | note | ACTION (Hold, Monitor, Witness): H
1ff1e0bd-0b4f-444d-a771-504b9a760227 | note | Detail: Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
eed78585-ac25-498b-a6f5-dc08748992dc | note | Frequency: Prior to any construction commencing
752960d6-41c6-4aa3-b575-080b7165061e | note | Inspection / Test Method: Document Review
f9da23f5-37c7-42df-b9ed-6baca7aa2300 | note | Conformance Criteria: Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority
504e7e93-5920-4853-aae2-133a91cef0d1 | note | Records: Permit attached or permit number noted.
| signoff | HOLD POINT
| checkpoint | 1.1 Permits & Services
4c10b021-7685-4631-ade9-d77e84d9639c | note | ACTION (Hold, Monitor, Witness): H
75d33cfe-0af3-4fdb-9ff5-53e46c9506e4 | note | Detail: Locate and mark out all existing services
3e9fb62a-10f7-4918-a27a-d15089cc2a56 | note | Frequency: Prior to any construction commencing
4b69bcc5-5df6-45e7-bdb5-229182cdad68 | note | Conformance Criteria: B4u dig procedure - follow utility protocols
ccf664cb-eb11-40ed-af95-83e7022ea107 | note | Records: B4u dig plans & GPR report attached
| signoff | HOLD POINT
| checkpoint | 2 Pre-Construction Sign Offs
7b000c77-4390-46d9-bf60-62082c074aae | note | ACTION (Hold, Monitor, Witness): H
74cea165-b7f0-4745-ad08-40112cd659e0 | note | Detail: Sub-Contract and Supplier Agreements
d4f8959d-9a6b-49ac-918e-e923222ec3e7 | note | Frequency: Prior to commencement.
f807329f-413f-4cfb-9076-c4a1b256deeb | note | Inspection / Test Method: Document Review
65c12716-4de2-4871-83c6-b63f656b3892 | note | Conformance Criteria: Sub-Contract and Supplier Agreements to be agreed and signed
d364de73-dfa1-4072-bff1-9982da820def | note | Records: Subcontract and Supplier Agreements
| signoff | HOLD POINT
| checkpoint | 3 Design
0c26d9a5-ccf6-4755-ac01-ac89144d6879 | note | ACTION (Hold, Monitor, Witness): H
4fdbbe36-0aef-4e97-97c2-66e49175ea98 | note | Detail: Design is approved and Drawings are of the latest revision.
ce200f98-ea1a-447d-9fb8-79e3bf64b512 | note | Frequency: Prior to commencement.
efb555f9-2217-40b1-adb0-507f56fdc7af | note | Inspection / Test Method: Document Review
49c0ad5f-e0a5-4f7f-9c4d-dbc0fb9dcbdf | note | Conformance Criteria: Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
9859f3c5-9d7f-492f-afc5-fabfa98360c4 | note | Records: Drawing Register.
| signoff | HOLD POINT
| checkpoint | 4 Survey Setout
5ef567b7-05c4-4072-b795-b9d3d878a766 | note | ACTION (Hold, Monitor, Witness): H
80869c21-4056-47b2-8e78-1bdf1fcaf1d3 | note | Detail: Setout Pipe Alignment and Service Locations with inlet & outlet points and inverts as required to construct to design
ab0a0f6f-fdc6-4623-acbd-ce5f75ddb53e | note | Frequency: Prior to commencement.
7f5f4023-efac-4fe1-b4c0-cdbc8e14edf5 | note | Inspection / Test Method: Survey
eee59466-462c-4959-9c14-68dc7d602cee | note | Conformance Criteria: As per Stellar Consulting Engineering Drawings: 2789-C3060 and/or Setout files
2b9a34d5-a211-4343-9c54-4d8ded1f2e3c | note | Records: Survey Receipt.
| signoff | HOLD POINT
| checkpoint | 5 Pipe and Manhole Material Compliance
d00519aa-7b94-4597-999b-bbcd9fbd0ab4 | note | ACTION (Hold, Monitor, Witness): H
10646e4c-1685-4e3b-abf2-0741362d9e94 | note | Detail: Cesspit, Manhole and Pipe shall comply with relevant AT/TDM standards
37bd7cc1-9405-4585-998e-7058b1ec2d3b | note | Frequency: Prior to commencement.
9c765384-69d7-48cf-bd28-758bfed6b9ea | note | Inspection / Test Method: Document Review, Visual Inspection
f182d5f3-8bb9-4321-af56-d7def8ac885d | note | Conformance Criteria: Pipe shall be Check for freshly formed pipes and return if required 1) DN225 Class 4 RCRRJ pipes AS/NZS 4058 2). All Concrete RCRRJ pipes to be fitted with Rubber rings 3). Pipes shall have product certification (ISO Type 5) to AS/NZS 4058 Prefabricated concrete Manhole shall be in accordance with TDM Standards & AC COP
627766d3-7c57-4964-a80a-4934555dab68 | note | Records: Manufacturers Data Sheets, Delivery Dockets
| signoff | HOLD POINT
| checkpoint | 6 Locate Existing Services by Hand Digging / Hydro Vac
64ba33aa-e928-4ff0-b2c7-f439a3552a8d | note | ACTION (Hold, Monitor, Witness): H
fc6d371b-76fa-4443-86ae-653bb0081dcb | note | Detail: Ensure all services conflicting with the line of trench have been exposed by hand digging.
5ada89b3-0b90-4337-a51f-44446b438923 | note | Frequency: Prior to commencement.
4824ee37-6b11-40f2-9502-e0146814d21a | note | Inspection / Test Method: Potholing / Survey
e791beb7-1d74-42fc-8b20-96d379f82104 | note | Conformance Criteria: All conflicts have been located. New services and / or conflicts to be advised to Project Manager.
e51a9da6-1e59-4c67-a6b5-6b81becddf47 | note | Records: As-built Drawings. Doc. Review
| signoff | HOLD POINT
| checkpoint | 7 Trenching & Excavation
e117d45b-9ab3-4a4f-bc55-8b083784024f | note | ACTION (Hold, Monitor, Witness): H
61c5ea18-bb74-45f1-8e5d-09f5590fff0e | note | Detail: Excavation methodology
3c80169a-af0c-44ba-a992-995b00f30a94 | note | Frequency: Daily
303ca3e1-d78c-4025-80e7-5a4e61650d71 | note | Inspection / Test Method: Prestart review
5b8633f8-ff71-427a-8768-4843cdfdfd4f | note | Conformance Criteria: The excavation, benching and shoring requirements shall be in accordance with Worksafe Excavation safety guidelines (2016)
996c164e-563c-4cd4-a6e1-0b7df26bd31e | note | Records: Prestart RCP
| signoff | HOLD POINT
| checkpoint | 7.1 Trenching & Excavation
cb1fb5af-932f-4383-b65f-82ee828c85d8 | note | ACTION (Hold, Monitor, Witness): M
61926801-8edc-42e4-a0cb-aa14935a1a44 | note | Detail: Trench Profile - Width
b3cfb3bd-9894-494f-a7f7-b879f5cca780 | note | Frequency: Daily / as trenching takes place. Different depth methodology
dd0a26b1-3db1-4517-b9de-74cec24bf6c1 | note | Inspection / Test Method: Visual Inspection, Excavation methodology
c1b596e8-b0b3-4341-a379-d0eb54ddc253 | note | Conformance Criteria: Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing
95de32d8-cc8f-4988-9c7c-bcb6421c7658 | note | Records: Construction Photos
| checkpoint | 7.2 Trenching & Excavation
2db21365-c18a-4ef8-8787-45c98fd363f1 | note | ACTION (Hold, Monitor, Witness): W
8c224eab-db92-4249-b1eb-00baf326438b | note | Detail: Trench Profile - Depth
971dd20f-991e-4956-838e-5902ea126f9d | note | Frequency: Daily / as trenching takes place.
12ac1402-0a15-4389-a503-e7971b664bb7 | note | Inspection / Test Method: Visual Inspection, Measurement
f3136228-f32a-44ae-9594-ea5b9ef5c59c | note | Conformance Criteria: Trench depth varies according to longsection and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings
fb7457ce-9488-495f-be08-8dba93cd3080 | note | Records: FH Drainage Line Record / Construction Photos
| checkpoint | 8 Bedding for Concrete Pipe Laying & Manhole & Cesspit
401f6e88-98ec-4b83-b98a-36776ad8654c | note | ACTION (Hold, Monitor, Witness): W
e01446e4-c773-45f7-b9b5-d64a3531b011 | note | Detail: Placing and compaction of Bedding Material.
144feafe-345a-492f-8a16-e7816e44e193 | note | Frequency: Inspected continuously during placing and compaction of Bedding Material.
ac6a6834-b2b2-498f-b280-25fabc0f6f98 | note | Inspection / Test Method: Visual Inspection
393291df-a25b-4639-ba85-5b1f5309f2b0 | note | Conformance Criteria: Bedding & Pipe surround material to be GAP7 or GAP 20 (Stevenson Quarry) or alternate material that complies with AS/NZS 3725
e5216534-5924-4500-bbba-c5d64dc5e171 | note | Records: FH Drainage Line Record / Construction Photos
| checkpoint | 9 Pipe Position Tolerance
ce19ce58-9d8e-45c9-88c3-159be2684391 | note | ACTION (Hold, Monitor, Witness): M
0716ece8-22cb-424b-853f-192e8cf0e3d9 | note | Frequency: At any point of pipe
69825e5c-a4bb-4f3f-b023-12fc6add586a | note | Conformance Criteria: Position tolerance for pipe laying at any point along the length of the installation shall be within ±30 mm from the specified design.
b82ff2fa-18a3-40eb-9e4a-b0510b87d18b | note | Records: FH Drainage Line Record, Survey Data.
| checkpoint | 10 Trench Backfill - Placing & Compacting
8c35da22-4bc5-45ff-b12c-cd86abd53ef8 | note | ACTION (Hold, Monitor, Witness): M
375db5b8-41dc-40d6-aead-1ccd835a4153 | note | Detail: Placing and compacting of Trench Backfill Material
5e188385-0073-47c0-bcc0-da68bfd713e9 | note | Frequency: Throughout Trench Backfilling operation.
836bd108-2f21-46b3-8ce6-7217bb7a8dc2 | note | Inspection / Test Method: Visual Inspection
4809184b-908c-475d-958f-5cdae77c70d3 | note | Conformance Criteria: Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm
992e92b1-9212-4056-9f50-b0166319a656 | note | Records: Construction Photos
| checkpoint | 11 As-Built Drawings
a5cc2192-9d03-42c9-b6e2-31e7e2b43c91 | note | ACTION (Hold, Monitor, Witness): W
744a17ef-64ee-49bd-b5ac-fcfe8cd2e6a2 | note | Detail: Red pen marked-up As-Builts of every 'Issued for Construction' AT drawings
5d944afd-f522-43b1-a5fd-02c11ff39c46 | note | Frequency: Final As-Built Drawings to be completed within three months of the construction completion of the asset or infrastructure.
a026919c-966a-42b6-863b-ec7062c3dc71 | note | Inspection / Test Method: Drawings / Visual Inspection
fe16844d-a82e-4644-9884-3ad7f0ebd311 | note | Conformance Criteria: As Built and GIS Data
db8f1524-6235-4117-90da-099fc5cba40c | note | Records: Redline As-Built Drawings, scanned as .pdf files.
| checkpoint | ITP Completion
9ef11f3f-3931-4817-a0df-2adf354929c9 | textbox | QA checked By Quality Manager:
6d394280-5c5b-4c4a-9354-4afef2eb2f77 | textbox | Accepted By Engineers Rep:
| checklist | QA Photos |  | QA Photos | 2f5e868a-dbe1-470b-a4fa-ea5658af03f4
| checkpoint | Add photos here:
| checklist | Raleigh Road Bus Lane - ITP - Civil Works | itp | ITP - Civil Works | df437c2d-f1c0-441a-835b-c89606177480
| section | Survey - Set out
| checkpoint | 1 - Site Set out
5780e91b-f572-533a-a67f-cf240fd28381 | note | VERIFICATION ACTIVITY: Surveyor
af44c257-96ff-5896-b754-611fdfdbbe36 | note | METHODS OR REFERENCE: Surveyor
12d43dba-ddfc-5f05-acdd-c6312bfc653e | note | FREQUENCY: Everysite
fc7f4a0b-ea03-56ba-a15f-b76eef817896 | note | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 2D model provided by designers. Site set out inspected with designers/MSQA and client ensure criterea is acceptable.
e83b6bc3-a349-516b-aeef-af6a2caf6bd8 | note | HOLD POINT: Inprocess Inspection
dd23215a-7d15-5b37-a012-f4259286d6cd | note | RECORDS: Onsite records/photos
9313fdde-4bdd-5101-bab7-045156166dcd | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Kerb and Channel
| checkpoint | 2 - Kerb & Channel
b5b5a87d-3ca9-5ecc-95d4-0f359c46113b | note | VERIFICATION ACTIVITY: QA FORM
1f385422-0d44-5485-b1d2-7267ab317f9f | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
9abbb252-3dd0-5fa8-a9aa-1b77d650b957 | note | FREQUENCY: Everysite
291730da-da81-51e8-903d-38cd7f48e13e | note | ACCEPTANCE CRITERIA: Kerb & Channel to be laid using precast hand-laid on compacted minimum 300mm GAP65 sub base with CIV > 25. Concrete 20MPa @28 Days
f8ad24af-f31b-5079-8fd5-300028db2e2a | note | HOLD POINT: Inprocess Inspection
fea80d6d-f5bf-5893-9478-0ff89cfcf63f | note | RECORDS: Clegg Sheet, photos. Concrete Plant Docket
1d2c9d6c-4914-58fa-a1ca-6560640cd897 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3 - Channel Level
49211669-57f0-577a-892e-c1184470f355 | note | VERIFICATION ACTIVITY: QA FORM
85fce96c-f8bc-5530-8cf0-f204f89b70b2 | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
0e2e9ebb-284c-5bcf-9c00-fbaa6f772c0a | note | FREQUENCY: Everysite
5d29ba52-afd3-5cc8-b493-f2d4df259a14 | note | ACCEPTANCE CRITERIA: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match new road level. Channel grade to follow long-sections provided in IFC set. Channel to be trowel finish.
71b5d9da-e88a-58d7-8cda-851761b17e95 | note | HOLD POINT: Inprocess Inspection
03ca83e1-4101-5b1e-a9b2-7e90d0bcc4f1 | note | RECORDS: FH channel QA sheet/photos
34fc0b49-175b-5695-90dd-8688d3c09e18 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Footpath & Pram Crossing
| checkpoint | 4 - Concrete Footpaths
8abc5c7e-2995-5115-9ad9-383fe817d6c3 | note | VERIFICATION ACTIVITY: QA FORM
89e8400a-2c07-5823-86a8-b479be6af29b | note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
ffeeeee0-d09a-5298-922b-09000398fbe7 | note | FREQUENCY: 10m Intervals
fc49297d-6eab-5626-ac4a-c2a7652bb4e5 | note | ACCEPTANCE CRITERIA: Basecourse - 100mm Gap40 min. thickness
ddd27802-75ac-5e36-9a7f-8a82efa862c4 | note | ○ Clegg CIV > 12 (frequency every 3m or minimum 4 spots per pour - excluding PX)
1d1277ca-f6df-5f70-a213-48dc613f00bf | note | ○ Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 black oxide with broom finish
78e49866-63c5-559a-b951-c56ae1c9647d | note | HOLD POINT: Inprocess Inspection
eb0926eb-2085-59c5-a9cd-6d96158fc1f9 | note | RECORDS: Clegg Sheet, photos. Concrete Plant Docket
8dd58a5d-7d07-5e55-a618-dc55f118b5fe | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 5 - Pram Crossing
77006c28-7d3e-5323-b3e1-d66be90a6ebf | note | VERIFICATION ACTIVITY: QA FORM
71625a49-e5ba-5405-9850-25197285f512 | note | METHODS OR REFERENCE: TDM Technical Standards - FP006
d24c5cd6-5985-5d2d-b0f8-a4f38bf4bc69 | note | FREQUENCY: Each Crossing
c23dcf4a-7871-5725-9200-bd43a1003720 | note | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
d1d4ce2e-c7d4-51dd-90e3-be55ab3a4350 | note | ○ Tactiles Directional & warning - 40mm; 600mm flares;width as per design;
e8eb6f60-47c9-5150-b910-c78d50fb637c | note | ○ Slope no greater than 1:12 where practicably possible
23783ca8-77ef-53f7-90ee-58fa26ac3561 | note | ○ Clegg CIV > 12
1dee669e-14ba-5dee-a153-450341d5f47c | note | HOLD POINT: Inprocess Inspection
ad0f410e-671c-5a5f-ad92-ae4f118b4ca6 | note | RECORDS: Photos
32348bde-4910-5c59-87f8-c10913a9ff64 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 6 - Service Covers and Street Furniture
28807e46-d81e-5ffa-bcfb-38a665310a9f | note | VERIFICATION ACTIVITY: Visual
96c7abe4-b1f3-5314-93e5-9c8c0e7ce368 | note | METHODS OR REFERENCE: AT Contract Specification 14000
50e357ba-35f9-5272-99c4-b40d53b0ddca | note | FREQUENCY: Everysite
84e25196-e0c3-5d84-9c19-68a45baa4cbe | note | ACCEPTANCE CRITERIA: Service covers to be adjusted to new surface levels. Ensure no damage is done to street furniture in the vicinity while carrying out works.
ec70341b-990c-56ff-9377-82bd56588182 | note | HOLD POINT: Inprocess Inspection
900e3aa0-6c90-5741-9920-caa5b8b3bfc1 | note | RECORDS: Nil
0745cbc6-1157-5299-8530-5ae4ef9b7fc0 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Tactile indicators
| checkpoint | 7 - Tactiles
fb1763b2-ca10-558a-acd5-748b4e63e844 | note | VERIFICATION ACTIVITY: Visual
d8cb3278-2e8e-5817-8450-0e0b1eb4dbbd | note | METHODS OR REFERENCE: TDM Technical Standards - FP0010
dbd63b71-e5bb-5b26-bc6e-a59f9c9a357a | note | FREQUENCY: Each PX
72d85f1f-d4e1-530a-b2e5-f06547ac4f07 | note | ACCEPTANCE CRITERIA: Tile set out position to be agreed with ATOC and Engineer. Warning TGSI tiles should have 100mm concrete haunching underneath
25df7e60-9a76-521e-8ccb-9a910536dc61 | note | HOLD POINT: Inprocess Inspection, Measurement
514275a8-0c5a-5f5b-bb04-804d5a0c2350 | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
3a615292-9fb2-5394-a7ce-22801681528d | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 8 - Tactiles
fc78d3bd-4b13-5d26-b13a-c7201644d6c1 | note | VERIFICATION ACTIVITY: Visual
34424b63-c397-5f8e-9dc0-87aeaa81725a | note | METHODS OR REFERENCE: NZTA RTS Guidelines for facilities for blind and vision impared pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
08442732-5323-528a-88d8-ecfd47399924 | note | FREQUENCY: Everysite
e50deda7-c0e1-5ead-9023-b1053c6fec31 | note | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
cd6316b4-b1f6-5487-9c4d-19cd760d0ac6 | note | HOLD POINT: Inprocess Inspection
95784465-adb3-5760-aa5b-637ca432e219 | note | RECORDS: Photos
2476bba6-e19e-58c4-b6d8-0282a4404b77 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 9 - Tactiles
c757062f-d45b-5b32-a171-b4677bbdd8cb | note | VERIFICATION ACTIVITY: Visual
719babe7-92ea-58f1-b159-a1c8ab187526 | note | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
e1c5f5d4-d174-5552-8bbf-801a74015d09 | note | FREQUENCY: Everysite
60727e2d-7017-5a29-bd41-9ff40574fae9 | note | ACCEPTANCE CRITERIA: Edge of warning indicators to set back 300mm from the face of the kerb or lane.
6beda5fb-c2ba-5e8d-8bcd-f2cf0640e2a4 | note | HOLD POINT: Inprocess Inspection
839c8351-545f-58f1-adfc-6585609ba47c | note | RECORDS: Photos
a8eb01d5-7c5d-5e78-93aa-10bdb367f99c | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Bus Shelter Pads (Minor 1300 & Minor 1500)
| checkpoint | 10 - Bus Shelter Pads
1e0f4fc1-7536-5288-afb9-52da46ac24ab | note | VERIFICATION ACTIVITY: Visual
d83bd4a0-9c33-5afe-b633-3ef97234d074 | note | METHODS OR REFERENCE: "Plumb Consultants" drawings Sheet S01 & S03 as per WSP IFC drawings sheet C121 & C123 revision 1
6f5c8493-f145-525b-b146-5dd0497fe292 | note | FREQUENCY: Everysite
204dfec0-8604-545d-909d-7a67da75d229 | note | ACCEPTANCE CRITERIA: 50-100mm basecourse. Clegg value acceptance criteria CIV>12.
3f253a20-3eb8-534e-88ca-f4c99e25caa9 | note | HOLD POINT: Inprocess Inspection
856ab0b0-4c4a-5442-b035-64444552edec | note | RECORDS: Clegg Sheet, photos. Concrete Plant Docket
dfa24fb1-8218-5d77-99ec-5bf1a9e63f8b | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 11 - Bus Shelter Pads
236458dc-6b1b-5e83-bbdc-1d3bc76ab811 | note | VERIFICATION ACTIVITY: Visual
5e057a6f-2020-577d-868e-182d778445fc | note | METHODS OR REFERENCE: "Plumb Consultants" drawings Sheet S01 & S03 as per WSP IFC drawings sheet C121 & C123 revision 1
e128f3c4-1236-59dc-ae3e-40b4cffd2bbd | note | FREQUENCY: Everysite
1c44e274-6667-5baf-97b4-603d5aa46d41 | note | ACCEPTANCE CRITERIA: 200mm thick 20MPa concrete with 4kg/m3 black oxide & broom finish.
50c38a66-c7da-52fb-9241-5283f6143ab3 | note | HOLD POINT: Inprocess Inspection
348f61a6-9c93-5c9d-9e5e-3bc6830d5403 | note | RECORDS: Clegg Sheet, photos. Concrete Plant Docket
fc784824-18c3-53f0-852c-db875ab1c2e9 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 12 - Bus Shelter Pads
d6d5eff8-c5e9-5408-b4fa-54f2b72bafa0 | note | VERIFICATION ACTIVITY: Visual
435b871f-0ccc-5ab4-8392-5c3cb5bf9dbb | note | METHODS OR REFERENCE: "Plumb Consultants" drawings Sheet S01 & S03 as per WSP IFC drawings sheet C121 & C123 revision 1
ebdbccbd-ea87-54b9-8967-f6d488a04f33 | note | FREQUENCY: Everysite
0f872fe3-d878-57f4-b054-88024e2fceb3 | note | ACCEPTANCE CRITERIA: Minor 1500 - 2 x layers of 665mesh
c615b2ce-062a-5734-ad86-3f7201926788 | note | ○ Minor 1300 - 2 x layers of 663 mesh
7e4787e5-1f1c-5add-8b08-b53e9dda3d18 | note | ○ 50mm top cover.
99a4aacc-03ff-5ea3-baa5-8645c5dc5559 | note | ○ 75mm bottom cover.
f7dcc4d4-ef98-5778-b5c9-0a9583c61748 | note | HOLD POINT: Inprocess Inspection
e61e5936-53b2-5089-85ab-406a2df704a4 | note | RECORDS: Clegg Sheet, photos. Concrete Plant Docket
fc3355c6-9d4f-514f-9cb0-b37d8f5e14a2 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Retaining Wall
| checkpoint | 13 - Timber Retaining Wall
b26d14a6-a7c2-5183-a82c-202b4dca4f28 | note | VERIFICATION ACTIVITY: Visual
8e4ef888-51a8-595b-83e8-0ea2a32a2a5d | note | METHODS OR REFERENCE: TDM ST0004 - Version A Timber Retaining Wall Detail
d75e1a94-0829-592b-9f3e-af167667cfc3 | note | FREQUENCY: Everysite
47ff18b3-0e88-533a-92c4-516ed03f13ad | note | ACCEPTANCE CRITERIA: 125 x 125 H5 Timber Posts @ 1.5m centres installed with 20MPA concrete. Concrete footing to be 325mm diametre.
3f80bf1b-862a-56b6-935a-c020d4663cef | note | ○ 150 x 50 RS Tanalised H5 Timber Rails. Provide 5-10mm gap between rails
40c800f7-7229-5970-b835-dc4c3562e083 | note | ○ Retaining wall slope to be 10:1 grade.
985cb284-26a4-5f27-a188-addaa67b001e | note | ○ Maximum height of wall = 1499mm.
8a0649fb-c202-5ea0-bbe3-9572f22faa6f | note | ○ Minimum embedded depth of post to be same as exposed height unless less than 300mm, then depth = 300mm.
c4276e36-84d8-5ebc-89d5-75145b63de68 | note | HOLD POINT: Inprocess Inspection
b81bbe96-e435-5a0a-8277-b3872cd87527 | note | RECORDS: Photos, Material Dockets, Dimension checks
8a824c24-ca3b-54c9-b3ed-7352ac74cbb9 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Grass Berm
| checkpoint | 14 - Grass Berms
799951ab-0803-5980-b1f5-2f72b7567d7c | note | VERIFICATION ACTIVITY: Visual
ff2d8e0b-3ef2-506d-b56f-79cff4efb37b | note | METHODS OR REFERENCE: ATCOP Section 12 Footpaths and Pedestrian Facilities
be1a610a-73e6-5b1b-a8d8-aab77296d633 | note | FREQUENCY: Everysite
83d76c41-6675-5d63-a512-c01813901b94 | note | ACCEPTANCE CRITERIA: 100mm thick layer of compacted approved quality topsoil, free of weeds and stones and sowed with grass seeds.
787a6cb0-5a06-5498-86eb-a8aeb487164b | note | HOLD POINT: Inprocess Inspection
45e670ff-196e-56aa-b49f-2ea4e228b5cf | note | RECORDS: Photos
6271a331-29e4-5408-8205-94c458766373 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Asbuilts
| checkpoint | 15 - As built information
57f846d0-16c7-50a4-b03e-32b603d1525e | note | VERIFICATION ACTIVITY: Drawings
2c875407-b0dd-50ef-9924-8727a929f578 | note | FREQUENCY: Every Site
0f707dc3-5ff8-5a61-a71b-d9b1a7bdf7c5 | note | ACCEPTANCE CRITERIA: As built drawings
b36b2d6b-2cd5-5dd2-bdbf-23e13246cded | note | HOLD POINT: In Process Inspection
bdf5812f-9ba7-5d60-a308-c662467e369f | note | RECORDS: Asbuilt records
d46e04df-57bc-57ff-a61c-77d07af044b0 | note | ONSITE RESPONSIBILITY: Site Engineer & PM
| checkpoint | 16 - RAMM DATA
44bec1c1-4d15-5c58-a9fa-af96f342cf88 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
665a306c-9bb5-599f-9bf5-635f583ae3c4 | note | FREQUENCY: Every Site
a03dbbec-e7df-5a1b-8e4a-49a29ffe06a8 | note | ACCEPTANCE CRITERIA: RAMM SHEET
1d7d134c-276a-5693-bacb-e11b6b2f9e40 | note | HOLD POINT: In Process Inspection
f70790af-f514-5a99-88dd-f3a773d85929 | note | RECORDS: RAMM Sheet
efa14c40-9b67-5d50-bc0a-23ba2cff6868 | note | ONSITE RESPONSIBILITY: Site Engineer & PM
| section | ITP APPROVAL
| checkpoint | ITP Approval
f97f0961-07a5-589a-b0bd-bcd20c41149e | note | Prepared by: Joseph John
ac59d668-85d8-50dd-8145-0075478c04fe | note | Approving Delegate: Denny Jeong
| checklist | Raleigh Road Bus Lane - ITP - Traffic Signal Ducting and Pole Erection | itp | ITP - Traffic Signal Ducting and Pole Erection | 11301eed-9e72-45ce-a4c6-7dd12f183f42
| checkpoint | 1 - Permits
08fdf723-65fe-5abf-aded-45d08e3df7d8 | note | H
22dce09b-e072-5323-adcf-e7ba0464eb59 | note | Detail - Obtain Permits
0c51ee88-663d-5d4e-937e-b58ca73afa0e | note | Frequency - As required
b4578e26-b5dc-50f1-a99d-cb0d131e373e | note | Inspection / Test Method - Document Review
ba14c9a6-b8e2-5340-9222-d6d479d1014f | note | Conformance Criteria - Authorisation to work, dig permit and service provider permits
d73c2ef0-fd37-5b81-9f40-3c64b172e979 | note | Records - This ITP signed
18df3715-7e7c-57a6-ae1b-0469ec27d9f1 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Design
673575cc-3f44-5baf-9877-e7d99baa59f8 | note | H
38702140-280c-59b8-a6cd-9df14d513fb7 | note | Detail - Ensure that Design is approved and Drawings are of the latest revision
f9995550-533b-5b72-980c-1057339133c3 | note | Frequency - Prior to commencement
e393a212-7f3a-5064-80d5-a3c480a4bb6b | note | Inspection / Test Method - Document Review
0228623a-99d2-5ff6-bc3a-451ec0210b51 | note | Records - Check Drawing Register
9c12e0ac-a3ae-5ea3-a169-f2559b95eda5 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.1 - Survey Setout
f5bc9286-3846-523c-8051-94777f97e608 | note | H
48da0a5f-d013-59e2-8d03-ea96ea8702fe | note | Detail - Setout ducting alignment and EOS FL depths. Setout and mark all known services along the cable corridor.
e03a2221-1aeb-596b-b222-77a80aaf9b70 | note | Frequency - Prior to commencement
13a6e7cc-87af-59d4-b74b-c93ba831d29a | note | Inspection / Test Method - Survey
bcbcd422-fa71-5a2d-9546-ac5bccd7538a | note | Conformance Criteria - Consistency with Drawings and Specifiactions
1358fece-0b04-5442-90c4-e31d42afc742 | note | Records - Survey Records
96c053b0-f269-5fff-9960-47540e49039e | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 -
1fc1aa87-129f-55e5-862f-9e969803dbc4 | note | H
1fa8d1b0-3027-5af8-95e5-40cf65fa72e8 | note | Detail - Confirm with Engineer/ATOC on site the exact locations of poles/controller/tactiles indicators.
a31d7f4e-31ae-5047-8fa6-90a056723cae | note | Frequency - Prior to installation
c2c0480d-8f73-5934-a13c-55463472d5f2 | note | Inspection / Test Method - Visual Inspection
da2bb6f0-4510-559b-b10d-30f8ac363174 | note | Conformance Criteria - Consistency with Drawings and Specifiactions & sign-off by Engineer/ATOC.
8e4a85ca-eb61-5fa5-a5f4-6184c142f9e1 | note | Records - Photos / Engineers approval documentation
16925830-e3d1-5a40-afc0-5d0c7d269724 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Locate existing services by hand digging/ hydrovac
9a1b97d0-8116-5f91-bd9e-1eeee9c32f49 | note | W
20468b46-38d1-5ac1-9195-1f81fd97c56c | note | Detail - Ensure all services conflicting with the line of trench has been exposed by hand digging or hydro excavation
29f54425-c183-55f6-98f8-bdc4017501f3 | note | Frequency - Prior to Installation
bd376650-23af-541c-ae0c-8307da876422 | note | Inspection / Test Method - Potholing
4b0321f8-b7c9-5bb0-af10-6892a87661fc | note | Conformance Criteria - All conflicts have been located and survey as built recorded
f4a7c793-ebb0-58b7-8bc8-1fcbc95f364b | note | Records - Digging/Excavating Control Checklist
5e29f380-13ba-5a7c-821f-8ae03b9322da | note | FH Initials - Site Engineer
| checkpoint | 5.1 - Material Compliance
5b388a2a-82ef-563a-ab36-8e23cab31045 | note | H
212b236b-f0d3-54d8-8f62-c9854b9eaa9e | note | Detail - Ensure duct pipes and poles are as per drawings and specification
74030a49-3d24-525e-918b-c5c838052f54 | note | Frequency - Upon delivery to site
0dcd5eb0-e8c3-5a18-9b6c-3e8006091629 | note | Inspection / Test Method - Ensure delivery docket matches materials
83497635-b031-5d3b-8010-27f2e2de0f3b | note | Records - Delivery Docket
2fce48d8-239d-5714-86b4-346f91cf7679 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.2 -
848606c5-b8ad-5207-be6e-3fe35739b138 | note | H
e7f803eb-9c69-5d5b-9c5b-3c9c1572dd48 | note | Detail - Ensure all concrete used is 20MPa mix for pole footings and concrete aprons around traffic assets.
d93b63b1-c567-5a39-932e-4b00c71c58d2 | note | Frequency - Upon delivery to site
e2f504fd-e041-599a-9639-1f1ca78f250b | note | Inspection / Test Method - Ensure delivery docket matches materials
596226c7-0949-5c12-af8a-4bb72ea86223 | note | Records - Delivery Docket
8c871b48-a9d2-58f6-9783-b9093685d9fe | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.1 - Trenching
4a8818e6-eef3-526e-a483-4faf1151f024 | note | H
28a5eaf2-6085-551d-80d3-025bd44a3028 | note | Detail - Inspect trench profile to ensure walls vertical, widths is 600mm max (two ducts). Ensure trench depth is sufficient to provide 600mm cover to duct when under berm/FP and 900mm cover under carriageway. Concrete capping detail to be followed where reduced cover is required due to existing services.
fdb542e2-8e84-5319-b4e7-c684b30856e3 | note | Frequency - 10m Intervals
e3d6c92c-78ec-5a6f-b7fc-6c152d439887 | note | Inspection / Test Method - Visual Inspection
3e8c30b1-d3cc-54fa-bafd-b69970ce197b | note | Conformance Criteria - Consistency with Drawings and Specifiactions. Concrete capping detail - WSP IFC Drawings Sheet C126.
f75aeee5-4193-5f9b-bb51-6f0ca5016d3e | note | Records - Photos
051fd79a-abbf-5dd3-abc0-8790eb074cd7 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.2 -
a40009fc-c9de-5b33-a86f-f83b3af3f9d3 | note | H
2624035d-aa31-5bfe-8368-907f69554c97 | note | Detail - Ensure trench is cut in a manner that will ensure ducts are layed at correct depths,grades and alignment as per design dwgs
86b2f273-ef3d-5ca0-95be-38e102b72c10 | note | Frequency - 10m Intervals
a057f626-9b75-5fdf-93fa-adf1dacfd6e0 | note | Inspection / Test Method - Measure
8567b637-3fcf-5c6a-a4d8-5af26e6ff835 | note | Conformance Criteria - Ensure trench alignment and levels match the design drawings
7dd50687-14e5-51d5-90b8-fb1247539a1b | note | Records - Dipsheet & Photos
5d0ea9d6-a521-542e-b727-0b6934930f57 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.3 -
5f1d80db-fbdb-5a28-b046-e590468c90f9 | note | H
2604a86a-55e8-5073-9f01-1601d61ab8ba | note | Detail - The trench on the carriageway should be filled with Gap40 and compacted and on top reinstated with AC14 or similar & match existing asphalt thickness. The finished level to be match with existing road level
280fc6f3-a78d-5b72-a0f8-a516107ee96e | note | Frequency - Each Site
36d8196a-af13-5e93-8dfa-beea35b573e8 | note | Inspection / Test Method - Visual Inspection
a8d3cd46-5e7e-590c-8e94-77f9d9328cf0 | note | Conformance Criteria - Reinstatement as per designer acceptance
d4ec64a8-8a80-5f4a-ac73-45d6f06a5701 | note | Records - Docket and photos
6cd7e876-41f6-5539-a548-164047de7acc | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.1 - Duct Installation
22476336-f233-5ee8-9cd8-cf39f7621481 | note | W
ae585ab2-c0a7-5b09-9dcb-5ce1d1e1013e | note | Detail - Place proposed ducts in locations where required. Draw wire tapes required and cap ducts where required to prevent ingress of material into duct.
73d15c05-4a75-5f64-9e89-074af47596cd | note | Frequency - Prior to Installation
fad8418f-967a-5718-8990-0d9569e72a9a | note | Inspection / Test Method - Visual inspection
ca34bfdd-c548-59ef-9bd3-afc88d1a7513 | note | Conformance Criteria - Consistency with Drawings and Specifiactions
81d63cfa-bd1a-5ed3-a6f9-b3804c4e3b06 | note | Records - Photos
644347c2-014a-5001-a2e1-0b4a262dac82 | note | FH Initials - Site Engineer
| checkpoint | 7.2 -
eebd9b58-56c1-5a5d-9246-233fc66d5046 | note | H
f050b958-3d98-5587-a9fc-0f6ee80b3c3a | note | Detail - Ensure minimum spacing of ducts requirements are met as per design dwgs and ATCop min spacing tables
7917d9de-1724-5503-afe7-d9462e8693f9 | note | Frequency - 10m Intervals
44ca65e8-efe0-5bc2-96a0-f928f484c4f4 | note | Inspection / Test Method - Visual inspection
200f49b6-3bf3-5588-abfd-0d9a30c5f8b0 | note | Conformance Criteria - Consistency with Drawings and Specifiactions
a52a898d-97d2-561b-a725-2f8b5dcdc27f | note | Records - Photos
35d5d2f6-3f85-5de6-b24d-669e801a555f | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.3 -
8e43d268-e90f-5532-8c86-cfa697aae47c | note | H
77762d46-43c7-5049-aaf4-89c86dbe0c40 | note | Detail - Asbuilt Survey
3698ed5e-ae2e-5721-b9b4-a9ff4610d201 | note | Frequency - 20m Intervals
b088ccb3-1411-50e4-b8f6-c50bb556d157 | note | Inspection / Test Method - Visual inspection
ed9cc7a6-a223-52a1-a85f-3a3c171ba93f | note | Conformance Criteria - Consistency with Drawings and Specifiactions
16ee4dcd-a1a4-541b-a163-9d8291dccbe4 | note | Records - Survey Records
65d1b8f6-5bdd-50ea-b3b2-f3977e2e262a | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8 - Bedding
5174c6f0-44d2-5274-8bf8-75129824f34f | note | H
6b0ff03c-a7b2-5442-af28-c4a8bd679646 | note | Detail - Lay min. 100mm gap20 or finer for bedding and haunching
b0bac3c0-9efc-5bae-989b-609f052ba61e | note | Frequency - 10m Intervals
d261bba5-f922-5d56-9517-887e486b9ba0 | note | Inspection / Test Method - Visual inspection
cd07df62-6359-5388-8c86-16c6888970d8 | note | Conformance Criteria - Consistency with Drawings and Specifiactions
69fc6d64-82a2-5df3-935c-8690c6f15ed7 | note | Records - Photos
602280f8-5735-52a8-81e3-cd9c165ab7eb | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Warning Tape
882fd27b-ec3e-5c21-a2ca-21164f9ed30b | note | H
adce2771-819a-508f-b88d-7cf38f82233b | note | Detail - Ensure warning tape gets installed 300mm above duct pipe for all new ducting lines.
5823625f-4256-5ee6-961b-35c9c4fc7ad6 | note | Frequency - 10m Intervals
e559498c-368e-5b2f-a012-78e0083daf43 | note | Inspection / Test Method - Visual inspection
c305ff5a-8ac9-5b4d-95a2-ab8ecd2cbcbf | note | Conformance Criteria - Consistency with Drawings and Specifiactions
e770e7ef-83a5-5cd7-8f32-94ee1ed8ed02 | note | Records - Photos
59f3fe38-8889-5ad6-beb0-4238d001df0a | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10.1 - Traffic signal pole erection
c4a5b039-3319-53ec-9732-1a4a371ec5e6 | note | H
d8a5ce85-6c1c-5c1b-a78a-5be7bd1808bd | note | Detail - Ensure Design engineer & ATOC inspect pole locations prior to proceeding
89bb1f89-89a8-5e9c-8489-8b0289201a9a | note | Frequency - Per pole
b2d5da08-36b2-59b2-81e4-9e3c2e38bf3f | note | Inspection / Test Method - Visual Inspection
c2840c67-d2a2-53bc-b552-41fd27861f5d | note | Conformance Criteria - Sign off by design engineer
019fc5fc-3cb7-59b7-af32-abeb39550f5c | note | Records - Engineer sign off
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10.2 -
bae6691f-40c7-5759-9d60-00917d5e13b8 | note | H
78e9d750-e7e3-59f9-9852-7dfc0f92980a | note | Detail - Ensure foundation hole excavation is as per design with required depths and widths
818664d7-2d83-58da-abab-222a226cbaed | note | Frequency - Per pole
9924c172-5d5d-5963-9581-393d25ac7242 | note | Inspection / Test Method - Measure
49293427-33b6-5e37-b711-3c532a900747 | note | Conformance Criteria - Consistency with Drawings and Specifiactions
e1cd1650-dea5-574f-b8b9-1a258233220c | note | Records - Dipsheet & Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10.3 -
0b8099d1-e59a-54c5-9726-d5a0e7dd0193 | note | H
d102fb6c-a409-5167-8a64-6948c193e6a9 | note | Detail - Ensure Poles are plumb and within design tolerances
7d5a8bf0-e7a0-57be-b873-b897e984f086 | note | Frequency - Per pole
7abf4018-5eb0-53a8-8b68-1809845c6010 | note | Inspection / Test Method - Visual Inspection
d51f8097-9795-5640-a740-96a7293e3b21 | note | Conformance Criteria - Consistency with Drawings and Specifiactions
e5004191-c08a-5b9e-a37c-6d67b2d6ee7e | note | Records - Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 11 - As-builts & C&I Diagram
b79084fe-8110-54ac-97c5-a0b2ebc50a68 | note | H
30e44089-1e72-52a0-8fcd-3594642fe50e | note | Detail - As-built as per ATOC requirements
e58081e0-862d-5e42-9eb1-12ddf1912684 | note | Frequency - At the completion of the Lot of work
2c8cd152-6878-5121-8b76-09ff714e7971 | note | Inspection / Test Method - Drawings
c4dbc68e-63b2-543c-938c-6ffa6a81bca8 | note | Conformance Criteria - As-built as per ATOC requirements
ca93d823-25c1-57ea-a18b-51f67580523b | note | Records - Asbuilt Drawing
c3dfe3c0-4280-5b38-a36b-9f7b61a3901d | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checklist | Richardson Road, Mount Roskill - ITP - Enabling Works - Footpath, Kerb and channel | itp | ITP - Enabling Works - Footpath, Kerb and channel | 99a654fd-cf54-471b-8fba-8cf823df0e2f
| section | Site Set Out
| checkpoint | 1 - Site Set out
26a9fb88-23a8-598d-9e62-85bd90f7da11 | note | VERIFICATION ACTIVITY: Surveyor
994bb1a7-ee82-5a2e-bd66-68bec005f165 | note | METHODS OR REFERENCE: Surveyor
f25d065a-45f5-5bd7-ad52-f1e680b61a18 | note | FREQUENCY: Everysite
4b80b4d5-85d2-5645-b537-f7c3539568a2 | note | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criterea is acceptable.
fd100338-9a17-55f6-ae75-3bf1dc6b2d8b | note | HOLD POINT: Mandatory HOLD POINT -
c3b8b5d8-15ec-5dc1-b30c-bc1d8e10d094 | note | RECORDS: Onsite records/photos
00359ea3-a587-5619-b223-e5b48f1461be | note | ONSITE RESPONSIBILITY: Site Engineer
| signoff | Mandatory HOLD POINT
| section | Materials
| checkpoint | 1 - Kerb & Channel
e4fcb035-8744-59a0-a794-fa582ea9b1e6 | note | VERIFICATION ACTIVITY: QA FORM
4fb9c14a-bc97-5c14-a0ee-62236d66b733 | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
dd7abc20-cb6e-59f0-b18a-b22774f478ac | note | FREQUENCY: Everysite
15f46c4b-5dac-5960-8ab9-344eb343d014 | note | ACCEPTANCE CRITERIA: Kerb & Channel to be precast hand-laid. Kerbing laid on 300mm min Gap 65 subbase in roads and 100mm GAP 40 in footpaths. (CBR>5).Concrete 20MPa @28 Days
c2f2be60-8fe3-57e8-bf7c-7ee9b94ed81c | note | HOLD POINT: Inprocess Inspection
da1a3276-ff09-536e-89a6-716095a36f4d | note | RECORDS: FH concrete QA sheet, photos. Concrete Plant Docket
8a4ce4c5-c774-5575-96e3-54a5ef94471e | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 2 - Channel Level
14b2ce5f-ba32-515f-93a1-b166e6a8cb19 | note | VERIFICATION ACTIVITY: QA FORM
3afac137-d7e5-5206-8c43-c9e9b18c207c | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
1cc608fc-c9c7-5c85-a28e-c8ac2c76a2c0 | note | FREQUENCY: Everysite
e1c4028f-6b69-56d3-b21f-d7962b6a8c7e | note | ACCEPTANCE CRITERIA: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
b55d05b3-7c26-5fae-a007-7337fd5821fb | note | HOLD POINT: Inprocess Inspection
e375b745-f4aa-5e7d-8017-a06c3ba31464 | note | RECORDS: FH concrete QA sheet
c53a5d82-0c34-5f90-9edc-8823415ef6db | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Construction
| checkpoint | 3 - Concrete Footpaths
4772daf2-b6ac-5778-a052-4c336382e0e2 | note | VERIFICATION ACTIVITY: QA FORM
2254ec7d-c8f8-5e46-9e8c-a1f0cc3705c4 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0003
188a9d86-0dd6-52ad-9d76-20ead686dfd1 | note | FREQUENCY: 10m Intervals
e9a148e9-9815-5cc7-9ebd-133f934cba8f | note | ACCEPTANCE CRITERIA: Subgrade - (CBR > 3)
8ca7b9d4-d5e3-5ed6-8cf7-44669d8802b3 | note | ○ Basecourse - 100mm min. thickness
b510d780-cf31-57db-aa72-c31b28fdfa7f | note | ○ Clegg CIV > 12
80332acb-2e9a-56dc-adfc-4cfac386b9b9 | note | ○ Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish
a41d6f16-1507-50e7-9e49-66cb2ba0023f | note | HOLD POINT: Inprocess Inspection, HOLD POINT, Prepour inspection
6c79dd23-5fa6-5dad-ac11-93c13f4b7bc3 | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
656876f2-b945-5fb7-b456-3d06fe0e58d2 | note | ONSITE RESPONSIBILITY: Site Engineer
| signoff | HOLD POINT
| checkpoint | 4 - Concrete Hardstand
f24c68b4-2ab9-5b0d-a026-c5ccaab2e3ec | note | VERIFICATION ACTIVITY: QA FORM
f9e7e9f7-4b02-5af4-a62c-ea13b1c93685 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
fc56de2a-9881-5178-ac51-3273c675ec43 | note | FREQUENCY: Everysite
13e85fc1-caaf-557a-aa60-c32093839b56 | note | ACCEPTANCE CRITERIA: Subgrade -(CBR > 3)
4352467c-2f7d-50f5-8a3d-d20ed57ab830 | note | ○ Basecourse - 100mm min. thickness GAP40
03a898f8-c0a8-59ff-8fff-7207ee56ecce | note | ○ Clegg CIV > 15
5bcf73cb-f2cc-56fd-9cf0-c1a1d8b00ef9 | note | ○ Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with exposed finish
bbc1a12f-c9cf-543d-ad2b-ea3507e75bfc | note | HOLD POINT: Inprocess Inspection
d857f6af-8a5f-57a2-a621-d944bf4f59a7 | note | RECORDS: FH concrete QA sheet, Concrete delivery, Dockets kept as record
7e82ab3c-1211-582d-8373-a0d0c3c967eb | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 5 - Grass Berms
d221e7df-37e7-5343-b83c-30278ea521c3 | note | VERIFICATION ACTIVITY: Visual
6e512e00-cb57-571d-bbc8-15b7a55a7f8a | note | METHODS OR REFERENCE: ATCOP Section 12 Footpaths and Pedestrian Facilities
2fa2c50d-a0ed-5200-ad33-0f812288e0d3 | note | FREQUENCY: 10m Intervals
ee280354-04f9-52a1-9387-4d1fad3a4467 | note | ACCEPTANCE CRITERIA: 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
528526ee-1971-5d5e-825e-ece31ee47d33 | note | HOLD POINT: Inprocess Inspection
d7faab83-7ebe-5296-90e3-8df959d437be | note | RECORDS: Photos
aebc7d68-31f1-5a35-a28f-ecdca8aa90e5 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 6 - Tactiles
bec4b657-9bea-5735-a376-82ac5c93c139 | note | VERIFICATION ACTIVITY: Visual
3bae0af3-3a43-56a5-83b0-53d306e0b68b | note | METHODS OR REFERENCE: NZTA RTS Guidelines for facilities for blind and vision impared pedestrians. AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY.
1d0086be-4784-5813-aa25-98be71a20e63 | note | FREQUENCY: Everysite
b3958e55-9088-562b-a4c4-8aec60b043ea | note | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
daa45d3f-8c50-57e3-92f1-bd02a53aeb0b | note | HOLD POINT: Inprocess Inspection
6b570296-c01e-5aab-bef8-d9774eafbdd4 | note | RECORDS: Photos
63207342-fe99-58c9-bd22-97aea56cfa50 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Asbuilts
| checkpoint | 7 - As built information
5593ad5f-3d79-57f8-9efe-5a0be8428760 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
c7b33e07-390e-528e-9855-97d81175a49c | note | FREQUENCY: Every Site
c5e5c75e-bfef-572b-89bd-675a9278f50f | note | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
f461af4a-4b2c-5c24-b8e7-3efab9a37aec | note | HOLD POINT: In Process Inspection
d52a1763-0d22-5559-b9e2-ac436fb3e0d5 | note | RECORDS: Asbuilt records
71ae41ac-4413-5708-8472-c82d61004e86 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| section | ITP APPROVAL
| checkpoint | ITP Approval
d371180a-e506-51df-8a57-bd78cd5bc88f | note | Prepared by: Cimyona Vinbi
d984d1a0-97c0-55eb-b005-f5880c297f73 | note | Approving Delegate: Daniel Tat
| checklist | Richardson Road, Mount Roskill - ITP - Raised Pedestrian Crossing | itp | ITP - Raised Pedestrian Crossing | 8ee09fce-f361-4768-bcee-b85572d48df0
| section | Details
| checkpoint | 1 - Permits
eee473a6-2a30-5670-b3ca-ef538dc39550 | note | H
bcf9216a-d423-5313-a08c-9382ea8acfad | note | Detail - Obtain Permits
7665acfa-ea68-5f0b-99f9-abd9c885bcbb | note | Frequency - As required
0b3f214a-4c02-5eb4-bf8b-4265c164b831 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
adc7d739-f9de-5c5c-8248-fcbe248b3729 | note | Conformance Criteria - Control Checklist - Fall Prevention (if applicable). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
b6d1bc9f-e461-511f-950f-92f8b3015092 | note | Records - Permit attached or permit number noted
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Pre-construction sign offs
21de652f-6b3d-5505-9874-2091472b0625 | note | H
23449bfe-a3c7-5756-9b1a-8a45734a6053 | note | Detail - Ensure that Sub-Contract and Supplier Agreements are signed
f2831609-6780-51be-a3ac-2425062f1f16 | note | Frequency - Prior to commencement
64520a61-47ce-59dd-8e06-e6ddd9ef2d1a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
4d616cd7-c4d8-5a4f-9221-47249868fba8 | note | Conformance Criteria - Signed Subcontractor and Supplier Agreements
5feb1d84-4406-52da-86e3-edfe9401dc64 | note | Records - Subcontract and Supplier Agreements
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.1 -
fe59f9a8-0416-54bd-9420-fe53b73fbc6c | note | H
26f4ff86-d6ad-56ab-a1a2-491b3edbca61 | note | Detail - Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
c1117374-7ef6-582f-a952-e3a59725a292 | note | Frequency - Prior to commencement
6b367d83-226b-54cf-ab74-d0c62fa56242 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
26bdacdd-de73-5707-8afa-af863c52593c | note | Conformance Criteria - TMP is approved by CAR manager for each site and works are only completed within the approved dates..
88beef62-729e-52b8-b339-0684c18779ba | note | Records - TMP on MyWorksites/On Site
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Design
1fd4642f-7268-5235-9a59-c2fbebe04d46 | note | H
043091fa-ccd2-5ab1-a29a-bebd6c33219f | note | Detail - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
3d8c69ca-054f-5f5a-b598-7fa4dafc4c40 | note | Frequency - Prior to commencement
2493d588-e40b-50d9-b337-ffad4952f1d3 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
c5ff5eb8-935a-51c8-a82c-ffd564c2fd60 | note | Conformance Criteria - IFC drawings have been received by Contractor
873ddb20-bb45-5c03-938d-ac17ac3ebb46 | note | Records - Check Drawing Register
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Installation of Erosion and Sediment Controls
91b53a1c-c17a-5487-b82a-43eb06e7fbd6 | note | H
aa4f01b1-9913-5d15-85c5-7bb5da74ca80 | note | Detail - Ensure that Erosion & Sediment Control in place
a60bfe9b-7609-560a-a0e7-093b94857195 | note | Frequency - Prior to commencement
e682dde7-3484-5aa1-8564-49f414a72b61 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
295e4419-71e2-5066-9bab-a75f24f48bf1 | note | Conformance Criteria - Territorial Authority has approved the asbuilts for the ESC controls constructed onsite and gives approval for construction to commence
0712f550-5ac0-5218-be42-6fe401e887fd | note | Records - Environmental Controls Audit
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Installation of Erosion and Sediment Controls
4d0c4a2e-885c-5ff0-8276-b1fa31a5e38a | note | H
f3aebac4-014b-5ab8-b22a-35bee1d26023 | note | Detail - Ensure that Erosion & Sediment Control in place
9e73178a-b499-5f03-ab03-4d68056982ea | note | Frequency - Prior to commencement
734116b4-44ee-50e3-80fa-89740302a14c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
2c28c05e-d0b0-51f2-b648-43a5073d9a9f | note | Conformance Criteria - Territorial Authority has approved the asbuilts for the ESC controls constructed onsite and gives approval for construction to commence
a0182700-e3b0-5fb1-9740-f6e0a1bd4700 | note | Records - Environmental Controls Audit
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Survey Setout
ca474177-c8c1-500d-9f46-900d022eae84 | note | H
0f740563-fd10-5a2c-93c6-991a2427e528 | note | Detail - Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations)
1bf4c27b-097a-5401-9abd-defa09affc1e | note | Frequency - Prior to commencement
8179a99f-0a38-5fb2-865e-ebfc2af2b735 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey + Smart Level
b24b3d9e-47ee-52c8-b88e-e36dc1fcdc66 | note | Conformance Criteria - Consistency with Construction Drawing
9f89a3ca-a380-5420-a863-0c39447444b9 | note | Records - Site Photos post surveying
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Locate Existing Services by Hand Digging
1c71af09-8f6b-5914-b5fd-a5685aeae1bf | note | H
3d4da3cf-a8d9-55a3-b750-437e5f4b1c67 | note | Detail - Ensure all services conflicting with the line of trench has been exposed by hand digging
d988c5e5-8bc2-500b-b775-482495d3e023 | note | Frequency - Prior to commencement
e816b07b-9660-5872-9b9f-c02ff9df7665 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Potholing
5858d5e1-34f9-5ff6-b872-30af3f29686e | note | Conformance Criteria - All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. Asbuilt all services
4751edf7-2284-5bd9-bd6f-4bd8b6a11221 | note | Records - Digging and excavation checklist, service planes,As-Built Drawings Doc. Review
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Material Compliance
7a707b9e-64a9-50f8-b56d-927e45571973 | note | H
d4746f2b-7218-59cc-b263-2b54825d0a67 | note | Detail - LESA dowels to be used at all construction joints
d80040f0-1420-5eba-a587-092fdd9463a8 | note | Frequency - Prior to pouring concrete
ff564c2d-d7c8-535b-833d-83a853b8ff9c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
ecfa65bd-771b-56e9-a042-676737300be8 | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
0f458b0d-89b5-51e6-95ba-597aa5643649 | note | Records - Delivery Dockets / Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.1 -
c0e09e49-bef8-50af-ae49-08bf2537948b | note | H
e2d4a5c7-2765-51ef-bffe-9db6bdd81a7a | note | Detail - 0.25mm polythene layer placed across all surface area at bottom of raised table
5b714c65-832e-5e46-83d5-08b953b4e5cf | note | Frequency - Prior to pouring concrete
33cc649f-00b9-5f96-9ceb-92907b4718ea | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, Document Review
9fd179ae-b489-5328-987f-3553188a7aee | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
9df6fda9-dd47-5eeb-8ba6-4365b5df0f55 | note | Records - Delivery Dockets / Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.2 -
ec7604ce-caa2-5ecd-b7cc-c7064f5f31a3 | note | H
50a84a66-a188-54f2-ae34-4a031736f26b | note | Detail - 50mm thick compacted layer of AP20 aggregate placed underneath polyethene layer.
cb769293-c31e-5d60-ab4a-30f622700ef5 | note | Frequency - Prior to pouring concrete
6f5a9f5b-472e-5f21-899f-e3c5101ceb64 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
2b46edff-5d23-51b0-9faf-71901512c151 | note | Conformance Criteria - CIV >15
79381d46-2e88-5517-a62b-ebc9d4a01737 | note | Records - Delivery Dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.3 - (1)
aaa2d1dc-4fd4-5d6b-9680-f452c5fab5bb | note | H
93908766-855b-5e78-9dec-f8aed26d0044 | note | Detail - All concrete delivered to site shall have 40MPa 28 day compressive strength with 4kg/m3 of Black Oxide Powder and 13mm aggregate chip size
c8cbf306-9aac-5584-89db-e23a0b569feb | note | Frequency - Prior to pouring concrete
3cec4997-e05d-5057-b1dd-132b375a96fd | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Concrete Delivery Dockets
5c5bf77e-af51-572a-b7e2-400efe7e1db4 | note | Conformance Criteria - Delivery Docket added to QA folder
e63cf5ec-b189-55e6-bc73-67b867fbfa21 | note | Records - Concrete Delivery Dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.3 - (2)
4e20d21f-3d5a-5d0c-9217-cdc88bf01214 | note | H
c3f67fa7-d78c-5b00-b1da-55d7858485e3 | note | Detail - Two layers of 663 steel mesh to be placed in the speed table with 50mm plastic chairs seperating them.
048e66b3-5e66-593b-8831-68af60bb958f | note | Frequency - Prior to pouring concrete
01854d08-df83-56c3-9f86-5609b6be0373 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
aef3f61d-d1c6-5b43-a94c-5872dd2b2b42 | note | Conformance Criteria - Delivery Docket added to QA folder
42786564-254d-5bfb-bd02-76aa98abeb6e | note | Records - Site photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8 - Temporary Works (Formwork)
80f0a7bf-12ae-5329-a82d-c3a2d04e8bce | note | W
99703af0-26b9-591c-9be7-3651721ecee4 | note | Detail - Formwork to be set to correct line and level
93f9a804-2170-52cd-8902-8f759e1a1c2f | note | Frequency - Prior to pouring concrete
73c9612e-7d88-58db-894f-b97b72bd2a3b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
b0012593-a59b-58ba-b2ce-0b9042633111 | note | Conformance Criteria - Concrete Inspection Record
dae15153-197c-504e-af4c-64f38cd70984 | note | Records - Concrete Formwork Checklist
| checkpoint | 8.1 -
d985b201-56dc-569e-81f6-0491bc4e0d4e | note | H
a4ecd59f-7532-5484-87ba-83d5eb03f8e3 | note | Detail - Raised table formwork to be 75mm above existing road level and be 300mm in depth and gradients respectively of entry and exit ramps
8c22e774-9578-5420-bdc0-a63715b68937 | note | Frequency - Prior to pouring concrete
47fbfebf-35f6-5360-b335-db393f399fc0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
27f6648c-8b4e-57d2-8295-c09a8d982221 | note | Conformance Criteria - Designer to inspect formation level
fef0be8b-3361-5d08-946f-9c9367b3cf54 | note | Records - Site photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8.2 -
a8ced5d3-4493-5b6f-a617-2f706617e423 | note | H
3de2f96d-1801-5f73-b6d0-818d436a9397 | note | Detail - Raised Table ramps to have 200mm depth at entry point and tie into 300mm depth to meet raised table
2dc5dea0-da1f-535f-90ef-20d8820ffedb | note | Frequency - Prior to pouring concrete
93c9b26e-23ad-53e0-a54f-7154482b4ddc | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
1c93bdf3-a76e-5484-8fd3-3327f8137e29 | note | Conformance Criteria - Designer to inspect formation level
4b717f0e-b762-56d0-a377-ff8be0f41589 | note | Records - Site photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8.3 -
e6730513-63aa-5d36-904e-90d1aee65e87 | note | H
703885b2-9129-5206-9ca7-2f08f437e656 | note | Detail - Raised Table ramps to be 1m across for entry and 1m for departure ramp.Toe to be 1m across for both entry and departure.
df834876-a4e3-59d1-8c62-bb2fcf7995bf | note | Frequency - Prior to pouring concrete
be468660-93b2-55d1-a4fe-ec8719fb3ef4 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
c0746b91-34c5-5729-a1e4-d9071f9cf706 | note | Conformance Criteria - Designer to inspect formation level
0cf38374-170b-5509-843a-d00a43211b12 | note | Records - Site photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8.4 -
21bc5afe-11a7-50fe-b292-ad8d9fccc788 | note | H
0c7da79a-128c-571b-84da-befe6c26ef6b | note | Detail - Raised Table ramps to be 1:15 gradient for ramps, with 2 layers of 663 mesh.
9dc41c9a-42c9-5d31-a296-43019103cdff | note | Frequency - Prior to pouring concrete
69af265b-28b2-5ed3-91d0-6a6790df9497 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
8acec489-fae6-5cc6-a9f2-a0080c828efc | note | Conformance Criteria - Designer to inspect gradient level
b86bd386-1215-54c7-8724-0da24bde8970 | note | Records - Site photos / Concrete Formwork Checklist
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8.5 -
2a9f2b28-759c-5abe-b8bd-5fb17634653f | note | H
ce806a29-e0e8-56c6-bec4-00e5ff14011a | note | Detail - The Site Engineer and MSQA Engineer must sign off the formwork prior to concrete being poured
09339550-ac8f-51f2-bef4-2b4fbb3566cd | note | Frequency - Prior to concrete pour
48bf0b03-978d-5a8f-ae5c-ae44435fa1eb | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
41f278ec-bd46-52be-9632-8db80288ef21 | note | Conformance Criteria - Concrete Inspection Record
dde3b851-3a7a-560d-b116-4fb5479243a2 | note | Records - Concrete Formwork Checklist
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Reinforcing
4a722d11-d306-57eb-8099-f660b52fd8ac | note | H
3c19345c-edb3-5b89-85f6-8737fdc794de | note | Detail - All construction joints are to contain 2 rows of LESA dowels or similar approved dowels . Speed basket system 50mm w/ Black 300*50*6mm plates @400 centres placed across the construction joint
68e6b970-c5a8-5bb6-b2f9-cd035fc96383 | note | Frequency - Prior to pouring concrete
03db163f-88a8-59dd-8a1b-0aa9e2e18eff | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
c2789de0-220f-5a7c-b63d-16bca3666571 | note | Conformance Criteria - Concrete Inspection Record
37db5e14-2f73-5743-bf95-d5e1647cdc2f | note | Records - Site photos/Concrete Formwork Checklist
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10 - Concreting
744ae68e-9842-542f-9b41-6d3dfb10e9cc | note | H
07c6cf80-ee64-5f5f-b7de-7b1b95243eb9 | note | Detail - The MSQA Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required
27a6c93d-540e-5dd7-a3c0-9ba653a1f422 | note | Frequency - Prior to concrete pour
e1e07271-4812-5bc8-b84b-a3e46f0afc7a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
cb16133a-448f-5b30-9a45-b4b0ec99095c | note | Conformance Criteria - Engineer will be notified via email/SMS at least 24 hours before required for inspection
8ef10b10-f7be-5570-9557-7e49e749bd61 | note | Records - Email / SMS
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10.1 -
4dc81c7f-d80c-5c98-a3f9-6dd59f97690e | note | W
13c6d3dd-0396-54bf-8400-655368b9536f | note | Detail - Vibrator to be used throughout concrete pour
a24cc981-0c5a-5335-8765-f502fdea5faa | note | Frequency - When pouring concrete
aa87f3e6-dcd0-5e16-92ee-b24bdcb16c0a | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
65997b82-97fa-5d59-b2bb-eaa2399bc6fe | note | Conformance Criteria - Concrete Inspection Record
63f1053f-9251-5aed-933e-cff302fcca9c | note | Records - Concrete Formwork Checklist
| checkpoint | 10.2 -
d079556a-e1a2-5a13-836f-116cbcb877c5 | note | H
751b71cb-3b83-5a86-8a79-b1e8df6ad14c | note | Detail - Concrete surfaces on ramps shall be U5 broomed finish and speed table top to be exposed.
e43a1216-4555-5568-b44b-a166e79c0a62 | note | Frequency - At completion of pour
b1541212-d64a-5d0d-9b4e-3926c5c089ab | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
c9271736-863a-57c9-b262-ba4468bd17ea | note | Conformance Criteria - Concrete Inspection Record
fd3c8a6b-6399-566a-85c3-dd659e60203f | note | Records - Concrete Formwork Checklist
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 11 - Curing
7e22030e-7c04-5b44-891d-85244aa2540c | note | M
a133821f-7443-57a1-87b2-25e34c897d73 | note | Detail - Concrete will be left for 48 hours minimum to cure before traffic is allowed on it.
54768c26-9894-5d51-a94c-eafd24e49b9d | note | Frequency - Post Pour
5592649b-0de6-5fca-a76c-9397b1bef6f0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Monitoring the time allowed for curing
cd2eecab-6888-5feb-9871-64cf5cae8dc2 | note | Conformance Criteria - 48 hours minimum have passed
0d5b0159-7d48-51ca-9126-899a38cbaeb1 | note | Records - Concrete Formwork Checklist
| checkpoint | 12 - Remove formwork
79c7c52e-2c13-531b-a8fd-1f2bd2c7926b | note | W
d2d9f964-6a82-5184-af52-c2275ac62cef | note | Detail - Remove formwork after 48 hours
301af622-1a50-5609-b9fe-675a5a77eb6a | note | Frequency - Post Curing
7b3df143-c772-51d0-8af0-85d51ef138d8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
2f368733-3f02-52c2-9b57-bbb156b5437b | note | Conformance Criteria - Concrete Inspection Record
56d417d9-4a72-5415-9c8e-06f37beb9d64 | note | Records - Concrete Formwork Checklist
| checkpoint | 13 - Asphalt- Concrete extension slab/ Toe
d6d2c6cb-f3b4-5595-b7be-02f8e9af9970 | note | H
3ea06749-04b4-568b-b57d-8324d78a331f | note | Detail - Two rows of Lesa diamond placed mid depth @400 C/C along construction joint as per 2789-C3500
7c565d36-64ac-5f9b-ac1b-774a2a24adb0 | note | Frequency - Prior to pouring concrete
eb30c1c9-f67e-5cfe-8dc9-4f46a95549c5 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
ae3bc2a6-e71b-59eb-ba23-830f0813ed39 | note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
f0532f89-1ad6-5d7a-ba81-28ba9a2b7893 | note | Records - Site photos,delivery dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 13.1 -
9ab177cb-fa6d-51e0-bc14-d550c6a5ad23 | note | H
248fb62c-7b8a-5ddf-9dfc-ec4866c23df0 | note | Detail - 150mm thick 40Mpa Concrete with two layers of 663 mesh
adc7424c-5148-5938-978c-7b26fa554eb0 | note | Frequency - Prior to pouring concrete
121cb8b5-83e6-5c30-b18e-821ac82d23a5 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
1cfac011-d232-5409-9406-e12fbd44af75 | note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
500d1d78-8ec1-5a1b-99c5-7019fdf377fc | note | Records - Site photos,delivery dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 13.2 -
d7b12a61-b33c-5981-bae4-ed0344b66baf | note | W
8ddb4444-232c-5695-bf41-29ddbcca63a5 | note | Detail - Tack Coat between AC and Concrete slab
1555001e-3855-578e-8b4b-5fdad3c1f37b | note | Frequency - Post Curing
478acb8c-6aff-50ac-97fb-d253f259b479 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
78c8fd9d-dda6-52fc-9d42-08f6939e3b02 | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
7fae017f-4bf4-5354-9e7d-f2714b9f2b60 | note | Records - Site photos
| checkpoint | 13.3 -
4edff50b-f31b-5e94-af1d-8d07c7198fb7 | note | W
f612631b-02de-59ba-ab25-d37d38274fea | note | Detail - 50mm thick DG10/Mix 7
8baa54ef-50bc-5036-a491-357838c4b3ac | note | Frequency - Post Curing
65462993-d95d-5ef1-bd03-666a826bdec5 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
789dab75-c476-5641-b781-2b9672986011 | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
a69d01e9-511b-5e14-ac14-da1b70f24ca4 | note | Records - Site photos,delivery dockets
| checkpoint | 14 - Lot Number QA File
7edba20a-0c94-5843-9464-1c235d4ec6a0 | note | W
c91adeea-59a4-539b-8d39-6f3df63a9f7d | note | Detail - Ensure all QA Records,site photos and incident cases (OFIs) are closed and included within QA file
27bacb75-ac0c-5006-95e1-9cb45ab59cee | note | Frequency - At completion of Lot
93980994-0b05-59e2-9c7f-d76d2d62f892 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
81404775-509b-5d52-813f-46ba2c11db48 | note | Conformance Criteria - All QA files compiled and sumbitted to client
6d8d56b6-81bb-502c-8582-7f1f5227731e | note | Records - QA records
| checkpoint | 14.1 -
780ebbe6-ca11-5132-b5b9-2151a6ef60d0 | note | W
2c80322d-866a-57a4-8b28-e0dc6d59477f | note | Detail - Delivery Dockets to be included in QA file
dead334e-59f1-5598-8180-2d0534a99c43 | note | Frequency - At completion of Lot
f037a60d-521b-54b1-9ee9-0ceb6b9daaed | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
db99635d-7726-5539-9e06-bc19568236c4 | note | Conformance Criteria - Delivery Dockets to be included in QA file
5efa7291-f245-5bbf-a98e-b2d6f2143bee | note | Records - QA records
| checkpoint | 15 - As-builts
e8b3c1b2-cf62-5747-a3f3-ff23edf65907 | note | H
db0939c5-178e-5df0-831b-2df08fddff68 | note | Detail - Red pen mark up drawings to be included in QA file
5c12af8d-da84-54ef-9175-21ec1e849b3a | note | Frequency - At the completion of the Lot of work
a66f35d4-c57c-55f2-876e-5bbd4eaeb455 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
03623a57-cc6f-5246-8342-a116106687c5 | note | Records - Asbuilt Drawing
| signoff | AUTHORITY HOLDPOINT
| checklist | Richardson Road, Mount Roskill - ITP - Stormwater Drainage | itp | ITP - Stormwater Drainage | 34b25dcd-3773-48ab-adf1-f91de9c1a3e5
| section | Details
| checkpoint | 1 - Permits & Services (1)
f2b5e336-4470-552a-9257-9aaefc0d6811 | note | H
e9019ef6-d0d6-5228-8b58-d0292de75659 | note | Detail - Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
60d90541-fb82-51da-98ee-3d4b2d2dda35 | note | Frequency - Prior to any construction commencing
a5b13639-1249-5bec-8874-c524ca791e93 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
5a07aa45-55bc-546e-8930-a063aa5bec6c | note | Conformance Criteria - Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority.
53d9f297-824c-5b3f-bd48-21a098e2a78a | note | Records - Permit attached or permit number noted.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1 - Permits & Services (2)
23e8cbeb-8557-5c0f-bd36-dd5150323d2f | note | H
5c984e7b-eeee-55a2-afce-be0c4208e7f1 | note | Detail - Locate and mark out all existing services
31f8da4b-b6d6-59e3-99b7-8863274fbe61 | note | Frequency - Prior to any construction commencing
787d5805-cb8b-5442-a79e-babc3eef2e74 | note | Conformance Criteria - B4u dig procedure - follow utility protocols
bf149e77-277f-5038-bb25-11cc5149db37 | note | Records - B4u dig plans & GPR report attached
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Pre-Construction Sign Offs
2c05ab45-cb6a-5eec-ab1c-67e8e56f4046 | note | H
62582519-1a9e-568f-8a27-e039905d84e3 | note | Detail - Sub-Contract and Supplier Agreements
cb78a951-46b1-5d09-b14b-67b1e294a808 | note | Frequency - Prior to commencement.
842583f0-5b8b-501f-8718-eb84ac9fa72e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
77cb57ed-6ad9-5a52-850e-665f39c9419d | note | Conformance Criteria - Sub-Contract and Supplier Agreements to be agreed and signed
eaa9716b-6585-532a-839d-77e11ff435d0 | note | Records - Subcontract and Supplier Agreements
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Design
4b358b53-8af5-52bb-af3c-997e3d73fb46 | note | H
9f3571b1-9747-5810-812a-2faec9f568c5 | note | Detail - Design is approved and Drawings are of the latest revision.
2073e0f6-14af-5163-b2ce-a59c6dc00770 | note | Frequency - Prior to commencement.
02530d93-ca2b-5ca6-9178-f602d6b4704f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
7c598c4b-75de-5a70-b34a-57717fac0e2b | note | Conformance Criteria - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
585d150a-3281-5645-b28c-25f99fe8bd2d | note | Records - Drawing Register.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Survey Setout
15f9b917-0859-5b99-a9be-64ee650abaed | note | H
35b5f71a-888f-5bec-9e7d-772b312c7a82 | note | Detail - Setout Pipe Alignment and Service Locations with inlet & outlet points and inverts as required to construct to design
8f34b720-9941-560d-a1ac-b1fa21ac2799 | note | Frequency - Prior to commencement.
a26c6441-3730-5942-85f0-db8bf3534494 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
a3e2fd44-537e-5993-9760-65bc6f6d4349 | note | Conformance Criteria - As per Stellar Engineering Drawings: 2789-C3060 or setout files
dd0a037e-ebb9-5ee4-8ca1-518542e8021d | note | Records - Survey Receipt.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Pipe and Manhole Material Compliance
d4a225b5-c666-559d-9088-e6a6e3c8cef4 | note | H
28482601-4c19-52e0-87e9-c5fa2079e51b | note | Detail - Cesspit, Manhole and Pipe shall comply with relevant AT/TDM standards
09063f23-98ba-5a70-af20-fe079a8c5cfc | note | Frequency - Prior to commencement.
a0a3a1f4-b638-5315-97c6-61f2e3c499e5 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review, Visual Inspection
35610d3e-62bd-5930-90f1-ccb54ac9e165 | note | Conformance Criteria - Pipe shall be
7702589f-226e-5006-ae97-e396e9ba7e53 | note | ○ Check for freshyly formed pipes and return if required
3463e64f-a064-5a4b-a705-df341dc389a6 | note | 1). DN225 Class 4 RCRRJ pipes AS/NZS 4058
3a607a00-2aae-5637-8d2c-7c6155b66f53 | note | 2). All Concrete RCRRJ pipes to be fitted with Rubber rings
b1964990-0ba4-53a2-89d0-d4fabcc81f71 | note | 3). Pipes shall have product certification (ISO Type 5) to AS/NZS 4058
3bd58535-7dba-5e7b-b06c-e5ead676c17a | note | ○ Prefabricated concrete Manhole shall be in accordance with TDM Standards & AC COP
275036e7-6a02-5944-815d-de7ca2ee566a | note | Records - Manufacturers Data Sheets, Delivery Dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Locate Existing Services by Hand Digging / Hydro Vac
e1046e55-61a8-5376-8b01-7583cf8e7492 | note | H
731074dc-d844-54f4-8380-77bbf785852c | note | Detail - Ensure all services conflicting with the line of trench have been exposed by hand digging.
ef126428-361e-53e6-9b22-e7763eb29602 | note | Frequency - Prior to commencement.
bc31597e-8fc9-55f8-99a1-4a388bec8bbe | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Potholing / Survey
915d9156-9130-5fdd-ae20-6cd56de8ba4a | note | Conformance Criteria - All conflicts have been located. New services and / or conflicts to be advised to Project Manager.
97fc56bc-06c1-56e3-89a8-377bef07c555 | note | Records - As-built Drawings. Doc. Review
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Trenching & Excavation (1)
649bba21-2c39-56ad-8269-780c1151bb88 | note | H
4d77a37c-df04-57fc-bde2-ac677dbc0347 | note | Detail - Excavation methodology
66b81765-2fd9-52f9-bad0-0ff8b54d90c1 | note | Frequency - Daily
3a612af4-5c11-5b78-8ac7-42ae8f64c73d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Prestart review
24f02457-02ac-52fe-83da-0f825faec3ce | note | Conformance Criteria - The excavation, benching and shoring requirements shall be in accordance with Worksafe Excavation safety guidelines (2016)
456a14e3-3758-585e-9794-3ab9f2d210f7 | note | Records - Prestart RCP
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Trenching & Excavation (2)
3fdcd514-a675-5db8-b842-b300cfbea9c7 | note | M
7b11b829-9e68-5a81-be29-f14bfc94c5be | note | Detail - Trench Profile - Width
82d6c50f-6700-525c-963c-6b593160e5d1 | note | Frequency - Daily / as trenching takes place. Different depth methodology
eb5b1a19-cfb7-5ebc-81e7-8f2424ed1105 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, Excavation methdology
6e5046be-70c8-5cec-aaaa-f6c257345ab3 | note | Conformance Criteria - Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing
6aef66da-472a-587c-bdef-00f28a169e25 | note | Records - Construction Photos
| checkpoint | 7 - Trenching & Excavation (3)
1ecf5e6a-d642-5a79-a3cd-994d88dd374f | note | W
1a882f7d-48ef-586e-8682-0fb14c87e26f | note | Detail - Trench Profile - Depth
697b3fc8-4654-58f3-8b21-98c65e6c95dd | note | Frequency - Daily / as trenching takes place.
481d75ce-418e-5d46-8002-e172b4dab4a5 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, Measurement
0bdf7431-8f7b-5f0b-aa11-ee3926bed827 | note | Conformance Criteria - Trench depth varies according to longsection and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings
780bbcf6-4520-503c-9206-441056dd8767 | note | Records - FH Drainage Line Record / Construction Photos
| checkpoint | 8 - Bedding for Concrete Pipe Laying & Manhole & Cesspit
bf38b7c7-636e-534b-bd7c-1b73e03887b1 | note | W
84eedb0a-3133-5ea9-90f2-416487c97bd9 | note | Detail - Placing and compaction of Bedding Material.
06a611b2-735c-5001-8b3b-9e622c108f4b | note | Frequency - Inspected continuously during placing and compaction of Bedding Material.
e430d54f-fb8a-53d7-8e07-f528143da73c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
bd908cbb-4875-59a7-a7f8-a627455747de | note | Conformance Criteria - Bedding & Pipe surround material to be GAP7 or GAP 20 (Stevenson Quarry) or alternate material that complies with AS/NZS 3725
eb94f834-a3fe-55d9-9ee4-aa00d85a4696 | note | Records - FH Drainage Line Record / Construction Photos
| checkpoint | 9 - Pipe Position Tolerance
c1fbdfc6-c56b-536e-ba99-dff3b58f2a1b | note | M
dd8cf554-19fe-5649-8d7a-f780ed0f3c2a | note | Frequency - At any point of pipe
84f5325e-d011-5532-ab1d-8b8fbfe4cc3b | note | Conformance Criteria - Position tolerance for pipe laying at any point along the length of the installation shall be within ±30 mm from the specified design.
d721b60b-f68c-5e85-b9c9-c77c77cd324b | note | Records - FH Drainage Line Record, Survey Data.
| checkpoint | 10 - Trench Backfill - Placing & Compacting
72b00030-2a45-5113-8461-f11134bf6c51 | note | M
1c0d3b5c-ef75-51e7-ae7b-83736f00119d | note | Detail - Placing and compacting of Trench Backfill Material
690ed6b8-330c-5885-96b8-3ea666292555 | note | Frequency - Throughout Trench Backfilling operation.
8a666255-bf30-506b-b286-6e1bedaafd65 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
6b4a0a11-ae9e-5d59-81de-6f6b07754570 | note | Conformance Criteria - Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm
abf551d8-e469-5567-ac50-1fd7a6850e48 | note | Records - Construction Photos
| checkpoint | 11 - As-Built Drawings
edd7d527-9c19-564f-ac2f-c8b584bba6f2 | note | W
507c3e8f-8b21-5c3d-ab92-b747f8c37d9d | note | Detail - Red pen marked-up As-Builts of every 'Issued for Construction' AT drawings
1c1442c9-177e-5759-a406-909be85bce91 | note | Frequency - Final As-Built Drawings to be completed within three months of the construction completion of the asset or infrastructure.
40e2f879-6460-59be-96c4-71bd5b63dea3 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings / Visual Inspection
ce7b0da4-c94d-51f1-b42d-48826538b489 | note | Conformance Criteria - As Built and GIS Data
79c8d5bb-604d-57d5-b00d-c5477727687f | note | Records - Redline As-Built Drawings, scanned as .pdf files.
| checklist | Richardson Road, Mount Roskill - ITP - Traffic Islands | itp | ITP - Traffic Islands | 8aba3b5b-c2a8-4803-843c-8592430939cf
| section | Materials
| checkpoint | 1 - Mountable Kerb
8c4d6385-50a2-58a5-a124-d21d7dcbc448 | note | VERIFICATION ACTIVITY: QA FORM
6b32e906-05bf-5864-8b62-8c351c359940 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
f2ed56e4-0804-5f2a-903b-fd080a163def | note | FREQUENCY: Everysite
fad0159d-3f11-5b3f-8ab5-ce5737d34853 | note | ACCEPTANCE CRITERIA: Mountable Kerb to be laid using precast hand-laid and painted with two coats of reflective paint
5fecd42b-85b5-513c-af33-1a91b4d6f829 | note | HOLD POINT: Inprocess Inspection
9c6a8a4a-f073-539f-91ed-d348f4e952cb | note | RECORDS: FH concrete QA sheet, photos.
102183ab-ba1a-5fa8-8002-4d56658ee722 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Construction
| checkpoint | 2 - Survey Setout
6a6473ef-b3b6-5273-9be3-9316840f12bf | note | VERIFICATION ACTIVITY: Survey
e45ef8c0-a80f-546e-a9d4-2d3ec81a4741 | note | METHODS OR REFERENCE: Setout Kerb Alignment required to construct to design
e1f27a52-ebc9-5637-b34f-dd954a2c0e54 | note | FREQUENCY: Prior to commencement.
c8a5c1f0-8906-548b-a3aa-b69eabd84e73 | note | ACCEPTANCE CRITERIA: Survey
e3709900-d680-5267-9852-89537577fb13 | note | HOLD POINT: As per Construction Drawings
9f6418f7-be7b-5340-a166-aa7608cf7d76 | note | RECORDS: Survey Receipt.
582ac1d5-98a4-56d5-91c4-0b8ca77936ac | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3 - Concrete Island (1)
bb5c81f5-5f54-595d-8fac-1d794996996c | note | VERIFICATION ACTIVITY: QA FORM
755ab118-fa52-5c58-bed5-f7f105c8515d | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
1083d7f2-5d90-5321-94b7-d5cc90d7f1b3 | note | FREQUENCY: Each Site
9feff643-1cb9-5e28-b669-dcae19746a32 | note | ACCEPTANCE CRITERIA: Kerbs to be haunced with 20MPa Concrete
5ffe95e0-42e0-5502-9e50-81d129be7d83 | note | HOLD POINT: Inprocess Inspection
ff75cb48-b62d-5509-92fb-ebf65335690a | note | RECORDS: Photos
375e671e-4095-54ae-8451-a60f7a4b61b0 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 3 - Concrete Island (2)
20469e49-057c-51af-be7c-e991d2d158bc | note | VERIFICATION ACTIVITY: QA FORM
bc27f641-61e8-5782-a213-f2d21c82f42e | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0003
6cbc4f1e-4469-5e19-9672-96cc9211042e | note | FREQUENCY: Each Site
143fcaf1-9a3d-5ac3-8723-ac0d1b0598c9 | note | ACCEPTANCE CRITERIA: Basecourse to be 150mm min thickness of GAP65
23f0acf7-4a1b-57a2-b392-1cf08f1b4d18 | note | HOLD POINT: Inprocess Inspection
d4bc9b04-42e2-5afc-b737-d3abefc647cc | note | RECORDS: Photos
24cfbd59-8d0a-5f5f-8b77-ce3c5c9a5bc9 | note | ONSITE RESPONSIBILITY: Site Engineer
| checkpoint | 4 - Concrete Infil
1e5d9c6b-641c-5df3-a614-1b038ebdb0d1 | note | VERIFICATION ACTIVITY: Concrete Infil
2a05c669-7f3c-5a7f-bff0-2dc16ad31d0d | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
27931e09-c04d-5ccd-a71c-b8268bce9c9d | note | FREQUENCY: Each Site
1e3e8af6-d540-5d2b-bec4-e769d12c8c48 | note | ACCEPTANCE CRITERIA: 180mm depth of 20MPa broom finish unreinforced Concrete with 4 kg/m3 Red oxide. Cross Fall of 2% or max rise in centre of 180mm.
a2624e78-af5d-5426-8647-9cc360a6ecd5 | note | HOLD POINT: Inprocess Inspection
058627e9-f751-5ab0-b1e5-2c163735a06f | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
5ef58dff-b31a-5da9-b9b6-60e156ccb416 | note | ONSITE RESPONSIBILITY: Site Engineer
| section | Asbuilts
| checkpoint | 5 - As built information
26f16e0b-e6d9-5659-bf6f-768c3dc2e46c | note | VERIFICATION ACTIVITY: Drawings
b4810b17-45c9-5623-a06f-c483c4c3c585 | note | FREQUENCY: Every Site
96f53baf-698f-5ab0-ae6c-0c3adb196b4e | note | ACCEPTANCE CRITERIA: As built drawings
b14b829d-17b2-5c51-b735-9c02b80823b3 | note | HOLD POINT: In Process Inspection
9ac7d801-6974-5bcc-8c25-73c7f20050c5 | note | RECORDS: Asbuilt records
0f5f4d67-2247-578d-a80d-8c21f491e181 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| checkpoint | 6 - RAMM DATA
57ddc4eb-b032-55f9-96c7-fccd80c8d118 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
004c70a4-1b43-5c25-b5d2-979b7b3578a1 | note | FREQUENCY: Every Site
abdce238-6900-59ce-9052-84082afee0e3 | note | ACCEPTANCE CRITERIA: RAMM SHEET
451be81c-9929-55c8-b033-4e6b990aeb53 | note | HOLD POINT: In Process Inspection
974ecea8-e922-5995-98c3-f3d8c308bcaa | note | RECORDS: Asbuilt records
6b4ee8ee-8a76-5ae5-aea4-33c6bfdbef63 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
| section | ITP APPROVAL
| checkpoint | ITP Approval
1367e6dd-9549-5c96-9480-1fe207d34a7e | note | Prepared by: Yeswanth Vemula
d6913f42-b9a0-58b8-8ead-60c206cb4e9d | note | Approving Delegate: Sumesh Sharma
| checklist | Rogan Arunel - ITP - Enabling Works |  | Drainage - Pipeline Installation - | 0aa34d49-8c64-43e0-8c3b-b526b2b13b1e
| section | Pre Start & Area Acceptance
| checkpoint | Latest consented drawings available, checked and referenced
becbf563-65cf-4d00-b2a6-e5a2cf94db78 | textbox | Relevant drawings & revisions for reference:
| signoff | Raise Remedial / Request Review
| checkpoint | Work area acceptable & approval to start work
| signoff | Raise Remedial / Request Review
| section | Pipeline Installation
| checkpoint | Setout Completed checked and accurate
| checkpoint | Excavation Accurate - Location & Depth
| signoff | Raise remedial / Request signoff
| checkpoint | Ground Conditions Checked & Acceptable
| checkpoint | Bedding depth and material correct
| checkpoint | Correct pipe laid to specified level and grade (all joints sealed correctly as specified)
| signoff | Connections to manholes complete and approved
| checkpoint | Air Test Complete (Sewer Only)
| checkpoint | All Pipe install elements completed - Install Completed
| section | Review & Handover
| checkpoint | All Pipe Install works completed, checked and reviewed as per specification
| signoff | Raise Remedial / Request Review
| checkpoint | Area left clean & tidy
| signoff | Raise Remedial / Request Review
| checklist | Rogan Arunel - ITP - Roundabout Construction |  | Drainage - Pipeline Installation - | c03ca805-3f48-41b0-bf35-c870cebcb437
| section | Pre Start & Area Acceptance
| checkpoint | Latest consented drawings available, checked and referenced
becbf563-65cf-4d00-b2a6-e5a2cf94db78 | textbox | Relevant drawings & revisions for reference:
| signoff | Raise Remedial / Request Review
| checkpoint | Work area acceptable & approval to start work
| signoff | Raise Remedial / Request Review
| section | Pipeline Installation
| checkpoint | Setout Completed checked and accurate
| checkpoint | Excavation Accurate - Location & Depth
| signoff | Raise remedial / Request signoff
| checkpoint | Ground Conditions Checked & Acceptable
| checkpoint | Bedding depth and material correct
| checkpoint | Correct pipe laid to specified level and grade (all joints sealed correctly as specified)
| signoff | Connections to manholes complete and approved
| checkpoint | Air Test Complete (Sewer Only)
| checkpoint | All Pipe install elements completed - Install Completed
| section | Review & Handover
| checkpoint | All Pipe Install works completed, checked and reviewed as per specification
| signoff | Raise Remedial / Request Review
| checkpoint | Area left clean & tidy
| signoff | Raise Remedial / Request Review
| checklist | Rogan Arunel - ITP - Stormwater Drainage |  | Drainage - Pipeline Installation - | a62a6240-7857-4f1d-a174-d73064348a8f
| section | Pre Start & Area Acceptance
| checkpoint | Latest consented drawings available, checked and referenced
becbf563-65cf-4d00-b2a6-e5a2cf94db78 | textbox | Relevant drawings & revisions for reference:
| signoff | Raise Remedial / Request Review
| checkpoint | Work area acceptable & approval to start work
| signoff | Raise Remedial / Request Review
| section | Pipeline Installation
| checkpoint | Setout Completed checked and accurate
| checkpoint | Excavation Accurate - Location & Depth
| signoff | Raise remedial / Request signoff
| checkpoint | Ground Conditions Checked & Acceptable
| checkpoint | Bedding depth and material correct
| checkpoint | Correct pipe laid to specified level and grade (all joints sealed correctly as specified)
| signoff | Connections to manholes complete and approved
| checkpoint | Air Test Complete (Sewer Only)
| checkpoint | All Pipe install elements completed - Install Completed
| section | Review & Handover
| checkpoint | All Pipe Install works completed, checked and reviewed as per specification
| signoff | Raise Remedial / Request Review
| checkpoint | Area left clean & tidy
| signoff | Raise Remedial / Request Review
| checklist | Sheehan Ave - ITP - Enabling Works - Footpath, Kerb and Channel |  | Enabling Works - Footpath, Kerb and Channel | b774ed50-7042-4632-8cd2-faff797647b8
| section | Site Set Out
| checkpoint | 1 - Site Set out
f6a0b195-fff7-53b6-8529-0d23ba59fa71 | note | VERIFICATION ACTIVITY - Surveyor
467d2f42-2ffa-58c9-8072-ff6288c704da | note | METHODS OR REFERENCE - Surveyor
7b56260d-11e8-5acb-9a68-3a30f5a69e79 | note | FREQUENCY - Every site
ecba7cbd-433a-58a2-9bf0-49099c5dc28f | note | ACCEPTANCE CRITERIA - Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
5e725552-888b-5f5f-8451-3424499e52d5 | note | Hold Point - Mandatory HOLD POINT -
f33b377b-ff40-5f88-9817-871bda2e97f7 | note | Records - Onsite records/photos
7528a18a-dc9b-5660-a4b2-d0cd6ebdbd5a | note | Onsite Responsibility - Site Engineer
| signoff | HOLD POINT
| section | Materials
| checkpoint | 2 - Kerb & Channel
e16bb5b0-835c-5745-a023-738e07858b32 | note | VERIFICATION ACTIVITY - QA FORM
80c3b7ad-2d91-5fe0-80b5-a45664a726c5 | note | METHODS OR REFERENCE - TDM Technical Standards - KC0001
6f1019e9-a8b3-5df5-ae3a-b674bb977c4a | note | FREQUENCY - Every site
5d455783-8a66-5fe4-952f-9316ae87ad22 | note | ACCEPTANCE CRITERIA - Kerb & Channel to be laid using precast hand-laid. On compacted GAP40. Concrete 20MPa @28 Days on 100mm GAP40 with the subgrade CBR>5
5dbf06ef-ca78-5a10-b17d-b036367b37a4 | note | Hold Point - In process Inspection
be432a6d-377e-52e5-831c-23b1dea39288 | note | Records - FH concrete QA sheet, photos. Concrete Plant Docket
043f99f2-5678-5140-8726-0f68f3c4d58e | note | Onsite Responsibility - Site Engineer
| checkpoint | 3 - Channel Level
d7e29910-2b5c-5b0f-b29e-5523b9a09d57 | note | VERIFICATION ACTIVITY - QA FORM
ed929b60-ca80-52a9-b37f-885fc2b053aa | note | METHODS OR REFERENCE - TDM Technical Standards - KC0001
85c72ae5-7d79-5e56-99fb-4ae70eb26caa | note | FREQUENCY - Every site
40615e96-c936-5f62-817b-28c91e650c49 | note | ACCEPTANCE CRITERIA - Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
707a86d9-8a91-504f-96c0-0e5b386d705c | note | Hold Point - In Process Inspection
61c5d0d9-3852-5764-b111-eef8edf13b98 | note | Records - FH concrete QA sheet
27b734a8-471d-5ad8-a781-0e583be51c13 | note | Onsite Responsibility - Site Engineer
| section | CIVIL WORKS
| checkpoint | 4 - Concrete Footpaths
03eb33ba-27ac-53fa-bfdd-3ce0a8bb2e02 | note | VERIFICATION ACTIVITY - QA FORM
65a10c4e-07f9-579a-9e75-4433af76d227 | note | METHODS OR REFERENCE - TDM Technical Standards - FP0001
b6837531-20e7-5c3f-a152-003914a120c1 | note | FREQUENCY - 10m Intervals
ccd216a3-d574-507a-9f6a-359117680258 | note | ACCEPTANCE CRITERIA - Basecourse - 100mm min. thickness GAP40. Clegg CIV > 12. Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish.
8d925024-2657-5e87-a6ae-b365973cdcad | note | Hold Point - Inprocess Inspection
90ebdbd5-4489-5849-81e1-ec5bac1055b1 | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
29b84b63-9656-529a-a8d2-71f06530de4c | note | Onsite Responsibility - Site Engineer
| checkpoint | 5 - Tactiles
d546fec8-b0e6-5de6-b788-7ea1bea57062 | note | VERIFICATION ACTIVITY - Visual
ff8f90c5-e1fc-500f-ab88-7d68a9d85dc4 | note | METHODS OR REFERENCE - TDM Technical Standards - FP0010
84e157d7-6d79-549f-b535-97596f7180be | note | FREQUENCY - Each PX
3292f323-d66f-5278-8265-a211c2a8a001 | note | ACCEPTANCE CRITERIA - Warning TGSI tiles should have 100mm concrete slab underneath
ee2153d3-9308-5dc5-8bc5-196bbc0f3ec4 | note | Hold Point - Inprocess Inspection, Measurement
071f064f-8186-5ac5-8af8-c56bfd772a15 | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
7a245c54-c797-5a48-8282-8e75db4ed2e2 | note | Onsite Responsibility - Site Engineer
| checkpoint | 5.1 - Tactiles
893ae7ea-e31f-5eee-a6f4-839d4379639b | note | VERIFICATION ACTIVITY - Visual
53b5365d-666f-56bd-b255-35ebb8106954 | note | METHODS OR REFERENCE - NZTA RTS Guidelines for facilities for blind and vision impaired pedestrians. AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY.
4c801836-3390-5eb0-8e2d-3085d96ffe6c | note | FREQUENCY - Every site
a2047e7e-d36c-51fe-86b0-bc95e73b06d0 | note | ACCEPTANCE CRITERIA - Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
798e3cfa-3d83-55de-9e62-1e9c2fec4e5a | note | Hold Point - In process Inspection
730f4df3-474b-5590-9e91-48e874bc244c | note | Records - Photos
7690dc5a-419b-5c4b-ae5a-9863a4639e58 | note | Onsite Responsibility - Site Engineer
| checkpoint | 5.2 - Tactiles
c95fe916-1d8f-5850-a9b7-674cf7adf28d | note | VERIFICATION ACTIVITY - Visual
03aba92e-aeca-58b0-b22b-84bb752fd4d8 | note | METHODS OR REFERENCE - AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
2ec13563-542e-5d6a-bcf7-e24b6e7fa1ba | note | FREQUENCY - Every site
3e26842d-f364-5a7d-9ae2-32f254bbe8f9 | note | ACCEPTANCE CRITERIA - Edge of warning indicators to set back 300mm from the face of the kerb or lane, extend the full width of ramp and be 600mm deep.
3d077907-e443-57af-b29b-1026862c360f | note | Hold Point - In process Inspection
afa8416e-0e2a-598f-936a-b4d614fd04c9 | note | Records - Photos
f81070b6-a103-59f0-8b8e-a1ab908f1ce4 | note | Onsite Responsibility - Site Engineer
| checkpoint | 5.3 - Tactiles
7a88d972-4a0a-5a5a-ba21-a011089cfd07 | note | VERIFICATION ACTIVITY - Visual
35de5e26-9d47-5bae-8657-f1fc78cc403a | note | METHODS OR REFERENCE - AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
93084d2c-69e1-56c9-94c8-de3f7a32e225 | note | FREQUENCY - Every site
879934af-516c-5315-b37d-8fc55c10546c | note | ACCEPTANCE CRITERIA - TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
c058f463-b45c-5e6f-bc5a-454c56f7e0de | note | Hold Point - In process Inspection
3d37c479-475d-5f34-9527-f2c4f03fea4b | note | Records - Photos
659798b9-a736-5c0f-9836-c4c1f915f06f | note | Onsite Responsibility - Site Engineer
| section | RAMM DATA
| checkpoint | 6 - As built information
d7d60908-e0d6-5aa4-b66c-4be0807c3f26 | note | VERIFICATION ACTIVITY - RAMM DATA SHEET
4f10629b-a734-592b-9f8a-eaaa5f6945f6 | note | FREQUENCY - Every Site
641911cc-b938-5f80-ba3a-7f73f492627c | note | ACCEPTANCE CRITERIA - As built drawings and Ramm Sheets Completed
76021637-66fe-58f4-bbe3-23e52563ae83 | note | Hold Point - In Process Inspection
74eabbcd-bfad-56be-a2a2-fba5ae52b8b6 | note | Records - As built records
fcc7b30b-b613-5502-b3ef-c42f271ada5f | note | Onsite Responsibility - Supervisor and Engineer
| checklist | Sheehan Ave - ITP - Raised Speed Table |  | Raised Speed Table | 96ac93e1-8978-4948-8d52-c81c3563cc2a
| checkpoint | 1 - Permits
eb353c99-b79f-53e9-8372-f53c4e530f9f | note | ACTION (Hold, Monitor, Witness) - H
8b0fbe2b-c5fa-5958-844f-41481128a0ea | note | Detail - Obtain Permits
5722a16d-5cb0-55d0-852b-9ee4046e61e4 | note | Frequency - As required
4c00a638-4cc6-51e3-9011-72eb8977bf0d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
07e22cd5-1626-51ee-a123-eb5bab3cfe42 | note | Conformance Criteria - Control Checklist - Fall Prevention (if applicable). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
60fff5d0-a63a-5fa4-b489-86fcac351aa7 | note | Records - Permit attached or permit number noted
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Pre-construction sign offs
f7b8f8d5-d020-5dde-913b-959f2f4efbfa | note | ACTION (Hold, Monitor, Witness) - H
77e88c12-aa2c-54ea-95e7-b6e6d2c3a633 | note | Detail - Ensure that Sub-Contract and Supplier Agreements are signed
420e1703-7176-5955-917d-59d8034dbbb6 | note | Frequency - Prior to commencement
316de513-ca26-5f08-9f18-86fbcd5dc222 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
fdda940f-d38b-5932-a788-08e2c35469d1 | note | Conformance Criteria - Signed Subcontractor and Supplier Agreements
16e3b644-c278-5f33-92f2-d55657d53663 | note | Records - Subcontract and Supplier Agreements
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.1 -
5bdd831f-f788-5cf4-afa6-9dfcd9c3426f | note | ACTION (Hold, Monitor, Witness) - H
a1b157cc-087c-5a45-9b69-67dd1a600347 | note | Detail - Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
f9651d82-09a1-5830-bc72-0fc233686527 | note | Frequency - Prior to commencement
5094ad6f-9f99-5c50-869e-ced636e424ee | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
680120c9-896b-54d3-9eda-1afd18def524 | note | Conformance Criteria - TMP is approved by CAR manager for each site and works are only completed within the approved dates..
4be9bbf6-0c8d-523f-b4cb-aaedc8c28965 | note | Records - TMP on MyWorksites/On Site
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 -
50bd5eba-9021-53c8-97cb-04e4d7f6cb34 | note | ACTION (Hold, Monitor, Witness) - H
2428ebdb-20e6-5f31-9222-57159cfff580 | note | Detail - Ensure all Sub-Contractors and Suppliers go through FH induction
8a2c7869-5f0b-5392-9da3-8b314b5ed13c | note | Frequency - On site daily
09d22ac4-7c37-572d-979f-dd146c426aa0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Induction
0ece3c94-cd43-5739-acb7-c11bd92be9a7 | note | Conformance Criteria - Supplier's and Subcontractor's signatures on hazard ID and pre-start documentation
9066934a-ade9-5c5b-9413-05d06e29b808 | note | Records - Hazard ID and Pre-starts to safety team
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Design
ee2fcab3-e72a-5807-9762-2071323964fc | note | ACTION (Hold, Monitor, Witness) - H
7c8219a3-c3ee-575e-9210-a3fe58f59c78 | note | Detail - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
1c8c184c-42b2-539d-b1de-55820438c2f9 | note | Frequency - Prior to commencement
c45971f7-25e0-5fb1-a17b-f1924c2141a2 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
c7fc1f86-a821-5997-8a91-adec90a957b7 | note | Conformance Criteria - IFC drawings have been received by Contractor
fca7ca7c-f5a2-5f7e-a536-1235500a92e4 | note | Records - Check Drawing Register
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Installation of Erosion and Sediment Controls
0bcfd015-1f45-5e5d-a4cd-f93e7e03c059 | note | ACTION (Hold, Monitor, Witness) - H
60e4fc2b-335d-52c6-8efa-1f46a715bc8f | note | Detail - Ensure that Erosion & Sediment Control in place
8476e748-4967-57d7-a702-68f1c01fe5b8 | note | Frequency - Prior to commencement
5a3be1de-0858-50ce-91ee-10ef8ea40af3 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
23651467-32fa-5f50-9ac5-b4d5b13411b8 | note | Conformance Criteria - Territorial Authority has approved the asbuilts for the ESC controls constructed onsite and gives approval for construction to commence
b1ae53fa-a298-51c7-a2c7-d837e1ddbd36 | note | Records - Environmental Controls Audit
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Survey Setout
a0290439-103d-5cd3-8978-6e11e191334e | note | ACTION (Hold, Monitor, Witness) - H
689f3de1-5c3c-59b4-b416-687b42fe359a | note | Detail - Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations)
bcaa693e-dab6-5184-9303-7d634432db02 | note | Frequency - Prior to commencement
53c3c73e-1751-59d0-bd1e-bb56c0e79d9c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey + Smart Level
c71ae9bb-2aa6-5b30-a051-007ff81b86a6 | note | Conformance Criteria - Consistency with Construction Drawing
58445448-204b-5932-be79-f8b53de9a633 | note | Records - Site Photos post surveying
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Locate Existing Services by Hand Digging
2fbc3663-7938-5d26-908a-d15e3ffb42c8 | note | ACTION (Hold, Monitor, Witness) - H
2096601e-8b76-5dbf-9704-f27b83b7e8ed | note | Detail - Ensure all services conflicting with the line of trench has been exposed by hand digging
abab33d3-a40f-524e-b860-72cacbd25e80 | note | Frequency - Prior to commencement
d2b1a41b-28bc-5950-8857-e081cbcd2b23 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Potholing
11f56dc7-d223-5999-8528-e3c9b4b1e71d | note | Conformance Criteria - All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. Asbuilt all services
51be112e-50f4-5295-8019-5543670ebd2b | note | Records - Digging and excavation checklist, service planes,As-Built Drawings Doc. Review
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Material Compliance
485f5cb3-d713-5a23-b758-59c8aacbd9da | note | ACTION (Hold, Monitor, Witness) - H
70b640b8-0580-551c-adf0-92e7535d44c2 | note | Detail - LESA dowels to be used at all construction joints at 600mm clearance
93d81f7f-aa15-558e-a62d-8610ce70383d | note | Frequency - Prior to pouring concrete
807d4275-ba18-5077-b671-5aeb91957b38 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
a4f89933-f739-5ab6-a699-9fec9ebceb33 | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
e35e1ea4-3b87-5650-b217-4d2d4a6cb37b | note | Records - Delivery Dockets / Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.1 -
e49c7070-449a-5245-992e-7eb1073ec0ee | note | ACTION (Hold, Monitor, Witness) - H
1b7718fe-cb88-5d6e-a721-aa448cfc10df | note | Detail - 0.25mm polythene layer placed across all surface area at bottom of raised table
a7c5c65e-4f51-51c0-a056-3b32e4f4deb3 | note | Frequency - Prior to pouring concrete
005b9f89-df65-55a1-adba-aecdf7a4adf5 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, Document Review
636ee06a-7ea7-56fc-99cf-5245e14ab933 | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
63c090a7-025a-5061-a207-6eb82817167f | note | Records - Delivery Dockets / Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.2 -
302c6591-44b7-598a-9e42-ee917079f369 | note | ACTION (Hold, Monitor, Witness) - H
c169ff04-8e56-564b-8f31-5e9cc5b145bf | note | Detail - 30mm thick compacted layer of AP20 aggregate placed underneath polyethene layer.
03894d99-773e-52b1-b122-b8405ff4b098 | note | Frequency - Prior to pouring concrete
713fab28-ee60-50fd-8c7e-2e9adaef651e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
d1efa73a-98cf-50ac-8a8b-20400b296af2 | note | Conformance Criteria - CIV >15
56f34088-0233-5d63-be43-0256b59d88a0 | note | Records - Delivery Dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.3 -
0c6c055c-4eff-59c5-9669-98a28069f465 | note | ACTION (Hold, Monitor, Witness) - H
32bc91a0-2921-5294-8643-b1368ee131ae | note | Detail - Two layers of 663 mesh 50mm cover from top and bottom to be placed inside with 70mm plastic chairs seperating.
640d71a2-002a-5e35-b0a9-d54b83d27fe1 | note | Frequency - Prior to pouring concrete
cb9ac078-b717-56c5-8a38-865a92fd2967 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
012e7a33-4996-59fc-8d4c-f8a5bd9abc5c | note | Conformance Criteria - Photos
37cee42f-80e0-52eb-a5dc-0c50835005ef | note | Records - Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.4 -
ec3978f3-d249-5c5b-ac64-9af0e277b38f | note | ACTION (Hold, Monitor, Witness) - H
2e061309-06a0-5890-a2b8-14b5f1074a1b | note | Detail - All concrete delivered to site shall have 50MPa 28 day compressive strength with 4kg/m3 of Black Oxide Powder
d7ed725f-3041-5641-a6e6-6fb664c3eecf | note | Frequency - Prior to pouring concrete
18ef0795-4d1d-5d15-9592-0d0f73fb949e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Concrete Delivery Dockets
6c59fb44-6268-53f0-aa57-7331d769a34e | note | Conformance Criteria - Delivery Docket added to QA folder
200379a3-337f-5556-8e2a-8a25535c0b36 | note | Records - Concrete Delivery Dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8 - Temporary Works (Formwork)
4986958f-2726-5fa9-aa76-0d6567c42e5c | note | ACTION (Hold, Monitor, Witness) - W
9ed30b2e-8c28-53d8-b79c-95cfa16efaa6 | note | Detail - Formwork to be set to correct line and level
1fd52606-1279-5971-bbcc-5da278b65b0c | note | Frequency - Prior to pouring concrete
fb063cb4-1186-51bb-87fc-03897a3335f0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
e2877f10-0d00-5ab8-be45-f96b94d8c77e | note | Conformance Criteria - Concrete Inspection Record
f018bc91-36a1-530d-8112-5be280c4c915 | note | Records - Concrete Formwork Checklist
| checkpoint | 8.1 -
8f402bca-2813-5e9a-929a-8161f250f734 | note | ACTION (Hold, Monitor, Witness) - H
417cfeaa-064e-5480-9250-4b7590ae2ed1 | note | Detail - Raised table formwork to be 75mm above existing road level and be 300mm in depth and gradients respectively of entry (1:15) and exit ramps (1:15)
cc09e993-a7d8-5274-b430-6d9c0f7489b2 | note | Frequency - Prior to pouring concrete
160486a0-54f0-5394-a2db-b2ea70e96daa | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
065228ce-014c-5e5b-91c0-f8df382d588d | note | Conformance Criteria - Designer to inspect formation level
b7fae449-a98c-5c68-ba0c-53c31dd44c83 | note | Records - Site photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8.2 -
870adcd9-0590-52d6-a738-4e92576a0409 | note | ACTION (Hold, Monitor, Witness) - H
27a7b9fa-6706-5bab-bf5d-7e0d48f4ddd5 | note | Detail - Raised Table ramps to have 250mm depth at entry point and tie into 300mm depth to meet raised table
f463e475-fcc7-5add-a803-26ba3182e4c1 | note | Frequency - Prior to pouring concrete
9f95f583-457b-5bc0-bd2f-4795cda13bae | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
74c43a30-a90c-567e-828f-b07c7e936cfd | note | Conformance Criteria - Designer to inspect formation level
ac69172d-41b2-5259-9f12-1672ab01ff43 | note | Records - Site photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8.3 -
c959049c-fde7-5827-99d4-4c0476ce8150 | note | ACTION (Hold, Monitor, Witness) - H
7735c2eb-ee1d-5d8c-91dd-3411503d7472 | note | Detail - Raised Table ramps to be 1.125m across for entry and 1.125m for departure ramp.Toe to be 0.5m to 1m across for both entry and departure with 50mm asphaltic wearing course
2387bdba-5bb0-59e3-bdb0-5ffc64d56aa0 | note | Frequency - Prior to pouring concrete
d7ffd7fe-96aa-55d3-8e43-962dc86c9a1f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
00607f3b-7add-5d0c-b354-adc4cb49ffa6 | note | Conformance Criteria - Designer to inspect formation level
62c6c662-e66e-5620-bf32-d2ef4c51ccae | note | Records - Site photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8.4 -
1dacbc18-0aa8-5ad1-bbd6-d5c351f8bc23 | note | ACTION (Hold, Monitor, Witness) - H
06d5e058-99be-537d-916b-f5c0f9831a73 | note | Detail - Raised Table ramps to be 1:10 gradient for ramps at entry and exit ramps to be 1:10 relative to the road
dd7610af-ee2c-58cf-bbdb-6b2cfaec60ca | note | Frequency - Prior to pouring concrete
87103b25-8b32-5599-8bb9-f37f649a204e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
a9df64c5-e5c2-5c85-9229-49be131bf352 | note | Conformance Criteria - Designer to inspect gradient level
e99fda58-9bd2-531c-86a2-86915e76d727 | note | Records - Site photos / Concrete Formwork Checklist
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8.5 -
cf396161-d014-5dc1-b356-5b38d04dde65 | note | ACTION (Hold, Monitor, Witness) - H
73a1ad95-98bc-5a40-aacd-e88f29944312 | note | Detail - The Site Engineer and MSQA Engineer must sign off the formwork prior to concrete being poured
75f59b6d-906f-5462-9329-59cd9005e0f9 | note | Frequency - Prior to concrete pour
d4226173-49a7-5bbd-9f71-b051e92dd48c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
30ec5ada-4872-5781-a896-38e1ad829f7f | note | Conformance Criteria - Concrete Inspection Record
254b0b43-1095-558e-972e-ca7d57fabfbb | note | Records - Concrete Formwork Checklist
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Reinforcing
3b6ee58c-729b-575c-90e1-2f2b82b0abec | note | ACTION (Hold, Monitor, Witness) - H
46f71afe-9193-5415-8b1c-9a4e953e87e6 | note | Detail - All construction joints are to contain 2 rows of LESA dowels or similar approved dowels .Dowell system 50mm w/ Black 300*50*6mm plates @600mm centres placed across the construction joint
80ab89e5-1f3c-58bb-910b-36a7b4ba2e1d | note | Frequency - Prior to pouring concrete
2a3d7ab4-ad87-5805-8bcd-aff571155512 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
56fcd899-1cdd-5e8d-8775-4f6accc268ae | note | Conformance Criteria - Concrete Inspection Record
3dc72349-dc3f-564e-81b6-f0382e9da733 | note | Records - Site photos/Concrete Formwork Checklist
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10 - Concreting
6c36ddfb-de8f-569a-96c8-2fdd81bbdc58 | note | ACTION (Hold, Monitor, Witness) - H
b9578acc-8363-5f1f-ad3f-b62aa3c58a44 | note | Detail - The MSQA Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required
71879ea3-476e-57f3-b13d-770835ae2e66 | note | Frequency - Prior to concrete pour
9b066fd6-292c-5843-ba1a-78379a922a59 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
27df3622-f7bb-5fe0-a83b-99db6327dddf | note | Conformance Criteria - Engineer will be notified via email/SMS at least 24 hours before required for inspection
dcfec44c-1786-513c-895c-2b1487c55478 | note | Records - Email / SMS
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10.1 -
ef32e2bd-1be1-5c48-a6e2-efc9ab21e7ae | note | ACTION (Hold, Monitor, Witness) - W
b46c2efa-03f0-5bc1-84d3-137efa622416 | note | Detail - Vibrator to be used throughout concrete pour
3fc17083-78a2-5365-901e-81667a0bdc9c | note | Frequency - When pouring concrete
53169be6-60df-587f-898d-5be32868b702 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
0a3b6d1e-6dc3-5b74-a3ab-4167d75f7fcd | note | Conformance Criteria - Concrete Inspection Record
d5d5d152-53bf-5d0b-bc94-79b9390c6bda | note | Records - Concrete Formwork Checklist
| checkpoint | 10.2 -
7e5b93cd-c260-5805-b7bc-1ee093a3e591 | note | ACTION (Hold, Monitor, Witness) - H
267af595-37da-57c9-8f1a-d4d5f0be45db | note | Detail - Concrete surfaces shall be U5 broomed finish for ramps, and exposed aggregate finish for table top.
e315b397-f7e0-5e8e-9c4c-164c15e38774 | note | Frequency - At completion of pour
dd686742-c28b-5662-8d0b-92915acf38d4 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
ee407f88-59e9-54f6-a370-9c3c382bbb0e | note | Conformance Criteria - Concrete Inspection Record
88c8f855-8561-554c-8050-77fa4745d3d3 | note | Records - Concrete Formwork Checklist
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 11 - Curing
94dacb7a-b156-5419-bd9c-24eefd3ce719 | note | ACTION (Hold, Monitor, Witness) - M
b45a0cab-8278-53f4-a325-be2fa35cece2 | note | Detail - Concrete will be left for 48 hours minimum to cure before traffic is allowed on it.
87f4be58-d0a3-5541-af6c-ac3c1db90716 | note | Frequency - Post Pour
58b14dcd-adf4-5487-9d0e-1f58252330f4 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Monitoring the time allowed for curing
c2e157fd-081b-575d-b02e-dad5de41aabe | note | Conformance Criteria - 48 hours minimum have passed
b9534dd2-199d-52c4-9333-34a27c0345cc | note | Records - Concrete Formwork Checklist
| checkpoint | 12 - Remove formwork
a556e20f-501a-5454-a902-c662ba3f0f1b | note | ACTION (Hold, Monitor, Witness) - W
fa1e5768-bd21-5ba4-a774-d6f9d7b8f67f | note | Detail - Remove formwork after 48 hours
716e3c96-9fb6-51f1-a9c2-0e2e5d5ae689 | note | Frequency - Post Curing
1c146922-3e16-5834-b6e1-94803acd724b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
ef5db697-5156-522b-a698-468f282fae61 | note | Conformance Criteria - Concrete Inspection Record
083a30ab-9709-55da-8d6f-7e99c5b65b26 | note | Records - Concrete Formwork Checklist
| checkpoint | 13 - Asphalt- Concrete extension slab/ Toe
7aa906b3-50ee-5b7b-9613-ed97099d2020 | note | ACTION (Hold, Monitor, Witness) - H
c41ddf57-475d-5c8e-a700-6224a971c041 | note | Detail - Two rows of Lesa diamond placed mid depth @600 C/C along construction joint as per TDM TC0022
3ce763e6-51e8-5b78-8894-efacdfbb7088 | note | Frequency - Prior to pouring concrete
7601d627-2d13-5af4-84a3-f2dcfafaa85e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
8e72520b-9163-5646-9607-777809c579a9 | note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
4490e65d-738c-5ee7-b4a7-8d9d74f683f0 | note | Records - Site photos, delivery dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 13.1 -
ccc62176-3f63-5909-9bee-1a96dde4ebf1 | note | ACTION (Hold, Monitor, Witness) - H
cfef0e9f-2b0e-5ce9-936a-2b3e9e0eff66 | note | Detail - 200mm thick 50MPa Concrete with two layers of 663 mesh
58ddd2d7-6909-52ea-b1cc-e2e332e01e95 | note | Frequency - Prior to pouring concrete
e5350613-88b6-52b1-93ed-edba1210ae05 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
a94f182f-f35d-5660-b791-eacd2a4e3960 | note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
74597500-7539-54b9-81c8-6646c5393d01 | note | Records - Site photos, delivery dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 13.2 -
134fba75-4f49-552b-8336-67b1cc305b38 | note | ACTION (Hold, Monitor, Witness) - W
9c106721-383c-5829-9021-b19d2b8b778e | note | Detail - Tack Coat between AC and Concrete slab
e7c01fdd-e094-5a75-927d-f91ce573f88c | note | Frequency - Post Curing
09b43418-fe8f-5a59-8ffc-d418d44a05e0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
511aaee8-8b4f-5551-a51c-33945b600bb5 | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
845ebd63-4a59-5852-b253-9a63a4a876aa | note | Records - Site photos
| checkpoint | 13.3 -
8e9e6b52-6442-54dc-9b4a-3ff730ec8074 | note | ACTION (Hold, Monitor, Witness) - W
afafa5f8-1fee-51e4-bdec-80122deb471b | note | Detail - 50mm thick DG10 / Mix 7
ff9b75dd-9a61-502f-a476-1b27c8da22cd | note | Frequency - Post Curing
dc27394a-ccbe-5827-b0f1-07808cd7c193 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
8a6141e0-e2e7-530e-849e-cdcf2cc51da0 | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
13252ec1-2859-5b17-bb17-b58e8b1c70e5 | note | Records - Site photos, delivery dockets
| checkpoint | 14 - Lot Number QA File
59a8eca1-0148-5088-b53c-2315038ac121 | note | ACTION (Hold, Monitor, Witness) - W
2d8b98e1-e8e3-5921-9598-ef5380171ded | note | Detail - Ensure all QA Records,site photos and incident cases (OFIs) are closed and included within QA file
ea70c2e3-9b5c-5d5c-8f28-809c0267d99d | note | Frequency - At completion of Lot
e06c87ee-0186-587c-8b36-d98e7e8cc312 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
c9aad2f7-ddee-5cc0-b884-454957686ced | note | Conformance Criteria - All QA files compiled and sumbitted to client
d772611e-3019-5e8a-b256-3f3b3fe58ea0 | note | Records - QA records
| checkpoint | 14.1 -
ab712974-099e-53cb-8e70-6f66be7fa04f | note | ACTION (Hold, Monitor, Witness) - W
ee32b7f1-6906-5f91-bb72-6e1e594934e2 | note | Detail - Delivery Dockets to be included in QA file
02ea7d99-d5cd-55e9-90ee-2a93647772c6 | note | Frequency - At completion of Lot
656015b2-3e6c-5b84-b487-dcd2004900e4 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
669721fa-467f-5a96-a515-ebe5435f9c05 | note | Conformance Criteria - Delivery Dockets to be included in QA file
71fe37e9-8d22-5b05-bb96-26b8ebfdf734 | note | Records - QA records
| checkpoint | 15 - As-builts
b08f14aa-1af7-5671-8e6c-4ffa85fa3ecd | note | ACTION (Hold, Monitor, Witness) - H
01e44315-2907-5341-a8ba-b6ed06bea9d8 | note | Detail - Red pen mark up drawings to be included in QA file
552b17cb-7ad5-5239-819f-c9f8893ebc51 | note | Frequency - At the completion of the Lot of work
edc3894e-f120-52f0-802c-23d87d6d548f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
a1cc0218-4a51-5a10-8cbf-8916d126d7b3 | note | Records - Asbuilt Drawing
| signoff | AUTHORITY HOLDPOINT
| checklist | Sheehan Ave - ITP - Traffic Islands |  | Traffic Islands | bc8ce031-cf01-4852-b193-159b04364a66
| section | Materials
| checkpoint | 1 - Mountable Kerb
98be0f9b-ad3e-59c0-bdbe-42f8e38eb172 | note | VERIFICATION ACTIVITY - QA FORM
3b71cec9-21e2-5948-9e4f-d2148528a2de | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002
395771d7-9b05-5066-9e0a-962a18cc78a3 | note | FREQUENCY - Everysite
203d768e-d99f-55e7-b6bd-a9f16db7ca2e | note | ACCEPTANCE CRITERIA - Mountable Kerb to be laid using precast hand-laid and painted with two coats of reflective paint
c690906c-00b1-59e9-952d-85534aa8f8b3 | note | Hold Point - Inprocess Inspection
f9c6db08-b2c5-5322-ac65-4677c142c984 | note | Records - FH concrete QA sheet, photos.
0ad6fc16-18f1-572b-bb9f-4e0e3b792c50 | note | Onsite Responsibility - Site Engineer
| section | Construction
| checkpoint | 2 - Survey Setout
3288d501-4e12-5b09-b20e-83c1eb54ffe9 | note | VERIFICATION ACTIVITY - Survey
9890337d-9ea7-58e2-adbc-f567635a63f8 | note | METHODS OR REFERENCE - Setout Kerb Alignment required to construct to design
fcf75e83-5683-5ec2-aa02-82ffb8aafacd | note | FREQUENCY - Prior to commencement.
c9e6d8f9-5724-5952-b8b1-e93ade194fbb | note | ACCEPTANCE CRITERIA - Survey
c310745f-7d24-532e-8b6d-3588766ed3bd | note | Hold Point - As per Construction Drawings
1adcf586-c63a-52c0-a97f-8844becc47d6 | note | Records - Survey Receipt.
7deafc1c-822c-59f5-8bc3-fa3eadd2845a | note | Onsite Responsibility - Site Engineer
| checkpoint | 3 - Concrete Island
fc08e85d-66c1-5b53-9ec4-780336f80139 | note | VERIFICATION ACTIVITY - QA FORM
20ad9134-a4bc-54a9-9bd8-0f0f205c353c | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002, TDM Technical Standards - IS0001 & IS0003
1f923be9-5909-59d8-a4c7-a404b27a2ce0 | note | FREQUENCY - Each Site
f5de6a3f-b90e-5ea3-9c3c-194dc668a8b9 | note | ACCEPTANCE CRITERIA - Kerbs to be haunced with 20MPa Concrete, Basecourse to be 150mm min thickness of GAP65
e0c00a9e-1953-5b11-be8d-fe31afe26422 | note | Hold Point - Inprocess Inspection
c7b990bd-cdfb-5925-8e4c-54b9d5b51fae | note | Records - Photos
8f99278e-aae5-545b-b627-6c5e154a2f7d | note | Onsite Responsibility - Site Engineer
| checkpoint | 4 - Concrete Infil
15153ff6-f572-558a-8f3e-40acba5aa89b | note | VERIFICATION ACTIVITY - QA FORM
2b9af827-d8e1-5ff0-b0f8-96db4e71ae79 | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002
3499d558-cffd-58ac-8f7d-9d212dd1473c | note | FREQUENCY - Each Site
ce82020b-79d4-52e7-a6fb-8152d8abaaf0 | note | ACCEPTANCE CRITERIA - 180mm depth of 20MPa broom finish unreinforced Concrete with 4kg/m3 red oxide, Cross Fall of 2% or max rise in centre of 180mm
5c94ddc8-5ca4-5b20-940c-4c829ed1bf05 | note | Hold Point - Inprocess Inspection
c5637bb0-b95a-504d-96cb-ecd8d012af4c | note | Records - FH concrete QA sheet. Concrete delivery, Dockets kept as record
26409d92-e71a-5a5f-9c4a-d9bba5df5e70 | note | Onsite Responsibility - Site Engineer
| section | Asbuilts
| checkpoint | 5 - As built information
d614c899-9bad-5d71-93d9-61393293e51c | note | VERIFICATION ACTIVITY - Drawings
2494d6bb-4faa-5f8a-a846-3e858a3ea2a4 | note | FREQUENCY - Every Site
74673376-e17b-5ea1-a55a-8e18b3b00c19 | note | ACCEPTANCE CRITERIA - As built drawings
6ff4b6bb-238f-5789-9faf-f241ae60a1a3 | note | Hold Point - In Process Inspection
55d397ae-a97e-5fce-87a1-8aa365462368 | note | Records - Asbuilt records
77996391-ac9d-5f2b-9431-3b10a76b5830 | note | Onsite Responsibility - Supervisor and Engineer
| checkpoint | 6 - RAMM DATA
39205635-c29e-5e6a-9f55-4445fa94557d | note | VERIFICATION ACTIVITY - RAMM DATA SHEET
7e349841-9ed6-50e5-8022-4978aa051b75 | note | FREQUENCY - Every Site
30214802-357b-56b2-b179-1b232997bc3a | note | ACCEPTANCE CRITERIA - RAMM SHEET
b92f940c-05f0-55bc-bb17-89cfdebac690 | note | Hold Point - In Process Inspection
3c5e311b-6482-5fc8-9318-d78cb1f0a376 | note | Records - Asbuilt records
bc988a67-597c-59f5-afa8-e60f37e0b026 | note | Onsite Responsibility - Supervisor and Engineer
| checklist | Stancombe Road - ITP - Enabling Works - Footpath + Pram |  | ITP - Enabling Works - Footpath + Pram | fd266961-f4e5-455c-b9ed-41246d7afede
| section | Site Set Out
| checkpoint | 1 Site Set out
1e4c7a14-897a-434e-9c71-20fb4d22f547 | note | VERIFICATION ACTIVITY: Surveyor
4d8d0429-5f81-4700-af48-172db9507f85 | note | METHODS OR REFERENCE: Surveyor
5c570415-51dd-4201-9f26-bdd0b2e3e290 | note | FREQUENCY: Every site
14368743-6dda-4527-bf63-000cd6c5e5c8 | note | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
4016eb69-5169-450a-a865-e9366d9fa180 | note | Hold Point: Mandatory HOLD POINT -
a75b5c4f-7cfe-41bc-821b-4e08372710c7 | note | Records: Onsite records/photos
c6456509-200b-4d96-a063-6629414d328e | note | Onsite Responsibility: Site Engineer
| signoff | HOLD POINT
| section | Construction
| checkpoint | 2 Concrete Footpaths
e16459ac-9503-47f9-916c-6c93334ca53f | note | VERIFICATION ACTIVITY: QA FORM
57fafe55-a8eb-4e07-ba39-725bec2f9483 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
5074c38e-486d-4335-b700-f32e40b91340 | note | FREQUENCY: 10m Intervals
37ed3d3b-3696-4c2e-9cd1-247ac09bc27f | note | ACCEPTANCE CRITERIA: Subgrade -(CBR > 3.5); Subbase - 150mm min. thickness of GAP65. ; Basecourse - 100mm thick AP40; Clegg CIV > 15; Surfacing - Concrete 150mm and 20 Mpa @ 28 days. 4kg/m3 blackoxide with broom finish
d41d7e97-c286-4da4-9cac-b5be67578822 | note | Hold Point: Inprocess Inspection
9d2bbd0c-4348-4144-b269-2b29231451f5 | note | Records: FH concrete QA sheet. Concrete delivery Dockets kept as record
511ce254-c572-4dfd-819d-fa2c91e89758 | note | Onsite Responsibility: Site Engineer
| checkpoint | 3.1
fe62006c-ae45-4b1d-98cb-1f70fc028fb4 | note | VERIFICATION ACTIVITY: Visual
6f80c284-eea0-45a3-b382-28abb9255f26 | note | METHODS OR REFERENCE: Drawing No: 2020-AT-006-03_G035 - SECTION A -G020
26164d12-8455-4a8b-a71a-1176cf2571c6 | note | ACCEPTANCE CRITERIA: Topsoil and grass on either side of the footpath section A - G020 with 1.5% gradient.
9bf6d0b2-734a-4449-b372-14065b0386bd | note | Hold Point: Inprocess Inspection
c462bc1d-989f-4c71-aac8-d1384d13b2db | note | Records: FH concrete QA sheet. Concrete delivery Dockets kept as record
44e328ca-672b-45cc-a300-f556c94711b3 | note | Onsite Responsibility: Site Engineer
| checkpoint | 3.2
90b67476-ec41-48d7-b550-890d5174e94a | note | VERIFICATION ACTIVITY: Visual
1d00f7ff-5354-4837-b324-4215b767bd21 | note | METHODS OR REFERENCE: Drawing No: 2020-AT-006-03_G035 - SECTION B -G020
97668250-00f2-4526-a326-0b97b2fd054b | note | ACCEPTANCE CRITERIA: 250mm mean diameter basalt rocks on either side of footpath under Section B - G020 with 1:2 gradient
60fe3450-22be-43a1-af5a-85f4d65c577e | note | Hold Point: Inprocess Inspection
fdf4e0d9-432c-41ce-b734-537da79e88df | note | Records: FH concrete QA sheet. Concrete delivery Dockets kept as record
36512a32-3bcc-44cc-ab50-e03d4a666e20 | note | Onsite Responsibility: Site Engineer
| checkpoint | 4 Concrete Pram Crossings (PX)
aacbc74b-fd5f-409c-8473-01e50537e088 | note | VERIFICATION ACTIVITY: QA FORM
e8f08555-8ce5-4808-b3d1-de5207dcfb07 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0006
a2993241-a291-4c72-b8ef-b57b547324f7 | note | FREQUENCY: Each PX
14f3c499-31e4-4cd7-98f2-861a96bbbb1f | note | ACCEPTANCE CRITERIA: Subgrade - (CBR > 3); Basecourse - 100mm min. GAP40 thickness; Clegg CIV > 15; Surfacing - Concrete 150mm and 20 Mpa @ 28 days. 4kg/m3 blackoxide with broom finish
49f61d85-4a51-4c8d-8307-d7bee29e0719 | note | Hold Point: Inprocess Inspection
6c4895f6-b719-4f31-8ce1-946c0054d431 | note | Records: FH concrete QA sheet. Concrete delivery Dockets kept as record
43a2063e-4a27-4d63-a42a-fcb5bdb39940 | note | Onsite Responsibility: Site Engineer
| checkpoint | 5
b9bd6769-9071-4fee-acc6-784fe47f6188 | note | VERIFICATION ACTIVITY: QA FORM
36c24408-48b0-41d7-9d3e-121a07e514cd | note | METHODS OR REFERENCE: TDM Technical Standards - FP0006
6ed89e3e-6bae-4c47-b4cf-6cd66e8e2b8a | note | FREQUENCY: Each PX
797dc9b8-9a20-4c33-ba24-0fc4bf5384cf | note | ACCEPTANCE CRITERIA: Warning TGSI tiles should have 100mm concrete slab underneath
09dfb963-c81f-4027-baf1-97db48909fca | note | Hold Point: Inprocess Inspection, Measurement
d1a2031b-b543-4be7-834b-e0575c7f5b6b | note | Records: FH concrete QA sheet. Concrete delivery Dockets kept as record
99e906c4-4135-4176-a681-0d27c812eefa | note | Onsite Responsibility: Site Engineer
| checkpoint | 6 Tactiles
8605d9d7-f4c3-43bf-b2e3-d17a2ef98f67 | note | VERIFICATION ACTIVITY: Visual
51aa71cc-9b7e-4ed6-8aad-e8bfb3d54ffc | note | METHODS OR REFERENCE: NZTA RTS Guidelines for facilities for blind and vision impaired pedestrians; AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
cfa6abd6-ccf9-437d-8962-515a593e192b | note | FREQUENCY: Everysite
ab55a1b1-e7b5-4fa3-a935-084c1b37c699 | note | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
8e2357c8-b463-40b3-a6cf-3b2ad564b9bd | note | Hold Point: Inprocess Inspection
ff80715e-43e7-49d9-aeaf-9019ef60bed6 | note | Records: Photos
88a3fb32-d059-452d-9960-fcb777024dbc | note | Onsite Responsibility: Site Engineer
| checkpoint | 6.1
819757d4-083f-4f9f-b8a7-7fb78f451b7e | note | VERIFICATION ACTIVITY: Visual
b56fc4f0-8a44-4c1d-b2d9-62ae7971019b | note | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
2b4c4055-c3ed-45bb-b113-7a4927abc638 | note | FREQUENCY: Everysite
23d25f60-f9d7-4346-99eb-15358ab9e91c | note | ACCEPTANCE CRITERIA: Edge of warning indicators to set back 300mm from the face of the kerb or lane, extend the full width of ramp and be 600mm deep.
d438d1d1-c997-42ef-b86f-82a1efaf2c4d | note | Hold Point: Inprocess Inspection
000eb175-2480-438c-ba08-16a3b1703fc7 | note | Records: Photos
840c32e4-c731-4a8b-98b2-3f44a2f961bd | note | Onsite Responsibility: Site Engineer
| checkpoint | 6.2
fa45484e-b77f-4fe6-96e3-77430e0a4d03 | note | VERIFICATION ACTIVITY: Visual
7873e08e-28a3-42cb-84bd-a5a7a378e261 | note | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
6381ba2c-5f91-4547-8294-c21a7d8ed570 | note | FREQUENCY: Everysite
fdd41caf-64c1-41c0-80fb-f3d0d74a9bda | note | ACCEPTANCE CRITERIA: TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
0fb4a6a7-62d3-4432-8341-3247354ed01d | note | Hold Point: Inprocess Inspection
9efd92e0-aa78-455b-baad-1476b3923ff5 | note | Records: Delivery Dockets/Photos
c72dcc25-d4fd-4f4d-95d0-a33f1e24b8c1 | note | Onsite Responsibility: Site Engineer
| section | Asbuilts
| checkpoint | 7 As built information
cd1c9f24-9924-4987-9521-d1b345bc36c0 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
9a8e92d4-7a80-43cb-9821-3826d88fc333 | note | FREQUENCY: Every Site
b4acd19d-99b4-48e8-b872-5aa4bfe30945 | note | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
9e6650b7-5407-4b68-a0e0-95c6f5be3850 | note | Hold Point: In Process Inspection
e7071eea-90b1-418b-af17-69e9547ca784 | note | Records: Asbuilt records
3a9a001f-70e7-439f-a268-517681984966 | note | Onsite Responsibility: Supervisor and Engineer
| checklist | Stancombe Road - ITP - Traffic Islands | itp | ITP - Traffic Islands | 65da4271-09f8-47e3-b8de-aa73d109da04
| section | Materials
| checkpoint | 1 Kerb
fa623a68-67cc-4a51-981b-5dffc9102a79 | note | VERIFICATION ACTIVITY: QA FORM
bd67a7cc-8a72-49b7-a7f2-e315a2db18db | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
126aef28-de76-4ec2-9275-398ad15aa3e8 | note | FREQUENCY: Everysite
6810be6d-5b4c-4fc0-8b72-3e02a0e275ce | note | ACCEPTANCE CRITERIA: Kerb to be laid using precast hand-laid
7c19e72f-b8ba-4093-a80e-666f59b09847 | note | Hold Point: Inprocess Inspection
d51cf50a-4751-4889-af04-ba1be4aa4b11 | note | Records: FH concrete QA sheet, photos.
c6386a31-6307-41b2-b2ce-2c390ec87835 | note | Onsite Responsibility: Site Engineer
| section | Construction
| checkpoint | 2 Survey Setout
be2c4477-adb2-4679-8e37-3fe9c8d443ff | note | VERIFICATION ACTIVITY: Survey
646d13ac-c7cc-4260-ad68-c4ef7257e90d | note | METHODS OR REFERENCE: Setout Kerb Alignment required to construct to design
157c53e9-ebee-4e37-8fe6-70c8a34d5172 | note | FREQUENCY: Prior to commencement.
b786b4f9-c51f-4615-b2c2-ab76ab5e30a5 | note | ACCEPTANCE CRITERIA: Survey
d86352d0-1476-4e50-b773-36c9257c8306 | note | Hold Point: As per AT Drawings 2020-AT-006-SD-G105
3042c3d5-c6a9-404b-8db2-7e7c93a259d4 | note | Records: Survey Receipt.
13708467-655d-48b0-83bc-ba69c8652b6d | note | Onsite Responsibility: Site Engineer
| checkpoint | 3 Concrete Island
592d45d5-64ff-4e89-8546-d7fb5eaa66d7 | note | VERIFICATION ACTIVITY: QA FORM
a41586b4-8349-4815-8f8e-dd5bcfda2fd2 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
a65cde82-0537-4c10-bb87-f8816c89a0f8 | note | FREQUENCY: Each Site
9f9a71a6-49c9-4661-bdbe-5b369d48c7bc | note | ACCEPTANCE CRITERIA: Bonding Agent to be applied on existing surface Mountable Kerbs to be sticked on to the existing road using suitable glue.
b09d4688-9916-4586-9838-67753cc99c2e | note | Hold Point: Inprocess Inspection
5cf88927-1a6a-45da-a7a1-73d5eb5931f0 | note | Records: Photos
f46d324b-4fbf-45b0-b22f-e2f2c1394dcc | note | Onsite Responsibility: Site Engineer
| checkpoint | 4 Concrete Infill
a7e0f38b-c66a-4eab-8ddd-27760c4d3179 | note | VERIFICATION ACTIVITY: QA FORM
33a75ccb-85ac-4288-b6b8-2cf013d5b6d4 | note | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
1c2d8eca-ec3e-47de-893e-38cdee4848c5 | note | FREQUENCY: Each Site
a0e0a413-adba-442d-ab59-64019bb06535 | note | ACCEPTANCE CRITERIA: 150mm depth of 20MPa Broom Finish Concrete with 8kg/m3 of black Cross Fall of 2% or max rise in centre of 150mm
bbd01586-1722-42c9-8adf-b7b7932c5406 | note | Hold Point: Inprocess Inspection
aba085be-501d-47f2-920e-26c44e2b9a39 | note | Records: FH concrete QA sheet. Concrete delivery Dockets kept as record
11e195af-e60c-4a6a-9369-4e0f65176c33 | note | Onsite Responsibility: Site Engineer
| section | Asbuilts
| checkpoint | 7 As built information
b80fb9f3-9273-4266-ab07-463bbb9388eb | note | VERIFICATION ACTIVITY: Drawings
9aaba3c1-e6c7-4854-90dd-47eb39c679ce | note | FREQUENCY: Every Site
7ddb194e-a972-4806-9087-350b39973b9b | note | ACCEPTANCE CRITERIA: As built drawings
a960a5fe-2cc1-47d7-8ecb-62f63514d7c3 | note | Hold Point: In Process Inspection
39f5f16a-de1d-47a4-a51a-626e81adf860 | note | Records: Asbuilt records
68295748-109a-4600-bd64-fb09de5e1137 | note | Onsite Responsibility: Supervisor and Engineer
| checkpoint | 7 RAMM DATA
d3985ace-934b-45f7-b9b7-2b25a503f8ec | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
6b9d2f00-d9d5-46e4-bea3-4158f1e36a29 | note | FREQUENCY: Every Site
ac49c353-9647-46cd-92af-34f4ff55cb7f | note | ACCEPTANCE CRITERIA: RAMM SHEET
0fced6eb-a759-41cc-b79f-7d48d02a6604 | note | Hold Point: In Process Inspection
29147546-8ff7-4ffb-a6f0-ac075234fbf1 | note | Records: Asbuilt records
db89d2e0-8beb-461d-a0dd-36e76f773300 | note | Onsite Responsibility: Supervisor and Engineer
| checklist | SYS - Graeme Ave - ITP - Enabling Works - Footpath, Kerb and channel | itp | ITP - Enabling Works - Footpath, Kerb and channel | 75776e96-50e6-481b-bbb8-9579de41a6da
| section | Site Set Out
| checkpoint | 1 Site Set out
ddbf4851-6782-4dc9-8ecf-7cb0af29712b | note | VERIFICATION ACTIVITY: Surveyor
6fa8e851-a74d-4306-8ab9-d8969e9a99b3 | note | METHODS OR REFERENCE: Surveyor
f71bce22-cd4b-4766-93d7-261cc7365384 | note | FREQUENCY: Everysite
b7c44e7d-ead7-4fd3-af6b-ea7e6c9e462a | note | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
3dc83e1d-9971-4985-bde4-f6415d4aeb7f | note | Hold Point: Mandatory HOLD POINT -
10c4a63e-2fde-4ad5-bc99-6cd54ac5dbfa | note | Records: Onsite records/photos
93e0a440-ec9e-4f87-b1d6-8ceee24dc4e8 | note | Onsite Responsibility: Site Engineer
| signoff | HOLD POINT
| section | Materials
| checkpoint | 2 Kerb & Channel
3051cf60-9bf9-4f3d-b5e8-6ef645de3eb0 | note | VERIFICATION ACTIVITY: QA FORM
da2443c6-a486-4bae-b1e5-15ea16b99ad4 | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
3906b831-e219-458b-b1cb-862957801317 | note | FREQUENCY: Everysite
5d675dcf-167d-4688-a464-5b0af8371e00 | note | ACCEPTANCE CRITERIA: Kerb & Channel to be precast hand-laid. . Kerbing laid on 300mm min Gap 65 subbase in roads and 100mm GAP 40 in footpaths (CBR>5).Concrete 20mpa @28 Days
a6f84927-d4cb-4998-b797-908fe82e4687 | note | Hold Point: In process Inspection
b91f6fc9-78cf-47bd-a2d8-1cd50cbeb400 | note | Records: FH concrete QA sheet, photos. Concrete Plant Docket
678c03ed-1a5b-4e95-b9a8-bd6fc0b8fce3 | note | Onsite Responsibility: Site Engineer
| checkpoint | 3 Channel Level
3aebc5bb-25f4-4e66-bd27-a34048026469 | note | VERIFICATION ACTIVITY: QA FORM
c4a60afa-39a2-4e17-9889-66180d561fe1 | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
5b3a5b37-20e9-4e71-8152-de720bb14854 | note | FREQUENCY: Everysite
207479d4-92d1-40f3-a869-254316bda6b8 | note | ACCEPTANCE CRITERIA: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
94936304-4b47-4273-8836-f1f12aec761d | note | Hold Point: In process Inspection
c3a1770f-cd18-498b-a9e3-7c4a34440310 | note | Records: FH concrete QA sheet
9fdd6928-3013-4ded-b2c4-c58df62ea723 | note | Onsite Responsibility: Site Engineer
| section | Civil Works
| checkpoint | 4 Concrete Footpaths
010e1387-dadd-4216-9ff9-642d398a00c1 | note | VERIFICATION ACTIVITY: QA FORM
d8c2ea60-b237-4230-bb55-57e4401cb2f3 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
9248cc05-a8dd-41ba-8d35-8e9971453fd6 | note | FREQUENCY: 10m Intervals
7d2c4c52-9d4f-40d7-83cf-1b1c7df5ebf9 | note | ACCEPTANCE CRITERIA: Subgrade -(CBR > 3); Basecourse - 100mm min. thickness GAP40; Clegg CIV > 15; Surfacing - Concrete 100mm and 20 Mpa @ 28 days. 4kg/m3 blackoxide with broom finish
74d6d778-6510-4711-8374-87e59e9ce6a6 | note | Hold Point: In process Inspection
28a9afce-e62c-452b-9d5b-5fb830043984 | note | Records: FH concrete QA sheet. Concrete delivery Dockets kept as record
b0b71762-6ef5-4c66-8dfc-b0dea9026224 | note | Onsite Responsibility: Site Engineer
| checkpoint | 5 Concrete Pram Crossings (PX)
16dcf99c-0395-40a6-8a84-2afe711c3c63 | note | VERIFICATION ACTIVITY: QA FORM
057e0743-6dc6-414d-8f21-5692bd316bfd | note | METHODS OR REFERENCE: TDM Technical Standards - FP0006
623f714f-8be4-40bb-99ae-ce74b691c59e | note | FREQUENCY: Each PX
33c0504f-d69c-408c-940f-3debc779ffeb | note | ACCEPTANCE CRITERIA: Subgrade - (CBR > 3); Basecourse - 100mm min. GAP40 thickness; Clegg CIV > 15; Surfacing - Concrete 150mm and 20 Mpa @ 28 days. 4kg/m3 blackoxide with broom finish
ac4f4091-574e-4b28-98ae-0a5ca90f8e7e | note | Hold Point: In process Inspection
c1eb0736-e609-4916-aea2-9d954b899f09 | note | Records: FH concrete QA sheet. Concrete delivery Dockets kept as record
58e717d9-deaf-4455-a1d1-03552c77b92c | note | Onsite Responsibility: Site Engineer
| checkpoint | 5.1 Concrete Pram Crossings (PX)
181bda09-b388-4b3f-b64d-a9abca2aba43 | note | VERIFICATION ACTIVITY: QA FORM
2b5ef084-00c8-493c-8b0c-d2cbe4cbe316 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0006
0d0d1deb-b9a7-4f3e-9c27-647f2f0150e3 | note | FREQUENCY: Each PX
d6754625-c053-412d-a990-ce7bb9d73ca6 | note | ACCEPTANCE CRITERIA: Warning TGSI tiles should have 100mm concrete slab underneath
317e18fd-d229-47da-8cf1-06f9bbb92ab9 | note | Hold Point: In process Inspection, Measurement
3d1f43c8-af21-450d-a702-16363ef8d8d2 | note | Records: FH concrete QA sheet. Concrete delivery Dockets kept as record
13a830d4-1d9d-46af-ab44-4abcc86dd002 | note | Onsite Responsibility: Site Engineer
| checkpoint | 6 Grass Berms
5ed909d1-6421-432d-97fa-e40f8b197e30 | note | VERIFICATION ACTIVITY: Visual
eec16ba6-01f4-448a-94eb-d70671cada8e | note | METHODS OR REFERENCE: ATCOP Section 12 Footpaths and Pedestrian Facilities
07972f8d-5755-49ac-a778-01ba62350c97 | note | FREQUENCY: 10m Intervals
7b6e382e-bbf4-4ed6-a9a8-95f06a8b60d3 | note | ACCEPTANCE CRITERIA: 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
426ff477-f0d3-46d8-9178-9c9fc8169851 | note | Hold Point: In process Inspection
5881e416-4a14-4d95-9638-5b26da8aa368 | note | Records: Photos
f1ba3078-6532-4e18-a9eb-0eb84d299407 | note | Onsite Responsibility: Site Engineer
| checkpoint | 7 Tactiles
6e9c1805-8995-4c17-a6ab-a5ab7c859305 | note | VERIFICATION ACTIVITY: Visual
dd20db48-d7e8-4680-b441-aa0f0f59ea0c | note | METHODS OR REFERENCE: NZTA RTS Guidelines for facilities for blind and vision impaired pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
9d023a4a-9b72-445b-b87e-0c6beaed1220 | note | FREQUENCY: Everysite
5b13c535-81f6-4142-ba49-540e7d8cc331 | note | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
5e3e9c5e-12b8-40f1-accf-ce7e0ff09409 | note | Hold Point: In process Inspection
096eba49-1b3e-4620-9d1f-0e8fe29577a7 | note | Records: Photos
23844e89-d32c-4fb5-81cf-a13f3e81659b | note | Onsite Responsibility: Site Engineer
| checkpoint | 7.1 Tactiles
5cf1303e-4296-4491-9e88-1e2625f0a4e3 | note | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
7022b0d9-bdb1-4cc2-aa96-4ca80f7b6813 | note | FREQUENCY: Everysite
0c27c4ca-bf10-4b3a-a3ea-aa4eab1ce7a0 | note | ACCEPTANCE CRITERIA: Edge of warning indicators to set back 300mm from the face of the kerb or lane, extend the full width of ramp and be 600mm deep.
18d525e5-8b26-4d23-86a1-cea15270c694 | note | Hold Point: In process Inspection
b322d525-0c8e-4eb9-983b-8fcfe44ff606 | note | Records: Photos
6a3a35dd-4c51-4802-bd72-798d0626da08 | note | Onsite Responsibility: Site Engineer
| checkpoint | 7.2 Tactiles
58f5320f-c67b-44e3-aa22-30f1cb154f23 | note | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
9601367f-19d8-4e96-a8c6-64c06f940bdf | note | FREQUENCY: Everysite
0d5443f5-fbca-4009-85af-8adce1a4d635 | note | ACCEPTANCE CRITERIA: TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
537cba37-c0c0-4533-91da-16f836f683d5 | note | Hold Point: In process Inspection
21226592-d23c-4a1b-8ab1-0591d16790db | note | Records: Photos
3249939c-3092-4e0e-b444-b8845885a66a | note | Onsite Responsibility: Site Engineer
| section | RAMM Data
| checkpoint | 8 As built information
fc411406-d276-49dd-ad73-9e2bb9dfd3b0 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
369deb07-0a8f-499b-8072-c41c501f2057 | note | FREQUENCY: Every Site
b820da13-b4e7-4679-972d-71e2cbb739b1 | note | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
d7f1a98e-1e0e-432c-a835-e371dd9ac6a5 | note | Hold Point: In Process Inspection
529fc5bb-0c9f-490d-a82a-5b1da48159d4 | note | Records: Asbuilt records
1b327156-63b5-41b4-9b22-3035f55cc755 | note | Onsite Responsibility: Supervisor and Engineer
| checklist | Triangle/Mokora - Ducting and Traffic Signals | itp | ITP - Ducting and Traffic Signals | b3c2130e-9f1d-4366-b99e-506a112601c8
| section | Ducting
| checkpoint | 1 - Permits
53b2afc1-acb2-586a-8571-a49eea0c611b | note | Inspection / Test Point - Permits
27032a19-e659-5ff9-9298-77aca02897b9 | note | ACTION - H
42f13e09-0ade-514d-b0f1-a0e38214747b | note | Detail - Obtain Permits
8c4e987e-3e56-5535-afc2-7374dc74dbe2 | note | Frequency - As required
d2d315b8-0ee7-5561-abdc-9ab715d5fc78 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
ef264d2a-23e3-50ef-90dc-7f7b45fc8e79 | note | Conformance Criteria - Authorisation to work, dig permit and first gas permit obtained
96e422b0-d724-55ba-801b-df0b27dca77d | note | Records - This ITP signed
86514a1e-a924-5bd5-a1af-d2337cba11ba | note | FH Initials - Site Engineer
| checkpoint | 2 - Design
c02560ae-fcd2-59fa-9157-4ef01b73e1b0 | note | Inspection / Test Point - Design
16be970f-c364-5af2-91dc-7a9f7c4106bc | note | ACTION - H
281a2c6d-cedc-5d5a-acbf-1e106d73c880 | note | Detail - Ensure that Design is approved and Drawings are of the latest revision
4b7debbc-31c1-53b9-8be8-466487abc5ab | note | Frequency - Prior to commencement
b56042f4-2c79-5a73-b08b-c2a4d2cf51e8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
6eec18cd-fc51-5d33-8b01-d72c817fdae6 | note | Records - Check Drawing Register
8df0694c-fce7-5626-98dd-e5c0471f3567 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Survey set out
c079b95a-09b2-5707-9b6e-e5fc800b9d93 | note | Inspection / Test Point - Survey set out
f0b8b5bf-d839-5376-b160-ef311ae4d2ee | note | ACTION - H
1262a144-88a8-5daf-b355-a48e2d1ab3a5 | note | Detail - set out ducting alignment and EOS FL depths. set out and mark all known services along the cable corridor.
4d75dc16-19c5-5e1f-89a2-7c6d9ac18320 | note | Frequency - Prior to commencement
b082723b-36d5-5351-9f0d-84ff31499389 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
982a56f1-6bef-5997-ad54-99cadbed28b1 | note | Conformance Criteria - Consistency with Drawings and Specifications
d53432f1-8ff8-52dc-bbbd-4ec83d7fccfb | note | Records - Survey Records
a465725c-6c0a-5372-8a3c-e06e1c4a3ac6 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.1 - Survey set out
7efc82cb-49c8-54c4-b6fc-9e938ca1206b | note | ACTION - H
493c628c-4cc1-5e10-ac5a-28ee1bde0343 | note | Detail - Confirm with Engineer on site the exact location of all posts, foundations, signs, cable chambers, cable ducts, loops and loop termination boxes( Toby boxes) before installation.
0245a2c0-c98d-5163-9e19-d2e166358a40 | note | Frequency - Prior to commencement
d620ce6f-a5c0-5ee0-bc7e-fc23aeb594e1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
b664973e-5778-5886-89e0-a81910ca3baa | note | Conformance Criteria - Consistency with Drawings and Specifications
3074b02c-f637-5db6-b31a-f5ae71c08d37 | note | Records - Photos / Engineers approval documentation
1fa5f70a-b366-5260-aec7-52ad1a7d2955 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Locate existing services by hand digging/ hydrovac
6c92a8cd-cf76-566e-aa8e-496d3fcd96c3 | note | Inspection / Test Point - Locate existing services by hand digging/ hydrovac
769fa145-c025-5d4a-b7d4-8b323d892863 | note | ACTION - W
7560d5f1-0f10-5928-b7e1-0b195f3895ab | note | Detail - Ensure all services conflicting with the line of trench has been exposed by hand digging or hydro excavation
12a9894e-25fd-5fc5-83f2-822440e58bb5 | note | Frequency - Prior to Installation
4106413a-20a4-5c72-9090-797ed2273555 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Potholing
bcd9e38b-05a2-5ade-a345-20432fd9092f | note | Conformance Criteria - All conflicts have been located and survey as built recorded
81087485-4ed2-544e-8518-01280fae6130 | note | Records - Digging/Excavating Control Checklist
4ebf0403-ba09-5574-9174-7caa292c33c5 | note | FH Initials - Site Engineer
| checkpoint | 5 - Material Compliance
a9e61cc5-f137-537c-9f9e-71d3d94270b0 | note | Inspection / Test Point - Material Compliance
1a7bdcf1-aa37-5c02-ac88-64df113265c8 | note | ACTION - H
005224a5-6262-534c-8882-7103d01b4456 | note | Detail - Ensure duct pipes and poles are as per drawings and specification
52c532e4-75ad-5ba9-b0d9-d2cf59d8e546 | note | Frequency - Upon delivery to site
d06abdf9-ee02-5661-ade1-b4a1bae49692 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure delivery docket matches materials
83242b78-99c7-578d-aedd-009f8b3e9d8b | note | Records - Delivery Docket
c50d31fd-0cf6-538a-8bb9-a346a11758bf | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Trenching
e5f2d25d-38a3-5887-aa89-cf5d6e4625e1 | note | Inspection / Test Point - Trenching
61f9d35b-8be3-5225-8396-167f9d81b646 | note | ACTION - H
8df9515a-030d-5ba7-bccf-804868095f5c | note | Detail - Inspect trench profile to ensure walls vertical, widths is 300mm max (single ducts). Ensure trench depth is sufficient to provide 600mm cover to duct when under berm (900mm cover when under road crossing)
3550e339-9b88-5062-97ab-3a4f35d211cf | note | Frequency - 10m Intervals
e9956d82-2610-5ed9-b717-67e271575978 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
5f7795f6-e1b3-5f9f-a64d-3aeda3ccdf53 | note | Conformance Criteria - Consistency with Drawings and Specifications
00937cb7-382e-5ad9-89df-4b16e77c3e39 | note | Records - Photos
b2f86b6c-afb3-52f6-bf96-e496ebc88abc | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.1 -
cf6ecbe2-284f-5f77-b6b4-d9cca9868007 | note | Inspection / Test Point -
bb6d3611-6d4e-54cd-97dc-14679dcd4712 | note | ACTION - H
0e528504-fb0e-5fa4-8c0b-404fc014d4f5 | note | Detail - Ensure trench is cut in a manner that will ensure ducts are layed at correct depths,grades and alignment as per design dwgs
d97d23a5-7cf1-5f58-9463-0b89cf7ad053 | note | Frequency - 10m Intervals
cbc1471c-a27b-56b7-a763-02259a22bbb9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
d052d515-ea10-5e89-9072-4a48215300c1 | note | Conformance Criteria - Ensure trench alignment and levels match the design drawings
18fac6c7-bafc-5b3e-971b-0059fc361dd0 | note | Records - Dipsheet & Photos
bcf6bbaf-2aac-5810-8c5b-d53741fb01cf | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Duct Installation
bc8ae8ce-8fc9-5607-8709-adc5aedaf6c7 | note | Inspection / Test Point - Duct Installation
5cb6ec98-461a-53d9-9cfe-b0060188d9ec | note | ACTION - W
ab3431d8-952c-5508-bc8c-11f9008d6a57 | note | Detail - Place proposed ducts in locations where required. Draw wire tapes required and cap ducts where required to prevent ingress of material into duct.
3ec326b5-e566-5526-b719-53d05a9166d5 | note | Frequency - Prior to Installation
1121f70b-0f12-54dd-8757-0efd37c73eb0 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
aa8f4dbc-7109-52db-804e-3249a040e55f | note | Conformance Criteria - Consistency with Drawings and Specifications
65226926-304b-5bc8-a616-14e82100bada | note | Records - Photos
e4e44f17-c344-511a-9645-5d2cdaf60619 | note | FH Initials - Site Engineer
| checkpoint | 7.1 -
8fce1be5-6d0b-5aec-a22b-80e3444386b7 | note | Inspection / Test Point -
750829ed-8501-5c97-8353-f6284ef90a83 | note | ACTION - H
f1e4cd5c-5fbe-5dbc-b193-0b90d45da2b6 | note | Detail - Ensure minimum spacing of ducts requirements are met as per design dwgs and ATCop min spacing tables
7edfce79-6205-50d1-96b2-8bbb86e1c06d | note | Frequency - 10m Intervals
a02f995b-241b-5d47-b7da-983e7b253096 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
a9a598b8-9bf6-502e-98e3-f133b98b8db9 | note | Conformance Criteria - Consistency with Drawings and Specifications
6de345a9-1fa7-591e-be9a-a1f29a0d920a | note | Records - Photos
bc73b671-b632-5949-b13d-d52f879b30d9 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.2 -
be0d88b7-131f-554d-a60f-533bfabdc65f | note | Inspection / Test Point -
84f14dc7-1d8a-50e6-9708-13d87573b0fd | note | ACTION - H
30f0d793-b730-5d03-8ebd-0c3060d3995f | note | Detail - Asbuilt Survey
144b2fa2-72e0-519f-9758-7ea1d0de01df | note | Frequency - 20m Intervals
71435f5b-456e-54fb-a949-0d2ade028464 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
b6d7e403-52d5-5c0e-ac1a-fb5b1ea8dae4 | note | Conformance Criteria - Consistency with Drawings and Specifications
de5bf9b7-281d-5125-a01b-b5eceb81b860 | note | Records - Survey Records
b9fb9620-f1af-59f9-a01d-dc648632df01 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8 - Bedding
3faa6602-9016-5e42-8a67-4a98f1c8bd28 | note | Inspection / Test Point - Bedding
5311bf78-3228-5b8f-a93a-a81c625c2d7e | note | ACTION - H
7c48b95c-a50f-5d11-8db4-e0e857b8c36d | note | Detail - Lay min. 150mm gap20 or finer for bedding and haunching
80f5f053-f105-5a70-9ed5-0b9c06d80ae8 | note | Frequency - 10m Intervals
c8dc7356-e151-515c-88c1-d5c5786b38b9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
296cca00-7431-55f4-b11f-f44af477e57f | note | Conformance Criteria - Consistency with Drawings and Specifications
b91eff43-0716-5921-b9e0-ed4b60a01a8b | note | Records - Photos
a5237a77-c7ed-53d4-b26a-1133383bf05c | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Warning Tape
fe88d8f1-4a01-5673-9715-6655a121791e | note | Inspection / Test Point - Warning Tape
f62c2bd1-9abd-548a-b6e9-97f65a1d9768 | note | ACTION - H
3c0dc7c5-2645-529f-9039-74bedc53a9d1 | note | Detail - Ensure warning tape gets installed 300mm above duct pipe for all new ducting lines.
aa6e97fc-278e-515b-b0de-68aa68f9cb56 | note | Frequency - 10m Intervals
7bce4963-863c-5f54-bdcc-287f4785e85f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
b08bc8ad-d98c-5100-9c7b-3274cc39e761 | note | Conformance Criteria - Consistency with Drawings and Specifications
2389f1bc-6cc8-5e5c-9e56-5b4ee74a9dc2 | note | Records - Photos
791d2d5c-92d9-5ee4-aea2-5152f9ab296f | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10 - Traffic signal pole erection
6dc48d30-2745-5d8d-97d5-178773da85ff | note | Inspection / Test Point - Traffic signal pole erection
d0f82e00-2637-5ef3-bf8d-6a48bb3eeb80 | note | ACTION - H
362449a6-12fa-5fcb-a7ca-d07a7e693a77 | note | Detail - Ensure Design engineer as inspected pole locations prior to proceeding
2adba43c-8a77-5af9-81e9-d0db99db1117 | note | Frequency - Per pole
2fbedb18-435c-5099-b28f-01d67cf055ae | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
cb1ea257-edb3-5008-a100-b0470302a9ae | note | Conformance Criteria - Sign off by design engineer
f7896853-772c-5d66-837a-74447b18e130 | note | Records - Engineer sign off
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10.1 -
870c77cc-e7f4-5774-9c47-19e86721bf37 | note | Inspection / Test Point -
6a45e845-5708-5c34-bead-2e7d06d1423b | note | ACTION - H
ec659785-3bef-5a83-8ae4-74e068d8b40c | note | Detail - Ensure Pot hole is as per design with required depths and widths
ab88dd10-0511-5c09-b565-2af632930747 | note | Frequency - Per pole
e00553a0-bf23-5717-a588-4e5bf8932d02 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
6255f427-dada-5d44-bb6d-c8e2d083c046 | note | Conformance Criteria - Consistency with Drawings and Specifications
55849a49-bfc1-5228-a1e6-d70a5c49d31a | note | Records - Dipsheet & Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10.2 -
287a3adc-d44a-5986-8db0-dd90e8fde8d1 | note | Inspection / Test Point -
67806246-0301-5668-8c21-8dd9e2f6c97c | note | ACTION - H
2cd44903-07d8-55a6-b5a0-14bc8313dbc8 | note | Detail - Ensure Poles are plumb and within design tolerances
bc5c7eb3-8498-51c7-96fc-27321b6e0858 | note | Frequency - Per pole
0e722b62-0ce6-5f38-b2af-d60d4bf3e43e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
86b002d4-dca6-59bd-998e-d676decb5835 | note | Conformance Criteria - Consistency with Drawings and Specifications
00fbf1d0-a45f-5c3c-8053-25d4e52c758e | note | Records - Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 11 - As-builts
9364e6c3-f12e-5694-a1c7-5af5b7f90378 | note | Inspection / Test Point - As-builts
c0b75a5f-f311-512b-937d-2d24bea5693f | note | ACTION - H
ace2f23d-10f0-5bed-b158-1532e151875e | note | Detail - Red pen mark up drawings to be included in QA file
a78e2fcf-f4b2-5629-a28f-49983e9101ac | note | Frequency - At the completion of the Lot of work
cf560b8e-9355-5427-b2b9-2bad1fd4f157 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
fb7286e4-c43c-5fb1-b059-c43958478cf1 | note | Records - Asbuilt Drawing
7ffd2356-c42e-5c61-8255-25841b5c5921 | note | FH Initials - Site Engineer
| signoff | AUTHORITY HOLDPOINT
| checklist | Triangle/Mokora - Enabling Works - Footpath, Kerb and channel and VX | itp | ITP - Enabling Works - Footpath, Kerb and channel and VX | 0dc1a437-30aa-4e0d-90f4-e306d6b6b684
| section | Kerb and channel
| checkpoint | 1 - Kerb & Channel
02ed84c5-ff9f-5c9e-8714-622f44356f51 | note | VERIFICATION ACTIVITY - QA FORM
ae9dd399-3abf-5e6e-9bd1-ba33615b41f5 | note | METHODS OR REFERENCE - TDM Technical Standards - KC0001 Type of Kerb used as per Design drawings
21f79190-0314-5c81-bd40-80bf0ed6bede | note | FREQUENCY - Every 10m for clegg Two point per 20m stretch for scalar where widening is occurring
0e71126f-54ea-5257-a9c3-43a3ff8e04a1 | note | ACCEPTANCE CRITERIA - Kerb & Channel to be laid using precast hand-laid. On compacted GAP40. Concrete 20MPa @28 Days on 100mm GAP40 with the subgrade CBR>5
721ed329-4576-5d97-9633-981580701eca | note | Hold Point - Inprocess Inspection
b652d509-c20d-5d47-abda-0df07b5f3682 | note | Records - FH concrete QA sheet, photos. Concrete Plant Docket
b821541d-f3cd-5049-8fbb-fcab11c667af | note | Onsite Responsibility - Site Engineer
69c137f2-39f0-5740-9e85-f2ac81319445 | note | Designers comment - - Kerb height across the length pedestrian croswalk reduced to 75mm. - Kerb height reduces to 120mm along south side over the extent of existing culvert. - TDM KC0001 there is criteria for undercut if CBR <5. So CBR testing should be included in ITP. Please state frequency and minimum tests. - include ITP for Kassle kerb installation
b845ca0d-b740-57bb-b608-5ec1aa9cad71 | note | FH Comment - Noted on levels however this subject to site out information/walkover. The CBR testing has been added however please note that achieving CBR >5 on K&C is very unlikely and most likely designer needs to provide undercut detail
| checkpoint | 2 - Channel Level
6594b7e5-b363-5b5a-a4c0-3ed09900820e | note | VERIFICATION ACTIVITY - QA FORM
db64d69d-ccb5-5b36-a1da-395cc8f43287 | note | METHODS OR REFERENCE - TDM Technical Standards - KC0001
cd3217ee-5e58-5f2d-abea-640455ac2930 | note | FREQUENCY - Every Site
32ec4184-6115-5359-a48b-a17ac9ffd00c | note | ACCEPTANCE CRITERIA - Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
1b804106-44d1-5991-8473-7fd21acde6e1 | note | Hold Point - Inprocess Inspection
507c6dd5-0c5c-5f71-8c37-9b00dc895b77 | note | Records - FH concrete QA sheet
c94bf256-ab39-54c7-906d-f41dc31d7996 | note | Onsite Responsibility - Site Engineer
6f994013-06a8-58d9-8b4e-26b2b6b3c025 | note | Designers comment - Channel longfall to be as per IFC long section
2430914e-a199-5066-8221-a5cee30169f5 | note | FH Comment - Noted
| section | Footpath
| checkpoint | 3 - Concrete Footpaths
0cb55b7c-1b91-5343-905b-20ed18138f76 | note | VERIFICATION ACTIVITY - QA FORM
899fa758-d3f5-570f-adc8-adb5700f4a87 | note | METHODS OR REFERENCE - TDM Technical Standards - FP0001
28ba7025-0b46-5451-a956-9bb0214fa7fc | note | FREQUENCY - 5m Intervals - Eastern/Western 5m intervals - Southern
fa2f453a-93dc-57f1-9636-1c340c832463 | note | ACCEPTANCE CRITERIA - Subgrade -(CBR > 3) Basecourse - 100mm min. thickness Clegg CIV > 12 Surfacing - Concrete 100mm and 20 Mpa @ 28 days. 4kg/m3 blackoxide with broom finish
2d1c59f4-960e-5a8b-89b0-bf0d35e0a76f | note | Hold Point - Inprocess Inspection
5408ebef-c145-56f7-ba01-92b4e90fbe3f | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
8aa1c1f5-56f6-5a47-95ab-59bcfe61a82c | note | Onsite Responsibility - Site Engineer, Engineer Rep/ MSQA
361d4c82-5282-5c43-abda-773cef4c1f45 | note | Designers comment - 10m is okay for southern side, for eastern and western side reduce frequency of clegg it to 3-4m. Specify saw cut interval and depth of sawcut. Include prepore inspection as hold point
2d4b4ff9-024d-55ab-b83b-aaef0fafe1fd | note | FH Comment - 5m for Easter/Western. Sawcut every 3m or more frequent at any service cover obstruction
| checkpoint | 4 - Concrete Vehicle Crossings (VX)
a8a8cfd7-a658-57c4-aff3-6d07a8b6ad2b | note | VERIFICATION ACTIVITY - QA FORM
9826d1c3-5347-597a-b516-3d99ba519d4c | note | METHODS OR REFERENCE - TDM Technical Standards - VX01202
5af7a04e-f7cf-53dc-b9c1-f724b39a7d15 | note | FREQUENCY - At Least 4 clegg each crossing - one in each corner.
94dbd622-55f5-5e9d-84bd-94923c677c75 | note | ACCEPTANCE CRITERIA - Subgrade - (CBR > 3) Basecourse - 100mm min. GAP40 thickness Clegg CIV > 12 Surfacing - Concrete 150mm and 20 Mpa @ 28 days. Oxide and finish as directed by engineer
e63175c1-ae6e-5496-9b3c-ea3fa4ba98d7 | note | Hold Point - Inprocess Inspection
fdf9a13a-4e91-5c91-9fad-4617007b4801 | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
583c51d6-7780-5816-a9ef-f86df10d71e3 | note | Onsite Responsibility - Site Engineer
2043663c-968e-595b-a8a2-0a0dfcd59c76 | note | Designers comment - frequency- At Least 4 clegg each crossing - one in each corner.
78ccd57c-8fda-5b8a-be7c-67251a385e78 | note | FH Comment - Noted
| checkpoint | 5 - Grass Berms
899e02c9-a3c4-5880-9efa-3adc5ef2a967 | note | VERIFICATION ACTIVITY - Visual
598b7140-a82e-5e08-8004-319fa2426c78 | note | METHODS OR REFERENCE - ATCOP Section 12 Footpaths and Pedestrian Facilities
15c3c7a8-7498-526e-897d-ba92f2076fd2 | note | FREQUENCY - 10m Intervals
bb56568d-61e3-50cc-aaa9-2f20093b66e0 | note | ACCEPTANCE CRITERIA - 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
270ef202-2f8b-5eb0-b0ec-5308a32332e0 | note | Hold Point - Inprocess Inspection
2a284281-d48c-5935-b776-f336ad90bedd | note | Records - Photos
d084fd00-5622-5372-a0e6-879898cd7697 | note | Onsite Responsibility - Site Engineer
4a5f2b31-1c13-516b-bc8d-b3986c0c986d | note | Designers comment - Change to TDM reference
4f0379d1-c564-5af2-b20c-2d2a0df11b74 | note | FH Comment - Please provide TDM reference
| checkpoint | 6 - Service Covers and Street Furniture
63208345-5c8d-51d0-9e3a-35f7b68f0ee4 | note | VERIFICATION ACTIVITY - Visual
d6033dd8-04af-5b98-ab62-b2c0bc43484e | note | METHODS OR REFERENCE - AT Contract Specification 14000
907108ee-032b-5a5b-8ad7-29035d3fda8c | note | FREQUENCY - Every Site
d7f21633-2cb8-54ef-9344-b725c0331410 | note | ACCEPTANCE CRITERIA - Service covers to be adjusted to new surface levels. Ensure no damage is done to street furniture in the vicinity while carrying out works.
63415d13-ded7-558c-a676-cd3c909eefad | note | Hold Point - Inprocess Inspection
7a1cd11b-d34b-562a-8aa8-fdeef8f5441e | note | Records - Nil
3b7cd785-bfd3-5aaa-916b-578e4fb09913 | note | Onsite Responsibility - Site Engineer
| checkpoint | 7 - Tactiles /Pram crossing
3eea9f33-6f6b-5ef6-823f-9045f9883254 | note | VERIFICATION ACTIVITY - Visual
332b8abb-75f9-5713-9d24-e423dce0ad87 | note | METHODS OR REFERENCE - As per Design Plan
d2a592be-8149-544e-a1a8-2630bea7412f | note | FREQUENCY - Every Site
52f653fb-356b-5d5b-b449-9fd9d7e6052a | note | ACCEPTANCE CRITERIA - Foreman to set out tactiles and agree location with ATOC and Engineer prior to concreting
335b9dc4-10bb-5c4f-b2ee-499a2ad79e66 | note | Hold Point - Inprocess Inspection
f37a354a-1525-5dc0-a922-7b7a38f3ab32 | note | Records - Photos
1452fac5-92af-52b9-ba44-1f6dd0ebe3e8 | note | Onsite Responsibility - Site Engineer
| checkpoint | 7.1 - Tactiles /Pram crossing
97a1602b-7452-55f7-824f-11d0fac9ee48 | note | METHODS OR REFERENCE - NZTA RTS Guidelines for facilities for blind and vision impaired pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
bd4f7720-6423-51c7-a139-b0a943ea4dcb | note | FREQUENCY - Every Site
d0a1bf03-c56d-53be-ab93-a71ac5e8bad1 | note | ACCEPTANCE CRITERIA - Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
b5096317-dabe-51bc-a1ef-7c46b356e867 | note | Hold Point - Inprocess Inspection
ea0a6a72-9cc6-5676-a38a-0a90e671267e | note | Records - Photos
b516b6a5-97d4-5180-ac2a-8cc336b5544e | note | Onsite Responsibility - Site Engineer
| checkpoint | 7.2 - Tactiles /Pram crossing
4a02e45f-92ff-56b9-a98a-0e0d9c085f06 | note | METHODS OR REFERENCE - AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
bb94ad80-3e96-5911-afb8-f82acba0c586 | note | FREQUENCY - Every Site
5cf2fd2b-8f86-546a-acfe-5e6d374a7004 | note | ACCEPTANCE CRITERIA - Edge of warning indicators to set back 300mm from the face of the kerb or lane, extend the full width of ramp and be 600mm deep.
fab6bb23-7ba3-55b8-be01-b8fa7cd33213 | note | Hold Point - Inprocess Inspection
5a6d02d4-2ad1-5343-aba7-f89a2cb69bdb | note | Records - Photos
8d18ac8e-31ce-591e-b43a-e9d011b1207a | note | Onsite Responsibility - Site Engineer
| checkpoint | 7.3 - Tactiles /Pram crossing
cab1e566-a994-5390-a963-67b30ec746d1 | note | METHODS OR REFERENCE - AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
8515fcf7-df20-5301-8163-2bea9ef26651 | note | FREQUENCY - Every Site
230b7724-631c-527c-9510-3fa2f18b64de | note | ACCEPTANCE CRITERIA - TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
cd0dfbb4-2dbc-58b0-a146-21b9bb703ca1 | note | Hold Point - Inprocess Inspection
70d5113e-343e-5e58-8713-47ce2f7adf84 | note | Records - Photos
0f649f1c-a858-56b5-bf12-6380032b890d | note | Onsite Responsibility - Site Engineer
| section | Asbuilts
| checkpoint | 7 - As built information
7e0667b5-6c93-51bc-8bd7-74a6c074ed88 | note | VERIFICATION ACTIVITY - Drawings
115d1f91-f8ed-516f-ac88-e20cc3c58d4a | note | METHODS OR REFERENCE - - As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP.
abfa4467-be0d-5301-9e58-22bf83d1a26b | note | FREQUENCY - Every Site
494507d0-2308-5a4c-adf6-eb5d2cbddef5 | note | ACCEPTANCE CRITERIA - As built drawings
ccd0a345-c07e-54a3-9f59-c58073d27648 | note | Hold Point - In Process Inspection
845b7967-6019-540d-87ba-a3bcea2d428a | note | Records - Asbuilt records
42537943-d96b-5b7d-b9fa-bc634730a732 | note | Onsite Responsibility - Supervisor and Engineer
035a7de3-ce24-5209-8976-4dac5cbf86fa | note | Designers comment - - As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP. - Provide a separate row for RAMM data sheets referencing the contract requirements
c61aa1c8-93c5-57ea-9bd5-da163e1e26ea | note | FH Comment - Noted
| checkpoint | 7 - RAMM DATA
e187201c-1089-5572-8f73-ee42eac757b6 | note | VERIFICATION ACTIVITY - RAMM DATA SHEET
6ff99795-0430-5c04-8bff-2032e688acc0 | note | METHODS OR REFERENCE - - As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP.
df3ecc4a-fe26-5797-bd38-3f5c327d4a9c | note | FREQUENCY - Every Site
6b99f1ea-1091-5d41-9d3c-ace31dd8e86d | note | ACCEPTANCE CRITERIA - RAMM SHEET
840902aa-71d5-5416-8d54-9ba11fa3ad8c | note | Hold Point - In Process Inspection
ce3d5385-6afe-5709-a946-10eb7b823578 | note | Records - Asbuilt records
97c03b7f-8195-5e2c-ae7e-f4676aaa8692 | note | Onsite Responsibility - Supervisor and Engineer
| checklist | Triangle/Mokora - Pavement | itp | ITP - Pavement | 93d1607f-1626-4a32-8620-51d2d01a97f2
| section | Materials
| checkpoint | 1 - Aggregate - AT AP40
5fb106e1-6a59-506c-bed4-89ba210b987f | note | ACTIVITY DESCRIPTION - Aggregate - AT AP40
8c60f304-0d1b-5f04-829a-a2b316154afe | note | VERIFICATION ACTIVITY - M
8c2b0d33-4582-594a-833f-4411d9a76682 | note | METHODS OR REFERENCE - Meets Contract Auckland Transport Project Spec Section 2.9 - Table 3
431f4cff-c0fb-5911-83ba-65be54f58b91 | note | FREQUENCY - Lot
7981ad80-2f0e-56b8-a4a5-1417ed0dd443 | note | ACCEPTANCE CRITERIA - A Grading as per NZS 4407 Test 3.8.1 crushing resistance - Less than 10% fines passing 2.36mm sieve size under 130 KN or greater weathering resistance - CA or better SE > 40 PI < 5 or NP
cbcba214-9c4a-556d-9a8f-dee71776ec55 | note | TYPE - Testing/Visual
f0268cc9-e40f-54c5-9465-9cfa4932482e | note | RECORDS - IANZ Lab results
da661d73-e122-5b31-a8df-671822e51fda | note | On Site Responsibility - Site Engineer
| checkpoint | 2 - Concrete Sub Base - 20 Mpa
8ab2952e-ae00-5944-b339-3517eb560a29 | note | ACTIVITY DESCRIPTION - Concrete Sub Base - 20 Mpa
60215f45-bf2f-58f6-a08d-e2a6a8474cde | note | VERIFICATION ACTIVITY - M
1bdd1432-fe00-58a9-8a5b-f389d93931a9 | note | METHODS OR REFERENCE - As per Design
2aee49d2-c1ff-5a2c-8832-758948268ddb | note | FREQUENCY - Two cylinders per day
1b1cfa12-4c08-5a79-834c-1c9dcf9aad0c | note | ACCEPTANCE CRITERIA - 20MPa Concrete (slump test < 120 and 28 Day UCS test from supplier)
8af74fc6-78d5-580f-973d-ccc349b9f127 | note | TYPE - Testing/Visual
acdc9e2b-46a2-5117-8ccb-f7d57a90c937 | note | RECORDS - Supplier report
79b4f832-342d-5d42-99c7-5b1edf9d3bbb | note | On Site Responsibility - Site Engineer
| checkpoint | 3 - Bitumen
f386b7c5-a86d-5f91-8207-606205dc0b7c | note | ACTIVITY DESCRIPTION - Bitumen
f6eff29f-94c8-590d-b0c7-6b8dd5f8f8b4 | note | VERIFICATION ACTIVITY - M
55076713-35bd-5e4f-9925-19415bb0b9c0 | note | METHODS OR REFERENCE - As per Design
40b59efa-5a91-5ce0-8059-33e26c188ff3 | note | FREQUENCY - Passing all tests listed in Table 1 of NZTA M/1
55342081-72f8-5fda-b5db-8b3517623233 | note | ACCEPTANCE CRITERIA - Passing all tests listed in Table 1 of NZTA M/1
2a314a14-5299-5cd7-afe3-94e160a3cb3b | note | TYPE - Testing/Visual
b9d863cd-0b2f-5bae-9b7c-5b9e467e974e | note | RECORDS - IANZ Lab results
4b89bb39-7067-5999-a931-cd8a8e8d2e15 | note | On Site Responsibility - Site Engineer
| checkpoint | 4 - Asphalt Mix Design
444ef31e-2a32-5358-8e72-b6ffc0821ad1 | note | ACTIVITY DESCRIPTION - Asphalt Mix Design
323a5ede-33df-5498-80b4-65f858a92e29 | note | VERIFICATION ACTIVITY - M
54c93776-59c9-5f3b-8b0d-0cbb4dffd430 | note | METHODS OR REFERENCE - JMF approved
2c3ed9bc-2215-5b8d-8313-b062f53192ac | note | FREQUENCY - JMF approved
55ceab41-daa3-547b-bc7d-01b9d0d4ea0b | note | ACCEPTANCE CRITERIA - AUSTROADS - AC20 & PMB AC14
862b13af-3e31-5900-afc4-464c0990fed2 | note | TYPE - Testing/Visual
583bbe7a-40d7-5080-beb7-f4dafb09963e | note | RECORDS - IANZ Lab results
0eca303d-50ff-5bd0-ae22-d23699f14f67 | note | On Site Responsibility - Site Engineer
| checkpoint | 5 - Production Tests
d694ef90-a411-5cdd-a938-eb4a8e7b3ed5 | note | ACTIVITY DESCRIPTION - Production Tests
bd0f279d-bc55-5023-a2b6-d2d7a9d2ec23 | note | VERIFICATION ACTIVITY - M
1e947690-d85e-5885-b043-0d3ffd5b8180 | note | METHODS OR REFERENCE - NZTA M/10 spec
0160e8ab-7ea9-51ad-a0d9-083a39c04a93 | note | FREQUENCY - 1 set every 300t
f4282e5b-998a-5bed-af11-88a6eea6acfa | note | ACCEPTANCE CRITERIA - NZTA M/10
ed7c2744-b66e-5c89-ba66-fd324e626dba | note | TYPE - Testing/Visual
b0e39435-6ee2-5828-91e6-2508194e6a1d | note | RECORDS - IANZ Lab results
83d1eb9c-a82c-5729-91ef-a8120e6aa09c | note | On Site Responsibility - Site Engineer
| checkpoint | 6 - MDD & OMC for AT AP40
67d16356-1703-5ecf-891d-6d19c82a5bef | note | ACTIVITY DESCRIPTION - MDD & OMC for AT AP40
9b4b82a1-6379-5750-8113-21b06382469f | note | VERIFICATION ACTIVITY - H
fbc136f3-c6f9-598d-8382-b7e5f9c56475 | note | METHODS OR REFERENCE - Laboratory MDD and OMC tests undertaken prior to construction confirming site targets
cda76e43-f511-5066-b373-44e5d178a10a | note | FREQUENCY - Once per material type
4aaef332-3358-517d-abc8-af609353abf0 | note | ACCEPTANCE CRITERIA - NZS 4402 Test 4.1.1 - MDD and OMC determined in accordance with applicable specification.
84267e69-cbd1-5533-ab28-59ac23f22aa5 | note | TYPE - Testing/Visual
7ddaeab4-9f07-50a1-a579-871fa36b347a | note | RECORDS - IANZ Lab results
0ec730d9-0f6f-5af0-861c-267f07025a9b | note | On Site Responsibility - Site Engineer
| section | Excavation/Undercut
| checkpoint | 7 - Milling / Cut to Waste (350mm)
c3d5dde1-5cb7-5992-bccc-b432340891ea | note | ACTIVITY DESCRIPTION - Milling / Cut to Waste (350mm)
88895d05-d1ab-5d88-968d-8f546a7960d6 | note | VERIFICATION ACTIVITY - Stringline
bb5f14eb-4d2c-5ac7-be47-284c6eaf9a54 | note | METHODS OR REFERENCE - Dip from stringline or survey as-built
40373c65-ce9b-5f8b-b146-c3ced3e6e2f5 | note | FREQUENCY - 10m each lane
4d6c3d56-3a76-50d7-9c46-a430dff9afa1 | note | ACCEPTANCE CRITERIA - +0 / -20mm to design level
a85344ee-efef-58e1-966b-d35c15367e90 | note | TYPE - Mandatory HOLD POINT
c00b04d9-c504-5170-b67a-1d635e49483f | note | RECORDS - Stringline Sheet
c2bf61c4-12f7-54e0-9cc9-5a13d8ebdc6a | note | On Site Responsibility - Project Engineer
| signoff | Mandatory HOLD POINT
| checkpoint | 8 - Proof Roll
e8a3fe1e-b452-5b1b-9aa8-aca2dd129f31 | note | ACTIVITY DESCRIPTION - Proof Roll
3b32d7a1-92ea-5ffa-ba7f-491357f4f5d0 | note | VERIFICATION ACTIVITY - Deformation testing of existing Sub Base
fc36742f-ea1d-5445-a345-9735ff8b6992 | note | METHODS OR REFERENCE - Visual Inspection
efae24ed-519b-512e-ab39-522e4f21ed23 | note | FREQUENCY - Existing milled Sub Base
303e1a3f-1aad-556e-87e7-fad01332b64a | note | ACCEPTANCE CRITERIA - No physical deformation or springing observed
19cde30b-16d3-59f6-a4c5-104f08ae1e25 | note | TYPE - Mandatory HOLD POINT Designer Sign Off Required
f4ac722c-51c3-56bd-95ac-4cf0b3dfb1d6 | note | RECORDS - QA Record
82487793-a39c-59a0-b4fd-15604bdc4105 | note | On Site Responsibility - Project Engineer
| signoff | Mandatory HOLD POINT
| checkpoint | 9 - Contingency Undercut
a36b2588-40b3-55d6-89a1-73a1a42e7ae1 | note | ACTIVITY DESCRIPTION - Contingency Undercut
1090b6e2-e99d-5bed-9ed7-bc0de53090e2 | note | VERIFICATION ACTIVITY - Contingency
82f45a3e-2fcf-5fa1-a1c4-7090346f0f6d | note | METHODS OR REFERENCE - Contingency Undercut
32e3e565-c514-5ca6-b540-2dff93fea37b | note | FREQUENCY - Areas with deformation under proof roll
e9ac61ff-5668-5d39-a579-d5716a5ea4ce | note | ACCEPTANCE CRITERIA - If significant deformation or springing is witnessed under the proof roll or the subgrade is encountered at 350mm then undercut by 180mm and replace with static compacted AT AP40.
b46b30b8-7483-5b16-894b-abbedbadd811 | note | TYPE - Inprocess Inspection
bfc4c3cd-cff0-5d61-8f87-d9167b84c62d | note | RECORDS - Site diary
934db33a-05f3-543a-a88f-46e469dad545 | note | On Site Responsibility - Project Engineer
| checkpoint | 10 - Widening Area - Milling / Cut to Waste (530mm)
a04696a0-27df-5e39-b063-591acb2ba581 | note | ACTIVITY DESCRIPTION - Widening Area - Milling / Cut to Waste (530mm)
3a42640f-be29-57ee-a48e-e744d3223b8c | note | VERIFICATION ACTIVITY - Stringline
99dc0315-e4fa-59c7-a0aa-b29a08cea398 | note | METHODS OR REFERENCE - Dip from stringline or survey as-built
b61ec14d-dee6-5215-ab3c-7b34e1f90e94 | note | FREQUENCY - 10m each lane
2e678695-5d93-5dfd-af14-d19fee242717 | note | ACCEPTANCE CRITERIA - +0 / -20mm to design level
22faccae-e41a-532f-90f8-89ee7f78164e | note | TYPE - Mandatory HOLD POINT
190a24cf-87c5-52f4-be7b-8fe5c076d73e | note | RECORDS - Stringline Sheet
e757d3a0-842d-5f01-aeda-c2af3182cd63 | note | On Site Responsibility - Project Engineer
| signoff | Mandatory HOLD POINT
| checkpoint | 11 - Subgrade
35561225-607a-52aa-834c-61b19443bd60 | note | ACTIVITY DESCRIPTION - Subgrade
dadb8d8d-9007-5af7-aa01-91b168070146 | note | VERIFICATION ACTIVITY - No unacceptable subgrade materials after excavation
04781f27-5c95-58b2-85dd-f2a7af2d317b | note | METHODS OR REFERENCE - Visual Inspection
05dfcd5c-8886-5460-9006-e97f2effe0e3 | note | FREQUENCY - NA
ae02edae-43ea-50eb-a57f-021371c5622f | note | ACCEPTANCE CRITERIA - Free of detritus and loose material
df24b2f3-049f-5082-a734-5e914e4969d0 | note | TYPE - Inprocess Inspection
61b4d4ff-10e3-5afd-8caf-c475c7b7dd99 | note | RECORDS - Site diary
68ef4bc3-d651-5c7f-926f-bc16adf01f8d | note | On Site Responsibility - Project Engineer
| section | AT AP 40 Sub Base (Widening Area)
| checkpoint | 12 - NDM & Plateau Test
b911417a-6600-5d09-917e-3d1969b9bbe2 | note | ACTIVITY DESCRIPTION - NDM & Plateau Test
7a77f141-18e0-5e45-a9ea-eb40fdbbff4b | note | VERIFICATION ACTIVITY - Testing
bd89d62b-e50a-533c-9738-ed5a410e1b5d | note | METHODS OR REFERENCE - Dip from stringline or survey as-built
2c8615db-d26b-528f-a00e-972653102948 | note | FREQUENCY - 1 test per 10m in each traffic lane (alternating wheel path)
9c282f43-6206-5942-8fb6-4b6f7c995506 | note | ACCEPTANCE CRITERIA - Clegg Test > or equal to CVI 35
36b28e27-92bf-59b0-8c07-c375f0c54869 | note | TYPE - Inprocess Inspection
4185b9ee-681e-5ee9-bd11-4da024b00937 | note | RECORDS - IANZ Lab results
afd1444f-21d9-5ac4-ac19-b0d2c4ff1473 | note | On Site Responsibility - Project Engineer
| checkpoint | 13 - Stringline & Level
bac86b29-ae15-529f-a9f1-1afeacb18efe | note | ACTIVITY DESCRIPTION - Stringline & Level
8db6abb2-98df-50e3-bbb5-d7897b9af6ca | note | VERIFICATION ACTIVITY - Testing
599384b4-2a8f-5f2e-8c44-764ec66f13ec | note | METHODS OR REFERENCE - Dip from stringline or survey as-built
fb201861-ff7c-59a0-9a91-943aea678d2a | note | FREQUENCY - 1 test per 10m in each traffic lane (alternating wheel path)
f53d4a49-f4dd-53bb-a597-c2df1838e01f | note | ACCEPTANCE CRITERIA - Constructed as per TNZ B/2, minimum compacted layer depth to not be less than 100mm. Finished surface of Sub Base 180mm thick. Tolerances (-25mm, +5mm).
56d13ce5-03ae-59be-b1ad-1505de3a9d58 | note | TYPE - Inprocess Inspection
785d974c-f1d6-50c8-ac9f-dbfb96c31bba | note | RECORDS - Stringline checks Photos
dc161eb9-8a7f-5745-8622-d728a7b0d6ed | note | On Site Responsibility - Project Engineer
| checkpoint | 14 - Proof Roll
c0f948d9-5bd6-5267-a3ed-f00f86633995 | note | ACTIVITY DESCRIPTION - Proof Roll
19a27645-be37-5b9a-987a-92eec20a3741 | note | VERIFICATION ACTIVITY - Visual Inspection
b867647b-1f0f-54a1-b044-c2abfc8f28e9 | note | METHODS OR REFERENCE - Visual Inspection
82b1e45a-8964-551e-95c8-32aebe68c710 | note | FREQUENCY - Continuous
a0847a71-cca0-5124-831b-b2b9b72a36f6 | note | ACCEPTANCE CRITERIA - Undertake proof roll of the Sub Base 12T static smooth drum roller - No springing or deformation under the roller
2178c4fe-a4ac-54c8-abf2-9ffefbdbae5e | note | TYPE - Mandatory HOLD POINT Designer Sign Off Required
6846b3a2-9bbc-5392-8cdc-949cd1a3f450 | note | RECORDS - Visual Inspection Photos
7514a015-ccf0-5cc5-83f5-5448807092b2 | note | On Site Responsibility - Project Engineer
| signoff | Mandatory HOLD POINT
| section | Undercutting Contingency
| checkpoint | 15 - Contingency Weak / Soft Spot
ffd0a696-eb85-5c28-bf61-7f7bd1b11e4f | note | ACTIVITY DESCRIPTION - Contingency Weak / Soft Spot
0d3efabd-c897-51b2-86f5-0e8a7ca49626 | note | VERIFICATION ACTIVITY - Scala Penetrometer tests
d53537d8-7051-5312-864a-59d692db31fb | note | METHODS OR REFERENCE - Design Report
6116cc42-9486-5219-8318-e65a78c81201 | note | FREQUENCY - At 10m intervals in each lane
4d0f99cb-c788-54f9-98be-4d401deb479e | note | ACCEPTANCE CRITERIA - Subgrade CBR ≥ 1
15d57923-4d98-5729-aa91-02442dd2e05c | note | TYPE - Mandatory HOLD POINT Designer Sign Off Required
ebc01f80-485a-5661-830a-3ed9c5ffdaaa | note | RECORDS - Marked up drawing
7395566c-d946-5088-9567-dafca75e2063 | note | On Site Responsibility - Project Engineer
| signoff | Mandatory HOLD POINT
| checkpoint | 16 - Contingency Undercut to be Confirmed by Designer following review of Scala and site conditions.
15fa8d52-2883-541c-9bab-fcadb9536554 | note | ACTIVITY DESCRIPTION - Contingency Undercut to be Confirmed by Designer following review of Scala and site conditions.
8b416f79-30eb-5ff7-9283-5ea1aed7229a | note | VERIFICATION ACTIVITY - Design
a7a5f90d-ac7c-52de-addb-169ca09071f1 | note | METHODS OR REFERENCE - Pavement Design
202897e3-b42e-583a-9bc5-e9905c2a384a | note | FREQUENCY - As required
02b28f3a-3ab2-5c13-a244-1c8f851782fa | note | ACCEPTANCE CRITERIA - As required based on Scala tests and site conditions. To be confirmed by Designer.
8548ca3d-8c3e-512c-b4ab-ae8075e30df9 | note | TYPE - Mandatory HOLD POINT Designer Sign Off Required
c132ed3a-239a-58ff-b3c8-d00bf9039a9a | note | RECORDS - Stringline Sheet
24c12f8d-c79f-5537-b623-8256950d6d66 | note | On Site Responsibility - Design Engineer
| signoff | Mandatory HOLD POINT
| section | Concrete Sub Base (150mm)
| checkpoint | 17 - Concrete Sub Base
1f6b5c08-8bdb-5340-987c-b1416a156a13 | note | ACTIVITY DESCRIPTION - Concrete Sub Base
fbd078cc-ecf8-53b8-a4be-3d8fbf24a732 | note | VERIFICATION ACTIVITY - Strength and slump
6182034d-16da-5706-86a9-bbb15c961428 | note | METHODS OR REFERENCE - Concrete dockets
68da7196-8e2e-510c-a5ff-4de11f43842a | note | FREQUENCY - each pour
ae0f0a4d-2a39-5947-9ae1-fd3233234d82 | note | ACCEPTANCE CRITERIA - Strength = 20MPa Supplier to send through cylinder strength report
3f6ee998-fe17-5d30-862f-caa42695c3eb | note | TYPE - Inprocess Testing
b3cd85cd-0766-5422-bb8f-b8ec9fda79c2 | note | RECORDS - Docket
95f96316-d0f8-5892-9ad0-e95158c57b2f | note | On Site Responsibility - Project Engineer
| checkpoint | 18 - Concrete Sub Base
c6beca4d-3406-5625-80cb-ce06a28918bf | note | ACTIVITY DESCRIPTION - Concrete Sub Base
aa0124ad-664f-50f6-92a8-ddbcfe4ba3bf | note | VERIFICATION ACTIVITY - Levels / thickness
659ebfad-c03c-59cd-b47d-a2a303df255b | note | METHODS OR REFERENCE - Dip from stringline
970e6387-f800-5006-be85-0af47da3c4c9 | note | FREQUENCY - 10m each lane
f0f16eb9-5547-5f8f-9aa9-3757fc598de6 | note | ACCEPTANCE CRITERIA - Target Depth = 150mm -10 / +10mm, 200mm from design surface level
fe1533a8-b38c-502d-8b1f-2759474fb766 | note | TYPE - Mandatory HOLD POINT Designer Sign Off Required
21456177-efc6-5d23-88ab-4408572942c2 | note | RECORDS - Stringline Sheet
db596ac4-854d-5c23-8494-8e2ca6f44033 | note | On Site Responsibility - Project Engineer
| signoff | Mandatory HOLD POINT
| checkpoint | 19 - Concrete Sub Base
66fa5a54-1125-5451-9c81-813306d1bd7b | note | ACTIVITY DESCRIPTION - Concrete Sub Base
da8448d6-dcb7-5525-a6b8-906b9d869707 | note | VERIFICATION ACTIVITY - Rake finish
2752e18c-b2a2-563a-8b1d-5e4900cdef98 | note | METHODS OR REFERENCE - Visual Inspection
cff42de8-7905-5476-be36-7ba11f7e8717 | note | FREQUENCY - NA
0ab5832d-57be-5c0e-9c43-b82f7dbebf31 | note | ACCEPTANCE CRITERIA - U5 rough finish or rake rough surface verified over 100% of surface area
188f120d-03cf-58aa-9c7f-19fa35a9ae8b | note | TYPE - Inprocess Inspection
19b59f3b-60a7-52c5-93e7-66b3cb16b228 | note | RECORDS - Site Records
709e571c-8cf1-5e8c-a504-281a2155df03 | note | On Site Responsibility - Project Engineer
| checkpoint | 20 - Concrete Joint
c58bf444-4a98-5947-bf21-896366cee9bd | note | ACTIVITY DESCRIPTION - Concrete Joint
a1a72775-b1b1-53ec-9cb9-8e4fb9481929 | note | VERIFICATION ACTIVITY - Roughened / Keyed Joint
9834edcf-0bf2-5b3c-8581-40f3f0e93ffd | note | METHODS OR REFERENCE - Visual Inspection
7596968c-28a2-56ae-ad45-a4ba9ea983b9 | note | FREQUENCY - Each Subsection
ab4080af-a1d0-5f1a-a9d6-b71f1ee7b447 | note | ACCEPTANCE CRITERIA - Roughened or keyed joint confirmed over full depth of concrete
2b43bb17-a588-5d9f-90ed-a80fbc6ab56f | note | TYPE - Mandatory HOLD POINT Designer Sign Off Required
cae897f3-90ac-5b56-9410-35105c7b0b35 | note | RECORDS - Site Records
3ba4f1c0-e5a4-5eb4-bcc8-5e6e7e81fff7 | note | On Site Responsibility - Project Engineer
| signoff | Mandatory HOLD POINT
| checkpoint | 21 - Concrete Curing
dd08c654-3d2a-52ba-ba3c-321266fd631a | note | ACTIVITY DESCRIPTION - Concrete Curing
e2d3c8e9-9be6-5ef0-b8f3-44afcfa6cc05 | note | VERIFICATION ACTIVITY - Visual Inspection
2299b1c7-3cad-5c88-98c2-ee34b0213ea3 | note | METHODS OR REFERENCE - Construction
9770fe27-208c-5a23-8800-898362feaf84 | note | FREQUENCY - Concrete Area
9a31068f-d8af-5965-b771-d5d38e076da3 | note | ACCEPTANCE CRITERIA - The concrete Sub Base requires a 48 Hr moist cure period to minimise cracking where traffic is not permitted. For cracking witnessed after the 48 hr period the following mitigation measures shall be undertaken: Cracking <1mm - Heavy Tack Coat Cracking 1 to 3mm - Heavy tack and reinforcement grid Cracking >3mm - Engineer Decision
7482ebb4-cb8d-579c-a3b4-1c6bad29ff53 | note | TYPE - Mandatory HOLD POINT AT Sign Off Required
6e8c638e-63ed-551e-aff1-66ef6cecc006 | note | RECORDS - Visual Inspection Photos
2689d729-d236-59bd-850a-8836b198a88f | note | On Site Responsibility - Project Engineer
| signoff | Mandatory HOLD POINT
| section | Emulsion (Concrete, AC layer, and on top of existing pavement)
| checkpoint | 22 - Emulsion tack coat
dc8176f5-fb71-5532-bd75-328489aa0255 | note | ACTIVITY DESCRIPTION - Emulsion tack coat
0693dec0-120b-5aa5-bf94-bd064f68439e | note | VERIFICATION ACTIVITY - CAT60 cationic emulsion or approved alternative
c85bd797-a6a7-58a2-899c-65c313759a3f | note | METHODS OR REFERENCE - Dip emulsion tank
d51fc9cc-546b-5fb1-804a-ba2e6cb7c7f6 | note | FREQUENCY - each lot
678bfa5f-d989-56d3-824d-4e51478243ac | note | ACCEPTANCE CRITERIA - 0.3 to 0.6 lt/m2 (minimum residual) based on requirements from design drawings.
44abc0b9-7db4-56a3-80ee-5b7c1fb8534d | note | TYPE - Inprocess Testing
2038168a-0ccf-588e-8334-264b7638f690 | note | RECORDS - Spray sheet
8185a284-f427-56fa-8630-7744bce649c5 | note | On Site Responsibility - Project Engineer
| checkpoint | 23 - Blinding
7f80f009-3402-511e-ad3c-e12b27e32061 | note | ACTIVITY DESCRIPTION - Blinding
ac87cbff-d2b2-5f87-8136-86f64d21944f | note | VERIFICATION ACTIVITY - Grade 5 chip
d9970d56-4739-5207-adad-addad435d9bb | note | METHODS OR REFERENCE - Aggregate Supply
8e0fd961-cdaf-5be2-b0df-4380130dc9a1 | note | FREQUENCY - each lot
6a780453-1523-5fce-bdca-7f86bb929a6a | note | ACCEPTANCE CRITERIA - Even application of blinding where required in accordance with the design drawings.
7a5842fc-52be-5731-9a32-85f7993041d5 | note | TYPE - Inprocess Testing
f093dc16-b80e-5089-841e-d3ef0dca808a | note | RECORDS - Spray sheet
5a32299d-8f67-5c0f-9fbd-5c0f218c4239 | note | On Site Responsibility - Project Engineer
| section | AC20 (160mm in two lifts)
| checkpoint | 24 - AC20
5b0a7da9-1a4a-5652-9781-6605b7ffc015 | note | ACTIVITY DESCRIPTION - AC20
67f1e15c-ecb9-560a-bc7b-395ad8318cd1 | note | VERIFICATION ACTIVITY - Check weather reports
70a727d7-cf29-5f8a-9f36-2fbcec61657f | note | METHODS OR REFERENCE - Forecast and thermometer
eeb61da5-9a3c-5104-8cb1-e05e23130051 | note | FREQUENCY - Daily
0c7ba1ba-45c2-5e4f-b955-818b1c46161d | note | ACCEPTANCE CRITERIA - No fog, rain or wet surface. Base temp ≥ 5o C
f80e3899-eb2f-59d5-87db-158b468163c4 | note | TYPE - Inprocess Testing
ff2267b7-5648-5d3e-b3a2-e6aea869b8c2 | note | RECORDS - AC check sheet
beedfa8d-f00e-5269-8987-343b5b27ad6d | note | On Site Responsibility - Project Engineer
| checkpoint | 25 - AC20
8c555dae-ef0c-5e3f-8868-e54a1dfb5d51 | note | ACTIVITY DESCRIPTION - AC20
b8feae65-6572-5306-adb4-f52961692d23 | note | VERIFICATION ACTIVITY - Ensure previous layer is broomed clean
a39c54e5-e0ce-5435-ab9e-86e86493115f | note | METHODS OR REFERENCE - Visual
84b16ba8-e1fc-52be-aa2b-daaccf1ff43b | note | FREQUENCY - Prior to starting
84e2aaed-73ad-59cb-9a5f-74c09e90b36e | note | ACCEPTANCE CRITERIA - Free of detritus and loose material
43bd6451-138b-54a9-928b-a2061965bf2c | note | TYPE - Inprocess Testing
f2df7383-fdae-59d7-8cd4-3e76272f3dfe | note | RECORDS - AC check sheet
05708904-a696-5b5f-bd49-9ad1485dd043 | note | On Site Responsibility - Project Engineer
| checkpoint | 26 - AC20
87c4faf2-1524-5ac2-8d56-7b89c2d2fe17 | note | ACTIVITY DESCRIPTION - AC20
fd45f815-9ef1-5832-89b8-7e80d47d47b1 | note | VERIFICATION ACTIVITY - Production tests
46204d37-d4d0-5df7-83ff-3f45d66f6149 | note | METHODS OR REFERENCE - Grading, binder content, max density, temp
b5e933c0-7243-550b-adc9-6a8800b5a0e1 | note | FREQUENCY - 1/300t
067d3294-e49f-52a5-bdc3-13ec1a7532d0 | note | ACCEPTANCE CRITERIA - NZTA M/10
066b938f-de55-5940-b4d1-9df72035c4f5 | note | TYPE - Inprocess Testing
b9143706-04e5-5826-8055-e4a58321dabc | note | RECORDS - Lab test
1e969a64-7a9d-5a12-bbd7-408167f3af3f | note | On Site Responsibility - Project Engineer
| checkpoint | 27 - AC20
ce3a6b42-4937-51ff-b199-e96523ad3600 | note | ACTIVITY DESCRIPTION - AC20
1407ea6f-bde9-5ddd-93e3-ed6da2df643f | note | VERIFICATION ACTIVITY - Surface finish inspection
1505ebec-0a70-5ce1-80c6-089bc448ce53 | note | METHODS OR REFERENCE - Visual inspection by the Engineer
40aeeb65-6dc5-576a-9de0-e4833e8e39c3 | note | FREQUENCY - Each lot
367bef8d-5183-5737-9cf5-aaea179e60be | note | ACCEPTANCE CRITERIA - Uniform texture, no roller marks, no bleeding, cracking or shoving, no crushing of the aggregate.
e9d24c77-d8e5-5b99-9a97-f8fc544c1dc5 | note | TYPE - Inprocess Testing
41215e09-97de-5218-a299-917092977238 | note | RECORDS - Inspection sheet
2eaa7d9b-e6bb-5081-b525-cfc195033b6f | note | On Site Responsibility - Project Engineer
| checkpoint | 28 - AC20
35c78fed-39f4-55c7-8213-c983b1a54af1 | note | ACTIVITY DESCRIPTION - AC20
d690d8ea-6f4a-5130-8555-916bae4c52eb | note | VERIFICATION ACTIVITY - Density testing
a865d8bb-2325-5b90-912d-99c3e36d8ec7 | note | METHODS OR REFERENCE - NDM
4eb4c5b1-7322-5f07-9e32-39d429a23356 | note | FREQUENCY - Every 30m2
5e91fad4-faec-5e5a-889d-f4a9523c82cf | note | ACCEPTANCE CRITERIA - Air voids (2% - 7%), in accordance with NZTA M/10 (2020)
6347f87a-b97e-55c9-b807-42b71ceaa2eb | note | TYPE - Inprocess Testing
806b7728-a524-5bc5-9ae2-01be8c505a8e | note | RECORDS - Inspection sheet
442fd436-d11a-51ff-8c07-8ed7054ac164 | note | On Site Responsibility - Project Engineer
| checkpoint | 29 - AC20
b9164f88-b5a0-500e-8c81-fc7f96670126 | note | ACTIVITY DESCRIPTION - AC20
a8e4251b-2a19-5548-b3c1-dcaf9a0f5756 | note | VERIFICATION ACTIVITY - As-built layer
d92486ab-81fd-531e-80ee-5316d9e02ede | note | METHODS OR REFERENCE - Stringline
adaf41d0-5498-569d-a69e-01accc7f3ecf | note | FREQUENCY - Each lot
2fa5e8f5-aa3c-5519-89ac-a8dbbb5938d7 | note | ACCEPTANCE CRITERIA - 160mm (+10 / -10mm), Constructed in two 80mm lifts.
07a4f282-43e3-50a4-80f4-8171908f441f | note | TYPE - Inprocess Testing
804fa204-2975-5c40-ab9e-67c8449e80c7 | note | RECORDS - As-built drawings & stringline measures
30ce4b71-6472-5ac7-be5e-f80ff4baee67 | note | On Site Responsibility - Project Engineer
| checkpoint | 30 - Joint Inspection
e5731c55-462b-542c-a0d3-96123146b61f | note | ACTIVITY DESCRIPTION - Joint Inspection
dc614178-e47e-5c84-90d3-9b6c8b303403 | note | VERIFICATION ACTIVITY - Visual
fc4cdeb0-f049-5c62-9863-203360feed18 | note | METHODS OR REFERENCE - Design Report
b8c8ddda-12c3-5921-ad1c-d9c193c7afb6 | note | FREQUENCY - Each Subsection
ce36886e-17d1-5b60-a51a-9e9190fa2595 | note | ACCEPTANCE CRITERIA - Transverse layer joints to be offset by 500mm and longitudinal layer joints to be offset by 150mm, as per the design drawings.
fc13b8e6-5009-57d4-977f-eaedb7f1af91 | note | TYPE - Mandatory HOLD POINT Auckland Transport Sign Off Required
c00a3bca-1e09-5330-8ebc-cfbdf43e3c12 | note | RECORDS - Site Records
430f3257-d557-5537-be5f-bf719d16dbea | note | On Site Responsibility - Project Engineer
| signoff | Mandatory HOLD POINT
| checkpoint | 31 - AC20
c9782328-e14d-5bf6-ae6f-725c8028b749 | note | ACTIVITY DESCRIPTION - AC20
ea3db3a9-6231-5c12-a9c5-91b51331477c | note | VERIFICATION ACTIVITY - Density testing
ff705d60-08da-5120-ae09-02c7179ed8a9 | note | METHODS OR REFERENCE - Cores (Random testing plan to be agreed with client)
dd81cc53-503c-5f19-b4e1-cd2078b65a2c | note | FREQUENCY - 1/300m2 or min 4 no.
318cc172-7d02-5c80-94d3-b8b7aeb85b00 | note | ACCEPTANCE CRITERIA - Air voids to meet NZTA M/10:2020
bc1ccded-4ce9-5ae2-9375-23afde794c20 | note | TYPE - Mandatory HOLD POINT Auckland Transport Sign Off Required
a098c08f-1ff1-5cc9-a102-0691be9d42cb | note | RECORDS - RFI response
45dd016c-e50d-5d2e-a77d-979e4605c724 | note | On Site Responsibility - Project Engineer
| signoff | Mandatory HOLD POINT
| checkpoint | 32 - AC20
16c11065-ee87-56a5-ab72-4b90344913aa | note | ACTIVITY DESCRIPTION - AC20
2fd4914b-b196-5447-9174-1303920ae251 | note | VERIFICATION ACTIVITY - Thickness (80mm layers with geogrid in between)
20553ed2-492c-5c90-aaf8-4b2b9c6a3390 | note | METHODS OR REFERENCE - Cores depth (Random testing standard)
b04cf9e5-8849-531e-8694-88687fcca2d1 | note | FREQUENCY - 1/300m2 or min 4 no.
cbadb86e-8939-5a20-89e3-48753b4390d8 | note | ACCEPTANCE CRITERIA - - Target depth 160mm
e6ab2bde-db47-5f2c-8ea7-80fec97df5e1 | note | TYPE - Mandatory HOLD POINT Auckland Transport Sign Off Required
80e41e31-a2d4-511f-abc6-980b472d2160 | note | RECORDS - Core test report
c76bcf90-995f-5de0-a444-d34e2d091dea | note | On Site Responsibility - Project Engineer
| signoff | Mandatory HOLD POINT
| section | Hatelit grid
| checkpoint | 33 - Hatelit
bb0bf400-1f46-5d39-9d61-89b3601f9a2b | note | ACTIVITY DESCRIPTION - Hatelit
e96e9174-116f-570f-adec-6e762be6ccfc | note | VERIFICATION ACTIVITY - Length direction grid overlap
0ea9535d-dec7-5123-a62d-6da1b3e84ec0 | note | METHODS OR REFERENCE - Visual inspection
8a94cbad-69f1-5776-962a-3b5ebab8432e | note | FREQUENCY - Ongoing during install
f017a3e7-074b-560f-9c73-d8f0df492a61 | note | ACCEPTANCE CRITERIA - Min. 250mm
85b63e4c-9695-5fb0-a030-7a3b1abd537f | note | TYPE - Inprocess Testing
d0d395ec-a3c9-5433-946b-5b428efae9f7 | note | RECORDS - Photo / diary note / check sheet
bb58e055-b09e-5664-8733-21b2eafbd75d | note | On Site Responsibility - Project Engineer
| checkpoint | 34 - Hatelit
ef7c3b87-534d-5d7e-a132-74193a3b73d0 | note | ACTIVITY DESCRIPTION - Hatelit
732d3764-7cd2-5098-b5d3-980063c2fe96 | note | VERIFICATION ACTIVITY - Cross direction grid overlap
1ea33caf-355b-56ba-813f-d16063b48213 | note | METHODS OR REFERENCE - Visual inspection
a86fd457-d2f4-5ab3-8252-1771b0c3e638 | note | FREQUENCY - Ongoing during install
13557e09-df12-516d-a402-46ec32826a23 | note | ACCEPTANCE CRITERIA - Min. 150mm
3768e4ff-4800-554e-8977-98a722cf7d81 | note | TYPE - Inprocess Testing
0d54ac33-85ce-52a3-afa0-e5482399bc77 | note | RECORDS - Photo / diary note / check sheet
93482be0-614a-5154-a812-9e8d602cead5 | note | On Site Responsibility - Project Engineer
| checkpoint | 35 - Hatelit
dfad841a-298b-53ec-95bd-e49bf505caec | note | ACTIVITY DESCRIPTION - Hatelit
8b71f3a2-99e4-57bb-ab6f-74c58aeb653d | note | VERIFICATION ACTIVITY - Tack coat
24f7c40f-f2cc-5521-806b-21b1165ec523 | note | METHODS OR REFERENCE - Visual inspection
186fd887-e18f-590a-8636-e3fe6c330bf7 | note | FREQUENCY - Ongoing during install
7d447eab-6064-57ff-b56c-9cc11c960536 | note | ACCEPTANCE CRITERIA - 0.4 lt / m2 - 0.8 lt/m2, residual bitumen emulsion (depending on surface condition)
2daf9bba-2add-5f03-9b5b-2aa56a71133c | note | TYPE - Inprocess Testing
658bd94b-d5f8-5909-8a50-39bd61993b30 | note | RECORDS - Photo / diary note / check sheet
798a1e4a-a85f-5193-9215-7b3e54840c80 | note | On Site Responsibility - Project Engineer
| checkpoint | 36 - Hatelit
a3b6465f-37e2-5ab3-a08b-1c5e809c407a | note | ACTIVITY DESCRIPTION - Hatelit
1f41af5e-1842-53ae-a49d-1ac3954abb46 | note | VERIFICATION ACTIVITY - Emulsion on overlaps
ab09cd2b-da20-5133-9a43-790bf256118c | note | METHODS OR REFERENCE - Visual inspection
d0f0ae2e-0027-5383-b215-67f7e6f77494 | note | FREQUENCY - Ongoing during install
7b9e0caf-4eea-5a0a-b963-6ece713e3e85 | note | ACCEPTANCE CRITERIA - 0.3 lt / m2 if required
47e481b8-0567-5e2e-ae93-5fccc345d3da | note | TYPE - Inprocess Testing
ad313587-956f-54d1-8d64-3449a41eecc1 | note | RECORDS - Photo / diary note / check sheet
4dcb76bd-4355-5712-9162-47e5852700b7 | note | On Site Responsibility - Project Engineer
| checkpoint | 37 - Hatelit
7a0a5eb2-684c-54ad-88df-87e5a22929fb | note | ACTIVITY DESCRIPTION - Hatelit
948d22aa-1106-5faa-8d20-aac411200adc | note | VERIFICATION ACTIVITY - Evenly laid grid
3a1a42a4-9c5a-543f-8915-132516c1385a | note | METHODS OR REFERENCE - Visual inspection
6e019a1b-5dc2-56bd-a1ff-d80aa9dfbdf3 | note | FREQUENCY - Ongoing during install
3d8b1d01-f2a1-5347-9480-4ddac92cac9f | note | ACCEPTANCE CRITERIA - Minimal air voids in grid, grid pulled tight
b4730571-554b-55d7-8b78-64948619541a | note | TYPE - Inprocess Testing
a6d96661-3d3b-559a-a40c-471e229d773d | note | RECORDS - Photo / diary note / check sheet
9a695813-6e6d-5cec-883b-e83064d2e801 | note | On Site Responsibility - Project Engineer
| checkpoint | 38 - Hatelit Blinding
08eeecb3-2124-569b-a3c7-936e556cbca5 | note | ACTIVITY DESCRIPTION - Hatelit Blinding
a62f28cb-6e58-57cb-8b97-373485deed22 | note | VERIFICATION ACTIVITY - Blinding Mix
396dafb1-ed6b-53d1-96a7-91f76936132b | note | METHODS OR REFERENCE - Even Spread of Blinding
686819e6-4e4c-5f95-a751-a9bac4adfd59 | note | FREQUENCY - Ongoing during install
fe223b27-0524-51e2-9934-38d8bfc200f7 | note | ACCEPTANCE CRITERIA - Blinding mix applied to the Hatelit prior to paving next AC lift
5d8cf60b-2079-5156-b507-3923125792b1 | note | TYPE - Inprocess Testing
7d742359-a5c8-5d5e-9481-d41bfeaf03c8 | note | RECORDS - Photo / diary note / check sheet
209709b4-2e5f-5d2a-9b95-c9fd842157e8 | note | On Site Responsibility - Project Engineer
| section | PMB AC14 Raised Table
| checkpoint | 39 - Visual Inspection for existing failures at intersection
de96a2bc-33ec-5eab-9fda-752edd3f7810 | note | ACTIVITY DESCRIPTION - Visual Inspection for existing failures at intersection
205f4797-884e-5ab6-a8a8-ddf005ad6d50 | note | VERIFICATION ACTIVITY - Visual
1f5197c2-6059-5a60-8c04-158a08704b7b | note | METHODS OR REFERENCE - Site Walkover
6be34b1a-ad75-578f-84b4-26d0d3a9a102 | note | FREQUENCY - Intersection Area
67c1e3e7-4d12-5bec-a839-975077d3de6c | note | ACCEPTANCE CRITERIA - Joint visual inspection undertaken to identify areas of pavement distress at the intersection that require undercut prior to the overlay. Undercut depth to be confirmed by Designer on-site following review of failure mechanism.
20849ad0-1bc0-5478-b223-8dc043cf564a | note | TYPE - Mandatory HOLD POINT Designer Sign Off Required
c04fcd4b-82e5-51db-af10-4ebc2d8e6fdd | note | RECORDS - Visual Inspection Photos
3966b529-74ff-5e50-a4a7-992386d9a872 | note | On Site Responsibility - Project Engineer/Designer
| signoff | Mandatory HOLD POINT
| checkpoint | 40 - PMB AC14
0b58efa5-5b35-58c1-852d-6b44e798e02e | note | ACTIVITY DESCRIPTION - PMB AC14
d53eb549-279b-5371-809f-196f3387c6e8 | note | VERIFICATION ACTIVITY - Check weather reports
2f16104f-6c99-53d6-952d-8d23e24a86d6 | note | METHODS OR REFERENCE - Forecast and thermometer
72288880-de50-516e-822a-39e633c2d9b6 | note | FREQUENCY - Daily
e8083ba2-ffef-5f98-ba09-1bd2c3639050 | note | ACCEPTANCE CRITERIA - No fog, rain or wet surface. Base temp ≥ 5o C
a78ce373-faee-5ba9-90ec-cd2f98bcd2d3 | note | TYPE - Inprocess Testing
b2aaea26-2d83-54f1-a29b-2902b14905da | note | RECORDS - AC check sheet
02a31ebb-c3ae-5e1b-9637-a7faea1d5620 | note | On Site Responsibility - Project Engineer
| checkpoint | 41 - PMB AC14
2a7c85c3-8d4a-5b67-b4aa-ae7f4921aa78 | note | ACTIVITY DESCRIPTION - PMB AC14
c0ad877a-0e59-5bc2-b9f0-3e0fdd398853 | note | VERIFICATION ACTIVITY - Ensure previous layer is broomed clean
979a5bb5-afcf-5377-9300-16ecf040e847 | note | METHODS OR REFERENCE - Visual
48c36c3c-37b2-52e2-b9aa-6ae8b3473648 | note | FREQUENCY - Prior to starting
c4716437-d4cb-56e0-ba80-91fd96dbc366 | note | ACCEPTANCE CRITERIA - Free of detritus and loose material
2420a03e-986c-5b22-a1b4-46e89d10d8b4 | note | TYPE - Inprocess Testing
e50cd3b7-9dff-5ba2-b3a3-979620ab7708 | note | RECORDS - AC check sheet
20baa21b-702b-5e79-b205-7ab7118bc76f | note | On Site Responsibility - Project Engineer
| checkpoint | 42 - PMB AC14
73d6930b-eea8-58a0-8d62-d1eabc936395 | note | ACTIVITY DESCRIPTION - PMB AC14
d80dc83c-7c60-58b5-918d-dc73f7953f57 | note | VERIFICATION ACTIVITY - Production tests
156142d2-cb85-5dd9-8b91-0283c40cacac | note | METHODS OR REFERENCE - Grading, binder content, max density, temp
361c7302-5675-5f53-924e-b76b1ffcd769 | note | FREQUENCY - 1/300t
d5a97775-fd26-5d5c-92c7-8fb2ee1d36cc | note | ACCEPTANCE CRITERIA - NZTA M/10
fd29a0e5-eeef-58d9-9611-4983a3ae0313 | note | TYPE - Inprocess Testing
cb1fad01-c9e8-5b94-bc16-a1a9aaf3b7ad | note | RECORDS - Lab test
8b8dd48d-8330-5d2c-8ac6-5097bb4a0df6 | note | On Site Responsibility - Project Engineer
| checkpoint | 43 - PMB AC14
56c1d178-5d13-55e6-b9b0-a3ddc577a368 | note | ACTIVITY DESCRIPTION - PMB AC14
fb209df9-076a-537e-aa85-39e95acd73c8 | note | VERIFICATION ACTIVITY - Surface finish inspection
30c784cd-0538-5439-95b1-5e630b8f1950 | note | METHODS OR REFERENCE - Visual inspection by the Engineer
fee720a0-0df0-503e-9949-47f486201aa2 | note | FREQUENCY - Each lot
9c47f145-c4c5-59de-a641-e62eab307239 | note | ACCEPTANCE CRITERIA - Uniform texture, no roller marks, no bleeding, cracking or shoving, no crushing of the aggregate.
c849c1de-50e4-5b30-bf46-0460361acc81 | note | TYPE - Inprocess Testing
e7432b47-b29c-52ae-83a3-e3f6c6135ef4 | note | RECORDS - Inspection sheet
e7d49f9c-31d8-5750-9dc0-c557e0090e77 | note | On Site Responsibility - Project Engineer
| checkpoint | 44 - PMB AC14
9ba4bc27-afbf-577b-ae7b-29ceff2c3aee | note | ACTIVITY DESCRIPTION - PMB AC14
1c6b24de-27c3-5abc-854e-bbdc531e641d | note | VERIFICATION ACTIVITY - Plateau Testing
ac513f18-11dd-5fc1-8547-1c0980c0a0e9 | note | METHODS OR REFERENCE - Plateau Testing of PMB AC14 hand-laid areas in accordance with NZTA M/10
34f072cf-20b2-5773-ae6d-e290bb994428 | note | FREQUENCY - Once for a hand laid area
ba8ec917-eead-5c3c-a6f6-f47b3c9acc90 | note | ACCEPTANCE CRITERIA - Plateau testing undertaken in hand laid area to determine the maximum achievable air voids target for NDM compliance
6a3b5aac-eb9d-50b8-b952-ef15bd857f48 | note | TYPE - Mandatory HOLD POINT Designer Sign Off Required
988a2d1f-6f5a-526b-8a92-48b91a392e5b | note | RECORDS - IANZ Lab results
953b2697-2223-5798-919b-2b50ba0a44cb | note | On Site Responsibility - Project Engineer
| signoff | Mandatory HOLD POINT
| checkpoint | 45 - PMB AC14
f0b712ca-333b-5f37-b04e-adc002e769cd | note | ACTIVITY DESCRIPTION - PMB AC14
a941d962-59c4-5f9e-a49f-e30a110eb03a | note | VERIFICATION ACTIVITY - Density testing
a33b97f5-c679-51fe-8a37-84ab46d66e74 | note | METHODS OR REFERENCE - NDM
0abf9fc6-ace7-59c9-9cb6-58cb71cb9513 | note | FREQUENCY - 1/10m staggered between wheel paths in each lane.
642ef2b5-0def-5ea6-a974-0bc36f92a671 | note | ACCEPTANCE CRITERIA - Paved Area: Air voids (2.2% - 7.2%), in accordance with NZTA M/10 (2020) Hand Laid Area: Within 2% of the plateau air voids
51e310df-4a6f-5563-9c04-f1433e980d37 | note | TYPE - Mandatory HOLD POINT Auckland Transport Sign Off Required
d8d2f28c-217c-585e-b02a-41d57a72ed9c | note | RECORDS - Inspection sheet
a2fd4ec8-eee8-5d52-9756-778f09bd4707 | note | On Site Responsibility - Project Engineer
| signoff | Mandatory HOLD POINT
| checkpoint | 46 - PMB AC14
8d6553c1-091a-5467-a66e-5a7bb0f45408 | note | ACTIVITY DESCRIPTION - PMB AC14
88405121-5d86-5da6-8de6-df21ab14bc12 | note | VERIFICATION ACTIVITY - As-built layer
a5a5d766-d617-52d7-9311-08ae82db248f | note | METHODS OR REFERENCE - Stringline
368eeb49-214d-5c4e-8b48-921b0fe423fd | note | FREQUENCY - Each lot
afadf1d6-9dc6-589b-8bb5-ba237721eccc | note | ACCEPTANCE CRITERIA - 60mm to 100mm lifts for undercut areas and 75mm overlay over the raised intersection area, based on the design drawings. Slope of ramp to be 1:20, as per design drawings.
1b7c5367-8121-5a59-a017-e927b910a3bd | note | TYPE - Inprocess Testing
9f5800a7-0671-5488-8e74-c4d64963ff3e | note | RECORDS - As-built drawings & stringline measures
2624d96a-e204-50a2-8456-661e941c40e3 | note | On Site Responsibility - Project Engineer
| checkpoint | 47 - Joint Inspection
d9830bcf-bd92-506e-8a38-da66b15191a3 | note | ACTIVITY DESCRIPTION - Joint Inspection
d00c9bef-3d1c-5401-a6c1-4dc7c4afbe17 | note | VERIFICATION ACTIVITY - Visual
9d8bbe1c-3b6f-5f06-b9e3-87f7180c0358 | note | METHODS OR REFERENCE - Design Report
c3b680ba-fe39-5efa-a90c-2b22b2cf2174 | note | FREQUENCY - Each Subsection
c80dbd76-9180-5ea7-bab7-38856c79e26a | note | ACCEPTANCE CRITERIA - Transverse layer joints to be offset by 500mm and longitudinal layer joints to be offset by 150mm, as per the design drawings.
a7038b4c-8ec7-5eac-b819-5a9c1b1523eb | note | TYPE - Mandatory HOLD POINT Auckland Transport Sign Off Required
1d678fe6-ad92-539c-86ea-a59eb750e800 | note | RECORDS - Site Records
2b088864-2674-5421-90c9-470b5187d415 | note | On Site Responsibility - Project Engineer
| signoff | Mandatory HOLD POINT
| section | Asphalt Surfacing
| checkpoint | 48 - Shape of road
ed2d119b-1370-563a-b51e-b20411d710a1 | note | ACTIVITY DESCRIPTION - Shape of road
cdce96bd-eba4-5691-acf5-ea7fbba5703c | note | VERIFICATION ACTIVITY - 3m straight edge
95c498ca-5b84-5532-a7c2-aebdcadb8ee7 | note | METHODS OR REFERENCE - NZTA M/10 spec
2bc248b5-e93b-5d6d-a462-221fae0a25ff | note | FREQUENCY - At joints and any other areas of concern
0b6ec332-a23a-563b-a1f3-3643600597d3 | note | ACCEPTANCE CRITERIA - Irregularities < 5mm under straight edge
495fa7e1-5f48-517e-b849-07c9d739f594 | note | TYPE - Inprocess Inspection
2e8dd431-1fdb-5d7b-8649-ee65ca65fff3 | note | RECORDS - Check sheet
3b248349-a2c7-5c18-836a-b56cf3789401 | note | On Site Responsibility - Project Engineer
| checkpoint | 49 - Temperature Limitations
9310f4af-041f-5e28-9dc3-a232656f131a | note | ACTIVITY DESCRIPTION - Temperature Limitations
8aacb685-0b8c-5403-9565-2fdffff0b1f3 | note | VERIFICATION ACTIVITY - Temperature
ef1528e1-7dce-5ef8-b7d5-83df6a8a3f6e | note | METHODS OR REFERENCE - Contract Spec / M10 Spec
24fe952a-2fcc-50cc-9e6a-ebc0be3ac4e4 | note | FREQUENCY - Every Site
48934214-fd00-5f93-8b06-f92e5917eb35 | note | ACCEPTANCE CRITERIA - Asphalt not to be paved when foggy or raining, or placed on a wet surface or when temperature is below the base temperature limitations of 10 Degrees Celsius
370ddf82-99bf-5e01-ad72-a9f099d5925e | note | TYPE - Inprocess Inspection
8b7d5076-2924-53d0-88cc-603326344925 | note | RECORDS - Asphalt QA
a8da6a82-5429-506f-9731-6c8f73985a3b | note | On Site Responsibility - Project Engineer
| checkpoint | 50 - Surface Preparation
fefc662e-cefa-5db5-90cd-8cd920bab1c9 | note | ACTIVITY DESCRIPTION - Surface Preparation
16b11dac-e418-5447-a064-7cb781815a83 | note | VERIFICATION ACTIVITY - Visual
d9b25a6f-ee67-52e5-8056-943ab87424bd | note | METHODS OR REFERENCE - NZTA M/10 spec
4227a9ec-bd46-5e00-9021-a5f47d3be552 | note | FREQUENCY - Every Site
3994d4d5-df98-5795-86d1-e8048ee1a5db | note | ACCEPTANCE CRITERIA - Swept clean; all necessary measures to prevent ponding prior to any surfacing
7d9955a8-eb0d-5f70-9f65-1885db8a740d | note | TYPE - Inprocess Inspection
7eed7f1f-1717-58e6-a35d-43ff11bcab6e | note | RECORDS - Visual
8364a6a5-c911-584f-b210-d345fc52cbde | note | On Site Responsibility - Project Engineer
| checkpoint | 51 - Joint Placement
4da82245-b644-5cab-940b-396e9e9f69fe | note | ACTIVITY DESCRIPTION - Joint Placement
e1e8a8f4-d4b7-5422-87dd-eb05abbdc110 | note | VERIFICATION ACTIVITY - Paving Plan
348e28e6-3818-5260-9ea5-b0665a83cd0a | note | FREQUENCY - Every Site
784f7a0e-7b3e-512a-9349-8b3c0d5adc89 | note | ACCEPTANCE CRITERIA - Paving Plan to be completed for every site with dimensions. Joint sealing shall be applied between new and existing surfacing. Joints off-set 150mm longitudinally, and 500mm transversely, as per the design drawings.
a804db0c-34d3-5b34-8450-50725c03219a | note | TYPE - Inprocess Inspection
6ac9cc33-1014-5776-9152-552355e0e0c7 | note | RECORDS - Nil
d75b1e75-80c5-5684-b133-e8e719b2a933 | note | On Site Responsibility - Project Engineer
| checkpoint | 52 - PMB AC14 - Layer thickness - 40mm compacted depth
e04ea6fc-e256-5bee-b415-325b78efac88 | note | ACTIVITY DESCRIPTION - PMB AC14 - Layer thickness - 40mm compacted depth
48370b6c-3aef-5d51-8010-3676b5bfef34 | note | VERIFICATION ACTIVITY - In Situ
0f76cd33-4aa9-5f46-ad4e-95bfdd39987d | note | METHODS OR REFERENCE - Contract Spec / NZTA M10 Spec
c15c703b-e839-5b8b-843e-15eec15c5854 | note | FREQUENCY - Continuous
affd5c56-acf1-5c6d-b341-121a1aeaf7ec | note | ACCEPTANCE CRITERIA - 40 mm minimum and 45 mm maximum compacted depth
473f2ba9-ee87-5d21-bfdf-e162ebf01044 | note | TYPE - Mandatory HOLD POINT Auckland Transport Sign Off Required
5f1bc6cf-a715-587c-ae91-a0ce0299f69f | note | RECORDS - Asphalt QA
85905d5b-fd31-585c-8242-34ec95a2d9c7 | note | On Site Responsibility - Project Engineer
| signoff | Mandatory HOLD POINT
| checkpoint | 53 - PMB AC14
87dae3d4-a4bc-5a48-8c45-dc8cd4a370b4 | note | ACTIVITY DESCRIPTION - PMB AC14
3dedb12e-322b-5e48-9901-2b7ee3f3966b | note | VERIFICATION ACTIVITY - Density testing
5e68bfbc-3071-59d1-87f1-83b01c7b79a0 | note | METHODS OR REFERENCE - NDM
126587ef-24ee-5e40-adad-e5eabf2a270a | note | FREQUENCY - 1/10m staggered between wheel paths in each lane.
ec41375b-a5ae-50ff-80f3-63acbe0b63ce | note | ACCEPTANCE CRITERIA - NZTA M/10
6cec7123-51f7-5e02-96fe-1a3aa32eda01 | note | TYPE - Mandatory HOLD POINT Auckland Transport Sign Off Required
5078e1dc-f8e8-5baa-a88b-47b6c4de07a6 | note | RECORDS - RFI response
82b13bc1-4187-5770-a0fa-347c72549165 | note | On Site Responsibility - Project Engineer
| signoff | Mandatory HOLD POINT
| checkpoint | 54 - Reinstatement of Linemarking and RRPM's
19eb69db-5756-5999-9fd3-9dc9a2b43964 | note | ACTIVITY DESCRIPTION - Reinstatement of Linemarking and RRPM's
308e71b0-0715-56d3-a077-7443acc4a5fb | note | VERIFICATION ACTIVITY - Visual
c038f634-f6bf-5f0a-a13f-511d6afd4f4f | note | METHODS OR REFERENCE - NZTA M7 approved (Class B or C as required for anticipated traffic level)
74c20a98-366b-5446-9cbf-2d0157c3134a | note | FREQUENCY - Every site
6d922c12-9ba6-5aeb-b8ec-199b73c30498 | note | ACCEPTANCE CRITERIA - *Carried out within 12 hours of each shift completed and as per the existing markings * Suitable Traffic Control to remain in place until pavement markings have been reinstated
a5f0775e-2576-53f3-a5f0-24bf7fdfdbaa | note | TYPE - Inprocess Inspection
64e8e07d-755c-5078-93d4-a8bcbc047572 | note | RECORDS - Linemarking Records
fe11e12f-e138-55aa-bed2-7137ccb58031 | note | On Site Responsibility - Project Engineer
| checklist | Triangle/Mokora - Stormwater Drainage | itp | ITP - Stormwater Drainage | ea5b5dee-f826-4d50-b0c1-5bf6de289a4b
| checkpoint | 1 - Permits & Services
edf59c30-ffed-5a56-ab74-abfde34b804b | note | Inspection / Test Point - Permits & Services
68b6e067-97e9-5c02-accd-9754bc4ef53f | note | ACTION - H
bd0db75a-05bc-5df3-850f-bfb305935466 | note | Detail - Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
b36abbd8-90b6-537d-bc7e-d90d19ed40a3 | note | Frequency - Prior to any construction commencing
5d5a7563-1c51-56cf-a344-e9864099a4d5 | note | Inspection / Test Method - Document Review
05a3b03e-f04b-56fc-8893-6091143881d0 | note | Conformance Criteria - Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority
0df16b94-1a6b-582b-b730-dcef6d700412 | note | Records - Permit attached or permit number noted.
5dccd84a-2573-551f-8d85-6e6c06929a07 | note | FH Initials - Site Engineer
70f81cc2-0930-53be-be96-13507289d246 | note | Design Engineer Initials
77af23bf-f560-5a93-98ca-7068fdb0a75e | note | Designers comment - Workover from Watercare obtained?
a2acd53c-d55d-528f-889b-2ec7a15d966e | note | FH Comment - Has been lodged with Mohammed
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.1 - Permits & Services
aad78433-2a87-5880-91d2-10ce0a4a65e7 | note | Inspection / Test Point -
b43fb145-b42e-55b5-9f46-fbb1821dcec7 | note | ACTION - H
20f0a791-5806-5b0e-97de-99ea616b2b66 | note | Detail - Locate and mark out all existing services
6d23a396-7c05-5c1f-aab2-b4708d49ad57 | note | Frequency - Prior to any construction commencing
8dd059e5-32e2-5231-aed2-4584e78a14d8 | note | Conformance Criteria - B4u dig procedure - follow utility protocols and GPR Report provided by Aerial Smith
6f12e89f-d679-53cf-86bd-c94008e1fd54 | note | Records - B4u dig plans & GPR report attached
1155552d-4950-5ef3-af52-61839ee26232 | note | FH Initials - Site Engineer
ea07e2d8-0bca-55d4-b52d-73953068ca3a | note | Design Engineer Initials
d899668b-709f-5993-96a7-e515b00f0912 | note | Designers comment - by BECA? Are they helping with GPR?
98cbceb9-7a16-53fb-aa9b-e35a9324ae33 | note | FH Comment - Has been revised to Aerial Smith
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Pre-Construction Sign Offs
1a11938d-0f80-5c79-9bfd-0ceb9d92b0c7 | note | Inspection / Test Point - Pre-Construction Sign Offs
64bbfda6-6261-5837-88c9-47cb991ff622 | note | ACTION - H
9cb696e2-8212-52a5-b3f0-2894221b8605 | note | Detail - Sub-Contract and Supplier Agreements
c4f10637-de0d-534a-ba85-4ac78b9f6ec3 | note | Frequency - Prior to commencement.
ca972219-5c1f-51fb-a762-7ff951461d87 | note | Inspection / Test Method - Document Review
c0b2ddf9-7c1f-5f43-b57d-1f92b4d64972 | note | Conformance Criteria - Sub-Contract and Supplier Agreements to be agreed and signed
4a660fe5-3b0e-553b-a522-8087885e5bea | note | Records - Subcontract and Supplier Agreements
cdba1a11-ede6-50bc-b796-3393c30fbc02 | note | FH Initials - Site Engineer
cb987693-2958-54e2-8cc5-88d8ffeb9a1e | note | Design Engineer Initials
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Design
40ea2643-5b45-5ccb-a35e-d638a88c2593 | note | Inspection / Test Point - Design
b4e75724-c865-5d6a-8c0b-127321b57353 | note | ACTION - H
6850a3aa-6863-53f7-8748-784bf913662b | note | Detail - Design is approved and Drawings are of the latest revision.
080986b2-7e31-54c3-800b-2da0c88cd3a6 | note | Frequency - Prior to commencement.
f2e6c519-28e3-576e-8b06-52323ce7acb3 | note | Inspection / Test Method - Document Review
b8d4ddc2-def8-55fd-b30b-eb543abedfdd | note | Conformance Criteria - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
2c8ad1dd-020d-5710-81da-a6825eea0d0e | note | Records - Drawing Register.
8f85bd20-5f79-5869-8c49-8f7fc78b948c | note | FH Initials - Site Engineer
3d731fd4-f752-5e33-b10f-b805ec1cbda5 | note | Design Engineer Initials
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Survey set out
9d39bb1a-e55c-57e7-afbd-0f0bd466d1f0 | note | Inspection / Test Point - Survey set out
5bd44bac-6411-554c-841e-98857476fbce | note | ACTION - H
f6000557-9988-5dfb-9092-a2192aebab73 | note | Detail - set out Pipe Alignment and Service Locations with inlet & outlet points and inverts as required to construct to design
a77017d6-5e84-502a-a166-f1edf6f77505 | note | Frequency - Prior to commencement.
fd180bd9-dcfc-5edc-b8df-006bca6fee58 | note | Inspection / Test Method - Survey
9caf16e9-6029-5ad3-9b80-58f8c2c054e3 | note | Conformance Criteria - As per eliga Drawings: 2020-AT-04_G060 REV2 & set out files
05c256c9-ecc8-5d46-90f6-2c2930d24759 | note | Records - Survey Receipt.
9fed3ae3-c947-5fc1-aa86-cea53937b913 | note | FH Initials - Site Engineer
30cdee89-beb0-5e7e-8d41-9f618238b4c1 | note | Design Engineer Initials
a2f22cfc-4250-580b-bfb3-cb99be9d811c | note | Designers comment - Please allow AT representative to review set out locations prior to catchpit installation. IFC drawing number incorrect, it refers to drainage plan prepared for Bucklands Beach RAB project.
ba05f955-938e-5a81-bd5f-f57b237c4be1 | note | FH Comment - Noted and allowed in Design Engineer initials
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Pipe and Manhole Material Compliance
43993f04-1813-553e-b76f-d9c648ff9f9a | note | Inspection / Test Point - Pipe and Manhole Material Compliance
72670a1f-ef78-56cc-9ef8-86691da1027c | note | ACTION - H
0d5692ae-2099-5671-b453-a110de8794bc | note | Detail - Cesspit, Manhole and Pipe shall comply with relevant AT/TDM standards
ad1cb477-7055-5270-a7ed-6f0d7e17fda0 | note | Frequency - Prior to commencement.
c77c3a0d-f5e1-501c-9c40-180e18f9b6f8 | note | Inspection / Test Method - Document Review, Visual Inspection
a143787a-3cd7-57a7-90a5-d8a2033b367b | note | Conformance Criteria - Pipe shall be Check for freshly formed pipes and return if required 1) DN300 Class 4 RCRRJ pipes AS/NZS 4058 2). All Concrete RCRRJ pipes to be fitted with Rubber rings 3). Pipes shall have product certification (ISO Type 5) to AS/NZS 4058 Prefabricated concrete Manhole shall be in accordance with TDM Standards & AC COP
4b76cf6f-2e4a-5073-a3eb-dd9f18b99dbd | note | Records - Manufacturers Data Sheets, Delivery Dockets
21ad2bfa-c3b2-5097-a1ed-58b2e30883a7 | note | FH Initials - Site Engineer
0c765f03-6497-502a-ab35-c2c0e799a8ac | note | Design Engineer Initials
49e2f641-92b5-50e0-92e3-38fc13cfed8f | note | Designers comment - Please specify pipe class. Manholes are AC assets and should comply with AC COP
40c22cd5-74bd-5cb2-b46a-32bef2790d5b | note | FH Comment - Class 4 has been specified
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Locate Existing Services by Hand Digging / Hydro Vac
59a023e1-e665-535c-9ac8-baca3b10b0d3 | note | Inspection / Test Point - Locate Existing Services by Hand Digging / Hydro Vac
39a8ea13-8d2a-55a0-90dd-9b0f9090ef03 | note | ACTION - H
264496d8-06f8-5598-9afc-8874c8f2106e | note | Detail - Ensure all services conflicting with the line of trench have been exposed by hand digging.
85ae82d7-6a1f-5c69-8653-cef8518f854b | note | Frequency - Prior to commencement.
a78d6a4b-97da-5a89-9ab8-d7f24894ea51 | note | Inspection / Test Method - Potholing / Survey
ee6548ac-2c8f-5760-aeb3-3df91c7bad73 | note | Conformance Criteria - All conflicts have been located. New services and / or conflicts to be advised to Project Manager. As-built all services.
95e01594-b9aa-5b36-9327-12659fa24ab7 | note | Records - As-built Drawings. Doc. Review
26e2e09f-c031-58b0-a726-7655b1db9cbe | note | FH Initials - Site Engineer
990cd89c-a6e6-58d1-8a78-264c9341b514 | note | Design Engineer Initials
0ed3baea-29ed-5ad1-a1ba-837ac1d233ed | note | Designers comment - Please ensure asst. to engineers reps is on site during hydro so that they can immediately inform designer for design changes minimising delay to the program
855b3fe1-5f9d-5cee-9dc0-8623b8227a89 | note | FH Comment - Noted. This can be revised if conflict persists
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Trenching & Excavation
0f3345dc-d5ce-5d12-9394-0838ec05361a | note | Inspection / Test Point - Trenching & Excavation
c4920f42-e44a-594c-9a85-d5a186494535 | note | ACTION - H
1387ddd3-80e5-5304-8123-ff2efa1ed359 | note | Detail - Excavation methodology
b9d1b422-cc51-5540-9d3c-dd12e40e3a10 | note | Frequency - Daily
f33049e6-c9dd-5d05-ac55-053a8d0bfb72 | note | Inspection / Test Method - Pre Start review
652daaba-bd0a-5550-bee6-0e71747a1661 | note | Conformance Criteria - The excavation, benching and shoring requirements shall be in accordance with Worksafe Excavation safety guidelines (2016)
6f35d215-a09b-58fe-aa54-83385f11cb2d | note | Records - Pre Start RCP
125eecf7-4d62-51be-a905-b93d8f87b91b | note | Design Engineer Initials
| checkpoint | 7.1 - Trenching & Excavation
49348c0c-6e09-5be2-b19e-bbfd10355ff8 | note | Inspection / Test Point -
3a81347a-3e9a-534c-894d-aed51725a8d5 | note | ACTION - M
4e1135f0-2747-5316-bec2-b9e2d3e8f389 | note | Detail - Trench Profile - Width
555e5376-b3fb-5f1f-8d92-ce7a435cbe38 | note | Frequency - Daily / as trenching takes place. Different depth methodology
44a19888-8222-5c07-842c-abba8c3fe1b1 | note | Inspection / Test Method - Visual Inspection, Excavation methodology
be65350c-7beb-58cf-b3c5-987df1ca5e82 | note | Conformance Criteria - Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing
49c2e00c-ba8e-5f38-9635-29a2f77d862b | note | Records - Construction Photos
c8b93c87-131d-55d3-8642-b073f0d97712 | note | FH Initials - Site Engineer
ea93d692-77c3-5858-b30b-b9f1705331bb | note | Design Engineer Initials
| checkpoint | 7.2 - Trenching & Excavation
625f266e-2b59-5842-a48e-067987952dac | note | Inspection / Test Point -
127305b0-096e-532e-9a0a-7d5eaedeef9c | note | ACTION - W
fe6598e8-dabb-5dda-932f-28901a0ae053 | note | Detail - Trench Profile - Depth
97a33852-4981-5696-b785-c5c587ae80a4 | note | Frequency - Daily / as trenching takes place.
da6834f2-995f-5e30-bffa-a3dc2f5ae7e5 | note | Inspection / Test Method - Visual Inspection, Measurement
24e7bd94-f926-5c51-a288-2c7aefe9f1eb | note | Conformance Criteria - Trench depth varies according to long section and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings
9e689216-8ab7-5be1-82ed-7968227b4874 | note | Records - FH Drainage Line Record / Construction Photos
6267ef00-a897-53c5-894d-9687ccc502d4 | note | FH Initials - Site Engineer
1d01185a-0da4-589a-9cc1-a1635cc54904 | note | Design Engineer Initials
| checkpoint | 8 - Bedding for Concrete Pipe Laying & Manhole & Cesspit
85d4dbf3-c9fe-5838-b535-72ef84f229e7 | note | Inspection / Test Point - Bedding for Concrete Pipe Laying & Manhole & Cesspit
31bf2f8e-8c08-5121-864f-2f7c2f9a0fca | note | ACTION - W
8ffd74e0-37b9-546a-8325-6770c7613a10 | note | Detail - Placing and compaction of Bedding Material.
08e44cfc-4b0b-56e5-9547-61202d588370 | note | Frequency - Inspected continuously during placing and compaction of Bedding Material.
9b09a3b1-8b67-503f-bdff-361d2f1f3536 | note | Inspection / Test Method - Visual Inspection
6edf25d8-98ca-51b0-90cb-25ff14eac341 | note | Conformance Criteria - Bedding & Pipe surround material to be GAP7 or GAP 20 (Stevenson Quarry) or alternate material that complies with AS/NZS 3725
f0d00c88-6abe-5989-9be8-833bfa0c15a5 | note | Records - FH Drainage Line Record / Construction Photos
d080559c-43c6-5599-8d75-9411811b994b | note | FH Initials - Site Engineer
343cea56-5e93-5c36-bafd-f41c65077b34 | note | Design Engineer Initials
| checkpoint | 9 - Pipe Position Tolerance
0d2530e6-f896-5e3b-a877-76958a60017c | note | ACTION - M
11d5e9ae-4c9f-5035-8efb-46ea3ed330e3 | note | Frequency - At any point of pipe
bd3089d1-de16-5890-9c49-729b156e6afc | note | Conformance Criteria - Position tolerance for pipe laying at any point along the length of the installation shall be within ±5 mm from the specified design.Any tolerance required more than +/- 10mm will require design engineers approval.
52e5767a-e4d2-5527-ba7d-17d802902d06 | note | Records - FH Drainage Line Record, Survey Data.
b149089a-c1fa-561e-8366-6a64c79d8417 | note | FH Initials - Site Engineer
eab6e415-163b-543c-b095-9fadc0f8891c | note | Designers comment - Min length of proposed SW pipe is less 2.0m, +/-30mm tolerance for short length is excessive. Can we you please include any tolerance required more than +/- 10mm will require design engineers approval.
ed5f7fa6-de87-5073-bbd3-86583bb04b74 | note | FH Comment - Noted. Has been added in conformance criteria
| checkpoint | 10 - Trench Backfill - Placing & Compacting
ef9569b3-11f3-5ae5-a9d9-d6037a7bb18d | note | Inspection / Test Point - Trench Backfill - Placing & Compacting
63d87dd5-04b1-55d3-b867-1c763d6bc938 | note | ACTION - M
e1ee7a57-f064-5a59-9549-c434a2db4d09 | note | Detail - Placing and compacting of Trench Backfill Material
da92b851-feef-575d-80ef-0d4e27c40fff | note | Frequency - Throughout Trench Backfilling operation.
85dcd1aa-ea9e-52d5-804f-c3564fad5c3f | note | Inspection / Test Method - Visual Inspection
d0a3f584-2780-5609-92ce-19da5f69eeeb | note | Conformance Criteria - Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm MR9 AP40 for Sub Base/basecourse. AP20 for bedding
ce169e35-7d01-5866-bb19-a755fa4dcd0d | note | Records - Construction Photos
b7226d78-26c4-5f96-9476-fdc838962beb | note | FH Initials - Site Engineer
10546664-f4f7-54c5-88d1-cdafdd66851e | note | Design Engineer Initials
1f1da6d8-0a21-52ec-9038-11b8b31dab59 | note | Designers comment - Provide compacted backfill specs to check against. Compaction? Backfill to match existing or use AP20 .
0afae7eb-f613-5eb4-a181-6c8fd9b097b9 | note | FH Comment - Noted. Has been added in conformance criteria
| checkpoint | 13 - Subsoil Material Compliance
c767991c-a034-53ea-a143-0a4fa242f5ee | note | Inspection / Test Point - Subsoil Material Compliance
8ebc3520-4d17-51e1-a9f7-9e93a404ac13 | note | ACTION - H
f1d7dd71-9bc7-5b20-b159-947b03083915 | note | Detail - Ensure Subsoil Drainage pipe complies with TDM RD010
7cdaf9dc-a46b-5ca6-b9ff-11a3a43b4a35 | note | Frequency - Upon delivery to site
80697313-f85e-5abd-a8c7-1381f384d8de | note | Inspection / Test Method - Ensure delivery docket matches materials delivered
484c37b9-28bc-5cfa-803c-d2c93b13487a | note | Conformance Criteria - 110mm diameter Drain flow TNZ F/2 Grade pipe - filter sock
d36d68a3-e23a-5bb5-af85-7579d0088a17 | note | Records - Delivery docket
e1de9540-229e-56c3-9c5c-b3ee723cdc74 | note | FH Initials - Site Engineer
180210a2-0272-58b0-8f3b-68a2cbc9cced | note | Design Engineer Initials
19c22924-bbe9-5901-a527-87d93a08107a | note | Designers comment - Change to ATCOP reference to TDM RD010. backfill material AP20? Specify spes for AP20.
97c2938d-fd9f-54a2-b2f1-86a03d3fba4e | note | FH Comment - Note that we have not allowed for fully wrapped subsoil trench
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 13.1 - Subsoil Material Compliance
7b3424a9-c168-59b4-b994-a94d32e0b040 | note | Inspection / Test Point -
7da366e1-1158-511a-8cca-3c3c4d74cad2 | note | ACTION - H
a68ed5c1-0935-59d7-8d49-ed7502cbc311 | note | Detail - Ensure Material for Bedding, Side support and backfill F6 filter sand drainage aggregate
7474637e-1089-5774-acae-683ea61dd3bd | note | Frequency -
94baea35-948f-5fd3-ad63-241bed7f0f29 | note | Inspection / Test Method - Visual Inspection
ca548565-a7a4-5d5d-be2e-14ff08699408 | note | Conformance Criteria - Ensure clean drainage aggregate - F2 Sand or scoria
0d18ae92-90d4-5906-96dc-c2b2f58e2170 | note | Records - Delivery docket
22c9a005-8d43-581c-8700-1c1d926330da | note | FH Initials - Site Engineer
f062dcdd-2f85-5840-a999-5eb282309ef7 | note | Design Engineer Initials
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 14 - Trenching
24e1783e-33c3-579c-8506-6ad7b7884d65 | note | Inspection / Test Point - Trenching
d7191ab9-c608-537f-a59e-906386476d29 | note | ACTION - H
4937c1ac-b3c3-5dc8-839c-5a2b8cea467a | note | Detail - Inspect trench profile and ensure it is 0.300m wide and 1.000m below Edge of Seal level.
589f8d1a-5e7f-5460-aebb-789cebd66721 | note | Frequency - 10m intervals
4faa461b-766d-5d37-8532-1f1c72c2246b | note | Inspection / Test Method - Visual inspection and measurement
620650ee-66ff-526e-a428-28d5298af2fd | note | Conformance Criteria - Record levels of base of trench on dip sheet. If the same trench is used to combine utility ducts than photos of warning tape to be recorded
3dfd6e9b-c5c5-5224-8579-8894f12bc1dd | note | Records - Photo / subsoil log
a637f1ba-89ce-5034-a9f5-c81c0bdbae8e | note | FH Initials - Site Engineer
b63d9363-8d65-5393-b0a3-7b36f411167b | note | Design Engineer Initials
c1f3b685-124b-5eb2-a1d8-b748d4333cec | note | Designers comment - Please capture evidence of installation of electrical warning tape and magslab where electrical cable is installed
702eeacc-b9df-5c15-a36b-dda94ae79566 | note | FH Comment - Noted. Has been added in conformance criteria
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 14.1 - Trenching
0947e2df-8fcf-5fa0-b25f-6da58651f156 | note | Inspection / Test Point -
8e469b71-a8f0-5d9f-af6d-08489edd60bc | note | ACTION - H
dce805b6-9a27-5450-b547-dc7a3c4570cc | note | Detail - Ensure the trench is cut in a manner than will ensure that the pipes will be laid true to the depths, grades and lines shown on the drawings.
618d304b-d7a8-5d15-bedd-a98e1b489bc5 | note | Frequency - 10m intervals
970d9a62-8273-5123-b30c-e94e2f4bb3c4 | note | Inspection / Test Method- Visual inspection and measurement
7c798be8-06d2-5803-97d9-db9d2e2435d9 | note | Conformance Criteria - Ensure trench line and levels match the design drawings
fc6b851e-0f20-5181-b4b0-a7e5e4834d6d | note | Records - Photo / subsoil log
43a5fd02-34dc-5429-b63f-97a4f1ecf795 | note | FH Initials - Site Engineer
136bdc8f-64a6-5cb1-b27a-59971a5cb43c | note | Design Engineer Initials
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 15 - Bedding, pipe installation and Backfill.
b99818b9-ee6e-5858-9a29-1886083011f4 | note | Inspection / Test Point - Bedding, pipe installation and Backfill.
348c1368-b7ee-50e2-ac4e-2612a38da08c | note | ACTION - W
180745af-aecb-5d1e-8024-e7e65c56e368 | note | Detail - Ensure 100mm thick F2 or scoria Drainage aggregate bedding is placed in base of trench.
6cca7344-2068-5513-b1f4-8a1809ba9c06 | note | Frequency - 10m intervals
88eca7ed-609f-5824-97f1-698e0fbdaf37 | note | Inspection / Test Method - Visual Inspection
5b0a323b-e727-5c55-9cd8-93c0d48a3aee | note | Conformance Criteria - Record levels of top of bedding on dip sheet
22e1f031-7d2b-5484-b3e0-ae2fedfa7a83 | note | Records - Photo / subsoil log
3098f757-9cf7-5a02-b660-8b9db599b7ae | note | FH Initials - Site Engineer
357ad296-3ea4-540c-ae21-f92965f35c0e | note | Design Engineer Initials
| checkpoint | 15.1 - Bedding, pipe installation and Backfill.
797cc6b9-97d4-5ec6-a7b8-fa11b86943af | note | Inspection / Test Point -
f654bbd3-7ca9-52d3-8f52-515bb9e1dedc | note | ACTION - W
fdc76545-69fe-5d76-9f46-3060d9268d57 | note | Detail - Ensure Subsoil Pipe is laid on the Bedding in the centre of the trench
4328bc8c-fe56-50f8-8b5d-2cd2cb9e3f81 | note | Frequency - 10m intervals
7069c34f-081b-54c1-921c-248ddb89bcca | note | Inspection / Test Method - Visual Inspection
7b5bdbbb-a6ab-554e-a707-bfaf61a0896a | note | Conformance Criteria - Consistency with Subsoil Details
ca47566c-d7e5-5c35-be82-6f8b0cb4a6b9 | note | Records - Photos
a7ca7cfe-1c68-5b5e-83d9-c5b9e2a5bacd | note | FH Initials - Site Engineer
be986429-d6a4-5a86-8df8-b994db7c1c12 | note | Design Engineer Initials
| checkpoint | 15.2 - Bedding, pipe installation and Backfill.
3d4d7386-af47-504f-960d-c5228747a8b9 | note | Inspection / Test Point -
e4bf838a-5668-54b3-9bff-a8c15a65bdb0 | note | ACTION - W
46599443-cd30-52da-ab18-f345704422ad | note | Detail - Backfill by tipping AP20 as bedding & AP 40as pavement structure into the trench
3cb5c006-e0ed-530a-b315-29c44fa54218 | note | Frequency - -
9d8a9558-ba40-5f77-93fb-5ebbfabf208e | note | Inspection / Test Method - Visual Inspection
a108f067-427b-529f-bc3e-08e6a7ee9cf1 | note | Conformance Criteria - Ensure good coverage
c2261608-1a9f-5847-953a-259cf59eb4da | note | Records - Photos
3c40fa05-28c0-5c1a-93e0-69d0007cc5d6 | note | FH Initials - Site Engineer
68a7eb99-3091-515d-a356-1a380eb0b29b | note | Design Engineer Initials
fc91f8b9-00ae-59d9-b60f-ec7ef523bd52 | note | Designers comment - TDM specifies AP20 as backfill material.
e34f31f2-983d-5f32-896d-ab147299c965 | note | FH Comment - Sub Base & basecourse AP 40 and bedding AP 20
| checkpoint | 16 - Catchpit Connection
31356826-59b9-5674-8a1f-5a78169543f6 | note | Inspection / Test Point - Catchpit Connection
a1b0d190-4ccb-58c1-b8c2-22ad1dfc627c | note | ACTION - W
9708f1d5-c29d-544a-867b-f0c60e6817af | note | Detail - Ensure minimum entry point 150mm above soffit of outlet stormwater pipe
092d7a17-08ba-569c-871c-388f5ab8df3c | note | Frequency - As required
6044f460-a357-52a7-820a-479dde4a072f | note | Inspection / Test Method - Visual Inspection
5a8fa0cf-4256-5977-a0cc-aa68b2cc06d9 | note | Conformance Criteria - Consistency with Subsoil Details
a6f9cb1d-6dca-533d-8767-3fa562d913d3 | note | Records - Photo / FHIMS-CS-4001
ef936003-be22-5151-a12c-e2a0cb4025da | note | FH Initials - Site Engineer
05b3c399-47c0-509a-bef3-ca393ca7f74d | note | Design Engineer Initials
| checkpoint | 16.1 - Catchpit Connection
b43dfea0-3157-5bf5-8a54-a97597b0ec4b | note | Inspection / Test Point - Catchpit Connection
2c73a5a4-85d5-51cf-86e6-7835f425a83a | note | ACTION - W
cba62b0f-6d52-5315-921b-58018c0cd626 | note | Detail - Perforate Catchpit and epoxy grout pipe from inside to completely seal connection.
c4a0e0ed-7e12-5c8b-ab79-9dc569aef320 | note | Frequency - As required
7da0f3f1-150a-5cf2-ac10-1ed1d853ce66 | note | Inspection / Test Method - Visual Inspection
7f68c318-a592-5bf6-bbf0-5016ef6aee2c | note | Conformance Criteria - Consistency with Subsoil Details
b97c4590-5f05-51ee-9f1b-6342bf654619 | note | Records - Photos
d07a6b7b-4adb-5b0f-bc4c-1af847525b7c | note | FH Initials - Site Engineer
a13b47f7-e613-532d-bd22-1b27074ce9b9 | note | Design Engineer Initials
| checkpoint | 17 - As-Built Drawings
a13a8670-4e69-5375-8812-d1a34c620edc | note | Inspection / Test Point - As-Built Drawings
c7d9402a-62e5-550b-97a3-ae862be8c368 | note | ACTION - W
fc3f854f-f68a-5512-800c-2aa3684f7bf0 | note | Detail - Red pen marked-up As-Builts of every 'Issued for Construction' AT /Eliga drawings
8bfffb33-a4dc-5697-a04e-ae5d99dd391c | note | Frequency - Final As-Built Drawings to be completed within three months of the construction completion of the asset or infrastructure.
c8f81027-f9bf-545f-8e19-8449d76aca19 | note | Inspection / Test Method - Drawings / Visual Inspection
24383d0f-9986-5694-ac11-04203545a499 | note | Conformance Criteria - As Built and GIS Data
76056740-4870-5174-966c-f4ce52e00fd5 | note | Records - Redline As-Built Drawings, scanned as .pdf files.
6852d022-2284-56e5-b1a5-f20b5f3e53cf | note | FH Initials - Site Engineer
4597242d-62be-56ee-ae23-6ad0ddce3bab | note | Design Engineer Initials
| checklist | Tui Rd - ITP - Enabling Works - Footpath, Kerb and Channel |  | Enabling Works - Footpath, Kerb and Channel | d128af73-4d51-4c5f-a6fb-2740c74ad43d
| section | Site Set Out
| checkpoint | 1 - Site Set out
b3a70e77-027b-5067-9797-c99e3ad76b1d | note | VERIFICATION ACTIVITY - Surveyor
3f56bf33-4668-5d49-85f1-015b209f89c9 | note | METHODS OR REFERENCE - Surveyor
87315cfb-95a1-5a5f-9548-d705f00ad218 | note | FREQUENCY - Every Site
e7eb2c4f-7f46-50f1-a7e5-ab729804a3a7 | note | ACCEPTANCE CRITERIA - Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
fe0823db-f60e-5def-bf6f-0982c19a477e | note | Hold Point - Mandatory HOLD POINT -
9b248af1-672b-5c69-ade7-dca23870892a | note | Records - Onsite records/photos
3e5b8ace-d656-5b9b-9a27-844a8ad9cbef | note | Onsite Responsibility - Site Engineer
| section | Materials
| checkpoint | 2 - Kerb & Channel
cc21a109-f5d8-59dc-a8d8-ccb0fa719e9a | note | VERIFICATION ACTIVITY - QA FORM
68efa75e-0683-52de-836e-acc48fc78302 | note | METHODS OR REFERENCE - TDM Technical Standards - KC0001
0da0e14f-fc29-5366-84a7-f3009be5c572 | note | FREQUENCY - Every Site
c7ff5a11-ceb5-5c8d-8756-c60a215acd73 | note | ACCEPTANCE CRITERIA - Kerb & Channel to be laid using precast hand-laid. On compacted GAP40. Concrete 20MPa @28 Days on 100mm GAP40
6916098d-ca06-5ee0-abac-2f868b9b43a7 | note | Hold Point - In Process Inspection
e20fdf9b-07d6-5852-8196-bfa70184b394 | note | Records - FH concrete QA sheet, photos. Concrete Plant Docket
27152a28-930c-57b5-96d2-e9e653b43b3d | note | Onsite Responsibility - Site Engineer
| checkpoint | 3 - Channel Level
80fb4431-347e-5fc9-a390-80d2363e2fbc | note | VERIFICATION ACTIVITY - QA FORM
adbb8108-2646-5c80-b145-604ccdb19d19 | note | METHODS OR REFERENCE - TDM Technical Standards - KC0001
b0e086f7-8085-54b8-adb0-f8151be47c89 | note | FREQUENCY - Every Site
2359dd18-04cc-5fb9-979a-0d0807063a44 | note | ACCEPTANCE CRITERIA - Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
88ffd02c-781d-5c9b-b776-059804f44728 | note | Hold Point - In Process Inspection
85b99411-f60c-562d-9170-3d17a7d61d28 | note | Records - FH concrete QA sheet, Photos
2e84f918-e5ad-55df-98fa-765269aa6b86 | note | Onsite Responsibility - Site Engineer
| section | Civil Works
| checkpoint | 4 - Concrete Footpaths
fb5de875-3277-5c1d-be8a-38991ec5ab37 | note | VERIFICATION ACTIVITY - QA FORM
c518ef1a-3e84-5f84-ae55-9971d1cf54bd | note | METHODS OR REFERENCE - TDM Technical Standards - FP0001
ca34de8c-09b6-51c3-853d-6cc2bddd3f90 | note | FREQUENCY - 10m Intervals
6c0ca541-b8e3-5b4b-a115-a77b853a3b34 | note | ACCEPTANCE CRITERIA - Basecourse - 100mm min. thickness GAP40 Clegg CIV > 12 Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish
87b50fe1-fc55-5b0b-83bd-353dbf8effd4 | note | Hold Point - In Process Inspection
8a153b91-0625-58d2-b649-6cbf79dfc0a7 | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
12bee3bb-6d14-5eb1-8392-c22d7b7e8373 | note | Onsite Responsibility - Site Engineer
| checkpoint | 5 - Tactiles
0525e1a9-82bb-5a87-b902-c881a86b1b0d | note | METHODS OR REFERENCE - TDM Technical Standards - FP0010
f3ed2490-8d03-5ddf-99ab-64d6b72238db | note | FREQUENCY - Each PX
c4d769a1-00b1-55fd-8d2b-b5522fc18538 | note | ACCEPTANCE CRITERIA - Warning TGSI tiles should have 150mm concrete slab underneath
eabc50a9-3774-567d-b460-c1133a69dd2c | note | Hold Point - In Process Inspection, Measurement
c29d65cc-4a8f-590d-83a0-ce9bb12ab667 | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
b59a52ba-d959-5a4e-927b-02c2b592d062 | note | Onsite Responsibility - Site Engineer
| checkpoint | 5.1
4f70dcdc-8b93-5768-893b-5e6f6a77f097 | note | VERIFICATION ACTIVITY - Visual
9b83a32f-20ad-5e95-af66-5b89e3d61942 | note | METHODS OR REFERENCE - NZTA RTS Guidelines for facilities for blind and vision impaired pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
8c16db9b-5b3b-5919-ba9a-d4695c6d4f1a | note | FREQUENCY - Every Site
2aa3cf13-0503-5d3b-bd50-d9d9d643c947 | note | ACCEPTANCE CRITERIA - Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
460c7b5a-1fee-50c5-8759-7dfef181f16b | note | Hold Point - In Process Inspection
8202732a-569e-511d-86cf-7b9ffd188a12 | note | Records - Photos
74267c85-a489-501d-b5cd-201dfa641df9 | note | Onsite Responsibility - Site Engineer
| checkpoint | 5.2
1986d75f-0988-559d-ae30-14e8963f3095 | note | METHODS OR REFERENCE - AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
dd3cd2ea-f63a-5704-9e80-f2eed6eb8c26 | note | FREQUENCY - Every Site
32eed9e8-68e1-5810-9cb3-25af3cd7a90e | note | ACCEPTANCE CRITERIA - Edge of warning indicators to set back 300mm from the face of the kerb or lane.
cb922aec-89b2-5406-9d32-d71ebc39804c | note | Hold Point - In Process Inspection
0e524f9a-f2d5-57eb-bb9f-e3d8bb71da16 | note | Records - Photos
99a962f5-7266-5fe6-a722-32cfde72b75f | note | Onsite Responsibility - Site Engineer
| checkpoint | 5.3
2d01a0cf-f00e-55f4-a9de-6728e500348b | note | METHODS OR REFERENCE - AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
d383a4bf-35d4-503a-b65c-7e49abc2b3f2 | note | FREQUENCY - Every Site
7bce9772-5d80-51c0-af1b-b30ab283bca4 | note | ACCEPTANCE CRITERIA - TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
ee32891e-ee3d-5bbd-aa22-a59b08c66ae8 | note | Hold Point - In Process Inspection
14f1fd15-686f-547e-9b9d-a90fbddf1aec | note | Records - Materials Dockets
d0a8c4db-804d-5119-a31a-c0edc6ed22b5 | note | Onsite Responsibility - Site Engineer
| section | 6
| checkpoint | 7 - As built information
54aa5161-1743-5e4a-8cff-14bd9ecab42d | note | VERIFICATION ACTIVITY - RAMM DATA SHEET
be6b6115-c6aa-5bae-b0f0-16e83ec6ebf9 | note | FREQUENCY - Every Site
bb427496-579d-5081-8569-1e414afd80cb | note | ACCEPTANCE CRITERIA - As built drawings and Ramm Sheets Completed
ea721030-d852-5e8a-9a22-c3494caed59a | note | Hold Point - In Process Inspection
7a35a218-bd56-57cd-b916-239c8298aaa9 | note | Records - Asbuilt records
2a722b40-e81b-54a4-9a0d-37cb0554ea83 | note | Onsite Responsibility - Supervisor and Engineer
| checklist | Tui Rd - ITP - Raised Pedestrian Crossing |  | Raised Pedestrian Crossing | 3e01324b-97bd-4304-a695-40a5afc03c19
| checkpoint | 1 - Permits
27fec997-1f82-5310-a4cc-3f9691948a2b | note | ACTION (Hold, Monitor, Witness) - H
a2c20484-92b0-5cab-a6a3-d03a74dc4fb7 | note | Detail - Obtain Permits
d4b27eea-bd64-57a3-ae39-3ebbdb2fe6f1 | note | Frequency - As required
7f910878-89d2-51db-b2fc-5f71824a2120 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
cba007e9-dee3-500a-bbdf-6c78285df40c | note | Conformance Criteria - Control Checklist - Fall Prevention (if applicable). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
5cda6189-272a-54c8-9343-26d493350df0 | note | Records - Permit attached or permit number noted
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Pre-construction sign offs
ba50fcd4-3675-5e7a-a113-e0a274676de4 | note | ACTION (Hold, Monitor, Witness) - H
82160531-d395-5185-9442-e95248c6a068 | note | Detail - Ensure that Sub-Contract and Supplier Agreements are signed
f8b58947-2fd3-5fcd-a022-a0315636a32f | note | Frequency - Prior to commencement
05024f3f-3f15-5eb2-80e1-6d830cca0280 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
ab121d92-9fa0-50e5-b67d-4cd715289895 | note | Conformance Criteria - Signed Subcontractor and Supplier Agreements
bf8e1f66-bfa9-5009-bb87-878a6e656cbd | note | Records - Subcontract and Supplier Agreements
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.1
490b54d8-cee7-5a0d-b461-4ee5588d78cc | note | ACTION (Hold, Monitor, Witness) - H
10b73f78-e2aa-5c01-b948-cb06210857bd | note | Detail - Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
2d6817f0-3d5c-5707-b2e6-710e8d101630 | note | Frequency - Prior to commencement
c4fae244-28fa-5940-8b7d-ba856b892ffc | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
2beb7e66-f246-5f81-b78d-3e9a02c78f71 | note | Conformance Criteria - TMP is approved by CAR manager for each site and works are only completed within the approved dates..
30c6733f-bca0-53a6-8edc-44cecd16c7de | note | Records - TMP on MyWorksites/On Site
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2
012826eb-b484-5c37-a7bf-64795adb6cdb | note | ACTION (Hold, Monitor, Witness) - H
b0bbf113-6700-5eb3-9efc-b7b615a18b9b | note | Detail - Ensure all Sub-Contractors and Suppliers go through FH induction
af959d9f-b841-5718-b712-271de5bd4e5b | note | Frequency - On site daily
067e1182-c9ce-5fa0-a3d5-8b9749c1ace4 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Induction
a620bf16-832d-5732-a10b-f63122d21cca | note | Conformance Criteria - Supplier's and Subcontractor's signatures on hazard ID and pre-start documentation
c94c1fa4-4ded-51d6-b54e-12044eaf5934 | note | Records - Hazard ID and Pre-starts to safety team
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Design
af37a7f9-2c6a-52ff-8b90-909bfd02d07e | note | ACTION (Hold, Monitor, Witness) - H
2e8076e2-a0d5-5bb7-ae4d-7d0ec5b6306d | note | Detail - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
53b66ce6-bc5c-5f33-93ec-01e24a0f9106 | note | Frequency - Prior to commencement
c94cebb2-abbc-5020-adb0-17627839f839 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
fb971300-7f0f-5d04-90ab-502f2a32dce6 | note | Conformance Criteria - IFC drawings have been received by Contractor
c7993e25-9740-57df-9ac8-32e8b18ec4e2 | note | Records - Check Drawing Register
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Installation of Erosion and Sediment Controls
e5fb46a3-8771-53fb-9667-9e6734bf3e09 | note | ACTION (Hold, Monitor, Witness) - H
c0431ac0-e406-5b79-ab8c-56fb3b0363ea | note | Detail - Ensure that Erosion & Sediment Control in place
ab73a007-3845-5cfe-93d3-753f7d4cb9ba | note | Frequency - Prior to commencement
2c3af693-6dd0-5d2b-a723-00799acf837e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
bf4c223e-a5cc-5950-85ad-6b75cefaf7e7 | note | Conformance Criteria - Territorial Authority has approved the asbuilts for the ESC controls constructed onsite and gives approval for construction to commence
f4e9ee70-9473-52fd-9a5e-969cbbe57b14 | note | Records - Environmental Controls Audit
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Survey Setout
815a3378-44d4-54df-8e16-4d6c3c6cefce | note | ACTION (Hold, Monitor, Witness) - H
593a26be-1f05-5362-9506-766133abb7b9 | note | Detail - Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations)
8c29b851-2b47-5048-a8af-044146a4f6da | note | Frequency - Prior to commencement
795013d8-3fd6-5bbe-b461-cd50fef67134 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey + Smart Level
7e84dfb9-1526-5a4d-8540-5e2f80164207 | note | Conformance Criteria - Consistency with Construction Drawing
72b42055-b6d9-5a27-ad36-b7190376faab | note | Records - Site Photos post surveying
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Locate Existing Services by Hand Digging
c856d8b7-357a-5203-99f5-31deade7ad26 | note | ACTION (Hold, Monitor, Witness) - H
2ec4271b-00a1-556c-bf1e-126f33d791e4 | note | Detail - Ensure all services conflicting with the line of trench has been exposed by hand digging
2654617d-8eff-524a-af84-598f53ad8aca | note | Frequency - Prior to commencement
3277c81e-d5c4-5c99-b1b7-958090c6aff1 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Potholing
c614999f-8faf-51e6-bdcd-d48482767e51 | note | Conformance Criteria - All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. Asbuilt all services
5230a6cd-2373-52a7-ae05-ac9a18b557a4 | note | Records - Digging and excavation checklist, service planes,As-Built Drawings Doc. Review
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Material Compliance
0b40cfbc-833f-5d05-a151-2f4007b2d180 | note | ACTION (Hold, Monitor, Witness) - H
e6c93ce3-581c-533e-b389-42b50db2837e | note | Detail - LESA dowels to be used at all construction joints at 600mm clearance
51326119-fb06-56cc-8a9f-3ceb529edd06 | note | Frequency - Prior to pouring concrete
e89f17e8-3833-58dc-8ca2-50e7ecad1ec9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
b3eeddcf-c067-5bbc-99ea-a1329329a47d | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
f1892a36-aef6-5b9b-beef-3c4b9e773cb7 | note | Records - Delivery Dockets / Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.1
48b882b9-5650-5ffd-b95e-f1eec2830178 | note | ACTION (Hold, Monitor, Witness) - H
889f887b-3692-5ca0-918a-866a30299a37 | note | Detail - 0.25mm polythene layer placed across all surface area at bottom of raised table
50359d7c-5839-5b20-9bc5-d3d8ee586712 | note | Frequency - Prior to pouring concrete
7430aedc-15a4-5911-9d6d-5936562d16d2 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, Document Review
add1d6bc-90ec-5128-9dbb-53a0d4f0f212 | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
6531d092-9893-552e-9d4c-431af47713f3 | note | Records - Delivery Dockets / Photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.2
47b5926c-e98d-5c36-8ecd-82e7847f4670 | note | ACTION (Hold, Monitor, Witness) - H
f77521dc-e705-5eaf-bd98-84ed6ab85e65 | note | Detail - 50mm thick compacted layer of AP20 aggregate placed underneath polyethene layer.
7cf6a455-319b-52de-8bb4-5c0624f06c5e | note | Frequency - Prior to pouring concrete
dbc8dc95-45a1-5fb1-b2a1-8999d8fe2ba5 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
52840ab0-e0c1-5e69-a331-31a44a64a55f | note | Conformance Criteria - CIV >15
edb89037-6b6d-5877-817e-0b6c5f2924ea | note | Records - Delivery Dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.3
59a05472-de83-5b1b-811e-1b663163b10c | note | ACTION (Hold, Monitor, Witness) - H
7e33e390-6ced-571a-8ccf-22e49bbbcd6e | note | Detail - Two layers of 663 mesh 50mm cover from top and bottom to be placed inside with 70mm plastic chairs separating.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.4
0ba35755-f9d6-593b-8cfd-b5b8915ac50a | note | ACTION (Hold, Monitor, Witness) - H
7dac000e-cb7d-5434-98c6-691aaf3a25b8 | note | Detail - All concrete delivered to site shall have 50MPa 28 day compressive strength with 4kg/m3 of Black Oxide Powder
871477b2-c4b9-56d0-9dce-bbdb7e7c8bc7 | note | Frequency - Prior to pouring concrete
a5c08413-d741-5698-b848-2db4c9565c21 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Concrete Delivery Dockets
30d097ea-1547-5f61-a6d0-b88edce8bb5d | note | Conformance Criteria - Delivery Docket added to QA folder
52c5f6ec-e404-550d-a6ad-f78191c91d9a | note | Records - Concrete Delivery Dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8 - Temporary Works (Formwork)
bbf4a7ac-639e-54a4-92a3-be6aae7ac957 | note | ACTION (Hold, Monitor, Witness) - W
28c6005a-d6f6-5be2-b8c2-c78c9bdd9ac5 | note | Detail - Formwork to be set to correct line and level
7db1a44d-138b-58f9-98d1-4bd677ba6241 | note | Frequency - Prior to pouring concrete
e00ef60f-7a88-5b22-9f8d-ee43da8d8dc7 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
21bffa84-4409-5d4f-b0fb-42219375537a | note | Conformance Criteria - Concrete Inspection Record
2e873039-432c-5a1a-9043-5175589eacfd | note | Records - Concrete Formwork Checklist
| checkpoint | 8.1
e757b3b5-b337-5965-85e3-54340712c0d5 | note | ACTION (Hold, Monitor, Witness) - H
73319b19-0ff2-506c-bbce-711d4c186787 | note | Detail - Raised table formwork to be 75mm above existing road level and be 300mm in depth and gradients respectively of entry (1:15) and exit ramps (1:15)
478ac928-e26f-5909-90eb-acad76d70cbe | note | Frequency - Prior to pouring concrete
a72e45b0-4eda-5396-9ad0-9f2771da502d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
a462f941-cdb2-57d0-9f0a-e8b209444a13 | note | Conformance Criteria - Designer to inspect formation level
b6915d64-da34-5392-bd43-673942c091ae | note | Records - Site photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8.2
afa30351-bcbc-5dc4-8602-ebff08308d52 | note | ACTION (Hold, Monitor, Witness) - H
d597cb87-06ba-5bb9-9093-3ccae6ac94fb | note | Detail - Raised Table ramps to have 250mm depth at entry point and tie into 300mm depth to meet raised table
84aec1bd-33c1-5c58-9786-5cd6d7ded30d | note | Frequency - Prior to pouring concrete
e25982b3-80d9-50d3-a436-3e733298eb3e | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
9d935748-7ce1-5299-a5fd-d4a5916740b7 | note | Conformance Criteria - Designer to inspect formation level
333b4c8b-37e1-5f98-bd3e-5b26e6548b6a | note | Records - Site photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8.3
def772d5-d7d3-50ef-a721-8444f53c14f4 | note | ACTION (Hold, Monitor, Witness) - H
25253775-40d1-5a4b-8a13-15ec440f6d1c | note | Detail - Raised Table ramps to be 1.125m across for entry and 1.125m for departure ramp.Toe to be 0.5 to 1m across for both entry and departure with 50mm asphaltic wearing course
90bfdea5-90b7-5657-8d22-68d78803e614 | note | Frequency - Prior to pouring concrete
6fd89d6a-1756-5e3e-a654-5d3b651c7592 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
85d79df7-de17-5e7d-bd89-b0d59fd44efe | note | Conformance Criteria - Designer to inspect formation level
aa6659c1-8018-5057-9b1a-aaf97974fb9c | note | Records - Site photos
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8.4
c5c20c4e-35b5-528b-a7ad-51046fbeb61b | note | ACTION (Hold, Monitor, Witness) - H
92c8a804-0a8b-5711-856a-a5c4de819972 | note | Detail - Raised Table ramps to be 1:15 gradient for ramps at entry and exit ramps to be 1:15 relative to the road
5416dafe-4bd5-5372-94c8-e5e1fe8dc175 | note | Frequency - Prior to pouring concrete
77cb0788-79f4-56f0-a33d-3e45d46bdce8 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
7ba57623-f318-5530-8a5c-9487a0e5b271 | note | Conformance Criteria - Designer to inspect gradient level
abbb0998-17d0-5efe-a368-fdcfb9a5c603 | note | Records - Site photos / Concrete Formwork Checklist
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 8.5
03b3871e-8b5d-579f-b624-600fab2edb4b | note | ACTION (Hold, Monitor, Witness) - H
14c1af3b-0a67-553d-96af-81e97e3ee855 | note | Detail - The Site Engineer and MSQA Engineer must sign off the formwork prior to concrete being poured
b8b72f22-3b69-5364-9042-2d91b0c6b7fc | note | Frequency - Prior to concrete pour
a947dc27-166f-5f9f-bf9c-52f2a217a8ee | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
89535c5e-fa95-5ff3-9d7e-60f66ba0f58a | note | Conformance Criteria - Concrete Inspection Record
d9df0870-7595-52f7-819f-052bc02233f7 | note | Records - Concrete Formwork Checklist
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 9 - Reinforcing
a483b9ca-69dd-5d0e-965a-9876b6d06dd8 | note | ACTION (Hold, Monitor, Witness) - H
f8562a44-3b70-5632-894e-17bb4af885eb | note | Detail - All construction joints are to contain 2 rows of LESA dowels or similar approved dowels .Dowell system 50mm w/ Black 300*50*6mm plates @400 centres placed across the construction joint
c65ab12b-6d56-5159-9d97-e6d403eee0e3 | note | Frequency - Prior to pouring concrete
c60057f7-1942-52f2-8def-a93f33fd5557 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
e46da85f-2479-5a14-a043-28a5437457a5 | note | Conformance Criteria - Concrete Inspection Record
87b1e9f5-c841-57f2-88e8-6f2a0bf8e63d | note | Records - Site photos/Concrete Formwork Checklist
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10 - Concreting
97896867-eeaf-5669-bad0-933437fd437c | note | ACTION (Hold, Monitor, Witness) - H
3e2fec61-c2dc-5909-98f3-3e43dd43a197 | note | Detail - The MSQA Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required
dd91c8a3-aa9c-5d52-bdc6-e20ff79db6b1 | note | Frequency - Prior to concrete pour
730251a8-99e1-5e3e-a425-18068f1a53c2 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
adfc2b04-0311-5462-bc5e-42481609a712 | note | Conformance Criteria - Engineer will be notified via email/SMS at least 24 hours before required for inspection
141ddc00-758a-5c78-9ea1-99d96eb70498 | note | Records - Email / SMS
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 10.1
69a7e782-0f20-505a-98ec-b3e7c658a1ae | note | ACTION (Hold, Monitor, Witness) - W
1b882c26-2e89-5dee-863b-97b2323fbd0c | note | Detail - Vibrator to be used throughout concrete pour
e7fed74c-3981-525a-8fa7-3e521d430634 | note | Frequency - When pouring concrete
d917a995-e97b-51fd-93dc-904643423fec | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
0a0b4d49-5465-5fb2-8337-d0042d902169 | note | Conformance Criteria - Concrete Inspection Record
137e8a40-f5dc-5c6d-85f8-487a576970ae | note | Records - Concrete Formwork Checklist
| checkpoint | 10.2
55104ca2-1171-5c98-a807-caf5f5bdfdcc | note | ACTION (Hold, Monitor, Witness) - H
874da190-d784-5979-be8b-4dc692c0b4a1 | note | Detail - Concrete surfaces shall be U5 broomed finish for ramps, and exposed aggregate finish for table top.
dc95e63c-d0ed-53fb-84e5-8cb6c1846885 | note | Frequency - At completion of pour
e0573e3c-88f3-5801-ab47-d79ac13a7ecc | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
75ae0ee2-9b1f-5ff8-be6c-f0a0df9f82e0 | note | Conformance Criteria - Concrete Inspection Record
7697fd61-0dca-59a9-b4d1-102d26a7a314 | note | Records - Concrete Formwork Checklist
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 11 - Curing
227f88b0-defc-59a4-b352-961044a03245 | note | ACTION (Hold, Monitor, Witness) - M
6ee763f0-07d1-515d-836c-3fb9effb7d37 | note | Detail - Concrete will be left for 48 hours minimum to cure before traffic is allowed on it.
f4dcc119-1795-5dc1-a2ef-79c4cfd1b896 | note | Frequency - Post Pour
9b0383db-3e56-5781-bd64-3d095d90fd5d | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Monitoring the time allowed for curing
1b26a275-ef51-5599-8c30-2e780b200566 | note | Conformance Criteria - 48 hours minimum have passed
0a7ebac8-54e0-5356-9e0b-7dcef3ce630d | note | Records - Concrete Formwork Checklist
| checkpoint | 12 - Remove formwork
449818d5-a8fa-5432-901b-84273c1baf4f | note | ACTION (Hold, Monitor, Witness) - W
8ba838c0-117d-54e9-a163-aafce54e32e3 | note | Detail - Remove formwork after 48 hours
1b267b34-95bd-51ef-98c6-2213412ec75f | note | Frequency - Post Curing
2720970a-a745-56b1-ab59-07e8eddb9a7f | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
c9844558-aad9-5670-9261-bf04227f82bc | note | Conformance Criteria - Concrete Inspection Record
380839cc-96a3-5bf7-bddd-d7d6f2a0f6ee | note | Records - Concrete Formwork Checklist
| checkpoint | 13 - Asphalt- Concrete extension slab/ Toe
e4e6cb12-36cd-5be5-ad6c-d82e34f146d7 | note | ACTION (Hold, Monitor, Witness) - H
7406339c-6ea2-5b73-a93b-3a9a37d8085d | note | Detail - Two rows of Lesa diamond placed mid depth @600 C/C along construction joint as per TDM TC003
f52b5f74-874e-59f7-8b81-e297374b6e30 | note | Frequency - Prior to pouring concrete
1fb52637-98a5-5d4c-a017-e2fdb27352e9 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
afa15d5e-0f9f-5d32-8ccc-eb24fc92ad38 | note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
033aec2b-ff3a-526e-a5a5-9dc1eef75402 | note | Records - Site photos,delivery dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 13.1
5b4601b9-3da8-5548-ab46-595494f86d5c | note | ACTION (Hold, Monitor, Witness) - H
61e36202-407b-58d6-ad9f-8481b35a1d40 | note | Detail - 200mm thick 50MPa Concrete with two layers of 663 mesh
28ea4af2-0b57-5405-a810-be40ff73f3e2 | note | Frequency - Prior to pouring concrete
186f1635-b6b6-525b-8fad-7dbd6a981c28 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
216ceaa9-74e6-50a8-8fd8-7f2e7d224541 | note | Conformance Criteria - Pre pour Inspection Checklist, Concrete Inspection records
a528a1ce-ab92-54b0-85f5-82c41fd5f307 | note | Records - Site photos,delivery dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 13.2
424df050-ce1b-5d7f-bd0c-a6219fc685bb | note | ACTION (Hold, Monitor, Witness) - W
019e82fa-e648-5f14-b981-eb8406cf8e9d | note | Detail - Tack Coat between AC and Concrete slab
6fa81800-074b-591d-bc88-b0865b2cd700 | note | Frequency - Post Curing
aef84e74-7adc-50f0-ab2c-cce47a8feb6c | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
12031c5e-62f6-5f52-9012-43b6d47ce676 | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
a6725812-8963-53ed-8f3e-5b6739097eea | note | Records - Site photos
| checkpoint | 13.3
69a64a59-21c4-578a-962a-830c2dabb06d | note | ACTION (Hold, Monitor, Witness) - W
6f6b6986-7281-5a94-ac09-6d6deb338865 | note | Detail - 50mm thick DG10 / Mix 7
3e85a88a-fda3-5e82-ba42-5b3f025bb890 | note | Frequency - Post Curing
b8a364da-5b5e-552d-8629-883309a956b6 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
09b600e8-603b-5b68-bbb9-7359aa74aac1 | note | Conformance Criteria - Photos + Delivery Docket added to QA folder
8f6fa0e8-02f3-5e72-80ec-e3395ef9f6ed | note | Records - Site photos,delivery dockets
| checkpoint | 14 - Lot Number QA File
66319e01-9a8e-5da4-9638-24ac676faf5d | note | ACTION (Hold, Monitor, Witness) - W
f1ac64d9-90f4-5d08-8288-892c1b229ced | note | Detail - Ensure all QA Records,site photos and incident cases (OFIs) are closed and included within QA file
0adc26f3-d8c5-58ca-b6a8-1ed26b528fd6 | note | Frequency - At completion of Lot
a60ccfde-8c3c-577c-8a6c-a4671dc0bd0b | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
008633e3-7f2a-539f-ae24-293654ffe57a | note | Conformance Criteria - All QA files compiled and submitted to client
f8cb7811-06b8-50ee-8538-5c3fa0184ff8 | note | Records - QA records
| checkpoint | 14.1
19c0fec5-a764-5d59-bc01-668d47d83585 | note | ACTION (Hold, Monitor, Witness) - W
c112341e-37cc-55c2-9ca4-7a51cd0c288f | note | Detail - Delivery Dockets to be included in QA file
4b44d7a0-d2ab-5adf-8d46-cc76328eceae | note | Frequency - At completion of Lot
b1ac1b10-9e79-5895-8c94-2156aed14103 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
d5a387e5-1cdf-56a7-8317-98d0ba782942 | note | Conformance Criteria - Delivery Dockets to be included in QA file
a0e1de13-b60d-5148-a8f8-be104e1450a4 | note | Records - QA records
| checkpoint | 15 - As-builts
8a21c5a9-6a5f-54d6-8e30-8c3e17a96fb6 | note | ACTION (Hold, Monitor, Witness) - H
dbcfa9ea-b4ec-508c-8b77-d6f22736ee67 | note | Detail - Red pen mark up drawings to be included in QA file
2e95b181-a164-54fb-93b3-fe14f66a0952 | note | Frequency - At the completion of the Lot of work
1ca6fcea-f576-5c6f-9ff8-65089baf9549 | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
df59df4b-91b4-5000-897e-646da754b63e | note | Records - Asbuilt Drawing
| signoff | AUTHORITY HOLDPOINT
| checklist | Tui Rd - ITP - Storm Water Drainage |  | Storm Water Drainage | 663f957f-e38a-466c-ac46-241b84567e9b
| checkpoint | 1 - Permits & Services
ce12ade3-cb7b-5499-bf6f-3ec7d4c22204 | note | ACTION (Hold, Monitor, Witness) - H
c7094bd4-e1ea-59b3-b91c-514084d1284a | note | Detail - Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
8b21e22a-e211-57bf-9de3-10b5b6c3af3a | note | Frequency - Prior to any construction commencing
e7a1811a-2e40-5d7c-a613-e6991e8fbdb5 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
cfedb522-4cc7-5979-b0a4-23c3f86df132 | note | Conformance Criteria - Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority
813b0721-0c7d-5aae-9f58-f3da43ea6b92 | note | Records - Permit attached or permit number noted.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1 - Permits & Services
5a0421d9-9d2e-5c84-98da-a04eb8897c0c | note | ACTION (Hold, Monitor, Witness) - H
b209d238-0232-5932-8aa0-c652838ec883 | note | Detail - Locate and mark out all existing services
e8d7e0ad-4ef3-57cb-84db-96901d156852 | note | Frequency - Prior to any construction commencing
43550723-4b57-5a79-a4ee-5721731ce73a | note | Conformance Criteria - B4u dig procedure - follow utility protocols
b7bc9add-d5d4-5b87-9cd3-7885ca2df1cf | note | Records - B4u dig plans & GPR report attached
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2 - Pre-Construction Sign Offs
7ef7394b-4c0a-5184-bb04-e5dc144cea7d | note | ACTION (Hold, Monitor, Witness) - H
c72270f7-5022-5151-83b1-b93258e009b0 | note | Detail - Sub-Contract and Supplier Agreements
9963b1df-256d-5332-977e-1e35461b8acc | note | Frequency - Prior to commencement.
004ebe3c-8101-57b1-9490-53ef8eb4ca4c | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
f59ccbe0-0c02-5bc4-af05-9c1599c7b30b | note | Conformance Criteria - Sub-Contract and Supplier Agreements to be agreed and signed
67b28206-1fad-5e9f-8111-bfc6206b15ab | note | Records - Subcontract and Supplier Agreements
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3 - Design
1439bcb0-ff56-5e50-8eac-67c7cf8a7bdb | note | ACTION (Hold, Monitor, Witness) - H
53ddcff0-f160-5431-af08-b292010ad49a | note | Detail - Design is approved and Drawings are of the latest revision.
8335cee4-c84a-54aa-8077-f713c2a00eff | note | Frequency - Prior to commencement.
f919c81f-0a04-5c43-b50a-f3f985d27250 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review
72203cdf-e3e8-564f-aa3d-84628ded8cae | note | Conformance Criteria - Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
0afb1d06-6010-5a16-aae4-e534e6acef14 | note | Records - Drawing Register.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4 - Survey Set out
695eeadb-21d8-520c-84a5-b815e9143c92 | note | ACTION (Hold, Monitor, Witness) - H
be0f5bc0-1f30-586c-b040-8ed1f07e35a1 | note | Detail - Set out Pipe Alignment and Service Locations with inlet & outlet points and inverts as required to construct to design
51069b86-ef88-58b9-86d7-4ee1774bd8bc | note | Frequency - Prior to commencement.
9b628672-dad7-51a1-98fa-0121b24a1215 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Survey
1bbc6cff-32f8-59ef-bb3a-5bba4b0536b2 | note | Conformance Criteria - As per BlueBarn Engineering Drawings: 02237.17-T-400 & Set out files
8441ed82-e175-54db-922e-ee4ade78bafd | note | Records - Survey Receipt.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5 - Pipe and Manhole Material Compliance
c9fa5ad7-ebe7-53a1-b38d-b89b9fa24373 | note | ACTION (Hold, Monitor, Witness) - H
fcfeb77e-56b2-53e8-a11d-ca331eea818a | note | Detail - Cesspit, Manhole and Pipe shall comply with relevant AT/TDM standards
364e94e3-1a7f-5f1a-a33a-0572b34905eb | note | Frequency - Prior to commencement.
6bf48cda-311b-5643-a54b-ea1526ee5920 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Document Review, Visual Inspection
b14f76c5-4a15-5117-b379-e861ce40a03d | note | Conformance Criteria - Pipe shall be Check for freshly formed pipes and return if required 1) DN300 Class 4 RCRRJ pipes AS/NZS 4058 2). All Concrete RCRRJ pipes to be fitted with Rubber rings 3). Pipes shall have product certification (ISO Type 5) to AS/NZS 4058 Prefabricated concrete Manhole shall be in accordance with TDM Standards & AC COP
b206e6ea-7685-5ac4-b53f-7918812b0798 | note | Records - Manufacturers Data Sheets, Delivery Dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6 - Locate Existing Services by Hand Digging / Hydro Vac
f44f8fe7-e799-5fce-b898-b1a983f26779 | note | ACTION (Hold, Monitor, Witness) - H
3d36c2cc-cd07-5999-89cc-e82f5595ee0a | note | Detail - Ensure all services conflicting with the line of trench have been exposed by hand digging.
9bb0c561-23b1-51c9-b09f-cce6d4479516 | note | Frequency - Prior to commencement.
72f38939-0521-5e68-964a-84b336f4bfab | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Potholing / Survey
d57c16bc-8e3c-590b-803a-96a90fb90597 | note | Conformance Criteria - All conflicts have been located. New services and / or conflicts to be advised to Project Manager.
da25078e-c472-5d7f-b8e0-e6d2ca32b5c3 | note | Records - As-built Drawings. Doc. Review
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Trenching & Excavation
ca817a5f-ec33-5e78-a10c-faddd889872b | note | ACTION (Hold, Monitor, Witness) - H
2f1b4bbb-1371-56bc-b001-c91590241d52 | note | Detail - Excavation methodology
c23b3876-2e6d-55e9-a4cb-1354c2e6bf68 | note | Frequency - Daily
d17c12be-f085-54f2-9aaf-7dcb36132d5e | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Prestart review
bc79b9e3-9b17-556f-860f-b2076a7751b7 | note | Conformance Criteria - The excavation, benching and shoring requirements shall be in accordance with Worksafe Excavation safety guidelines (2016)
05f33886-f526-5cb8-a173-639a8a88d2cf | note | Records - Prestart RCP
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7 - Trenching & Excavation
9c26b39e-6b6e-5a31-abdc-1e37a3e82be8 | note | ACTION (Hold, Monitor, Witness) - M
3c5780f5-f074-5200-a1cf-0b4ce3c3457a | note | Detail - Trench Profile - Width
dd00e04a-51b5-545a-86b5-169f52d07b78 | note | Frequency - Daily / as trenching takes place. Different depth methodology
de46a123-f3cc-5b44-bbf1-9b215b3f5e37 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection, Excavation methodology
146b0783-00c8-5c6b-86bc-8f6b4f9b901a | note | Conformance Criteria - Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing
8dc0da60-6656-5335-a24a-717ffa1ea55c | note | Records - Construction Photos
| checkpoint | 7 - Trenching & Excavation
e1b507b9-acd6-549b-b766-51bf826a8188 | note | ACTION (Hold, Monitor, Witness) - W
cbdaedc2-9529-547f-beab-f99b31a066b6 | note | Detail - Trench Profile - Depth
f55ee2bf-d821-50a7-8c69-bfb528371505 | note | Frequency - Daily / as trenching takes place.
63a96001-621a-5c0d-8577-6e9acee93800 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection, Measurement
c908020b-e5ed-5ce0-b27a-a71ded00e5b9 | note | Conformance Criteria - Trench depth varies according to long section and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings
bf3da196-eed0-5ed7-8cc3-1f7575b69f44 | note | Records - FH Drainage Line Record / Construction Photos
| checkpoint | 8 - Bedding for Concrete Pipe Laying & Manhole & Cesspit
2b4984e0-e464-5af1-b3f6-65dfb79e03cd | note | ACTION (Hold, Monitor, Witness) - W
37e2d56f-faaa-5b15-bc0a-ef364b50b088 | note | Detail - Placing and compaction of Bedding Material.
7b0db10e-d525-5e5d-b05f-934ac13facc6 | note | Frequency - Inspected continuously during placing and compaction of Bedding Material.
3d88c325-430e-555a-9116-b4dcffc07fd9 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
7f167ad5-14d7-533d-bebf-97fa4baf9434 | note | Conformance Criteria - Bedding & Pipe surround material to be GAP7 or GAP 20 (Stevenson Quarry) or alternate material that complies with AS/NZS 3725
31a4f39e-4026-5c70-bd42-b201cf10ed37 | note | Records - FH Drainage Line Record / Construction Photos
| checkpoint | 9 - Pipe Position Tolerance
cac18c6b-ea1b-56e6-8c32-4a83da7d0787 | note | ACTION (Hold, Monitor, Witness) - M
69c29f0f-2a49-5699-bc78-16db35a32f83 | note | Frequency - At any point of pipe
a35be04f-e8c4-5531-8d4c-b79675c7c016 | note | Conformance Criteria - Position tolerance for pipe laying at any point along the length of the installation shall be within ±30 mm from the specified design.
5a63b9d7-fe06-5dd8-9809-b932614ceee6 | note | Records - FH Drainage Line Record, Survey Data.
| checkpoint | 10 - Trench Backfill - Placing & Compacting
78ad3be4-f2bd-554d-ad7b-b0c66d78819b | note | ACTION (Hold, Monitor, Witness) - M
1ea30a9b-ead1-53f1-b050-78ee41c5e9a5 | note | Detail - Placing and compacting of Trench Backfill Material
2f862942-ca48-5d04-adce-9974ce20f575 | note | Frequency - Throughout Trench Backfilling operation.
e42a7896-fb0d-5427-8f5f-4eedade00d96 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Visual Inspection
9ff021eb-8ec7-5510-9cb8-f9aad7645160 | note | Conformance Criteria - Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm
4171789b-8831-527b-8a39-2b33323aff76 | note | Records - Construction Photos
| checkpoint | 11 - As-Built Drawings
b91c72a1-211f-5989-b3ee-198c8943c6f0 | note | ACTION (Hold, Monitor, Witness) - W
57ccb85a-d32c-53cf-b96c-98deba6cae9c | note | Detail - Red pen marked-up As-Built of every 'Issued for Construction' AT drawings
c5e98eab-cc38-59f3-b681-a4d8b2b28339 | note | Frequency - Final As-Built Drawings to be completed within three months of the construction completion of the asset or infrastructure.
cc8e8e67-1400-5203-ac6f-d3fce4c21cb3 | note | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) - Drawings / Visual Inspection
6a67a938-4f28-561e-a79e-338133464b25 | note | Conformance Criteria - As Built and GIS Data
1e002b85-2907-53a2-a42e-b6bf254ca696 | note | Records - Redline As-Built Drawings, scanned as .pdf files.
| checklist | Tui Rd - ITP - Vulnerability Users Package 13 |  | Vulnerability Users Package 13 | 75434e9c-041b-4cf4-894f-88f23485bffa
| section | Materials
| checkpoint | 1 - Mountable Kerb
94c29683-000e-5ad4-baa7-381d30a63125 | note | VERIFICATION ACTIVITY - QA FORM
38b77392-6d8a-5669-9bf2-4b2286d099e0 | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002
38bf7a47-02cd-571c-b2a6-96bc01455ea9 | note | FREQUENCY - Every Site
bd4f7313-e3ba-54a7-937e-79978ceb53e2 | note | ACCEPTANCE CRITERIA - Mountable Kerb to be laid using precast hand-laid and painted with two coats of reflective paint
03564ad4-0295-5594-b61a-de9d6fdde1f7 | note | Hold Point - In Process Inspection
15c7dc6c-1098-5087-b503-10e99190ede4 | note | Records - FH concrete QA sheet, photos.
2933e632-e6aa-59e5-84e5-4aef10b68ef5 | note | Onsite Responsibility - Site Engineer
| section | Construction
| checkpoint | 2 - Survey Setout
ed391fcb-a866-56b7-93e4-e000060df3d3 | note | VERIFICATION ACTIVITY - Survey
f4c4c86c-7cc3-5ab4-a324-b94a772fcdb5 | note | METHODS OR REFERENCE - Setout Kerb Alignment required to construct to design
c551bc75-c040-5570-a643-f43c3840cb2e | note | FREQUENCY - Prior to commencement.
d7226633-2898-5063-942b-4523db21108e | note | ACCEPTANCE CRITERIA - Survey
a2bea14c-64b0-5c5d-afec-f40c0341b7d7 | note | Hold Point - As per Construction Drawings
d21a34d8-ec14-5fdc-a8ab-a56ac3ad66e0 | note | Records - Survey Receipt.
c5f988be-dcfc-5446-9166-c6fc43bb40fd | note | Onsite Responsibility - Site Engineer
| checkpoint | 3 - Concrete Island
9482d2ec-5678-56e2-920b-afd3f4d1bb7a | note | VERIFICATION ACTIVITY - QA FORM
b2480276-0192-5a19-967b-cd97340fe315 | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002
c34c0bfb-2210-5a2f-9092-376ce938fab4 | note | FREQUENCY - Each Site
f1eb70e5-24bf-596e-ae0b-743f12a50d83 | note | ACCEPTANCE CRITERIA - Kerbs to be haunced with 20MPa Concrete
b5b98a1d-99b9-557f-a382-d196dc140631 | note | Hold Point - In Process Inspection
77293155-9995-599f-8e5e-a46ed25637c4 | note | Records - Photos
47f2e84e-b7b4-50d0-b769-66311c61bbe3 | note | Onsite Responsibility - Site Engineer
| checkpoint | 3.1
60d3b457-c9f0-5a03-ae39-a6bc1fbcff18 | note | VERIFICATION ACTIVITY - QA FORM
206df951-7b57-5537-9f9c-ab13e5f1dcaa | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0003
9f1bf784-5774-5ee0-8430-6b9e88cc8aed | note | FREQUENCY - Each Site
18e194e2-71c1-5f7b-95c4-366dcafd22de | note | ACCEPTANCE CRITERIA - Basecourse to be 150mm min thickness of GAP65
1f76bb0d-f2c9-57ba-8903-7fe44c8ca105 | note | Hold Point - In Process Inspection
26349673-7af0-5578-b5db-4a0b9e79bbda | note | Records - Photos
e97f7af5-1318-5c81-93a2-6cce5c5baf2e | note | Onsite Responsibility - Site Engineer
| checkpoint | 4 - Concrete Infill
c83ed801-4fcb-5608-a4f0-ba0c73e8ab78 | note | VERIFICATION ACTIVITY - QA FORM
43f75fb0-9a72-53d1-bafe-7de3bf90c7a9 | note | METHODS OR REFERENCE - TDM Technical Standards - IS0001 & IS0002
e354e8c0-11b3-58fd-96a8-66da32c1f76b | note | FREQUENCY - Each Site
4442734f-9a30-591b-bda3-317d02657947 | note | ACCEPTANCE CRITERIA - 180mm depth of 20MPa broom finish unreinforced Concrete with 4kg/m3 black oxide Cross Fall of 2% or max rise in centre of 180mm
df61d890-2f3d-5c13-821d-43d77c948fe5 | note | Hold Point - In Process Inspection
9789fcd8-140c-50c9-b4ce-ef6eaf7e0eee | note | Records - FH concrete QA sheet. Concrete delivery Dockets kept as record
aff2f3c6-59f8-5b68-83af-950a1ab48c1f | note | Onsite Responsibility - Site Engineer
| section | Asbuilts
| checkpoint | 5 - As built information
99a6f738-ab02-5e58-ae8b-0f0d2245799a | note | VERIFICATION ACTIVITY - Drawings
9a3f6f03-183b-5d15-b777-047cac93bee1 | note | FREQUENCY - Every Site
f3ff6937-51ac-5a91-8867-c745b903bdf8 | note | ACCEPTANCE CRITERIA - As built drawings
a07961c4-9679-55e0-a098-9d182e37301d | note | Hold Point - In Process Inspection
96727ea3-028a-55a3-88dd-baa946fbd8f8 | note | Records - Asbuilt records
102c410c-a20b-52c0-8caf-2361f9081784 | note | Onsite Responsibility - Supervisor and Engineer
| checkpoint | 6 - RAMM DATA
6adaa422-0fc6-5c48-a24f-a245fee2fcae | note | VERIFICATION ACTIVITY - RAMM DATA SHEET
05069357-aa84-5f7a-accd-74102c0b3ac1 | note | FREQUENCY - Every Site
e3eb42c7-a885-5d9f-9c76-2edd5cdb49a3 | note | ACCEPTANCE CRITERIA - RAMM SHEET
eb26769c-bd32-5db0-82c9-423f27719af5 | note | Hold Point - In Process Inspection
fdf070a9-7a57-54b4-906a-725a84d4c257 | note | Records - Asbuilt records
6dd51130-6780-5762-8bac-1efbbe660b6e | note | Onsite Responsibility - Supervisor and Engineer
| checklist | White Swan Road - ITP - Enabling Works | itp | ITP - Enabling Works - Footpath, Kerb and channel | 9d455e5b-818c-43a7-b9d1-4d9974122c06
| section | Site Set Out
| checkpoint | 1 - Site Set out
0aae5897-5811-52d6-b99f-29734b66f84c | note | Verification Activity: Surveyor
b12d1d36-d2af-51f5-b067-2872c23b98e9 | note | Methods or Reference: Surveyor
a8792956-6eda-575c-924b-50bd998dd41d | note | Frequency: Everysite
136d5b3b-ccc8-59aa-ae53-f1f3c0a75ee1 | note | Acceptance Criteria: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
ed31d76a-26b3-5395-b763-2711fec7c61b | note | Hold Point: Mandatory HOLD POINT -
81f37a40-e143-508f-91ad-1b60c6ac8c93 | note | Records: Onsite records/photos
0b323bc5-be2f-5a99-8abd-2df986c8bfc7 | note | Onsite Responsibility: Site Engineer
| signoff | Hold Point
| section | Materials
| checkpoint | 2 - Kerb & Channel
71a1af8a-433d-50b1-9369-b155396a6752 | note | Verification Activity: QA FORM
22c42fd2-39f9-52fc-a74b-dcd54b8bc764 | note | Methods or Reference: TDM Technical Standards - KC0001
18cc8839-afc7-574d-b088-f36e8d9fcc6e | note | Frequency: Everysite
837713d8-7696-5f5d-85de-f8a29087ea85 | note | Acceptance Criteria: Kerb & Channel to be laid using precast hand-laid. On compacted GAP40. Concrete 20MPa @28 Days on 100mm GAP40 with the subgrade CBR>5
eb28a6bb-cc26-504b-8089-0cdf5023115f | note | Hold Point: Inprocess Inspection
03a34348-d5a2-584c-8f2f-3b07c2334b84 | note | Records: FH concrete QA sheet, photos. Concrete Plant Docket
bfe3f346-c471-528f-b61a-c77e9fc0709f | note | Onsite Responsibility: Site Engineer
| checkpoint | 3 - Channel Level
d69d4120-a636-5ce7-937d-a9cec0137707 | note | Verification Activity: QA FORM
416dae5e-1a90-5a87-98e5-a99651599f4c | note | Methods or Reference: TDM Technical Standards - KC0001
0b818f4f-6441-52c7-9880-9b4aa9e7138e | note | Frequency: Everysite
d8d3ab91-1960-595e-8f43-1294dcd08a96 | note | Acceptance Criteria: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
35454415-2d54-52bd-88e5-2f604921a923 | note | Hold Point: Inprocess Inspection
a2c47a03-6621-5943-855b-caf2a7b36088 | note | Records: FH concrete QA sheet
ea6af2fa-cc9d-52b3-87ed-801e92407c00 | note | Onsite Responsibility: Site Set Out
| section | Civil Works
| checkpoint | 4 - Concrete Footpaths
5e13389b-535b-54a6-8fb5-ca876101ea05 | note | Verification Activity: QA FORM
8326a15a-b381-5074-9596-79bead8726f8 | note | Methods or Reference: TDM Technical Standards - FP0001
de3281d3-e1f1-5c97-aa1e-6e0bd9db691a | note | Frequency: 10m Intervals
6b14b2dd-36f7-55f0-a9bf-32c92d54aa54 | note | Acceptance Criteria: Subgrade -(CBR > 3) Basecourse - 100mm min. thickness GAP40 Clegg CIV > 12 Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with EXPOSED finish
58ee572f-6506-50a7-a16e-c809dca08488 | note | Hold Point: Inprocess Inspection
c86fd46e-0a44-5b14-8744-c74190fe41a9 | note | Records: FH concrete QA sheet. Concrete delivery Dockets kept as record
2f1462db-54fc-5a18-9072-a18ae7923e52 | note | Onsite Responsibility: Site Engineer
| checkpoint | 5
a7471bbe-b80b-5090-b221-b0165c0714aa | note | Methods or Reference: TDM Technical Standards - FP0010
82925fcf-36f9-55db-8dcf-4f821988e4fa | note | Frequency: Each PX
d21e8dd2-0426-552b-9897-222ef0602303 | note | Acceptance Criteria: Warning TGSI tiles should have 100mm concrete slab underneath
5a6abe93-0a37-59ab-8594-c8fbd89a5416 | note | Hold Point: Inprocess Inspection, Measurement
f9a7d82c-08e5-5c98-b543-9b6193780a44 | note | Records: FH concrete QA sheet. Concrete delivery Dockets kept as record
facddef4-97af-5240-8e5f-bcba80e60b08 | note | Onsite Responsibility: Site Engineer
| checkpoint | 6 - Tactiles
f5c69796-e779-570c-b87c-74a774d831e7 | note | Verification Activity: Visual
04a06c68-b92e-5755-a1bd-5151c2989515 | note | Methods or Reference: NZTA RTS Guidelines for facilities for blind and vision impaired pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
72341d07-de64-57f7-807b-93469053c40a | note | Frequency: Everysite
55781b57-ac06-5835-9dcd-6d3ac36f75ec | note | Acceptance Criteria: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
dc435dc8-6bba-56a8-988b-65e58dc6bb4b | note | Hold Point: Inprocess Inspection
26ffd1d4-6661-5797-bc1f-bee77bdfc59c | note | Records: Photos
d0793ea9-20ad-5250-82b8-2dd2d6b00c42 | note | Onsite Responsibility: Site Engineer
| checkpoint | 6.1
e0c77b29-2196-5e69-9684-dbb5d4a8c3a0 | note | Methods or Reference: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
a0d0dc57-6713-58fa-9df2-40b17e62b6f9 | note | Frequency: Everysite
6cbeddef-fc0a-5f6b-9b4c-05c8bd19b812 | note | Acceptance Criteria: Edge of warning indicators to set back 300mm from the face of the kerb or lane, extend the full width of ramp and be 600mm deep.
759c0270-b7c6-5735-8b44-e3c983b9e401 | note | Hold Point: Inprocess Inspection
6e5b1467-d145-53f3-9646-29580ab85b25 | note | Records: Photos
537199b8-1283-545b-b6fc-8a346d15c9e2 | note | Onsite Responsibility: Site Engineer
| checkpoint | 6.2
589af09c-f603-5ad7-97d3-a63afd34b7c0 | note | Methods or Reference: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
492b8288-93a5-567d-a2d8-adeebd72e912 | note | Frequency: Everysite
a3861ca2-14ed-5887-8361-282a6e37e94c | note | Acceptance Criteria: TGSI tiles should be sealed yellow pigmented 300mm*300mm*60mm concrete tile warning type B in footpath and pedestrian crossing
bcb5da55-0a93-5aed-b7eb-476b6f2d2090 | note | Hold Point: Inprocess Inspection
3fc1faad-22c4-5567-82a5-dd4ac52206c8 | note | Records: Photos
6e748668-28f0-5f7b-bf8f-05345cc6fb5f | note | Onsite Responsibility: Site Engineer
| section | RAMM Data
| checkpoint | 7 - As built information
ef92e8be-8cfc-53df-8f78-100374d1694f | note | Verification Activity: RAMM DATA SHEET
60ee0ed4-9da3-5523-a3d1-5f57af753c9d | note | Frequency: Every Site
51d8cfb9-e487-5df7-93b5-2009283911ff | note | Acceptance Criteria: As built drawings and Ramm Sheets Completed
2a8de693-1eb4-5978-9532-f98dedc917dd | note | Hold Point: In Process Inspection
3ad10fd8-a7ea-52ba-9c9b-91bc99a946d5 | note | Records: Asbuilt records
c5819110-a2a4-5181-9bf0-b186bd615f90 | note | Onsite Responsibility: Supervisor and Engineer
| checkpoint-no-value | ITP Approval
025945a9-36ab-56ca-93b0-494536be30de | note | Prepared by: Cimyona Vinbi (21/02/22)
14c2f6f3-a240-55b1-9c53-2fee05c736ca | note | Approving Delegate: Daniel Tat (15/03/22)
| checklist | White Swan Road - ITP - Stormwater Drainage | itp | ITP - Stormwater Drainage | d563898b-cc0c-4315-b092-5351ed7ff32b
| checkpoint | 1 - Permits & Services
31475d75-f06a-5fbc-b369-bcafcd8ad77f | note | ACTION (Hold, Monitor, Witness): H
d5706de0-c40c-5724-83a7-63d777480637 | note | Detail: Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
9ac1b4a8-cf72-5798-a0de-b0f08d2de4d5 | note | Frequency: Prior to any construction commencing
828b603a-f7a4-5eec-99e2-6f10a3d1c440 | note | Inspection / Test Method: Document Review
3344f3dd-8b35-536d-95c2-e02ddc272e96 | note | Conformance Criteria: Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority
13b1f17f-8211-5dea-8171-e49d5faaed89 | note | Records: Permit attached or permit number noted.
d39ef3d6-50b9-5fcd-acff-9d9ddf770283 | textbox | FH Initials - Site Engineer:
| signoff | HOLD
| checkpoint | 1.1 - Permits & Services
c925a7b0-456e-5430-b812-92352e94875b | note | ACTION (Hold, Monitor, Witness): H
9aeb9fd4-0c2c-5365-93cd-0d820b7b4629 | note | Detail: Locate and mark out all existing services
75abd92f-5fae-56f3-88f0-345df82ba1b7 | note | Frequency: Prior to any construction commencing
9b733c25-da1f-575c-a3b3-4581f6fc143d | note | Conformance Criteria: B4u dig procedure - follow utility protocols
05f6d7b7-448c-5fbf-aaf7-6ead68059bb4 | note | Records: B4u dig plans & GPR report attached
8e824f3c-0ebf-55a9-bb90-286c1029f3fd | textbox | FH Initials - Site Engineer:
| signoff | HOLD
| checkpoint | 2 - Pre-Construction Sign Offs
74f42b61-2bd3-58a4-b7f3-afdeca997b96 | note | ACTION (Hold, Monitor, Witness): H
067ecccb-be46-5471-ae33-50902d8e7e05 | note | Detail: Sub-Contract and Supplier Agreements
25a1c5cb-3df4-5b1b-9f6f-d38490f96149 | note | Frequency: Prior to commencement.
aa4c9920-32d5-5c13-aca4-2e10070ebaef | note | Inspection / Test Method: Document Review
1f9aa577-996f-5ee4-9a1d-548df7d46332 | note | Conformance Criteria: Sub-Contract and Supplier Agreements to be agreed and signed
5cf47b41-47ab-5302-a8fc-0f192bf6dad8 | note | Records: Subcontract and Supplier Agreements
ebe035a4-9fbe-5014-944f-9f9feae28401 | textbox | FH Initials - Site Engineer:
| signoff | HOLD
| checkpoint | 3 - Design
2bcb0abf-8fa2-56f9-b4c6-2a3347c45046 | note | ACTION (Hold, Monitor, Witness): H
7fa06da5-d2c4-518f-94fa-d4641229db86 | note | Detail: Design is approved and Drawings are of the latest revision.
0d3dac44-637d-5141-98b3-06f59d36848c | note | Frequency: Prior to commencement.
aa4cef3a-ad8a-5550-9cd1-0b4cb3c2db3b | note | Inspection / Test Method: Document Review
2343def0-f067-5c5c-a3a6-8a4f5eea8726 | note | Conformance Criteria: Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
c3a2faa7-b4ca-5047-9da4-3f3a80cf1b37 | note | Records: Drawing Register.
c08ba414-52ab-5a98-a115-beb7a29e56ec | textbox | FH Initials - Site Engineer:
d1249327-e888-5850-9db9-48c8649a2c24 | textbox | FH Initials - Design Engineer's Rep:
| signoff | HOLD
| checkpoint | 4 - Survey Setout
60ff7e38-934d-5eb6-87a6-cfb26d6440eb | note | ACTION (Hold, Monitor, Witness): H
f927d707-6475-5939-bbc3-5bc478752855 | note | Detail: Setout Pipe Alignment and Service Locations with inlet & outlet points and inverts as required to construct to design
64b11fb1-44d9-5451-a57b-032adf3bf042 | note | Frequency: Prior to commencement.
0e19af56-10ac-5016-988d-1cd71866130d | note | Inspection / Test Method: Survey
1ae80683-4542-567c-b30f-8550647254cb | note | Conformance Criteria: As per Blue Barn Consulting Engineering Drawings: 02188-T-400 & Setout files
2b8063f9-ec97-598d-8fb1-cea10a020096 | note | Records: Survey Receipt.
5d399fcd-f879-5857-a997-3152ba189cc2 | textbox | FH Initials - Site Engineer:
| signoff | HOLD
| checkpoint | 5 - Pipe and Manhole Material Compliance
5195f64e-1034-52d7-ae42-9b8752150b2a | note | ACTION (Hold, Monitor, Witness): H
b55bd1c9-07a8-50a5-a066-6df6198ff554 | note | Detail: Cesspit, Manhole and Pipe shall comply with relevant AT/TDM standards
24933ea3-9df1-549d-989c-31135a63cf1e | note | Frequency: Prior to commencement.
17b615c3-ea64-5f12-8052-717bbe3c802a | note | Inspection / Test Method: Document Review, Visual Inspection
cfbc177a-21cb-5e56-9b9d-09f7f9ba8777 | note | Conformance Criteria: Pipe shall be Check for freshly formed pipes and return if required 1) DN225 Class 4 RCRRJ pipes AS/NZS 4058 2). All Concrete RCRRJ pipes to be fitted with Rubber rings 3). Pipes shall have product certification (ISO Type 5) to AS/NZS 4058 Prefabricated concrete Manhole shall be in accordance with TDM Standards & AC COP
481b1646-f7f5-5caa-862b-553fe9239164 | note | Records: Manufacturers Data Sheets, Delivery Dockets
64b5c1cc-9eb3-512f-9423-380a91b8de95 | textbox | FH Initials - Site Engineer:
| signoff | HOLD
| checkpoint | 6 - Locate Existing Services by Hand Digging / Hydro Vac
90e322c0-35c2-5266-87cf-8301cdcc8576 | note | ACTION (Hold, Monitor, Witness): H
3cfe7cc2-b9cc-5e07-bba6-bd5cb84db475 | note | Detail: Ensure all services conflicting with the line of trench have been exposed by hand digging.
eeb752b3-eca4-52fb-b052-26aab83165fa | note | Frequency: Prior to commencement.
0631ac1d-24a2-5ac8-888d-d595766e2ec7 | note | Inspection / Test Method: Potholing / Survey
351fa7d3-95a9-58ca-9e9e-12c072f9a186 | note | Conformance Criteria: All conflicts have been located. New services and / or conflicts to be advised to Project Manager.
d58c8838-842d-5910-a182-87eeb6936e3a | note | Records: As-built Drawings. Doc. Review
07d1a4cf-fe67-5528-925e-6794bcb40275 | textbox | FH Initials - Site Engineer:
| signoff | HOLD
| checkpoint | 7 - Trenching & Excavation
14eeb07c-5096-5f83-9d55-4355d44868ea | note | ACTION (Hold, Monitor, Witness): H
ee89d0d0-4a31-5577-a0e7-cd732f3611ab | note | Detail: Excavation methodology
c110c911-6a5f-5afa-81ca-064aae206534 | note | Frequency: Daily
882fcdc4-6106-5ea3-9e75-a5bea91e6f13 | note | Inspection / Test Method: Prestart review
4ede7f38-1b33-5939-9760-80cc4a0e2c67 | note | Conformance Criteria: The excavation, benching and shoring requirements shall be in accordance with Worksafe Excavation safety guidelines (2016)
5ce786de-1246-5c00-a3d6-30fef0fc7106 | note | Records: Prestart RCP
fdd71b9d-1014-5fbb-a1e3-b30c7f237bdd | textbox | FH Initials - Site Engineer:
| signoff | HOLD
| checkpoint | 7.1 - Trenching & Excavation
2bf08752-75fc-53f8-86c1-793027b4eda3 | note | ACTION (Hold, Monitor, Witness): M
7fc597df-9071-5caa-9507-390c712b44fb | note | Detail: Trench Profile - Width
deb288c5-328d-5967-9af3-3467d7c99a1a | note | Frequency: Daily / as trenching takes place. Different depth methodology
9dffdfd8-282b-59cf-b9cc-68986350fb1d | note | Inspection / Test Method: Visual Inspection, Excavation methodology
e05c3e89-0f27-52b7-968e-32ad2cac9328 | note | Conformance Criteria: Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing
b8696e72-27ad-500e-a091-ac3f6bb26d2e | note | Records: Construction Photos
866d15f0-ab38-5b6a-8ffd-f59af68acd9b | textbox | FH Initials - Site Engineer:
| checkpoint | 7.2 - Trenching & Excavation
2881868d-770e-52f8-a4c9-c8284603724d | note | ACTION (Hold, Monitor, Witness): W
82b76a0d-1aeb-5dc9-8236-035b8aaeddca | note | Detail: Trench Profile - Depth
3badf86e-3a49-59b7-b4e6-3f18540a9267 | note | Frequency: Daily / as trenching takes place.
481a363f-07dc-5bde-be42-90659028a0af | note | Inspection / Test Method: Visual Inspection, Measurement
2e730f69-5af1-5c23-887e-359cb219fe30 | note | Conformance Criteria: Trench depth varies according to longsection and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings
087b4da6-406d-5f6b-b008-ef71b6db8112 | note | Records: FH Drainage Line Record / Construction Photos
57f47e4e-d3c3-5118-a635-8fbf7cb2605c | textbox | FH Initials - Site Engineer:
| checkpoint | 8 - Bedding for Concrete Pipe Laying & Manhole & Cesspit
3e8fade3-3af5-5566-a6f7-3008d0457884 | note | ACTION (Hold, Monitor, Witness): W
866be954-f01f-5c55-90f5-42c584444bd5 | note | Detail: Placing and compaction of Bedding Material.
05cda5fb-002d-51a6-8d8c-a394184dfb2c | note | Frequency: Inspected continuously during placing and compaction of Bedding Material.
135b9055-6432-555a-871f-967e568da482 | note | Inspection / Test Method: Visual Inspection
0e985ce1-b439-5a1a-85f9-043bd23b394d | note | Conformance Criteria: Bedding & Pipe surround material to be GAP7 or GAP 20 (Stevenson Quarry) or alternate material that complies with AS/NZS 3725
9bfeedad-64ab-5fa9-8041-2439715fcdd9 | note | Records: FH Drainage Line Record / Construction Photos
0b473c68-3584-5850-8fbd-5a6eef0363ea | textbox | FH Initials - Site Engineer:
| checkpoint | 9 - Pipe Position Tolerance
d42d7cad-e39d-5c55-a2d1-518388b59aaf | note | ACTION (Hold, Monitor, Witness): M
59883d93-8b9a-58b6-b45e-64afb1aa16f6 | note | Frequency: At any point of pipe
022de414-f903-5404-96a9-f7871608f68e | note | Conformance Criteria: Position tolerance for pipe laying at any point along the length of the installation shall be within ±30 mm from the specified design.
51656817-e55b-5e68-b75b-4ffa2d7f8203 | note | Records: FH Drainage Line Record, Survey Data.
ac941886-6da3-5ea4-9286-4441452e1f9e | textbox | FH Initials - Site Engineer:
| checkpoint | 10 - Trench Backfill - Placing & Compacting
366354f2-d94e-592e-925b-77541e094c1b | note | ACTION (Hold, Monitor, Witness): M
db9580ed-89fa-530e-ac6b-e97c289f95d9 | note | Detail: Placing and compacting of Trench Backfill Material
fd900b3b-58c4-517b-8d6e-650139d7c14e | note | Frequency: Throughout Trench Backfilling operation.
73dd78b3-4fe6-5a8c-b9c5-eded80d9aaca | note | Inspection / Test Method: Visual Inspection
f873e0a1-03b0-5b0a-9acf-c9c4f0cbe092 | note | Conformance Criteria: Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm
c6bdf922-5a1c-582d-99a1-7bb0568c67bd | note | Records: Construction Photos
dc18ad46-4508-549d-94b3-d28d7785c6d6 | textbox | FH Initials - Site Engineer:
| checkpoint | 10 - Trench Backfill - Placing & Compacting
a99d6a43-49df-537c-a631-9aa1349d3ca3 | note | ACTION (Hold, Monitor, Witness): M
6731abcc-ff73-5f3f-a967-a51ddee1678d | note | Detail: Placing and compacting of Trench Backfill Material
9d6737d5-5ed6-50eb-a576-553dffed253a | note | Frequency: Throughout Trench Backfilling operation.
c5b3880d-72af-565b-98e3-c1f4e547993b | note | Inspection / Test Method: Visual Inspection
692f4bc7-1409-5846-a977-5097b1063be2 | note | Conformance Criteria: Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm
2352a394-9ebe-57d9-94e1-1a2fdb977aa8 | note | Records: Construction Photos
b9c26345-44d5-5d3b-9fb7-574eef88ae71 | textbox | FH Initials - Site Engineer:
eeaeb32a-5f04-5d70-837a-51b0c0352dd5 | textbox | FH Initials - Design Engineer's Rep:
| checkpoint | ITP Completion - QA checked By Quality Manager:
| signoff | Add Signature
| checkpoint | ITP Completion - Accepted By Design Engineer's Rep:
| signoff | Add Signature