## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Enabling Works - Footpath, Kerb and Channel, Pram Crossing | itp |  |  |  |  | Generic - ITP - Enabling Works - Footpath, Kerb and Channel, Pram Crossing
section | Site Set Out
checkpoint | 1 - Site Set out
label | VERIFICATION ACTIVITY: Surveyor
label | METHODS OR REFERENCE: Surveyor
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
label | HOLD POINT: Mandatory HOLD POINT -
label | RECORDS: Onsite records/photos
label | ONSITE RESPONSIBILITY: Site Engineer
holdpoint | AUTHORITY HOLDPOINT
section | Kerb and Channel
checkpoint | 2A - Kerb & Channel
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - KC0001
label | FREQUENCY: Every 10m for Scalar
label | ACCEPTANCE CRITERIA: Subgrade CBR > 5
label | HOLD POINT: In process Inspection
label | RECORDS: Scalar Sheet
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 2B - Kerb & Channel
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - KC0001
label | FREQUENCY: Every 10m for Clegg
label | ACCEPTANCE CRITERIA: Kerb & Channel to be laid using precast hand-laid on compacted GAP40.
label | ○ Thickness - 100mm on Footpath / 300mm on roads
label | ○ CVI > 12
label | HOLD POINT: In process Inspection
label | RECORDS: Clegg Sheet, Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 2C - Kerb Setout
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - KC0001
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Site Setout as per construction drawings and heights and falls verified
label | HOLD POINT: Mandatory HOLD POINT -
label | RECORDS: K&C Pre-pour Checklist
label | ONSITE RESPONSIBILITY: Site Engineer / MSQA
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2D - Channel Material
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - KC0001
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Concrete Strength 20MPa @28 Days
label | HOLD POINT: In process Inspection
label | RECORDS: Concrete Docket
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 2E - Channel Level
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - KC0001
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
label | HOLD POINT: In process Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
section | Footpath
checkpoint | 3A - Concrete Footpaths
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - FP0001
label | FREQUENCY: 10m intervals
label | ACCEPTANCE CRITERIA: Subgrade CBR > 3
label | HOLD POINT: In process Inspection
label | RECORDS: Scalar Sheet
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 3B - Concrete Footpaths
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - FP0001
label | FREQUENCY: 10m intervals
label | ACCEPTANCE CRITERIA: Basecourse - 100mm min. thickness
label | ○ Clegg CIV > 12
label | HOLD POINT: In process Inspection
label | RECORDS: Clegg Sheet, Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 3C - Footpath Setout
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - FP0001
label | FREQUENCY: 10m intervals
label | ACCEPTANCE CRITERIA: Site set out as per construction drawings and heights and falls verified
label | HOLD POINT: Mandatory HOLD POINT -
label | RECORDS: Pre-pour Concrete Sheet, Photos
label | ONSITE RESPONSIBILITY: Site Engineer / MSQA
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3D - Footpath finishing
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - FP0001
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Concrete Strength 20 MPa @ 28 days.
label | ○ 4kg/m3 black oxide with broom finish or black oxide exposed (shall match to existing)
label | ○ Standard Footpath - 100mm thick
label | ○ Heavy Duty - 150mm thick
label | HOLD POINT: In process Inspection
label | RECORDS: Concrete Docket, Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 4 - Grass Berms
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: ATCOP Section 12 Footpaths and Pedestrian Facilities
label | FREQUENCY: 10m Intervals
label | ACCEPTANCE CRITERIA: 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
label | HOLD POINT: In process Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 5 - Service Covers and Street Furniture
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: AT Contract Specification 14000
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Service covers to be adjusted to new surface levels. Ensure no damage is done to street furniture in the vicinity while carrying out works.
label | HOLD POINT: In process Inspection
label | RECORDS: Nil
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 6A - Tactiles /Pram crossing
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: TDM Technical Standards - FP006
label | ○ TDM Technical Standards - FP0010
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Tactiles set out must be agreed with MSQA
label | ○ Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
label | ○ Warning TGSI tiles should have 100mm concrete slab underneath
label | HOLD POINT: Mandatory HOLD POINT -
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer / MSQA
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6B - Tactile Material
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: NZTA RTS Guidelines for facilities for blind and vision impaired pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type - 300x300mmx60mm
label | HOLD POINT: In process Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 6C - Tactile
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Edge of warning indicators to set back 300mm from the face of the kerb or lane, extend the full width of ramp and be 600mm deep.
label | HOLD POINT: In process Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
section | As-builts
checkpoint | 7 - As built information
label | VERIFICATION ACTIVITY: Drawings
label | METHODS OR REFERENCE: As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP.
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: As-Built drawings
label | HOLD POINT: In Process Inspection
label | RECORDS: As-built records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
checkpoint | 8 - RAMM DATA
label | VERIFICATION ACTIVITY: RAMM DATA SHEET
label | METHODS OR REFERENCE: As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP.
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: RAMM SHEET
label | HOLD POINT: In Process Inspection
label | RECORDS: As-built records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
section | ITP APPROVAL
checkpoint | ITP Approval
note | Prepared by: Daniel Tat
note | Approving Delegate: Daeyoung Jeong
checklist | ITP - Traffic Islands | itp |  |  |  |  | Generic - ITP - Traffic Islands
section | Materials
checkpoint | 1 - Kerb
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Kerb to be laid using precast hand-laid
label | HOLD POINT: In process Inspection
label | RECORDS: FH Concrete QA sheet, Photos
label | ONSITE RESPONSIBILITY: Site Engineer
section | Construction
checkpoint | 2 - Survey Setout
label | VERIFICATION ACTIVITY: Survey
label | METHODS OR REFERENCE: Setout Kerb Alignment required to construct to design
label | FREQUENCY: Prior to commencement.
label | ACCEPTANCE CRITERIA: Survey
label | HOLD POINT: In process Inspection
label | RECORDS: Survey Receipt.
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 3A - In-Situ Concrete Island
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - IS0001
label | FREQUENCY: Each Site
label | ACCEPTANCE CRITERIA: Kerb to be laid using precast hand-laid on compacted basecourse. Gaps between kerbs shall be no larger that 10mm
label | ○ CVI > 12
label | HOLD POINT: In process Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 3B - Stick On Concrete Island
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - IS0002
label | FREQUENCY: Each Site
label | ACCEPTANCE CRITERIA: Bonding Agent to be applied on existing surface
label | ○ Mountable Kerbs laid flat to be sticked on to the existing road using Epoxy Mortar Mix.
label | ○ Gaps between kerbs shall be no larger that 10mm
label | HOLD POINT: In process Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 4 - Concrete Infill
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
label | FREQUENCY: Each Site
label | ACCEPTANCE CRITERIA: 150/180mm depth of 20MPa Concrete
label | ○ Surface finish to confirm with Engineer's Rep
label | ○ Cross Fall of 2% or max rise in centre of 180mm
label | HOLD POINT: In process Inspection
label | RECORDS: FH Concrete QA sheet. Concrete Delivery Dockets.
label | ONSITE RESPONSIBILITY: Site Engineer
section | As-builts
checkpoint | 7 - As built information
label | VERIFICATION ACTIVITY: Drawings
label | METHODS OR REFERENCE: As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP.
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: As built drawings
label | HOLD POINT: In Process Inspection
label | RECORDS: As-built records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
checkpoint | 7 - RAMM DATA
label | VERIFICATION ACTIVITY: RAMM DATA SHEET
label | METHODS OR REFERENCE: As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP.
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: RAMM SHEET
label | HOLD POINT: In Process Inspection
label | RECORDS: As-built records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
section | ITP APPROVAL
checkpoint | ITP Approval
textbox | Prepared by:
textbox | Approving Delegate:
checklist | ITP - Enabling Works - Vehicle Crossing | itp |  |  |  |  | Generic - ITP - Enabling Works - Vehicle Crossing
section | Site Set Out
checkpoint | 1 - Site Set out
label | VERIFICATION ACTIVITY: Surveyor
label | METHODS OR REFERENCE: Surveyor
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Site set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
label | HOLD POINT: Mandatory HOLD POINT -
label | RECORDS: Onsite records/photos
label | ONSITE RESPONSIBILITY: Site Engineer
holdpoint | AUTHORITY HOLDPOINT
section | Standard VX
checkpoint | 2A - Residential VX
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - VX101 - 104
label | FREQUENCY: Each VX
label | ACCEPTANCE CRITERIA: Subgrade CBR > 3
label | HOLD POINT: In process Inspection
label | RECORDS: Scalar Sheet
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 2B - Residential VX
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - VX101 - 104
label | FREQUENCY: 4 Cleggs per VX
label | ACCEPTANCE CRITERIA: VX to be laid using on compacted 100mm min GAP40.
label | ○ CVI > 12
label | HOLD POINT: In process Inspection
label | RECORDS: Clegg Sheet, Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 2C - Residential VX
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - VX101 - 104
label | FREQUENCY: Every VX
label | ACCEPTANCE CRITERIA: Site set out as per construction drawings and heights and falls verified
label | HOLD POINT: Mandatory HOLD POINT -
label | RECORDS: Concrete Pre-pour Checklist
label | ONSITE RESPONSIBILITY: Site Engineer / MSQA
holdpoint | AUTHORITY HOLDPOINT
checkpoint | VX Material
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - VX101 - 104
label | FREQUENCY: Every VX
label | ACCEPTANCE CRITERIA: 665 Mesh Required if 4 or more dwellings
label | HOLD POINT: In process Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 2D - VX Material
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - VX101 - 104
label | FREQUENCY: Every VX
label | ACCEPTANCE CRITERIA: Concrete Strength 20MPa @28 Days
label | ○ Thickness - 150mm
label | ○ 4kg/m3 black oxide with broom finish or black oxide exposed (shall match to existing)
label | HOLD POINT: In process Inspection
label | RECORDS: Concrete Docket
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 2E - Residential VX
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - VX101 - 104
label | FREQUENCY: Every VX
label | ACCEPTANCE CRITERIA: Saw cut expansion joints at 4m centres maximum each way in addition to saw cuts shown on dwg
label | HOLD POINT: In process Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 2D - Residential VX
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - VX101 - 104
label | FREQUENCY: Every VX
label | ACCEPTANCE CRITERIA: Saw cut expansion joints at 4m centres maximum each way in addition to saw cuts shown on dwg
label | ○ 1m reinstatement on carriageway
label | HOLD POINT: In process Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 3 - Grass Berms
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: ATCOP Section 12 Footpaths and Pedestrian Facilities
label | FREQUENCY: 10m Intervals
label | ACCEPTANCE CRITERIA: 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
label | HOLD POINT: In process Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
section | As-builts
checkpoint | 4 - As built information
label | VERIFICATION ACTIVITY: Drawings
label | METHODS OR REFERENCE: As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: As-Built drawings
label | HOLD POINT: In Process Inspection
label | RECORDS: As-built records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
checkpoint | 5 - RAMM DATA
label | VERIFICATION ACTIVITY: RAMM DATA SHEET
label | METHODS OR REFERENCE: As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: RAMM SHEET
label | HOLD POINT: In Process Inspection
label | RECORDS: As-built records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
section | ITP APPROVAL
checkpoint | ITP Approval
note | Prepared by: Daniel Tat
note | Approving Delegate: Daeyoung Jeong
checklist | ITP - Stormwater Drainage | itp |  |  |  |  | Generic - ITP - Stormwater Drainage
section | Stormwater Drainage
checkpoint | 1 - Permits & Services (1)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
label | FREQUENCY: Prior to any construction commencing
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA: Relevant Fulton Hogan Permits to Work.
label | ○ AT Access Authority approved and signed by RCA Authority.
label | RECORDS: Permit attached or permit number noted.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1 - Permits & Services (2)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Locate and mark out all existing services
label | FREQUENCY: Prior to any construction commencing
label | CONFORMANCE CRITERIA: B4u dig procedure - follow utility protocols and GPR Report
label | RECORDS: B4u dig plans & GPR report attached
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Pre-Construction Sign Offs
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Sub-Contract and Supplier Agreements
label | FREQUENCY: Prior to commencement.
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA: Sub-Contract and Supplier Agreements to be agreed and signed
label | RECORDS: Subcontract and Supplier Agreements
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Design
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Design is approved and Drawings are of the latest revision.
label | FREQUENCY: Prior to commencement.
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA: Ensure that Design is approved and Drawings are of the latest revision.
label | ○ Drawings to be 'ISSUED FOR CONSTRUCTION' status.
label | ○ HOLD POINT of not issued to IFC.
label | RECORDS: Drawing Register.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Survey Setout
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Setout Pipe Alignment and Service Locations with inlet & outlet points and inverts as required to construct to design
label | FREQUENCY: Prior to commencement.
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Survey
label | CONFORMANCE CRITERIA: As per IFC Drawings and design AutoCAD file.
label | RECORDS: Survey Receipt.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Pipe and Manhole Material Compliance
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Cesspit, Manhole and Pipe shall comply with relevant AT/TDM/AC Standards
label | FREQUENCY: Prior to commencement.
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review, Visual Inspection
label | CONFORMANCE CRITERIA: Pipe shall be check for freshly formed pipes and return if required
label | 1) Class 4 RCRRJ pipes AS/NZS 4058
label | 2) All Concrete RCRRJ pipes to be fitted with Rubber rings
label | 3) Pipes shall have product certification (ISO Type 5) to AS/NZS 4058
label | ○ Prefabricated concrete Manhole shall be in accordance with TDM Standards
label | RECORDS: Manufacturers Data Sheets, Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Locate Existing Services by Hand Digging / Hydro Vac
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure all services conflicting with the line of trench have been exposed by hand digging.
label | FREQUENCY: Prior to commencement.
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Potholing / Survey
label | CONFORMANCE CRITERIA: All conflicts have been located. New services and / or conflicts to be advised to Project Manager. As-built all services.
label | RECORDS: As-built Drawings. Doc. Review
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Trenching & Excavation (1)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Excavation methodology
label | FREQUENCY: Daily
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Prestart review
label | CONFORMANCE CRITERIA: The excavation, benching and shoring requirements shall be in accordance with WorkSafe Excavation safety guidelines (2016)
label | RECORDS: Prestart RCP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Trenching & Excavation (2)
label | ACTION (Hold, Monitor, Witness): M
label | DETAIL: Trench Profile - Width
label | FREQUENCY: Daily / as trenching takes place. Different depth methodology
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection, Excavation methodology
label | CONFORMANCE CRITERIA: Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing
label | RECORDS: Construction Photos
checkpoint | 7 - Trenching & Excavation (3)
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Trench Profile - Depth
label | FREQUENCY: Daily / as trenching takes place.
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection, Measurement
label | CONFORMANCE CRITERIA: Trench depth varies according to long section and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings
label | RECORDS: FH Drainage Line Record / Construction Photos
checkpoint | 7 - Trenching & Excavation (4)
label | ACTION (Hold, Monitor, Witness): M
label | DETAIL: Trench Base
label | FREQUENCY: Every 10m
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Scalar testing
label | CONFORMANCE CRITERIA: Trench base capacity to be tested using scala testing. Not less than 3 blows per 150mm for CBR 3.5 and 200mm for CBR 2.
label | RECORDS: Test reports / Construction Photos
checkpoint | 8 - Bedding for Concrete Pipe Laying & Manhole & Cesspit
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Placing and compaction of Bedding Material.
label | FREQUENCY: Inspected continuously during placing and compaction of Bedding Material.
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
label | CONFORMANCE CRITERIA: Bedding & Pipe surround material to be GAP7 or GAP 20 or alternate material that complies with AS/NZS 3725
label | RECORDS: FH Drainage Line Record / Construction Photos
checkpoint | 9 - Pipe Position Tolerance
label | ACTION (Hold, Monitor, Witness): M
label | DETAIL:
label | FREQUENCY: At any point of pipe
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review):
label | CONFORMANCE CRITERIA: Position tolerance for pipe laying at any point along the length of the installation shall be within ±10 mm from the specified design.
label | RECORDS: FH Drainage Line Record, Survey Data.
checkpoint | 10 - Trench Backfill - Placing & Compacting
label | ACTION (Hold, Monitor, Witness): M
label | DETAIL: Placing and compacting of Trench Backfill Material
label | FREQUENCY: Throughout Trench Backfilling operation.
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
label | CONFORMANCE CRITERIA: Backfill shall be placed in layers less than 200 mm thick.
label | ○ Compacted backfill material to be free of Lumps > 150mm
label | ○ ATAP40 for subbase/basecourse.
label | RECORDS: Construction Photos
section | Subsoil Construction
checkpoint | 13 - Subsoil Material Compliance (1)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure Subsoil Drainage pipe complies with TDM RD010
label | FREQUENCY: Upon delivery to site
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Ensure delivery docket matches materials delivered
label | CONFORMANCE CRITERIA: 110mm diameter Drain flow TNZ F/2 Grade pipe - filter sock
label | RECORDS: Delivery docket
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13 - Subsoil Material Compliance (2)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure Material for Bedding, Side support and backfill F2 filter sand drainage aggregate
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Ensure clean drainage aggregate - F2 Sand
label | RECORDS: Delivery docket
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14 - Trenching (1)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Inspect trench profile and ensure it is 0.300m wide and 375mm below subgrade
label | FREQUENCY: 10m intervals
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection and measurement
label | CONFORMANCE CRITERIA: Record levels of base of trench on dip sheet.
label | RECORDS: Photo / subsoil log
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14 - Trenching (2)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure the trench is cut in a manner than will ensure that the pipes will be laid true to the depths, grades and lines shown on the drawings.
label | FREQUENCY: 10m intervals
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection and measurement
label | CONFORMANCE CRITERIA: Ensure trench line and levels match the design drawings
label | RECORDS: Photo / subsoil log
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 15 - Bedding, pipe installation and Backfill (1)
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Ensure 50/100mm (KC or Road) thick F2 Drainage aggregate bedding is placed in base of trench.
label | FREQUENCY: 10m intervals
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Record levels of top of bedding on dip sheet
label | RECORDS: Photo / subsoil log
checkpoint | 15 - Bedding, pipe installation and Backfil (2)
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Ensure Subsoil Pipe is laid on the Bedding in the centre of the trench
label | FREQUENCY: 10m intervals
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Consistency with Subsoil Details
label | RECORDS: Photos
checkpoint | 15 - Bedding, pipe installation and Backfill (3)
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Backfill by tipping AP20 as bedding & ATAP40 as pavement structure into the trench
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Ensure good coverage
label | RECORDS: Photos
checkpoint | 16 - Catchpit Connection (1)
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Ensure minimum entry point 150mm above soffit of outlet stormwater pipe
label | FREQUENCY: As required
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Consistency with Subsoil Details
label | RECORDS: Photo
checkpoint | 16 - Catchpit Connection (2)
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Perforate Catchpit and epoxy grout pipe from inside to completely seal connection.
label | FREQUENCY: As required
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Consistency with Subsoil Details
label | RECORDS: Photos
checkpoint | 17 - As-Built Drawings
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Red pen marked-up As-Builts of every 'Issued for Construction'
label | FREQUENCY: Final As-Built Drawings to be completed within three months of the construction completion of the asset or infrastructure.
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Drawings / Visual Inspection
label | CONFORMANCE CRITERIA: As Built and GIS Data
label | RECORDS: Redline As-Built Drawings, scanned as .pdf files.
section | ITP APPROVAL
checkpoint | ITP Approval
textbox | QA checked By Quality Manager:
textbox | Accepted By Engineers Rep:
checklist | ITP - Traffic Signal Ducting and Pole Erection | itp |  |  |  |  | Generic - ITP - Traffic Signal Ducting and Pole Erection
section | Ducting
checkpoint | 1 - Permits
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Obtain Permits
label | FREQUENCY: As required
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA: Authorisation to work, dig permit and first gas permit obtained
label | RECORDS: This ITP signed
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Design
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure that Design is approved and Drawings are of the latest revision
label | FREQUENCY: Prior to commencement
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA:
label | RECORDS: Check Drawing Register
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Survey Setout (1)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Setout ducting alignment and EOS FL depths. Setout and mark all known services along the cable corridor.
label | FREQUENCY: Prior to commencement
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Survey
label | CONFORMANCE CRITERIA: Consistency with Drawings and Specifications
label | RECORDS: Survey Records
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Survey Setout (2)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Confirm with Engineer on site the exact location of all posts, foundations, signs, cable chambers, cable ducts, loops and loop termination boxes( Toby boxes) before installation.
label | FREQUENCY: Prior to commencement
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
label | CONFORMANCE CRITERIA: Consistency with Drawings and Specifications
label | RECORDS: Photos / Engineers approval documentation
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Locate existing services by hand digging/ hydrovac
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Ensure all services conflicting with the line of trench has been exposed by hand digging or hydro excavation
label | FREQUENCY: Prior to Installation
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Potholing
label | CONFORMANCE CRITERIA: All conflicts have been located and survey as built recorded
label | RECORDS: Digging/Excavating Control Checklist
checkpoint | 5 - Material Compliance (1)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure duct pipes and poles are as per drawings and specification
label | FREQUENCY: Upon delivery to site
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Ensure delivery docket matches materials
label | CONFORMANCE CRITERIA:
label | RECORDS: Delivery Docket
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Material Compliance (2)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure all concrete used is 20MPa mix
label | FREQUENCY: Upon delivery to site
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Ensure delivery docket matches materials
label | CONFORMANCE CRITERIA:
label | RECORDS: Delivery Docket
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Trenching
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Inspect trench profile to ensure walls vertical, widths is 300mm max (single ducts). Ensure trench depth is sufficient to provide 600mm cover to duct when under berm (900mm cover when under road crossing)
label | FREQUENCY: 10m Intervals
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
label | CONFORMANCE CRITERIA: Consistency with Drawings and Specifications
label | RECORDS: Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.1 - Trenching
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure trench is cut in a manner that will ensure ducts are laid at correct depths, grades and alignment as per design dwgs
label | FREQUENCY: 10m Intervals
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measure
label | CONFORMANCE CRITERIA: Ensure trench alignment and levels match the design drawings
label | RECORDS: Dip sheet & Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Duct Installation
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Place proposed ducts in locations where required. Draw wire tapes required and cap ducts where required to prevent ingress of material into duct.
label | FREQUENCY: Prior to Installation
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Consistency with Drawings and Specifications
label | RECORDS: Photos
checkpoint | 7.1 - Duct Installation
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure minimum spacing of ducts requirements are met as per design dwgs and Atop min spacing tables
label | FREQUENCY: 10m Intervals
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Consistency with Drawings and Specifications
label | RECORDS: Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.2 - Duct Installation
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: As-built Survey
label | FREQUENCY: 20m Intervals
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Consistency with Drawings and Specifications
label | RECORDS: Survey Records
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Bedding
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Lay min. 150mm GAP<12 for bedding and haunching
label | FREQUENCY: 10m Intervals
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Consistency with Drawings and Specifications
label | RECORDS: Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Warning Tape
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure warning tape gets installed 300mm above duct pipe for all new ducting lines.
label | FREQUENCY: 10m Intervals
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Consistency with Drawings and Specifications
label | RECORDS: Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Traffic signal pole erection
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure Design engineer as inspected pole locations prior to proceeding
label | FREQUENCY: Per pole
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
label | CONFORMANCE CRITERIA: Sign off by design engineer
label | RECORDS: Engineer sign off
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10.1 - Traffic signal pole erection
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure Pot hole is as per design with required depths and widths
label | FREQUENCY: Per pole
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measure
label | CONFORMANCE CRITERIA: Consistency with Drawings and Specifications
label | RECORDS: Dip sheet & Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10.2 - Traffic signal pole erection
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure Poles are plumb and within design tolerances
label | FREQUENCY: Per pole
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
label | CONFORMANCE CRITERIA: Consistency with Drawings and Specifications
label | RECORDS: Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 - As-builts
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Red pen mark up drawings to be included in QA file
label | FREQUENCY: At the completion of the Lot of work
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Drawings
label | CONFORMANCE CRITERIA:
label | RECORDS: As-built Drawing
holdpoint | AUTHORITY HOLDPOINT
section | ITP APPROVAL
checkpoint | ITP Approval
textbox | Drawings used for Construction incl. Rev numbers:
textbox | Reference Documentation (Notices/OFIs etc):
textbox | QA Compiled By:
textbox | QA checked By Project manager:
textbox | QA checked By Contract Manager:
textbox | Accepted By Design/AT Engineer: