## Sheet2
CONTRACT: Metro Sports, Christchurch | [7 empty] | ITP NO. CPB-NZ1006-ITP-4002 |  | REV.1
PLAN FOR: FITOUT | [7 empty] | SHEET 1 | OF 1
Contract Master Prog. No. | Activity Numbers | Activities: | Internal Glazing Installation (APL) |  |  |  |  | CLIENT: CPB Contractors
INSPECTION STAGE Identify the stages and list the approvals, inspections and tests to be carried out. |  | Specification Reference |  | Inspection |  |  | Verifying Record
|  |  |  | By | Frequency | Hold Point Y / N | Document Name | Records Kept By | Comments
DOCUMENTATION RECEIVED: a) Received QA documents. b) Check for Damage, Quantity, Quality of goods. c) Received all relevant setout/survey drawings. |  | HBP details and requirements, Project Specification |  | Alu-fix (Installer) | Each Delivery | N | Alu-fix Checklist | Alu-fix/HBP
INITIAL INSPECTION: a) Gridlines and RL’s are visible and accessible. b) Installation area free from obstruction and has suitable access. |  | n/a |  | Alu-fix (Installer) | Each Delivery | N | Alu-fix Checklist | Alu-fix/HBP
SEISMIC SILL, HEAD, JAMBS and BRACKETS: a) Opening Structure correct at sill, head and jambs. b) Waterproofing / wrapping complete around entire opening. c) Sill head, jamb & splice fixings are fitted correctly as per specifications and to correct RL. d) Seismic frame inspected and defect free. e) Seismic sill, head & jambs levelled to correct height. f) All fixings, corner angles and splice plates are sealed and neatly tooled. |  | a~f) Manufacturers details & Requirements. HBP Shop Drawings Project Specification |  | Alu-fix (Installer) CPB Client | Each Area Random Witness Point | N N N | Visual Hagley Glazing QA Checklist This to be held as a 'live record'. And be updated daily as the work progresses completed form above plus WITPOINT to client | Alu-fix/HBP Aconex / Omtrak | Checklists to be countersigned by CPB on completion
INSPECTION STAGE Identify the stages and list the approvals, inspections and tests to be carried out. |  | Specification Reference |  | Inspection |  |  | Verifying Record
|  |  |  | By | Frequency | Hold Point Y / N | Document Name | Records Kept By | Comments
PRE-INSTALLATION: a) Check panel identification with set out plans. b) Verify that the panel to be installed will be in the correct location. c) Visual inspection for any glass or sealant defects. d) Inspected for any other damage, eg dents or scratches. e) Check that the gaskets are in place without damage or voids and that the gaskets are crimped in place at both ends. f) Check that the sub-sills are clean and free from debris. |  | a~f) Manufacturers details & Requirements. HBP Shop drawings Project Specification |  | Alu-fix (Installer) CPB Client | Each Area Random Witness Point | N N N | Visual Alu-fix Checklist This to be held as a 'live record'. And be updated daily as the work progresses completed form above plus WITPOINT to client | Alu-fix/HBP Aconex / Omtrak | Checklists to be countersigned by CPB on completion
FLUSH GLAZE & HINGED DOOR INSTALLATION (where applicable): a) Check each panel is in the correct position. b) Check each panel is plumb, levelled, and true. c) Check that the gap between the mullions is as per design. d) Check beads are fitted and rubbered off e) Horizontal and vertical air seals applied and neatly tooled. f) Horizontal and vertical seals applied and neatly tooled. g) Rain shield flashings are installed correctly. h) Head flashing installed correctly. i) Door fitted to specifications. j) All hinges and screws are fitted. k) All gaps are correct around door. l) Door opens and closes freely. m) Lock/Handle are operating correctly. n) Closer is fitted and adjusted correctly. o) Threshold fitted correctly. |  | a~o)Manufacturers details & Requirements. HBP Issue drawings Door Hardware Schedule Project Specification |  | Alu-fix (Installer) CPB Client | Each Area Random Witness Point | N N N | Visual Hagley Glazing QA Checklist This to be held as a 'live record'. And be updated daily as the work progresses completed form above plus WITPOINT to client | Alu-fix/HBP Aconex / Omtrak | Checklists to be countersigned by CPB on completion
INSPECTION STAGE Identify the stages and list the approvals, inspections and tests to be carried out. |  | Specification Reference |  | Inspection |  |  | Verifying Record
|  |  |  | By | Frequency | Hold Point Y / N | Document Name | Records Kept By | Comments
GLASS INSTALLATION (where applicable): a) Glass Identified as correct type for location as per shop drawings b) Backing Rubbers continuous, sealed in corners and free of damage c) Glazing Blocks setout and type are correct. d) Glass placed in opening damage free. e) Safety stamp visible. (industry standard is bottom right from outside) f) Beads securely fitted and damage free. g) Correct glazing wedge used and rubber off ensuring there is no gaps and corners are sealed. h) Glass trade clean, free of defects and protection tape fitted where required. |  | a~h) Manufacturers details & Requirements. HBP Isings Project Specification c~g) NZS4223.3:2016 |  | GLass Guru (Installer) CPB Client | Each Area Random Witness Point | N N N | Visual Hagley Glazing QA Checklist This to be held as a 'live record'. And be updated daily as the work progresses completed form above plus WITPOINT to client | Glass Guru/HBP Aconex / Omtrak | Checklists to be countersigned by CPB on completion
PROTECTION: a) Protective delivery film removed to external faces only. b) Protective tape applied to all internal faces. |  | HBP requirements |  | Alu-fix (Installer) | As Above | N | As Above | Alu-fix/HBP
CLEAN & CLEAR AWAY: a) Clear Workplace etc. b) Remove Debris & Waste Materials to skip. c) Make Good any damaged areas. |  | c) Repair Method procedure by HBP |  | Alu-fix (Installer) | a), b) Daily | N | Visual c) HBP repair record for each repair | HBP | All windows to be checked prior to handover
INSPECTION & ACCEPTANCE: |  |  |  | HBP & CPB Client | Each Area | Y | Completed Form above plus CPB HOLDPOINT to Client | HBP & CPB Aconex / Omtrak | Checklists to be countersigned by CPB on completion
HBP Agreement: Date: |  |  |  | CPB Agreement: Date: |  |  |  | Client Agreement: Date: