## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP-3004 - Curtain Wall Installation | [5 empty] | CPB-NZ1006-ITP-3004 - Curtain Wall Installation - Rev 2
section | DOCUMENTATION RECEIVED:
checkpoint | a) Received QA documents.
label | Specification Reference: HBP details and requirements, Project Specification
label | Inspection - By: Alu-fix (Installer)
label | Inspection - Frequency: Each Delivery
label | Inspection - Hold Point (Y/N): N
label | Verifying Record - Document Name: Alu-fix Checklist
label | Verifying Record - Records Kept By: Alu-fix/HBP
checkpoint | b) Check for Damage, Quantity, Quality of goods.
label | Specification Reference: HBP details and requirements, Project Specification
label | Inspection - By: Alu-fix (Installer)
label | Inspection - Frequency: Each Delivery
label | Inspection - Hold Point (Y/N): N
label | Verifying Record - Document Name: Alu-fix Checklist
label | Verifying Record - Records Kept By: Alu-fix/HBP
checkpoint | c) Received all relevant setout/survey drawings.
label | Specification Reference: HBP details and requirements, Project Specification
label | Inspection - By: Alu-fix (Installer)
label | Inspection - Frequency: Each Delivery
label | Inspection - Hold Point (Y/N): N
label | Verifying Record - Document Name: Alu-fix Checklist
label | Verifying Record - Records Kept By: Alu-fix/HBP
section | INITIAL INSPECTION:
checkpoint | a) Gridlines and RL’s are visible and accessible.
label | Specification Reference: n/a
label | Inspection - By: Alu-fix (Installer)
label | Inspection - Frequency: Each Delivery
label | Inspection - Hold Point (Y/N): N
label | Verifying Record - Document Name: Alu-fix Checklist
label | Verifying Record - Records Kept By: Alu-fix/HBP
checkpoint | b) Installation area free from obstruction and has suitable access.
label | Specification Reference: n/a
label | Inspection - By: Alu-fix (Installer)
label | Inspection - Frequency: Each Delivery
label | Inspection - Hold Point (Y/N): N
label | Verifying Record - Document Name: Alu-fix Checklist
label | Verifying Record - Records Kept By: Alu-fix/HBP
section | SEISMIC SILL, HEAD, JAMBS and BRACKETS:
checkpoint | a) Opening Structure correct at sill, head and jambs.
label | Specification Reference:
label | ○ Manufacturers details & Requirements.
label | ○ HBP Shop Drawings
label | ○ Project Specification
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Alu-fix Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses
label | Verifying Record - Records Kept By: Alu-fix/HBP
checkpoint | b) Waterproofing / wrapping complete around entire opening.
label | Specification Reference:
label | ○ Manufacturers details & Requirements.
label | ○ HBP Shop Drawings
label | ○ Project Specification
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Alu-fix Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses
label | Verifying Record - Records Kept By: Alu-fix/HBP
checkpoint | c) Sill head, jamb & splice fixings are fitted correctly as per specifications and to correct RL.
label | Specification Reference:
label | ○ Manufacturers details & Requirements.
label | ○ HBP Shop Drawings
label | ○ Project Specification
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Alu-fix Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses
label | Verifying Record - Records Kept By: Alu-fix/HBP
checkpoint | d) Seismic frame inspected and defect free.
label | Specification Reference:
label | ○ Manufacturers details & Requirements.
label | ○ HBP Shop Drawings
label | ○ Project Specification
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Alu-fix Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses
label | Verifying Record - Records Kept By: Alu-fix/HBP
checkpoint | e) Seismic sill, head & jambs levelled to correct height.
label | Specification Reference:
label | ○ Manufacturers details & Requirements.
label | ○ HBP Shop Drawings
label | ○ Project Specification
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Alu-fix Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses
label | Verifying Record - Records Kept By: Alu-fix/HBP
checkpoint | f) All fixings, corner angles and splice plates are sealed and neatly tooled.
label | Specification Reference:
label | ○ Manufacturers details & Requirements.
label | ○ HBP Shop Drawings
label | ○ Project Specification
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Alu-fix Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses
label | Verifying Record - Records Kept By: Alu-fix/HBP
checkpoint | g) Check primary brackets are seated correctly and are in the correct position. All nuts and washers are correct as per design.
label | Specification Reference:
label | ○ Manufacturers details & Requirements.
label | ○ HBP Shop Drawings
label | ○ Project Specification
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Alu-fix Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses
label | Verifying Record - Records Kept By: Alu-fix/HBP
checkpoint | h) Check primary brackets are torqued to correct setting 30Nm.
label | Specification Reference:
label | ○ Manufacturers details & Requirements.
label | ○ HBP Shop Drawings
label | ○ Project Specification
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Alu-fix Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses
label | Verifying Record - Records Kept By: Alu-fix/HBP
section | PRE-INSTALLATION:
checkpoint | a) Check panel identification with set out plans.
label | Specification Reference:
label | ○ Manufacturers details & Requirements.
label | ○ HBP Shop drawings
label | ○ Project Specification
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness Point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Alu-fix Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses
label | Verifying Record - Records Kept By: Alu-fix/HBP
checkpoint | b) Verify that the panel to be installed will be in the correct location.
label | Specification Reference:
label | ○ Manufacturers details & Requirements.
label | ○ HBP Shop drawings
label | ○ Project Specification
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness Point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Alu-fix Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses
label | Verifying Record - Records Kept By: Alu-fix/HBP
checkpoint | c) Visual inspection for any glass or sealant defects.
label | Specification Reference:
label | ○ Manufacturers details & Requirements.
label | ○ HBP Shop drawings
label | ○ Project Specification
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness Point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Alu-fix Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses
label | Verifying Record - Records Kept By: Alu-fix/HBP
checkpoint | d) Inspected for any other damage, eg dents or scratches.
label | Specification Reference:
label | ○ Manufacturers details & Requirements.
label | ○ HBP Shop drawings
label | ○ Project Specification
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness Point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Alu-fix Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses
label | Verifying Record - Records Kept By: Alu-fix/HBP
checkpoint | e) Check that the gaskets are in place without damage or voids and that the gaskets are crimped in place at both ends.
label | Specification Reference:
label | ○ Manufacturers details & Requirements.
label | ○ HBP Shop drawings
label | ○ Project Specification
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness Point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Alu-fix Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses
label | Verifying Record - Records Kept By: Alu-fix/HBP
checkpoint | f) Check that the sub-sills are clean and free from debris.
label | Specification Reference:
label | ○ Manufacturers details & Requirements.
label | ○ HBP Shop drawings
label | ○ Project Specification
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness Point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Alu-fix Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses
label | Verifying Record - Records Kept By: Alu-fix/HBP
section | INSTALLATION:
checkpoint | a) Check each panel is set to the correct height.
label | Specification Reference:
label | ○ Manufacturers details & Requirements.
label | ○ HBP Issue drawings
label | ○ Project Specification
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Alu-fix Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses
label | Verifying Record - Records Kept By: Alu-fix/HBP
checkpoint | b) Check each panel is plumb, levelled and true.
label | Specification Reference:
label | ○ Manufacturers details & Requirements.
label | ○ HBP Issue drawings
label | ○ Project Specification
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Alu-fix Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses
label | Verifying Record - Records Kept By: Alu-fix/HBP
checkpoint | c) Check that the gap between the mullions is as per design.
label | Specification Reference:
label | ○ Manufacturers details & Requirements.
label | ○ HBP Issue drawings
label | ○ Project Specification
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Alu-fix Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses
label | Verifying Record - Records Kept By: Alu-fix/HBP
checkpoint | d) Check bracket is engaged correctly to the primary bracket.
label | Specification Reference:
label | ○ Manufacturers details & Requirements.
label | ○ HBP Issue drawings
label | ○ Project Specification
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Alu-fix Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses
label | Verifying Record - Records Kept By: Alu-fix/HBP
checkpoint | e) Check that the lock off angle is fitted correctly.
label | Specification Reference:
label | ○ Manufacturers details & Requirements.
label | ○ HBP Issue drawings
label | ○ Project Specification
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Alu-fix Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses
label | Verifying Record - Records Kept By: Alu-fix/HBP
checkpoint | f) Verify that the connecting spigot and front soaker are clean, sealed and neatly tooled.
label | Specification Reference:
label | ○ Manufacturers details & Requirements.
label | ○ HBP Issue drawings
label | ○ Project Specification
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Alu-fix Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses
label | Verifying Record - Records Kept By: Alu-fix/HBP
checkpoint | g) Check beads are fitted and are rubbered off.
label | Specification Reference:
label | ○ Manufacturers details & Requirements.
label | ○ HBP Issue drawings
label | ○ Project Specification
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Alu-fix Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses
label | Verifying Record - Records Kept By: Alu-fix/HBP
checkpoint | h) Horizontal and vertical air seals applied and neatly tooled.
label | Specification Reference:
label | ○ Manufacturers details & Requirements.
label | ○ HBP Issue drawings
label | ○ Project Specification
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Alu-fix Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses
label | Verifying Record - Records Kept By: Alu-fix/HBP
checkpoint | i) Horizontal and vertical weather seals applied and neatly tooled.
label | Specification Reference:
label | ○ Manufacturers details & Requirements.
label | ○ HBP Issue drawings
label | ○ Project Specification
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Alu-fix Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses
label | Verifying Record - Records Kept By: Alu-fix/HBP
checkpoint | j) Rain shield flashings are installed correctly.
label | Specification Reference:
label | ○ Manufacturers details & Requirements.
label | ○ HBP Issue drawings
label | ○ Project Specification
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Alu-fix Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses
label | Verifying Record - Records Kept By: Alu-fix/HBP
checkpoint | k) Head flashing installed correctly.
label | Specification Reference:
label | ○ Manufacturers details & Requirements.
label | ○ HBP Issue drawings
label | ○ Project Specification
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Alu-fix Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses
label | Verifying Record - Records Kept By: Alu-fix/HBP
checkpoint | l) Parapet flashings are installed.
label | Specification Reference:
label | ○ Manufacturers details & Requirements.
label | ○ HBP Issue drawings
label | ○ Project Specification
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Alu-fix Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses
label | Verifying Record - Records Kept By: Alu-fix/HBP
section | LOUVRE INSTALLATION (where applicable):
checkpoint | a) Louvres are installed in the right location.
label | Specification Reference:
label | ○ Manufacturers details & Requirements.
label | ○ HBP Issue drawings
label | ○ Project Specification
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness Point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Alu-fix Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses
label | Verifying Record - Records Kept By: Alu-fix/HBP
checkpoint | b) Louvres are set to the correct position (height).
label | Specification Reference:
label | ○ Manufacturers details & Requirements.
label | ○ HBP Issue drawings
label | ○ Project Specification
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness Point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Alu-fix Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses
label | Verifying Record - Records Kept By: Alu-fix/HBP
checkpoint | c) All bolts are tight.
label | Specification Reference:
label | ○ Manufacturers details & Requirements.
label | ○ HBP Issue drawings
label | ○ Project Specification
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness Point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Alu-fix Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses
label | Verifying Record - Records Kept By: Alu-fix/HBP
checkpoint | d) Check the louvre is scratch and defect free.
label | Specification Reference:
label | ○ Manufacturers details & Requirements.
label | ○ HBP Issue drawings
label | ○ Project Specification
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness Point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Alu-fix Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses
label | Verifying Record - Records Kept By: Alu-fix/HBP
checkpoint | e) All drain holes are drilled and are clear of debris.
label | Specification Reference:
label | ○ Manufacturers details & Requirements.
label | ○ HBP Issue drawings
label | ○ Project Specification
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness Point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Alu-fix Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses
label | Verifying Record - Records Kept By: Alu-fix/HBP
section | PROTECTION:
checkpoint | a) Protective delivery film removed to external faces only.
label | Specification Reference: HBP requirements
label | Inspection - By: Alu-fix (Installer)
label | Inspection - Frequency: As Above
label | Inspection - Hold Point (Y/N): N
label | Verifying Record - Document Name: As Above
label | Verifying Record - Records Kept By: Alu-fix/HBP
checkpoint | b) Protective tape applied to all internal faces.
label | Specification Reference: HBP requirements
label | Inspection - By: Alu-fix (Installer)
label | Inspection - Frequency: As Above
label | Inspection - Hold Point (Y/N): N
label | Verifying Record - Document Name: As Above
label | Verifying Record - Records Kept By: Alu-fix/HBP
section | CLEAN & CLEAR AWAY:
checkpoint | a) Clear Workplace etc.
label | Specification Reference: c) Repair Method procedure by HBP
label | Inspection - By: Alu-fix (Installer)
label | Inspection - Frequency: a), b) Daily
label | Inspection - Hold Point (Y/N): N
label | Verifying Record - Document Name: Visual, c) HBP repair record for each repair
label | Verifying Record - Records Kept By: HBP
label | Comments: All windows to be checked prior to handover
checkpoint | b) Remove Debris & Waste Materials to skip.
label | Specification Reference: c) Repair Method procedure by HBP
label | Inspection - By: Alu-fix (Installer)
label | Inspection - Frequency: a), b) Daily
label | Inspection - Hold Point (Y/N): N
label | Verifying Record - Document Name: Visual, c) HBP repair record for each repair
label | Verifying Record - Records Kept By: HBP
label | Comments: All windows to be checked prior to handover
checkpoint | c) Make Good any damaged areas.
label | Specification Reference: c) Repair Method procedure by HBP
label | Inspection - By: Alu-fix (Installer)
label | Inspection - Frequency: a), b) Daily
label | Inspection - Hold Point (Y/N): N
label | Verifying Record - Document Name: Visual, c) HBP repair record for each repair
label | Verifying Record - Records Kept By: HBP
label | Comments: All windows to be checked prior to handover
section | CURTAIN WALL SITE TEST:
checkpoint | a) Water test in accordance with test procedure
label | Specification Reference: Project water test Procedure
label | Inspection - By: Alu-fix (Installer)/ HBP
label | Inspection - Frequency: As required
label | Inspection - Hold Point (Y/N): N
label | Verifying Record - Document Name: Alu-fix / HBP Test Report
label | Verifying Record - Records Kept By: Alu-fix/HBP
label | Comments: Water Testing locations as required
section | INSPECTION & ACCEPTANCE:
checkpoint | INSPECTION & ACCEPTANCE
label | Inspection - By: HBP & CPB Client
label | Inspection - Frequency: Each Area
label | Inspection - Hold Point (Y/N): Y
label | Verifying Record - Document Name: Completed Form above plus CPB HOLDPOINT to Client
label | Verifying Record - Records Kept By: HBP & CPB
textbox | HBP Agreement:
textbox | CPB Agreement:
textbox | Client Agreement:
holdpoint | HOLD POINT