## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP-4002 - Internal Glazing Installation (APL) | [5 empty] | CPB-NZ1006-ITP-4002 - Internal Glazing Installation (APL) - Rev 1
section | DOCUMENTATION RECEIVED:
checkpoint | a) Received QA documents.
label | Specification Reference: HBP details and requirements, Project Specification
label | Inspection - By: Alu-fix (Installer)
label | Inspection - Frequency: Each Delivery
label | Inspection - Hold Point (Y/N): N
label | Verifying Record - Document Name: Alu-fix Checklist
label | Verifying Record - Records Kept By: Alu-fix/HBP
checkpoint | b) Check for Damage, Quantity, Quality of goods.
label | Specification Reference: HBP details and requirements, Project Specification
label | Inspection - By: Alu-fix (Installer)
label | Inspection - Frequency: Each Delivery
label | Inspection - Hold Point (Y/N): N
label | Verifying Record - Document Name: Alu-fix Checklist
label | Verifying Record - Records Kept By: Alu-fix/HBP
checkpoint | c) Received all relevant setout/survey drawings.
label | Specification Reference: HBP details and requirements, Project Specification
label | Inspection - By: Alu-fix (Installer)
label | Inspection - Frequency: Each Delivery
label | Inspection - Hold Point (Y/N): N
label | Verifying Record - Document Name: Alu-fix Checklist
label | Verifying Record - Records Kept By: Alu-fix/HBP
section | INITIAL INSPECTION:
checkpoint | a) Gridlines and RL’s are visible and accessible.
label | Specification Reference: n/a
label | Inspection - By: Alu-fix (Installer)
label | Inspection - Frequency: Each Delivery
label | Inspection - Hold Point (Y/N): N
label | Verifying Record - Document Name: Alu-fix Checklist
label | Verifying Record - Records Kept By: Alu-fix/HBP
checkpoint | b) Installation area free from obstruction and has suitable access.
label | Specification Reference: n/a
label | Inspection - By: Alu-fix (Installer)
label | Inspection - Frequency: Each Delivery
label | Inspection - Hold Point (Y/N): N
label | Verifying Record - Document Name: Alu-fix Checklist
label | Verifying Record - Records Kept By: Alu-fix/HBP
section | SEISMIC SILL, HEAD, JAMBS and BRACKETS:
checkpoint | a) Opening Structure correct at sill, head and jambs.
label | Specification Reference: a~f) Manufacturers details & Requirements. HBP Shop Drawings Project Specification.
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness Point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Hagley Glazing QA Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses completed form above plus WITPOINT to client
label | Verifying Record - Records Kept By: Alu-fix/HBP, Aconex / Omtrak
label | Comments: Checklists to be countersigned by CPB on completion
checkpoint | b) Waterproofing / wrapping complete around entire opening.
label | Specification Reference: a~f) Manufacturers details & Requirements. HBP Shop Drawings Project Specification.
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness Point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Hagley Glazing QA Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses completed form above plus WITPOINT to client
label | Verifying Record - Records Kept By: Alu-fix/HBP, Aconex / Omtrak
label | Comments: Checklists to be countersigned by CPB on completion
checkpoint | c) Sill head, jamb & splice fixings are fitted correctly as per specifications and to correct RL.
label | Specification Reference: a~f) Manufacturers details & Requirements. HBP Shop Drawings Project Specification.
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness Point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Hagley Glazing QA Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses completed form above plus WITPOINT to client
label | Verifying Record - Records Kept By: Alu-fix/HBP, Aconex / Omtrak
label | Comments: Checklists to be countersigned by CPB on completion
checkpoint | d) Seismic frame inspected and defect free.
label | Specification Reference: a~f) Manufacturers details & Requirements. HBP Shop Drawings Project Specification.
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness Point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Hagley Glazing QA Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses completed form above plus WITPOINT to client
label | Verifying Record - Records Kept By: Alu-fix/HBP, Aconex / Omtrak
label | Comments: Checklists to be countersigned by CPB on completion
checkpoint | e) Seismic sill, head & jambs levelled to correct height.
label | Specification Reference: a~f) Manufacturers details & Requirements. HBP Shop Drawings Project Specification.
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness Point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Hagley Glazing QA Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses completed form above plus WITPOINT to client
label | Verifying Record - Records Kept By: Alu-fix/HBP, Aconex / Omtrak
label | Comments: Checklists to be countersigned by CPB on completion
checkpoint | f) All fixings, corner angles and splice plates are sealed and neatly tooled.
label | Specification Reference: a~f) Manufacturers details & Requirements. HBP Shop Drawings Project Specification.
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness Point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Hagley Glazing QA Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses completed form above plus WITPOINT to client
label | Verifying Record - Records Kept By: Alu-fix/HBP, Aconex / Omtrak
label | Comments: Checklists to be countersigned by CPB on completion
section | PRE-INSTALLATION:
checkpoint | a) Check panel identification with set out plans.
label | Specification Reference: a~f) Manufacturers details & Requirements. HBP Shop drawings Project Specification.
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness Point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Alu-fix Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses completed form above plus WITPOINT to client
label | Verifying Record - Records Kept By: Alu-fix/HBP, Aconex / Omtrak
label | Comments: Checklists to be countersigned by CPB on completion
checkpoint | b) Verify that the panel to be installed will be in the correct location.
label | Specification Reference: a~f) Manufacturers details & Requirements. HBP Shop drawings Project Specification.
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness Point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Alu-fix Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses completed form above plus WITPOINT to client
label | Verifying Record - Records Kept By: Alu-fix/HBP, Aconex / Omtrak
label | Comments: Checklists to be countersigned by CPB on completion
checkpoint | c) Visual inspection for any glass or sealant defects.
label | Specification Reference: a~f) Manufacturers details & Requirements. HBP Shop drawings Project Specification.
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness Point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Alu-fix Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses completed form above plus WITPOINT to client
label | Verifying Record - Records Kept By: Alu-fix/HBP, Aconex / Omtrak
label | Comments: Checklists to be countersigned by CPB on completion
checkpoint | d) Inspected for any other damage, eg dents or scratches.
label | Specification Reference: a~f) Manufacturers details & Requirements. HBP Shop drawings Project Specification.
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness Point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Alu-fix Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses completed form above plus WITPOINT to client
label | Verifying Record - Records Kept By: Alu-fix/HBP, Aconex / Omtrak
label | Comments: Checklists to be countersigned by CPB on completion
checkpoint | e) Check that the gaskets are in place without damage or voids and that the gaskets are crimped in place at both ends.
label | Specification Reference: a~f) Manufacturers details & Requirements. HBP Shop drawings Project Specification.
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness Point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Alu-fix Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses completed form above plus WITPOINT to client
label | Verifying Record - Records Kept By: Alu-fix/HBP, Aconex / Omtrak
label | Comments: Checklists to be countersigned by CPB on completion
checkpoint | f) Check that the sub-sills are clean and free from debris.
label | Specification Reference: a~f) Manufacturers details & Requirements. HBP Shop drawings Project Specification.
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness Point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Alu-fix Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses completed form above plus WITPOINT to client
label | Verifying Record - Records Kept By: Alu-fix/HBP, Aconex / Omtrak
label | Comments: Checklists to be countersigned by CPB on completion
section | FLUSH GLAZE & HINGED DOOR INSTALLATION (where applicable):
checkpoint | a) Check each panel is in the correct position.
label | Specification Reference:
label | ○ a~o)Manufacturers details & Requirements.
label | ○ HBP Issue drawings
label | ○ Door Hardware Schedule
label | ○ Project Specification
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness Point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Hagley Glazing QA Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses completed form above plus WITPOINT to client
label | Verifying Record - Records Kept By: Alu-fix/HBP, Aconex / Omtrak
label | Comments: Checklists to be countersigned by CPB on completion
checkpoint | b) Check each panel is plumb, levelled, and true.
label | Specification Reference:
label | ○ a~o)Manufacturers details & Requirements.
label | ○ HBP Issue drawings
label | ○ Door Hardware Schedule
label | ○ Project Specification
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness Point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Hagley Glazing QA Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses completed form above plus WITPOINT to client
label | Verifying Record - Records Kept By: Alu-fix/HBP, Aconex / Omtrak
label | Comments: Checklists to be countersigned by CPB on completion
checkpoint | c) Check that the gap between the mullions is as per design.
label | Specification Reference:
label | ○ a~o)Manufacturers details & Requirements.
label | ○ HBP Issue drawings
label | ○ Door Hardware Schedule
label | ○ Project Specification
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness Point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Hagley Glazing QA Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses completed form above plus WITPOINT to client
label | Verifying Record - Records Kept By: Alu-fix/HBP, Aconex / Omtrak
label | Comments: Checklists to be countersigned by CPB on completion
checkpoint | d) Check beads are fitted and rubbered off
label | Specification Reference:
label | ○ a~o)Manufacturers details & Requirements.
label | ○ HBP Issue drawings
label | ○ Door Hardware Schedule
label | ○ Project Specification
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness Point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Hagley Glazing QA Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses completed form above plus WITPOINT to client
label | Verifying Record - Records Kept By: Alu-fix/HBP, Aconex / Omtrak
label | Comments: Checklists to be countersigned by CPB on completion
checkpoint | e) Horizontal and vertical air seals applied and neatly tooled.
label | Specification Reference:
label | ○ a~o)Manufacturers details & Requirements.
label | ○ HBP Issue drawings
label | ○ Door Hardware Schedule
label | ○ Project Specification
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness Point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Hagley Glazing QA Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses completed form above plus WITPOINT to client
label | Verifying Record - Records Kept By: Alu-fix/HBP, Aconex / Omtrak
label | Comments: Checklists to be countersigned by CPB on completion
checkpoint | f) Horizontal and vertical seals applied and neatly tooled.
label | Specification Reference:
label | ○ a~o)Manufacturers details & Requirements.
label | ○ HBP Issue drawings
label | ○ Door Hardware Schedule
label | ○ Project Specification
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness Point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Hagley Glazing QA Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses completed form above plus WITPOINT to client
label | Verifying Record - Records Kept By: Alu-fix/HBP, Aconex / Omtrak
label | Comments: Checklists to be countersigned by CPB on completion
checkpoint | g) Rain shield flashings are installed correctly.
label | Specification Reference:
label | ○ a~o)Manufacturers details & Requirements.
label | ○ HBP Issue drawings
label | ○ Door Hardware Schedule
label | ○ Project Specification
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness Point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Hagley Glazing QA Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses completed form above plus WITPOINT to client
label | Verifying Record - Records Kept By: Alu-fix/HBP, Aconex / Omtrak
label | Comments: Checklists to be countersigned by CPB on completion
checkpoint | h) Head flashing installed correctly.
label | Specification Reference:
label | ○ a~o)Manufacturers details & Requirements.
label | ○ HBP Issue drawings
label | ○ Door Hardware Schedule
label | ○ Project Specification
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness Point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Hagley Glazing QA Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses completed form above plus WITPOINT to client
label | Verifying Record - Records Kept By: Alu-fix/HBP, Aconex / Omtrak
label | Comments: Checklists to be countersigned by CPB on completion
checkpoint | i) Door fitted to specifications.
label | Specification Reference:
label | ○ a~o)Manufacturers details & Requirements.
label | ○ HBP Issue drawings
label | ○ Door Hardware Schedule
label | ○ Project Specification
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness Point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Hagley Glazing QA Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses completed form above plus WITPOINT to client
label | Verifying Record - Records Kept By: Alu-fix/HBP, Aconex / Omtrak
label | Comments: Checklists to be countersigned by CPB on completion
checkpoint | j) All hinges and screws are fitted.
label | Specification Reference:
label | ○ a~o)Manufacturers details & Requirements.
label | ○ HBP Issue drawings
label | ○ Door Hardware Schedule
label | ○ Project Specification
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness Point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Hagley Glazing QA Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses completed form above plus WITPOINT to client
label | Verifying Record - Records Kept By: Alu-fix/HBP, Aconex / Omtrak
label | Comments: Checklists to be countersigned by CPB on completion
checkpoint | k) All gaps are correct around door.
label | Specification Reference:
label | ○ a~o)Manufacturers details & Requirements.
label | ○ HBP Issue drawings
label | ○ Door Hardware Schedule
label | ○ Project Specification
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness Point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Hagley Glazing QA Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses completed form above plus WITPOINT to client
label | Verifying Record - Records Kept By: Alu-fix/HBP, Aconex / Omtrak
label | Comments: Checklists to be countersigned by CPB on completion
checkpoint | l) Door opens and closes freely.
label | Specification Reference:
label | ○ a~o)Manufacturers details & Requirements.
label | ○ HBP Issue drawings
label | ○ Door Hardware Schedule
label | ○ Project Specification
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness Point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Hagley Glazing QA Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses completed form above plus WITPOINT to client
label | Verifying Record - Records Kept By: Alu-fix/HBP, Aconex / Omtrak
label | Comments: Checklists to be countersigned by CPB on completion
checkpoint | m) Lock/Handle are operating correctly.
label | Specification Reference:
label | ○ a~o)Manufacturers details & Requirements.
label | ○ HBP Issue drawings
label | ○ Door Hardware Schedule
label | ○ Project Specification
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness Point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Hagley Glazing QA Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses completed form above plus WITPOINT to client
label | Verifying Record - Records Kept By: Alu-fix/HBP, Aconex / Omtrak
label | Comments: Checklists to be countersigned by CPB on completion
checkpoint | n) Closer is fitted and adjusted correctly.
label | Specification Reference:
label | ○ a~o)Manufacturers details & Requirements.
label | ○ HBP Issue drawings
label | ○ Door Hardware Schedule
label | ○ Project Specification
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness Point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Hagley Glazing QA Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses completed form above plus WITPOINT to client
label | Verifying Record - Records Kept By: Alu-fix/HBP, Aconex / Omtrak
label | Comments: Checklists to be countersigned by CPB on completion
checkpoint | o) Threshold fitted correctly.
label | Specification Reference:
label | ○ a~o)Manufacturers details & Requirements.
label | ○ HBP Issue drawings
label | ○ Door Hardware Schedule
label | ○ Project Specification
label | Inspection - By:
label | ○ Alu-fix (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness Point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Hagley Glazing QA Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses completed form above plus WITPOINT to client
label | Verifying Record - Records Kept By: Alu-fix/HBP, Aconex / Omtrak
label | Comments: Checklists to be countersigned by CPB on completion
section | GLASS INSTALLATION (where applicable):
checkpoint | a) Glass Identified as correct type for location as per shop drawings
label | Specification Reference:
label | ○ a~h) Manufacturers details & Requirements.
label | ○ HBP Isings Project Specification
label | ○ c~g) NZS4223.3:2016
label | Inspection - By:
label | ○ GLass Guru (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness Point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Hagley Glazing QA Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses completed form above plus WITPOINT to client
label | Verifying Record - Records Kept By: Glass Guru/HBP, Aconex / Omtrak
label | Comments: Checklists to be countersigned by CPB on completion
checkpoint | b) Backing Rubbers continuous, sealed in corners and free of damage
label | Specification Reference:
label | ○ a~h) Manufacturers details & Requirements.
label | ○ HBP Isings Project Specification
label | ○ c~g) NZS4223.3:2016
label | Inspection - By:
label | ○ GLass Guru (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness Point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Hagley Glazing QA Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses completed form above plus WITPOINT to client
label | Verifying Record - Records Kept By: Glass Guru/HBP, Aconex / Omtrak
label | Comments: Checklists to be countersigned by CPB on completion
checkpoint | c) Glazing Blocks setout and type are correct.
label | Specification Reference:
label | ○ a~h) Manufacturers details & Requirements.
label | ○ HBP Isings Project Specification
label | ○ c~g) NZS4223.3:2016
label | Inspection - By:
label | ○ GLass Guru (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness Point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Hagley Glazing QA Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses completed form above plus WITPOINT to client
label | Verifying Record - Records Kept By: Glass Guru/HBP, Aconex / Omtrak
label | Comments: Checklists to be countersigned by CPB on completion
checkpoint | d) Glass placed in opening damage free.
label | Specification Reference:
label | ○ a~h) Manufacturers details & Requirements.
label | ○ HBP Isings Project Specification
label | ○ c~g) NZS4223.3:2016
label | Inspection - By:
label | ○ GLass Guru (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness Point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Hagley Glazing QA Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses completed form above plus WITPOINT to client
label | Verifying Record - Records Kept By: Glass Guru/HBP, Aconex / Omtrak
label | Comments: Checklists to be countersigned by CPB on completion
checkpoint | e) Safety stamp visible. (industry standard is bottom right from outside)
label | Specification Reference:
label | ○ a~h) Manufacturers details & Requirements.
label | ○ HBP Isings Project Specification
label | ○ c~g) NZS4223.3:2016
label | Inspection - By:
label | ○ GLass Guru (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness Point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Hagley Glazing QA Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses completed form above plus WITPOINT to client
label | Verifying Record - Records Kept By: Glass Guru/HBP, Aconex / Omtrak
label | Comments: Checklists to be countersigned by CPB on completion
checkpoint | f) Beads securely fitted and damage free.
label | Specification Reference:
label | ○ a~h) Manufacturers details & Requirements.
label | ○ HBP Isings Project Specification
label | ○ c~g) NZS4223.3:2016
label | Inspection - By:
label | ○ GLass Guru (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness Point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Hagley Glazing QA Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses completed form above plus WITPOINT to client
label | Verifying Record - Records Kept By: Glass Guru/HBP, Aconex / Omtrak
label | Comments: Checklists to be countersigned by CPB on completion
checkpoint | g) Correct glazing wedge used and rubber off ensuring there is no gaps and corners are sealed.
label | Specification Reference:
label | ○ a~h) Manufacturers details & Requirements.
label | ○ HBP Isings Project Specification
label | ○ c~g) NZS4223.3:2016
label | Inspection - By:
label | ○ GLass Guru (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness Point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Hagley Glazing QA Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses completed form above plus WITPOINT to client
label | Verifying Record - Records Kept By: Glass Guru/HBP, Aconex / Omtrak
label | Comments: Checklists to be countersigned by CPB on completion
checkpoint | h) Glass trade clean, free of defects and protection tape fitted where required.
label | Specification Reference:
label | ○ a~h) Manufacturers details & Requirements.
label | ○ HBP Isings Project Specification
label | ○ c~g) NZS4223.3:2016
label | Inspection - By:
label | ○ GLass Guru (Installer)
label | ○ CPB
label | ○ Client
label | Inspection - Frequency:
label | ○ Each Area
label | ○ Random
label | ○ Witness Point
label | Inspection - Hold Point (Y/N):
label | ○ N
label | ○ N
label | ○ N
label | Verifying Record - Document Name:
label | ○ Visual
label | ○ Hagley Glazing QA Checklist
label | ○ This to be held as a 'live record'. And be updated daily as the work progresses completed form above plus WITPOINT to client
label | Verifying Record - Records Kept By: Glass Guru/HBP, Aconex / Omtrak
label | Comments: Checklists to be countersigned by CPB on completion
section | PROTECTION:
checkpoint | a) Protective delivery film removed to external faces only.
label | Specification Reference: HBP requirements
label | Inspection - By: Alu-fix (Installer)
label | Inspection - Frequency: As Above
label | Inspection - Hold Point (Y/N): N
label | Verifying Record - Document Name: As Above
label | Verifying Record - Records Kept By: Alu-fix/HBP
checkpoint | b) Protective tape applied to all internal faces.
label | Specification Reference: HBP requirements
label | Inspection - By: Alu-fix (Installer)
label | Inspection - Frequency: As Above
label | Inspection - Hold Point (Y/N): N
label | Verifying Record - Document Name: As Above
label | Verifying Record - Records Kept By: Alu-fix/HBP
section | CLEAN & CLEAR AWAY:
checkpoint | a) Clear Workplace etc.
label | Specification Reference: c) Repair Method procedure by HBP
label | Inspection - By: Alu-fix (Installer)
label | Inspection - Frequency: a), b) Daily
label | Inspection - Hold Point (Y/N): N
label | Verifying Record - Document Name: Visual, c) HBP repair record for each repair
label | Verifying Record - Records Kept By: HBP
label | Comments: All windows to be checked prior to handover
checkpoint | b) Remove Debris & Waste Materials to skip.
label | Specification Reference: c) Repair Method procedure by HBP
label | Inspection - By: Alu-fix (Installer)
label | Inspection - Frequency: a), b) Daily
label | Inspection - Hold Point (Y/N): N
label | Verifying Record - Document Name: Visual, c) HBP repair record for each repair
label | Verifying Record - Records Kept By: HBP
label | Comments: All windows to be checked prior to handover
checkpoint | c) Make Good any damaged areas.
label | Specification Reference: c) Repair Method procedure by HBP
label | Inspection - By: Alu-fix (Installer)
label | Inspection - Frequency: a), b) Daily
label | Inspection - Hold Point (Y/N): N
label | Verifying Record - Document Name: Visual, c) HBP repair record for each repair
label | Verifying Record - Records Kept By: HBP
label | Comments: All windows to be checked prior to handover
section | INSPECTION & ACCEPTANCE:
checkpoint | INSPECTION & ACCEPTANCE
label | Inspection - By: HBP & CPB Client
label | Inspection - Frequency: Each Area
label | Inspection - Hold Point (Y/N): Y
label | Verifying Record - Document Name: Completed Form above plus CPB HOLDPOINT to Client
label | Verifying Record - Records Kept By: HBP & CPB Aconex / Omtrak
label | Comments: Checklists to be countersigned by CPB on completion
textbox | HBP Agreement:
textbox | CPB Agreement:
textbox | Client Agreement:
holdpoint | HOLD POINT