## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | Precast Beams |  | Precast Beams | 0e491e7c-b06d-435b-a8c8-5b83797c2e5f
| section | Pre-Pour Checklist
| checkpoint | Pre-Pour Checklist completed
69ddc27c-944c-54f5-830f-9f39c43c92cf | textbox | Cast Number
97e51e40-ff27-5519-a027-354694360410 | textbox | Bridge Name
76733c08-6c15-5a0c-bf1f-bb99445b3a54 | textbox | Precast Beam 1
7c7d5b48-8d5c-5f4a-bf48-893a28e4207b | textbox | Precast Beam 2
| checkpoint | Shop Drawings approved for Works
| checkpoint | Mould Dimensions are within Shop Drawings Tolerance
74ee71ab-b575-5cdc-9f7e-dd547016dade | note | Length
aff9f0e0-cad2-5ab6-b276-88d891e55799 | note | Width
606f209a-f3de-5faa-be75-f0d395e8fc2b | note | Height
714442a2-058e-5a00-af46-2b2a3136e6a1 | note | Straightness
84c64428-e6e8-5549-b776-ab30b938366a | note | Cross-section
| checkpoint | Mould Surface Checked
2748c8af-19e1-548f-adb0-664a9dcb1f30 | note | Cleaned
637effe0-d931-510a-82f8-2e6342bd4a1a | note | Sealed
a4a83c07-e369-53bb-9c33-03eb07335ee4 | note | Rubbers in Place
eead9c61-721b-53ba-b57f-bde477bdedca | note | Oiled
1e8b471e-1d3e-525a-8d32-b54c1c4ae4b3 | note | Chamfers in Place
| checkpoint | Reinforcement in Accordance with Drawings
aec0f3e6-ac1c-57b7-a465-368d9e0ffeef | note | Reinforcement size
9cb5fcb9-dfc7-5fd3-aebd-4451240f8056 | note | Lap Length
c8ed53ea-3419-5b66-8e84-a4b88aa0bd48 | note | Splicing
b90bf41f-1e4b-5468-be5c-e02ba235a2e0 | note | Bar Chairs
| checkpoint | Cover maintained and within tolerance
| checkpoint | All Cast-in Items are installed in accordance with Drawings
bf5415bc-b861-5076-9d0c-c6c25ed0cd69 | note | Cast-in Items
82a3cc6f-80b6-551f-8328-bc7a3127f092 | note | Fittings
aee5f22f-cbda-58bd-94c0-6503b2bdb7c3 | note | Lifters Position and Type
| checkpoint | Prestressing Strands
bfbf8372-e27a-5af0-ac9b-144d79f63e2d | textbox | Enter Coil Number Used for this Cast
a55457a7-5acd-5d7b-84e8-db2e54d82886 | note | Sag Load all Strand
3c980f2d-06a3-524c-af0b-7cca8969653c | note | Mutli-Stress as per Pre-stressing Procedures
| checkpoint | All Temperature Loggers are installed as per Approved WMS
13a440a3-2b2b-5e27-81f8-83103266b69a | note | Every 25m
36f41c3f-7d20-525f-b766-6ab2183c57a6 | note | 1 x End Block Mid-Diaphragm
6156b3c3-8419-5c74-aa9a-376cd3603544 | note | 1 x Within Cover Zone
4e710c70-7f37-5c0f-959e-62a4a7c6ebe8 | note | 1 x Within Tent/Tarp Enclosure (Outside concrete)
448d0395-20ce-554b-80ae-8fd020e31bf9 | note | 1 x Outside Tent/Tarp Enclosure (Ambient Temperature)
| checkpoint | Ensure All temperature Loggers are Working (Check App)
| checkpoint | Prepare Stressing Records and Submit to Client for Review
| signoff | (HOLD POINT FOR CLIENT TO SIGN OFF)
| checkpoint | QA Engineer Check Completed by
| checkpoint | Client Inspector (if present)
| section | Supervisor Release
| checkpoint | Supervisor Release to Engineering Team
| section | Casting Checklist
| checkpoint | Casting Information
279189f0-9cd5-58b0-a3ab-d7616ecf7eb9 | textbox | Cast Date
| checkpoint | Concrete Delivery Dockets
7a9219c0-8c0b-52a0-85b4-9cfb5a3f004b | textbox | Concrete Delivery Dockets
| checkpoint | Total Concrete Volume
9573cbe4-2cf6-507f-abc7-7803e8c15e88 | textbox | Volume (m3)
| checkpoint | Mix Design Verified (BH1445 - S50 or WS504MC09 - S50)
b7e0b8de-95b9-5c71-b3ce-b44d40d2c0b7 | note | Concrete Mix Strength (Mpa)
| checkpoint | Ambient Temperature within Limits
61e6f0f8-3b5c-5ea3-93fc-c8e2f65a983d | note | 5 - 38°C
| checkpoint | Concrete Temperature
dcfe9852-d880-5266-b958-758ea717102b | note | max 32°C
| checkpoint | Slump within Allowable Tolerance
04a5df8c-abb7-53ca-8ba1-2dd9d60476b1 | textbox | Slump 1
26c1c358-e31f-58cb-b804-586c63f82403 | textbox | Slump 2
1318ca1d-9feb-50ae-82b4-8d4924aaeed9 | note | WA Premix 180 ± 40mm / Holcim 200 ± 40mm
| checkpoint | Truck Tested for strength
f813cccb-b6d8-5b70-b1cb-cd94ccae724e | textbox | Test Report Reference Number 1
cc46ebdb-9fe4-5664-8b9e-5f21e4feae1a | textbox | Test Report Reference Number 2
| checkpoint | Time Lag Between Trucks (< 20min)
| checkpoint | Concrete Placed within 90min from Batching Plant
| checkpoint | No Free Fall During Pour (< 2m)
| checkpoint | Required Finish Applied as per Drawings
| checkpoint | Concrete Covered Overnight
| checkpoint | Cylinders Stored next to Bed
| section | Stripping Checklist
| checkpoint | Date Stripped
182128b4-0827-568a-a1ad-90f3ba7d41a0 | textbox | Enter Date
| checkpoint | Concrete Cylinders Crushed and Submitted to Client
ab28fc0b-0991-5022-b6c0-6897f13435fc | textbox | Stripping Strength
5b89f5a3-86e5-5fda-9f1a-6706609f8307 | note | Strength = Reading / 7.851
| signoff | (HOLD POINT FOR CLIENT TO SIGN OFF)
| checkpoint | Lifting Strength Achieved
| checkpoint | Product Clearly Labelled
| checkpoint | Product Dimensions Achieved and are within Specified Tolerance
8af16b73-9c36-5294-9da4-f07548436a5d | note | Length
37034791-b51d-5f88-bc21-34414d2f1281 | note | Width
0a90a16f-8dd4-57c9-927e-1687fe96f120 | note | Height
ee5d777e-2013-599a-8848-04599edbdc7d | note | Straightness
b6e707e8-d9d3-569f-9297-b613fc6ff749 | note | Cross-section
| checkpoint | Specified Finish Achieved
| checkpoint | Cast-in Items are all in Place and within Specified Tolerance
e0143584-2d3e-59d4-834f-27583442163b | note | Cast-in Items
a3de4609-ec4a-50a1-92b2-ae4c925747a1 | note | Fittings
4c670b3e-d5d6-5fa6-a1bb-14e6dbdce8f2 | note | Lifters Position and Type
| checkpoint | Lifted and Handled as per Drawings
| checkpoint | Storage/Stacking as per Approved Plan
| checkpoint | Curing as per Approved Methodology
| checkpoint | Post-Pour Works Completed (As Required)
81e02f2e-7e8c-52a5-8958-0022edb5fb64 | textbox | Strands are Cut Flush
a8b15bc3-450b-55b1-8773-b7ef46a1a221 | textbox | Strands Bulbs as per Drawing
ff65c190-9ed8-5f66-9704-94bf768369cd | textbox | Starter Bars are Bent as Required
987cbce0-eb20-517b-b332-bebc69bc680d | textbox | All Drain Holes are Clean
85a3cef7-0fb0-56fe-b612-847e4c9f9e9c | textbox | All Miscellaneous Items are Completed
| checkpoint | Survey Hog of Beams (Dumpy)
41f9b1a1-1a9a-5959-a168-2a1604bdd484 | textbox | First Reading (Once Stripped)
38dd0615-4019-59ac-814e-32dab10cef23 | textbox | Second Reading (if required)
748ba577-d1ea-5ae5-8713-5043f3529a7e | textbox | Final Reading (Prior to Delivery)
| checkpoint | Temperature Logging Completed and Conforming. Attach Results
| section | Any Defect Identified
| checkpoint | Punchlisting Completed
| checkpoint | Repairs Required (if applicable)
| checkpoint | Repairs Completed as per approved WMS (if applicable)
| checkpoint | Any NCR Required (if applicable)
| checkpoint | NCR Approved by Client and Repairs Completed (if applicable)
| section | As-Built Drawings
| checkpoint | As-Built Drawings Completed, Stamped and Attached
| section | Concrete Strength Test Report
| checkpoint | Concrete Strength Test Report Received
0b347553-ffde-5cbf-a182-943dd3914560 | textbox | Concrete Test Report Number 1
c13b7364-6e07-56fc-8e78-4e1f7109fb8d | textbox | 7 Day Strength (1)
53d248e5-06aa-536c-b9fd-5360906da685 | textbox | 7 Day Strength (2)
02d3129d-2d17-5b3f-befb-7d00976cf5fe | textbox | 28 Day Strength (3)
f719f956-61e0-5ea7-a7b7-705401ece406 | textbox | 28 Day Strength (4)
72e8fe90-b833-56f9-ba84-82650a3f4305 | textbox | 28 Day Strength (5)
0972ae2e-72db-5211-9743-f311b84f9151 | textbox | 28 Day Strength (6)
| section | Transportation Requirements
| checkpoint | Certificate of Conformance
| checkpoint | Inspection Release Certificate
| checkpoint | Delivery Notes
| checkpoint | Delivery Dockets
| section | Final Acceptance (Conforming to all Requirements and is Ready for Transport)
| checkpoint | Completed by
| checkpoint | Reviewed by
| signoff | (INTERNAL HOLD POINT)
| checkpoint | Client Representative (if applicable)
| checklist | Precast Parapets |  | Precast Parapets | d7cd58f5-7463-4349-8d99-4406a01fe391
| section | Pre-Pour Checklist
| checkpoint | Pre-Pour Checklist completed
bfbc23d4-a352-552b-a2c7-45979702de9e | textbox | Cast Number
fc5aaa44-61f6-5fc6-bb8d-cd8e31343df0 | textbox | Bridge Name
fdf5894b-ff7f-5471-9baf-63832f4dce5a | textbox | Precast Parapet 1
89a670b5-1aed-5a5c-9633-5c10ef91c344 | textbox | Precast Parapet 2
| checkpoint | Shop Drawings approved for Works
| checkpoint | Mould Dimensions are within Shop Drawings Tolerance
69c54da1-1e77-5690-b3e2-dbc62c699f8b | note | Length
22b42ddb-c588-52d7-8bd9-f085f083c6e5 | note | Width
7cd8bc91-9341-5e61-8872-dcaa214311c3 | note | Height
1eb3bdc5-dbf2-541d-a4a3-1a55ad84fd62 | note | Straightness
2c5a2511-6487-5f88-9096-ef25311056a4 | note | Cross-section
| checkpoint | Mould Surface Checked
5733e599-6d9e-5980-8aca-2f07e4a5f777 | note | Cleaned
9907a1bd-75ab-5f8e-9932-4827cfaaf880 | note | Sealed
cf5796e4-b90a-5c26-983f-40544e965c13 | note | Rubbers in Place
bbf22f82-62f2-5b08-9d23-e3ef37824d30 | note | Oiled
ca1219ab-fd65-5440-9115-dc86fd063868 | note | Chamfers in Place
| checkpoint | Reinforcement in Accordance with Drawings
ca091c1a-ea55-5abc-8d63-e35a7630f5d8 | note | Reinforcement size
77aa81b4-8559-571b-b69d-b6a06cd22717 | note | Lap Length
37af8ffc-a071-5e7b-a7d7-bac6b6805886 | note | Splicing
fc3b16a1-cef9-5aba-86e0-15808860b5fb | note | Bar Chairs
| checkpoint | Cover maintained and within tolerance
| checkpoint | All Cast-in Items are installed in accordance with Drawings
33b9a5cb-3b0d-54ac-a498-6b3f7a04023d | note | Cast-in Items
99b5fcf0-9416-5831-885d-8ac8ea686ff9 | note | Fittings
4b45ea79-2b04-56f1-8c33-74d8bbfb6c15 | note | Lifters Position and Type
| checkpoint | QA Engineer Check Completed by
| checkpoint | Client Inspector (if present)
| section | Supervisor Release
| checkpoint | Supervisor Release to Engineering Team
| section | Casting Checklist
| checkpoint | Casting Information
12a09dc4-63b4-5429-baae-fb47542cb652 | textbox | Cast Date
| checkpoint | Concrete Delivery Dockets
291d9c08-8a37-5f94-9e06-3c4398c1ae1a | textbox | Concrete Delivery Dockets
| checkpoint | Total Concrete Volume
591ed45c-a8bc-573e-8807-ef28e5f9c4c1 | textbox | Volume (m3)
| checkpoint | Mix Design Verified (AH1404 - S40)
462af439-7d4b-58aa-8b89-333539d376e5 | note | Concrete Mix Strength (Mpa)
| checkpoint | Ambient Temperature within Limits
a1c1909a-c209-5688-87e5-e3fa3a3bef2c | note | 5 - 38°C
| checkpoint | Concrete Temperature
93a61757-807d-5a41-b500-5325ededcc73 | note | max 32°C
| checkpoint | Slump within Allowable Tolerance
3b503ce6-b1ba-5aaa-890f-c45e2361a96e | textbox | Slump 1
bac33c18-0730-5986-aa31-b909c92d88ae | textbox | Slump 2
f2536ae6-3b9e-5ca0-9e60-8f56ae933a58 | note | WA Premix 120 ± 30mm
| checkpoint | Truck Tested for strength
54a5b59c-9365-5319-8d31-208e498bac57 | textbox | Test Report Reference Number 1
858d684d-9ce1-50d6-93fe-0633f9dd0b79 | textbox | Test Report Reference Number 2
| checkpoint | Time Lag Between Trucks (< 20min)
| checkpoint | Concrete Placed within 90min from Batching Plant
| checkpoint | No Free Fall During Pour (< 2m)
| checkpoint | Required Finish Applied as per Drawings
| checkpoint | Concrete Covered Overnight
| checkpoint | Cylinders Stored next to Bed
| section | Stripping Checklist
| checkpoint | Date Stripped
4c2d73cf-ff57-556c-989c-6d4dfcf42674 | textbox | Enter Date
| checkpoint | Concrete Cylinders Crushed and Submitted to Client (HOLD POINT FOR CLIENT TO SIGN OFF)
61ee43c0-63b8-5ec3-8f17-468900624590 | textbox | Stripping Strength
df4b2d3e-e2d3-5063-98e1-9288721f926e | note | Strength = Reading / 7.851
| checkpoint | Lifting Strength Achieved
| checkpoint | Product Clearly Labelled
| checkpoint | Product Dimensions Achieved and are within Specified Tolerance
3d5c31c9-3bed-52e7-b2b5-f0083008aa6b | note | Length
96937069-fdab-5c4c-a487-fdd251c0380d | note | Width
7ed9c413-f41a-549c-bd88-7b3378fe5aca | note | Height
b6191723-7fee-5649-87ba-b6549841bdf2 | note | Straightness
ab86df7b-eac5-5441-a4ab-6e0bb61a192b | note | Cross-section
| checkpoint | Specified Finish Achieved
| checkpoint | Cast-in Items are all in Place and within Specified Tolerance
13fc2a04-fb9c-5db3-b612-d826de78fb1b | note | Cast-in Items
325bcfc2-cc4c-545e-9c73-1568adbce00e | note | Fittings
c42c975a-02e0-5877-aec8-103ee1323a4e | note | Lifters Position and Type
| checkpoint | Lifted and Handled as per Drawings
| checkpoint | Storage/Stacking as per Approved Plan
| checkpoint | Curing as per Approved Methodology
| checkpoint | Post-Pour Works Completed (As Required)
8120ba02-7679-5d7e-b881-4354797e85da | textbox | All Miscellaneous Items are Completed
| section | Any Defect Identified
| checkpoint | Punchlisting Completed
| checkpoint | Repairs Required (if applicable)
| checkpoint | Repairs Completed as per approved WMS (if applicable)
| checkpoint | Any NCR Required (if applicable)
| checkpoint | NCR Approved by Client and Repairs Completed (if applicable)
| section | As-Built Drawings
| checkpoint | As-Built Drawings Completed, Stamped and Attached
| section | Concrete Strength Test Report
| checkpoint | Concrete Strength Test Report Received
07bbfd76-bbc7-58f1-b8a2-d96752298e41 | textbox | Concrete Test Report Number 1
ddd898ad-32a5-5ce3-ab54-31286bdbe9a0 | textbox | 7 Day Strength (1)
77ee37d4-70bd-542f-98fa-368e3a05703d | textbox | 7 Day Strength (2)
b47579bc-0a66-521f-85ed-7133966fb57b | textbox | 28 Day Strength (3)
476e1692-5423-59c7-aa43-8c175a197efa | textbox | 28 Day Strength (4)
f0cccd57-81d8-5d64-8ad1-04410fa068d2 | textbox | 28 Day Strength (5)
3e03c326-e779-5bb4-afad-138bd02e161a | textbox | 28 Day Strength (6)
| section | Transportation Requirements
| checkpoint | Certificate of Conformance
| checkpoint | Inspection Release Certificate
| checkpoint | Delivery Notes
| checkpoint | Delivery Dockets
| section | Final Acceptance (Conforming to all Requirements and is Ready for Transport)
| checkpoint | Completed by
| checkpoint | Reviewed by
| signoff | (INTERNAL HOLD POINT)
| checkpoint | Client Representative (if applicable)
| checklist | Preliminary Activities and Materials Approval |  | Preliminary Activities and Materials Approval | 9add3973-fbc7-4b08-a3ae-4bc39edc9b86
| section | Preliminary Activities (Approved by Client)
| checkpoint | Compliance to AS/NZ ISO 9001:2015
| checkpoint | HSE Management Plan
| checkpoint | Permacast Project Quality Management Plan
| checkpoint | Inspection & Test Plan
| checkpoint | MDR Index
| checkpoint | Work Method Statement (WMS) - Prestress
| checkpoint | Work Method Statement (WMS) - Curing
| checkpoint | Concrete Repair Methodology
| checkpoint | Shop Drawings
| checkpoint | All Technical Query Forms (TQs) Reviewed and Approved for Works
| section | Concrete
| checkpoint | S50 Concrete Mix Design Approved by Client
35b827b2-6518-5db7-aa56-67712999ac45 | note | Supplier : Holcim
fa888c8e-78f0-5915-abbb-c4eceb8f213e | note | Mix Code: WS504MC09 (S50/20/200)
2faffdc3-d3c3-5fe5-98fa-c45bad81f4bc | note | Slump : 200 ± 40
| checkpoint | S50 Concrete Mix Design Approved by Client
f095430b-3ae7-58ea-95a3-155a20e4bdc9 | note | Supplier : WA Premix
d05990ab-ae16-55a8-9778-47a017878584 | note | Mix Code: BH1445 (S50/14/200)
e91eb68c-f933-5ddf-aa8f-481a68b55054 | note | Slump : 180 ± 40
| section | Steel Reinforcement
| checkpoint | Inspection of Delivery to Confirm Compliance with Order and Drawings
| checkpoint | Cut Bar Length Tolerance +0mm -10mm, Bends in Plane, Correct Cog Lengths etc.
| section | Prestressing Tendons
| checkpoint | Inspection of Delivery to Confirm Compliance with Order and Drawings
| checkpoint | Ensure that all Coil Numbers are recorded
| checkpoint | Stressing Calculations Submitted and Approved by Client for Works
| checkpoint | Stressing Jack Calibration Certificates
| section | Lifting Anchors
| checkpoint | Lifting Design Approved by Client
| checkpoint | Lifting Devices Approved by Client
| checkpoint | Inspection of Delivery for Completeness and Quality
| section | Cast-in Items and Ferrules
| checkpoint | All Cast in Materials Approved
| checkpoint | Inspection of Delivery for Completeness and Quality