## Sheet3
Inspection and Test Plan Te Ara o Te Ata rev02 Fill 12 & 13 Main Gully Subsoil Drainage Install - ITP # MMA-QA-LOT-Z03-EW-GE003 rev 2
| This ITP has been prepared by |  |  | Reviewed by (QA representative) |  |  | Reviewed by (DSR Representative) | [6 empty] | Approved by [Construction Manager]
Rev Number | Name | Signature | Date | Name | Signature | Date | Name |  | Signature |  | Date |  |  | Name |  | Signature |  | Date
Rev 01 | Thomas Puxley |  | 2022-08-23
Rev 02 | Thomas Puxley | T. Puxley | 2023-11-17 | Ramy Faragalla | R. Faragalla | 2023-11-17 | Danny Beasant |  | D.Beasant |  | 2023-11-17 |  |  | Hardus Pieters
Rev 03
Rev 04
ITP NO: MMA-QA-LOT-Z03-EW-GE003 |  | Project: Te Ara o Te Ata | [5 empty] | Method Statement Ref: |  |  | Rev.02
Verification Method: Hold [H] – work will not proceed past Hold Point until released by organisation imposing hold; Inspection [I] – formal inspection activity to be undertaken and recorded; ensure correct verifying records are in place; Witness [W] – an inspection that may be witnessed by organisation imposing hold; allow reasonable notification period; Review [R] – review of reports, records or other evidence of compliance. | [7 empty] | Responsibilities PE = MTM Alliance Construction TWD = Temporary Design Team
Activity/Specification: Drainage and Earthworks | [7 empty] | Area Location / Work Breakdown: Zone 5
Item | Construction Step or Material |  | Specifications and Standards |  | Acceptance criteria and testing |  |  |  | Method (H,I,W,R) |  |  |  | Verifying Records Checklists, Test and Supplier Certificates |  | Site Engineer approved | DSR Engineer verification | Certified Complete (Date, relevant checklist title/lab report number etc)
Responsible [tick]
[5 empty] | Method/ Description | Test frequency |  | Conformance Criteria | Contractor | Designer | Client | Lab
1.0 Pre-Construction
1.01 | Confirm Method Statement Signed off |  | MMA-DES-GEO-E1-SPC-3859 |  | Document Review | Prior to Work, Once |  | Approved by Relevant Parties | H | H |  |  | Signed Copy of Method Statement
1.02 | Confirm Compliance against Resource Consent & Management Plans |  | MMA-DES-GEO-E1-SPC-3859 |  | Document Review | Prior to Work, Once |  | Approved Management Plans, SCWMP and CWP | H | H |  |  | Signed Management Plans, Approved SCWMP and Approved CWP
1.03 | Confirm IFC Design is in place |  | MMA-DES-GEO-E1-SPC-3859 |  | Document Review | Prior to Work, Once |  | IFC Drawings Approved |  | H |  |  | IFC Drawings Issued
1.04 | Complete Permit To Dig |  | Internal Permit |  | Document Production | All Excavation works |  | Signed off Permit to Dig | H |  |  |  | Permit to Dig Form
2.0 Material Compliance
2.01 | Order Subsoil Pipes |  | MMA-DES-GEO-E1-SPC-3859 As per relevant Drawing set MMA-DES-GEO-E1-DRG-4006 |  | Ensure Pipes are ordered as per drawing | All Subsoils |  | Ordered Pipes match Drawing & Spec. Unless Specified otherwise Main Gully, 160mm NEXUS HI-WAY, Side Gully, 110 NEXUS HI-WAY | R, I |  |  |  | Delivery Dockets Material Complaince Certifcate/Data Sheets Material Delivery Inspection Checksheet
2.02 | Order Geotextile Material |  | MMA-DES-GEO-E1-SPC-3859 TNZ F/7 Bidim-Storage-Installation-Guide-M142-10-14-NZ.pdf |  | Document Review | All Geotextiles |  | Ensure Geotextile ordered meets specification & drawings Non-Woven Strength Class C For Cohesive Soil Type Filtration Class 1 or 3 (BIDIM A29) Stored off ground, under shade, rolls come wrapped | R, I |  |  |  | Material Complaince Certifcate/Data Sheets Delivery Dockets
2.03 | Order Subsoil Drainage Backfill Material |  | MMA-DES-GEO-E1-SPC-3859 NZTA F/2: 2013, TNZ F6:2003 Fill 12 & 13 Specific - Section 9.1 of MMA-DES-GEO-E1-SPC-3862 |  | Laboratory Testing | All Material |  | Drainage Aggregate shall be open course graded clean (Preferably washed) durable aggregate. Crushing resistance or not less than 100kN when tested as per NZS4407:1991 Test 3.11 Permeability, k - >or equal 1 x 10-4 m/s Comply with grading as per 4.13 of the specification | R | H |  | R | PSD Results Permeability Test Results Crushing Resistance Test RFI - Confirmation of Material acceptance from Designers
HOLD POINT ABOVE
2.04 | Order FarmBoss Pipes (Temporary Drainage) |  | Relevant Temporary Work Design R2.6-Farmboss-Polypropylene-Pipe.pdf |  | Document Review Material Delivery Inspection | All Pipe |  | FarmBoss is rate SN6 Confirm all couplers match | R, I |  |  |  | Delivery Docket Material Delivery Inspection Checksheet
3.0 During Construction
3.01 | Clearing and Stripping of Area Note: Fill 12 and 13 are exempt from Organic Waste Clearing and Stripping when >5m from finished ground level |  | Section 6.2 & 6.3 MMA-GEO-E1-SPC-3859 |  | Removal of Organic Material | All areas. Subsoil Checklist completed for every independent section and minimum 100m length. |  | Removal of all growth other than grass and weeds. Extraction of stumps and all roots greater than 25mm The depth of topsoil stripping shall be sufficient to remove all organic material, turf and significant plant roots | I |  |  |  | Subsoil Install Checklist, Photographs |  | Not applicable
3.02 | Formation Level Inspection |  | Section 9.6 MMA-GEO-E1-SPC-3859 |  | Visual | At formation level before installing the geotextile. First section of pipe and then once every 50 m of pipe laid. |  | Gully base shall be shaped with loose debris and soft silt removed. The Constructor shall identify any areas where significant water flows or seepages occur within the natural topography of the site. DSR shall advise whether additional primary, secondary or other collector drains are required. | H | H |  |  | Subsoil Install Checklist, Photographs
3.03 | Lay Geotextile (BIDIM A29) |  | TNZ F/5:2000 (testing, Storage and Install) Bidim-Storage-Installation-Guide-M142-10-14-NZ.pdf MMA-DES-GEO-E1-SPC-3859.01 |  | Inspection | All BIDIM. Subsoil Checklist completed for every independent section and minimum 100m length. |  | Installed in area as per drawings, 300mm minimum lap. | H | R |  |  | Subsoil Install Checklist, Photographs
3.04 | Install Bedding Material for Subsoil |  | MMA-DES-GEO-E1-SPC-3859 Section 5.0 - NZTA F2:2013 |  | Inspection | All Subsoils. Subsoil Checklist completed for every independent section and minimum 100m length. |  | Not less than 150mm Bedding or as per Dwg Main Gully - 20mm Drainage Aggregate- Side Gully - 20mm Drainage Aggregate | I | R |  |  | Subsoil Install Checklist, Photographs
3.05 | Install Main Gully Subsoil |  | MMA-DES-GEO-E1-SPC-3859 Section 8. NZTA F/2: 2013 |  | Inspection | All Subsoils. Subsoil Checklist completed for every independent section and minimum 100m length. |  | Set true to line and level, lay at lowest point of stream. Min offset of 200mm from gully side wall as per DWG. Perforations to TOP ( red stripe appears approximately opposite this unpunched invert and so should be installed facing up in the trench) Joints to have Spigot and socket to be clean prior to joining | I | R |  |  | Subsoil Install Checklist, Photographs
3.06 | Install 450mm FarmBoss (temporary Additional Drainage) |  | MMA-DES-GEO-E1-SPC-3859 R2.6-Farmboss-Polypropylene-Pipe.pdf |  | Inspection | All FarmBoss. Subsoil Checklist completed for every independent section and minimum 100m length. |  | Laid on a minimum of 150 mm Bedding for 450 mm diameter. Prior to tracking heavy loads it is recommend at least 750mm of material is placed above the pipe. | I |  |  |  | Subsoil Install Checklist, Photographs
3.07 | Install Backfill Material |  | MMA-DES-GEO-E1-SPC-3859 Section 6 - NZTA F/5: 2000 |  | Inspection | All Subsoils. Subsoil Checklist completed for every independent section and minimum 100m length. |  | Not less than 300mm drainage aggregate cover or as per Dwg Main Gully - 20mm Drainage Aggregate Side Gully - 20mm Drainage Aggregate | I | R |  |  | Subsoil Install Checklist, Photographs
3.08 | Install Vertical Subsoils and Connections |  | MMA-DES-GEO-E1-SPC-3859 |  | Inspection | All Subsoils. Subsoil Checklist completed for every independent section and minimum 100m length. |  | 110mm NEXUS HI-WAY as per drawings | I | R |  |  | Subsoil Install Checklist, Photographs
3.09 | Install Additional Vertical Subsoils |  | MMA-DES-GEO-E1-SPC-3859 |  | Inspection | All Subsoils. Subsoil Checklist completed for every independent section and minimum 100m length. |  | Constructor to identify any significant water flows within natural topography and request designer to confirm if install is required | I | R |  |  | Subsoil Install Checklist, Photographs, As built Formal correspondence
3.1 | Wrap Geotextile |  | MMA-DES-GEO-E1-SPC-3859 Bidim-Storage-Installation-Guide-M142-10-14-NZ.pdf |  | Inspection | All Geotextiles. Subsoil Checklist completed for every independent section and minimum 100m length. |  | Installed in area as per drawings, 300mm minimum lap. | I | R |  |  | Subsoil Install Checklist, Photographs
3.11 | Lay protective Fill Layer over Lapped Geotextile to allow plant to Run over top |  | MMA-DES-GEO-E1-SPC-3859 BIDIM - Storage & Installation Guide |  | Inspection | All Subsoils. Subsoil Checklist completed for every independent section and minimum 100m length. |  | Cover above Geotextile 150mm minimum for firm foundations and 300mm minimum for soft foundations (NB - 750mm cover required above FarmBoss) Material Compliant as per earthworks spec | I |  |  |  | Subsoil Install Checklist, Photographs
3.12 | Construct Outlet structures |  | MMA-DES-GEO-E1-SPC-3859 Section 10.2 |  | Inspection | All Subsoils. Subsoil Checklist completed for every independent section and minimum 100m length. |  | Extend 100mm into Manhole Structure. OR Fills 12 & 13 terminate at least 1.0m from finished fill profile | I |  |  |  | Subsoil Install Checklist, Photographs
4.0 Post Construction
4.01 | Completion of works |  | MMA-DES-GEO-E1-SPC-3859 & IFC drawings |  | Inspection | All Subsoils |  | Ensure the Subsoil and Drainage Backfill Material is below the finished fill surface as per plans and that the farmboss is capped at completion of use | I | R |  |  | Subsoil Install Checklist, Photographs
4.02 | Provide Maintenance and Inspection Report/As Built |  | MMA-DES-GEO-E1-SPC-3859 |  | Maintenance and Inspection Report Completed | All Subsoils |  | Detail location of all drainage outlets, flushing points, and associated features that require maintenance and inspection. Drawings showing locations and extent of drainage. Electronic images (photographs) of outlets and features shall be provided. As Built every 100m of Subsoil & FarmBoss. As Built all Joints of Subsoil and FarmBoss | I | R |  |  | As Built Plan Redline markup