## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-003 – Subsoil Drainage Install | itp |  |  |  | Yes | ITP-003 - Subsoil Drainage Install | a8522bb4-ee4b-4459-b361-a9f54ede29bc
section | 1.0 Pre-Construction
checkpoint | 1.01 - Confirm Method Statement Signed off
label | Method/Description - Document Review
label | Test frequency - Prior to Work, Once
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Signed Copy of Method Statement
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.02 - Confirm Compliance against Resource Consent & Management Plans
label | Method/Description - Document Review
label | Test frequency - Prior to Work, Once
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Signed Management Plans, Approved SCWMP and Approved CWP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.03 - Confirm IFC Design is in place
label | Method/Description - Document Review
label | Test frequency - Prior to Work, Once
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - IFC Drawings Issued
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.04 - Complete Permit To Dig
label | Method/Description - Document Production
label | Test frequency - All Excavation works
label | Contractor - H
label | Verifying Records Checklists, Test and Supplier Certificates - Permit to Dig Form
section | 2.0 Material Compliance
checkpoint | 2.01 - Order Subsoil Pipes
label | Method/Description - Ensure Pipes are ordered as per drawing
label | Test frequency - All Subsoils
label | Contractor - R, I
label | Verifying Records Checklists, Test and Supplier Certificates - Delivery Dockets, Material Complaince Certifcate/Data Sheets, Material Delivery Inspection Checksheet
checkpoint | 2.02 - Order Geotextile Material
label | Method/Description - Document Review
label | Test frequency - All Geotextiles
label | Contractor - R, I
label | Verifying Records Checklists, Test and Supplier Certificates - Material Complaince Certifcate/Data Sheets, Delivery Dockets
checkpoint | 2.03 - Order Subsoil Drainage Backfill Material
label | Method/Description - Laboratory Testing
label | Test frequency - All Material
label | Contractor - R
label | Designer - H
label | Lab - R
label | Verifying Records Checklists, Test and Supplier Certificates - PSD Results, Permeability Test Results, Crushing Resistance Test, RFI - Confirmation of Material acceptance from Designers
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.04 - Order FarmBoss Pipes (Temporary Drainage)
label | Method/Description - Document Review, Material Delivery Inspection
label | Test frequency - All Pipe
label | Contractor - R, I
label | Verifying Records Checklists, Test and Supplier Certificates - Delivery Docket, Material Delivery Inspection Checksheet
section | 3.0 During Construction
checkpoint | 3.01 - Clearing and Stripping of Area
label | Note: Fill 12 and 13 are exempt from Organic Waste Clearing and Stripping when >5m from finished ground level
label | Method/Description - Removal of Organic Material
label | Test frequency - All areas. Subsoil Checklist completed for every independent section and minimum 100m length.
label | Contractor - I
label | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
checkpoint | 3.02 - Formation Level Inspection
label | Method/Description - Visual
label | Test frequency - At formation level before installing the geotextile. First section of pipe and then once every 50 m of pipe laid.
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.03 - Lay Geotextile (BIDIM A29)
label | Method/Description - Inspection
label | Test frequency - All BIDIM. Subsoil Checklist completed for every independent section and minimum 100m length.
label | Contractor - H
label | Designer - R
label | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
checkpoint | 3.04 - Install Bedding Material for Subsoil
label | Method/Description - Inspection
label | Test frequency - All Subsoils. Subsoil Checklist completed for every independent section and minimum 100m length.
label | Contractor - I
label | Designer - R
label | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
checkpoint | 3.05 - Install Main Gully Subsoil
label | Method/Description - Inspection
label | Test frequency - All Subsoils. Subsoil Checklist completed for every independent section and minimum 100m length.
label | Contractor - I
label | Designer - I
label | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
checkpoint | 3.06 - Install 450mm FarmBoss (temporary Additional Drainage)
label | Method/Description - Inspection
label | Test frequency - All FarmBoss. Subsoil Checklist completed for every independent section and minimum 100m length.
label | Contractor - I
label | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
checkpoint | 3.07 - Install Backfill Material
label | Method/Description - Inspection
label | Test frequency - All Subsoils. Subsoil Checklist completed for every independent section and minimum 100m length.
label | Contractor - I
label | Designer - R
label | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
checkpoint | 3.08 - Install Vertical Subsoils and Connections
label | Method/Description - Inspection
label | Test frequency - All Subsoils. Subsoil Checklist completed for every independent section and minimum 100m length.
label | Contractor - I
label | Designer - R
label | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
checkpoint | 3.09 - Install Additional Vertical Subsoils
label | Method/Description - Inspection
label | Test frequency - All Subsoils. Subsoil Checklist completed for every independent section and minimum 100m length.
label | Contractor - I
label | Designer - R
label | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs, As built, Formal correspondence
checkpoint | 3.10 - Wrap Geotextile
label | Method/Description - Inspection
label | Test frequency - All Geotextiles. Subsoil Checklist completed for every independent section and minimum 100m length.
label | Contractor - I
label | Designer - R
label | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
checkpoint | 3.11 - Lay protective Fill Layer over Lapped Geotextile to allow plant to Run over top
label | Method/Description - Inspection
label | Test frequency - All Subsoils. Subsoil Checklist completed for every independent section and minimum 100m length.
label | Contractor - I
label | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
checkpoint | 3.12 - Construct Outlet structures
label | Method/Description - Inspection
label | Test frequency - All Subsoils. Subsoil Checklist completed for every independent section and minimum 100m length.
label | Contractor - I
label | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
section | 4.0 Post Construction
checkpoint | 4.01 - Completion of works
label | Method/Description - Inspection
label | Test frequency - All Subsoils
label | Contractor - I
label | Designer - R
label | Verifying Records Checklists, Test and Supplier Certificates - Subsoil Install Checklist, Photographs
checkpoint | 4.02 - Provide Maintenance and Inspection Report/As Built
label | Method/Description - Maintenance and Inspection Report Completed
label | Test frequency - All Subsoils
label | Contractor - I
label | Designer - R
label | Verifying Records Checklists, Test and Supplier Certificates - As Built Plan, Redline markup