## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Rough In |  |  |  |  | Yes | Rough In | 015120eb-ed5d-4483-ae06-d17780bcaedb
checkpoint-status |  |  | checkpoint | Cavity pockets installed
checkpoint-status |  |  | checkpoint | Mark Out Noggins - Bathrooms, TV, Tablet Mount
checkpoint-status |  |  | checkpoint | Install Window Reveals
checklist-flat |  |  | checklist | Rough In (Cavity Pockets & PMJ) |  |  |  |  | Yes | Rough In (Cavity Pockets & PMJ) | 0de2fc2d-2a9c-4b51-9a4c-483351c078b3
checkpoint-status |  |  | checkpoint | Cavity pockets installed
checkpoint-status |  |  | checkpoint | Add pressed metal jamb
checklist-flat |  |  | checklist | Rough In (Cavity Pockets Only) |  |  |  |  | Yes | Rough In (Cavity Pockets Only) | 400ca255-c6eb-475e-9c6f-3df43583f90d
checkpoint-status |  |  | checkpoint | Cavity pockets installed
checklist-flat |  |  | checklist | Fit Off |  |  |  |  | Yes | Fit Off | 6460b8f0-a2bf-4e64-a9ea-747b4705aa98
checkpoint-status |  |  | checkpoint | Installation of door hardware and door closes sufficiently
checkpoint-status |  |  | checkpoint | Bathroom and toilet vanity installed
checkpoint-status |  |  | checkpoint | Handrails, toilet rolls and towel rails installed
checkpoint-status |  |  | checkpoint | Entry door hardware installed and closes sufficiently
checkpoint-status |  |  | checkpoint | Fire tags installed on the door and door jamb
checkpoint-status |  |  | checkpoint | Shower trays installed
checkpoint-status |  |  | checkpoint | Area left clean and tidy (attach photo)
checkpoint-status |  |  | checkpoint | All work 100% completed to required specifications
checklist-flat |  |  | checklist | Rough In (Cavity Pockets & PMJ) |  |  |  |  | Yes | B03/B04 - Rough In (Cavity Pockets & PMJ) | 753c9255-575d-493e-b6df-dc6e570f890a
checkpoint-status |  |  | checkpoint | Cavity pockets installed
checkpoint-status |  |  | checkpoint | Install pressed metal jamb
checklist-flat |  |  | checklist | Rough In - Apartments |  |  |  |  | Yes | B03/B04 - Rough In - Apartments | a5391898-dcd7-4e01-a1ae-195bb2fb6602
checkpoint-status |  |  | checkpoint | Cavity pockets installed
checkpoint-status |  |  | checkpoint | Install laundry stackers
checkpoint-status |  |  | checkpoint | Add bathroom noggins
checkpoint-status |  |  | checkpoint | Add window noggins
checklist-flat |  |  | checklist | Common Area Checklist |  |  |  |  | Yes | Common Area Checklist | bbd81f08-140a-40e2-971b-1377bc300f03
checkpoint-status |  |  | checkpoint | Installation of skirting
checkpoint-status |  |  | checkpoint | Installation of architraves
checkpoint-status |  |  | checkpoint | Installation of dado rail
checkpoint-status |  |  | checkpoint | Installation of arcade joinery (where required)
checkpoint-status |  |  | checkpoint | Installation of fire doors
checkpoint-status |  |  | checkpoint | Installation of all door hardware & door closes sufficiently
checkpoint-status |  |  | checkpoint | Fire tags installed on the door and door jamb
checkpoint-status |  |  | checkpoint | Area left clean and tidy (attach photo)
checkpoint-status |  |  | checkpoint | All work 100% completed to required specifications
checklist-flat |  |  | checklist | Common Area Checklist |  |  |  |  | Yes | Common Area Checklist | be0fd10a-c1a7-4334-9e35-6ef4839b54c0
checkpoint-status |  |  | checkpoint | Installation of door hardware
checkpoint-status |  |  | checkpoint | Installation of skirting
checkpoint-status |  |  | checkpoint | Installation of architraves
checkpoint-status |  |  | checkpoint | Installation of dado rail
checkpoint-status |  |  | checkpoint | Installation of arcade joinery (where required)
checkpoint-status |  |  | checkpoint | Installation of smoke doors
checkpoint-status |  |  | checkpoint | Installation of fire doors
checkpoint-status |  |  | checkpoint | Fire tags installed on the door and door jamb
checkpoint-status |  |  | checkpoint | Area left clean and tidy (attach photo)
checkpoint-status |  |  | checkpoint | All work 100% completed to required specifications
checklist-flat |  |  | checklist | Handover |  |  |  |  | Yes | Handover | caf59254-f9c4-45a8-93a9-774727955b0e
checkpoint-status |  |  | checkpoint | All aspects of works completed and inspected by Ryman Foreman
checkpoint-status |  |  | checkpoint | Any rectification works have been carried out if required
checkpoint-status |  |  | checkpoint | Site left clean and tidy - All excess spoil and materials removed
checkpoint-status |  |  | checkpoint | General photos/comments/observations of Site Prior to Handover
holdpoint |  |  | signoff | ENSURE ALL CHECKPOINTS ARE SATISFACTORILY COMPLETED
checklist-flat |  |  | checklist | Rough In (PMJ Only) |  |  |  |  | Yes | Rough In (PMJ Only) | d170e62b-1f48-4623-88ac-48f2998cca0c
checkpoint-status |  |  | checkpoint | Add pressed metal jamb
checklist-flat |  |  | checklist | Care/ALS Fit Off Checklist |  |  |  |  | Yes | Care/ALS Fit Off Checklist | d8f42fe3-58c3-45f5-ad89-0660de212459
checkpoint-status |  |  | checkpoint | Installation of door hardware and door closes sufficiently
checkpoint-status |  |  | checkpoint | Bathroom and toilet vanity installed
checkpoint-status |  |  | checkpoint | Handrails, toilet rolls and towel rails installed
checkpoint-status |  |  | checkpoint | Entry door hardware installed and closes sufficiently
checkpoint-status |  |  | checkpoint | Fire tags installed on the door and door jamb
checkpoint-status |  |  | checkpoint | Shower trays installed
checkpoint-status |  |  | checkpoint | Install TV Brackets, Tablet Mounts
checkpoint-status |  |  | checkpoint | Area left clean and tidy (attach photo)
checkpoint-status |  |  | checkpoint | All work 100% completed to required specifications
checklist-flat |  |  | checklist | Installation |  |  |  |  | Yes | Installation | fd185a2a-b6e3-483a-9395-65c555d2404e
checkpoint-status |  |  | checkpoint | Internal doors hung
checkpoint-status |  |  | checkpoint | Skirting installed
checkpoint-status |  |  | checkpoint | Cavity doors installed
checkpoint-status |  |  | checkpoint | Window architraves installed
checkpoint-status |  |  | checkpoint | Wardrobe jamb installed
checkpoint-status |  |  | checkpoint | Entry door hung
checkpoint-status |  |  | checkpoint | All install work 100% completed to required specifications
checkpoint-status |  |  | checkpoint | Area left clean and tidy (attach photo)