## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | CS-4012 - MSE Wall Geogrid Checklist | [5 empty] | CS-4012 - MSE Wall Geogrid Checklist
section | Details
checkpoint-no-status | Details
textbox | Work Area:
textbox | Sub Work Area:
textbox | Lot:
textbox | Sublot:
date | Document Date:
textbox | Created By:
textbox | Structure Name:
textbox | Drawing No:
textbox | Grid Layer Number:
textbox | Structure Location:
textbox | Drawing Rev No:
textbox | Grid RL:
section | Conformance Criteria
checkpoint | Check installation of each course
label | No gaps between adjacent units, max. vertical height prior to backfill is 2 units, min. pin connections per block is 2 upper and 2 lower.
textbox | Initials:
date | Date:
checkpoint | Confirm front face alignment in each course is within the allowable tolerance
textbox | Initials:
date | Date:
checkpoint | Inspect wall batter, wall batter to be within 2 degrees of design batter.
textbox | Initials:
date | Date:
checkpoint | Confirm density results before placing Geogrid layer
textbox | Initials:
date | Date:
checkpoint | Confirm the type of Geogrid
textbox | Initials:
date | Date:
checkpoint | Confirm the correct length of Geogrid
label | Inspect bodkin joints (where used) to join shorter pieces of Geogrid, 1 max. per length of Geogrid.
textbox | Initials:
date | Date:
checkpoint | Confirm the correct elevation of Geogrid.
label | Place within 75mm of design elevation
textbox | Initials:
date | Date:
checkpoint | Ensure Geogrid is placed flat on top of the compacted layer
textbox | Initials:
date | Date:
checkpoint | Ensure Geogrid is connected correctly to the block pin connectors.
label | Max horizontal distance between geogrids at wall face is 10mm
textbox | Initials:
date | Date:
checkpoint | Ensure plant does not track over Geogrid
textbox | Initials:
date | Date:
checkpoint | Tension geogrid and peg to hold geogrid tight
textbox | Initials:
date | Date:
checkpoint | Place backfill across the geogrid, plant can track onto geogrid when 150mm min backfill has been placed
textbox | Initials:
date | Date:
checkpoint | Monitor plant and equipment keep 1m from front face of wall.
textbox | Initials:
date | Date:
checkpoint | Design Engineer inspection?
textbox | Initials:
date | Date:
checkpoint-no-status | Comments:
checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
label | Position: Site Engineer
textbox | Site Engineer - Name:
date | Site Engineer - Date:
label | Position: Design Engineer
textbox | Site Engineer - Name:
date | Site Engineer - Date:
label | (Note: Attach a sketch showing grid on a separate sheet as necessary)
holdpoint | Sign