## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | CS-4025 - Drainage Line Record | [5 empty] | CS-4025 - Drainage Line Record
section | Details
checkpoint-no-status | Details
textbox | Drawing No (& Rev No):
textbox | Drainage Line:
radio | HS3 / HS2 / H2 | HS3,HS2,H2
date | Date:
section | Inspection Stage
checkpoint | Set out by surveyor & handover to subcontractor completed
textbox | Initials:
date | Date:
checkpoint | Start point (i.e. manhole/headwall) checked for line & level prior to commencing this drainage line
textbox | Initials:
date | Date:
checkpoint | Foundation Undercut Compaction base of trench subgrade Scalas taken every __m
textbox |  |  |  | m
textbox | Initials:
date | Date:
label | Comments:
radio | Under cut required? | Yes,No
textbox | Depth:
checkpoint | Bedding Zone Compaction Testing every __m
textbox |  |  |  | m
textbox | Initials:
date | Date:
label | Comments:
textbox | Material:
checkpoint | Engineer to inspect base of trench
textbox | Initials:
date | Date:
checkpoint | Trench width per __m culvert line
textbox |  |  |  | m
textbox | Initials:
date | Date:
checkpoint | Pipe Laying Inspected and approved by Site Engineer
textbox | Initials:
date | Date:
checkpoint | All Connections completed and inspected as per specifications
textbox | Initials:
date | Date:
label | Comments:
textbox | Structure (In):
textbox | Structure (Out):
checkpoint | Haunch Zone Compaction Testing every __m
textbox |  |  |  | m
textbox | Initials:
date | Date:
label | Comments:
textbox | Material:
checkpoint | Side Zone Compaction Testing every __m
textbox |  |  |  | m
textbox | Initials:
date | Date:
label | Comments:
textbox | Material:
checkpoint | Manhole Conections to Pipe Joints Haunched/Concreted/Epoxied
textbox | Initials:
date | Date:
checkpoint | CCTV Completed and passed
textbox | Initials:
date | Date:
checkpoint | Water tightness test passed
textbox | Initials:
date | Date:
checkpoint | Final visual Inspection Completed and approved by Engineer
textbox | Initials:
date | Date:
radio | Invitation to inspect: | Accepted,Declined
label | Design Team
textbox | Design Team - Rep:
date | Design Team - Date:
checkpoint-no-status | Comments:
checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
textbox | Name:
textbox | Position:
date | Date:
holdpoint | Sign
section | Drainage Line Record
checkpoint-no-status | Direction of Flow
radio | Indicate Direction of Flow | <,>
checkpoint-no-status | Invert Level (In)
textbox | Design:
textbox | As-Built:
checkpoint-no-status | Invert Level (Out)
textbox | Design:
textbox | As-Built:
checkpoint-no-status | Structure (1)
textbox | Structure Name:
label | Status: New
textbox | (New) Dia:
label | (New) Type: MH
textbox | (New) Distance to Flexi Joint:
textbox | (New) Epoxied:
textbox | (New) Water tight:
textbox | (New) Depth: |  |  | (Measured from MH Base to underside of Concrete Lid).
textbox | (New) Throat Depth: |  |  | (Measured from underside of concrete lid to finished final lid level (FSL)).
label | Status: Existing
textbox | (Existing) Dia:
label | (Existing) Type: WW
textbox | (Existing) Distance to Flexi Joint:
textbox | (Existing) Epoxied:
textbox | (Existing) Water tight:
textbox | (Existing) Depth: |  |  | (Measured from MH Base to underside of Concrete Lid).
textbox | (Existing) Throat Depth: |  |  | (Measured from underside of concrete lid to finished final lid level (FSL)).
checkpoint-no-status | Pipe Details
textbox | (1) Dia:
textbox | (1) Length:
textbox | (1) Material:
textbox | (1) Class:
date | (1) Test Date:
label | (1) Air test: Pass
textbox | (2) Dia:
textbox | (2) Length:
textbox | (2) Material:
textbox | (2) Class:
date | (2) Test Date:
label | (2) Air test: Fail
checkpoint-no-status | Structure (2)
textbox | Structure Name:
label | Status: New
textbox | (New) Dia:
label | (New) Type: MH
textbox | (New) Distance to Flexi Joint:
textbox | (New) Epoxied:
textbox | (New) Water tight:
textbox | (New) Depth: |  |  | (Measured from MH Base to underside of Concrete Lid).
textbox | (New) Throat Depth: |  |  | (Measured from underside of concrete lid to finished final lid level (FSL)).
label | Status: Existing
textbox | (Existing) Dia:
label | (Existing) Type: WW
textbox | (Existing) Distance to Flexi Joint:
textbox | (Existing) Epoxied:
textbox | (Existing) Water tight:
textbox | (Existing) Depth: |  |  | (Measured from MH Base to underside of Concrete Lid).
textbox | (Existing) Throat Depth: |  |  | (Measured from underside of concrete lid to finished final lid level (FSL)).
checkpoint-no-status | MATERIAL TYPES AND SOURCE
textbox | Undercut Depth:
textbox | Undercut Depth - Type:
textbox | Undercut Depth - Source:
textbox | Bedding, Haunch & Side Zone Depth:
textbox | Bedding, Haunch & Side Zone Depth - Type:
textbox | Bedding, Haunch & Side Zone Depth - Source:
textbox | Backfill Depth:
textbox | Backfill Depth - Type:
textbox | Backfill Depth - Source:
textbox | Design Grade:
textbox | As-Built Grade:
section | Connections
checkpoint-no-status | 1
textbox | Distance (m)
textbox | Dia (mm)
textbox | Depth @ BDY
textbox | House / Lot No.
textbox | Length (m)
checkpoint-no-status | 2
textbox | Distance (m)
textbox | Dia (mm)
textbox | Depth @ BDY
textbox | House / Lot No.
textbox | Length (m)
checkpoint-no-status | 3
textbox | Distance (m)
textbox | Dia (mm)
textbox | Depth @ BDY
textbox | House / Lot No.
textbox | Length (m)
checkpoint-no-status | 4
textbox | Distance (m)
textbox | Dia (mm)
textbox | Depth @ BDY
textbox | House / Lot No.
textbox | Length (m)
checkpoint-no-status | 5
textbox | Distance (m)
textbox | Dia (mm)
textbox | Depth @ BDY
textbox | House / Lot No.
textbox | Length (m)
checkpoint-no-status | 6
textbox | Distance (m)
textbox | Dia (mm)
textbox | Depth @ BDY
textbox | House / Lot No.
textbox | Length (m)
checkpoint-no-status | 7
textbox | Distance (m)
textbox | Dia (mm)
textbox | Depth @ BDY
textbox | House / Lot No.
textbox | Length (m)
checkpoint-no-status | 8
textbox | Distance (m)
textbox | Dia (mm)
textbox | Depth @ BDY
textbox | House / Lot No.
textbox | Length (m)
checkpoint-no-status | 9
textbox | Distance (m)
textbox | Dia (mm)
textbox | Depth @ BDY
textbox | House / Lot No.
textbox | Length (m)
checkpoint-no-status | 10
textbox | Distance (m)
textbox | Dia (mm)
textbox | Depth @ BDY
textbox | House / Lot No.
textbox | Length (m)
checkpoint-no-status | 11
textbox | Distance (m)
textbox | Dia (mm)
textbox | Depth @ BDY
textbox | House / Lot No.
textbox | Length (m)
checkpoint-no-status | 12
textbox | Distance (m)
textbox | Dia (mm)
textbox | Depth @ BDY
textbox | House / Lot No.
textbox | Length (m)
checkpoint-no-status | 13
textbox | Distance (m)
textbox | Dia (mm)
textbox | Depth @ BDY
textbox | House / Lot No.
textbox | Length (m)
checkpoint-no-status | 14
textbox | Distance (m)
textbox | Dia (mm)
textbox | Depth @ BDY
textbox | House / Lot No.
textbox | Length (m)
checkpoint-no-status | 15
textbox | Distance (m)
textbox | Dia (mm)
textbox | Depth @ BDY
textbox | House / Lot No.
textbox | Length (m)
checkpoint-no-status | 16
textbox | Distance (m)
textbox | Dia (mm)
textbox | Depth @ BDY
textbox | House / Lot No.
textbox | Length (m)
checkpoint-no-status | 17
textbox | Distance (m)
textbox | Dia (mm)
textbox | Depth @ BDY
textbox | House / Lot No.
textbox | Length (m)
checkpoint-no-status | 18
textbox | Distance (m)
textbox | Dia (mm)
textbox | Depth @ BDY
textbox | House / Lot No.
textbox | Length (m)
checkpoint-no-status | 19
textbox | Distance (m)
textbox | Dia (mm)
textbox | Depth @ BDY
textbox | House / Lot No.
textbox | Length (m)
checkpoint-no-status | 20
textbox | Distance (m)
textbox | Dia (mm)
textbox | Depth @ BDY
textbox | House / Lot No.
textbox | Length (m)
checkpoint-no-status | 21
textbox | Distance (m)
textbox | Dia (mm)
textbox | Depth @ BDY
textbox | House / Lot No.
textbox | Length (m)
checkpoint-no-status | 22
textbox | Distance (m)
textbox | Dia (mm)
textbox | Depth @ BDY
textbox | House / Lot No.
textbox | Length (m)
checkpoint-no-status | 23
textbox | Distance (m)
textbox | Dia (mm)
textbox | Depth @ BDY
textbox | House / Lot No.
textbox | Length (m)
checkpoint-no-status | 24
textbox | Distance (m)
textbox | Dia (mm)
textbox | Depth @ BDY
textbox | House / Lot No.
textbox | Length (m)
checkpoint-no-status | 25
textbox | Distance (m)
textbox | Dia (mm)
textbox | Depth @ BDY
textbox | House / Lot No.
textbox | Length (m)
checkpoint-no-status | 26
textbox | Distance (m)
textbox | Dia (mm)
textbox | Depth @ BDY
textbox | House / Lot No.
textbox | Length (m)
checkpoint-no-status | 27
textbox | Distance (m)
textbox | Dia (mm)
textbox | Depth @ BDY
textbox | House / Lot No.
textbox | Length (m)
checkpoint-no-status | 28
textbox | Distance (m)
textbox | Dia (mm)
textbox | Depth @ BDY
textbox | House / Lot No.
textbox | Length (m)
checkpoint-no-status | 29
textbox | Distance (m)
textbox | Dia (mm)
textbox | Depth @ BDY
textbox | House / Lot No.
textbox | Length (m)
checkpoint-no-status | 30
textbox | Distance (m)
textbox | Dia (mm)
textbox | Depth @ BDY
textbox | House / Lot No.
textbox | Length (m)
checkpoint-no-status | 31
textbox | Distance (m)
textbox | Dia (mm)
textbox | Depth @ BDY
textbox | House / Lot No.
textbox | Length (m)
checkpoint-no-status | 32
textbox | Distance (m)
textbox | Dia (mm)
textbox | Depth @ BDY
textbox | House / Lot No.
textbox | Length (m)