## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | CS-4076 - Asphalt Laying Checklist | [5 empty] | CS-4076 - Asphalt Laying Checklist
section | Pre Laying (Tasks 1-7)
checkpoint | Final confirmation job is ready (Site Handover, Job Instruction sheet)
checkpoint | Undertake Emulsion Tack Coat Risk Assessment
label | By Who: Foreman
checkpoint | Confirm job matches Laying Plan. If not, confirm and communicate variation with manager/ customer
label | By Who: Foreman
checkpoint | Visual Inspection of site and stringlines completed as per Site Handover
checkpoint | Daily Pre-Start Meeting/Hazard ID completed
checkpoint | Approved Traffic Management Plan on site (implemented and effective)
checkpoint | Vehicle Movement Plan
checkpoint | Fences, walls, kerbs protected and environmental controls in place
checkpoint | Pre-seal prep including offset of services/ roadmarking and protection of fixtures
checkpoint | Laying Plan and Rolling pattern confirmed
checkpoint | Paver setup. Screed checked at start of the day (level and feed controls functional)
checkpoint | Stringline Tie in points to calculate required asphalt thickness
checkpoint | Starting blocks in place (including compaction allowance)
section | During Laying (Tasks 8-9)
checkpoint | Tack coat applied and cured
checkpoint | Mix visually inspected and the ‘in hopper’ temperature is within tolerances (contract-specific)
checkpoint | Mat depth control (contract-specific)
checkpoint | Stringline Tie in points for correct depth
checkpoint | Rollers working to agreed pattern
checkpoint | Shape and levels achieved as per specification
checkpoint | QA forms completed as per Job Instruction form
section | Post Laying (Tasks 10-11)
checkpoint | Measure and record area, quantities and spread rate
checkpoint | Post-paving subcontractors notified
checkpoint | Collate QA forms and supporting documentation (refer Job Instruction)
checkpoint | Post paving as-builts, coring, survey
checkpoint | Plant de-established and off-hired as appropriate
checkpoint | Roadmarking checked and completed
checkpoint | Traffic loops / counter loops reinstated
checkpoint | Traffic management de-established
checkpoint | Services exposed, raised and painted
checkpoint | (hydrants, valves, manholes)
checkpoint | Job site safe and tidy
checkpoint | Job site tidy. All AC piles picked up. Kerbs chipped and swept. Drains checked for AC. No footprints left in gardens/berms
checkpoint | Transition joins/tie ins are tight and flush (no high/low ridges, no risk of plucking out).
checkpoint | Longitudinal and fresh joins are all tight and flush (no high/low ridges, no risk of plucking out – water running freely across joins).
checkpoint | Kerbs – height/finish requirements met across 100% of job (refer Job Instruction)
checkpoint | Ride Quality – Drive over site - no bumps can be felt
checkpoint | No visible surface defects (roller / stretch marks)
section | General comments
checkpoint-no-status | General comments:
label | Score Guideline (record comments/details)
label | 1 - Not Acceptable (remedial/rework required, advise Manager)
label | 2 - Acceptable (no obvious problems, can be handed over to client)
label | 3 - Excellent (entire job above standard)
checkpoint-no-status | Job quantities/spread rate
textbox | Hand lay (H), Paver lay (P)
textbox | Mix Type
textbox | Area (m2)
textbox | Depth as per Job Sheet
textbox | Tonnes Purchased
textbox | Wastage Tonnes
textbox | Tonnes Laid
textbox | Average Depth (mm)
textbox | Emulsion Primer (l)
label | Depth = Tonnes ÷ Conversion Factor (Density) ÷ area (m2)
checkpoint | Signoff
textbox | Signed by Foreman:
date | Signed by Foreman - Date:
textbox | Reviewed by Manager:
date | Reviewed by Manager - Date:
holdpoint | SIGNATURE