## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | CS-4077 - Light Column Installation Record | [5 empty] | CS-4077 - Light Column Installation Record
section | Details
checkpoint-no-status | Details
textbox | Drawing No:
textbox | Pole No:
section | Column Foundation
checkpoint | Confirm Light Pole Locations are as per latest Drawing revision and does not clash with other Services.
textbox | Initials:
date | Date:
label | Comments: Design Engineer to approve if the location needs to be moved.
textbox | OFI No:
checkpoint | Check Survey Setout and Setbacks are to the dimensions as detailed on drawings.
textbox | Initials:
date | Date:
checkpoint | Confirm Foundation Type i.e. Ground plant, Barrier mount etc.
textbox | Initials:
date | Date:
section | Excavation
checkpoint | Pothole existing services within close proximity to the foundation.
textbox | Initials:
date | Date:
checkpoint | Ensure permit to dig is in place.
textbox | Initials:
date | Date:
checkpoint | Check depth and diameter at completion.
textbox | Initials:
date | Date:
checkpoint | Ensure base of shaft is clean and dry.
textbox | Initials:
date | Date:
checkpoint | If fixing onto barrier ensure bolts drilled to correct depth.
textbox | Initials:
date | Date:
section | Concreting & Backfilling
checkpoint | Check the location, orientation, level and verticality of foundation prior to pouring/backfilling.
textbox | Initials:
date | Date:
checkpoint | Ensure 1 x 65mm dia flexi duct is installed and taped off at each end.
textbox | Initials:
date | Date:
checkpoint | Design Engineer inspected the foundation prior to pouring
textbox | Initials:
date | Date:
checkpoint | Order concrete for shear base, ensure correct mix delivered, correct slump, concrete vibrated, dockets collected
textbox | Initials:
date | Date:
label | Comments:
textbox | Concrete strength |  |  | Mpa
label | Attach delivery dockets and write the road light column numbers on the docket
checkpoint | Suitable backfill material to be placed and tampered for compaction
textbox | Initials:
date | Date:
checkpoint | Concrete/backfill placed to just below the shear base and concrete splashes onto column washed off.
textbox | Initials:
date | Date:
checkpoint | At the completion of the concreting/backfilling check the foundation location, level, verticality and height from FRL.
textbox | Initials:
date | Date:
label | Comments: Foundation may have moved during concreting/backfilling
section | Installing Column & Outreach
checkpoint | Ensure concrete foundation has been left for min. 3 days before erecting road light column
textbox | Initials:
date | Date:
checkpoint | Check road light column for any damage
textbox | Initials:
date | Date:
label | Comments: Do not install if damaged
checkpoint | Assemble Light column on the ground (protect column by blocking off the ground)
textbox | Initials:
date | Date:
label | Comments:
textbox | Column Type:
textbox | Outreach Type:
textbox | Outreach Length:
textbox | Luminaire Type:
checkpoint | Check all bolts on shear bases have been torqued
textbox | Initials:
date | Date:
label | Comments: Adjust column to ensure vertical
checkpoint | Check orientation of road light column and outreach
textbox | Initials:
date | Date:
label | Comments: Torque to 200kPa, check the bolt and slack back to 100kPa
checkpoint | Check the internal wiring of the road lighting column. Ensure 2.5mm2 cables, 2 core NS
textbox | Initials:
date | Date:
checkpoint | Check Connectors & Earth Conductors have been installed
textbox | Initials:
date | Date:
checkpoint | Danger Live Wires sticker on gear door
textbox | Initials:
date | Date:
checkpoint | Check that the Road light is installed to the design height above road level
textbox | Initials:
date | Date:
label | Comments:
textbox | Laser Measurement:
textbox | Design Measurement:
label | Tolerance = +/-500mm
section | Signoff
checkpoint-no-status | Comments:
checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
label | Position: Site Engineer
textbox | Site Engineer - Name:
date | Site Engineer - Date:
label | Position: Design Engineer
textbox | Design Engineer - Name:
date | Design Engineer - Date:
holdpoint | SIGN