## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | CS-4078 - Signal Pole Installation Record | [5 empty] | CS-4078 - Signal Pole Installation Record
section | Details
checkpoint-no-status | Details
textbox | Drawing No:
textbox | Pole No:
section | Pole Footing
checkpoint | Confirm signal pole locations are as per latest Drawing revision and does not clash with other Services.
textbox | Initials:
date | Date:
label | Comments: Design Engineer to approve if the location needs to be moved.
checkpoint | Check Survey Setout and Setbacks are to the dimensions as detailed on drawings.
textbox | Initials:
date | Date:
checkpoint | Footing Type
textbox | Initials:
date | Date:
label | Comments:
label | ○ RS 115
label | ○ RS 168
section | Excavation
checkpoint | Pothole existing services within close proximity to the foundation.
textbox | Initials:
date | Date:
section | Socket / Flange Installation
checkpoint | Ensure duct is connected to socket.
textbox | Initials:
date | Date:
checkpoint | Design Engineer inspected the foundation prior to pouring
textbox | Initials:
date | Date:
checkpoint | Prepour checksheet completed
textbox | Initials:
date | Date:
checkpoint | Order concrete for footing, ensure correct mix delivered, correct slump, concrete vibrated, dockets collected
textbox | Initials:
date | Date:
label | Comments:
textbox | Concrete strength |  |  | MPa
label | Attach delivery dockets and write the road light column numbers on the docket
checkpoint | Use a stump pole to check verticality and height from FRL.
textbox | Initials:
date | Date:
section | Installing Signal Pole
checkpoint | Ensure concrete foundation has been left for min. 3 days before erecting signal pole
textbox | Initials:
date | Date:
checkpoint | Check signal pole for any damage
textbox | Initials:
date | Date:
label | Comments: Do not install if damaged
checkpoint | Assemble signal pole on the ground (protect column by blocking off the ground)
textbox | Initials:
date | Date:
label | Comments:
textbox | Pole Type:
textbox | P43 DWG:
checkpoint | Check orientation of signal lanterns
textbox | Initials:
date | Date:
checkpoint | Pole identification completed
textbox | Initials:
date | Date:
section | Signoff
checkpoint-no-status | Comments:
checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
label | Position: Site Engineer
textbox | Site Engineer - Name:
date | Site Engineer - Date:
label | Position: Design Engineer
textbox | Design Engineer - Name:
date | Design Engineer - Date:
holdpoint | SIGN