## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | CS-4100 - Subgrade Approval Checksheet | [5 empty] | CS-4100 - Subgrade Approval Checksheet
checkpoint | Area completely stripped of topsoil & organics
textbox | Initials - Design Engineer:
date | Date:
label | Comments:
textbox | Chainage Start:
textbox | Finish:
label | Photos of area are taken & kept with QA records
checkpoint | Topsoil strip topo survey carried out
textbox | Initials - Site Engineer:
date | Date:
label | Comments:
textbox | Survey receipt #
checkpoint | Scala Penetrometer Test carried out
textbox | Initials - Site Engineer:
date | Date:
label | Comments: To the correct frequency & results captured on the earthwork lab testing register
checkpoint | Proof Roll carried out & witnessed
textbox | Initials - Design Engineer:
date | Date:
label | Comments:
textbox | Equipment used:
checkpoint | Did Proof Roll pass
textbox | Initials - Design Engineer:
date | Date:
label | Comments: If yes moved to #10, If not undercut required continue below
checkpoint | Undercut area is to be marked out onsite by Design Engineer
textbox | Initials - Design Engineer:
date | Date:
checkpoint | Undercut to be inspected before backfilling commences by Design Engineer
textbox | Initials - Design Engineer:
date | Date:
label | Comments: To determine that all undercut areas are prepared to the specifications
checkpoint | Undercut area to be surveyed
textbox | Initials - Site Engineer:
date | Date:
label | Comments:
textbox | Survey receipt #
checkpoint | Backfill material is approved to be used and is tested in accordance with specifications
textbox | Initials - Site Engineer:
date | Date:
label | Comments: Lab Test Result register
checkpoint | Site is prepared for bulk filling to commence
textbox | Initials - Site Engineer:
date | Date:
checkpoint-no-status | Comments:
checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
label | Position: Site Engineer
textbox | Site Engineer - Name:
date | Site Engineer - Date:
label | Position: Design Engineer
textbox | Design Engineer - Name:
date | Design Engineer - Date:
holdpoint | SIGN