## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | CS-4117 - Guardrail Installation Record | [5 empty] | CS-4117 - Guardrail Installation Record
section | DETAILS
checkpoint-no-status | Details
textbox | Work Area:
textbox | Sub Work Area:
textbox | Lot:
textbox | Sublot:
label | Document Date: 27/11/2019
label | Created By: Kirsty George
textbox | Drawing No:
textbox | Rev No:
textbox | Chainage:
section | Guardrail Installation
checkpoint | When driving post, use a driving cap with timber or plastic insert to avoid damage to the post
textbox | Initials:
date | Date:
checkpoint | Height to centre of rail is 635mm
textbox | Initials:
date | Date:
checkpoint | Top of post should be a minimum of 20mm above top of guardrail
textbox | Initials:
date | Date:
checkpoint | Post is aligned with flanges rail for road side applications and alignment is alternating for median applications
textbox | Initials:
date | Date:
checkpoint | There is a 90mm dia. Washer between rail and post.
textbox | Initials:
date | Date:
checkpoint | Rail is lapped in the direction of traffic
textbox | Initials:
date | Date:
checkpoint | All bolts are fully tightened
textbox | Initials:
date | Date:
checkpoint | Nut on backside of post is a splice nut
textbox | Initials:
date | Date:
checkpoint | If a median installation-excessive bolt length is cut off on backside
textbox | Initials:
date | Date:
checkpoint | That transition details to existing guardrail or terminations are correct
textbox | Initials:
date | Date:
checkpoint-no-status | Comments:
checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
label | Position: Site Engineer
textbox | Site Engineer - Name:
date | Site Engineer - Date:
label | Position: Design Engineer
textbox | Design Engineer - Name:
date | Design Engineer - Date:
holdpoint | SIGN
section | Thriebeam Installation
checkpoint | Panels are pre-bent to suite curves.
textbox | Initials:
date | Date:
checkpoint | The rail height is in accordance with the plans and specification.
textbox | Initials:
date | Date:
checkpoint | Correct lapping of rail away from the direction of Traffic.
textbox | Initials:
date | Date:
checkpoint | Timber block outs secured to the post.
textbox | Initials:
date | Date:
checkpoint | Rail is aligned and level.
textbox | Initials:
date | Date:
checkpoint | Posts align, at correct spacing and backfilled compacted.
textbox | Initials:
date | Date:
checkpoint | Post bolts are tight and washer is fitted at the back of post.
textbox | Initials:
date | Date:
checkpoint | Backing pieces are fitted at the intermediate post only.
textbox | Initials:
date | Date:
checkpoint | With flange based post the necked bolts are installed with washer.
textbox | Initials:
date | Date:
checkpoint-no-status | Comments:
checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
label | Position: Site Engineer
textbox | Site Engineer - Name:
date | Site Engineer - Date:
label | Position: Design Engineer
textbox | Design Engineer - Name:
date | Design Engineer - Date:
holdpoint | SIGN