## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | CS-4120 - Wire Rope Installation Record | [5 empty] | CS-4120 - Wire Rope Installation Record
checkpoint-no-status | Details
textbox | Work Area:
textbox | Sub Work Area:
textbox | Lot:
textbox | Sublot:
label | Document Date: 27/11/2019
label | Created By: Kirsty George
textbox | Drawing No:
textbox | Rev No:
textbox | Chainage:
checkpoint | Drilled holes spacing does not exceed 3M and are 300mm diameter and 750mm deep.
textbox | Initials:
date | Date:
label | Comments: Consistency with Construction Drawing, Details and Notes.
checkpoint | Concrete is 25Mpa.
textbox | Initials:
date | Date:
checkpoint | Concrete Dockets Collected
textbox | Initials:
date | Date:
checkpoint | The plastic Socket is correctly positioned and a rebar ring is placed 100mm down from top.
textbox | Initials:
date | Date:
checkpoint | Post are installed with slot orientation consistent for the entire length of the barrier.
textbox | Initials:
date | Date:
checkpoint | Top 2 Cables are positioned in the Top slot while the bottom 2 cables sit at the bottom of the slots on either post
textbox | Initials:
date | Date:
label | Comments: Cable Heights 530, 650, 770 and 790mm (+ or – 30mm)
checkpoint | Ensure no corrosion to the internal collars at swage connection
textbox | Initials:
date | Date:
label | Comments: Also check swage seat & collar thread connection. Should be tight and should not be able to undo once in place.
checkpoint | All posts have a plastic cap inserted in the Top and pushed hard home.
textbox | Initials:
date | Date:
checkpoint-no-status | Comments:
checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
label | Position: Site Engineer
textbox | Site Engineer - Name:
date | Site Engineer - Date:
label | Position: Design Engineer
textbox | Design Engineer - Name:
date | Design Engineer - Date:
holdpoint | SIGN