## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | ITP-005 - Crushed Rock Class 3 (Lot2) | itp | ITP-005 - Crushed Rock Class 3 (Lot2) |  | d7cf7754-dc3b-4383-9851-c5cbf6e51e96
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Crushed Rock Mix design
5df8fd2b-804a-5fdd-8798-137996ecd16e | note | FREQUENCY: Prior to Commencing Work
26d6a5d7-b0ac-533c-a1d1-0390110aca5f | note | ACCEPTANCE CRITERIA: Crushed rock mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mix Designs as listed in Section 175.
4f5f962d-aff8-59ca-aef4-e249cc0e63fd | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.812.09
858c507c-252b-5c23-9516-fdfe8410b5e6 | note | INSPECTION/TEST METHOD: Document Review
6bfdcc6b-2464-5c87-bb74-1f06a79b4c99 | note | RECORD OF CONFORMITY: Mix Design VicRoads Approval
a5910a80-6c56-53d9-8fc8-7ac2973807e7 | note | HP*
b6bdf2f3-8562-5905-ad14-114372514d29 | note | RESPONSIBILITY: Project Engineer
e2d958e4-8678-53bc-ae43-b9d83c152969 | date | Date Completed:
| section | 2 - Placing Fill
| checkpoint | 2.1 - Transverse Joints
d433567e-491d-5dac-be39-e738c9e2d543 | note | FREQUENCY: Check prior to placing material
9688c7e8-5ebd-5582-94b3-cf484f8195c2 | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of jointsTransverse joints shall be offset from one layer to next by not less than 2 metres
bf1c0df8-1aa4-5355-8bc2-6f9432fc071c | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.07 (a), Cl.304.07 (c)
a440c872-391c-5f5f-b5dd-92bd4c86b79b | note | INSPECTION/TEST METHOD: Site Inspection
b694529d-347f-53a4-b87e-64b8228a16cc | note | RECORD OF CONFORMITY: Signed ITP
3c671a9b-d1dc-53a4-876b-9a6293e8b4a5 | note | IP
51807ee2-3c30-5313-a27d-9b3daced151c | note | RESPONSIBILITY: Project Engineer
4b617b14-17d3-550b-8f9b-b691228e23f8 | date | Date Completed:
| checkpoint | 2.2 - Longitudinal Joints
7bb272b0-0d94-5b41-9f0a-867a6169eeab | note | FREQUENCY: Check prior to placing material
e5841c53-ed67-56a7-9657-6d73b5f8de07 | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of jointsLongitudinal joints offset from one layer to next by not less than 150mmLongitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane.
4e51a026-3eee-5552-a6f7-fc39b55dfe46 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.07 (a), Cl.304.07 (d), Cl.304.07 (e)
4549121c-430c-51ff-b310-05bceec742a1 | note | INSPECTION/TEST METHOD: Site Inspection
ccb618b0-478f-5130-a2c6-d98627b66f93 | note | RECORD OF CONFORMITY: Signed ITP
8de080c6-3fa7-53cb-996b-8e567b7f9170 | note | IP
bc7b38eb-d4c2-5478-9a23-f64060ff6f94 | note | RESPONSIBILITY: Project Engineer
2b484de9-ac0a-512b-b933-d4c8a4b99344 | date | Date Completed:
| checkpoint | 2.3 - Lot Size
8bc13945-fd64-5872-9b13-f1d5b2ae0ef9 | note | FREQUENCY: Check prior to placing material
64ebccbb-df2e-57b9-9bf5-41cabbe96a65 | note | ACCEPTANCE CRITERIA: A single lot shall be considered a single layer of 4000m2 or one days production in a single layer, whichever is lesser.
4ed09f60-f49c-5149-82cb-7a73489bd6fa | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.08 (b)(ii) Table 304.111
6f3b6669-945f-56bf-b0f5-25fdfaa023e0 | note | INSPECTION/TEST METHOD: Site Inspection
6366df16-9d1e-53cd-b170-516d419db823 | note | RECORD OF CONFORMITY: Signed ITP
3ce576ef-ca24-57d4-97a9-c537ab92fce9 | note | IP
314d79b6-5ab1-5062-9c05-d42eaf7ac1a7 | note | RESPONSIBILITY: Project Engineer
db643df3-e130-5724-8f2b-2a8824a151ef | date | Date Completed:
| checkpoint | 2.4 - Proof Roll
9a0b9fa2-f1a0-51ed-8d70-1aa7f50fbb13 | note | FREQUENCY: After placing material
ddeab0ea-ff5b-5602-adb1-3025ac23a16c | note | ACCEPTANCE CRITERIA: Pavement lots should be subject to proof roll as outlined in VicRoads Section 173, under supervision of Superintendent
b898c241-973c-5691-a74c-3474e1e49fc7 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.08(b)(iv), Cl. 173
7d734fcc-77c4-53fe-b3f1-096837e540da | note | INSPECTION/TEST METHOD: Site Inspection
b1d15bae-60cd-5336-bea1-57aa1e818af1 | note | RECORD OF CONFORMITY: Signed ITP
77117a51-edc1-5612-bd43-810db7ce75cf | note | WP
c9d30983-dfc4-5f39-bd43-dc69fca63807 | note | RESPONSIBILITY: Project Engineer & Superintendent
222aa8a6-f32b-545e-a39f-483436c19a69 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 3 - Testing Requirements
| checkpoint | 3.1 - Determine Testing Scale & Initial testing frequency
d3d4576a-eb68-55fd-842d-f24c80d556fe | note | FREQUENCY: Prior to Testing
4f0e032d-c2af-5483-8acf-2addd96bbf9c | note | ACCEPTANCE CRITERIA: Table 204.161 from VicRoads Standard nominates the level of testing required for acceptance of Surface Level Measurement.
c939f9e8-560d-5178-8989-b0fe8b9b602e | note | ○ Scale A - Initially test every lot until 3 consecutive lots of like material and/or work have achieved the standards specified in Clauses 304.08. and 304.10. If no failures, Reduced Frequency applies as specified in Table 304.111.
63b04594-85b2-53b8-8b0d-dad4456cb43e | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.161
260e08a8-5768-50fb-ae68-c27971a45f4b | note | ○ VicRoads Spec.
63aee9dc-1451-5c14-bfb6-4bad1729d9ce | note | ○ Cl.304.08 (a)
ef73c914-0d0f-5ee8-b03f-5cab3f259055 | note | ○ Cl.304.11 (b)
4d0c2860-43dd-5669-861b-ff443fab7f70 | note | ○ Cl.304.11 (c)(i)
0069e047-8df9-532f-912b-1c2d8cedc9d2 | note | ○ Table 304.111
26b52ff7-ec44-5cab-b2ba-5f1d578763e6 | note | INSPECTION/TEST METHOD: Document Review/ Site Inspection
f53bfdb6-5318-5d97-a7a8-695f9706e786 | note | RECORD OF CONFORMITY: Signed ITP
4f480eeb-324a-504b-9e86-bff734a32362 | note | IP
ee65661a-a8a8-50df-b49b-56e812630ed4 | note | RESPONSIBILITY: Project Engineer
3a6431a9-8094-5a63-a85d-9ab25d4d9cbb | date | Date Completed:
| checkpoint | 3.2 - Modified Compactive Effort
32dbe510-6c73-5168-914a-22e24a3ed8ab | note | FREQUENCY: As per 3.1
7f5b3425-b5fd-5d1c-97df-bf17b4b39bcf | note | ACCEPTANCE CRITERIA: Characteristic Value of Density Ratio for Subbase:- > 97.0% (Scale B) 1 per every lot
f58dfcac-1dc8-5b87-bb20-1efc50710e10 | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 304.081
6294bf8b-c9ad-53e3-ab30-29f4db2ba233 | note | INSPECTION/TEST METHOD: Site Inspection
0bd4618e-8363-5ef5-843d-5ceedf151202 | note | RECORD OF CONFORMITY: Test Records
8e935d89-8389-5b3c-89d1-92a9aa716e82 | note | TP
df786c3e-9b92-520d-86e2-ed489ff6ac31 | note | RESPONSIBILITY: Project Engineer
9a648157-18a8-527b-8bd7-62bb5e51d189 | date | Date Completed:
| checkpoint | 3.3 - Survey Level Conformity
9f76a73b-ec77-5401-ab27-fce7452a1806 | note | FREQUENCY: At completion
38e0bd54-a70e-5a40-ba9b-cabef1c8cb0b | note | ACCEPTANCE CRITERIA: Scale B:
d50b4def-6454-5adc-b3d2-e4dbbf57027b | note | ○ Minimum number of measurements per lot: 40 For Upper
689b0c95-7b08-5a7c-aa86-b20ecfee60dd | note | ○ Upper Subbase: Mean + 6mm to - 12mm with a maximum Standard Deviation of 8mm
cad12e62-4647-523a-9cf5-c667aaec4f26 | note | ○ Lower Subbase: Mean +8mm to -16mm with a maximum Standard Deviation of 10mm.
17fe9cb6-7b73-5669-8d7c-eddc6ac3c019 | note | ○ Base: Mean ± 8mm with a maximum Standard Deviation of 8mm.
d1b84624-52fd-5b5e-827d-38aeaca0b5e1 | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 304.061, Table 304.062
6c327eba-1aa6-5bbb-bb91-61eba973e57a | note | INSPECTION/TEST METHOD: Site Inspection
6a97fc61-5224-5ae9-b53e-20f275c8c9d8 | note | RECORD OF CONFORMITY: Test Records
4aa6a648-0463-57b9-a2aa-6846a4dc67d1 | note | TP
debe3581-02cd-55bf-8e1c-b0dc75a5700a | note | RESPONSIBILITY: Project Engineer
06caa7b6-001b-57a0-9f6b-1f515ba05d7b | date | Date Completed:
| checkpoint | Final Inspection
c4af552d-b9a1-5ced-ac96-aa333bd29bbd | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
31263faf-d6ed-5aea-80a2-a4cfb7cdc551 | textbox | Print Name:
26ec9255-13dd-55ee-9a72-64d6906a6102 | textbox | Position:
215f280d-4183-5111-9d27-1521c05eba30 | date | Date: