## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | ITP-014 - Earthworks and Subgrade Preparation Lot1 (East) | itp | ITP-014 - Earthworks and Subgrade Preparation Lot1 (East) |  | 20a70ec9-4eec-4879-971d-ea10892db417
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
8a775dd1-f693-5de5-9668-5471dd38b858 | note | FREQUENCY: Prior to commencing any activity
7f15375f-b763-59b9-af57-4973fe9cffee | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
5fe85fb2-57c9-5f11-a46a-16c15c66dd7b | note | – using the correct and complete set of drawings
41915e96-5372-5c44-94f5-1b84b28f2d47 | note | – all drawings are the latest revision
9ae67b70-b965-5510-a073-ca2454c0a0c7 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
3966b7f4-4c87-558f-99d2-10868325f49c | note | INSPECTION/TEST METHOD: Visual inspection
309875d7-034d-540a-9e88-08a6f785efd8 | note | RECORD OF CONFORMITY: This ITP signed off
bb97017b-8636-5855-9735-c65e542cf151 | note | HP*
218ba34a-98f8-5da7-a50e-0c0045717010 | note | RESPONSIBILITY: Project Engineer / Site Foreman
b684da10-f210-5ba7-9894-a1ca1b0d4951 | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
74e0a49c-3ee7-52e1-a481-ef2f0dca33c4 | note | FREQUENCY: Prior to commencing any activity
5a255568-a2a9-54f1-baf9-052574ba8029 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & ITP
171168bc-8b91-5d6f-805e-d643b1dff324 | note | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, ITP
d01a598c-27f1-57b7-a441-a24749dcd6b1 | note | INSPECTION/TEST METHOD: Visual Inspection
e99852e9-7ea0-501b-bf91-c5165e8a3d70 | note | RECORD OF CONFORMITY: This ITP signed off
13aa8f3f-8f36-5a0e-b002-0f686ef551de | note | HP*
de81b1aa-191b-5d26-9bd9-40be55f6017b | note | RESPONSIBILITY: Project Engineer / Site Foreman
7df3a554-8124-538f-afd1-d61c21aa863e | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Survey Set-Out
a6c3695d-2531-5cc1-91e1-1d0e4a0e79de | note | FREQUENCY: Prior to commencement of excavation
5bde262a-acfe-523a-b0de-a9c027dbd757 | note | ACCEPTANCE CRITERIA: Area has been set out in accordance with the drawings
ec4584d4-1279-5235-aa63-8a8af5c2b3f9 | note | REFERENCE DOCUMENTS: Work Procedure
1ecc548c-2074-5546-be5a-ad720f2d2874 | note | INSPECTION/TEST METHOD: Verify
92ee3ded-98a3-59f9-aa17-ae3e418a5545 | note | RECORD OF CONFORMITY: This ITP signed
cfb9f335-cf8f-55e5-bc06-5c21a2dfc2ab | note | IP
b1372482-8f58-521a-9c81-91a46d94384a | note | RESPONSIBILITY: Engineer/ Surveyor
0ab96c84-7e8e-5cbe-ace1-ff9567fe35eb | date | Date Completed:
| checkpoint | 2.2 - Excavation Permit
5db52b9a-b810-56e5-b74a-0f122adf99e8 | note | FREQUENCY: Lot
3ce1ab84-8f1d-533f-8703-d30c9ca3777d | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
0d5befd2-9943-55d5-b480-03c3d9690473 | note | ○ Plant and equipment shall be appropriate for the task.
774fc3f3-f987-517a-a68b-149e4a0c2ae3 | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
e864774f-2353-53ed-8e13-4a232ccc967a | note | REFERENCE DOCUMENTS: Excavation permit
58ff8dbb-d8d6-5864-ba26-f395a4b38f69 | note | INSPECTION/TEST METHOD: Verify
f4ab4416-a295-5e99-9ba2-394ef8e0f2aa | note | RECORD OF CONFORMITY: This ITP Signed Off
35074abc-cb80-50ea-929d-927613bee362 | note | HP*
6a659eb7-0691-5229-8fc2-5e36c7a4bec3 | note | RESPONSIBILITY: Project Engineer
7ae69c46-c454-572d-b0ee-6f9b49d6af54 | date | Date Completed:
| checkpoint | 2.3 - Excavate Pavment to specified depth and dispose material offsite
5ad2edfe-ac7d-574f-a4ff-06f2e2a386ec | note | FREQUENCY: Lot
f35d1886-95af-55f9-86ef-0418f9982069 | note | ACCEPTANCE CRITERIA: Correct levels and profiles achieved based on the tollerances below
747111cb-ff40-5042-b395-41c0406f2cc6 | note | ○ +15, -30mm at subgrade level
211c9392-8337-5eae-b496-9ad8c8b4e793 | note | ○ Cross check with survey pegs and record excavation depths using GPS
98e92282-f715-5f03-963f-c694d1844a56 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.04(c)
31a14c2c-5480-5ace-ad27-c4ca5489406c | note | INSPECTION/TEST METHOD: String Sheets to be used as no design survey avaliable
811629c0-de7f-569d-856f-c40595f5c244 | note | RECORD OF CONFORMITY: This ITP Sign off and String Sheet Acceptance
9f622b1e-1177-5d29-a5fe-cbded023d16c | note | HP
d00e8e97-3b18-5760-9349-d12be9bfc87a | note | RESPONSIBILITY: Project Engineer
da3ed79d-8ac6-5caa-9d7f-a8aa6fb51709 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Material classified as silt
57756fd9-166e-5ebc-9c2a-77210be56d47 | note | FREQUENCY: Prior to Commencing
35c49237-c918-5846-8977-225f5fcbeff4 | note | ACCEPTANCE CRITERIA: Material classified as silt, either before or after compaction, is not acceptable as Type A material without stablisation to the satisfaction of the Superintendent
7c53585d-7361-5702-a40c-ab0f06357409 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.04(c)
3b2df51f-2a30-58ab-b58b-07b95ab8fe4c | note | INSPECTION/TEST METHOD: Document Review
39bb56da-7a55-5cfd-87e9-c473eaf67d9c | note | RECORD OF CONFORMITY: Superintendent satisfied with Stabilisation, Signed ITP/ records
6f82b515-13a7-5fe4-9257-23cfdb0a43bb | note | HP
5f0a58b9-57c4-543d-b01c-52873c8d958f | note | RESPONSIBILITY: Engineer or Forman / DTP Superintendent
4dc764a5-79d3-5f03-89a0-07142ceeb726 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - Acceptance of Rock Subgrade (when applicable)
6baa7419-47f7-5419-a403-18d4a3a2951e | note | FREQUENCY: Prior construction of the regulating layer
236a6041-c1d8-5a9c-8244-4dae7bc4fbcf | note | ACCEPTANCE CRITERIA: Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
768a927e-86ec-5fdb-9185-dd8d762274c6 | note | ○ Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
0c985d49-fa6a-5ae6-89b4-6448642c8076 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.06(f)
e6938dde-f419-57c4-bbbd-55de847dca1a | note | INSPECTION/TEST METHOD: Site Inspection/ Document Review
2aff5dff-ad43-5954-94c0-bf506b3373f3 | note | RECORD OF CONFORMITY: Superintendent acceptance, Signed ITP
844efe7a-a0fd-588e-8697-14303f5f00d1 | note | HP
adc485fe-523a-5353-94ab-fdf1954cf9ef | note | RESPONSIBILITY: Engineer or Forman / DTP Superintendent
8fbe3281-61dd-5d4d-af30-f22144f0abdb | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.6 - Unsuitable Material
b0f63966-5d08-5ed0-aab0-871660267b4a | note | FREQUENCY: Each Lot
193de2af-f1ac-5ac3-b797-ed7868eed17c | note | ACCEPTANCE CRITERIA: Where Unsuitable material is encountered, proposed in-situ treatment must be submitted to the superintendent for review.
b316e722-1014-5485-b092-8316ad26e733 | note | REFERENCE DOCUMENTS: 204.07(d)
771101c5-23a5-55e6-8562-edf7ee5750bc | note | INSPECTION/TEST METHOD: Visual Inspection
0e4c6209-2841-5f85-97b9-60dc2fb3f151 | note | RECORD OF CONFORMITY: This ITP Signed Off
9d6747df-4427-595d-bdf4-170d9e5c89c5 | note | HP
c04ddd05-a8e1-5abd-8318-0fa0b2247322 | note | RESPONSIBILITY: Engineer or Forman / DTP Superintendent
75212bb6-6970-5138-b423-b77ee38c6e8c | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.7 - Groundwater
b722f133-46ed-5d87-8b9a-99cc3234a77e | note | FREQUENCY: Each Lot
aeb7fdb4-6c07-53e4-af0f-83df99b1b7f9 | note | ACCEPTANCE CRITERIA: Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review.
1a3140c5-2509-5c35-9399-1fce8e2def91 | note | ○ The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater
7e349899-8b12-5caf-8620-41f92a3d3b56 | note | REFERENCE DOCUMENTS: 204.06 (h)
d820c398-c6b5-5f67-b2b1-1abb3ee2c38a | note | INSPECTION/TEST METHOD: Visual inspection
429e3661-96d7-513f-b424-249e37a09d2e | note | RECORD OF CONFORMITY: This ITP signed off
d5274ed7-3a7c-54cc-8ff3-b74f5dbe852a | note | HP
8c99ea72-7254-5ef9-8276-723bab02d4ad | note | RESPONSIBILITY: Engineer or Forman / DTP Superintendent
2616818f-a694-50f7-8b59-17aa38c46ead | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 3 - Testing
| checkpoint | 3.1 - Proof Rolling
b39e3fe0-2675-52e3-a233-77e466bdec9f | note | FREQUENCY: Each Lot
a52c7d82-6c75-5895-b538-a1c3bf5f1b09 | note | ACCEPTANCE CRITERIA: Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
2058a991-922c-5a94-81f1-359992e84981 | note | REFERENCE DOCUMENTS: Cl 204.12 Section 173
c93a13ca-1b1a-5d5f-9d36-4f1f4a330b23 | note | INSPECTION/TEST METHOD: Visual Inspection
2a0eda39-b73b-51e2-b222-49f9aa8a5472 | note | RECORD OF CONFORMITY: This ITP signed off
65443544-577e-5d11-bd3c-2251e5a9077b | note | HP*, WP
6d8d56a6-69f6-5030-bf07-b5c9e4210bbe | note | RESPONSIBILITY: Engineer or Forman / DTP Superintendent
3922ebc8-87e6-5885-8040-062544c58e72 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Final Inspection
3dd5f0f5-b6ef-55cd-9962-a4510d4c4e88 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
23732055-7aa4-5311-a9f3-f40f0c85c619 | textbox | Print Name:
7c8dce47-676a-58d3-abd3-1595169e62db | textbox | Position:
b0a9e3fa-48f9-530d-8093-fa9e96042953 | date | Date:
| checklist | ITP-005 - Crushed Rock Class 3 (Lot2) | itp | ITP-005 - Crushed Rock Class 3 (Lot2) |  | d7cf7754-dc3b-4383-9851-c5cbf6e51e96
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Crushed Rock Mix design
5df8fd2b-804a-5fdd-8798-137996ecd16e | note | FREQUENCY: Prior to Commencing Work
26d6a5d7-b0ac-533c-a1d1-0390110aca5f | note | ACCEPTANCE CRITERIA: Crushed rock mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mix Designs as listed in Section 175.
4f5f962d-aff8-59ca-aef4-e249cc0e63fd | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.812.09
858c507c-252b-5c23-9516-fdfe8410b5e6 | note | INSPECTION/TEST METHOD: Document Review
6bfdcc6b-2464-5c87-bb74-1f06a79b4c99 | note | RECORD OF CONFORMITY: Mix Design VicRoads Approval
a5910a80-6c56-53d9-8fc8-7ac2973807e7 | note | HP*
b6bdf2f3-8562-5905-ad14-114372514d29 | note | RESPONSIBILITY: Project Engineer
e2d958e4-8678-53bc-ae43-b9d83c152969 | date | Date Completed:
| section | 2 - Placing Fill
| checkpoint | 2.1 - Transverse Joints
d433567e-491d-5dac-be39-e738c9e2d543 | note | FREQUENCY: Check prior to placing material
9688c7e8-5ebd-5582-94b3-cf484f8195c2 | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of jointsTransverse joints shall be offset from one layer to next by not less than 2 metres
bf1c0df8-1aa4-5355-8bc2-6f9432fc071c | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.07 (a), Cl.304.07 (c)
a440c872-391c-5f5f-b5dd-92bd4c86b79b | note | INSPECTION/TEST METHOD: Site Inspection
b694529d-347f-53a4-b87e-64b8228a16cc | note | RECORD OF CONFORMITY: Signed ITP
3c671a9b-d1dc-53a4-876b-9a6293e8b4a5 | note | IP
51807ee2-3c30-5313-a27d-9b3daced151c | note | RESPONSIBILITY: Project Engineer
4b617b14-17d3-550b-8f9b-b691228e23f8 | date | Date Completed:
| checkpoint | 2.2 - Longitudinal Joints
7bb272b0-0d94-5b41-9f0a-867a6169eeab | note | FREQUENCY: Check prior to placing material
e5841c53-ed67-56a7-9657-6d73b5f8de07 | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of jointsLongitudinal joints offset from one layer to next by not less than 150mmLongitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane.
4e51a026-3eee-5552-a6f7-fc39b55dfe46 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.07 (a), Cl.304.07 (d), Cl.304.07 (e)
4549121c-430c-51ff-b310-05bceec742a1 | note | INSPECTION/TEST METHOD: Site Inspection
ccb618b0-478f-5130-a2c6-d98627b66f93 | note | RECORD OF CONFORMITY: Signed ITP
8de080c6-3fa7-53cb-996b-8e567b7f9170 | note | IP
bc7b38eb-d4c2-5478-9a23-f64060ff6f94 | note | RESPONSIBILITY: Project Engineer
2b484de9-ac0a-512b-b933-d4c8a4b99344 | date | Date Completed:
| checkpoint | 2.3 - Lot Size
8bc13945-fd64-5872-9b13-f1d5b2ae0ef9 | note | FREQUENCY: Check prior to placing material
64ebccbb-df2e-57b9-9bf5-41cabbe96a65 | note | ACCEPTANCE CRITERIA: A single lot shall be considered a single layer of 4000m2 or one days production in a single layer, whichever is lesser.
4ed09f60-f49c-5149-82cb-7a73489bd6fa | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.08 (b)(ii) Table 304.111
6f3b6669-945f-56bf-b0f5-25fdfaa023e0 | note | INSPECTION/TEST METHOD: Site Inspection
6366df16-9d1e-53cd-b170-516d419db823 | note | RECORD OF CONFORMITY: Signed ITP
3ce576ef-ca24-57d4-97a9-c537ab92fce9 | note | IP
314d79b6-5ab1-5062-9c05-d42eaf7ac1a7 | note | RESPONSIBILITY: Project Engineer
db643df3-e130-5724-8f2b-2a8824a151ef | date | Date Completed:
| checkpoint | 2.4 - Proof Roll
9a0b9fa2-f1a0-51ed-8d70-1aa7f50fbb13 | note | FREQUENCY: After placing material
ddeab0ea-ff5b-5602-adb1-3025ac23a16c | note | ACCEPTANCE CRITERIA: Pavement lots should be subject to proof roll as outlined in VicRoads Section 173, under supervision of Superintendent
b898c241-973c-5691-a74c-3474e1e49fc7 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.08(b)(iv), Cl. 173
7d734fcc-77c4-53fe-b3f1-096837e540da | note | INSPECTION/TEST METHOD: Site Inspection
b1d15bae-60cd-5336-bea1-57aa1e818af1 | note | RECORD OF CONFORMITY: Signed ITP
77117a51-edc1-5612-bd43-810db7ce75cf | note | WP
c9d30983-dfc4-5f39-bd43-dc69fca63807 | note | RESPONSIBILITY: Project Engineer & Superintendent
222aa8a6-f32b-545e-a39f-483436c19a69 | date | Date Completed:
| section | 3 - Testing Requirements
| checkpoint | 3.1 - Determine Testing Scale & Initial testing frequency
d3d4576a-eb68-55fd-842d-f24c80d556fe | note | FREQUENCY: Prior to Testing
4f0e032d-c2af-5483-8acf-2addd96bbf9c | note | ACCEPTANCE CRITERIA: Table 204.161 from VicRoads Standard nominates the level of testing required for acceptance of Surface Level Measurement.
c939f9e8-560d-5178-8989-b0fe8b9b602e | note | ○ Scale A - Initially test every lot until 3 consecutive lots of like material and/or work have achieved the standards specified in Clauses 304.08. and 304.10. If no failures, Reduced Frequency applies as specified in Table 304.111.
63b04594-85b2-53b8-8b0d-dad4456cb43e | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.161
260e08a8-5768-50fb-ae68-c27971a45f4b | note | ○ VicRoads Spec.
63aee9dc-1451-5c14-bfb6-4bad1729d9ce | note | ○ Cl.304.08 (a)
ef73c914-0d0f-5ee8-b03f-5cab3f259055 | note | ○ Cl.304.11 (b)
4d0c2860-43dd-5669-861b-ff443fab7f70 | note | ○ Cl.304.11 (c)(i)
0069e047-8df9-532f-912b-1c2d8cedc9d2 | note | ○ Table 304.111
26b52ff7-ec44-5cab-b2ba-5f1d578763e6 | note | INSPECTION/TEST METHOD: Document Review/ Site Inspection
f53bfdb6-5318-5d97-a7a8-695f9706e786 | note | RECORD OF CONFORMITY: Signed ITP
4f480eeb-324a-504b-9e86-bff734a32362 | note | IP
ee65661a-a8a8-50df-b49b-56e812630ed4 | note | RESPONSIBILITY: Project Engineer
3a6431a9-8094-5a63-a85d-9ab25d4d9cbb | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Modified Compactive Effort
32dbe510-6c73-5168-914a-22e24a3ed8ab | note | FREQUENCY: As per 3.1
7f5b3425-b5fd-5d1c-97df-bf17b4b39bcf | note | ACCEPTANCE CRITERIA: Characteristic Value of Density Ratio for Subbase:- > 97.0% (Scale B) 1 per every lot
f58dfcac-1dc8-5b87-bb20-1efc50710e10 | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 304.081
6294bf8b-c9ad-53e3-ab30-29f4db2ba233 | note | INSPECTION/TEST METHOD: Site Inspection
0bd4618e-8363-5ef5-843d-5ceedf151202 | note | RECORD OF CONFORMITY: Test Records
8e935d89-8389-5b3c-89d1-92a9aa716e82 | note | TP
df786c3e-9b92-520d-86e2-ed489ff6ac31 | note | RESPONSIBILITY: Project Engineer
9a648157-18a8-527b-8bd7-62bb5e51d189 | date | Date Completed:
| checkpoint | 3.3 - Survey Level Conformity
9f76a73b-ec77-5401-ab27-fce7452a1806 | note | FREQUENCY: At completion
38e0bd54-a70e-5a40-ba9b-cabef1c8cb0b | note | ACCEPTANCE CRITERIA: Scale B:
d50b4def-6454-5adc-b3d2-e4dbbf57027b | note | ○ Minimum number of measurements per lot: 40 For Upper
689b0c95-7b08-5a7c-aa86-b20ecfee60dd | note | ○ Upper Subbase: Mean + 6mm to - 12mm with a maximum Standard Deviation of 8mm
cad12e62-4647-523a-9cf5-c667aaec4f26 | note | ○ Lower Subbase: Mean +8mm to -16mm with a maximum Standard Deviation of 10mm.
17fe9cb6-7b73-5669-8d7c-eddc6ac3c019 | note | ○ Base: Mean ± 8mm with a maximum Standard Deviation of 8mm.
d1b84624-52fd-5b5e-827d-38aeaca0b5e1 | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 304.061, Table 304.062
6c327eba-1aa6-5bbb-bb91-61eba973e57a | note | INSPECTION/TEST METHOD: Site Inspection
6a97fc61-5224-5ae9-b53e-20f275c8c9d8 | note | RECORD OF CONFORMITY: Test Records
4aa6a648-0463-57b9-a2aa-6846a4dc67d1 | note | TP
debe3581-02cd-55bf-8e1c-b0dc75a5700a | note | RESPONSIBILITY: Project Engineer
06caa7b6-001b-57a0-9f6b-1f515ba05d7b | date | Date Completed:
| checkpoint | Final Inspection
c4af552d-b9a1-5ced-ac96-aa333bd29bbd | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
31263faf-d6ed-5aea-80a2-a4cfb7cdc551 | textbox | Print Name:
26ec9255-13dd-55ee-9a72-64d6906a6102 | textbox | Position:
215f280d-4183-5111-9d27-1521c05eba30 | date | Date: