## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-169-RAIL-BRUNT-Rail Delineation Permanent Fencing
ITP Description: |  | BRUNT-Rail Delineation Permanent Fencing
Discipline (e.g. CIV/STR/RAIL: |  | 169-RAIL
Revision Number: |  | 1
Revision Date: |  | 2024-05-20
ITP created by: |  | Jason Lee
ITP approved for use by: |  | Jon De Castro
Special Notes to ConQA Team : |  | ITP for Brunt Rd Project
Inspection & Test Plan - Rail Delineation Fencing-Permanent
|  |  | Doc. No.: ITP-169-RAIL-BRUNT-Rail Delineation Permanent Fencing | [5 empty] | Revision: | 1
[9 empty] | Date: | 2024-05-20
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | IFC Drawings VicRoads Section 610 VicRoads Section 630 VicTrack STD_C0031 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Materials
2.1 | Concrete Mix for Footings | IFC Drawings | Concrete Mix is Registered with VicRoads. Minimum Strength of 20MPa concrete to be used as per IFC drawings. | Document Review | Each Mix | HP | SE/Site Supervisor | This ITP Signed Off Attach: Supplier Material Conformance Certificate Delivery Dockets
2.2 | Weld Mesh Fences and Gates | IFC Drawings AS4792 | All weld mesh fences and gates to be galvanised steel with black powder coat unless nominated otherwise on fencing plans. Galvanised coating shall comply with AS/NZS 4792 with a coating class of HDG 300 mimum | Document review Visual and Measure | All elements | IP | SE/Site Supervisor | This ITP Signed Off Attach: Supplier Material Conformance Certificate Delivery Dockets
3 | Pre-construction / Pre-installation Activities
3.1 | Survey Set-out | IFC Drawings | Survey to set out the following but not limited to: existing services, post locations, refuge bays. Offset checked against the running edge prior to installation of posts. Engineer to verify alignment of posts using string line or equivalent. | Measure Visual | Each element | IP | Surveyor SE/PE | This ITP Signed Off
4 | Construction / Installation Activities
4.1 | Excavation works | IFC Drawings VicTrack STD_C0031 | Excavation for post foundation must not undermine track, footing of existing structures and comply with the PTDT requirements. Follow asset owners guidelines for work around their service. Excavation must use Non Distructive Digging in the rail corridor | Measure Visual | Each Post | IP | SE/Site Supervisor | This ITP Signed Off
4.2 | Ground Conditions | IFC Drawings | All post (fence and gate) foundations to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material. If the ground material on site does not meet the design assumptions, the Geotechnical Engineer shall be notified to determine if design change is required. | Visual | Each post | IP | SE/Site Supervisor | This ITP Signed Off
4.3 | MTM OHW Structures | IFC Drawings VicTrack STD_C0031 | Fencing must be a minimum 2m away from OHW Structures. Where temporary fence is in proximity of the OHW Structure, the OHW Structure is to be cladded with timber for a minimum height of 2.4m from ground level. | Measure | Each Overhead | IP | SE/Site Supervisor | This ITP Signed Off
4.4 | Fence Post Foundation | IFC Drawings VicTrack STD_C0031 | Typical Footing: Footing dimension 600mm deep, 200mm diameter Gate Footing (3m to 5m gate opening) - 300mm diameter by 1200mm depth Gate Footing (5m to 8m gate opening) - 450mm diameter by 1500mm depth Gate Footing (9m to 12m gate opening) - 600mm diameter by 1600mm depth Seperation Gap Footing - 450mm diameter by 1200mm depth. | Measure | Each footing | IP | SE/Site Supervisor | This ITP Signed Off
4.5 | Concrete Footing | Site Sampling & Testing Procedure 610.16 (b) | Concrete cast in one continuous operation to be tested at a frequency as shown below: 0m³ to 10m³ = 1 sample 10m³ to 25m³ = 2 samples 25m³ to 50m³ = 3 samples 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders. For each additional 50m³ and additional sample shall be taken. Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing). Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum. Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength. | Test | Each element | IP | Concrete Tester Foreman SE/PE/SPE | This ITP Signed Off Concrete Pour Record
4.6 | Fence Post Installation | IFC Drawings | Maximum post spacing to be 2.405m. Spacing may be locally decreased as required to avoid existing services Max. post height 1800mm above ground level Vertical Tolerance: ±20mm from the design line. | Measure | Each post | IP | SE/Site Supervisor | This ITP Signed Off
4.7 | Chain Wire Mesh Installation | IFC Drawings VicTrack STD_C0031 | Chain-wire mesh 1800x50x2.50 to be fixed to fence post with Tek Screw and 25mm U-Clip | Visual | Each element | IP | SE/Site Supervisor | This ITP Signed Off
4.8 | Bracing | IFC Drawings | 50 SHS x 2.5 Diagonal bracers to be installed at vehicle gate as per IFC Drawings | Visual | Each element | IP | SE/Site Supervisor | This ITP Signed Off
4.9 | Seperation Gap | IFC Drawings | 100mm Seperation Gap between the existing fence and new fence to be installed. | Measure | Each element | IP | SE/Site Supervisor | This ITP Signed Off
4.1 | Gate Installation - Gate | IFC Drawings | Gates to be fabricated to the installed gate posts with equal spacing welded mesh. Braces and Verticals Mesh to be installed as per the IFC | Measure | Each Gate | IP | SE/Site Supervisor | This ITP Signed Off
5 | Post-construction / Post-installation Activities
5.1 | Fence Height and Track Clearance | IFC Drawings | Vertical gaps between finished surface level and the bottom of the fence panel are to be 50mm minimum to 150mm maximum | Measure | Each lot | IP | SE/Site Supervisor | This ITP Signed Off
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /