## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-169-RAIL-BRUNT-Rail Delineation Permanent Fencing Rev 1 | itp |  |  |  |  | ITP-169-RAIL-BRUNT-Rail Delineation Permanent Fencing Rev 1 | faf72238-b5a3-423f-a401-7c94bfc3ebe7
section | 1. Referenced Documentation
checkpoint-no-status | 1. Referenced Documentation
label | Document Title: ITP-169-RAIL-BRUNT-Rail Delineation Permanent Fencing
label | ITP Description: BRUNT-Rail Delineation Permanent Fencing
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): 169-RAIL
label | Revision Number: 1
label | Revision Date: 20/05/2024
label | ITP created by: Jason Lee
label | ITP approved for use by: Jon De Castro
checkpoint | 1.1 - Non Dependent
label | Reference - IFC Drawings VicRoads Section 610, VicRoads Section 630, VicTrack STD_C0031
section | 2. Materials
checkpoint | 2.1 - Concrete Mix for Footings
label | Reference - IFC Drawings
label | Acceptance Criteria - Concrete Mix is Registered with VicRoads.
label | ○ Minimum Strength of 20MPa concrete to be used as per IFC drawings.
label | Method - Document Review
label | Frequency - Each Mix
label | Category - HP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP Signed Off
label | ○ Attach: Supplier Material Conformance Certificate, Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Weld Mesh Fences and Gates
label | Reference - IFC Drawings AS4792
label | Acceptance Criteria - All weld mesh fences and gates to be galvanised steel with black powder coat unless nominated otherwise on fencing plans. Galvanised coating shall comply with AS/NZS 4792 with a coating class of HDG 300 mimum
label | Method - Document review, Visual and Measure
label | Frequency - All elements
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP Signed Off
label | ○ Attach: Supplier Material Conformance Certificate, Delivery Dockets
section | 3. Pre-construction / Pre-installation Activities
checkpoint | 3.1 - Survey Set-out
label | Reference - IFC Drawings
label | Acceptance Criteria - Survey to set out the following but not limited to: existing services, post locations, refuge bays.
label | ○ Offset checked against the running edge prior to installation of posts.
label | ○ Engineer to verify alignment of posts using string line or equivalent.
label | Method - Measure, Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - Surveyor, SE/PE
label | Verifying Documents - This ITP Signed Off
section | 4. Construction / Installation Activities
checkpoint | 4.1 - Excavation works
label | Reference - IFC Drawings VicTrack STD_C0031
label | Acceptance Criteria - Excavation for post foundation must not undermine track, footing of existing structures and comply with the PTDT requirements.
label | ○ Follow asset owners guidelines for work around their service.
label | ○ Excavation must use Non Distructive Digging in the rail corridor
label | Method - Measure, Visual
label | Frequency - Each Post
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP Signed Off
checkpoint | 4.2 - Ground Conditions
label | Reference - IFC Drawings
label | Acceptance Criteria - All post (fence and gate) foundations to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material.
label | ○ If the ground material on site does not meet the design assumptions, the Geotechnical Engineer shall be notified to determine if design change is required.
label | Method - Visual
label | Frequency - Each post
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP Signed Off
checkpoint | 4.3 - MTM OHW Structures
label | Reference - IFC Drawings VicTrack STD_C0031
label | Acceptance Criteria - Fencing must be a minimum 2m away from OHW Structures.
label | ○ Where temporary fence is in proximity of the OHW Structure, the OHW Structure is to be cladded with timber for a minimum height of 2.4m from ground level.
label | Method - Measure
label | Frequency - Each Overhead
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP Signed Off
checkpoint | 4.4 - Fence Post Foundation
label | Reference - IFC Drawings VicTrack STD_C0031
label | Acceptance Criteria - Typical Footing: Footing dimension 600mm deep, 200mm diameter
label | ○ Gate Footing (3m to 5m gate opening)
label | – 300mm diameter by 1200mm depth
label | ○ Gate Footing (5m to 8m gate opening)
label | – 450mm diameter by 1500mm depth
label | ○ Gate Footing (9m to 12m gate opening)
label | – 600mm diameter by 1600mm depth
label | ○ Seperation Gap Footing
label | – 450mm diameter by 1200mm depth.
label | Method - Measure
label | Frequency - Each footing
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP Signed Off
checkpoint | 4.5 - Concrete Footing
label | Reference - Site Sampling & Testing Procedure 610.16 (b)
label | Acceptance Criteria - Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | ○ 0m³ to 10m³ = 1 sample
label | ○ 10m³ to 25m³ = 2 samples
label | ○ 25m³ to 50m³ = 3 samples
label | ○ 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
label | – For each additional 50m³ and additional sample shall be taken.
label | – Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
label | – Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
label | – Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | Method - Test
label | Frequency - Each element
label | Category - IP
label | Responsibility - Concrete Tester, Foreman, SE/PE/SPE
label | Verifying Documents - This ITP Signed Off, Concrete Pour Record
checkpoint | 4.6 - Fence Post Installation
label | Reference - IFC Drawings
label | Acceptance Criteria - Maximum post spacing to be 2.405m. Spacing may be locally decreased as required to avoid existing services
label | ○ Max. post height 1800mm above ground level
label | ○ Vertical Tolerance: ±20mm from the design line.
label | Method - Measure
label | Frequency - Each post
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP Signed Off
checkpoint | 4.7 - Chain Wire Mesh Installation
label | Reference - IFC Drawings VicTrack STD_C0031
label | Acceptance Criteria - Chain-wire mesh 1800x50x2.50 to be fixed to fence post with Tek Screw and 25mm U-Clip
label | Method - Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP Signed Off
checkpoint | 4.8 - Bracing
label | Reference - IFC Drawings
label | Acceptance Criteria - 50 SHS x 2.5 Diagonal bracers to be installed at vehicle gate as per IFC Drawings
label | Method - Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP Signed Off
checkpoint | 4.9 - Seperation Gap
label | Reference - IFC Drawings
label | Acceptance Criteria - 100mm Seperation Gap between the existing fence and new fence to be installed.
label | Method - Measure
label | Frequency - Each element
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP Signed Off
checkpoint | 4.10 - Gate Installation - Gate
label | Reference - IFC Drawings
label | Acceptance Criteria - Gates to be fabricated to the installed gate posts with equal spacing welded mesh.
label | ○ Braces and Verticals Mesh to be installed as per the IFC
label | Method - Measure
label | Frequency - Each Gate
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP Signed Off
section | 5. Post-construction / Post-installation Activities
checkpoint | 5.1 - Fence Height and Track Clearance
label | Reference - IFC Drawings
label | Acceptance Criteria - Vertical gaps between finished surface level and the bottom of the fence panel are to be 50mm minimum to 150mm maximum
label | Method - Measure
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP Signed Off
checkpoint | Final Inspection
note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
date | Date Completed:
signoff | Sign ITP