## Sheet1
Homi Train Station - Inspection and Test Plan
Project Area |  | Homai Train Station |  |  |  | Rev | 1 |  | Inspection and Test Codes:
Activity Title |  | Fences and Gates |  |  |  | Date | 20.12.2024 |  | [R] Review | Review of reports, records or other evidence of compliance.
Location | [5 empty] | Lot No. |  |  | [I] Inspection | In process check, work proceeds. Record the check if required.
Ref # |  | DN1212-ITP-016 | [6 empty] | [W] Witness | Inspection to be witnessed on site and recorded. Record to be filed.
DNZ Project Manager: |  | Dan Trotman | [6 empty] | [H] Hold | No work to proceed past Hold Point until this is completed, recorded and released
AT Project Manager: |  | Mike Robertson
DNZ Project Engineer: |  | Grant Wallace
Drawings/Reference Documents: |  | 3235599-SP03-CA-1015 3235599-SP03-CA-1016 3235599-SP03-CA-1017 3235599-SP03-CA-1018 3235599-SP03-CA-1019
Specifications: |  | KiwiRail Standard - Hurricane (folded panel Rigid wire) KiwiRail Enhanced Urban Environment
ITP Item # | Construction Activity or Material Element |  | Standard, Drawing or Specification Reference | Construction Activity Description, Test Type and Acceptance Criteria |  | Test Frequency |  | QA Record | Verification Method and On Site Responsibilities |  |  | DNZ Rep Sign and Date
[9 empty] | DNZ Engineer | Engineer's Rep | Designer Rep
1 | PRELIMINARY AND GENERAL
1.1 | IFC Drawings and Specification |  | ACC | A minimum of two weeks prior to construction: document review. DWG’s are for construction or as per instruction Works done in accordance with Project specification |  | Once |  | N/A | R |  | H | Sign | 2025-02-17
1.2 | Method Statement & JSEA Development |  | The Downer Standards (TDS) | Prior to construction: document review. |  | Once |  | Method Statement & JSEA Completed & signed by relevant authority | H | R | R | Sign | 2025-02-17
1.3 | Permit to Dig |  | DN-ZH-ST043 Ground Disturbance | Prior to construction. Permit in work package |  | Permit issued each week |  | Permit number ....................... | H |  |  | Sign | 2025-02-17
1.4 | Survey Model |  | N/A | Model Review. |  | Once |  | Visual Inspection & measurement Survey Check set out as per design | H |  |  | Sign | 2025-02-17
1.5 | Corridor Access Requests (CAR) |  | N/A | Corridor Access Requests (CARs) is required before any work is carried out on public roads. |  | Once |  | Approved CAR | H |  |  | Sign | 2025-02-17
2 | MATERIAL APPROVALS
2.1 | Fence panels |  | 3235599-SP03-CA-1017 Note: 1 | Fences to be hot dip galvanized. |  | Preconstruction - once |  | Delivery Dockets Ineight Approvals | I |  | R | Sign | 2025-02-17
2.2 | Fence posts |  | 3235599-SP03-CA-1017 Note: 3 | Fence post must be 65mm SHS hot dip R3 Galvanised square hollow section or similar approved. |  | Preconstruction - once |  | Delivery Dockets Ineight Approvals | R |  | R | Sign | 2025-02-17
3 | CONSTRUCTION ACTIVITIES
3.1 | Pre-installation |  | DN1212: CKT - 000060 | complete permanent fencing checksheets |  | During construction - once |  | Checksheets & photos | I |  |  | Sign | 2025-02-17
4 | FINAL RECORDS
4.1 | Construction Record Compilation |  | N/A | Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted. |  | Once |  | QA Records | H |  | R | Sign | 2025-02-17
4.2 | Survey Records |  | N/A | Ensure all items have been surveyed. |  | Once |  | As-Built | H |  | R | Sign | 2025-02-17
4.3 | Redline Drawings |  | IFC Drawings | Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. |  | Once |  | IFC Mark-Up | H |  | R | Sign | 2025-02-17
4.4 | Non-conformances |  | DN1212-DOW-PLA-PM-0005 QMP | Non-conformances reports to be raised when specification not met. All non-conformances within the area under review need to be listed on the NCR report. NCR Reference ….................. |  | When Required |  | NCR Forms on InEight | H |  | R | Sign | 2025-02-17
Comments:
ITP APPROVAL PROCESS
Prepared By: Site Engineer |  |  | Moses Kaufanga |  | Signed: |  | Date:
Reviewed By: Quality Mgr./Eng. |  |  | Nas Matar |  | Signed: |  | Date:
Reviewed By: Project Manager |  |  | Dan Trotman |  | Signed: |  | Date:
Reviewed By: Design Engineer |  |  | Daniel Cvitanich |  | Signed: |  | Date:
Reviewed By: AT Project Manager |  |  | Werner Nel |  | Signed: |  | Date:
Reviewed By: AT Engineer to Contract |  |  | Mike Robertson |  | Signed: |  | Date:
FINAL ITP CLOSE-OUT
Downer Project/Site Engineer |  |  | Grant Wallace |  | Signed: |  | 2025-02-17
QA Mgr./Engineer |  |  |  |  | Signed: |  | Date:
Designers Rep(Assistant) |  |  |  |  | Signed: |  | Date:
Note on A35: Kelsey Wong: ITP Revision to be signed and approved the Project Lead prior to construction. Final version issued to Quality Engineer / Engineer's Rep for Comment and Acceptance of ITP.