## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
8eb822b5-a279-45f8-b187-326dc5d71aee | checklist | DN1212-ITP-001 Concrete Footpath Rev2 | itp | DN1212-ITP-001 Concrete Footpath
38820775-d13e-4983-a44e-287170916540 | section | 1 - PRELIMINARY AND GENERAL
9c5620dd-712e-4602-ac4c-60657b8854b7 | checkpoint | 1.1 - IFC Drawings and Specification
3880bc4b-7b5c-5a63-b1cc-69676c84ed1c | note | Standard, Drawing or Specification Reference - ACC
80f1154b-b0bf-54d8-b4a9-d17b2c954847 | note | Construction Activity Description, Test Type and Acceptance Criteria - A minimum of two weeks prior to construction: document review. DWG’s are for construction or as per instruction
c12c78b0-8954-55c9-a9d8-1990c10e2f3d | note | ○ Works done in accordance with Project specification
7d68c84c-dc5c-506a-90b2-d8cf32da1f2e | note | Test Frequency - Once
056f39eb-47c7-5fe5-b52f-465b0b02af1d | note | QA Record - N/A
96080ce2-5c4d-5bdb-ae1c-90e8ae915ef6 | note | DNZ Engineer - R
0e93766c-2956-57ee-b8e6-aa8d4e896ac9 | note | Designer Rep - H
ae3fc8b0-3ba8-4eb6-a6a8-9dd8fba4b280 | signoff | AUTHORITY HOLDPOINT
6823f7f0-4a97-4ac1-897a-be92d459fb8e | checkpoint | 1.2 - Method Statement & JSEA Development
8a86e831-ca46-5559-a815-96aba75a6ea4 | note | Standard, Drawing or Specification Reference - The Downer Standards (TDS)
847851fa-0f23-540d-a7e7-bc35ab9af9f3 | note | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction: document review.
6fd867de-e380-5f30-91c0-a47bea6a1d3a | note | Test Frequency - Once
2d49cb81-5084-50df-b4f4-911ce41f9db1 | note | QA Record - Method Statement & JSEA Completed & signed by relevant authority
89770c9a-5917-5dae-b54f-7f9013c08904 | note | DNZ Engineer - H
f03b0de3-64f8-54a9-94a8-d26e9089536d | note | Engineer's Rep - R
d4b1de8b-3154-5630-8c70-35ac345083ff | note | Designer Rep - R
34aca323-6f82-4a76-bec0-7078cac31b3f | signoff | AUTHORITY HOLDPOINT
72f29a71-cf7c-42f7-b303-21ccad757177 | checkpoint | 1.3 - Permit to Dig
030d367e-2d62-574f-b800-a00a48287811 | note | Standard, Drawing or Specification Reference - DN-ZH-ST043 Ground Disturbance
de6323e4-6afe-59ef-add0-6cfc4184350f | note | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction. Permit in work package
810b68ab-9254-5fb7-a351-bc6357b89664 | note | Test Frequency - Permit issued each week
f916783b-dc8b-5963-ad65-e7725f13acd0 | textbox | QA Record - Permit number
833dbe8b-5134-57ad-9290-c995e210d754 | note | DNZ Engineer - H
d3ea1e69-e11e-4924-ab55-4b377de46530 | signoff | AUTHORITY HOLDPOINT
09b621a1-cd59-4a98-875a-7caf42c9a638 | checkpoint | 1.4 - Survey Model
29c2e033-8b83-5b4d-b2e4-4a26fda7ce6e | note | Standard, Drawing or Specification Reference - N/A
440d57be-7453-5787-a9c9-e3c4d7adc731 | note | Construction Activity Description, Test Type and Acceptance Criteria - Model Review.
9b4dfe3f-cc65-5100-83a0-3fabe89f9065 | note | Test Frequency - Once
fdd9f306-fb9c-500f-bd98-092453e1774a | note | QA Record - Visual Inspection & measurement Survey Check set out as per design
3c333d29-680d-5e37-a019-859501b763b7 | note | DNZ Engineer - H
f4a8dbc3-c031-4cad-8c01-1a6f7f5b8a6e | signoff | AUTHORITY HOLDPOINT
9c858345-b5fd-4d2a-ba9b-c750259939f9 | section | 2 - MATERIAL APPROVALS
f1f3e5c0-1a3f-43b1-ab6b-687c372bc22f | checkpoint | 2.1 - Concrete Mix Design
3a2786d5-c548-5ed2-a77f-b61ce1283669 | note | Standard, Drawing or Specification Reference - 746-22-052-PS Section 5.2, NZS 3114:1987, part 2 Exposed Aggregate surfaces.
2c7bef63-4b6a-571c-b84e-166620647da2 | note | Construction Activity Description, Test Type and Acceptance Criteria - Mix Design approved by designer.
69a9d6dc-7475-52b7-8441-cf2d993f4e22 | note | ○ 20Mpa Concrete with 4% Black Oxide, maximum 19mm aggregates.
3feb15aa-c13e-5252-b5fa-5d9901a605db | note | Test Frequency - Once
cb1a8b53-a30a-5936-bee4-23b5218c2ad3 | note | QA Record - Approved Mix
7020b0df-78f9-57e4-9a93-14aa2b6f11d6 | textbox | InEight Reference
5f7d19af-c9df-52cb-8ca2-3a1289c97580 | note | DNZ Engineer - R
cf328b58-8d3b-5c74-96ec-a0c8eda72ae7 | note | Designer Rep - H
d563f239-b6fa-4e1f-b1b5-ba7ed61ea19b | signoff | AUTHORITY HOLDPOINT
03678886-ca6f-4781-a4f3-6557f87e38e9 | checkpoint | 2.2 - ATAP40/GAP40 - Material Source property testing and sampling
a53dcabc-5e7b-55bb-a9d2-84abc8de421f | note | Standard, Drawing or Specification Reference - TNZ M/4: 2006 - 3, NZS 4407 : 1991, NZS 4402 : 1986
05ead482-f56d-5c59-a325-fd8342fdb191 | note | Construction Activity Description, Test Type and Acceptance Criteria - The basecourse aggregate shall be sampled and testing by an IANZ accredited laboratory for crushing resistance, wethering quality Index and California bearing ratio ( Class 3 & 4)
6ba4b2cb-08aa-5c51-88a6-77b85140c0d2 | note | Test Frequency - Once Per Year Or Every 10 000 m³
fdce9ef3-db5b-5014-be92-6d6d726fc754 | note | QA Record - IANZ Test Report
3d1bda34-b848-56dc-aeac-dae0af934ae2 | note | DNZ Engineer - R
3181b171-cab8-59ba-b585-fc24dbe1e178 | note | Designer Rep - H
72136807-03ad-4b03-820f-1535199c0c2a | signoff | AUTHORITY HOLDPOINT
2a7b8e83-27a4-4ee1-a6d7-3f43f579b685 | checkpoint | 2.3 - ATAP40/GAP40 - Production property testing and sampling
df2671eb-df11-5e84-ba35-6a18413110e2 | note | Standard, Drawing or Specification Reference - TNZ M/4: 2006 - 4, NZS 4407 : 1991
4814780a-ae05-5c0d-83d6-635f0214759b | note | Construction Activity Description, Test Type and Acceptance Criteria - The basecourse aggregate shall be sampled and testing by an IANZ accredited laboratory for Quality of fines as per M/4 fiqure 1, Broken Face content and WET particle size distribution Limits and shape control
c59c4503-49bf-555e-b715-4737c9feb2e2 | note | Test Frequency - Once Per Year
41b4205e-a2b0-5267-87f5-2ca6da5684a8 | note | ○ Or Every 10 000 m³
a3287230-1b97-5bab-b4b9-45bcd8d43f1f | note | QA Record - IANZ Test Report
5f721988-ceb3-559c-9ca3-c5bd9b83d681 | note | DNZ Engineer - R
678a1825-bf79-57fb-a335-fd0c0e984e28 | note | Designer Rep - H
61aa58c3-7ab7-468c-bc7b-cd2b2cf0973b | signoff | AUTHORITY HOLDPOINT
6c8567b6-4dd8-43e7-af8b-5d29c04a51bf | checkpoint | 2.4 - ATAP40/GAP40 - Testing for layor compaction - MDD
c12c79cf-d444-5841-a820-578d0a1d0943 | note | Standard, Drawing or Specification Reference - TNZ B/02: 2005 - 7.5, NZS 4402:1986 - 4.1.3
8979071b-bbb5-5687-8099-67b53e76cb23 | note | Construction Activity Description, Test Type and Acceptance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC).
b686ed6b-57bc-5ed0-80c4-e650238014f9 | note | ○ Average MDD 95% with a minimum of 92%
2157fe88-99ce-56fc-a41c-33e5ea8b0760 | note | Test Frequency - Once Per Year Or Every 5 000 m³
04220e3c-9509-5d6c-902c-3f377a72ee80 | note | QA Record - IANZ Test Report
cc51ba3a-b8a2-5b47-93d1-97e34cac9fa8 | note | DNZ Engineer - R
5eebe1b6-1822-5dd0-a7ac-7d1f7e6a8645 | note | Designer Rep - H
bfc958cb-d185-400d-8dbc-5cb8ad8e0646 | signoff | AUTHORITY HOLDPOINT
cc1d560c-12b1-4056-980f-cf4f8817254f | checkpoint | 2.5 - Reinforcing Steel
4f03de88-55bd-5a7e-8fd1-57eb302507b4 | note | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1031 - Rev 1
586a8600-94d1-5075-a207-12d0db8daae9 | note | Construction Activity Description, Test Type and Acceptance Criteria - SE62 - 665 Mesh Grade 500E.
c4c8a037-aefd-52c4-8bb6-827691bfb7e8 | note | Test Frequency - Once
26ce066a-146a-5ab6-835b-03caae60b26c | note | QA Record - Mill Certificates & Approval
b3da3a6d-85cc-5771-ae0a-ef0f6b02d556 | note | DNZ Engineer - H
51f80e34-4184-5a68-8ca2-d9f4d295e0af | note | Designer Rep - R
412b4ddb-b9b9-41c8-a2e5-910db9af75dd | signoff | AUTHORITY HOLDPOINT
88cdbabf-2b27-47a5-be15-f0afc4c02fcf | checkpoint | 2.6 - Contraction Joints
fb91dcd4-153b-589d-9b84-bb751693bbac | note | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1031 - Rev 1
7fd869c2-e59a-580b-9e82-f15bfb73fa5b | note | Construction Activity Description, Test Type and Acceptance Criteria - 400mm long 12mm Galvanised Rod in Sleeve @ 450mm centres.
6d6d2d08-c2a1-5b1e-a526-7e2d3240875a | note | Test Frequency - Once
d6a0b2c5-0f41-5a0e-8ba7-f2f7a302089c | note | QA Record - Mill Certificates & Approval
0aaa7ebd-2ac8-5349-b185-f020993dea99 | note | DNZ Engineer - H
c57599a1-aab1-512e-9649-452382d3f9ac | note | Designer Rep - R
319f5f0e-b80a-48e3-9ed1-e5026b2ca879 | signoff | AUTHORITY HOLDPOINT
728d4893-7f89-4b42-a47b-603ea57f0d80 | checkpoint | 2.7 - Tactile Indicators
47d11475-5e4a-5a78-bbed-040180f34e7a | note | Standard, Drawing or Specification Reference - TDM Standard Engineering Detail for Footpaths Section 3.6: Footpath surfaces and construction, FP009 Pram Crossing 3235599-SP03-CA-1001 - Rev 1 Note 11
ac05919e-815c-5aa6-994b-0385ca263f10 | note | Construction Activity Description, Test Type and Acceptance Criteria - 300mm x 300mm x 60mm thick yellow anti-slip precast concrete.
92cda185-11da-5db8-8af3-99aa7c825c35 | note | Test Frequency - Once
cbbf4f35-776c-5084-93b2-356c2a99d4b9 | note | QA Record - MDS & Approval
df618c67-afdd-5c12-8963-e0297c1f4e05 | note | DNZ Engineer - H
7162d791-67ad-5a5d-9730-312d7808ba4e | note | Designer Rep - R
edeefd9b-7562-40a4-b996-666134167dd4 | signoff | AUTHORITY HOLDPOINT
3b134f08-338d-4bf8-acae-c151fc5f6609 | checkpoint | 2.8 - Joint Sealer
3bcd87d3-94d7-5536-9e05-2f7e86041a8b | note | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1031 - Rev 1
04ae746b-c84f-5b91-afca-0ad1a9616e76 | note | Construction Activity Description, Test Type and Acceptance Criteria - SIKAFLEX 11FC or similar approved product.
75917124-52e1-500d-9fb5-d0267df91763 | note | Test Frequency - Once
02b8f67d-6080-5e64-8ccb-7d9c72581995 | note | QA Record - MDS & Approval
0483b9a2-b80b-5bec-9aeb-843f8889e16b | note | DNZ Engineer - H
8fe434c9-dadb-5814-94ff-17c436aee7e3 | note | Designer Rep - R
6ef60587-60c7-4878-8ffa-0829d5bed5ce | signoff | AUTHORITY HOLDPOINT
2a17166c-3d29-44f9-877b-ed5467fb28c0 | checkpoint | 2.9 - Joint Filler
cac3bb19-08e7-5441-9af6-1e88b0901d64 | note | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1031 - Rev 1
e4fbe897-5d32-5f36-a4cc-1e7e2fcb0d35 | note | Construction Activity Description, Test Type and Acceptance Criteria - 8mm Polystyrene joint filler .
e42ee09b-4576-50b4-a72c-38bebc4a0020 | note | Test Frequency - Once
fe7fa4b6-761b-57cd-b906-1fe5ef46442d | note | QA Record - MDS & Approval
365bab6b-35db-55e2-a685-002b491d3cc2 | note | DNZ Engineer - H
a90d3690-89df-58b0-8559-7b1fdef8a466 | note | Designer Rep - R
81892fd5-15df-4680-857b-1f95a929656a | signoff | AUTHORITY HOLDPOINT
ca6fb8fe-d095-48c9-9ebc-d2a8641bef35 | checkpoint | 2.10 - Stitching Reinforcing Bars
530285e2-8abd-53f5-b104-fb43dbdde24d | note | Standard, Drawing or Specification Reference - AT Detail FP002
10f0e9e5-6a27-52ba-bb90-69b36abe7a43 | note | Construction Activity Description, Test Type and Acceptance Criteria - 900mm long 16mm diagnonal bars at 45̊ to any chamber. Grade 300
a545b410-6206-50b9-98e0-1d4a92a1de8b | note | Test Frequency - As required
33cf44a1-8e70-52ff-a3e3-ac07e955b9ee | note | QA Record - Mill Certificates & Approval
b32dfb10-362f-56df-b32c-b372e3cf115b | note | DNZ Engineer - H
61dbee1a-db61-5453-a492-5a9359ea35fa | note | Designer Rep - R
b77fd9fc-3d19-4f52-8066-83d9675fe605 | signoff | AUTHORITY HOLDPOINT
d9c571c2-fe6a-4944-a246-865e6aef0f6e | checkpoint | 2.11 - Geotextile
df409957-12dd-59e7-8389-a9cf211ef99c | note | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1031 - Rev 1
35f5173d-e615-5019-b4e4-bef949657160 | note | Construction Activity Description, Test Type and Acceptance Criteria - A29 Geotextile Bidim, or similar approved product.
4eb028d5-a0d2-52cd-b080-a0567242c404 | note | Test Frequency - As required
d5aa7822-9031-5a05-92a9-fe2d9b0d8392 | note | QA Record - MDS & Approval
623d2c14-1736-57bc-a328-66eed502ca7c | note | DNZ Engineer - H
66d31ba2-9bc0-5866-82b4-faf1d2f5626b | note | Designer Rep - R
96fc0178-240e-48fa-a739-2ef19b7c7421 | signoff | AUTHORITY HOLDPOINT
498f2c53-a991-4f73-89de-490813bd0563 | checkpoint | 2.12 - Geogrid
e66b031a-65fa-5c52-b104-5ae9511ee74b | note | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1031 - Rev 1
981da877-d527-5657-9c3d-0ba907caae6b | note | Construction Activity Description, Test Type and Acceptance Criteria - Tensar Triax 170 Geogrid or similar approved product.
c5339f99-244d-579a-a2db-353465d6dd78 | note | Test Frequency - As required
3a737c87-792b-5944-9b2a-32c44d8b7556 | note | QA Record - MDS & Approval
cd5e77b7-3569-587b-b944-b5e7f6f4f4da | note | DNZ Engineer - H
6ec924df-ee5e-5e63-b814-e43e68be9da4 | note | Designer Rep - R
6495eba6-b87c-4914-a61c-f81530e161e7 | signoff | AUTHORITY HOLDPOINT
acac2160-d80a-46d3-b4f3-68b899ea04d0 | section | 3 - CONSTRUCTION ACTIVITIES
759a03ce-8fb8-4ca5-9e69-32e15a64fa7f | checkpoint | 3.1 - Footpath set out and excavation to subgrade
b0a29b30-764c-5f2b-97a8-0e8d5d528c7c | note | Standard, Drawing or Specification Reference - IFC drawings and Models 746-22-052-PS Page 9 Table 1
5ac1d67d-beb7-59c3-b5f3-4838f4eaeb7e | note | Construction Activity Description, Test Type and Acceptance Criteria - Straight edge check ensure it is within 20mm from 3m straight edge, parallel or across each lane.
0abf8ba5-0979-5296-bb29-a85fd886b107 | note | ○ NO WATER PONDING ON SUBGRADE.
8ca207d6-8f28-5c23-b81f-13b5b3b215f6 | note | Test Frequency - Every 5m
787f297d-d029-55d0-8c7c-b709da0a714b | note | QA Record - As-Built or Stringline checksheet
6a8e29b1-e644-57ca-b118-e1d3eee85c25 | note | DNZ Engineer - H
aadb307f-568d-4b66-a396-9066b173bad4 | signoff | AUTHORITY HOLDPOINT
7d29143f-2879-4a5f-b098-2ebd8e53c841 | checkpoint | 3.2 - Foundation - Subgrade Testing (Scala)
5af1b157-b42b-5c03-8736-74e84a2bceda | note | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1001 - Rev 1, Note 12 746-22-052-PS Page 9 Table 1
5c492b44-f10d-53b2-85af-9f1784687eb4 | note | Construction Activity Description, Test Type and Acceptance Criteria - If caly based material is encountered - ensure subgrade has a minimum CBR of 3
f2215280-1a3e-54a9-9667-74ef5adc0fea | note | ○ Test to a depth to 1m, not less than 3 blows per 150mm for CBR 3.5% and 3 blows per 200mm for CBR 2%.
1368d29c-59bb-524a-983c-e85d734e7aea | note | Test Frequency - Every 25m²
c6305a30-9e8b-59f1-8483-deaff92830e5 | note | QA Record - Scala Test Results - CBR of 3
4d3c21aa-4e06-5ccd-b4a8-f476ec9acf8f | note | DNZ Engineer - H
5e4f218c-c5d0-5d0a-b1b4-371b841bce01 | note | Designer Rep - R
6eb7586f-b4be-40a0-a5b5-1354a6587cd2 | signoff | AUTHORITY HOLDPOINT
7af87028-ec5b-4465-8104-4964844502d5 | checkpoint | 3.3 - Foundation - Subgrade Testing (Existing footpath) (Clegg)
b10c4ee1-ab94-560f-b935-cc8e47d8b968 | note | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1001 - Rev 1, Note 12 746-22-052-PS Page 9 Table 1
a1f3a1f0-ab35-5bb6-a8ba-4905dd9b5e6f | note | Construction Activity Description, Test Type and Acceptance Criteria - If granular material is encountered - Minimum CIV of 12
feb0fcf3-a171-5ac9-b74c-5a4c2aa9d4fd | note | Test Frequency - Every 10m
3e6aa958-2567-5052-9ee4-69bfc8580b0f | note | QA Record - Clegg Test Results - min CIV 12
3484f796-2011-5659-8b60-3c294dc52706 | note | DNZ Engineer - H
182a9543-f496-5b30-908a-cf8b2aaf7a47 | note | Designer Rep - R
622373aa-f964-4e72-a887-c0ca089c45c0 | signoff | AUTHORITY HOLDPOINT
0a7c41cf-11fd-4909-9597-a5b708c3d4e2 | checkpoint | 3.4 - Place Geotextile
8a0a2562-ac45-5650-9ddc-5b0c96373616 | note | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1001 - Rev 1, Note 12
4f9e1ad4-4332-534f-9941-915251e5fb84 | note | Construction Activity Description, Test Type and Acceptance Criteria - An underlying geotextile layer is to be laid between the granular material (GAP40) and the Subgrade.
68ee8095-7202-5f4c-888a-a568dba0b347 | note | ○ A29 Bidim, ensure top, bottom and sides are coverd.
4d94397b-48fe-5304-b627-8e6343757119 | note | Test Frequency - Per inpsection
c8e8b86a-b714-5769-a883-e4fce2720ed6 | note | QA Record - Checksheet, Photos
a42a9daa-3096-511a-be4b-e507b0aacbce | note | DNZ Engineer - I
d5dd85aa-638e-4904-bd50-b47da07a3aee | checkpoint | 3.5 - Undercut (If required)
2594a804-7c38-530c-a911-0b543d68e43e | note | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1001 - Rev 1, Note 12 746-22-052-PS Page 10 Table 2
df0cbd44-43e6-5aa4-b11b-7d26fb756fec | note | Construction Activity Description, Test Type and Acceptance Criteria - Prior to subgrade undercutting, the Engineer shall confirm the extent of subgrade undercut and the colume if in-situ material to be removed.
9d3812b4-c5fb-5b1b-8110-49dfb802a7f4 | note | Test Frequency - As required
45684d06-dbbf-51e9-9c2d-deae9ef2e3a8 | note | QA Record - HP Release
993a379b-f344-5a2c-868f-22e24217949e | note | DNZ Engineer - I
ecc4e3d0-ab74-5b42-a5c2-28362f017aad | note | Designer Rep - H
84e61d4d-dfdf-4e72-8a19-a0bfcef0c768 | signoff | AUTHORITY HOLDPOINT
36893440-f90b-409f-a32f-7c3a94f08ba5 | checkpoint | 3.6 - Place Geogrid (Only required for undercuts)
7269be83-ac0e-5950-8a0a-f496ea5850a1 | note | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1001 - Rev 1, Note 12 746-22-052-PS Page 10 Table 2
f98456a0-40c5-509c-847d-2d09699a2775 | note | Construction Activity Description, Test Type and Acceptance Criteria - Placed above the geotextile prior to backfilling.
43d493f3-df6e-5f68-8600-c000f02c95c3 | note | Test Frequency - As required
67eeca39-ad2e-5fa7-a166-129a4bf7c231 | note | QA Record - Checksheet, Photos
6f74799b-b6c7-57b8-8874-61959534a19d | note | DNZ Engineer - I
9efc3886-90d6-4b98-91d0-301c856f0a0f | checkpoint | 3.7 - Place and compact Basecourse GAP40
b8b4e6e6-4fc8-505a-9112-63d2a3d0f55d | note | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1001 - Rev 1, Note 9
92ee5142-2d13-5e0c-9c21-376185964a2f | note | Construction Activity Description, Test Type and Acceptance Criteria - 100mm thick layer compacted where no undercut is required
131c967e-0aee-5d65-bc8c-e33640d0fdc9 | note | ○ Where undercut is required: Contractor to notify Engineer.
dc648beb-95cf-51b9-b11e-daa9ae6c822a | note | ○ Minimum CLEGG CIV - 12.
814d2ed4-e7ae-519c-898b-ce4f6450fcff | note | Test Frequency - Every 10 m
0db29abc-0291-5be5-926d-56f2df7bee0d | note | QA Record - Clegg Test Results and photos
8b9b0c73-38d5-5f5b-b960-00908edb33ca | note | DNZ Engineer - I
b474359c-6449-4c59-b690-ef2d44ae03bc | checkpoint | 3.8 - Timber edging
b8ec62fc-633f-514d-ba03-9cf3dfa30908 | note | Standard, Drawing or Specification Reference - IFC Set out
6a55691d-2d98-55a3-86ac-a4fa170e4c25 | note | Construction Activity Description, Test Type and Acceptance Criteria - All footpaths shall be contained by either a concrete kerb or edging, or by treated timber edge boards, which shall form part of the finished work. Minimum width 1800mm and maximum 3000mm 150mm thick.
0e1645c4-1add-527f-848d-63759c7c434c | note | Test Frequency - As required
43f142db-b542-5ec3-bd37-48737eda1bad | note | QA Record - Checksheet, Photos
4d6912d8-5b08-5536-84c6-6b004b29b952 | note | DNZ Engineer - I
b1b4a5cf-d92a-4d6d-a5ac-8cfbe751c599 | checkpoint | 3.9 - Place Reinforcing Mesh
13d80696-806d-576f-90fe-3b69ac213082 | note | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1031 - Rev 1, 3235599-SP03-ST-3002 Note 6.1
ed2c833c-daab-5435-b5ad-885638385bf6 | note | Construction Activity Description, Test Type and Acceptance Criteria - 665 mesh, centrally placed.
028e2bab-1830-50cf-9849-4f3b66446636 | note | ○ Minimum overlap of 200mm between outermost cross wires.
c290e1c8-00aa-56c6-bdd6-0eff611eb7a7 | note | Test Frequency - Every pour
8aba9b19-659b-5993-962c-b92fd628bed2 | note | QA Record - Checksheet, Photos
1411f7dd-02cd-5189-b797-c6858e8e8551 | note | DNZ Engineer - I
1940521d-1781-47f8-86c5-59f45135b8a3 | checkpoint | 3.10 - Place Contraction Joints
66384c3e-54ba-541c-bd0f-88ddc5040780 | note | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1031 - Rev 1
b735b860-6eb0-5a11-ae0d-cdc152e6667a | note | Construction Activity Description, Test Type and Acceptance Criteria - 400mm long 12mm Galvanised Rod in Sleeve @ 450mm centres.
a9517bef-0b60-512d-93cf-7b3bb2ea7382 | note | ○ Installed every 15m.
868903d2-2265-5cfa-9de8-96addae91246 | note | Test Frequency - Every 15m
5de791d4-af7f-5186-ba77-977d69604c43 | note | QA Record - Checksheet, Photos
095055f3-c905-5e08-81c6-0b9c3bc61751 | note | DNZ Engineer - I
11b08d43-00bd-46e6-8867-3f7989be57fc | checkpoint | 3.11 - Place Tactilies
b9f123a7-f877-58ed-bab1-d389ad3d501e | note | Standard, Drawing or Specification Reference - TDM Standard Engineering Detail for Footpaths Section 3.6: Footpath surfaces and construction, FP009 Pram Crossing 3235599-SP03-CA-1001 - Rev 1, Note 11
3e679336-e140-56ff-b28b-ee202f403ad0 | note | Construction Activity Description, Test Type and Acceptance Criteria - Tactile pavers shall be bedded on 100mm thick 20Mpa concrete.
fbabf4db-517b-5fec-9c29-c3bc4f8877b0 | note | ○ Orientation and set out shall be approved by the Engineer and or ATOC Representative prior to concrete placement.
b0f879d7-c7f8-5c7a-99df-d3a0ee1cda3a | note | ○ A one coat sealer with UV stabiliser is to be applied for maintenance and durability reasons
50925fd8-0ca4-5e7e-b6f7-9bfc6ce5a2c6 | note | Test Frequency - Per installation
5a4397d5-25f5-5ff5-9fdb-ba85fb38bfa1 | note | QA Record - Delivery dockets, Checksheet, Photos
46d92927-160b-5031-abe9-9f014f9f2ec2 | note | DNZ Engineer - H
936b6d09-85b3-5b30-b865-968449c2112f | note | Designer Rep - I
a0763c65-c674-44e6-a40a-3571626c3b20 | signoff | AUTHORITY HOLDPOINT
40a579ba-92c8-45d3-9713-82224eb1f136 | checkpoint | 3.12 - Place reinforcing Stitching Bars
719eb90e-4c10-59e2-878b-ee57838a3dd1 | note | Standard, Drawing or Specification Reference - AT Detail FP002
f977906d-d7aa-59e7-ada4-e716b6351743 | note | Construction Activity Description, Test Type and Acceptance Criteria - Stitching bars to be included around Manholes chambers, valves, hydrants and lightpoles to prevent cracking at the re-entrant corners.
4947920b-59fc-5d17-8ad3-2077876ea10f | note | ○ 900mm long 16mm diagnonal bars at 45̊ to any chamber. Grade 300
00b6327d-1696-584b-b806-2ce1787e93a9 | note | Test Frequency - As required
645ee32f-e56a-5d1d-9e30-7112845d6f9e | note | QA Record - Mill certificates and photos
8aef3e91-d532-5606-a65c-fbccf84bf9e0 | note | DNZ Engineer - I
a4292d1c-f1ac-49e8-a1ad-57b19e81f11c | checkpoint | 3.13 - Concrete Pre-Pour
4768b0b7-eafd-5e6f-bd62-2a8d57d64f1f | note | Standard, Drawing or Specification Reference - AT Detail FP001, 3235599-SP03-CA-1031 - Rev 1
22ebdfe0-ef22-51c7-8123-12820771bc24 | note | Construction Activity Description, Test Type and Acceptance Criteria - Ensure pre-pour checks has been completed with the Engineer prior to concrete pour, target concrete cover 50mm around each edge
0ddc06c0-da4e-5a84-8ef6-4434338aa58c | note | Test Frequency - Every Pour
e812e26b-4612-5442-ab4c-eaea58afd916 | note | QA Record - Pre-Pour Checklist
2745c096-e837-56d3-9b5c-d0e711d98da4 | note | DNZ Engineer - H
35ae51e8-f796-5d9e-9c43-13a2b25412a8 | note | Designer Rep - I
3089a663-1869-4562-a7a2-3f2c9270e61b | signoff | AUTHORITY HOLDPOINT
61fddb97-0d8c-4dc2-9a6f-3236427a4d86 | checkpoint | 3.14 - Concrete Pour
64345507-8741-5fa3-aba3-22bb2664c4c1 | note | Standard, Drawing or Specification Reference - AT Detail FP001, 3235599-SP03-CA-1031 - Rev 1
dfe48f8b-5140-5b9d-9db6-4a2708549e64 | note | Construction Activity Description, Test Type and Acceptance Criteria - 2% Cross Fall Towards Carriageway. (1% min. 3% max.)
72c1117b-fed4-5850-88f1-371a20a8631c | note | ○ 20Mpa Concrete with 4% Black Oxide, maximum 19mm aggregates.
3f62ba45-22a3-5489-ab29-8c83c3b89451 | note | ○ Slump 120mm (±30mm)
b461f654-8d5d-59ad-8706-ef418acd9d4c | note | Test Frequency - Every Pour
f2411308-3701-5f21-a189-618acadb2488 | note | QA Record - 7 day and 28 day Concrete Test Results from supplier, Slump Test Results (onsite)
10edeb23-41ab-5fa4-be4c-ee733051cf62 | note | DNZ Engineer - W
f0d63463-59d5-5dcf-af3c-e71290612f74 | note | Designer Rep - W
7998bdd6-290b-4721-9aef-3d8936f22b71 | checkpoint | 3.15 - Concrete Finish
7306a334-fefd-528a-a973-079e45bea852 | note | Standard, Drawing or Specification Reference - AT Detail FP001, 3235599-SP03-CA-1031 - Rev 1
44b61a99-9199-5d05-a35f-d7bc3eecb5fd | note | Construction Activity Description, Test Type and Acceptance Criteria - 20Mpa Concrete with 4% Black Oxide, maximum 19mm aggregates.
2bc38c51-1192-5f9e-9b22-455236fb89e8 | note | ○ Exposed finish apply surface with Rugasol C.
88753f82-94fd-5891-a4af-0948c7cf709b | note | ○ Exposure of the aggregate should begin when the surface can bear the weight of the paviour without making a surface impression deeper than 2mm. The surface shall be sprayed and brushed across the entire surface using a medium-bristle broom (U5 finish) and a continuous water spray to wash away the cement paste, exposing the aggregate evenly to an average depth of 2-3 mm.
2a96ad23-9bec-5006-847f-3e7c30a2d760 | note | Test Frequency - Every Pour
7e73733d-48a5-559c-ae07-9224b0d14800 | note | QA Record - Post pour inspection checksheet
15103c68-d895-57cb-8c6c-93da9a9a1256 | note | DNZ Engineer - W
bd05377f-f6a1-400a-a56b-70c94bff16ce | checkpoint | 3.16 - Saw Cut Joints
bd847148-e5e6-57f3-a4ea-db48a2084bd3 | note | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1001 - Rev 1, Note 5, AT TDM
e2033d7b-4d99-5fc2-bd43-7a3265cb73f9 | note | Construction Activity Description, Test Type and Acceptance Criteria - Saw cut joints to be constructed to 1/3 of the concrete depth at a spacing of no greater than 3m.
d80d09c0-f2a6-5cdf-8943-5482b9665ce7 | note | Test Frequency - Every 3m
feca5fdc-8e82-5661-bc8e-b6f8b9874f27 | note | QA Record - Photos
30e4dcf5-b718-543d-acba-d819daf84539 | note | DNZ Engineer - W
f742da13-72a5-49d3-9916-9be496aea094 | section | 4 - FINAL RECORDS
57b3bf18-4684-4653-9818-3cde7511ea1d | checkpoint | 4.1 - Construction Record Compilation
2c07629d-8a2b-54fe-8e52-eb1324e58252 | note | Standard, Drawing or Specification Reference - N/A
b0af1e1a-dd4c-5257-9b6d-e72b13230831 | note | Construction Activity Description, Test Type and Acceptance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
af1865dc-f3c4-5492-817a-46929205a2b4 | note | Test Frequency - Once
126fb380-39cf-5a9f-b6dd-b4ec95c5f6af | note | QA Record - QA Records
bca13338-a5f9-50a0-a988-28c348217b46 | note | DNZ Engineer - H
65793536-0d34-5505-a8b0-71fa31f09e18 | note | Designer Rep - R
3d4a84aa-72de-41c1-a993-63ba557b828d | signoff | AUTHORITY HOLDPOINT
bbbf3776-1bd8-4c04-b49f-f23aea6f7379 | checkpoint | 4.2 - Survey Records
d87ca04e-a24c-5e60-b7ed-9d594345074f | note | Standard, Drawing or Specification Reference - N/A
ba290f35-7e92-5b07-be53-04c12050197a | note | Construction Activity Description, Test Type and Acceptance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
2c19a64f-d74a-5f5b-96ec-11f241d4e53a | note | Test Frequency - Once
d81443bb-0702-5e4d-8d83-3652ba47472b | note | QA Record - As-Built
55efd879-998a-5868-aa35-3b4615849a64 | note | DNZ Engineer - H
553152bc-74e9-536b-9b27-177a83675e2f | note | Designer Rep - R
64f608a4-734c-4f6a-84f9-0cfba9742575 | signoff | AUTHORITY HOLDPOINT
1ded465c-067a-446b-ba99-f4a73cdf612c | checkpoint | 4.3 - Redline Drawings
0b6fce22-0017-5f47-9de0-ff53353c5775 | note | Standard, Drawing or Specification Reference - IFC Drawings
3e5d028b-a688-5459-a157-0e086149454c | note | Construction Activity Description, Test Type and Acceptance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.
3e42d55b-7fc6-56fa-b69d-cd0dfc653be0 | note | Test Frequency - Once
ed938605-2786-5f7a-a51b-462110e0883b | note | QA Record - IFC Mark-Up
a868f4a2-548d-5ab6-b053-eef2eb439664 | note | DNZ Engineer - H
a42ce858-1b42-5f3b-8dd6-d3f039632a58 | note | Designer Rep - R
3c296b0b-fc34-4569-9c68-fb829f2803d8 | signoff | AUTHORITY HOLDPOINT
17650747-28fc-4c0c-9779-581decf71b04 | checkpoint | 4.4 - Defect, Snag and Punch List
e0372f88-056f-50ec-a68c-0c92a8f879f2 | note | Standard, Drawing or Specification Reference - DN1212-DOW-PLA-PM-0005 QMP
298a2902-547a-5754-ac12-72295a08aece | note | Construction Activity Description, Test Type and Acceptance Criteria - Update the project Defect, Snag and Punch List Register
e6d58a23-1f22-572d-b418-adf4f81ca483 | note | Test Frequency - If required
0bb32fa6-b105-5cf7-9049-c64c3b566071 | note | QA Record - Snag Register
8191f135-b4f6-53a2-ae8f-ffb1b42254df | note | DNZ Engineer - H
53fc376e-a875-559e-aa34-61e13ca21022 | note | Designer Rep - R
252f6ab3-cf0b-417a-925b-ade7c1d4866c | signoff | AUTHORITY HOLDPOINT
2e78b82b-cd43-4c6b-a16f-65f253533843 | checkpoint | 4.5 - Non-conformances
20834ce1-be45-5453-9654-c681313e2c9a | note | Standard, Drawing or Specification Reference - DN1212-DOW-PLA-PM-0005 QMP
998e97b6-c635-5dfd-97fc-33281ada41ce | note | Construction Activity Description, Test Type and Acceptance Criteria - Non-conformances reports to be raised when specification not met. All non-conformances within the area under review need to be listed on the NCR report.
0b946165-2454-5e24-ad14-d5710186e997 | textbox | NCR Reference
1d3d1992-bf41-5ab9-aba2-be0401483f57 | note | Test Frequency - When Required
6a366753-8173-5011-9cfd-a56ef14ab363 | note | QA Record - NCR Forms on InEight
a7fca9fd-1980-5db5-a09a-079a606141c4 | note | DNZ Engineer - H
0f9321e0-7e2b-51a8-8f9b-6638b5d1fedf | note | Designer Rep - R
0bf85f53-a0b9-4731-a5c7-861b773067f1 | signoff | AUTHORITY HOLDPOINT
bacc6ad1-527f-40e9-9629-055a96bd7b8f | section | ITP APPROVAL PROCESS
a5a15efd-c190-42a4-901f-a8519390c8cc | checkpoint-no-value | ITP APPROVAL PROCESS
0233959a-8503-58b6-b606-ccccb0c892d2 | note | Prepared By: Quality Engineer - Nas Matar
db59bec0-4ac7-59ab-b396-92170a58fe82 | note | Reviewed By: Project Manager - Dan Trotman
bf7ee570-795a-5ac3-811d-909a41e60090 | note | Reviewed By: QA Manager - Cordelia Gridler-Brown
efdcecdb-2249-5a11-b1d7-f928a1f8648d | note | Reviewed By: Design Engineer - TBC
56648f48-eea6-5cea-ba06-339dcd6abc9a | note | Reviewed By: AT Project Manager - Mike Robertson
86fa02dc-9659-572d-8557-938861e3d0fd | date | Date:
7f52a519-fb14-43bd-bc63-d1ed59a6fe31 | section | FINAL ITP CLOSE-OUT
c200d87f-d3e1-4bea-84f5-355bd68d7827 | checkpoint | FINAL ITP CLOSE-OUT
5fb7b146-c587-51f3-be06-681b229b5635 | textbox | Downer Project/Site Engineer:
1fdff931-cfb6-5a29-a8c7-d78ebd33837c | textbox | QA Mgr./Engineer:
72fa00e5-b3ad-501f-857e-7e3226e0dda4 | textbox | Designers Rep(Assistant):
3004942d-c363-5e9e-8b40-c88a93bc7019 | date | Date:
56c16199-844e-4241-bfe5-0ff00677c155 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
b2d33f8e-a610-5e26-b317-8d1c24480443 | textbox | Contractor's Rep Name:
1aa3abaf-132b-5fa2-99b0-3ffd428483be | textbox | Engineer's Rep. Name:
94fa42c2-3074-5d8e-8e21-dd82d3fc795d | date | Date:
92bd5454-ad17-432b-b5cb-e17c16463c71 | signoff | Add Signature
f5099d7b-faa4-49e2-92f0-ca8eb2463e82 | checklist | DN1212-ITP-002 Pilling Rev5 | itp | DN1212-ITP-002 Pilling
6230ea6e-e84b-41e0-bc06-077189e51a06 | section | 1 - PRELIMINARY AND GENERAL
04424eaf-7ec1-4905-87a1-c1274a719de8 | checkpoint | 1.1 - IFC Drawings and Specification
d52ba76f-2dfe-5767-a94c-6a3630659d46 | note | Standard, Drawing or Specification Reference - ACC
c5283fea-dbea-5c99-9b46-fa28cdd09322 | note | Construction Activity Description, Test Type and Acceptance Criteria - A minimum of two weeks prior to construction: document review. DWG’s are for construction or as per instruction
53fe6c38-9d40-5414-be2e-97e7cb339c39 | note | ○ Works done in accordance with Project specification
3c795a21-2f09-533a-b64f-5c062eae623a | note | Test Frequency - Once
64079b46-e3a6-5674-aa27-76d8216c42fa | note | QA Record - N/A
384b99c1-2d18-5e2b-9a06-a7060a28d0c8 | note | DNZ Engineer - R
2d1d7174-22fc-526b-a8dc-799a51372c62 | note | Designer Rep - H
0984bd00-e098-4d7f-8404-a8baf0711411 | signoff | AUTHORITY HOLDPOINT
2e958160-694a-41ea-a790-4dc8de8cffd1 | checkpoint | 1.2 - Method Statement & JSEA Development
8d7a94ee-bd4f-5dff-a202-129978656cb1 | note | Standard, Drawing or Specification Reference - The Downer Standards (TDS)
e1e5f04c-90a7-5e3a-8c9a-96238ad5e6c8 | note | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction: document review.
8d1473d3-b298-5c08-ba33-bf6c97d2f2dc | note | Test Frequency - Once
d7e6530e-5fb7-50db-a3ff-bfc3902709c1 | note | QA Record - Method Statement & JSEA Completed & signed by relevant authority
578d429f-0722-5904-86b9-0907e153122f | note | DNZ Engineer - H
8ac9b53e-63ac-5c20-ba3a-93ee74ddcb7c | note | Engineer's Rep - R
71fa31be-3994-5694-ba0d-42e22613ca5c | note | Designer Rep - R
be0322bc-193c-4f30-b105-ef44f4ba5c81 | signoff | AUTHORITY HOLDPOINT
ac535b3b-e8c5-4150-a0c2-1edc99d6957e | checkpoint | 1.3 - Permit to Dig
8fae22b0-5474-5f09-8f26-7bb59e4016db | note | Standard, Drawing or Specification Reference - DN-ZH-ST043 Ground Disturbance SP03-ST-3150
d9c27ffe-49cc-5f53-8f77-6eb11593fcc7 | note | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction, all services shall be located ahead of construction.
df004eaa-9379-58a5-9d65-e3771e21804f | note | ○ Permit in the work package.
9fa9e705-33d9-54d4-88ae-864c989636aa | note | Test Frequency - Permit issued each week
79b8a620-1c66-5658-84ff-d9a48c2efa64 | textbox | QA Record - Permit number
fd74c72d-9bbe-5734-a59d-e39833ccfa31 | note | DNZ Engineer - H
25eb8ea3-14a6-4f71-8e7d-57e710ecd207 | signoff | AUTHORITY HOLDPOINT
a45999e7-af9b-441c-800a-0d1d2e238fe1 | checkpoint | 1.4 - Survey Model
bcec3c14-f1d6-5720-80ab-598002d470bc | note | Standard, Drawing or Specification Reference - N/A
bc82d445-66e7-5212-8375-c69f2b7333da | note | Construction Activity Description, Test Type and Acceptance Criteria - Model Review.
754d3252-0191-5b40-ac4c-062d53c00a46 | note | Test Frequency - Once
94996765-a5ce-59a0-817c-bab885d5a50e | note | QA Record - Visual Inspection & measurement Survey Check set out as per design
55ca2b8c-e404-512a-a453-f029866b7f0d | note | DNZ Engineer - H
22709567-94c6-41be-a8d8-d1b2b1da3db9 | signoff | AUTHORITY HOLDPOINT
ee4ffc79-ec12-46a6-b918-67bd01aad9cd | checkpoint | 1.5 - Lift Plan
5a27eae7-eb2f-5f01-9be1-5c2cc00ddb48 | note | Standard, Drawing or Specification Reference - DG-ZH-ST047 Cranes and Lifting Equipment Standard
9f90b723-e720-5296-bf12-398b347705d3 | note | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction. For lifting of casing, reinforcing cages, tremmie pipes etc shall be in place ahead of construction, a Complex lift plan for the Crane and lift card for lifting with Excavators.
47438308-9bfa-5475-bfac-da8b08a25adb | note | ○ Lift plan included in the work package.
18d359c0-9783-58f6-ae27-a458be9203bd | note | Test Frequency - Prior to Construction when required
8a4f9599-2a38-5e43-abd3-4a013c6247a1 | textbox | QA Record - Permit number
7be9df51-662b-5d62-894f-c48cba450ca9 | note | DNZ Engineer - H
d91ab962-330a-44f5-9b50-8dbe194fd769 | signoff | AUTHORITY HOLDPOINT
96b3e7b7-1e9f-439a-b9b2-da13db0adeea | checkpoint | 1.6 - Hot Works
84a7c0af-d4e7-543e-9487-4a14602aab58 | note | Standard, Drawing or Specification Reference - DG-ZH-ST041 Hot Work Standard
0ca3e4f8-46c4-599d-b452-63eb02969384 | note | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction,for welding, gas cutting, grinding etc a Hot work permit shall be in place ahead of construction.
83d13bda-4a36-5b75-ab66-1d41942c9914 | note | ○ Permit in the work package.
8e9ff973-0030-533c-8e81-648c0a13d4cb | note | Test Frequency - Prior to Construction when required
57912fcb-4b70-598e-a5ce-5d181563ba26 | textbox | QA Record - Permit number
9228dac7-a1d2-58d6-8fed-7b32438652ce | note | DNZ Engineer - H
42a8ea4c-82ae-4868-a28b-bba746ecc679 | signoff | AUTHORITY HOLDPOINT
7b70bd6e-019d-4b52-8fe8-56642bfbb41d | checkpoint | 1.7 - Working at Heights
2033e872-d66d-5997-a6d0-46669298d833 | note | Standard, Drawing or Specification Reference - DG-ZH-ST042 Working at Heights Standard
d43b20e9-11bf-5b12-86b9-21c2886fca2a | note | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction, permit in work package.
d4cb3525-cf12-5fbe-9a5a-c4a52ed00f5c | note | Test Frequency - Prior to Construction when required
0d3824ea-b2e5-5396-9de8-26896245a192 | textbox | QA Record - Permit number
602ec510-e3c4-5dfa-81b3-2d6b5075c8c2 | note | DNZ Engineer - H
92a583dd-e025-4b29-87ac-729f3c9d180f | signoff | AUTHORITY HOLDPOINT
86f7874e-d681-468a-8487-17dc53e3ff79 | checkpoint | 1.8 - Permit to Pump Concrete
c33f9c49-bd14-59ff-bc8f-01d60b6a64d6 | note | Standard, Drawing or Specification Reference - NZ Concrete Contractors Association
820a9052-318b-5679-906a-e3ca4fe9ccde | note | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction, permit in work package.
8ce5846e-36c0-5410-be61-97face863596 | note | Test Frequency - Prior to Construction when required
13b630f8-2cf7-5bd5-ba5b-1e2122de6111 | textbox | QA Record - Permit number
ec6052dc-38a0-50c7-a722-5ca3b0df00c7 | note | DNZ Engineer - H
cf897af2-8a55-418a-bb51-0ce8b16ccd16 | signoff | AUTHORITY HOLDPOINT
14b4c0a5-4bcd-4bea-b91a-8ccc3818ad0d | checkpoint | 1.9 - Permit to Enter (Rail Corridor)
019fed5f-1d87-5684-bb23-8488117ab4c4 | note | Standard, Drawing or Specification Reference - DG-ZH-ST010-NZ Working in the Rail Corridor
9a492842-d16d-5c6c-b04d-a33958acff06 | note | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction, permit in work package.
ab1464d6-6ad5-5c81-8472-f35dda92ace2 | note | Test Frequency - Prior to Construction when required
0da4d932-7c27-547e-98f4-399de7c8afb8 | textbox | QA Record - Permit number
11ab2258-1337-59ca-826a-9ada2b00c9f9 | note | DNZ Engineer - H
c1268762-8b30-4e1d-838d-9cc3d5af985a | signoff | AUTHORITY HOLDPOINT
23591cc3-7826-4d13-a337-9d41f106d650 | section | 2 - MATERIAL APPROVALS
a13b62ce-30ed-41e8-820d-1cbe655acfcc | checkpoint | 2.1 - Concrete Mix Design
d5fd79c0-6a4f-5b1c-a0f0-46b4e22faee0 | note | Standard, Drawing or Specification Reference - 746-24-874-AC Table 4 C0601.4.4, C0610.2
30c43346-c30f-5523-b0d2-70cc4e5d7033 | note | Construction Activity Description, Test Type and Acceptance Criteria - 40 Mpa, 11mm Aggregate size. Self Compacting.
6f0d3157-f3a4-561d-9053-57736e2516ef | note | ○ Target Slump 550mm ±50mm
b7d41079-8da4-5284-8836-7eb75b3666e1 | note | Test Frequency - Once
4f18fe30-1bbe-50e3-8631-072edce7f726 | note | QA Record - Approved Mix
f2a36a82-3f6b-5ae8-9ff4-6a2ee5add953 | textbox | InEight Reference
0420d78f-0355-5bb2-b2af-489391b3c90b | note | DNZ Engineer - R
e54078c2-6d4d-5fe6-99a5-f31b4584955c | note | Designer Rep - H
81110b79-0ea8-45c4-b939-c913e3c8814e | signoff | AUTHORITY HOLDPOINT
b7ab0ccc-e3c4-43cd-b044-ba8773bcd0a0 | checkpoint | 2.2 - Steel Casing
6ebf6311-3146-5cab-9f00-b6202de19985 | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3150-1 Note 4.0
9a0b1002-3289-50ce-9c0c-4dd902e242d4 | note | Construction Activity Description, Test Type and Acceptance Criteria - Details of the proposed casings shall be submitted to the Engineer for review and approval.
730e45ef-14c9-5d67-a343-c3697b61b952 | note | ○ 1219 OD permanent steel casing grade API 5L X52, thickness 16mm.
141e58e8-ed30-5c87-a28f-da081de47343 | note | Test Frequency - Each Casing
bde4a1d2-8952-5c02-a0a2-5b69e1fea656 | note | QA Record - Mill Certifcates, QA Report
1e440670-ced1-54a0-b8a8-4158a981c457 | note | DNZ Engineer - R
cbbdfd82-46c0-5d62-bb3c-6169388ec4d6 | note | Designer Rep - H
d398a49d-35a0-4bbe-824f-606a394d5b22 | signoff | AUTHORITY HOLDPOINT
02625370-1f2f-4dc5-9939-50cef2a8b8ab | checkpoint | 2.3 - Reinforcing Steel
59254380-9a73-5ce1-9236-486b8541bad4 | note | Standard, Drawing or Specification Reference - AS/NZS 4671, 746-24-874-AC C0600.17
9b8e28f6-d6b2-527d-ad5f-da1b4664c05e | note | Construction Activity Description, Test Type and Acceptance Criteria - Grade 500E MA
8fa0b78d-33ca-5aeb-a1f1-a5b6fb69d471 | note | ○ Reid Bars to Column Starter Cage
c9ae2282-23f8-51fa-8591-f3c2c72d8438 | note | ○ Reid Bars for hanging pile cage
6dc4395a-7cee-54ac-a01e-96b790987630 | note | ○ Sonic Tubes for CSL
f273da99-2aee-5bc8-aa83-a4f35dd7f80f | note | ○ Shop drawing and shop drawing check form to be provided to the Engineer for review.
1c996ef1-ce02-50f0-a142-8060cca1c8d3 | note | Test Frequency - Each Cage
fc53ca96-6796-5675-b74c-32849d768153 | note | QA Record - Shop Drawing Approval, Pile Cage inspection
69e5cff5-55b9-50d9-9153-0d36482a5865 | note | DNZ Engineer - R
32490a39-6ffa-5c35-9e47-321f6c8031fc | note | Designer Rep - H
727f3fb3-aee1-4685-b327-449d5d4e95b9 | signoff | AUTHORITY HOLDPOINT
5d9ef48e-b3e7-4b65-aaf0-9205d6721d3e | section | 3 - Construction Activities
4b78ef41-6247-4ee7-905b-364880edf9f5 | checkpoint | 3.1 - Pile Set-Out
ba9fe811-a74e-5be7-a92a-6c5e4a95f75f | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3150-1
c176710b-7abf-51f9-89c1-7c01ba9dfee7 | note | Construction Activity Description, Test Type and Acceptance Criteria - Before commencing pile drilling operations, survey set out pile position based on model. Set out to include; pile centre, height and offset.
7a1ea9b5-ab91-569e-bbd2-028464828d0c | note | Test Frequency - Each Pile
4a790d3f-64e7-5866-a986-12a9599514c1 | note | QA Record - As-Built
30bc087b-f9b0-5b82-8bf9-159d8ff50ab0 | note | DNZ Engineer - W
aa19a500-ff9d-4b3a-acb7-a1d32ce1b6b1 | checkpoint | 3.2 - Pile Casing Installation
5b5eaeca-dafa-5922-b2de-ffeecd75475e | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3150-1
01086716-399b-5c87-b634-ca02cdf76dbc | note | Construction Activity Description, Test Type and Acceptance Criteria - Pile casing to be installed into a shallow pre drilled hole. Pile casing to be as per submitted methodology and correspondence. Pile casing verticality to be checked using a spirit level.
d50bcfc5-d73d-5675-8820-3b5a5c98caf4 | note | Test Frequency - Each Pile
45b1d941-6351-5124-bc8e-7c9b825eb944 | note | QA Record - As-Built
b5df45cc-8dfb-5962-95ca-f403d73876cb | note | DNZ Engineer - I
32755e78-086c-4126-9e77-28805d84d598 | checkpoint | 3.3 - Welding of pile cages
1912483b-19c5-560f-a61b-bb2b6f1b086e | note | Standard, Drawing or Specification Reference - C0602.5.6, C0602.5.7
8e762757-c30a-5f86-bc80-af4d577a3deb | note | Construction Activity Description, Test Type and Acceptance Criteria - All welding of reinforcement shall be carried out in accordance with AS/NZS 1554.3.
4c7b1d43-d171-5be1-a3f9-10ee49856c97 | note | ○ The welding procedure shall be made available to the Engineer upon request.
cfd4c57a-b532-5d19-a52f-b10e5ae7da02 | note | ○ All welds shall be category SP in accordance with AS/NZS 1554.3
d5453b19-5420-5243-a8bf-d87ba61024d6 | note | ○ 100% visual examination by independent welding inspector.
c408f5cf-06e1-5de9-a488-a08478709aa6 | note | Test Frequency - As required
39cf82da-d198-5e63-91c0-67d854733ecc | note | QA Record - Welder Qualification, Weld Procudure, NDE Report
9e39831f-e707-5188-b4eb-bd26d7ec6c6a | note | DNZ Engineer - R
827cb397-f51c-5b08-8b50-5d78997bb5ff | note | Designer Rep - H
c75aef8d-1493-4cbf-a4ef-03885dae3c70 | signoff | AUTHORITY HOLDPOINT
4a57dba6-c60b-4337-b852-897dd43e6f74 | checkpoint | 3.4 - Pile Auger / Excavation
4f5ddb98-8801-5651-a2f0-e954cdb019b7 | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3150-1 Note 3.9
7ae53e2c-be64-5871-bbb9-169a85382215 | note | Construction Activity Description, Test Type and Acceptance Criteria - Depth to be checked and recorded after auger/excavation.
00469501-3c76-5981-a47d-c07f8abd6a0d | note | ○ Diameter of pile shall not be less than the specified diameter.
a94f1292-acdd-5984-b0f8-cbe8e346842e | note | ○ ±75mm positional tolerance, Max 1:75 (H:V) verticality tolerance.
9c49fa9f-e8d1-5474-8004-3351a4078c7c | note | Test Frequency - Each Pile
bb381810-5727-5717-bfef-d944fb293d74 | note | QA Record - Survey Checks, Pile Card, Photos
f6c0f5df-e67b-53db-bccf-493302b288f5 | note | DNZ Engineer - I
29a51f0c-f8cb-5f47-8e73-0bfa1dcf834b | note | Designer Rep - W
ea73f6ef-436a-41ee-bde5-3c0362a48f62 | checkpoint | 3.5 - Geotechnical Engineer Pile Inspection
ac9536d7-8f83-5152-8c59-a7afb86e6caf | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3150-1 Note 2.3, 3.2, 3.8, C0500 A3.0.5
fb9da19e-af56-5f56-82ec-e41b75821363 | note | Construction Activity Description, Test Type and Acceptance Criteria - Geotechnical Engineer to confirm top of rock during the pile boring operation. And to inspect the material at the base and side of the rock socket complies with the design requirements (Bearing) at least equal to or greater than that nominated on the drawings.
6e2c372b-bba8-578c-97b2-24e95a3e9089 | note | ○ The pile card shall be signed by the inspecting Engineer confirming inspection has taken place and the founding stratum meets the relevant design requirements.
6acd91a1-aa6a-590f-a4d0-be044f4e6470 | note | ○ Tolerance on Top of Rock level variance of ±2m from anticipated level is acceptable.
d132c757-975d-5744-b087-4f15d6fd39a9 | note | Test Frequency - Each Pile
90110fbf-a256-555f-a246-49a6f8ea1650 | note | QA Record - MSQ SVR Pile Card
25b41a7a-7d00-5f21-9209-5c838e99e043 | note | DNZ Engineer - I
f09e90ea-b8d6-5a0a-886e-c1f26141084e | note | Designer Rep - H
0f2086f7-1888-493b-8b6c-ce60b447baf8 | signoff | AUTHORITY HOLDPOINT
135e843d-a60e-4538-8536-6c146d52071b | checkpoint | 3.6 - Geotechnical Engineer Pile Toe Inspection
be5fb248-3a56-5d4b-aae0-ee5c0cb48de1 | note | Standard, Drawing or Specification Reference - C0500 A6.0.2 Table 2
1378323a-2c71-59a8-9cf3-b1893f030236 | note | Construction Activity Description, Test Type and Acceptance Criteria - Geotechnical Engineer to inspection base cleanliness prior to reinforcing cage placement.
f2948e30-63ca-5e77-9389-0eb562c1628e | note | Test Frequency - Each Pile
4859e95a-aff7-5d3a-ae54-df5735da7ce5 | note | QA Record - MSQ SVR Pile Card
40b8ffd3-cd7d-5f4f-b0df-51f7bcd17d69 | note | DNZ Engineer - I
aa31e3c5-2461-59cc-bc91-b1d9076fffb5 | note | Designer Rep - H
f452816f-bc4e-4119-8970-e086a228fd8f | signoff | AUTHORITY HOLDPOINT
1902f08c-1740-4623-88ac-106550f6f64c | checkpoint | 3.7 - Structural Engineer Reinforcing Cage Inspection
c674374e-d346-528f-a2f2-121a6369ace2 | note | Standard, Drawing or Specification Reference - C0700
83a83c28-a3ee-5531-a0fb-8f9671c74d38 | note | Construction Activity Description, Test Type and Acceptance Criteria - Structural Engineer to inspect the reinforcing cages that it comply with the design requirements.
73062417-a181-558a-a591-1081fd19df15 | note | Test Frequency - Each Cage
42937d83-e014-58ca-b1de-25d5f1732d7f | note | QA Record - MSQA SVR
6b404351-0e59-534d-81ee-58534a67b054 | note | DNZ Engineer - I
ee40a366-e570-552b-96fb-eb3537a46085 | note | Designer Rep - H
6422878e-fb25-4a16-9ff9-71e34cfab7c8 | signoff | AUTHORITY HOLDPOINT
7c8638c9-cd17-429a-8f75-6cce6940cfb9 | checkpoint | 3.8 - Pile Reinforcing Installation
b4d61070-2348-5f4e-aedf-faa10ddc2f74 | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3151-1 Note 2.4 & 2.7, 3.3, 746-24-874-AC C0601.8
f60c1d4e-4935-54ec-9be5-b0518a393ebc | note | Construction Activity Description, Test Type and Acceptance Criteria - Once the Geotechnical Engineer has accepted the founding conditions, and the Structural Engineer has inspected the reinforcing cage, placement of the cage shall occur as soon as possible.
eab73055-dc02-5afb-82cc-4a4c790dda08 | note | ○ Minimum concrete cover 75mm at any location.
e78bf431-0252-51e9-ba87-45f0e6016272 | note | ○ Tolerance on Spiral Spacing +10mm for 150mm Spiral.
ec16b6de-c4c1-563d-8604-9806a3de2bec | note | Test Frequency - Each Pile
73d407f5-c953-5f4e-b30e-9ef0484f2f83 | note | QA Record - Survey Checks before and after pour. As-Built, Pile Card
e4e23dc1-67e4-5ff6-816b-01d28314dcd9 | note | DNZ Engineer - I
fd378f03-9697-5a40-9f04-e83f7d3ee695 | note | Designer Rep - W
b186878b-34ce-456d-9b83-14f786bd5965 | checkpoint | 3.9 - Steel Tube Installation
c3fc4caf-7e2a-542c-a9e0-519d1addd790 | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3151-1 Note 1.7
f6b5854e-d47c-5ceb-81fd-036dc4664062 | note | Construction Activity Description, Test Type and Acceptance Criteria - 4 x 40mm ID Integrity testing steel tube shall be installed at equal distance around the inside of the reinforcing cage for the full length of the pile.
6974aa8c-1d0d-55ce-83ae-5ff282b7976f | note | Test Frequency - Each Pile
d917939a-d15b-5100-8cfc-ffa108177da8 | note | QA Record - Photos, Structural Eng. Inspection, As-Built, Pile Card
fad9c700-91af-5d4c-aae5-649edd35947a | note | DNZ Engineer - H
5fc0cf91-46cb-529c-9aca-75323259bd54 | note | Designer Rep - W
d8f3de78-8702-43e8-9c47-47fd8da03d7a | signoff | AUTHORITY HOLDPOINT
253945af-8653-4baf-b373-57e0337c2069 | checkpoint | 3.10 - Pre-Pour Inspection
a571792f-7366-58a5-8317-b922700b6c0b | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3150-1 Consent Inspection Schedule
933fe8f1-b2db-5f69-913e-db6385130556 | note | Construction Activity Description, Test Type and Acceptance Criteria - 2 Days notice to the Design Engineer. Pre-Pour inspection to be completed by DNZ Engineer, Auckland Council Inspector and Design Engineer.
aa55e448-2007-5f67-9c58-b7c5ba32514a | note | Test Frequency - Each Pile
2197129b-608f-5ccf-b4a0-97ec523f16db | note | QA Record - MSQA SVR, Pile Card, Building Consent Booklet
81a872f1-fe96-5af1-b28e-de423ee063ca | note | DNZ Engineer - I
0cf99f18-96fa-51f8-b91e-0f50e020b6bb | note | Designer Rep - H
612ca147-4180-41e3-8102-e4deb6f3f380 | signoff | AUTHORITY HOLDPOINT
b04a242b-cd72-4697-91c5-c16e10bcb86d | checkpoint | 3.11 - Pile Concrete Pour
598a2df7-65b9-593f-bfb7-06df0f745445 | note | Standard, Drawing or Specification Reference - 746-24-874-AC C0601.4.6, C0601.10.4, 3235599-SP03-ST-3151-1 Note 3.6
0f9d4240-c258-5317-9482-058245400fc0 | note | Construction Activity Description, Test Type and Acceptance Criteria - 40Mpa Concrete.
a414b03c-6a75-57ec-a4bf-ab93106887d0 | note | ○ 3 Specimens tested 1 x 7 Days & 2 x 28 Days.
2580703f-24c2-56dd-834f-e70c75bc6373 | note | ○ Spead test shall be completed on each sample taken from the chute.
b7100780-0467-5d14-85ce-cb73740b8444 | note | ○ Column and pile cage to be suspended for a minimum of 8 hours after placement of concrete.
0ffd7ec0-99ed-5042-9baa-a0e3f1398c06 | note | ○ Pile concrete is to be over-poured.
19c724c4-7417-5012-b6a9-6c03e0647600 | note | Test Frequency - Each Pile
9f8568f4-a11e-5e7f-ab56-1cca3451fab5 | note | QA Record - Concrete Dockets, Compressive Test Results, Slump Test Results, Photos
02e2edc1-f1f5-5a6a-a73a-26148c2f4868 | note | DNZ Engineer - I
0e30bb03-c315-53d3-95eb-6810b27523d5 | note | Designer Rep - H
1420d106-c020-47af-8e6f-521763ed6d40 | signoff | AUTHORITY HOLDPOINT
9cceb561-d074-45fa-8104-6128a1d06f75 | checkpoint | 3.12 - Pile Surface Finish / Construction Joint
9d11e19c-ca9d-58d7-9b1a-349a5634c9c2 | note | Standard, Drawing or Specification Reference - 746-24-874-AC C0602.6, 3235599-SP03-ST-3151-1 Note 3.6 NZS 3109
3a90fb08-9434-5e19-af46-153c16bf19c2 | note | Construction Activity Description, Test Type and Acceptance Criteria - Over-Poured concrete shall be removed carefully without damaging the reinforcing cage to form a Type B Construction Joint at the top of pile.
4e398574-270c-5ad2-b528-03cdb4dfb454 | note | Test Frequency - Each Pile
335aa576-aad2-571b-82bf-5aa71a3a5b36 | note | QA Record - Photos
19d5be92-7402-5456-8c29-92cb4d7e71b6 | note | DNZ Engineer - I
5f313f44-1c5a-53e3-a206-dc3758200663 | note | Designer Rep - W
cc4eb903-a97a-4b4b-bbef-257d4991540d | checkpoint | 3.13 - Post-Pour Inspection Cross Hole Sonic Loggging
5a36ef88-c5ba-5219-8add-ee686e80d088 | note | Standard, Drawing or Specification Reference - 746-24-874-AC C0500.2 A5.0
d15564d2-4f86-5dfd-90ed-5974b0ecacbb | note | Construction Activity Description, Test Type and Acceptance Criteria - Testing to be undertaken at 8 days
44d5b562-cf0a-52ba-bf8b-d5033ba4ffd1 | note | ○ Preliminary results shall be submitted to the Engineer within 1 day of completion of the test results. The Final results and findings shall be submitted to the Engineer within 3 days of completion to the test. Once the Engineer has reviewed the results of the tested piles, and are satisfactory the tubes shall be grouted with a 40Mpa Cementitious grout.
77b4dd25-085a-5fa5-b190-6558c21e1b64 | note | Test Frequency - Once
c01aa085-5c85-5ae4-9b51-371cc37537e0 | note | QA Record - Test Reports
a9cde838-1ce5-5c01-9953-e80976abb0d8 | note | DNZ Engineer - H
2d9297e2-f131-575b-882d-bf7bfddddf6a | note | Designer Rep - R
578dbb9c-9021-46b1-8779-9cb02e2381d1 | signoff | AUTHORITY HOLDPOINT
eb094b48-28e4-479c-9bb1-9f6658109c0b | section | 4 - FINAL RECORDS
052842e8-530c-42cf-b20e-558f18532cfc | checkpoint | 4.1 - Survey Records
c89d24c3-5d36-5eb7-9788-636333254cf7 | note | Standard, Drawing or Specification Reference - N/A
2f84749b-db64-55dc-8adb-4e0e9ca408f0 | note | Construction Activity Description, Test Type and Acceptance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
a9b4b483-b2e0-52bb-99a1-582c37e47924 | note | Test Frequency - Once
4fe63e2a-3e81-518b-82c7-6826cf47b0bd | note | QA Record - As-Built
c8bc61dc-d81e-5aa6-9555-ec296ae55621 | note | DNZ Engineer - H
79585f40-3f9c-5b71-b1bc-746d5f911654 | note | Designer Rep - R
cca09936-8fcf-479e-92a6-ae7e1090f814 | signoff | AUTHORITY HOLDPOINT
161a1a88-4f8c-4cce-9554-68d5c6c33c03 | checkpoint | 4.2 - Redline Drawings
ee2f5cc9-754f-5916-9cae-f84243cd709f | note | Standard, Drawing or Specification Reference - IFC Drawings
2fc44fd0-3e55-5fd5-8739-280f986c8d30 | note | Construction Activity Description, Test Type and Acceptance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.
902ef243-2a34-5a65-9167-fd109ae9daf8 | note | Test Frequency - Once
faa34484-4bfa-5dd4-bc2e-7ff055b69c5f | note | QA Record - IFC Mark-Up
a8580204-45af-5f56-879f-25a9294005bd | note | DNZ Engineer - H
cdc44bb4-1ffb-5141-a113-0cdfc1d1c1ab | note | Designer Rep - R
2b67b62b-e426-4834-8ec4-1283e7de2727 | signoff | AUTHORITY HOLDPOINT
2e2f5efe-e9b3-4914-bf1b-36f1b4da383c | checkpoint | 4.3 - Defect, Snag and Punch List
a13ed3ba-7f87-5b01-8b91-e62210f4c3f5 | note | Standard, Drawing or Specification Reference - DN1212-DOW-PLA-PM-0005 QMP
cb328779-affb-54b3-811a-8fb1870331a6 | note | Construction Activity Description, Test Type and Acceptance Criteria - Update the project Defect, Snag and Punch List Register
4a852843-622b-5cde-b234-9b14dc738e35 | note | Test Frequency - If required
b393a8fa-29e3-5c14-933c-ae5f2582d4e4 | note | QA Record - Snag Register
239e85ac-0f7b-5aa3-a91e-7873bd586665 | note | DNZ Engineer - H
1e246544-10ee-5d57-b2b8-3d15bb159eae | note | Designer Rep - R
3c84c0a1-3cc3-47c0-bf92-a581d912e3c4 | signoff | AUTHORITY HOLDPOINT
6f440c47-69ac-482f-b323-85c5bcdeb68e | checkpoint | 4.4 - Non-conformances
33477c1b-0efd-5ee9-9a20-ff863f872f1a | note | Standard, Drawing or Specification Reference - DN1212-DOW-PLA-PM-0005 QMP
79de7f0d-9ea6-5e64-9bc8-f19a960ec5e2 | note | Construction Activity Description, Test Type and Acceptance Criteria - Non-conformances reports to be raised when specification not met. All non-conformances within the area under review need to be listed on the NCR report.
e39fa22e-992a-5445-a2d2-27e3556805a0 | textbox | NCR Reference
b349fdb9-305f-542a-b727-fcc28aa8614e | note | Test Frequency - When Required
ff5aab1c-2d6e-5f19-b12f-a7ff275d7318 | note | QA Record - NCR Forms on InEight
a3a7bb93-7237-5aa0-b6ee-2434736a6fd3 | note | DNZ Engineer - H
db01fca5-6cbd-59f9-b08d-21c84465aff6 | note | Designer Rep - R
75ae5e04-5b92-4904-81fb-6b085e416cc2 | signoff | AUTHORITY HOLDPOINT
471bd145-c4aa-4a86-889c-293407ab6d07 | section | ITP APPROVAL PROCESS
4bd14162-3b4d-45ef-8b76-4e31cc07b987 | checkpoint-no-value | ITP APPROVAL PROCESS
80ff22ed-af11-5a26-afb3-b4fc96eae3e1 | note | Prepared By: Quality Engineer - Nas Matar
2b29f868-5f5b-5f9f-9e1c-043204b6bfe4 | note | Reviewed By: Project Manager - Dan Trotman
379afbbe-5c7c-5aa5-afe9-3fdca2e63e72 | note | Reviewed By: QA Manager - Cordelia Gridler-Brown
2eda7883-2cb5-5f23-9ea1-d3401e467a6b | note | Reviewed By: Design Engineer - TBC
919205a4-5d9b-58f3-a973-46943f95fdc6 | note | Reviewed By: AT Project Manager - Mike Robertson
6cbb5d29-0d3c-5c26-9611-0ad875024473 | date | Date:
85f7c76d-1385-4c02-ba7e-a0b7571da052 | section | FINAL ITP CLOSE-OUT
c826fb7a-8684-4a6c-9bcb-9a6691ed4c18 | checkpoint | FINAL ITP CLOSE-OUT
5fbda94c-b590-5e25-8040-fd6038e9c11e | textbox | Downer Project/Site Engineer:
c80f91ba-5c37-5939-af4b-c663cd5308de | textbox | QA Mgr./Engineer:
d65a5fec-fc50-5a46-b0f3-bce45332ae80 | textbox | Designers Rep(Assistant):
4ae24214-9af7-5de8-ba97-277de4a374ef | date | Date:
70c444f2-5369-4f6d-a286-1932cff82803 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
b5d8e742-17a6-5299-abdc-7f1baaf6c788 | textbox | Contractor's Rep Name:
13014c33-c214-5885-b6d3-58b529d4be73 | textbox | Engineer's Rep. Name:
5f7f7333-3642-5efc-9d71-c8004288b751 | date | Date:
ed9a0f0d-8f29-4b78-8f6f-75f31372dcdd | signoff | Add Signature
4ae43855-5126-448b-ac04-cf497693e4bc | checklist | DN1212-ITP-005 Stair Case Rev4 | itp | DN1212-ITP-005 Stair Case
9d2b1c5e-782c-4799-8a70-8caade8a8162 | section | 1 - PRELIMINARY AND GENERAL
7bca67e0-13ea-495d-8742-f7810a98e880 | checkpoint | 1.1 - IFC Drawings and Specification
4001e8c5-02b4-5bb5-add6-fe77ddaeb0d6 | note | Standard, Drawing or Specification Reference - ACC
b77e3ddd-d49c-586f-a2db-0559985a3e3c | note | Construction Activity Description, Test Type and Acceptance Criteria - A minimum of two weeks prior to construction: document review. DWG’s are for construction or as per instruction
e1e707a8-9b54-52c8-9d98-ee1284eac43f | note | ○ Works done in accordance with Project specification
0517d674-b5c6-5a0d-a7f0-27f2e496bcf2 | note | Test Frequency - Once
28070120-02e5-535e-a97a-13bb9ddf3527 | note | QA Record - N/A
ac0c1563-b552-5344-9e55-d348b65bbd4b | note | DNZ Engineer - R
c640d60c-79fe-55d6-ac18-29a770c5c0f1 | note | Designer Rep - H
130d8247-3bbd-4b2c-97b5-fd208910d966 | signoff | AUTHORITY HOLDPOINT
59cefdfd-fcf7-41c0-a656-a187ea9e23cf | checkpoint | 1.2 - Method Statement & JSEA Development
c4cf9f84-df11-5a26-bc1e-d71a7b0319c4 | note | Standard, Drawing or Specification Reference - The Downer Standards (TDS)
50aba03c-9828-527c-9608-08b910b43765 | note | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction: document review.
f3862a93-65c3-534d-884e-56a6a87c49a7 | note | Test Frequency - Once
39b28761-418c-5374-b748-65c35fba8390 | note | QA Record - Method Statement & JSEA Completed & signed by relevant authority
f890e72a-32f8-5aee-a849-44e7585f602e | note | DNZ Engineer - H
ff727602-5c61-5831-b021-a730dfee5131 | note | Engineer's Rep - R
014c865f-7182-51ce-b345-cebfb40e4e65 | note | Designer Rep - R
fbbb9b34-1117-4a9d-a857-a1e0a535e241 | signoff | AUTHORITY HOLDPOINT
c50f0633-eb74-4fd3-84a8-5bdb8d3a7258 | checkpoint | 1.3 - Permit to Dig
56835d05-1b8b-539c-aae3-deb0aa877b61 | note | Standard, Drawing or Specification Reference - DN-ZH-ST043 Ground Disturbance
37c18343-acd9-51e6-ab10-30ef45aef768 | note | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction. Permit in work package
3acdcd84-e546-529e-b14c-550f58d80f92 | note | Test Frequency - Permit issued each week
1cfb96ac-239d-5289-ab61-6779dc4492ca | textbox | QA Record - Permit number
dfecfcc5-9047-54b4-bea5-1ef85baab348 | note | DNZ Engineer - H
c046366b-b021-46a6-85f2-9bc3b9970dda | signoff | AUTHORITY HOLDPOINT
f78c738c-f27a-4a90-bd74-3f895a00401a | checkpoint | 1.4 - Survey Model
8c4199dd-f8e8-54f7-ad3d-32450aac4ec6 | note | Standard, Drawing or Specification Reference - N/A
18f8396e-ee6d-5dfb-aeb1-af7836166d44 | note | Construction Activity Description, Test Type and Acceptance Criteria - Model Review.
c11bb8e7-da46-5d03-8245-fa70bb085c93 | note | Test Frequency - Once
a75768a8-4809-57b2-9866-a6ceaa35f0f6 | note | QA Record - Visual Inspection & measurement Survey Check set out as per design
bb3e2ae1-e766-51f0-be3d-cc4e51c7c5a6 | note | DNZ Engineer - H
ab58d5fc-9a44-446e-a5b4-bb097a6876a0 | signoff | AUTHORITY HOLDPOINT
68470d35-04ba-4883-9ba1-67adc460b1d7 | checkpoint | 1.5 - Lift Plan
245931c3-9a86-574d-8050-33faa1891f81 | note | Standard, Drawing or Specification Reference - DG-ZH-ST047 Cranes and Lifting Equipment Standard
e402c515-b659-502e-85af-967183298273 | note | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction. For lifting of reinforcing cages, lift plan shall be in place ahead of construction, a Complex lift plan for the Crane and lift card for lifting with Excavators.
ba8a6bfd-9292-5e94-a07e-da052ac1f271 | note | ○ Lift plan included in the work package.
106059ea-d0e2-5354-a992-5ded8df48931 | note | Test Frequency - Prior to Construction when required
3d1a4415-6030-576f-9313-81aac9edf319 | textbox | QA Record - Permit number
e9743ece-bdc0-52af-95b4-5dff8b857a17 | note | DNZ Engineer - H
7d9c74d1-f906-4a23-8521-09a3c80768f8 | signoff | AUTHORITY HOLDPOINT
5fc81a44-f681-4584-93d8-955e71a428de | section | 2 - MATERIAL APPROVALS
bc6a4989-45dd-4589-8f18-a89f42216e28 | checkpoint | 2.1 - Concrete Mix Design
8d0339e6-5a2f-5235-ab13-4d22869c5da3 | note | Standard, Drawing or Specification Reference - 746-22-052-PS Section 5.2, NZS 3114:1987, part 2 Exposed Aggregate surfaces.
6ac59327-b063-511e-8056-a6625d8bd9c9 | note | Construction Activity Description, Test Type and Acceptance Criteria - Mix Design approved by designer.
5c3737ab-b9b3-54c7-b237-9ddeb8cd6272 | note | ○ 40Mpa Concrete with maximum 19mm aggregate
a1f788b8-2b04-503f-b549-1de8ef24605d | note | ○ Slump 120mm-160mm
7013a244-1744-5607-a787-a1bc8258a141 | note | ○ 4kg/m³ of black oxide to be used as per AT spec, exposed aggregate finish to be installed..
dffa3341-2398-542f-a433-7a185018a0aa | note | Test Frequency - Once
5c1441ab-0f97-555f-9392-18b27505d265 | textbox | QA Record - Approved Mix InEight Reference
59fea113-81f3-544f-b85c-015514b82979 | note | DNZ Engineer - R
3b26d6ef-50f1-57bb-8bc5-5cb876e2c3c4 | note | Designer Rep - H
e693c72c-cc40-4e66-9882-99e675682cba | signoff | AUTHORITY HOLDPOINT
3fbd1950-431c-42f2-aad2-b13b8a77ad06 | checkpoint | 2.2 - ATAP65/GAP65 - Material Source property testing and sampling
5cce4821-a8b7-5952-aaef-929c9b6ba047 | note | Standard, Drawing or Specification Reference - TNZ M/4: 2006 - 3, NZS 4407 : 1991, NZS 4402 : 1986 (Original detail was concrete blinding but changed by site to GAP 65 for easier bulidability)
f0e7fb29-26b2-5faf-af48-7b6360d65e69 | note | Construction Activity Description, Test Type and Acceptance Criteria - The basecourse aggregate shall be sampled and testing by an IANZ accredited laboratory for crushing resistance, wethering quality Index and California bearing ratio ( Class 3 & 4)
df03e630-71d4-5461-b96b-d36fe768113b | note | Test Frequency - Once Per Year Or Every 10 000 m³
dba35612-a5a5-5e2e-ab5e-cac66fe3be81 | note | QA Record - IANZ Test Report
cbe86e62-59ce-51f6-af8c-f5c52eff9d6a | note | DNZ Engineer - H
8e54445e-cc07-5f34-94f3-324dca85fe18 | note | Designer Rep - R
807d7055-0e31-4837-b163-e0089a69a91f | signoff | AUTHORITY HOLDPOINT
8d2fa7e8-6619-4e89-832f-3e3af90f17f0 | checkpoint | 2.3 - ATAP65/GAP65 - Production property testing and sampling
f58d85f8-5f3a-53f6-b96c-94013487c7b1 | note | Standard, Drawing or Specification Reference - TNZ M/4: 2006 - 4, NZS 4407 : 1991 (Original detail was concrete blinding but changed by site to GAP 65 for easier bulidability
ac5c6051-7cd0-597f-8877-b3118560838d | note | Construction Activity Description, Test Type and Acceptance Criteria - The basecourse aggregate shall be sampled and testing by an IANZ accredited laboratory for Quality of fines as per M/4 fiqure 1, Broken Face content and WET particle size distribution Limits and shape control
116e82ca-fc5b-57a6-b9ef-50775caa23dc | note | Test Frequency - Once Per Year Or Every 10 000 m³
7fd92bda-372c-5b98-8a7c-a0b7c42eff7b | note | QA Record - IANZ Test Report
810a77b5-fb2d-501f-b558-b708ea95408e | note | DNZ Engineer - H
d522f6fc-f9e7-5e72-809b-6e2ae9b07ef2 | note | Designer Rep - R
01b365fc-63e9-4e84-8470-38a5d688da0d | signoff | AUTHORITY HOLDPOINT
5d85422b-51d6-4fd5-848d-51e0dc96d184 | checkpoint | 2.4 - ATAP65/GAP65 - Testing for layor compaction - MDD
ca15d480-add7-5248-8e83-7758252ae897 | note | Standard, Drawing or Specification Reference - TNZ B/02: 2005 - 7.5, NZS 4402:1986 - 4.1.3 (Original detail was concrete blinding but changed by site to GAP 65 for easier bulidability
f1121f44-c216-5c98-99c0-9b5ba2ddf3d4 | note | Construction Activity Description, Test Type and Acceptance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC).
72756ca9-7e20-58b4-b27f-24054685d045 | note | ○ Average MDD 95% with a minimum of 92%.
13fa41d8-dce7-5bcb-89dc-f1152aaf0639 | note | Test Frequency - Once Per Year Or Every 5 000 m³
abe362cc-5898-550b-a439-3710ef9bcee3 | note | QA Record - IANZ Test Report
f3ab19f5-ee49-5a8f-a425-0d2d31735884 | note | DNZ Engineer - H
adbbbd79-d90a-5f44-a4ed-8b443c53121f | note | Designer Rep - R
219383b5-1177-4c0c-8793-76a92c3a262f | signoff | AUTHORITY HOLDPOINT
f0586d26-95ab-4f60-972a-28db8b0717f1 | checkpoint | 2.5 - Reinforcing Steel
af0a31e3-a5f1-5c9a-b8f4-a726b492b1e2 | note | Standard, Drawing or Specification Reference - 24-178_FC_201124
341fe511-fa2a-5b8f-99dd-8ce686c6ca9b | note | Construction Activity Description, Test Type and Acceptance Criteria - Supplied by pre-cast sub contractor as per drawing 24-178_FC_201124. Original detail was insitu but all work will be pre-cast.
e6f05588-9627-5170-860c-eb2d11ff9213 | note | Test Frequency - Once
12dbe0eb-104b-5a69-90fc-6fb4c87f2d2d | note | QA Record - Mill Certificates & Shop Drawing Approval
1758846b-73c6-5382-b631-940729ea29b9 | note | DNZ Engineer - S
d9eb77cd-9e6d-56c9-ab42-b12a90a86d1b | note | Designer Rep - H
fb1f3774-0001-41d7-88c7-3aa43910889f | signoff | AUTHORITY HOLDPOINT
3e60b5b1-7893-4471-ae91-ffcc202820c5 | checkpoint | 2.6 - Tactile Indicators
6813aef5-4322-5075-b81c-a5ec5e13eeb2 | note | Standard, Drawing or Specification Reference - TDM Standard Engineering Detail for Footpaths Section 3.6: Footpath surfaces and construction, FP009 Pram Crossing, 3235599-SP03-CA-1001 - Rev 1, Note 11
3e4f52e2-77b3-5801-bcdf-4e9264aa646a | note | Construction Activity Description, Test Type and Acceptance Criteria - 300mm x 300mm x 60mm thick yellow anti-slip will be installed in the insitu stitch pour section.
d5d67ee3-0293-56ef-8abb-4569bd3fba79 | note | Test Frequency - Once
01ccf5fb-2599-5e35-beed-bd7d38c30041 | note | QA Record - MDS & Approval
a5d45343-2b88-5246-92b4-be0f53416ae2 | note | DNZ Engineer - R
b3b36562-d159-5695-bb5a-4da56c93175d | note | Designer Rep - H
e20289be-f7b1-4085-9b4d-30663ac072ee | signoff | AUTHORITY HOLDPOINT
9fe83701-a7d2-4da1-9924-cce65ad713cd | checkpoint | 2.7 - Tactile Cement Blinding
9ef90f03-fcb3-5129-93af-a20b373e7e03 | note | Standard, Drawing or Specification Reference - TDM Standard Engineering Detail for Footpaths Section 3.6: Footpath surfaces and construction, FP009 Pram Crossing, 3235599-SP03-CA-1001 - Rev 1, Note 12
0b343c0c-9646-5689-90b7-efc20c3a69c4 | note | Construction Activity Description, Test Type and Acceptance Criteria - Minimum 50 Mpa cement to be used according to supplier installations.
6c21fa75-770c-5bf4-8440-0d723e9ae384 | note | Test Frequency - Once
b7501787-8e05-583f-a0ae-b01ac32e1e55 | note | QA Record - MDS & Approval
46c2fcb7-b1bf-5c9c-b765-bf6e19e419e7 | note | DNZ Engineer - R
aca225c5-1b81-546d-b0a2-9a81b858a025 | note | Designer Rep - H
37abea85-57a5-4e0c-8f0e-ef8854789ce7 | signoff | AUTHORITY HOLDPOINT
6b0f9b02-5af5-4b02-98b3-e40ddff69513 | checkpoint | 2.8 - Joint Filler
66a731ac-0acb-5047-94fe-41e05eb812dc | note | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1025 - Rev 1
db537ba9-e556-5df3-b0ee-06825f46c33c | note | Construction Activity Description, Test Type and Acceptance Criteria - Sika BlackSeal-1 Bitumionous joint filler or alternativly approved material.
462448ef-8421-5006-a078-c1a80dda4c12 | note | Test Frequency - Once
f74185de-a371-5fa3-8978-a8e2c7ef2092 | note | QA Record - MDS & Approval
6dfadc0c-6f1d-57ae-8732-a49732275ab6 | note | DNZ Engineer - H
facb4aa3-941a-53a2-b48f-15912cd7fdc9 | note | Designer Rep - R
feddc9f1-721f-47f3-9acb-04b6b49d7944 | signoff | AUTHORITY HOLDPOINT
89fbc859-202d-4811-9b16-ec0b7f2eafd7 | checkpoint | 2.9 - Moddex Handrail
37a977e9-a0b7-52ca-adee-9390160e3c8a | note | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1024 - Rev 1, 3235599-SP03-CA-1025 - Rev 1, Note 1.11
5afa30df-ca3d-57d8-a842-d9abb0abe1b3 | note | Construction Activity Description, Test Type and Acceptance Criteria - Moddex AR10 or Similar approved handrail.
64539a53-2dcc-5efd-908e-1c92744ac638 | note | Test Frequency - Once
3ad3991a-ea1f-59a7-88e6-1cc5a2cb2de7 | note | QA Record - PS1 & Approval
c1a223c9-ec06-5177-a583-f6bc4226a908 | note | DNZ Engineer - H
1f77c2f8-dd14-5577-906f-2dddd380e19a | note | Designer Rep - R
d0690c22-adc9-4d33-b847-9f504c824261 | signoff | AUTHORITY HOLDPOINT
7fa4512c-7b13-45f1-8432-109f6466496f | section | 3 - CONSTRUCTION ACTIVITIES
e1bebae5-aa44-49a3-aad5-44e08b81ae0f | checkpoint | 3.1 - Staircase set out and excavation to subgrade
5c6f261c-b908-5898-9d4a-f12e9a676638 | note | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1024 - Rev 1, 746-22-052-PS Page 9 Table 1
273b47cc-0581-529a-b491-9bda97d5d87e | note | Construction Activity Description, Test Type and Acceptance Criteria - Excavated as per IFC long section.
67bf525e-9836-5ed6-8c4b-aca82571531b | note | Test Frequency - Once
1c5c6869-3454-5d27-bb2b-141f306a3300 | note | QA Record - As-Built
22f3846e-01bb-5d16-befd-363a2b183ce1 | note | DNZ Engineer - H
765c3813-9613-4f4b-850f-315d3c4a497e | signoff | AUTHORITY HOLDPOINT
47408621-fbbf-4235-b330-3207097e312b | checkpoint | 3.2 - Installation of benching
ae1d2d3b-24e9-5120-8d05-debe2f487c95 | note | Standard, Drawing or Specification Reference - As Per CAN 033
511fdc3a-f191-5c0e-a5b2-d257bd5a6b15 | note | Construction Activity Description, Test Type and Acceptance Criteria - Installation of benching for backfill of GAP 65 as per CAN 033
b215d288-6631-5ac5-b8d2-522743d99dc6 | note | Test Frequency - Once
b354120f-adf2-5d3c-90dd-4d0b2349dcbe | note | QA Record - Photos
05408cdb-ff12-5274-bb0a-a6122ff417c7 | note | DNZ Engineer - H
3d74f4c9-d471-58c1-93d2-d274484f5933 | note | Designer Rep - R
92d24a1b-9055-4bd8-a335-ff753350775d | signoff | AUTHORITY HOLDPOINT
49b7406b-5cd3-47cd-b142-b738ef3d73a3 | checkpoint | 3.3 - Subgrade Testing (Scala)
a8bad3d6-4774-59f5-b717-9438df91bfbe | note | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1025 - Rev 1, Note 2.3a, 746-22-052-PS Page 9 Table 1
08bcc9f5-17a7-53cb-8cba-f5bbd47d8c3b | note | Construction Activity Description, Test Type and Acceptance Criteria - If clay based material is encountered - ensure subgrade has a minimum CBR of 3
368d7ec5-fc74-5889-83fe-2800cdc4a2d7 | note | ○ Test to a depth to 1m, not less than 3 blows per 150mm for CBR 3.5% and 3 blows per 200mm for CBR 2%.
29b66a53-b882-5d20-a8e5-45e15538a7e4 | note | Test Frequency - 1 per unit
42b12326-869e-5885-852b-ff88159149b9 | note | QA Record - Scala Test Results, CBR of 3
e741a24d-66f2-56b6-8e62-2606533bc848 | note | DNZ Engineer - R
2049c5ef-4e81-526c-8c20-268bf57c595f | note | Designer Rep - H
fc302b42-371e-41c3-bb04-03bd1c2fe5c5 | signoff | AUTHORITY HOLDPOINT
04121164-2714-4833-b91d-0c98616aeea4 | checkpoint | 3.4 - Undercut (If required)
4a101374-18de-5337-8d02-7b2b7525c24c | note | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1025 - Rev 1, Note 2.3c, 746-22-052-PS Page 10 Table 2, NZS 4407:2015 4.1.2
f28e0edc-85a9-5cb1-9fcd-becce12d7650 | note | Construction Activity Description, Test Type and Acceptance Criteria - Prior to subgrade undercutting, the Engineer shall confirm the extent and depth of subgrade undercut.
22f2ec67-382a-5832-84f7-596b7e003b3d | note | ○ Replace with compacted AP/GAP 65, compact to a minimum 95% MDD.
33c6714d-5250-57f8-b210-6947c4eb3a13 | note | ○ Minimum two NDM tests per footing location.
e5c0c8a3-ae63-5b65-ba98-b69c3b6b7bce | note | Test Frequency - As required
a522b5d9-443e-5944-ae54-9bbeb8595d53 | note | QA Record - NDM Results
a3cd9a95-c3ff-54b3-9d0a-4d4ac37e8ce7 | note | DNZ Engineer - I
c43d9549-dcd7-5d78-87b9-f5a78ff2a6a9 | note | Designer Rep - H
d1a8386e-8717-4b68-b357-2297000f1435 | signoff | AUTHORITY HOLDPOINT
4641941a-40fb-45f7-a475-65de7b08b4f7 | checkpoint | 3.5 - Precast Units Pre-Pour
b3e5f3a1-0c0b-5cd9-b89d-da7113e8152d | note | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1024 - Rev 1
e73e83d5-d1b2-5240-b28c-4eb88ab9e0bf | note | Construction Activity Description, Test Type and Acceptance Criteria - Supplier to fabricate precast units as per the approved shop drawings.
9864ab4d-cabe-5512-9de1-720a9a88dee3 | note | ○ Pre-Pour inspection to be completed by DNZ and BECA Representative.
a9455710-89e3-5d51-b905-e07467acca69 | note | Test Frequency - Every Unit
cbb47ae8-a0e9-593c-b16e-18d6c5372f05 | note | QA Record - Supplier QA Report, Concrete Test Results, Mill Certificates
2f5556e6-c78b-5818-8eb1-d660a077604d | note | DNZ Engineer - I
314ce1db-2ce6-5cb0-aa89-b6f0f396e073 | note | Designer Rep - H
c7cb910e-800e-46c9-b8aa-bfbf8a5c7bff | signoff | AUTHORITY HOLDPOINT
32a57a27-206d-4e6b-9421-aa88301b228a | checkpoint | 3.6 - Precast Units Post-Pour
3303373a-229f-5ec0-ad36-ef6ad554e669 | note | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1024 - Rev 1
4c963b8a-93f5-54ca-b74b-29a6960f2592 | note | Construction Activity Description, Test Type and Acceptance Criteria - Before site delivery, a post-pour inspection must be completed by the DNZ Engineer or Precast Supplier to check for any defects and to confirm that the exposed aggregate finish meets the design intent.
8f81dee2-8bae-58cf-932a-50b66d9375be | note | Test Frequency - Every Unit
fdc21205-567a-5471-9b0b-c806d9dedb76 | note | QA Record - Supplier QA Report, Photos
de81c961-65b9-51e6-816c-b63116843e39 | note | DNZ Engineer - I
2e435ab2-ac59-4377-86a6-41bd652281a3 | checkpoint | 3.7 - Insitu Stitch Works
a622b710-60ac-543b-bd35-e55d15188bde | note | Standard, Drawing or Specification Reference - 24-178_FC_201124, 3235599-SP03-CA-1031
dd8111c7-d9cc-588a-9bab-d5402c1adcad | note | Construction Activity Description, Test Type and Acceptance Criteria - Required at the top and the bottom of stairs.
4184133a-82e9-52d5-bcce-58baea8b1e2b | note | ○ As per RFI 012 - Staircase Detail.
76eb09bd-e456-5a71-a3e7-4f5d9a5c6791 | note | ○ Starter bars will project into the top landing only. Starter bars from the precast section shall be lapped with DH12 bars which extend (and terminate with cover) to the end of the insitu portion of the stairs landing.
2b30d137-76ac-5580-ae7f-c456f3b9eb18 | note | ○ Cover of reinforcement will be checked with minimum 75mm cover at the base of reinforcement with 50mm cover on the side.
cb15f045-581c-5526-83e2-dc7cce0beb14 | note | ○ Concrete will also be poured as per AT finish with exposed aggregate finish and 4kg/m³ of black oxide present.
39f46076-77f6-5d51-b1fb-01c87609f4c4 | note | ○ Precast to be shrink wrapped to allow 7 Days curing time.
03728bac-0a48-528f-a722-02cc2b0886f5 | note | Test Frequency - Every Stitch
aaac493d-6775-50da-a536-032c5aac53aa | note | QA Record - Concrete Dockets, Pre-pour checklist, Photos
dfdc4601-c3aa-54c2-a916-5e68ab463b63 | note | DNZ Engineer - I
c8e2b1c7-749d-4a13-a0a0-fe3a7e93ebb6 | checkpoint | 3.8 - Place Tactilies
1ac1eec4-ff07-5f1b-9612-812cd6aa31a0 | note | Standard, Drawing or Specification Reference - TDM Standard Engineering Detail for Footpaths Section 3.6: Footpath surfaces and construction, FP009 Pram Crossing, 3235599-SP03-CA-1001 - Rev 1, Note 11
a0721ff5-8b13-5fa9-934c-57cfd60db6c3 | note | Construction Activity Description, Test Type and Acceptance Criteria - Note that per CAN 2, the middle landing of staircases will not have tactiles. Only the pre-cast units that will be installed on top and bottom landing.
ec4a7d54-1422-51ea-8c56-857ab0bf862e | note | ○ The horizontal tolerence should be between 3mm and 5mm. Vertical tolerance -10mm max.
4f75f47b-32ca-527c-abf7-33f884855d03 | note | ○ Orientation and set out shall be approved by the Engineer and or ATOC Representative prior to concrete placement.
c1366063-3566-5abb-855f-f7007e95a963 | note | ○ A one coat sealer with UV stabiliser is to be applied for maintenance and durability reasons
021e874f-3559-5e51-9909-73faa3fd2c6e | note | Test Frequency - Per installation
91cd0a7b-129c-5ad7-b357-5e80d13e7609 | note | QA Record - Delivery Dockets, Photos
112792e7-7b3c-56ce-8797-bbf79c3a7cb3 | note | DNZ Engineer - H
4c08e970-d7b7-5056-b355-e69eaf150c75 | note | Engineer's Rep - I
a8d15893-8daa-5db2-8b2b-9dedf2312f5a | note | Designer Rep - I
e98c69d6-b5f2-4bbe-9180-e621b9dcb547 | signoff | AUTHORITY HOLDPOINT
4b56d2a8-94e5-4301-80f6-a1db114629e9 | section | 4 - FINAL RECORDS
e0c9d8a1-612c-4991-8b3c-962594f7ccd8 | checkpoint | 4.1 - Construction Record Compilation
a68ada6d-e5b0-5138-b815-f2284e566a8f | note | Standard, Drawing or Specification Reference - N/A
335f5571-812c-5c1e-b21a-af410be3e51a | note | Construction Activity Description, Test Type and Acceptance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
fd39369f-7f4b-52b1-888d-f638d0e69ef7 | note | Test Frequency - Once
23f09bdc-57c7-5344-adf1-a8ab3892f1c4 | note | QA Record - QA Records
5f64bad0-3a66-5748-a540-1260ae420745 | note | DNZ Engineer - H
b5adb60c-59b8-5b61-a8f6-a06671513ea5 | note | Designer Rep - R
df339f47-2b07-4000-84e4-3c0000b49b10 | signoff | AUTHORITY HOLDPOINT
74117716-7fbf-4e48-8ce2-adc31625abce | checkpoint | 4.2 - Survey Records
54e96a45-10c4-52f5-b401-d51a34d7f642 | note | Standard, Drawing or Specification Reference - N/A
2189cf04-a9c1-5131-bdeb-35ee42910016 | note | Construction Activity Description, Test Type and Acceptance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
fc3a5753-64f2-5da5-91d0-7fd7a9965100 | note | Test Frequency - Once
de7becd0-2027-5bdc-8b6e-b9857c82db29 | note | QA Record - As-Built
601aacdc-f39e-52d7-b1ba-79bb91746e2c | note | DNZ Engineer - H
653b6721-de09-5818-8d8b-bae3c3904c3e | note | Designer Rep - R
9bbd7d23-e256-4f32-add4-b4f94e3018d6 | signoff | AUTHORITY HOLDPOINT
30aa196d-acda-4b3d-b33b-5d1e9b570791 | checkpoint | 4.3 - Redline Drawings
261d3826-533b-50a6-ae1d-e680b7147030 | note | Standard, Drawing or Specification Reference - IFC Drawings
21e398ad-7980-5c7f-bfdf-5b1d991f641a | note | Construction Activity Description, Test Type and Acceptance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.
b47a5864-a580-5996-918e-2c438afe71d7 | note | Test Frequency - Once
0e2fa7e3-bcb0-58a7-aa99-d8a09db572c4 | note | QA Record - IFC Mark-Up
c2e481db-0b79-52fe-814f-f89284d27498 | note | DNZ Engineer - H
d55e83cf-bb1e-56fb-b039-1ef08cd0ad20 | note | Designer Rep - R
ce163b82-0a1a-4fb5-89f8-d68bd46863bc | signoff | AUTHORITY HOLDPOINT
a20c9252-1855-4d8a-8c22-e297fe684b4d | checkpoint | 4.4 - Defect, Snag and Punch List
8baa8a16-6add-552a-a4a8-019817457a5c | note | Standard, Drawing or Specification Reference - DN1212-DOW-PLA-PM-0005 QMP
86f8c13e-b416-53bd-a43a-090f001b5b7a | note | Construction Activity Description, Test Type and Acceptance Criteria - Update the project Defect, Snag and Punch List Register
8af8f5be-9a97-57f5-9990-4d1f84a040a5 | note | Test Frequency - If required
0fd91b42-b2b6-5281-925d-7bd0e9d70dfa | note | QA Record - Snag Register
5ca0e524-f48d-5f15-b9fb-d385ed44f93f | note | DNZ Engineer - H
8ee3635b-5b35-5293-81b4-f4c69d640955 | note | Designer Rep - R
ff691c09-9054-4902-8ee0-a6b08f4627c2 | signoff | AUTHORITY HOLDPOINT
ce15913f-80cb-4ca4-9bf7-4acd14978bc1 | checkpoint | 4.5 - Non-conformances
5187fbb9-36db-5ea7-b550-980afd4416aa | note | Standard, Drawing or Specification Reference - DN1212-DOW-PLA-PM-0005 QMP
d9bed5cb-daae-536b-92d6-78cc1b3798fe | note | Construction Activity Description, Test Type and Acceptance Criteria - Non-conformances reports to be raised when specification not met. All non-conformances within the area under review need to be listed on the NCR report.
3f715a15-9c29-5832-bc07-7036da1adcc4 | textbox | NCR Reference
38d4c4ca-192c-5cd3-b3ab-45a8b1189f9b | note | Test Frequency - When Required
15aa4ff0-9276-50f4-8394-1ffa0c53bbf4 | note | QA Record - NCR Forms on InEight
52c6d707-db53-543d-babb-d3fe33cf3c2b | note | DNZ Engineer - H
ac42eb97-f574-5f6e-bd9b-9655c63076f1 | note | Designer Rep - R
16d83ac8-3600-4b02-bfd8-6332b6e5df37 | signoff | AUTHORITY HOLDPOINT
2037f9a5-af1f-47bf-b019-0eba4167ac82 | section | ITP APPROVAL PROCESS
e28d6f17-0cb5-4ef3-b165-df85b6bef760 | checkpoint-no-value | ITP APPROVAL PROCESS
d07cf6c7-6dbd-5630-a5e5-3f4c3dcd739d | note | Prepared By: Quality Engineer - Nas Matar
509aede9-d77b-5bc2-b7f8-8663fa6180a7 | note | Reviewed By: Project Manager - Dan Trotman
9186bd80-4f82-539b-82ec-a7650a72bf6e | note | Reviewed By: Design Engineer - Daniel Cvitanich
97c83a0b-f2b6-5921-a748-8db4bb104a6c | note | Reviewed By: AT Project Manager - Mike Robertson
ebc17cb5-97ca-536c-b037-b8fb1c843ab4 | date | Date:
02293cc0-241f-42e4-b9bb-8c56fbdfc16a | section | FINAL ITP CLOSE-OUT
57c488ce-3d8e-4d3b-aa2c-ff9ec3da750d | checkpoint | FINAL ITP CLOSE-OUT
177bd902-3f27-5b3d-b985-c128d25d4289 | textbox | Downer Project/Site Engineer:
55670b30-a0ad-5a61-bcd7-287588718925 | textbox | QA Mgr./Engineer:
ead2bf46-ff53-5b1f-9be5-87764b607420 | textbox | Designers Rep(Assistant):
85fc736e-a834-54ba-8a8b-b9d20cf91af6 | date | Date:
5e71343d-0c29-4595-ae99-e7e4e4da32f1 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
164f0234-40e7-51db-b5cf-0d29cca16329 | textbox | Contractor's Rep Name:
48f8cad7-c61a-5105-af6d-ddc63f93ac39 | textbox | Engineer's Rep. Name:
c4181882-7db0-5686-b7dd-372fba5c9182 | date | Date:
b44becb0-bc92-464b-b931-ead0534067fa | signoff | Add Signature
f4115cc5-cd7f-4944-8e50-0a1ef5747713 | checklist | DN1212-ITP-006 Ducting Rev4 | itp | DN1212-ITP-006 Ducting
4e385244-b016-44ec-932c-8a5131cd2388 | section | 1 - PRELIMINARY AND GENERAL
dfe13233-1d14-421f-a335-df1c1cea1a33 | checkpoint | 1.1 - IFC Drawings and Specification
2b0456c3-722f-5026-8ae1-3b9eb7bf7c42 | note | Standard, Drawing or Specification Reference - ACC
6d8dbeb5-2e13-51ba-997c-ec393297844f | note | Construction Activity Description, Test Type and Acceptance Criteria - A minimum of two weeks prior to construction: document review. DWG’s are for construction or as per instruction
b152e5ca-2205-566b-a4f2-717f16852e1c | note | ○ Works done in accordance with Project specification
7df589f8-f2a0-5dc5-a577-bb4a1da308bf | note | Test Frequency - Once
ca678604-d5ef-56ea-94ce-7d61fb7338dc | note | QA Record - N/A
59e5f9d0-1a77-5d58-9907-0aedb6f393d6 | note | DNZ Engineer - R
4803200a-f4a2-5e13-a305-6dd73af9291a | note | Designer Rep - H
7e605536-bafe-4903-99f6-3323257707e3 | signoff | AUTHORITY HOLDPOINT
f71bc233-6cc3-466f-907c-61d9b0081d99 | checkpoint | 1.2 - Method Statement & JSEA Development
a5956e5e-a31f-538a-b316-c6b1adb61cbb | note | Standard, Drawing or Specification Reference - The Downer Standards (TDS)
14457bfd-01f2-5cfe-862f-a57e42ff14e8 | note | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction: document review.
2f2d7922-e3d8-5eee-8d0d-299876b8755e | note | Test Frequency - Once
930364df-a111-5f01-9188-1b81bbf9c4a9 | note | QA Record - Method Statement & JSEA Completed & signed by relevant authority
2f61fe23-3f55-5154-af63-650a9f89ee52 | note | DNZ Engineer - H
09437a06-4989-56b0-8dce-8d624145df1c | note | Engineer's Rep - R
9b4847f7-429e-5f35-ba5a-4692258d8e25 | note | Designer Rep - R
f4aab4ed-bf2f-49ce-85b6-03e001c7f816 | signoff | AUTHORITY HOLDPOINT
3ebe19f0-97c6-4e47-af0a-721690433558 | checkpoint | 1.3 - Permit to Dig
82392a74-d16e-5919-bcc4-225099decda2 | note | Standard, Drawing or Specification Reference - DN-ZH-ST043 Ground Disturbance
2186cd5c-d01e-5552-8d33-591e8d138496 | note | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction. Permit in work package
104118bd-3719-53cd-bc4c-9df7c1959ec4 | note | Test Frequency - Permit issued each week
458467df-4ec3-5c80-86cd-f953fa89bce0 | textbox | QA Record - Permit number
cf85603d-8ffe-52c1-beb2-c78e87b01ff9 | note | DNZ Engineer - H
d7f3a404-604e-4e65-8476-c537a21c9a82 | signoff | AUTHORITY HOLDPOINT
ab0a96b0-a3ba-495d-ba99-302513a29dd0 | checkpoint | 1.4 - Survey Model
b697819c-edfe-57fe-b59a-1bbd0946776b | note | Standard, Drawing or Specification Reference - N/A
c06cbb60-cce3-52f4-8198-39becf622910 | note | Construction Activity Description, Test Type and Acceptance Criteria - Model Review.
514c1fa6-3e03-5d51-8f4c-7f5f89454a84 | note | Test Frequency - Once
9c54d6f9-5abe-5e4e-bf01-060d02b3ca1f | note | QA Record - Visual Inspection & measurement Survey Check set out as per design
942edf80-ac93-5394-a5c3-202edfc6db20 | note | DNZ Engineer - H
43e0dc0c-0f9b-47d3-b872-1245bb404dd2 | signoff | AUTHORITY HOLDPOINT
f8107342-02db-4088-9377-190ffd0a3855 | checkpoint | 1.5 - Corridor Access Requests (CAR)
eef0e414-205e-5a9a-8f15-c03bfcee510f | note | Standard, Drawing or Specification Reference - N/A
60b12665-6fc3-506d-9db5-ea6ed2de4d6b | note | Construction Activity Description, Test Type and Acceptance Criteria - Corridor Access Requests (CARs) is required before any work is carried out on public roads.
9c690859-8e58-59bc-982d-0ff91cba657a | note | Test Frequency - Once
aeac6eb4-49ea-5ef5-ba68-ea37ed7f1c55 | note | QA Record - Approved CAR
d3b57c27-01a5-5e66-8fd8-b2f166b506ed | note | DNZ Engineer - H
c866231f-7a5a-46a8-99d6-8fd10eee1122 | signoff | AUTHORITY HOLDPOINT
29903955-b845-4679-8cca-dfc2373ac6f2 | checkpoint | 1.6 - Temporary Traffic Management Plan (TTMP)
3098dca1-cbdd-56fd-b023-7d7812eac116 | note | Standard, Drawing or Specification Reference - COPTTM
210919a5-31c0-56cb-adbd-811fa812bc80 | note | Construction Activity Description, Test Type and Acceptance Criteria - Prior to works commencing: Review Approved TTMP.
081c67a3-774c-5cda-abde-e9e175e564f9 | note | ○ Required before any work is carried out on public roads.
9f49b43a-d612-5563-934e-02432dc04425 | note | Test Frequency - Once
3d6476fc-b04b-5465-aaa6-e350428dec19 | note | QA Record - Approved TTMP
57d641e3-51a7-5ee9-95d5-6e862b6f8625 | note | DNZ Engineer - H
a9f15313-bf1b-42f3-aa7f-73b5c6dc8f3f | signoff | AUTHORITY HOLDPOINT
6603affb-1887-4e65-b284-6afb85d8c2a3 | section | 2 - MATERIAL APPROVALS
3cb12ac7-f769-4e3e-ba16-b201ff6fae38 | checkpoint | 2.1 - Electrical Ducts: 100mm or 50mm nominal bore Orange Skin PVC Duct
28f7e9ea-3b49-5346-878f-2a30320c1027 | note | Standard, Drawing or Specification Reference - AS/NZS 3000
ee58b787-0669-502a-b6b5-457ac1d38c1e | note | Construction Activity Description, Test Type and Acceptance Criteria - Telecom Standard SN9 rating.
b0a1d0e3-659b-5ecc-88cb-9a71c2ce96e7 | note | ○ All bends to be swept bends.
8ef247a3-1cce-5af9-9a94-df1205c02c4d | note | Test Frequency - Once
7b31e407-9bf3-5185-8703-abab50c036ef | note | QA Record - Delivery Dockets
8114eb0e-6e5f-5dc4-ae78-d17722e94b08 | note | DNZ Engineer - I
1d73d853-8e4f-59e9-8d56-b03364958bcc | note | Designer Rep - R
b9431d87-4d42-4772-8f3f-138a8688b2cb | checkpoint | 2.2 - GAP 7 or Sand
aba1263c-7452-5b77-ada1-e3a4cf498eb3 | note | Standard, Drawing or Specification Reference - AS/NZS 3000 Figure 3.14 Page 201
a56c2b0e-7285-5b43-8b37-5dc62b0c5c38 | note | Construction Activity Description, Test Type and Acceptance Criteria - Gap7 or Sand to be used for bedding.
92edcf05-499e-5897-85e7-ce8a2eca3724 | note | ○ Maximum particle size 7mm.
ec52f00a-d437-53e1-9cc3-94f2f352451f | note | Test Frequency - Once
97f4685f-172a-56c0-bf66-26a50ea54458 | note | QA Record - Delivery Dockets
652ef001-4402-59d5-9b24-bb4386eff6c0 | note | DNZ Engineer - R
aed954ef-ae35-5730-a090-0b6a8020c1cd | note | Designer Rep - R
96f26df0-7397-4936-9c73-4bc2e669023e | checkpoint | 2.3 - Electrical Warning Tape
62002f7c-5957-5be7-91ac-17b4b0f06ef2 | note | Standard, Drawing or Specification Reference - AS/NZS 2648.1, AS/NZS 3000-Section 3.11.4.5 Page 198
af761d61-1a8f-565d-b602-347a796fd48c | note | Construction Activity Description, Test Type and Acceptance Criteria - 150mm Wide Plastic Orange warning tape with black lettering stating: "WARNING ELECTRICAL CABLE BELOW".
590b7df5-2546-53fe-9af2-edb487fd2282 | note | ○ Complying with AS/NZS 2648.1.
cffc9a5a-f4d5-5038-81e7-44c3ed15c279 | note | Test Frequency - Once
0ce6c9fd-439d-523f-9900-888e1e149842 | note | QA Record - Delivery Dockets
9b76a294-572d-5460-bc31-25edc64bbeff | note | DNZ Engineer - I
e0504890-c73e-5045-8378-a66425338ba1 | note | Designer Rep - R
e1bb1831-343b-465d-a3d9-20620b7f2a6b | checkpoint | 2.4 - Epoxy Mortar
e61fcfb5-ea1e-57e6-8bee-51b68ed5df75 | note | Standard, Drawing or Specification Reference - MDS
9f5eafb8-5029-58cd-a959-2ec966ec4cb1 | note | Construction Activity Description, Test Type and Acceptance Criteria - Hybond Two Part Epoxy Mortar or similar approved product.
904b9ed7-1e1e-5502-a8fd-6bbde80200bb | note | Test Frequency - Once
a7dfbc21-03bf-5284-bccf-264e133accbd | note | QA Record - MDS
b5198a8a-b5be-5dfd-a706-07abb9076c43 | note | DNZ Engineer - R
af811c7c-33ec-5153-b9e8-42fb4232dfb5 | note | Designer Rep - R
63a2cdfe-8ea1-4868-9828-c111f40a511d | checkpoint | 2.5 - PVC Solvent Cement
d4c36584-0554-5e53-8a4d-76b74813e00d | note | Standard, Drawing or Specification Reference - MDS
d5311792-b81a-5ba2-aa5f-7122a11d4654 | note | Construction Activity Description, Test Type and Acceptance Criteria - Marley clear solvent cement or similar approved product.
c57ffeaa-cd52-50ec-b6b4-69be6a5c5ac8 | note | Test Frequency - Once
7eb143ca-3046-5d2d-a18e-1bc945ef0d7f | note | QA Record - MDS
288f2c71-5133-5df0-8c2b-30b960b056ef | note | DNZ Engineer - I
2c04c894-7014-5d75-ac9b-53ca81280226 | note | Designer Rep - R
1462f35c-9c28-4850-bc7e-9dbf2fbcd95f | checkpoint | 2.6 - GAP65
25369d75-c513-58fe-8194-93bd7d1d476f | note | Standard, Drawing or Specification Reference - TNZ M/4: 2006 - 3, NZS 4407 : 1991, NZS 4402 : 1986
97ae3648-29f3-5004-8e21-168498e916cf | note | Construction Activity Description, Test Type and Acceptance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ accredited laboratory for crushing resistance, wethering quality Index and California bearing ratio ( Class 3 & 4).
29351e19-1611-5451-9883-fceabdbd3ecd | note | Test Frequency - Once Per Year
8dc91f5b-abfd-5022-91f1-34daaffc91e6 | note | Or
ed4df001-3a85-5c2f-a1c5-a3794d42951b | note | ○ Every 10 000 m³
5653a24b-5c58-5f8a-9339-a7891c8d235a | note | QA Record - Test Report
ae8d9055-2312-5172-9b87-f0255bca43b9 | note | DNZ Engineer - R
a978d13b-c263-53a3-9d3e-f115c6780b3f | note | Designer Rep - R
4af3eab7-bca1-486c-94c5-b4b7abe96d74 | checkpoint | 2.7 - Mechanical Protection (Mag Slab)
3ef4f1b3-0656-55be-b761-7aef33799582 | note | Standard, Drawing or Specification Reference - AS/NZS 3000 Figure 3.14 Page 201, AS4702-2000, AS/NZS 2648
4d3c4fb1-4e61-5c16-82ff-ecfb5bbe0e81 | note | Construction Activity Description, Test Type and Acceptance Criteria - Polymeric cable protection cover 150mm Wide Mag Slab or similar approved product.
fcdc6c21-e4e4-59d7-b5a6-809428eb9ee9 | note | Test Frequency - If required
071d61e3-13f4-522f-80a2-8b95025d51a2 | note | QA Record - Delivery Docket
bdc7cacb-fccd-5faf-a1de-2accb07b0b1d | note | DNZ Engineer - I
83212b19-76ec-56c0-94c2-e31adb20431b | note | Designer Rep - R
dc3a0b68-4119-4ba8-9132-b07569a35fc5 | checkpoint | 2.8 - Blue Building Strap (Draw-Wire)
3553bb2e-b825-5ce0-be5b-f3d3bb628db6 | note | Standard, Drawing or Specification Reference - AS/NZS 3000
76c6b885-53b1-5f0d-8d9d-99b56128387a | note | Construction Activity Description, Test Type and Acceptance Criteria - 19mm x 300mm or 25mm x 250m Blue Polythene Strapping.
6709b656-d925-558e-a0f8-52b6eb18c2fb | note | Test Frequency - Once
e887e805-de0c-56aa-a733-4aa82caed6ed | note | QA Record - Delivery Dockets
016afc31-a874-5895-bc34-78b02b9cf897 | note | DNZ Engineer - I
db177da9-5474-45b2-a382-e8b3cc628464 | section | 3 - CONSTRUCTION ACTIVITIES
6e5607c6-f247-4698-9950-91e40a0661e3 | checkpoint | 3.1 - Use of Existing Ducting
63586736-85b6-5993-b9db-fede95c56454 | note | Standard, Drawing or Specification Reference - 3235599-SP03-BE-1011, 3235599-SP03-BE-1012, 3235599-SP03-BE-1013 Note 3 & 4
080b9127-36f0-548d-8aaf-9698299e14b2 | note | Construction Activity Description, Test Type and Acceptance Criteria - Confirm space for new wirring within existing ducting route prior to the installation. If there is no space available, DNZ to size and run a new duct from MSB-E to Existing Electrical Pit.
f039853f-2c4b-559a-9f44-74bb2617de6a | note | Test Frequency - Where required
3b38fd27-a21a-5ed1-bf1e-f1d75538db3b | note | QA Record - As-Built
c633d08d-5362-57dc-be55-3bca8c3d25d6 | note | DNZ Engineer - I
5e847646-1854-4d6b-afee-bbd5edc58532 | checkpoint | 3.2 - Survey Set-Out
29ce9795-48d1-5771-b605-d278f00d89bd | note | Standard, Drawing or Specification Reference - IFC Drawings
643bb0cf-e094-50d6-bfe7-615fbae6d188 | note | Construction Activity Description, Test Type and Acceptance Criteria - Before works commencement.
3f8ae8d3-f507-54c9-936e-989bc79efc3a | note | ○ Set out by Surveyor.
d1ef4cd1-cbf2-5ecd-8048-a5b696312d83 | note | ○ Alignment as per IFC drawings.
fb9c087a-b8b7-53e8-949e-b1352181f652 | note | Test Frequency - Once
fa28adcb-7b1b-5bba-8ca8-adeb1c824b5f | note | QA Record - As-Built
1c80454f-1ccf-59d6-9946-96b29886f33a | note | DNZ Engineer - H
2614eb8c-293c-4397-a90b-643b82c268de | signoff | AUTHORITY HOLDPOINT
f2181d7f-dbb5-4f63-9852-7c52e7e081af | checkpoint | 3.3 - Trench Excavation to Depth
05a2052c-f321-5423-8366-f64b01d23825 | note | Standard, Drawing or Specification Reference - 3235599-SP03-BE-1011, 3235599-SP03-BE-1012, 3235599-SP03-BE-1013, AS/NZS 3000 Figure 3.14 Page 201
a69f9933-0d6d-5fc8-875c-142f2f19f7d2 | note | ○ Auckland Transport Design Manual (TDM) - Street Lighting Appendix L-Electrical Cable Specification Section 6.2
742017a2-129e-528c-a398-12b7b40fc29f | note | Construction Activity Description, Test Type and Acceptance Criteria - Ensure excavation depth achieves the minimum cover of 600mm from ground level to top of installed duct.
0685b023-9485-5182-9589-93ae86fd78a9 | note | Test Frequency - Once
7af17c24-bed9-50e3-a6aa-badfc6d30731 | note | QA Record - Checklist, Photos
1df1978e-a4e2-59c0-8fcb-7e48554acc03 | note | DNZ Engineer - I
608cf624-1c07-4cbd-9a20-88c4747c293a | checkpoint | 3.4 - Place Bedding
629ba469-7ddb-5dad-b135-fa65283f73af | note | Standard, Drawing or Specification Reference - AS/NZS 3000 Figure 3.14 Page 201
16e80ee5-6e51-50e8-a9d0-e3919a806fc8 | note | Construction Activity Description, Test Type and Acceptance Criteria - Ensure bedding thickness is a minimum of 50mm of GAP7 or Sand.
97d3125e-04d9-5e36-b012-590171e61462 | note | Test Frequency - Once
771eeace-3102-5bb1-a0d2-0c7fde65e803 | note | QA Record - Checklist, Photos
def1a8b7-ecd3-51fc-9077-59f3d18d202e | note | DNZ Engineer - I
5ba59050-ddc3-51c7-a1a4-c0766d933fdd | note | Designer Rep - R
763cbf62-d273-44c9-b6c3-a6317db21405 | checkpoint | 3.5 - Lay Ducting
9f2ff47f-7658-584d-8590-57970b9845a1 | note | Standard, Drawing or Specification Reference - 3235599-SP03-BE-1011, 3235599-SP03-BE-1012, 3235599-SP03-BE-1013
7a234ea8-4dbf-5134-b945-0d47bb6b7c14 | note | Construction Activity Description, Test Type and Acceptance Criteria - Minimum cover 600mm from ground level to top of installed duct.
a6ec6885-53ae-5d15-8461-e4164122d120 | note | ○ Lay ducting and back fill with GAP7 or Sand ensuring to have a minimum of 50mm on top of duct.
7f29e4c4-e75b-5101-a89f-eef94c8a1c33 | note | ○ Ensure 50mm separation between electrical ducts running parallel.
a24540de-700c-59f4-ad63-5c2c360ea6db | note | ○ Ducts to extend 50mm inside the pit.
ee05bcbc-505b-56b1-a3f9-2a85c23eac2d | note | Test Frequency - Once
fd35e61b-13a1-544c-9699-c9767bda6f7a | note | QA Record - Checklist, Photos
c98d0acc-72e2-5272-ae25-78926c32b5a0 | note | DNZ Engineer - R
75cf2772-ee19-5f00-8d94-4801187081a8 | note | Designer Rep - H
83ca3639-b652-4402-8be2-ba0a3e844778 | signoff | AUTHORITY HOLDPOINT
5c547189-62ad-4d5b-ae95-0cff9556c99c | checkpoint | 3.6 - Draw-wire Installation
94133966-638a-5270-a32a-ddc58303417a | note | Standard, Drawing or Specification Reference - N/A
63b5c94b-2817-594c-bdb4-7e67881ddcad | note | Construction Activity Description, Test Type and Acceptance Criteria - Draw-wire to be installed with 2.0m of slack on both ends of duct.
06eada17-fb90-5338-b290-906709620bcb | note | Test Frequency - Each Duct
404bda11-7a38-5fe7-89cb-8391ce962156 | note | QA Record - Checklist, Photos
4b103cc3-e5ea-5448-bb25-c128d87cba6e | note | DNZ Engineer - I
139ea4e9-a540-5d0e-9586-b333d8dded97 | note | Designer Rep - H
61cc2f18-b61e-443d-afb7-65c8e2f8a5df | signoff | AUTHORITY HOLDPOINT
3c8ba998-fb4f-44e8-bc93-ab6f2fc07f17 | checkpoint | 3.7 - Mag Slab Installation
6a3ed86b-ea3c-58fa-85fc-4c5d87a63326 | note | Standard, Drawing or Specification Reference - AS/NZS 3000 Figure 3.14 Page 201
ba899ffe-b738-5784-8679-58799e0cda75 | note | ○ Auckland Transport Design Manual (TDM) - Street Lighting Appendix L-Electrical Cable Specification Section 6.4
726a4389-b0c5-5e11-95f0-4762030cbb53 | note | Construction Activity Description, Test Type and Acceptance Criteria - If required mag slab to be placed 75mm approximatly from top of ducts.
14a3278f-0b89-5110-8c5f-af3fa31684d8 | note | Test Frequency - Each Trench
ce3c519a-f303-5511-b412-b66ca8504992 | note | QA Record - Checklist, Photos
0b7f675e-7cf5-5f8d-8b44-5381ef2bd68e | note | DNZ Engineer - I
b8fc0ab4-ac49-554f-adfe-d4d2c2599455 | note | Designer Rep - H
01bb7a36-1303-4abe-b376-f68683b92536 | signoff | AUTHORITY HOLDPOINT
109dac43-e99b-4734-8179-13f2281f8f99 | checkpoint | 3.8 - Marker Tape Installation
9c6c08f5-f46c-5bda-b32f-d64d4a0814e8 | note | Standard, Drawing or Specification Reference - AS/NZS 3000 Figure 3.14 Page 201
74fabbfe-36d6-54f6-9b75-d40a80aea58e | note | ○ Auckland Transport Design Manual (TDM) - Street Lighting Appendix L-Electrical Cable Specification Section 6.5
9be7de06-9298-5bb1-baf2-037096727088 | note | Construction Activity Description, Test Type and Acceptance Criteria - Plastic warning tape to be placed 250mm below ground level prior to GAP65 backfill.
09bc36d0-4368-5c26-bdd3-d9831975248d | note | Test Frequency - Each Trench
eb581a37-6499-5390-8a23-11d1dabccb58 | note | QA Record - Checklist, Photos
ee945adb-3953-5da4-bbc7-d0a7c8f62977 | note | DNZ Engineer - I
3d2905ea-e254-5745-a31f-6fcbd473cbe2 | note | Designer Rep - H
39f766ea-ee57-4a6a-9654-8e18062397bc | signoff | AUTHORITY HOLDPOINT
a657b586-48fe-40f7-9f0d-bfa7ca151d46 | checkpoint | 3.9 - Backfill in Layers
8e7ee2f8-bdd1-5ee0-bf7f-9581c6f711f2 | note | Standard, Drawing or Specification Reference - Auckland Transport Design Manual (TDM) - Street Lighting Appendix L-Electrical Cable Specification Section 6.3
2829e11e-8c3d-599d-858c-a00efdfec3b9 | note | Construction Activity Description, Test Type and Acceptance Criteria - Ensure trench is backfilled with GAP65.
bab911a3-3a5d-5159-8334-72b23b14a494 | note | ○ Backfill in 100mm layers, hand ramming the first two layers followed by power compaction.
a7f942c4-4394-5f4e-993a-976671b5f882 | note | ○ Clegg test each backfill layer to achieve CIV: 12
baa25bc9-53a6-50c8-b173-0a722a734942 | note | Test Frequency - Each Layer
38c3401b-b70e-5b0e-841d-4437cd7e5876 | note | QA Record - Photos, Clegg Results, Checklist
a61be16a-9d6e-56fd-8122-c50ee2c9e958 | note | DNZ Engineer - I
560a86f6-50d4-5136-af46-003f8bdc08c7 | note | Designer Rep - R
06a3403a-7748-4956-b5c0-5cdb8a8a2053 | checkpoint | 3.10 - End caps or electrical tape
87621d83-8c2c-55ca-ad97-2fe24ee9ce74 | note | Standard, Drawing or Specification Reference - N/A
ded41c42-e736-59e2-899d-36862ac0a69d | note | Construction Activity Description, Test Type and Acceptance Criteria - Ensure all ends to have capping or tape cover.
ed939dfa-a6dc-59ae-a33f-f67c9ba53c00 | note | Test Frequency - Where required
361f23af-dfa2-59f7-874c-2c0e6f06a866 | note | QA Record - Photos
ae5f406f-3871-516c-8269-1bf7b90e7c53 | note | DNZ Engineer - I
573b88c9-764e-47e4-83d2-70691bb34d2a | section | 4 - FINAL RECORDS
628652f6-dd0c-4890-9570-f75d0d0ae9a5 | checkpoint | 4.1 - Construction Record Compilation
4364b821-8533-56f6-afc8-c3750c00a184 | note | Standard, Drawing or Specification Reference - N/A
efa6313b-8cb7-5c1d-9155-0c8599a97b72 | note | Construction Activity Description, Test Type and Acceptance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
bf38c797-8dea-5a44-8aed-8a618619b095 | note | Test Frequency - Once
3902fc7d-3946-5adf-b111-233cd60a7762 | note | QA Record - QA Records
3b001148-c0e8-535a-bce5-0327e481c18d | note | DNZ Engineer - H
3b625ade-fde1-5165-9450-8593d006de0d | note | Designer Rep - R
1fe4e9e7-7ea6-44df-8144-c4df0b3a00ad | signoff | AUTHORITY HOLDPOINT
1e80d1d2-bf58-49da-886b-d894bd4aad84 | checkpoint | 4.2 - Survey Records
e5530e23-f31c-5835-8f33-41f843a63afe | note | Standard, Drawing or Specification Reference - N/A
12515992-37ba-59c7-8a7a-f5e9e0a31a40 | note | Construction Activity Description, Test Type and Acceptance Criteria - Ensure all items have been surveyed.
95dd849e-4495-53ce-a13c-cdb9472b3409 | note | Test Frequency - Once
218c5a48-04c1-512d-b637-059c4ad306a9 | note | QA Record - Survey Data
fd9fefa9-2026-5899-8dad-6ebaa6ec22cb | note | DNZ Engineer - H
494cad47-b2aa-5092-916f-5e1b79411343 | note | Designer Rep - R
0fd7d7f8-632f-42b4-acca-3a5f497e6a5a | signoff | AUTHORITY HOLDPOINT
c5f581db-20cb-40b1-ac60-28f058bc1a2b | checkpoint | 4.3 - Redline Drawings
7686fafe-f10c-5fdb-beea-55e1e58c8ddd | note | Standard, Drawing or Specification Reference - IFC Drawings
ede31543-3d89-5593-9723-967c3b28b8ba | note | Construction Activity Description, Test Type and Acceptance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.
ed2624d5-f062-5b45-b7a1-c0d1d0c1a4a5 | note | Test Frequency - Once
7847b5c7-180a-54e6-ac3a-9a4a7bc4c9ce | note | QA Record - IFC Mark-Up
fef0a444-beb8-5e38-b658-46d614ef902a | note | DNZ Engineer - H
572440d2-592a-5864-8afe-5d8feaa7348d | note | Designer Rep - R
96dff737-abd8-472a-ad70-d73e2a9e35c0 | signoff | AUTHORITY HOLDPOINT
1eaac162-3f6f-45d7-b2f6-8d08f91bc02e | checkpoint | 4.4 - As-Built
4b2ced3d-89cc-593c-aa91-e5003beff588 | note | Standard, Drawing or Specification Reference - Contract Specifications - General Section 2 Page 21
cce884f0-5488-5153-b312-6096c021fcaf | note | Construction Activity Description, Test Type and Acceptance Criteria - Complete final as-built 2D drawings to be handed over with the CAD files.
96e4ae0f-81b2-51cd-a55b-f364063f9bf4 | note | Test Frequency - Once
a5ff30f7-cad4-5daa-bf42-6aaea4e7aea4 | note | QA Record - As-Builts
f1bded90-6ff1-5fc0-b8e7-81ff30b78124 | note | DNZ Engineer - H
bde71c62-f900-5951-a6bc-6421f427b6d7 | note | Designer Rep - R
e309053a-479b-46b2-801c-6a1ca073d352 | signoff | AUTHORITY HOLDPOINT
eb7b2417-6c3a-465c-9ee9-517dd6041939 | checkpoint | 4.5 - Non-conformances
c8d88679-fcc5-5349-8427-7956a6be4166 | note | Standard, Drawing or Specification Reference - DN1212-DOW-PLA-PM-0005 QMP
fc4d7456-9f78-5943-9609-223dec4a569b | note | Construction Activity Description, Test Type and Acceptance Criteria - Non-conformances reports to be raised when specification not met. All non-conformances within the area under review need to be listed on the NCR report.
d3fd35b5-e64e-5230-a91b-af6169ca7a55 | textbox | NCR Reference
3d1de7b0-f78f-56bd-977f-162e01104606 | note | Test Frequency - When Required
12f8b6fb-4b24-5869-96b9-6525fd890f83 | note | QA Record - NCR Forms on InEight
ef554fc1-b1b6-5399-9ad0-e6c73023d780 | note | DNZ Engineer - H
bf9eecf6-445a-524f-95cc-2ea0516d502a | note | Designer Rep - R
6eb4c4b7-478c-413f-9404-58d865ff4003 | signoff | AUTHORITY HOLDPOINT
63b40952-f650-4a9f-9d17-f161582516f9 | section | ITP APPROVAL PROCESS
71c79db7-b59c-4a9d-b223-fcc060d18d38 | checkpoint-no-value | ITP APPROVAL PROCESS
cb8e067c-55aa-5ffe-a619-deddad953367 | note | Prepared By: Site Engineer - Moses Kaufanga
9ce79c5d-ccf0-5ae7-b0d6-28390185994a | note | Reviewed By: Quality Mgr./Eng. - Nas Matar
f45df07c-922b-5225-a34b-56592ad06cc8 | note | Reviewed By: Project Manager - Dan Trotman
658c9490-2e4c-5c79-858e-a5564e4c7eba | note | Reviewed By: Design Engineer - Daniel Cvitanich
8a6a89e3-c028-598b-baae-d51a70e2e321 | note | Reviewed By: AT Project Manager - Werner Nel
b1df2442-d6e4-55ce-94f3-63c60e2528d4 | note | Reviewed By: AT Engineer to Contract - Mike Robertson
7d4be000-b8fb-51b2-8b32-4233ce38efee | date | Date:
814b4993-f293-4fcf-8103-2fefff0da367 | section | FINAL ITP CLOSE-OUT
1338ab75-cf5f-4a45-8da4-902773d860e2 | checkpoint | FINAL ITP CLOSE-OUT
668a1fe6-ef52-55b7-b0a4-e34298278e52 | textbox | Downer Project/Site Engineer:
6058649e-a423-5b6e-b4ba-a02811303f4c | textbox | QA Mgr./Engineer:
20fe8917-8b77-53ae-aba0-88399c1e7883 | textbox | Designers Rep(Assistant):
ad8adc24-cd92-592f-9cb6-dbf26e79b580 | date | Date:
58b307f6-e32d-4fc5-aa5a-077c65cda6ca | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
a8a0e189-52e1-5fe4-96b6-50261a032071 | textbox | Contractor's Rep Name:
31f0c3c3-a31b-56d7-8863-2ec606a94f8b | textbox | Engineer's Rep. Name:
08b3cd5a-e923-58ee-aeca-e7905a598204 | date | Date:
e04b0779-7280-42dd-bd75-345a996c1d6b | signoff | Add Signature
1698c9e8-355f-449e-8382-ccaa15b9c107 | checklist | DN1212-ITP-007 Pier 3 & Pier 4 - Column and Headstock Construction Rev2 | itp | DN1212-ITP-007 Pier 3 & Pier 4 - Column and Headstock Construction
ffdc8b3d-d7bb-4061-8c18-8fa55a082036 | section | 1 - PRELIMINARY AND GENERAL
7a654c5e-afdc-47a1-accc-5a1e38a4b17d | checkpoint | 1.1 - Method Statement Development & Safety Analysis
3cc88eef-a02b-5b42-a4b7-1998702cbf83 | note | Standard, Drawing or Specification Reference - The Downer Standards (TDS)
7f010b7a-c2db-5562-ba18-4e81ae920f30 | note | Construction Activity Description, Test Type and Acceptance Criteria - Prior to Construction: Document Review
cc892e28-0985-5e6b-bb32-4e1a2d55b860 | note | ○ Method Statement & JSEA
ed6b1ca4-5b6a-57e2-849c-4c1de4113159 | note | ○ Completed & signed by relevant authority
2a9b3476-b8ba-578c-8e2f-589ab7d76a68 | note | Test Frequency - Once
f9b95148-17a7-5c97-b8e6-8c7a8175c897 | note | QA Record - Work pack (MS,JSEA,ITP)
071edde1-a632-53b5-a4e9-f37a1ec203d9 | note | DNZ Engineer - H
823709f6-ad5a-594f-8a61-d7820dab52fa | note | Engineer's Rep - R
c50e77c0-8fd3-5a77-b072-af1aa3404cb4 | note | Designer Rep - R
61e55096-f304-4632-9949-d1b968e1c7bc | signoff | AUTHORITY HOLDPOINT
c9aa638d-9bbb-4f87-a767-305f903ff1e2 | checkpoint | 1.2 - IFC Drawings and Specification
ddeb3147-0ae3-5dbe-bff7-ae1213d73b15 | note | Standard, Drawing or Specification Reference - ACC
8658085d-41bb-5220-8115-d3a8f77cf25f | note | Construction Activity Description, Test Type and Acceptance Criteria - A minimum of two weeks prior to construction: document review. DWG’s are for construction or as per instruction
eb397d6a-b556-5608-a5df-30c205ecc56a | note | ○ Works done in accordance with KiwiRail specification
6bea7482-793f-5324-8679-007b6abf6332 | note | Test Frequency - Once
a9a9fcf4-3efb-58b1-9369-a0556c65f464 | note | QA Record - N/A
1a0fcac4-4015-5aa0-a6bc-6a282f6ddb1b | note | DNZ Engineer - R
e0d8f861-a9ef-4b22-a572-d2540104d677 | checkpoint | 1.3 - Model
55e46cad-b631-5624-a66a-d434459348e0 | note | Standard, Drawing or Specification Reference - ACC
5f6bdfef-0562-5986-b8a6-907d81a01c61 | note | Construction Activity Description, Test Type and Acceptance Criteria - Model reviewed and confirmed with correct location; depth, height and orientation for column and headstock
351539df-4473-5862-aeb9-97e1a099aad4 | note | Test Frequency - Once
e49f7a0e-9e5e-5c8a-9175-7c07f3dae903 | note | QA Record - N/A
b04816ee-01a3-5c15-ada9-ae5228aeea7d | note | DNZ Engineer - R
dd5e35c4-0f09-4589-a31e-f4c95d3f4995 | checkpoint | 1.4 - Permit to Dig
524f5899-8792-56ab-adba-d6d2e41ca4be | note | Standard, Drawing or Specification Reference - DG-ZH-ST004 Ground Disturbance
be550c5a-a6be-520c-8a8d-31104767870f | note | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction. Permit in work package
610f0322-beb8-54c0-ab47-b66bf107808c | note | Test Frequency - Permit issued each week
fe521728-a481-5b03-9bd2-3de7cc93db6f | textbox | QA Record - FlowForm Permit Register/Permit Number
d84cf5eb-a0eb-55c5-a529-14808208210b | note | DNZ Engineer - H
462d888f-874f-47f2-b90e-14a98b5f3604 | signoff | AUTHORITY HOLDPOINT
b49b2435-a769-4bda-82fd-1555ef6e06ed | checkpoint | 1.5 - Lifting Permit
92bbc22e-0674-588a-b8a6-16a8fb6290bc | note | Standard, Drawing or Specification Reference - DG-ZH-ST047 Cranes and Lifting Equipment Loads
f77dbc8a-d3d3-5d9d-8448-1af468055124 | note | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction. Permit in work package
7d1c6321-5a6c-5f64-ac25-eb9f10078650 | note | Test Frequency - Prior to Construction when required
4bf93129-31f4-5d21-8d35-57c8a2a2e3cd | textbox | QA Record - FlowForm Permit Register/Permit Number
8692a1fa-02d0-5175-bba3-2433c958ac14 | note | DNZ Engineer - H
5be26801-db5f-4426-b3e5-51917b4fa1fc | signoff | AUTHORITY HOLDPOINT
1b992f4c-8159-4db3-97c4-0b10fdcb5bb2 | checkpoint | 1.6 - Working at Heights Permit
6335430a-68ca-5455-960b-23916adfb780 | note | Standard, Drawing or Specification Reference - DG-ZH-ST042 Working at Height
6ae38829-fa6c-5bcc-91d0-6468a50d93bd | note | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction. Permit in work package
78989969-3ee0-590d-bbc6-d6fbc6df05ca | note | Test Frequency - Permit issued each week
25936885-ec17-5ffe-9ed8-24bbc9ed967f | textbox | QA Record - FlowForm Permit Register/Permit Number
9a0674de-db22-5a54-a3f5-ca1dfd489b4e | note | DNZ Engineer - H
9d2f60b4-f4dd-41c4-b6c1-d6b2c3f560d9 | signoff | AUTHORITY HOLDPOINT
5a8e08c4-3ac3-4247-acd5-3248bf94ccb8 | checkpoint | 1.7 - Permit to Load - Scaffolding
ea7aa643-1378-5b40-bfbf-cf5208b92f85 | note | Standard, Drawing or Specification Reference - DG-DM-PR036 Temporary Works Procedure DG-DM-FM066
e6aecbf7-06ce-575d-a3d7-c9498bb928f5 | note | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction. Permit in work package
2fcf5802-4f98-5637-9230-3decfa887f67 | note | Test Frequency - Permit Issued prior to construction
95e54fa2-3c99-59f5-8c4e-82da19a1f643 | note | QA Record - Temp Works Certification ITP
9d82b09b-1692-5c22-8171-2012916f00ac | textbox | Permit to Load - PtL
ff2b3505-04b4-5e76-8384-17936a1219bd | note | DNZ Engineer - H
36acbf8a-a5f7-49ee-a384-1dc5d2185160 | signoff | AUTHORITY HOLDPOINT
6d06dc4d-3ae0-4976-a720-b5a09283bb1b | section | 2 - MATERIAL APPROVALS
202256e8-3669-46ba-9cb2-1f640da0741e | checkpoint | 2.1 - Concrete Mix Design
79e2b6f8-036b-5171-9276-1a7890f6048a | note | Standard, Drawing or Specification Reference - NZS 3104, SP-NIMT-ST-AD-00001, Section 2.3.10
833fe720-ec47-5144-8fce-b055c77de23f | note | Construction Activity Description, Test Type and Acceptance Criteria - Concrete mix details shall be provided to the Engineer for review and approval.
decf3b7e-a7c5-5016-806c-d551d2f8a8a3 | note | ○ 50MPa @ 28 Day Compressive Strength.
55dbcdae-5cee-53ee-9336-3d8696a49702 | note | Test Frequency - Once
9e617322-4aa5-5ca6-945b-e15c5cd47d51 | textbox | QA Record - Mix Certification InEight Response
193f5fa3-c84b-54dc-a1f7-f82e0a86c3f5 | note | DNZ Engineer - R
607568cf-3ab1-5b1f-84f6-d80ea16420b8 | note | Designer Rep - H
591820ff-9f27-409e-b6d1-175a181593af | signoff | AUTHORITY HOLDPOINT
28428a70-59e0-49ba-9528-ca7abb9391e4 | checkpoint | 2.2 - Reinforcing Cages
6b14639c-db98-5c92-a594-dade137b60f8 | note | Standard, Drawing or Specification Reference - Reinforcing Cage Drawings -
8d499fd3-c998-5ff9-bb65-bb9056c64402 | note | Construction Activity Description, Test Type and Acceptance Criteria - As per Column Reinforcing IFC detail drawings.
7392bf82-e29d-5594-a8ad-7d1619d7cbd7 | note | ○ Shop Drawings shall be provided to the Engineer for review and approval.
88c557be-66d4-53d1-ab03-34601b4ac5b6 | note | ○ Note any changes undertaken to reinforcing to be captured as per item 4.2
75cd019d-80da-5ac2-8fbb-412af6a762a9 | note | Test Frequency - Every Reinforcement Cage
e58092ff-59cb-5bd7-aec4-9a372e1bc007 | note | QA Record - Mill Test Certificates, Delivery Dockets
04a7d466-0942-5f82-8830-7055a2f1691d | textbox | In Eight Response
2a08596b-dbd3-528e-b2d9-aa5f060587b2 | note | DNZ Engineer - I
3b1699b5-0593-52fd-8421-b37a08b42cca | note | Designer Rep - H
3c0d9337-62f6-48f3-9163-2de325b3470b | signoff | AUTHORITY HOLDPOINT
bb1f6ac4-0d03-4ba1-86ef-2ed039994236 | checkpoint | 2.3 - Formwork
018f7896-f6aa-5780-bf8a-3078b65a8d2d | note | Standard, Drawing or Specification Reference - Material Data Sheet, Temporary works drawings Piers 3 and 4.
a783744a-c7a5-5243-8031-95ce0e91a057 | note | Construction Activity Description, Test Type and Acceptance Criteria - Formwork of choice from sub-contractor, Standard panels up to 900mm wide modules
70f4240b-3391-5c9a-bc15-dc13ace1c7b5 | note | ○ Rigid hollow-section steel frame
1e7da56a-680d-5811-84ad-488101ecc380 | note | ○ High-grade hot dip galvinising for durability & long life
54d37da3-7c6d-58b7-ac2c-8fbfb2320674 | note | ○ Gang forms and lifting applications available
2fffb114-beae-5f1f-80ca-960d2fa26c84 | note | ○ Full range of safety features
116a11a0-87a6-527e-a8ad-d270485575a7 | note | ○ High Quality plywood
b372cee6-f111-57d9-acac-988f511c6f2d | note | ○ 60kN/m2 permissible fresh concrete pressure
c97bce07-9d24-521a-b710-f0fb6ace9722 | note | ○ To be captured on temp works drawings.
8897ad12-2c7a-5b71-a106-abb6e2715311 | note | ○ Inclusive of structural shore loading for super structure
0fda30f9-13ca-5c77-aca5-9020268de542 | note | Test Frequency - Once
014c7c27-7878-5429-95e2-3d46bde48762 | note | QA Record - MDS
2bfbcc97-cec1-50ad-8296-45df04314256 | note | DNZ Engineer - I
e47b59ff-58dd-5e41-8a8d-699c0861a91d | note | Designer Rep - R
b2597bc3-bfe9-473f-bcd0-160629bdb307 | checkpoint | 2.4 - Formwork Curing Agent
06532ebf-fabf-5dfa-945b-5052f232d4e7 | note | Standard, Drawing or Specification Reference - Material Data Sheet
0e388d2f-d3b9-5505-87ed-d4f8bf302bd9 | note | Construction Activity Description, Test Type and Acceptance Criteria - Chemical curing agent.
6a58d3db-2f6b-5de3-85f0-2f91b15f8440 | note | ○ Concrete to be retained in shutter for at least 3 days, must obtain 30 Mpa prior to striking. Curing agent to be applied to the top to of concrete pour to act as a sealant.
8949213b-e059-5f5b-b5b1-e1e457f386bf | note | Test Frequency - Once
6cad5877-9093-5111-be01-417ea63f08bf | note | QA Record - MDS
0c9dd370-2987-51e1-9591-4035bf43a62a | note | DNZ Engineer - R
c56fdcb6-2a1d-5109-9aa7-3d88679a73b5 | note | Designer Rep - R
222df4e2-a7c4-4bbd-9776-29fbeb5e949d | checkpoint | 2.5 - Reid Bars
66272e0d-dd9a-5f7f-8c44-7f08dc68da3c | note | Standard, Drawing or Specification Reference - Material Data Sheet, 3235599-SP03-ST-3002
d410f337-7adf-50ad-a0d6-d104e724d46a | note | Construction Activity Description, Test Type and Acceptance Criteria - RB25FNS Reidbar Steel Flange nut, as per noted 8 & 9 on drawing 3235599-SP03-ST-3002. Proposed epoxy will be per manufacturers recommendations to use C8 extreme epoxy. Superstructural couplers will be covered under PFS installation methodology and ITP. This is only for column / headstock construction.
995aeba0-c50f-5e6a-b502-b7c337bd6f7b | note | Test Frequency - Once
f50a7f64-f4af-5cd0-b720-a96412ad3a10 | textbox | QA Record - MDS, Delivery Dockets, mill certs
4c2b4109-a5be-500b-a468-401ca190a4ad | note | DNZ Engineer - R
705b63e1-579f-5920-8028-2fc18ec91450 | note | Designer Rep - R
32c3f0af-96f5-44b3-80c4-57be55f49a80 | section | 3 - CONSTRUCTION ACTIVITIES
cde30153-181a-47d0-9814-d487da832262 | checkpoint | 3.1 - Column Set-Out
87a1c10c-5033-5985-a9cf-802246066b6c | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3100, 3235599-SP03-ST-3150, 3235599-SP03-ST-3202
b929c7bd-3964-5771-a4d5-4107627b4c11 | note | Construction Activity Description, Test Type and Acceptance Criteria - Before commencing formwork installation, survey set out column position based on drawings with RL supplied. Set out to include; Column centre, height and offset. Tollerances for insitu concrete pour taken from NZS 3109 table 5.2
e73ece89-4edc-5da0-af5e-aaeea91a85a2 | note | Test Frequency - Each Column
b6437a3e-0f1a-5d2d-aab7-5df276070e30 | note | QA Record - As-Built
182e0a17-8d82-54d4-ad18-68199b3f7256 | note | DNZ Engineer - W
42799705-2236-4c06-8ee9-ff33f6bdea8a | checkpoint | 3.2 - Formwork Installation
654a0891-16bd-5b11-8f92-1a1a0cb0c8dc | note | Standard, Drawing or Specification Reference - Material Data Sheet, Temporary works drawings Piers 3 and 4.
6ec6f93b-a767-51e1-9438-a2f2fac56172 | note | Construction Activity Description, Test Type and Acceptance Criteria - As per Temporary works drawings for Piers 3 & 4. Inclusive of shoreloading requirements for the support of the bridge superstructure around Piers 3 and Piers 4.
a4d7e671-3041-5385-8d77-5b1179a11e99 | note | Test Frequency - Each Structure
5794096b-cce6-5235-803d-13fdb5265fdd | note | QA Record - Photos plus signed off Temporary works inspection of shuttering and formwork.
b6d22890-e618-5201-843d-ef7d42b72774 | note | DNZ Engineer - W
bbf3d45a-9ace-4a5c-bea8-80af2df17a13 | checkpoint | 3.3 - Steel Cage Installation
1881af31-0dac-5af5-8a91-988c626b2883 | note | Standard, Drawing or Specification Reference - As per detail Sheets for Pier 3 and Pier 4, 3235599-SP03-ST-3210
555022c4-7520-51d8-a162-780e647fed0b | note | Construction Activity Description, Test Type and Acceptance Criteria - Cage installation will checked prior to placement to ensure that cage inspection requirements identified by BECA on 09/12/24 have been addressed and closed out prior to placement. Checks to be undertaken to confirm that lap lenths have been achieved during placement and survey to be undertaken to confirm posistion.
539fee06-9ce2-596d-b18f-13579a03759b | note | Test Frequency - Each Structure
33ccd413-510e-5e2d-bbf3-27067d7d7d10 | note | QA Record - Photos
9228ff19-a189-5245-acc8-a64dd41e3140 | note | DNZ Engineer - H
252de4a2-bf83-5b54-85e9-65ec54ab345b | note | Designer Rep - R
09d44251-3d27-4b88-813b-d4a0726a1e5a | signoff | AUTHORITY HOLDPOINT
bd5d3567-3a5c-41d6-9673-e0404996798f | checkpoint | 3.4 - Concrete Pre-Pour Inspection
7891e6e2-968a-5f3d-ab13-0c61a43b4d63 | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3200 - PROPOSED ACCESS RAMP- EXISTING PIER 1 DETAILS
b5b3b7b8-a2c2-5a84-8606-4a1fcb44a75f | note | ○ 3235599-SP03-ST-3201 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS
98b502e2-746d-59af-b097-cd0f5d21fc86 | note | ○ 3235599-SP03-ST-3202 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS
3cc5303e-c5f8-5ea8-b3b5-720c5b37ca86 | note | ○ App 1C - 746-24-847-AC - Tech Spec - Geo & Struc
0678a978-144a-56b4-9479-6e840b6cccd4 | note | Construction Activity Description, Test Type and Acceptance Criteria - Reinforcing cage as per IFC and shop drawings.
d29e8668-0e0b-5802-b9fe-b9a793e59fe7 | note | ○ Correct number of bars and grade.
04098c2f-f597-54f4-bef6-f0d29a8b9291 | note | ○ Correct steel lapping.
c1ca51bc-fe82-5163-ace6-099e11fee517 | note | ○ Earthing and Earth terminal tested and inspected.
43a68830-981d-52e0-bb9b-6039bb34c6e7 | note | ○ Formwork installed as per the Temporary works drawings.
1f35660f-b193-5053-a822-1927efdf299b | note | ○ Minimum 40mm cover achieved.
9140f5c4-1408-5fe1-9142-29093d01fdcc | note | ○ Test specimens to be supplied by plant for every 75m³ for each shift of conncrete ordered.
89eda0c1-a9fb-54e4-87a2-4a4f36464583 | note | Test Frequency - Each Structure
e65d8caa-5d37-58bf-90dd-ba68834f2249 | note | QA Record - Survey Check, Structural Engineer Inspection, MSQA SVR, Pre-Pour Checklist, Photos
11dec618-9978-56a9-94f3-c2f261ee5726 | note | DNZ Engineer - I
09f59f2d-8dc1-5e83-a10c-4a0e930999ec | note | Designer Rep - H
a2ebb6d5-6d81-48d7-b1c9-2868ce9618b2 | signoff | AUTHORITY HOLDPOINT
ba1e936c-e582-46ad-a8db-7ed28de7cff5 | checkpoint | 3.5 - Concrete Pour
a706fef9-f0f9-5142-af32-f4abffbf0ee1 | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3200 - PROPOSED ACCESS RAMP- EXISTING PIER 1 DETAILS
7776eb5c-9248-523c-969c-d2a947d0bb80 | note | ○ 3235599-SP03-ST-3201 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS
88f49055-8d80-5a12-9b99-c1852cf749e4 | note | ○ 3235599-SP03-ST-3202 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS
23e35de1-6c45-5bce-b7a3-654ebb89e710 | note | ○ App 1C - 746-24-847-AC - Tech Spec - Geo & Struc
c6e2e82c-bf7d-5ba3-8a85-d5c0f408d464 | note | Construction Activity Description, Test Type and Acceptance Criteria - Concrete: 50MPa - Self Compacting Concrete - WS5010FS
ce415a85-281d-58e5-acc5-4fdc17992588 | note | ○ Cylinder test taken at supply Yard only.
0e799d90-29f4-5f03-b4d6-cb914d5b901b | note | ○ Spread Test to be completed on site prior to concrete pour.
dcd55f2b-685e-5daa-9362-85113c99c02b | note | ○ Target Spread Test - 680mm +/- 60mm
bb2f9661-8461-55d1-85d1-5bd4610543ab | note | Test Frequency - Each Pour
98af72dc-9e40-5118-a65c-fe7355b658ad | note | QA Record - Delivery Dockets, Compressive Test Results, Photos
395dff4c-6aa5-58c2-b877-5318c1efa7db | note | DNZ Engineer - H
63dee53a-ee48-595e-abc6-37d0c2776a51 | note | Designer Rep - W
6ea8432d-b0f8-4007-aed3-1995388fe6f2 | signoff | AUTHORITY HOLDPOINT
efec5100-d9c8-46e2-8454-545816e73afb | checkpoint | 3.6 - Stuctural Concrete Finish
1fffc2b7-f0be-5afe-a2b2-33c4475c2484 | note | Standard, Drawing or Specification Reference - App 1C - 746-24-847-AC - Tech Spec - Geo & Struc 3235599-SP03-ST-3003, NZS 3114, NZS 3109
527bb078-c2f4-5d08-885a-8f884b265eb9 | note | Construction Activity Description, Test Type and Acceptance Criteria - Non Visible Surface Finish - F1
fd13832a-652b-5c9e-a658-051e2a5f6d67 | note | ○ Visible Surface Finish - F5
8bb09fee-9c87-58d3-b1c0-b1ebefcf83c8 | note | Test Frequency - Each Structure
511f9593-d85e-53c1-80f1-a93fbebbefe6 | note | QA Record - Visual Inspection, Photos
e03f78d3-fb23-5744-8486-fb069b8914f8 | note | DNZ Engineer - H
0ebcb849-5b54-5282-8108-5decfbbc3804 | note | Designer Rep - I
4c6c02a8-bc08-4542-b560-0fb47e659119 | signoff | AUTHORITY HOLDPOINT
4e62344d-72df-428c-92d5-2101068d0aaf | checkpoint | 3.7 - Concrete Curing
06697d8e-6b8c-596e-a796-19003987122b | note | Standard, Drawing or Specification Reference - App 1C - 746-24-847-AC - Tech Spec - Geo & Struc 3235599-SP03-ST-3200
74e964a1-f23d-50e1-b2b4-3d6b53d4573f | note | Construction Activity Description, Test Type and Acceptance Criteria - Concrete to be cured for a minimum of 3 days as per drawing st-3200, curing methodology will be formwork curing. Cylinder to be taken at 3 days to verify strength of 30 Mpa has been achieved prior to stripping of formwork.
38b5115d-76a6-5298-9340-5eaaab7cef9b | note | Test Frequency - Each Structure
22ba0104-3bef-5e4b-9d2a-a1062f363ef6 | note | QA Record - Concrete strength results, concrete pour checksheet notifying date of formwork striking.
bf70ff71-73a2-546a-9ead-c9e44e032bb4 | note | DNZ Engineer - H
e5e045ce-c609-5577-ad19-0f657a4ca893 | note | Designer Rep - R
1968d9db-bf28-4dfa-aa7c-41dd3598ddf7 | signoff | AUTHORITY HOLDPOINT
0fb2f3e1-e01e-4f36-a6d8-7cfda9ac3fb5 | checkpoint | 3.8 - Post Pour Inspection
2df0fcf0-8dc4-5629-9fb7-20f713eb390c | note | Standard, Drawing or Specification Reference - App 1C - 746-24-847-AC - Tech Spec - Geo & Struc 3235599-SP03-ST-3003, NZS 3114
0a171f76-f9a5-5ff3-a400-c41ca10963cb | note | Construction Activity Description, Test Type and Acceptance Criteria - Joint inspection be undertaken with designer to inspect shutters of structure following removal of shutters and survey/ check dimeniosn of structure have acieved stipulated tollarences stated in drawing suite and NZS 3109 Must achieve F5 finish for surface.
2e3e27e1-de35-546e-843d-45933161107f | note | Test Frequency - Each Headstock
c49eeae6-a83b-5620-90e8-e731b482f0f6 | note | QA Record - Visual Inspection, Photos
fa10f291-4b85-5f92-8300-a479206e4199 | note | DNZ Engineer - H
05cb2c3c-33e6-5649-b62b-28bab62750b5 | note | Designer Rep - W
6d891d2d-6942-43a4-9513-00108b50abb0 | signoff | AUTHORITY HOLDPOINT
aa1675d2-ed49-46ad-bb30-cdfdea185c5b | section | 4 - FINAL RECORDS
8b785a05-1d7f-43e9-abcf-b3b8269c5138 | checkpoint | 4.1 - As-Built
d3744949-6169-59fb-a199-3bdff1c510da | note | Standard, Drawing or Specification Reference - N/A
d209e5bf-a221-5a17-8614-17b3ae380c81 | note | Construction Activity Description, Test Type and Acceptance Criteria - Installed as per design drawings. All compliance recorded CAD files
d83b1bad-034a-5969-8242-c888da234145 | note | Test Frequency - Once
ec3ca733-a505-55b9-a991-7e3c18ec7407 | note | QA Record - As-Built
99685870-3973-596e-ab77-308f3a5e6d10 | note | DNZ Engineer - H
96d1b520-52ef-5015-b33e-b4e857c915bf | note | Designer Rep - R
f19c362e-c467-4c19-9086-4d157eef25a9 | signoff | AUTHORITY HOLDPOINT
e1c2cb2a-f9e0-474c-9280-25e0a9b8c191 | checkpoint | 4.2 - Redline Mark-Up
18e1d76b-44f8-57f9-8209-bfa46f6298f6 | note | Standard, Drawing or Specification Reference - IFC Drawings
c1fa479c-9c16-58fa-b2a9-be28b264b98d | note | Construction Activity Description, Test Type and Acceptance Criteria - IFC Drawings mark-Up on ACC sheets dated and signed.
6a22557e-9be8-5e75-819b-a6fa400b899b | note | Test Frequency - Once
6cdf9390-6fa7-5b12-839b-6ae7cc62e0c5 | note | QA Record - IFC Drawings Mark-Up on ACC
066d6fee-94f3-5111-85a2-8242eebadb75 | note | DNZ Engineer - H
381acdff-955d-59ec-82c8-70b71aae8882 | note | Designer Rep - R
fec8c6c7-ab92-4989-915b-515f0bc5ab45 | signoff | AUTHORITY HOLDPOINT
c5c32853-2a42-4ed5-9c11-20f4b438ae63 | checkpoint | 4.3 - Non-conformances
f09f6ff6-262b-532b-a291-879223e495fe | note | Standard, Drawing or Specification Reference - DN1212-DOW-PLA-PM-0005 QMP
09645545-5634-514c-88f7-59bd380dfe56 | note | Construction Activity Description, Test Type and Acceptance Criteria - Non-conformances reports to be raised when specification not met. All non-conformances within the area under review need to be listed on the NCR report.
66d2709a-9a36-5b3a-b0a6-d7b23e1f367b | textbox | NCR Reference
b746cc88-1d44-5b80-bd5a-f5c9c360ff9f | note | Test Frequency - Each NCR
4e081e1d-7c21-555f-be3f-990383eb8129 | note | QA Record - NCR forms on InEight
3e881ba8-2c2b-5e87-946f-7c0a7afc1da7 | note | DNZ Engineer - H
72af8567-87e1-4242-bd18-4638bdad93f0 | signoff | AUTHORITY HOLDPOINT
426f0540-b1cd-46f2-a54e-59e99f8adac9 | section | ITP APPROVAL PROCESS
0978716c-9472-426f-bbb2-c64d5cec475c | checkpoint-no-value | ITP APPROVAL PROCESS
f86102aa-09ff-5cb5-bc2c-f613baad2d24 | note | Prepared By: Project Engineer - Grant Wallace
530f886e-d723-5b77-8ad4-e67dd59872ef | note | Reviewed By: Project Manager - Dan Trotman
a531a345-2538-5a99-9c1a-1f356d360888 | note | Reviewed by: Quality Manager - Cordelia Girdler-Brown
160b9dd5-b92c-5596-be8d-d7d7fe044e8b | note | Reviewed By: Design Engineer - Daniel Cvitanich
964c2386-f234-5fe9-a4fc-638724d12b52 | note | Reviewed By: AT Project Manager - Nel Werner
008a98d3-a8c1-5caa-add0-e83599b27e3f | note | Reviewed By: AT Engineer to Contract - Mike Robertson
a347e0b9-baa5-55be-b9f9-bdaecd20a8ab | date | Date:
9e01db1d-ac9c-41d7-b0de-07e0de5bcc93 | section | FINAL ITP CLOSE-OUT
916b0bbc-3dad-4089-aba7-e8ca9bf1a635 | checkpoint | FINAL ITP CLOSE-OUT
ecb3cfa3-ecaa-5929-a366-1a135743229e | textbox | Downer Project/Site Engineer:
0f3b1ba2-b31b-5ef9-b6aa-646170d2cbcc | textbox | QA Mgr./Engineer:
d0e21c55-67c7-5574-bf63-b50ac614178c | textbox | Designers Rep(Assistant):
d33b1b8f-fce3-5842-8f47-6f94663f715b | date | Date:
ce238338-b00f-4dda-a99d-c63431f666f2 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
367cbdb7-5275-503e-9c99-d6768c7e0d32 | textbox | Contractor's Rep Name:
576a2824-9ff3-58f5-acc5-05d3fe764a1d | textbox | Engineer's Rep. Name:
799d2463-15ad-513e-8a1c-1b41dddeee30 | date | Date:
608a407e-3de8-4210-9844-b400a34724c1 | signoff | Add Signature
510b18a6-65b5-488d-a9fb-ff9bcbbabb4a | checklist | DN1212-ITP-008 Pier 1 & Pier 2 Headstock construction (Replacement) Rev2 | itp | DN1212-ITP-008 Pier 1 & Pier 2 Headstock construction (Replacement)
ccb678d9-7a49-45d2-bfce-14b7ef233cef | section | 1 - PRELIMINARY AND GENERAL
42a5594f-9736-44e3-a1e1-588fce582ed4 | checkpoint | 1.1 - Method Statement Development & Safety Analysis
76d6e544-3c81-5649-bb6c-2c241216e567 | note | Standard, Drawing or Specification Reference - The Downer Standards (TDS)
5971bd7c-48a8-5846-a41f-97682ed2e2e5 | note | Construction Activity Description, Test Type and Acceptance Criteria - Prior to Construction: Document Review
f832bf58-8f05-5ac2-ad73-29d1acda8506 | note | ○ Method Statement & JSEA
79f4c7bc-03d4-5744-b30b-40dde8a97a9c | note | ○ Completed & signed by relevant authority
b3a9253f-10a8-5a09-9c8c-b60266d690d7 | note | Test Frequency - Once
56924c5a-5082-5bdd-81f4-9b4ac57d9edd | note | QA Record - Work pack (MS,JSEA,ITP)
cfbe7521-863f-58c0-9d9f-d8a3e5609ec2 | note | DNZ Engineer - H
367d9653-196b-5bfa-91d5-7808ca641b88 | note | Engineer's Rep - R
870f3043-9c7d-5ae7-9ce9-ffe56758ffce | note | Designer Rep - R
7dd89642-65fb-44f0-a094-20cbbd8ccc2a | signoff | AUTHORITY HOLDPOINT
d9b5906a-0a75-45bb-a301-bc121daa0aac | checkpoint | 1.2 - IFC Drawings and Specification
4ba8a7ee-ff27-568c-a949-421bd7a4f690 | note | Standard, Drawing or Specification Reference - ACC
5659762e-7445-506e-9238-d88fb25c561b | note | Construction Activity Description, Test Type and Acceptance Criteria - A minimum of two weeks prior to construction: document review. DWG’s are for construction or as per instruction
a8f506e1-8340-5c2d-b800-343e67d03208 | note | ○ Works done in accordance with KiwiRail specification
2ab74e40-17ad-5bc5-bf0d-eca748145eb1 | note | Test Frequency - Once
d1229049-e3f6-54e5-a4da-bb6344f099dc | note | QA Record - N/A
892faf5a-9675-55bb-aef2-76bbeb64279f | note | DNZ Engineer - R
11b86d94-91ae-4790-81f1-dee712309841 | checkpoint | 1.3 - Model
32952953-b863-567b-88fc-942f61168e80 | note | Standard, Drawing or Specification Reference - ACC
3f95b6d9-ba78-562a-9ffa-3a6767cdfa52 | note | Construction Activity Description, Test Type and Acceptance Criteria - Model reviewed and confirmed with correct location; depth, height and orientation for column, headstock and stiarcase
008be01e-01ed-5bb0-9a4b-f9f2a8c290f5 | note | Test Frequency - Once
97c954f6-6536-5abe-a6a5-0b8557e7d560 | note | QA Record - N/A
0064ba56-b607-5e40-8a4e-62e777ea9ad5 | note | DNZ Engineer - R
f8d071cf-246d-44ed-847a-3ccd9073bd89 | checkpoint | 1.4 - Lifting Permit
1607a450-52aa-5648-8926-c7a7fdc69194 | note | Standard, Drawing or Specification Reference - DG-ZH-ST047 Cranes and Lifting Equipment Loads
edeb54e5-59dc-58ef-a135-45ed0a27a967 | note | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction. Permit in work package
2aa27bf5-0ea3-5f67-bebd-c090d6e87f5e | note | Test Frequency - Prior to Construction when required
f34f2e4d-2eb1-5869-bc0b-afd47d75ae68 | textbox | QA Record - FlowForm Permit Register/Permit Number
1fa1ddc2-f9ac-54d4-9b26-96686c7a1b76 | note | DNZ Engineer - H
6d79de67-8b0f-4468-972b-4a94081a076a | signoff | AUTHORITY HOLDPOINT
184a5a2d-3e52-469c-ba38-237d4522c899 | checkpoint | 1.5 - Working at Heights Permit
11ab2fdb-37e3-5513-9482-58939db17a8e | note | Standard, Drawing or Specification Reference - DG-ZH-ST042 Working at Height
5bcfe457-216d-5188-8311-f3bcc25940d8 | note | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction. Permit in work package
8c834b12-7992-57b9-ba5f-70e3f02b4721 | note | Test Frequency - Permit issued each week
1a09702f-ab1e-595a-a3b5-11ebdc17df39 | textbox | QA Record - FlowForm Permit Register/Permit Number
be8daee1-0e6a-5f9f-b779-f264cad43797 | note | DNZ Engineer - H
1eb79ddb-0bf1-4a59-9a0f-028f688c9780 | signoff | AUTHORITY HOLDPOINT
efafa4e0-88ba-4b3f-aaed-d5a1166f2c97 | checkpoint | 1.6 - Permit to Load - Scaffolding
48e26b1f-69d9-5aa0-8420-90b9ad965a18 | note | Standard, Drawing or Specification Reference - DG-DM-PR036 Temporary Works Procedure DG-DM-FM066
1dd5d152-e47a-531b-9056-eb75f3cfe5ee | note | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction. Permit in work package
93747b53-775e-5e62-9606-54dfc40282f6 | note | Test Frequency - Permit Issued prior to construction
b304412f-b667-5bdd-8929-7088b8ed46e5 | note | QA Record - Temp Works Certification ITP
ab1ceaa0-efe1-5417-b30f-f501312765dc | textbox | Permit to Load - PtL
6f04185f-c711-5a7e-b23d-d7dfbfc55a48 | note | DNZ Engineer - H
2e51cc42-310a-4cc4-a7ec-6491280be245 | signoff | AUTHORITY HOLDPOINT
e140a677-864f-4c08-885a-90ee319ed6f7 | section | 2 - MATERIAL APPROVALS
8beb882e-0c61-4995-aa0f-6b73fad8001e | checkpoint | 2.1 - Concrete Mix Design
48c06a60-8d52-59f7-9acd-1e39e522b004 | note | Standard, Drawing or Specification Reference - NZS 3104, App 1C - 746-24-847-AC - Tech Spec - Geo & Struc
b557ed58-2bfa-560d-a089-8e331f189166 | note | Construction Activity Description, Test Type and Acceptance Criteria - Concrete mix details shall be provided to the Engineer for review and approval.
883a61a9-d2dd-5240-9ddd-77fcd80dfbd7 | note | ○ 50MPa @ 28 Day Compressive Strength.
5998e113-b739-52c5-890f-189032e1cb93 | note | Test Frequency - Once
86203f2e-3a01-518b-b4ef-66a2fb4999f8 | textbox | QA Record - Mix Certification InEight Response
6660ed75-cd0d-5e3e-8359-fa8deb29b3a0 | note | DNZ Engineer - R
793d8f4f-e1d9-57a1-8d9c-ccb834eed37c | note | Designer Rep - H
6ec04feb-3ca8-4f01-82f4-d139deb9ea05 | signoff | AUTHORITY HOLDPOINT
e31b829f-106b-47d3-9e60-6701af46643b | checkpoint | 2.2 - Reinforcing Cages
9380a9dc-77a7-5c9d-a3c7-fa5cc944fa2b | note | Standard, Drawing or Specification Reference - Reinforcing Cage Drawings -
00b1803f-ced8-57f5-a89e-afecabe9c3fb | note | Construction Activity Description, Test Type and Acceptance Criteria - As per Column Reinforcing IFC detail drawings.
4593ef4e-65b7-5335-a521-18dd870ed11b | note | ○ Shop Drawings shall be provided to the Engineer for review and approval.
46d707db-ee29-5cb4-9d79-f049694a23ab | note | ○ Note any changes undertaken to reinforcing to be captured as per item 4.2
ff4d4237-4ced-56dc-a9cb-fcda79d10fed | note | Test Frequency - Every Reinforcment Cage
37298774-9758-5148-a145-38e3fe8c1901 | note | QA Record - Mill Test Certificates, Delivery Dockets
f51554a0-3531-5d23-b0ba-8ba49254e659 | textbox | In Eight Response
1cb052f2-1141-50c4-9619-f049dadc85b6 | note | DNZ Engineer - I
014cf0f4-4a83-5637-91a6-165e1f73ba27 | note | Designer Rep - H
d480eb98-d80c-4bc9-8870-dae457eaabbf | signoff | AUTHORITY HOLDPOINT
49d0a11e-177b-40ca-a17f-375138f53786 | checkpoint | 2.3 - Formwork
e1385e14-f793-53d5-b728-4a29e8be4d9e | note | Standard, Drawing or Specification Reference - Material Data Sheet, Temporary works drawings Piers 1 and 2.
0ae951a7-de63-583f-a063-86a71ba5ca3e | note | Construction Activity Description, Test Type and Acceptance Criteria - Formwork of choice from sub-contractor, Standard panels up to 900mm wide modules
dc16e043-8ae7-5968-98f5-a78f76ccf1f8 | note | ○ Rigid hollow-section steel frame
9652fbb4-aef4-56b8-a856-660ebf5fcde8 | note | ○ High-grade hot dip galvinising for durability & long life
f1fe8046-7096-5746-8f4e-e0d0ef8ae5f2 | note | ○ Gang forms and lifting applications available
25d53097-a7a4-5f7f-9bec-fad540919e6a | note | ○ Full range of safety features
95c824fe-3a7a-5e24-b7e8-77ccb05eb815 | note | ○ High Quality plywood
7213d704-a515-5d23-ac4d-0f29ab32ecdf | note | ○ 60kN/m2 permissible fresh concrete pressure
3cd25163-f8dc-5792-921f-1a2242099457 | note | ○ To be captured on temp works drawings.
dcaaae05-3fd9-5a90-92d5-6e2007335498 | note | ○ Inclusive of structural shore loading for super structure
f045688d-205f-5056-ad64-afdd64365240 | note | Test Frequency - Once
49455fe3-e472-5349-b5c8-a03c54b4cc87 | note | QA Record - MDS
7d528184-a640-5ada-abd3-7fde2c07cc6a | note | DNZ Engineer - R
144ae67a-35f8-50ca-8f0d-ccdc6d8775fb | note | Designer Rep - R
5a53b93e-ca7c-4c11-adce-747e4a739bf5 | checkpoint | 2.4 - Formwork Curing Agent
b097bc53-2fa0-5f2a-b1fc-d33c69622084 | note | Standard, Drawing or Specification Reference - Material Data Sheet
9892c662-63aa-5ba9-a9af-2893b9b0e2fd | note | Construction Activity Description, Test Type and Acceptance Criteria - Chemical curing agent.
c193dadb-0fea-5405-a94c-468aff1474ad | note | ○ Concrete to be retained in shutter for at least 3 days, must obtain 30 Mpa prior to striking. Curing agent to be applied to the top to of concrete pour to act as a sealant. Not to be applied to top of headtock as type B constrcution Joint is required.)
b4b1daaa-7378-5c03-90fd-27012679f207 | note | Test Frequency - Once
1dc456e4-640b-535d-a245-07633d1b0c7f | note | QA Record - MDS
ac1a4a62-b987-5d63-a8ab-c020c19f8a46 | note | DNZ Engineer - R
8df71cc6-bb61-50ca-897b-ef5b896afbca | note | Designer Rep - R
8e5ea66a-4a2f-4b6d-83b6-326c407056aa | checkpoint | 2.5 - Reid Bars Products
1bee428a-08e6-53ac-b8e0-a034a32633e6 | note | Standard, Drawing or Specification Reference - Material Data Sheet, 3235599-SP03-ST-3002, CAN 010
676aa789-ed96-5973-b683-cd8670b36609 | note | Construction Activity Description, Test Type and Acceptance Criteria - RB25FNS Reidbar Steel Flange nut & RB25 Couplers as per noted 8 & 9 on drawing 3235599-SP03-ST-3002. Proposed epoxy will be per manufacturers recommendations to use C8 extreme epoxy. Superstructural couplers will be covered under PFS installation methodology and ITP. This is only for column / headstock construction.
6610bf51-2025-57c9-bd06-1812383f6702 | note | Test Frequency - Once
bb12796a-926b-5e53-b9c9-637a9d2aed0e | textbox | QA Record - MDS, Delivery Dockets, mill certs
65272718-33fb-5b99-a284-72ecaa52862b | note | DNZ Engineer - R
272d4b49-528f-5681-89b2-090ac743d680 | note | Designer Rep - R
338eb036-e001-4c06-80d3-d1e79c64fcd3 | section | 3 - CONSTRUCTION ACTIVITIES
fd22ad4a-cb9f-4733-9c65-559faeb2b67a | checkpoint | 3.1 - Setout
5bf482b7-df53-5dfd-944b-fdc9ce970068 | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3100
b881a7ad-f3a7-59cc-b707-23e9b996eb84 | note | ○ 3235599-SP03-ST-3150
73b07a75-db5e-5c1f-8837-b4962a9c6353 | note | ○ 3235599-SP03-ST-3202
b39f9c3b-b036-57c3-ae3a-9ea2511f7991 | note | Construction Activity Description, Test Type and Acceptance Criteria - Before commencing formwork installation, survey set out column position based on drawings with RL supplied. Set out to include; Column centre, height and offset. Tollerances for insitu concrete pour taken from NZS 3109 table 5.2
0dbfb6ee-29cd-50b2-9a89-02dddeaabe4e | note | Test Frequency - Each Headstock
8e40a94b-e279-5044-aa8f-10ef571d1303 | note | QA Record - As-Built
b4c77f2b-bbd4-5454-b109-3d0eec3df038 | note | DNZ Engineer - H
11293add-9baa-59d5-8710-1119ffd81ecd | note | Designer Rep - R
9dd1b30c-57a8-4a40-91fa-612a9362877d | signoff | AUTHORITY HOLDPOINT
57cd1115-4a35-4e8e-b0fd-9745d65b16fd | checkpoint | 3.2 - Formwork Installation
227d9706-fd8f-5aff-9395-7d7ae7506268 | note | Standard, Drawing or Specification Reference - Material Data Sheet, Temporary works drawings Piers 1 and 2.
8c9ea74e-cab5-5c39-8dbd-d151bfe913f1 | note | Construction Activity Description, Test Type and Acceptance Criteria - As per Temporary works drawings for Piers 1 & 2. Inclusive of shoreloading requirements for the support of the bridge superstructure around Piers 1 and Piers 2.
d4e46c76-6b46-5f6e-9e22-8cd5698d8e0c | note | Test Frequency - Each Headstock
591b29f1-851c-520c-a57d-a33fd7e67858 | note | QA Record - Photos plus signed off Temporary works inspection of shuttering and formwork.
ca35797f-ded3-5369-ba67-7924734fd5a5 | note | DNZ Engineer - H
8a9f830a-ca2b-5259-9b38-521397d76a07 | note | Designer Rep - R
0e22d27f-9cc7-497e-a7b8-02c3fcad8f15 | signoff | AUTHORITY HOLDPOINT
67d88bba-c880-4f3a-bb6d-e19cfc15ff09 | checkpoint | 3.3 - Steel Cage Installation
8d316256-4187-576b-ab83-d866a9f4abad | note | Standard, Drawing or Specification Reference - As per detail Sheets for Pier 1 and Pier 2, 3235599-SP03-ST-3210
20b8e634-63a1-5da5-95eb-6f2bbe69ae4b | note | Construction Activity Description, Test Type and Acceptance Criteria - Cage installation will checked prior to placement to ensure that cage inspection requirements identified by BECA on 09/12/24 have been addressed and closed out prior to placement. Checks to be undertaken to confirm that lap lenths have been achieved during placement and survey to be undertaken to confirm posistion.
011de0b8-c29a-5f3b-b826-15c7293a7c13 | note | Test Frequency - Each Headstock
acdeb04c-f7be-5e37-899f-32432b28d02d | note | QA Record - Photos
29a76f97-578a-569b-8d40-c2a0332f6080 | note | DNZ Engineer - H
008b2426-51ee-5128-9293-66b029e0b008 | note | Designer Rep - R
c269cec5-df73-4c94-b6b9-e74b0d6453b2 | signoff | AUTHORITY HOLDPOINT
6cfdeb8c-f4ef-43d1-a129-4cc8713c3464 | checkpoint | 3.4 - Reidbar Product Installation
c6bb3ae8-8471-5ece-932c-41e989173edc | note | Standard, Drawing or Specification Reference - CAN 010
7cd8d4b5-bfec-568a-b8b1-a6efe218fcde | note | Construction Activity Description, Test Type and Acceptance Criteria - As per CAN 010 regarding the installation of pier imnterface couplers as per option 1
fb0f9b30-f56e-5aab-aff1-802d43b71274 | note | ○ Product to be installed as per manufacturers instructions with C8 extreme epoxy placed internally within coupler
e36420dc-3c24-5c72-8602-814c0b94ef5f | note | Test Frequency - Each Headstock
2e31e54c-ea11-5066-89b6-c6f0720fab9e | note | QA Record - Photos of Epoxy and coupler installation
5a441acf-d2e3-5876-b422-63a9cc49520d | note | DNZ Engineer - H
a00828a7-558c-5655-a048-e10dc8705c7a | note | Designer Rep - R
cecbfa51-e53f-4d13-b5ed-bdf3077adde4 | signoff | AUTHORITY HOLDPOINT
4c49283e-895c-4280-b311-dad3b1de582d | checkpoint | 3.5 - Concrete Pre-Pour Inspection
b9b2939b-f0fc-5412-8d3a-f3a28c421f4c | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3200 - PROPOSED ACCESS RAMP- EXISTING PIER 1 DETAILS
d6131073-2043-5801-99e4-fa2f916aa58d | note | ○ 3235599-SP03-ST-3201 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS
1765aa14-317b-5705-a1cf-2941abcb2042 | note | ○ 3235599-SP03-ST-3202 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS
1af9eda7-e703-5cdb-b183-f48808e78e3b | note | ○ App 1C - 746-24-847-AC - Tech Spec - Geo & Struc
c8b0c2a8-b8a3-5761-9965-e8abe11d5259 | note | Construction Activity Description, Test Type and Acceptance Criteria - Reinforcing cage as per IFC and shop drawings.
87c6cb2f-8db3-5423-8e9c-6bbd1a118891 | note | ○ Correct number of bars and grade.
2ef2fa17-15a4-5275-a97e-7ae30379c269 | note | ○ Correct steel lapping.
94d857c8-c55f-5ab1-b26b-6e50d3aa229f | note | ○ Earthing and Earth terminal tested and inspected.
16e593d7-3dfe-54e9-90e1-272085333075 | note | ○ Formwork installed as per the Temporary works drawings.
1784599f-338e-5a17-8b12-58aacc629868 | note | ○ Minimum 40mm cover achieved.
7549a84d-e478-5dd5-a10e-9cd6b56db6cf | note | ○ Test specimens to be supplied by plant for every 75m³ for each shift of conncrete ordered.
a02681b6-35de-534c-8b34-12d6907fb8cd | note | Test Frequency - Each Headstock
9d29bfce-2cf6-5c77-89a5-0edc52fa424e | note | QA Record - Survey Check, Structural Engineer Inspection, MSQA SVR, Pre-Pour Checklist, Photos
da526953-9963-5420-b6cf-0886ca117e4c | note | DNZ Engineer - I
19479370-a1b4-5d6f-bc44-cc68d4709a9f | note | Designer Rep - H
d30212dd-ce99-4fdf-b010-ff0be72687be | signoff | AUTHORITY HOLDPOINT
659f7f8a-6ff3-4f96-8d67-f7efce0f964a | checkpoint | 3.6 - Concrete Pour
ceb55a8d-3bb6-5a9a-964a-b07dc7518abc | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3200 - PROPOSED ACCESS RAMP- EXISTING PIER 1 DETAILS
c1b14627-4b89-5fda-be7b-e67567232111 | note | ○ 3235599-SP03-ST-3201 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS
c646ad79-61b1-5725-8665-3de8de552c3b | note | ○ 3235599-SP03-ST-3202 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS
0c67d782-8e25-55ff-9c34-fc4c7c7bdb8e | note | ○ App 1C - 746-24-847-AC - Tech Spec - Geo & Struc
979aadc5-6a24-566a-b091-ba9682e71295 | note | Construction Activity Description, Test Type and Acceptance Criteria - Concrete: 50MPa - Self Compacting Concrete - WS5010FS
3183974d-f82c-5630-988b-60b73d5f6377 | note | ○ Cylinder test taken at supply Yard only.
bfc35073-ff26-56e6-9d8e-eefd4d137212 | note | ○ Spread Test to be completed on site prior to concrete pour.
6845802c-c9d0-5b0f-9d09-41ec0dde3e2a | note | ○ Target Spread Test - 680mm +/- 60mm
0192228f-4af8-5cc8-8a31-0a6dbf4904a1 | note | Test Frequency - Each Headstock
3d3185c6-1db6-5fec-a746-6ab672743f9d | note | QA Record - Delivery Dockets, Compressive Test Results, Photos
22cc1723-42af-5d14-ae82-bdf903988db8 | note | DNZ Engineer - H
d90e03b5-88e8-5d83-9022-eae648fd291e | note | Designer Rep - W
578f8bbe-20c5-47d7-b088-ba045e5dd1c5 | signoff | AUTHORITY HOLDPOINT
1571b78d-2200-474d-b356-81e0f1b76884 | checkpoint | 3.7 - Surface Finish/Construction Joint
7ace006b-31cc-5736-b353-83654a6d6200 | note | Standard, Drawing or Specification Reference - App 1C - 746-24-847-AC - Tech Spec - Geo & Struc 3235599-SP03-ST-3200, NZS 3114
e482b019-bd73-5e03-b561-24df2039de89 | note | Construction Activity Description, Test Type and Acceptance Criteria - F1 Surface Finish - Concealed Formed faces
662f30f1-624e-5e4b-9ae2-1174c18ca4ef | note | ○ F5 Surface Finish - Exposed and Visible Faces
d81aa5b9-4f03-53a6-a613-8cae6c9b3172 | note | ○ Type B Construction Joint to be installed on top of headstock.
a837d8cd-9c15-5482-8b66-157b07a509e5 | note | ○ Insitu Concrete Stich Pour on Pier 1 - surface to have U2 broomed finish for slip resitstance in both rain and dry as per NZBC D1 requirements.
773eb081-c768-53d7-894f-ce99eac287ee | note | Test Frequency - Each Headstock
7a025022-fb32-51b9-ac9e-cff4735cad8f | note | QA Record - Visual Inspection, Photos
faff0c20-4fa8-5aaf-a90e-97d5d4eba3b1 | note | DNZ Engineer - H
ac13b3ff-825f-5728-84a8-f325330e1a62 | note | Designer Rep - I
89ca5d31-7e3f-4e1d-bd89-59cbe527ce57 | signoff | AUTHORITY HOLDPOINT
b00aa3be-c018-48eb-8d9a-6ee708b3e92c | checkpoint | 3.8 - Concrete Curing
43135e36-3388-5eee-bc05-44039846e9cf | note | Standard, Drawing or Specification Reference - App 1C - 746-24-847-AC - Tech Spec - Geo & Struc 3235599-SP03-ST-3200
a9a7f642-539c-5ecd-a352-793fd1f6bc26 | note | Construction Activity Description, Test Type and Acceptance Criteria - Concrete to be cured for a minimum of 3 days as per drawing st-3200, curing methodology will be formwork curing. Cylinder to be taken at 3 days to verify strength of 30 Mpa has been achieved prior to stripping of formwork.
9f903576-9ae4-5e55-b70b-f525c68c3181 | note | Test Frequency - Each Headstock
00e4e16e-1028-5601-a07f-a2eb7d731ec1 | note | QA Record - Concrete strength results, concrete pour checksheet notifying date of formwork striking.
9b1c34a8-0d63-566a-b9f7-efe1f0f56dfd | note | DNZ Engineer - H
62c11326-3a4c-5c3f-946c-0338b74fdb3a | note | Designer Rep - R
14902b6f-a996-4d02-a955-6547207d2af1 | signoff | AUTHORITY HOLDPOINT
f2b7c46c-39e3-4ec6-94f3-755faf537782 | checkpoint | 3.9 - Post Pour Inspection
6f831f51-77c1-53f9-b7eb-8fb7beec6ba9 | note | Standard, Drawing or Specification Reference - App 1C - 746-24-847-AC - Tech Spec - Geo & Struc 3235599-SP03-ST-3003, NZS 3114
af65c607-321c-5655-8d09-40819913ccc8 | note | Construction Activity Description, Test Type and Acceptance Criteria - Joint inspection be undertaken with designer to inspect shutters of structure following removal of shutters and survey/ check dimeniosn of structure have acieved stipulated tollarences stated in drawing suite and NZS 3109
e381ccc2-303e-57fb-b338-56c44dbece7f | note | Test Frequency - Each Headstock
5dcbbef3-a3d0-56f1-aab2-f33d963a9851 | note | QA Record - Visual Inspection, Photos
e578a346-cb11-5962-a140-3219dbf33908 | note | DNZ Engineer - H
1ecd8f88-6f4f-50a6-8ccf-71cb357df707 | note | Designer Rep - W
b6031188-1148-48f3-829f-85c1910e399a | signoff | AUTHORITY HOLDPOINT
00ff8b27-c87a-4e57-a424-b211f7ffcc6d | section | 4 - FINAL RECORDS
cdeea08e-542c-4740-82de-a14f8a9ec379 | checkpoint | 4.1 - As-Built
78a9ac35-07b1-5fa3-8505-85a58978fdaf | note | Standard, Drawing or Specification Reference - N/A
d86abf3b-a203-5ce5-9cdf-96277d1534d7 | note | Construction Activity Description, Test Type and Acceptance Criteria - Installed as per design drawings. All compliance recorded CAD files
a3fb773e-6298-512d-b962-48474ef372d7 | note | Test Frequency - Once
cdee8087-f870-51ce-ac61-9615e5ff19bb | note | QA Record - As-Built
eb7ab5f6-5897-5067-8918-f898ffa10bcf | note | DNZ Engineer - H
11f3f426-0ea6-581a-af28-e12ae465549b | note | Designer Rep - R
f6d321fc-601b-4bcd-a36b-183c1eee71c5 | signoff | AUTHORITY HOLDPOINT
8f133224-cd86-41c3-ac8f-e3e995da43b3 | checkpoint | 4.2 - Redline Mark-Up
13d653b1-a017-5d51-81e9-9248dc88eb70 | note | Standard, Drawing or Specification Reference - IFC Drawings
36aa29c9-a42f-5116-9f7d-88b686005eaf | note | Construction Activity Description, Test Type and Acceptance Criteria - IFC Drawings mark-Up on ACC sheets dated and signed.
c769269e-972b-5454-ae08-a30e0a61a63e | note | Test Frequency - Once
d210d781-5372-51f7-abab-19f9c67c2f3b | note | QA Record - IFC Drawings Mark-Up on ACC
75a66758-440b-5317-91d8-20b01595e1a7 | note | DNZ Engineer - H
73c9aea5-476c-5301-9fcb-3053e1b9b2b8 | note | Designer Rep - R
4e81d575-6c34-437f-9a51-fd1878c470db | signoff | AUTHORITY HOLDPOINT
c1f9602f-f2fa-4261-b179-b219aa155cfe | checkpoint | 4.3 - Non-conformances
8feaf45d-efea-5c5f-81f4-106f97f37d4c | note | Standard, Drawing or Specification Reference - DN1212-DOW-PLA-PM-0005 QMP
283dee3f-9532-5733-b3ba-3519ee711e04 | note | Construction Activity Description, Test Type and Acceptance Criteria - Non-conformances reports to be raised when specification not met. All non-conformances within the area under review need to be listed on the NCR report.
8a75a1bc-b8b7-5fc9-b85b-19c5febb9c71 | textbox | NCR Reference
e3542f84-3ef7-52d2-8832-f8c696dfc664 | note | Test Frequency - Each NCR
9b1c6861-15b1-509e-b701-b6189dec197b | note | QA Record - NCR forms on InEight
1605a7a8-c0cf-5d80-8129-b9c4b309af92 | note | DNZ Engineer - H
48268376-6664-444e-b62f-4d768edf0b44 | signoff | AUTHORITY HOLDPOINT
2aabab80-5af0-48d4-a356-1178fc06217c | section | ITP APPROVAL PROCESS
c26548c3-9746-4f63-a984-1a78f80a909b | checkpoint-no-value | ITP APPROVAL PROCESS
81f38844-e87e-52d6-aea3-26df38cad6ef | note | Prepared By: Project Engineer - Grant Wallace
a10bc318-6c60-5564-9236-d0bcbaaf5a7d | note | Reviewed By: Project Manager - Dan Trotman
df289987-33c4-5352-8d74-f336968e8649 | note | Reviewed by: Quality Manager - Cordelia Girdler-Brown
814ed76f-f1d0-570e-8b2e-117ffbbf33f3 | note | Reviewed By: Design Engineer - Daniel Cvitanich
9578f4ad-63af-54b5-8340-2bbcaf3d0ec1 | note | Reviewed By: AT Project Manager - Werner Nel
9dc84140-2f8a-5328-9417-9b5a14dc11e2 | note | Reviewed By: AT Engineer to Contract - Mike Robertson
7403e2ee-76b3-5de0-96e1-d2f941b3f8e8 | date | Date:
ce69f30b-0051-4edc-aa68-70806d0f4804 | section | FINAL ITP CLOSE-OUT
dc98c7c8-0479-4065-9443-3011daa7a32c | checkpoint | FINAL ITP CLOSE-OUT
01042e09-055d-587b-bed1-1e851d42154d | textbox | Downer Project/Site Engineer:
3a124312-cc1d-5bdf-a0d2-ffbc316f05c3 | textbox | QA Mgr./Engineer:
8fb59b22-bbab-5804-adac-0a0e638db9fb | textbox | Designers Rep(Assistant):
b4969911-0e38-5bfa-875d-f6d4423b8014 | date | Date:
2078fae5-2a03-4b52-b732-83b9c5c2da3d | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
405e4288-6739-5288-89c6-23a6293caab4 | textbox | Contractor's Rep Name:
bc99ad64-847c-55ba-8387-d9da32549d8f | textbox | Engineer's Rep. Name:
97a69354-f759-5150-a0d3-04483ecb9520 | date | Date:
4c6f856b-b871-4fd5-a052-41a540ecef7b | signoff | Add Signature
f23d9088-eed0-4caf-bd72-f577fd34dd15 | checklist | DN1212-ITP-009 Bridge Abutment Rev3 | itp | DN1212-ITP-009 Bridge Abutment
b8ed6318-d90f-4d8c-8983-27ab37b19f18 | section | 1 - PRELIMINARY AND GENERAL
b29d424b-c220-4a40-9c05-09c0c692af73 | checkpoint | 1.1 - Method Statement Development & Safety Analysis
5c014077-340b-5a72-a59d-f8fb4fc0afe5 | note | Standard, Drawing or Specification Reference - The Downer Standards (TDS)
632a6973-cc60-5838-a867-9ea436abb089 | note | Construction Activity Description, Test Type and Acceptance Criteria - Prior to Construction: Document Review
f9329fcb-605c-5a60-8b40-09547be2b5ce | note | ○ Method Statement & JSEA
a0c200bf-9171-5793-bc35-d486c02e732b | note | ○ Completed & signed by relevant authority
c48570ae-bbcf-51b0-a5f8-5dd2eb78c18c | note | Test Frequency - Once
cace7d01-00d0-57e3-b9ea-e549017a79d0 | note | QA Record - Work pack (MS,JSEA,ITP)
7d1b0e99-60c6-5d50-a17a-62dbab83d20c | note | DNZ Engineer - H
f1b1033e-4130-5b81-b114-c3f41db8004a | note | Engineer's Rep - R
a33e3cae-a916-55d9-b4c4-a2fc43d46e25 | note | Designer Rep - R
e6993b12-6a18-4b80-b997-303ac32f45b9 | signoff | AUTHORITY HOLDPOINT
34015e90-57e6-470f-ad66-ff150570b93c | checkpoint | 1.2 - IFC Drawings and Specification
c5afac63-28d3-59a4-88ef-791405784f8e | note | Standard, Drawing or Specification Reference - ACC
80e9e0e2-72a9-5548-902f-6c967081bf0a | note | Construction Activity Description, Test Type and Acceptance Criteria - A minimum of two weeks prior to construction: document review. DWG’s are for construction or as per instruction
3760d794-2a35-5165-889f-f94c338d48ff | note | ○ Works done in accordance with KiwiRail specification
4fa137b7-4e74-5e00-a8a8-fde0287a51d7 | note | Test Frequency - Once
93bea42b-bd76-599a-a3bb-53655fa59620 | note | QA Record - N/A
5826b7dd-a562-565e-8ea5-154c0ce95459 | note | DNZ Engineer - R
d8ae04eb-1751-4601-995c-cc307b4f1659 | checkpoint | 1.3 - Model
fd436e53-db97-5415-89b7-c77f77949e3b | note | Standard, Drawing or Specification Reference - ACC
8ffa793c-635a-56ff-9b74-dae2e261146f | note | Construction Activity Description, Test Type and Acceptance Criteria - Model reviewed and confirmed with correct location; depth, height and orientation for column, headstock and stiarcase
32fd7c15-7602-55f8-b407-3723ba46cc17 | note | Test Frequency - Once
8a9da8c4-368e-593a-9cee-c8ddb851de6c | note | QA Record - N/A
ab106735-ad69-5d72-97e0-a9dd93efa1f0 | note | DNZ Engineer - R
e997aaa1-92ce-40fb-9e01-91d45db68cea | checkpoint | 1.4 - Permit to Dig
a0e52a8b-c585-5bcd-b0fc-7d8c8895a70a | note | Standard, Drawing or Specification Reference - DG-ZH-ST004 Ground Disturbance
bde6c98f-b2f1-5996-9d90-2a7f6b72c289 | note | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction. Permit in work package
9ca616d5-0e67-5c94-b73c-2c3ebd2fadc3 | note | Test Frequency - Permit issued each week
bcba4bb3-6956-50ea-b4a5-7ff25dfaa9c1 | textbox | QA Record - FlowForm Permit Register/Permit Number
f4df7b1a-88e3-54e0-a73f-129aa8e56a1b | note | DNZ Engineer - H
afa488fc-89d0-48f7-b865-6b47011748c1 | signoff | AUTHORITY HOLDPOINT
364260e6-74d7-4c50-8526-9c9b4c673c94 | checkpoint | 1.5 - Lifting Permit
5dba0b61-37b1-5eac-88dd-5684f705315f | note | Standard, Drawing or Specification Reference - DG-ZH-ST047 Cranes and Lifting Equipment Loads
59240cba-2a61-5084-a5bb-42f7eb1bfe48 | note | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction. Permit in work package
8085067f-2315-56fd-a4d0-7fd4d7e09beb | note | Test Frequency - Prior to Construction when required
9015dc8b-4aee-5332-8a3b-7a2d36e69745 | textbox | QA Record - FlowForm Permit Register/Permit Number
97f9cbbf-c832-56e9-9f48-61540a81c43b | note | DNZ Engineer - H
bb498c16-83e6-4205-a835-e3abc04e72f0 | signoff | AUTHORITY HOLDPOINT
b8a31fd1-6ee4-41d5-b3d8-fe182f46c7a1 | section | 2 - MATERIAL APPROVALS
b31a08e4-d755-4886-815d-43d60664f0a1 | checkpoint | 2.1 - Concrete Mix Design
a67afd58-ad10-507a-b789-03ffb24baae6 | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3250: Note 2.1
f47c3e38-626b-571b-acfd-8ec2b1486c9d | note | Construction Activity Description, Test Type and Acceptance Criteria - Concrete mix details shall be provided to the Engineer for review and approval.
46911014-991e-5633-9008-d6e5e0cb93ab | note | ○ 40MPa @ 28 Day Compressive Strength.
d72150b4-8f61-52d9-a2cc-e9f614221d0e | note | Test Frequency - Once
c3d50f08-56da-5222-b7c4-54d5bdc60f0b | note | QA Record - Mix Certification, Plant Certification
fbfebf60-59b0-5bb4-9b1f-715225493c86 | textbox | InEight Approval
a2cbd65f-46fc-597a-b795-ca7118171861 | note | DNZ Engineer - R
1c8ab187-68b4-5411-a800-f5ba94c405e3 | note | Designer Rep - H
9c8e066d-6dd2-44e2-8cfe-56470e3594f1 | signoff | AUTHORITY HOLDPOINT
35929600-479f-4bef-8091-207af1abcd9c | checkpoint | 2.2 - Reinforcing Cage
4ea0debb-7631-54e4-b2ba-929c4aa9fb83 | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3250: Note: 2.3, 3235599-SP03-ST-3002, AS/NZS 4671
ce0ea040-f064-542e-bc9d-5d2161e78220 | note | Construction Activity Description, Test Type and Acceptance Criteria - As per Abutment Reinforcing IFC detail drawing.
89656a98-4db7-5011-894e-64d4ce60253c | note | ○ Shop Drawings shall be provided to the Engineer for review and approval.
701ed0da-63a3-50d1-8a87-01c93f4f6ad6 | note | ○ Grade 500E MA.
02be6def-bc06-5d91-8e30-63e8b343a66e | note | Test Frequency - Once
959cf260-4f12-549d-8035-d87e58780b7a | note | QA Record - Mill Test Certificates, Delivery Dockets
0e9e45a2-eb1c-55a2-a86f-266ac3184355 | textbox | Shop Drawing Approval
0ce651c8-338d-501a-acd3-5c39e3d2763f | note | DNZ Engineer - I
50436228-c1e9-5b0e-a758-1decac87f605 | note | Designer Rep - H
4c8b5c1f-6f4e-4d59-bf69-8c0f5faf1b54 | signoff | AUTHORITY HOLDPOINT
96c9e5fc-f250-4208-972d-f72b7e23276e | checkpoint | 2.3 - Formwork
e50ff706-1c56-5bf4-9bc6-c04ad9e8ae46 | note | Standard, Drawing or Specification Reference - MDS, Temporary works drawings Abutment A
88b6e2d7-be68-5be4-837b-b4589dfcb03d | note | Construction Activity Description, Test Type and Acceptance Criteria - Formwork of choice from sub-contractor, Standard panels up to 900mm wide modules
0f782b3a-9788-517f-8436-bd61114a3d8e | note | ○ Full range of safety features
343e3678-d17e-5a2f-a78f-57f15fa0c948 | note | ○ High Quality plywood to provide
9a9beb31-131c-5f26-a71c-951d063c1b0c | note | ○ F5 finish.
b346d05e-b01e-5f70-b646-0088dbb631c9 | note | Test Frequency - Once
db730794-48a6-5601-9c8e-3b1586341b1e | note | QA Record - MDS
e5b06a32-3111-5f02-ab61-84043deaabc6 | note | DNZ Engineer - I
fdc32c13-555e-5445-b69e-319653b1cd08 | note | Designer Rep - R
0bca309d-36d2-4810-af02-b8580a0ce898 | checkpoint | 2.4 - Formwork Curing Agent
7aac0a49-44b5-517d-bbdd-3f99596c3c3d | note | Standard, Drawing or Specification Reference - MDS
16b3be2e-7ac8-5eca-926e-74224c8a5cd9 | note | Construction Activity Description, Test Type and Acceptance Criteria - Chemical curing agent.
40478c9b-4acd-59d9-b01c-e78def40e093 | note | Test Frequency - Once
bf3b51cc-3734-5a97-82b6-254572d69bb4 | note | QA Record - MDS
e4a0d502-8976-5c67-b52e-2745e9bb3340 | note | DNZ Engineer - R
4e620978-371c-5016-a442-ec2a80328c35 | note | Designer Rep - R
74c82c4c-1f4d-470b-80c3-19b54077616a | checkpoint | 2.5 - RCC65
a8b0d210-484a-514e-9a9c-08e7cf2b9191 | note | Standard, Drawing or Specification Reference - MDS
ba3a6aab-797e-5cb3-8f32-ecd69d6dbe6a | note | Construction Activity Description, Test Type and Acceptance Criteria - Recycled crushed concrete 65.
6b209e36-c2ed-5673-be29-79193a0b6a31 | note | Test Frequency - Once
4518d1fc-7cc6-5aaf-a037-dd99dd2c98fa | textbox | QA Record - Test Reports InEight Approval
089456fc-0dd7-5333-9839-5905ac6d59d5 | note | DNZ Engineer - R
cb23632e-b9b2-504c-a717-633cec837055 | note | Designer Rep - R
fed6f6a1-c34a-4759-8b5f-71c1e27fadd9 | checkpoint | 2.6 - Threaded M20 Bolts
6f166fd1-f663-5fb5-a542-aee1888cfc7b | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3250: Note 1.5
4fbf77b0-d9db-5859-867f-c4ae5a1faba7 | note | Construction Activity Description, Test Type and Acceptance Criteria - Grade 316 (A4) SS M20 uplift restraint hold down bolts, to have UTS of 700MPa.
bd057411-86cb-5457-a711-f5c752dc84b6 | note | Test Frequency - Once
75527cca-2aa6-57ef-b819-83b75e7a5971 | note | QA Record - Mill Certificates, Delivery Dockets
1850e57c-75d9-543d-b53d-9aab0397a049 | note | DNZ Engineer - I
627937c5-17f6-50cc-a9a3-837086c9fd8d | note | Designer Rep - R
88ab2101-a73c-44f4-92bf-30aa29e987b4 | checkpoint | 2.7 - Geotextile (Bidim)
a5be9871-32f2-5950-abdc-7a866b22d09e | note | Standard, Drawing or Specification Reference - MDS
7b5e296a-a6ae-5809-a84e-bbeb6555743d | note | Construction Activity Description, Test Type and Acceptance Criteria - Geotextile A29 or similar approved material.
bd96cdbd-0108-5234-b6d4-0d4caba41171 | note | Test Frequency - Once
02673abf-c875-5966-b8fe-54c0785cf70e | note | QA Record - MDS
3777f2c6-ca8e-58bc-bf7e-e5e0425bb10b | note | DNZ Engineer - R
31db40e0-02ea-5f33-841d-b1b78958c11b | note | Designer Rep - R
0a1f96d7-a0b7-4091-b9b2-317d314931d4 | checkpoint | 2.8 - Sika Rugasol C
182f8b1b-f67d-5190-b6c0-a4bc450a4f60 | note | Standard, Drawing or Specification Reference - NZS 3104, 3235599-SP03-ST-3002, Section 2.1
1444572e-ec88-5360-991e-b4a828db8bdf | note | Construction Activity Description, Test Type and Acceptance Criteria - Sika Rugasol C to be used for forming construction joint.
5d27f73c-2a2b-57d0-a2f5-749379483739 | note | Test Frequency - Once
f0a36e9d-1daf-57b9-b2f6-6b460734b25f | note | QA Record - MDS
ab02cfbe-fb54-5093-998e-bf7688c853a5 | note | DNZ Engineer - R
9c1af98e-3630-5ae3-b0e8-aa5e4f7d28a2 | note | Designer Rep - R
4a84fc86-8a05-44c4-8c3f-a65525345489 | checkpoint | 2.9 - Bearing
86b68d0c-d0c3-5d04-94b2-459318663bdb | note | Standard, Drawing or Specification Reference - AS5100.4 NZTA Bridge Manual, 3235599-SP03-ST-3252: Section 2
fca65fc9-4ce7-51fb-bc15-62fa9720e652 | note | Construction Activity Description, Test Type and Acceptance Criteria - All details and dimensions to be confirmed upon final bearing selection, including coordination of hold down bolts with the bearing supplier. Bearing shall be replaceable, bearing shall have temporary transit plates that hold the bearing in the preset position ready for installation. Bearings shall be level in both directions after making allowance for girder camber if any.
547a8b86-44a3-53cf-bf2a-899f864cf68f | note | Test Frequency - Once
b48cf25c-8a28-5827-90a7-a70331acc628 | textbox | QA Record - Bearing Certification InEight Approval
486094ce-2cca-59a1-81e1-df377b1e8676 | note | DNZ Engineer - R
65fd6f13-9da8-5505-a6bb-d7196e2a23ab | note | Engineer's Rep - R
fea3145d-25a9-577f-b34f-ef2aa680a67e | note | Designer Rep - H
ca47feb7-2aa0-4206-890d-9100e36d81f1 | signoff | AUTHORITY HOLDPOINT
fa4ff1ed-12cd-4978-abb0-2311b878eaec | section | 3 - CONSTRUCTION ACTIVITIES
01c5c9ab-e5ae-4ed0-be3c-7f7940f0934d | checkpoint | 3.1 - Survey Setout
6b5c2880-1116-5923-aa70-7560be2434b2 | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3100
ab0a9809-a678-51cb-b236-c3c86b3f9407 | note | ○ 3235599-SP03-ST-3150
f004d7c8-bee5-5dda-a199-f46d5eda0045 | note | ○ 3235599-SP03-ST-3202
724df964-bbd7-53ac-82f8-16e579b6974b | note | Construction Activity Description, Test Type and Acceptance Criteria - Survey set out Abutment position based on model. Set out to include; Centre of abutment, height and offsets. Tollerances for insitu concrete pour taken from NZS 3109 table 5.2
6bb532b6-ffb2-5627-ad5b-52660be00945 | note | Test Frequency - Once
8bdd7d79-0ace-5936-9b5c-874ecebd0e3a | note | QA Record - As-Built
6c1606bb-ca1a-5c45-8c29-86c65db477cc | note | DNZ Engineer - W
0a98b86c-c474-4c7b-8f39-955633e795eb | checkpoint | 3.2 - Excavation
d88e1295-6e14-5051-a77d-ae956ae71e94 | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3250
dc8345f7-7f68-5f2d-a789-6502d6cc166d | note | Construction Activity Description, Test Type and Acceptance Criteria - Excavtion to be 1000mm below existing platform level.
2b66b1b3-259c-5200-8f5c-4b6532b26eb5 | note | ○ Insitu subgrade material at the base of undercut shall be inspected by the Engineer to confirm design assuptions prior to backfilling.
455b1190-7c12-50e7-b3ee-b70e53e11d02 | note | Test Frequency - Once
5b8a610d-f2b3-5d40-a68d-07df9bf04b9f | note | QA Record - Photos
c1e4dd93-5257-581e-a48b-04ebbeb5aec9 | note | DNZ Engineer - I
3e043e24-3c7a-4277-9d1e-f7f01791accd | checkpoint | 3.3 - Subgrade Testing
7fa2cafa-953b-5f86-aeb1-9fbc16550621 | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3250: Note 3.2
f9ea5320-e4eb-5504-9dce-ce2a1f1d350e | note | Construction Activity Description, Test Type and Acceptance Criteria - Minimum subgrade shear strength of 40kPa.
ae03f850-881d-558c-a301-db2044734201 | note | Test Frequency - Once
9d473e6a-b468-5dbb-b16c-cd2e80dadc14 | note | QA Record - Shear Vane Test Results, Photos
d4433b99-fd0c-574d-9b97-008f3a4c5523 | note | DNZ Engineer - H
d34d7737-84e4-5111-ae0f-8d2d9d18a57d | note | Designer Rep - I
ca38eaca-f46b-422c-a63c-35204dbd8bbb | signoff | AUTHORITY HOLDPOINT
91aed22b-bf44-41cd-9f5c-6428eb1dbdfb | checkpoint | 3.4 - Subgrade Undercut (If required)
c6588e1f-6521-59a4-987e-4648a461eb9f | note | Standard, Drawing or Specification Reference - 746-24-847-AC Tech Spec Section C0302.4.2, 3235599-SP03-ST-3250: Note 3.2
d16e10cf-d971-5f11-bcf4-169d2516c240 | note | Construction Activity Description, Test Type and Acceptance Criteria - Prior to subgrade undercutting, the Engineer shall confirm the extent of subgrade undercut and fill requirements.
324d77df-0ff5-54e6-8249-5606403d4d6e | note | ○ Undercut area to be wrampped in A29 and backfilled and compacted in layers of 200mm RCC65.
28e16673-d55a-5475-bd30-876e4447cbd7 | note | Test Frequency - Once
4a363364-effc-5975-9989-0bf15e9b4a07 | note | QA Record - As-Built, Photo
e89fc530-2d70-583d-ab78-bd291cbd18f0 | note | DNZ Engineer - I
89503ca2-9be6-5567-a63b-4bd6ab53c81d | note | Designer Rep - H
c97ce577-dac9-4600-8d6e-8fc2866de5f3 | signoff | AUTHORITY HOLDPOINT
50efdaf9-e36e-43ab-a607-9533314b5106 | checkpoint | 3.5 - Backfill & Compaction
0c1464d2-a628-5308-971a-fcc4a50f5ecc | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3250, 746-24-847-AC Tech Spec Section C0302.4.3,4&5
b12e5008-823c-5c64-aee9-68beda4ae34a | note | Construction Activity Description, Test Type and Acceptance Criteria - Subgrade to be covered with A29 or similar approved Geotextile.
7aaedc68-90f5-5dd1-a3a4-f7cda46822d9 | note | ○ Backfill to be in maximum of 200mm layers.
66762a09-d2c3-578b-ac29-e80877bd1d99 | note | ○ Each lift to be tested to 95% MDD.
1203905d-db90-56d4-895d-bcab9f7601e6 | note | Test Frequency - Once
32f618b7-790f-5403-84d5-e02f7e3d8343 | note | QA Record - NDM Test Results, Photos
2b5b7aed-4059-52c1-899c-9509ba2a5764 | note | DNZ Engineer - H
a5c9bd17-11a4-57e1-88c5-102caaa4fda4 | note | Designer Rep - I
07bd9e43-2552-42ab-8786-0397822ce911 | signoff | AUTHORITY HOLDPOINT
399ad18c-21db-4ddd-a30f-b0a4359b646f | checkpoint | 3.6 - Formwork Installation
016ac118-da2a-5fb6-bf9d-e8d6937f7f3c | note | Standard, Drawing or Specification Reference - MDS
543dabbe-7b5c-5ea5-bdd2-d0e1d16df0c1 | note | Construction Activity Description, Test Type and Acceptance Criteria - As per Temporary works drawings for Abutment A and shop drawings.
03fc7ebc-c3a8-5b13-92c2-ed34f87b33f7 | note | Test Frequency - Once
6bd28eac-8a94-5a5b-b998-7f927348ef34 | note | QA Record - Pre-Pour Checksheet, Photos
ade139c2-dfd9-5fbc-a4ca-9f0166f9576e | note | DNZ Engineer - H
6ceb9ff8-e385-4920-855f-35eb5d17d306 | signoff | AUTHORITY HOLDPOINT
895daf67-c501-476f-820c-6d1b09d22952 | checkpoint | 3.7 - Reinforcing Cage Installation
22be2b86-026e-5e1a-9bc4-c0317a61b6d8 | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3250
5197ac09-5c2a-57ea-b7e2-2e5b62285c04 | note | Construction Activity Description, Test Type and Acceptance Criteria - Installed as per IFC detail drawing.
f225f855-7b3c-5ab3-a506-c346d9ca3145 | note | Test Frequency - Once
f68f3fe8-73a6-5aec-ac46-a93bc88a1c1e | note | QA Record - Pre-Pour Checksheet, Photos
8f5d054c-744f-5509-8fdf-0c615b33eda6 | note | DNZ Engineer - H
53f58fc0-5694-594b-9f04-ea74ba8c12ff | note | Designer Rep - I
1dd98856-f72d-4e6e-bdff-af968978c9bb | signoff | AUTHORITY HOLDPOINT
eaab468b-c0dd-49bd-a652-e70463324650 | checkpoint | 3.8 - Girder Installation on Temporary shore loading
d6b773b2-25cf-5c50-b1cb-bd172b318fea | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3250
ac72d6bf-d013-555b-81b8-4112cc1e4ae6 | note | Construction Activity Description, Test Type and Acceptance Criteria - Shore loading sign off by the Temporary Works Engineer.
9da07360-e9f5-5816-955b-9869a4511dd8 | note | ○ Surveyor as-built for girder installation.
be568501-eb35-52fb-9c0a-dfd1de9b5dfe | note | Test Frequency - Per Girder
10791f0b-8f98-5900-a140-21596f1fdd1e | note | QA Record - As-Built, PT Load Certificate
84ea622e-61fa-5c22-95cb-fe43703c713f | note | DNZ Engineer - H
f5644ef4-1470-4a18-92fa-8a0846b4241a | signoff | AUTHORITY HOLDPOINT
e56426d3-c1c9-4f3e-93ff-c78c56531175 | checkpoint | 3.9 - M20 Threaded Rods Installation
4f426296-5a02-51ab-8495-d4810e0c93e1 | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3250: Note 1.5
5b5795a0-eff5-5049-a663-238169d00960 | note | Construction Activity Description, Test Type and Acceptance Criteria - M20 Grade 316 threaded rod with SS nut, lock nut and nylon washer to be installed in the reinforcing cage, and to have 250mm minimum embedment into abutment.
87c2cc7f-8848-526d-a3ee-6d846bd579a9 | note | Test Frequency - Once
558cb51c-91d3-5820-87dc-52806b4d7c43 | note | QA Record - Pre-Pour Checksheet, Photos
352d8394-29f1-5e19-8b5a-4bed39e07912 | note | DNZ Engineer - H
e692a93f-f750-5c10-a07b-a6572a34333d | note | Designer Rep - I
501f78fd-2ae4-4df1-be9d-9cd206571517 | signoff | AUTHORITY HOLDPOINT
ca485bbf-6700-4708-9eda-6dfbee41b323 | checkpoint | 3.10 - Concrete Pre-Pour Inspection
86fe4c3e-3851-54e6-b085-99922ab865ae | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3250
dba5e957-0e90-5e32-bf90-be5edab26690 | note | Construction Activity Description, Test Type and Acceptance Criteria - Reinforcing cage as per IFC and shop drawings.
0ad5cc5b-2242-50dd-acc5-9f5c6aa28a86 | note | ○ Correct number of bars and grade.
a5eec022-d63e-554f-82a6-c3d24aeffeb9 | note | ○ Correct steel lapping.
1748a7b3-2203-5f8b-9547-7bc409470e20 | note | ○ Minimum cover to be 40mm or 75mm if casted directly on exposed earth.
f40c521b-b242-526f-a7c8-9823020c2ef8 | note | Test Frequency - Once
ec0b6a2d-fd97-5796-a1b7-b2172c2647c5 | note | QA Record - Survey Check, Structural Engineer Inspection, MSQA SVR, Pre-Pour Checksheet, Photos
3174bc09-6d58-5ee9-b735-d81f4385704b | note | DNZ Engineer - I
4aca82ea-8b25-5d96-b476-01137645f6f7 | note | Designer Rep - H
6ee19806-14e6-4567-8005-d4e9869162da | signoff | AUTHORITY HOLDPOINT
149c8843-d68a-4c9a-88ee-a0c8465a7072 | checkpoint | 3.11 - Concrete Pour
8102be16-3b0e-5a7f-9778-ab68443cc820 | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3250: Note 2.1
b9d125e2-63b4-5b27-bb8f-21da62d07ae2 | note | Construction Activity Description, Test Type and Acceptance Criteria - Concrete: 40MPa
ef8ae1af-8f47-594d-a3b7-1ae0cbab49f4 | note | ○ 28 Days Concrete Compressive Strength.
f88e1867-5c70-550a-9edb-a3cdad1d206e | note | Test Frequency - Each Pour
40eda5aa-f6ce-5603-b85d-598a8b6ddafd | note | QA Record - Delivery Dockets, Compressive Test Results, Photos
b5435ac0-ddcb-5652-9ad8-3226e381f002 | note | DNZ Engineer - H
d38ee0dc-e1fc-5af6-b588-9bf9cc086789 | note | Designer Rep - W
54fe44f9-0430-4e7e-9cf4-722aded986e1 | signoff | AUTHORITY HOLDPOINT
bb6eb755-6fe6-471d-b71b-7e118f792fdf | checkpoint | 3.12 - Abutment Surface Finish
5a625e0c-705b-520a-aa39-d4de6f307a8c | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3250: Note 2.4
7c38534a-2826-545b-b258-68f3ac6a08fc | note | Construction Activity Description, Test Type and Acceptance Criteria - All surfaces subjected to foot traffic to have F5 finish (exposed aggregate finish).
2f6b2d91-8f1b-57a4-9b3c-93ba599a1435 | note | Test Frequency - Every Section
7d6e7970-25a3-5d82-b22d-d9923213a657 | note | QA Record - Photos
fd97ccc3-3b00-55c6-97c2-923068497e82 | note | DNZ Engineer - I
3c6e972c-487d-5c85-9b9c-2dd36a23eeae | note | Designer Rep - I
d5083924-6e69-4f84-a730-e6c0ef74fd96 | section | 4 - FINAL RECORDS
0af638ca-9f50-4335-8314-7e6296ed2db3 | checkpoint | 4.1 - As-Built
92bce253-40fa-5ac1-ad69-f369d51d5a26 | note | Standard, Drawing or Specification Reference - DN1212-DOW-PLA-PM-0005 QMP
e487ddb1-ce55-56da-9c6c-0df73127e7c1 | note | Construction Activity Description, Test Type and Acceptance Criteria - Installed as per design drawings. All compliance recorded CAD files
bddc41a4-194d-5e7f-b985-be21503f7016 | note | Test Frequency - Once
f9c88f00-d29e-5a5b-b093-1059d9a7982c | note | QA Record - As-Built
645fcd04-01f0-57ce-9215-b041b4442bba | note | DNZ Engineer - H
b2fd3ed1-597f-511c-a84e-4f2b7313f37a | note | Designer Rep - R
68b07ce8-26d1-4082-8f29-fb78d4957bde | signoff | AUTHORITY HOLDPOINT
b454da2f-472d-49af-b675-2c4df50214f1 | checkpoint | 4.2 - Redline Mark-Up
bbd9821c-6e5e-576e-985d-82e9e5cc934a | note | Standard, Drawing or Specification Reference - IFC Drawings
79327fc9-7452-53a2-b512-43a5a37b7606 | note | Construction Activity Description, Test Type and Acceptance Criteria - IFC Drawings mark-Up on ACC sheets dated and signed.
7d328fed-896a-5994-8b5a-bc710c718c51 | note | Test Frequency - Once
47654426-d851-5a16-b6f1-7e72011856fa | note | QA Record - IFC Drawings Mark-Up on ACC
6afc98ff-74f5-53f6-a718-9e105736e99d | note | DNZ Engineer - H
a6ca20dc-f351-5acc-94ee-39d315983804 | note | Designer Rep - R
4f29c6c7-11e7-4d64-84ff-f0f4cb414ead | signoff | AUTHORITY HOLDPOINT
76452594-6aeb-4d65-9c82-b36fc6439370 | checkpoint | 4.3 - Non-conformances
67f2aa03-2494-5962-b0be-773c859f6f70 | note | Standard, Drawing or Specification Reference - DN1212-DOW-PLA-PM-0005 QMP
6a1136a3-7d29-5a46-b405-72f6a6ab639f | note | Construction Activity Description, Test Type and Acceptance Criteria - Non-conformances reports to be raised when specification not met. All non-conformances within the area under review need to be listed on the NCR report.
d0716b66-34b7-5348-af29-3a87a90346e2 | textbox | NCR Reference
e718f3ce-a16d-5eaf-a200-48c6ae7dfc86 | note | Test Frequency - Each NCR
25a1dcd2-a722-58de-90ef-c603550c755b | note | QA Record - NCR forms on InEight
ce11650f-8426-513d-9172-14e30223e790 | note | DNZ Engineer - H
aa0289fe-1c24-4ed1-b26e-a7d4151d5c9b | signoff | AUTHORITY HOLDPOINT
7dc9cd03-bbb3-40b2-b6de-c73a0aeda4c9 | section | ITP APPROVAL PROCESS
f61646a8-e8ef-49dc-ae5f-9cd38e9043a6 | checkpoint-no-value | ITP APPROVAL PROCESS
d76ed120-93a4-5977-b900-486df7a6e8ca | note | Prepared By: Project Engineer - Moses Kaufanga
3019967b-e561-55bb-8cca-53048a370e2d | note | Reviewed By: Project Manager - Dan Trotman
1f9ae90d-8b1d-5232-b1ec-214c19646e7b | note | Reviewed by: Quality Mgr./Eng. - Nas Matar
162c8d81-eb72-526f-9694-08fa3a91b479 | note | Reviewed By: Design Engineer - Daniel Cvitanich
ee716adc-20c4-5700-8c70-d841d61ea5e7 | note | Reviewed By: AT Project Manager - Werner Nel
db64da17-c0e8-56d6-8af2-6f215b4bfbcd | note | Reviewed By: AT Engineer to Contract - Mike Robertson
3cb4ea39-2920-5042-8b47-4ffff5f04232 | date | Date:
f890af6e-5619-429f-9daa-6cdf9a00797b | section | FINAL ITP CLOSE-OUT
39a9880a-46c9-47cf-b464-5765ff9f36f1 | checkpoint | FINAL ITP CLOSE-OUT
fc826271-65c3-5b52-ae28-c27f2cce5f3d | textbox | Downer Project/Site Engineer:
9a640347-a35b-56d8-ac79-7459b30f5f1c | textbox | QA Mgr./Engineer:
af461aa9-56dd-5cc2-b587-519998568ea2 | textbox | Designers Rep(Assistant):
18b680c3-5311-50f0-9186-b7a44c5bcab6 | date | Date:
ad9e9078-05a1-4e46-8fee-a941fd3585c2 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
b4b3eb55-e4d4-5d0a-99e1-60a5e9f73cc0 | textbox | Contractor's Rep Name:
ead33a53-2527-57c0-a4a5-577aae2c65c3 | textbox | Engineer's Rep. Name:
6b86368e-cdfa-5e54-82fa-2dcbcc30c3bb | date | Date:
e6555854-ab3e-4d56-b85c-ed32cde63f60 | signoff | Add Signature
dcb21021-b367-4cca-abad-a717345b0d92 | checklist | DN1212-ITP-010 Bridge Access Ramp Rev2 | itp | DN1212-ITP-010 Bridge Access Ramp
946cbe3f-d938-4b79-8835-6e77c9c51d58 | section | 1 - PRELIMINARY AND GENERAL
7531564d-e6b2-4213-acb4-f9d69c43ea09 | checkpoint | 1.1 - Method Statement Development & Safety Analysis
6d9d813b-e98c-5045-bcad-ff618d474bee | note | Standard, Drawing or Specification Reference - The Downer Standards (TDS)
018f862a-6c1e-57ee-8372-d229cc6e0992 | note | Construction Activity Description, Test Type and Acceptance Criteria - Prior to Construction: Document Review
b2b5dac4-4e7a-53d0-895f-3bb1852d9015 | note | ○ Method Statement & JSEA
204c507b-8aee-5428-a9ef-7373b0dfff42 | note | ○ Completed & signed by relevant authority
0dad4cc5-ad9e-5078-8b0f-77fb712c2dae | note | Test Frequency - Once
fe9cea6c-fce3-588c-bfee-ccc42784da36 | note | QA Record - Work pack (MS,JSEA,ITP)
3a4d2cd1-442d-5cf1-88c1-72f9bca78d26 | note | DNZ Engineer - H
f66e057a-6931-5243-a4d3-a5e4e02bdf97 | note | Engineer's Rep - R
91ec816c-6d08-5996-ae55-3680bc955579 | note | Designer Rep - R
b21dcc69-4a98-4abc-b53a-8313df3afab4 | signoff | AUTHORITY HOLDPOINT
d140b224-c4bf-459c-9adf-7031ca9500d0 | checkpoint | 1.2 - IFC Drawings and Specification
48018d3c-b941-5cbf-814f-f6b3981c7a33 | note | Standard, Drawing or Specification Reference - ACC
7c186336-3cdb-5164-bc4a-bd9397300cf4 | note | Construction Activity Description, Test Type and Acceptance Criteria - A minimum of two weeks prior to construction: document review. DWG’s are for construction or as per instruction
7906d7b9-cf2d-5563-acf4-da129e0bf5e5 | note | ○ Works done in accordance with KiwiRail specification
952380cc-cc23-5beb-8a5c-05b433fb1981 | note | Test Frequency - Once
febd8b7b-2164-5480-a7e1-4bea863eb502 | note | QA Record - N/A
36713360-862d-5a7b-a493-47a797a42420 | note | DNZ Engineer - R
d9f600e1-4e05-49c9-85ca-a092350e226a | checkpoint | 1.3 - Model
d3aa42a3-3b68-5511-9804-78b459fcd02c | note | Standard, Drawing or Specification Reference - ACC
d5d52df0-26aa-528e-82ed-5de218d98928 | note | Construction Activity Description, Test Type and Acceptance Criteria - Model reviewed and confirmed with correct location; depth, height and orientation for column, headstock and staircase
7d320b3e-07f5-5b93-9ea8-76d2e7626fb9 | note | Test Frequency - Once
f477176c-bb3f-50ba-b525-44096e44c0ca | note | QA Record - N/A
60119f59-0a36-529e-8df5-473aa762b793 | note | DNZ Engineer - R
46cb5387-803e-41ea-b700-1777a164ff9d | checkpoint | 1.4 - Permit to Dig
696ee9ac-5993-5635-8ba3-3c53897d7ddf | note | Standard, Drawing or Specification Reference - DG-ZH-ST004 Ground Disturbance
cc10f3e7-3b1f-5353-895a-ec154211328f | note | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction. Permit in work package
1bfde6eb-1b32-59eb-b316-35d4af04e87e | note | Test Frequency - Permit issued each week
abce4b85-64b9-5a72-82e5-59f8cdfc550a | textbox | QA Record - FlowForm Permit Register/Permit Number
90bd506f-2abd-5d7c-9f75-7595b2323f3e | note | DNZ Engineer - H
5766adde-7154-4d25-87da-3d6a48bb0dd9 | signoff | AUTHORITY HOLDPOINT
3c88205f-1e04-43ac-bc79-0ce1cc6d7697 | checkpoint | 1.5 - Lifting Permit
f2528e4d-93f5-564d-80fb-4761e11b8eb5 | note | Standard, Drawing or Specification Reference - DG-ZH-ST047 Cranes and Lifting Equipment Loads
c8a97ef6-f9be-594f-97bf-87d79212e2c1 | note | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction. Permit in work package
143943fc-af9d-51c2-86f9-12fb007df0c4 | note | Test Frequency - Prior to Construction when required
63d48f58-f75d-5b0c-8dbb-2a83834e1da0 | textbox | QA Record - FlowForm Permit Register/Permit Number
5c42de2a-074c-5548-9061-dd2eadb8d642 | note | DNZ Engineer - H
3a57a1fd-e304-483b-8ea1-bfb53e22e365 | signoff | AUTHORITY HOLDPOINT
38c8ca17-c7e4-43cf-afb6-0cc084dbfd01 | section | 2 - MATERIAL APPROVALS
a96b7294-85e8-4b37-ad8d-1964eea989c3 | checkpoint | 2.1 - Concrete Mix Design
38253927-aa4d-513f-b225-958e8c836840 | note | Standard, Drawing or Specification Reference - NZS 3104, 3235599-SP03-ST-3253 Section 2.1
2d953f2e-674e-5b66-9bad-a6e1ec452e17 | note | Construction Activity Description, Test Type and Acceptance Criteria - Concrete mix details shall be provided to the Engineer for review and approval.
ea4d6208-1426-5a05-ae6f-90597eaa10d5 | note | ○ 50MPa @ 28 Day Compressive Strength.
1f93ef7d-2618-5e8d-bb5a-f4331bf61828 | note | Test Frequency - Once
2d6af16f-9d4e-5626-8573-df2adf914eca | note | QA Record - Mix Certification, Plant Certification
bda653d3-d955-572b-acf9-47ecf415d06e | textbox | InEight Approval
2873ac9a-f77b-5201-bee3-2a2e31db25c1 | note | DNZ Engineer - R
0222d32a-ccee-58f3-8a6d-5388b5bebb7e | note | Designer Rep - H
3c3b6725-4ea5-43e2-ac7e-a7cf6d203d5e | signoff | AUTHORITY HOLDPOINT
1fab479a-7716-4ead-9b75-434c99605234 | checkpoint | 2.2 - Reinforcing Steel
4591046d-6669-5df8-b082-cc3e94197d8e | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3253: Note 2.3, AS/NZS 4671
199bb439-7bea-5939-bd8a-385f0e66ac0d | note | Construction Activity Description, Test Type and Acceptance Criteria - As per Access Ramp Reinforcing IFC detail drawings.
7464ac94-f293-5c64-bc88-668a51a1ea46 | note | ○ Shop Drawings shall be provided to the Engineer for review and approval.
180b7748-4676-52c8-be1d-c10e4506554c | note | ○ Reinforcing steel to be grade 500E MA.
cadc0722-29b2-53a7-af48-c4979775a2f8 | note | Test Frequency - Once
645fccb2-dc36-5849-804c-5a481c740e2a | note | QA Record - Mill Test Certificates, Delivery Dockets
1f337bbe-87b7-5860-928d-60908ebaaf37 | textbox | Shop Drawing Approval
1aaf5ec9-4a67-574e-b0c8-1fb0baa7b597 | note | DNZ Engineer - I
4657043b-8c4f-577f-8572-58ed00d52626 | note | Designer Rep - H
1d559e5b-ad83-449e-9b25-19cd4ffe578e | signoff | AUTHORITY HOLDPOINT
d82115ff-3c84-483c-87ad-b2fd95ed99b2 | checkpoint | 2.3 - Formwork
0e6eeebd-0d2b-50c2-8393-1198bb52c1ba | note | Standard, Drawing or Specification Reference - MDS, Temporary works drawings
74666567-ddca-5277-86ef-bd3d28c71da1 | note | Construction Activity Description, Test Type and Acceptance Criteria - Formwork of choice from sub-contractor, Standard panels up to 900mm wide modules
ceffcfbd-9ed1-5f0e-a818-490b90c0cdb1 | note | ○ Full range of safety features
5073b939-4f9b-55ae-9432-223f712ca2f3 | note | ○ High Quality plywood to provide F5 finish.
c42f8cda-7379-5582-8582-26d6efaba855 | note | Test Frequency - Once
7dcb84a4-88f0-5f23-a6a7-1059da2272c1 | note | QA Record - MDS
8363fc4d-9cfe-556f-b2cc-f34bf372c8cb | note | DNZ Engineer - I
1093ae95-da28-5a82-a2b5-a10630affe49 | note | Designer Rep - R
c06d88c5-5e57-4c23-a3c6-6ba852f625f3 | checkpoint | 2.4 - Formwork Curing Agent
fcbb7bec-c9d7-5c52-be37-b3773346a173 | note | Standard, Drawing or Specification Reference - Material Data Sheet
613ad856-b2f3-52f6-b83e-94767998b3c2 | note | Construction Activity Description, Test Type and Acceptance Criteria - Chemical curing agent.
c12d3485-3bfc-5cbb-a981-87f7a5f6fc37 | note | Test Frequency - Once
cf86bc31-9399-5d40-beea-0d9e726cf43c | note | QA Record - MDS
78368017-1f95-5ff4-ab04-de71a3eadaa5 | note | DNZ Engineer - R
16c4c235-5abc-57a5-83ac-bd5e2326c6ce | note | Designer Rep - R
a205e9ef-dbfd-4d12-95f1-3979613266f3 | checkpoint | 2.5 - RCC65
ef654cdc-5036-585c-ab31-5279ad7e1be0 | note | Standard, Drawing or Specification Reference - Material Data Sheet
962db1cf-d64c-5fbb-821e-0d006d0291e1 | note | Construction Activity Description, Test Type and Acceptance Criteria - Recycled crushed concrete 65.
ff263eac-29a0-52d5-83c0-0aa2f3be8222 | note | Test Frequency - Once
1f093fb0-70f7-5548-a38b-62329a1d2b76 | note | QA Record - Test Reports
a64f4125-7137-5c3d-a52c-6cdb6443bbc4 | textbox | InEight Approval
a3b5f967-a333-5a2a-ad55-cf3671c0bb40 | note | DNZ Engineer - R
581f4fa7-3e9e-5c39-96b3-ba21959e923c | note | Designer Rep - R
c611d607-3c3c-46ed-99c8-8e01aa8b8984 | checkpoint | 2.6 - Geotextile (Bidim)
fdea9857-6d71-5412-bd71-25102ddd375a | note | Standard, Drawing or Specification Reference - MDS
a538cf54-eb10-5277-9de2-400a5ae88b80 | note | Construction Activity Description, Test Type and Acceptance Criteria - Geotextile A29 or similar approved material.
f8959ded-6946-5be2-b351-106e5d3aa262 | note | Test Frequency - Once
870a6dd1-8eab-5b13-9c00-cf336b59f6ee | note | QA Record - MDS
863037d2-e619-57fa-b74f-43b28b7e11a5 | note | DNZ Engineer - R
ab177de2-7d98-51ae-9c83-367dc824154d | note | Designer Rep - R
2b16c44f-31ac-41fc-a637-f9cbf183991d | section | 3 - CONSTRUCTION ACTIVITIES
99eb4e99-a699-441e-821e-6b1cf2051b87 | checkpoint | 3.1 - Survey Setout
2a80f630-339a-5e29-a594-cd74fa3f56b1 | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3100, 3235599-SP03-ST-3253
27da0e98-4e17-5df6-8c42-a638246d2c73 | note | Construction Activity Description, Test Type and Acceptance Criteria - Survey set out Ramp position based on model. Set out to include; Centre of Ramp, height and offsets. Tolerances for insitu concrete pour taken from NZS 3109 table 5.2
94ee7033-dc2a-5046-bc59-acdce12077c6 | note | Test Frequency - Once
2802ac57-8caa-5869-b551-c11f9282d915 | note | QA Record - As-Built
5506c26b-8253-56d2-a4cc-9037a5a45e18 | note | DNZ Engineer - W
c78d331c-b997-4c74-bfcb-f7277c3f87a3 | checkpoint | 3.2 - Excavation
4b8a8424-12e9-55e3-878d-d9a4a132cb8b | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3250: Note 3.5
5be1dafc-295d-5b92-a88f-b7d150ce9a98 | note | Construction Activity Description, Test Type and Acceptance Criteria - Excavation to be 500mm below existing platform level.
1e7e1d75-026f-59ec-82ea-57b5f22ed5b8 | note | ○ Insitu subgrade material at the base of undercut shall be inspected by the Engineer to confirm design assumptions prior to backfilling.
a3c21481-07c2-5f50-8755-f60b98b4784e | note | Test Frequency - Once
64b08114-e934-5ed3-bc41-5203f10221c0 | note | QA Record - Photos
56049e95-07dc-5e1f-974d-53421e814af9 | note | DNZ Engineer - I
66e95582-aa8d-47db-87f4-80417b76c124 | checkpoint | 3.3 - Subgrade Testing
760e42c1-529a-5ee1-bf3b-cb7562d394ff | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3253, 3235599-SP03-ST-3250
0106976c-e8e4-5613-ab65-bc978cec01a8 | note | Construction Activity Description, Test Type and Acceptance Criteria - Minimum subgrade shear strength of 40kPa.
b16eb3bf-f738-5c6d-b2de-e0bcbe731e57 | note | Test Frequency - Once
10372306-aa55-59eb-a5bd-7fd153d7f1ee | note | QA Record - Shear Vane Test Results, Photos
79ff1380-b075-5e2b-abc7-c602a76c0011 | note | DNZ Engineer - H
932ac744-e84d-5eab-bcba-c36bf94e1ab0 | note | Designer Rep - I
93699153-cef5-4ee3-adb2-bcd1be040a82 | signoff | AUTHORITY HOLDPOINT
eae23f46-6ac3-452d-b279-36bc230c2f4f | checkpoint | 3.4 - Subgrade Undercut (If required)
ce7468b7-f2a9-5584-8133-13e7e1298c95 | note | Standard, Drawing or Specification Reference - 746-24-847-AC Tech Spec Section C0302.4.2, 3235599-SP03-ST-3250: Note 3.2
57b74bac-672a-5e2e-878e-7a938cdfcb96 | note | Construction Activity Description, Test Type and Acceptance Criteria - Prior to subgrade undercutting, the Engineer shall confirm the extent of subgrade undercut and fill requirements.
ac5af4da-ea96-58c6-bd63-d96f97e8af39 | note | ○ Undercut area to be wrapped in A29, backfilled and compacted in layers of 200mm RCC65.
7c396e96-38cc-5f93-807c-35c5e1865b8d | note | Test Frequency - Once
2d84ffb2-d1be-5a3a-91bf-7d2cef689544 | note | QA Record - As-Built, Photo
61a1d071-1dcd-5fe1-8274-4b705d05525f | note | DNZ Engineer - I
b5aa64ba-ce67-54a6-9d66-35cfc1083f0e | note | Designer Rep - H
49b05f62-534e-474e-af08-2798c069ab02 | signoff | AUTHORITY HOLDPOINT
23a22f1b-0bab-4ea7-9d62-53d6c47082b9 | checkpoint | 3.5 - Backfill & Compaction
c1bd8870-edf3-5adf-afc1-8a93f0dbda67 | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3250, 746-24-847-AC
8ef0833d-91a1-5280-90ea-a45825047868 | note | Construction Activity Description, Test Type and Acceptance Criteria - Backfill lift to be backfilled at maximum 200mm lifts.
258eb572-49d0-5a21-b6d3-8f09bd97766f | note | ○ Each lift to be tested to a minimum of MDD of 95%
1b87c719-5778-5f26-9e05-eee1fbb8cfcd | note | Test Frequency - Once
94d72a63-17a9-51f2-b866-cb2c05ddb998 | note | QA Record - NDM Test Results, Photos, As-Built
bd7c2229-f804-50d9-bab5-66dc426e5b82 | note | DNZ Engineer - H
39a05fef-c824-5d63-b78c-56dfaf5b9c7b | note | Designer Rep - I
c7451e45-aa43-45a3-9e42-b89c818e6304 | signoff | AUTHORITY HOLDPOINT
c1a052da-4fae-4825-840f-36f669995766 | checkpoint | 3.6 - Formwork Installation
dbceb354-4844-5b91-806f-9a1586a39015 | note | Standard, Drawing or Specification Reference - MDS
efc9c990-2df5-5a07-83e4-76b01d04177c | note | Construction Activity Description, Test Type and Acceptance Criteria - As per Temporary works drawings for Access Ramp.
f0c72352-57d1-5f0f-a661-b560767cdae3 | note | Test Frequency - Once
84ca0cf6-7a7d-55bb-8927-e5cc81e8ef0c | note | QA Record - Prepour Checksheet, Photos
1b92fdbd-c1dc-5a78-a9c6-648d238e52a2 | note | DNZ Engineer - H
c67711c9-7acc-58cf-a131-50f002bad6c9 | note | Designer Rep - H
17640d55-ab9e-45c8-8605-5364270df29a | signoff | AUTHORITY HOLDPOINT
6d6d56da-5f8d-43dd-af61-3f55b31ee10a | checkpoint | 3.7 - Reinforcing Installation
68f792b4-8ee2-5555-af76-032f373cb89c | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3253
5d312d26-5568-5f10-8059-3f9d39385ba7 | note | Construction Activity Description, Test Type and Acceptance Criteria - Installed as per IFC detail drawing & shop drawing details
89f71a57-c43e-5374-a221-88ce47443a97 | note | Test Frequency - Once
dbd5458a-edaa-5bd0-9fb1-63bc51a43592 | note | QA Record - Pre-Pour Checksheet, Photos
771fec1a-a3a7-5305-b3b4-7a0657e35d47 | note | DNZ Engineer - H
f6e926d1-fa42-5e95-b871-a09d444c4958 | note | Designer Rep - I
46fce7a7-34b9-41ad-84b8-d79f3c270088 | signoff | AUTHORITY HOLDPOINT
0fb04c3c-de65-460c-983c-8f343e3c1ad5 | checkpoint | 3.8 - Concrete Pre-Pour Inspection
7ea15bd1-4535-5d6c-8ccf-f52619648fd7 | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3253: Note 2.2
c41c508c-41f3-56db-a317-c3015b906b51 | note | Construction Activity Description, Test Type and Acceptance Criteria - Reinforcing cage as per IFC and shop drawings.
5f509de1-766f-5268-bda4-2c6cf49786fb | note | ○ Correct number of bars and grade.
ff88e7f7-b0f9-5d38-b45d-9c4869bb6c54 | note | ○ Correct steel lapping.
0facbcf3-c8b3-52be-9b72-e8fff2944d83 | note | ○ Minimum cover to be 40mm or 75mm if casted directly on ground.
97203503-bbcb-56d9-b5e9-e1d2f732f780 | note | Test Frequency - Once
fb809896-3116-5817-aaac-08f4115195a0 | note | QA Record - Survey Check, Structural Engineer Inspection, MSQA SVR, Pre-Pour Checklist, Photos
a5208b23-1e1a-5ec0-9bdc-037dac16246e | note | DNZ Engineer - I
23798572-26fe-52eb-9ecf-b6416c99ee9e | note | Designer Rep - H
8c4c2882-d6f7-4f4a-97fd-65494e24467f | signoff | AUTHORITY HOLDPOINT
da7c2f95-894a-4710-9a9e-6bba1dd39c39 | checkpoint | 3.9 - Concrete Pour
a3a58754-762a-5b09-ac1d-0157bdc2ac79 | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3253: Note 2.1, NZS3104:2021
184b5f70-260d-5a1d-94be-c7d9e264b23b | note | Construction Activity Description, Test Type and Acceptance Criteria - Concrete: 50MPa as approved by designer.
ab994858-42ab-5700-9205-b56a0a8066ce | note | ○ Cylinder test taken at supply Yard only for 7 and 28 days.
69c3f552-d6e3-556e-ae2e-e954021bde6c | note | Test Frequency - Each Pour
d414bab6-ca2f-5616-bc96-232a75a0fe81 | note | QA Record - Delivery Dockets, Compressive Test Results, Photos
9c6ad9f1-afb3-550c-b9c7-3d50012eda17 | note | DNZ Engineer - H
ad8846a8-a629-555f-9aa6-3ce47b54c7e6 | note | Designer Rep - W
1aac07ad-37d4-4441-9cd6-d9bcce22b7a6 | signoff | AUTHORITY HOLDPOINT
cf28b599-bd84-416e-a110-c6aa439b821b | checkpoint | 3.10 - Slab joints
16fddb74-b428-511b-9f88-7b0e43ea5832 | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3253, Detail C
e696979a-52ca-5a68-8adb-79cf0a7fa34a | note | Construction Activity Description, Test Type and Acceptance Criteria - All joints between concrete ramp sections to have PEF rod and SikaFlex 11C grey or equivalent on outer face.
aaa922f1-8f97-525f-8da5-3548b7c87790 | note | Test Frequency - Each Ramp section.
0dfa061b-f233-5ddc-8b1a-78f25ec1b7c6 | note | QA Record - MDS & Photos
a93d820f-a2bc-5fd6-b1cd-b2730c6546a4 | note | DNZ Engineer - I
f9309823-b9ab-5113-9f49-3cbe173f6679 | note | Designer Rep - W
b81fd719-c7f6-475c-b9b0-f2d9ea1d41b7 | checkpoint | 3.11 - Ramp Surface Finish
838832ac-42e4-5ad7-b276-93c81892efb4 | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3253: Note 2.4, NZBC D1.
c0e727a2-9ca0-5fb2-833c-15f0671fb51f | note | Construction Activity Description, Test Type and Acceptance Criteria - All surfaces subjected to foot traffic to have F5 finish (Exposed Aggregate finish).
42f8ee29-594d-588e-be84-2ee66bdfdbb7 | note | Test Frequency - Once
45b81d95-fd02-554e-a424-a9ea40b7eada | note | QA Record - Prepour Checksheet, Photos
b861622d-43af-5f87-ac11-d9ebbf6b3d54 | note | DNZ Engineer - I
857e5768-439e-5af3-a3ec-376a5d676832 | note | Designer Rep - I
e4b16374-d47f-4df7-ad91-73384c8411ed | section | 4 - FINAL RECORDS
edcb650b-1138-46c6-a1a2-8562b4ef4527 | checkpoint | 4.1 - As-Built
a31c9cf8-af7a-53af-9129-c2f117986bd0 | note | Standard, Drawing or Specification Reference - N/A
ab1e8d9d-7fc4-5ef1-a43e-a88c7fd7d83c | note | Construction Activity Description, Test Type and Acceptance Criteria - Installed as per design drawings. All compliance recorded CAD files
2e0cb735-19e4-513a-907d-bba6b803e174 | note | Test Frequency - Once
ec3ab112-8735-530b-ba3e-cb77e34cfcc9 | note | QA Record - As-Built
8c8060ce-f69a-5168-a922-e9337b1f4402 | note | DNZ Engineer - H
1b870b2e-de29-5ca8-9875-bbae7a21e235 | note | Designer Rep - R
92013edd-b356-4052-83e4-5119cabb3110 | signoff | AUTHORITY HOLDPOINT
6f985a3c-046c-4b99-8814-31505bd9a404 | checkpoint | 4.2 - Redline Mark-Up
ad0dcd2f-d61a-5184-8ea9-3cbea9f27633 | note | Standard, Drawing or Specification Reference - DN1199-PLA-0006
eba13a4f-b086-5acb-a771-7017c6757af4 | note | Construction Activity Description, Test Type and Acceptance Criteria - IFC Drawings mark-Up on PDF
ed558610-d1dd-5ad5-b41d-4fd418697482 | note | Test Frequency - Once
e6c09db0-2e4f-56ad-bbfb-fa4bec5ac885 | note | QA Record - IFC Drawings Mark-Up on PDF
d4705fb0-2987-568f-adea-0b9ea7393ef0 | note | DNZ Engineer - H
1a3b3714-17ea-5d80-aea2-9deeb6e0c230 | note | Designer Rep - R
ab76c579-3533-45f0-b9a2-b541f1bdfa02 | signoff | AUTHORITY HOLDPOINT
5ef05276-a6a7-4120-bbf7-4eefaa45c909 | checkpoint | 4.3 - Non-conformances
106a5eac-9bfa-5e83-aac8-b407359c10d5 | note | Standard, Drawing or Specification Reference - DN1199-PLA-0006
56b20238-b123-545b-afe5-82c743966bef | note | Construction Activity Description, Test Type and Acceptance Criteria - Non-conformances reports to be raised when specification not met. All non-conformances within the area under review need to be listed on the NCR report.
940f1303-372f-5332-8171-5015995769c5 | textbox | NCR Reference
64b4d143-0da4-5c7f-bd80-894d2fe3a622 | note | Test Frequency - Each NCR
50d0c2ac-ed8a-5761-abd3-2469658f5f00 | note | QA Record - NCR forms on InEight, DN1190-PLA-0006
52caf414-cb28-5b43-b600-584741ca5a69 | note | DNZ Engineer - H
03a504e8-a6ff-510f-93d5-a57b3ce9dacb | note | Designer Rep - R
4c1413ec-0ad2-4833-893a-1a9d21d6e5e4 | signoff | AUTHORITY HOLDPOINT
36e7fd8c-fb34-4bb5-9ea9-9d8f98077c27 | section | ITP APPROVAL PROCESS
7f30528b-9a53-48b9-afb1-3a7615cc51b4 | checkpoint-no-value | ITP APPROVAL PROCESS
0a0d7724-c1d4-5312-9779-7c20674eabc4 | note | Prepared By: Site Engineer - Moses Kaufanga
d2e8c9a6-73d2-5af4-8fef-c3fc70794d05 | note | Reviewed By: Project Manager - Dan Trotman
3ea025e9-27f3-5c08-aecc-7d2c4314e874 | note | Reviewed by: Quality Mge./Eng. - Nas Matar
0b46699c-b090-5800-8bf0-4e30d42fa211 | note | Reviewed By: Design Engineer - Daniel Cvitanich
dca00910-4c70-53db-a3e8-b0324686313d | note | Reviewed By: AT Project Manager - Werner Nel
ecc4e063-19b4-5e16-9e24-78542834421a | note | Reviewed By: AT Engineer to Contract - Mike Robertson
05ea35ee-89c0-51b3-89be-d1ca6e7d0a36 | date | Date:
904db983-da87-43a1-9049-5c7c77f2b22c | section | FINAL ITP CLOSE-OUT
86195d03-80e1-488b-b010-ecba02c41ffc | checkpoint | FINAL ITP CLOSE-OUT
f4549692-3a9f-5313-935d-0fc9533b280f | textbox | Downer Project/Site Engineer:
4dd4a44a-ab2a-5b9b-a8b8-a2316f5cd62e | textbox | QA Mgr./Engineer:
f1a51b68-a1c5-5521-870e-5aeaa2c02bdf | textbox | Designers Rep(Assistant):
f744e25e-42ef-55c1-9ffa-4255c836ee81 | date | Date:
ff28852f-be5b-4b26-9968-94a4b84b68df | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
47e0e8de-7a48-56a8-a667-71034b4f8138 | textbox | Contractor's Rep Name:
2cb821f6-10a1-5e4b-858e-7a2c0504b3f8 | textbox | Engineer's Rep. Name:
9e9496b4-04a9-5f0c-b478-3e425a0e1537 | date | Date:
22aab9a2-5a49-4d84-b971-9a186b315d9d | signoff | Add Signature
e12a2484-dcaf-4774-9377-136acfbf8446 | checklist | DN1212-ITP-011 Lighting Rev2 | itp | DN1212-ITP-011 Lighting
681a0205-9d35-4e5e-867d-876e120158c2 | section | 1 - PRELIMINARY AND GENERAL
3c2cf524-6f58-433f-ae9c-03b30cf1c233 | checkpoint | 1.1 - Method Statement Development & Safety Analysis
cb7b3506-36cf-5010-a3d0-ba6b29107e42 | note | Standard, Drawing or Specification Reference - The Downer Standards (TDS)
d47bc267-8252-5872-8b99-280531d49b18 | note | Construction Activity Description, Test Type and Acceptance Criteria - Prior to Construction: Document Review
3987c666-71ab-5a83-80a8-96f2f12f4ed2 | note | ○ Method Statement & JSEA
39465ff0-a759-52d6-be27-a69a0503af76 | note | ○ Completed & signed by relevant authority
6566690b-3767-5ac7-acb4-4e34666a532b | note | Test Frequency - Once
acc8bc45-f602-5c03-8da0-52f80109babf | note | QA Record - Work pack (MS,JSEA,ITP)
8d922ec3-ca61-5987-ad49-035b59f6153b | note | DNZ Engineer - H
550a43ad-6283-519f-b5f0-02d814be6626 | note | Engineer's Rep - R
baf064e8-6e9a-5048-9c9d-b2164d6dea29 | note | Designer Rep - R
89e602ca-2016-4fdb-8980-723ec1b12943 | signoff | AUTHORITY HOLDPOINT
929a5f40-0797-42ef-8bfb-79735ec09d8c | checkpoint | 1.2 - IFC Drawings and Specification
dc5a0b9b-6bee-5adc-bf96-4e25c1fdbd83 | note | Standard, Drawing or Specification Reference - ACC
0064ae6e-9aa7-5c15-8f2e-9c1e4f1a0526 | note | Construction Activity Description, Test Type and Acceptance Criteria - A minimum of two weeks prior to construction: document review. DWG’s are for construction or as per instruction
f372709e-fafe-52f1-96f9-ea8e788e0f97 | note | ○ Works done in accordance with KiwiRail specification
02491721-c8cf-5539-86fb-f54168d8be48 | note | Test Frequency - Once
43311fbf-18a8-5c28-9f7c-abdb04a03585 | note | QA Record - N/A
55f0128f-a300-5160-9809-0f8beb8f2aed | note | DNZ Engineer - R
27766101-12d4-42ed-a7b2-60b42b302c81 | checkpoint | 1.3 - Model
b81310ad-d5fd-5faf-a152-2e2d05b6da2b | note | Standard, Drawing or Specification Reference - ACC
0463538a-b16c-5b95-8039-6f9ff7f9b2e9 | note | Construction Activity Description, Test Type and Acceptance Criteria - Model reviewed and confirmed with correct location; depth, height and orientation for each light pole.
c7009aae-7d62-5ca1-939a-826e2f20e4da | note | Test Frequency - Once
6aec83de-bbee-53b8-a755-7c931062ec58 | note | QA Record - N/A
183f9ea0-6431-5ef2-bb8a-9ace6db888e2 | note | DNZ Engineer - R
9aef3879-1fe0-4f10-9466-23787ce9a2e6 | section | 2 - MATERIAL APPROVALS
510d9136-1306-448d-9fc1-8c0aa180ca37 | checkpoint | 2.1 - GAP40
4ee956c6-e329-5b0c-8bec-986700bc1b83 | note | Standard, Drawing or Specification Reference - AS/NZS1260, AS/NZS 2053
f441df3e-4d31-55cb-9f0b-f2b8b25b34a5 | note | Construction Activity Description, Test Type and Acceptance Criteria - General all passing
dc519dbc-7d91-5709-a7df-7dce5c13da0b | note | Test Frequency - Once
17b8a164-68ea-522d-9004-8209542d4777 | note | QA Record - Mix Certification
cd090b0b-5369-56dd-b592-b223b1587a22 | textbox | InEight Approval
9ebde60d-686e-57c2-97b2-cfab46ca57ae | note | DNZ Engineer - R
d3b3f717-60d2-5323-8adb-f69871efc8e1 | note | Designer Rep - H
401e5234-ba98-4b0b-bb0f-2418dc833b66 | signoff | AUTHORITY HOLDPOINT
38c80c85-44c8-4b5d-9c88-954f54e3779c | checkpoint | 2.2 - Light Pole
c9ddac68-f889-5cad-917c-8978abb99360 | note | Standard, Drawing or Specification Reference - AS/NZS 4680, IFC Drawings
9457434f-3bb0-5c5a-a1e3-b4641a8f9505 | note | Construction Activity Description, Test Type and Acceptance Criteria - Light Pole type, height, outreach arm lengths as per IFC drawings
39cc2a75-1130-5f5c-bda8-e2ea861fa0ed | note | Test Frequency - Once
a3c7cd59-89c9-5903-a87a-bf60114f46df | note | QA Record - MDS
d5528602-4345-5a62-8b3b-303ccb0f6f99 | textbox | InEight Approval
81c59ceb-9163-50de-bdcc-9920cd31a2a9 | note | DNZ Engineer - I
d1062ae5-5bd8-591a-8f6a-02b8c7638327 | note | Designer Rep - R
30819174-47b4-4fed-afe2-929bc543e35f | checkpoint | 2.3 - Cable
a46916cc-777d-595b-a2c1-142985cce071 | note | Standard, Drawing or Specification Reference - 3235599-SP03-BE-1000: Note 10
ae960cf5-b38b-5a57-913b-7e86230a2eac | note | Construction Activity Description, Test Type and Acceptance Criteria - Cables must meet AS/NZS 3000 & AS/NZS5000 requirements.
72df498e-a053-5aa7-91d9-6dc669de1b0f | note | ○ Supplied by Electrical Subcontractor.
c6b8a6ab-1a28-5cbc-8eea-8ff87c31f989 | note | ○ Minimum Street Lighting supply cable size shall be 1C 10mm² neutral screen cable.
81fd4111-c926-57eb-8bc2-e5c4de96b9cc | note | Test Frequency - Once
e19b0119-931b-5d7c-913a-17af5470ccc7 | note | QA Record - MDS
2bce251c-3cfd-5383-96cd-1e2dcdbe1af4 | textbox | InEight Approval
9c29ddd6-de6b-58bd-b5e1-5e92cc7a0c49 | note | DNZ Engineer - I
4cb80250-5396-5c7e-ac95-cfac1e271ae1 | note | Designer Rep - R
9250249d-65b1-4e1e-a7e9-cff7c9fd0e8e | checkpoint | 2.4 - Luminaires
f3b4e711-1bac-5a50-a223-f5d4d9432375 | note | Standard, Drawing or Specification Reference - 3235599-SP03-BE-1000: Note 5,7
9dbee8db-0c34-5ba8-914c-764113faf539 | note | Construction Activity Description, Test Type and Acceptance Criteria - Luminaires as per IFC approved drawings and specifications.
022634ad-aaed-5caf-911d-4b52bbe1ef8b | note | ○ All Luminaires shall be tilted at an angle of 0 Degrees to Horizontal unless stated otherwise.
3da8da58-11c7-508e-9f58-b16272d8ea0e | note | ○ Each Luminar shall be provided with a 7 - PIN NEMA Socket and a LPC (Light Point Controller) to provide on-off light switching.
7559d494-51aa-5c27-9ecb-4e3813d760b3 | note | ○ 10 year Warranty from Supplier.
f374cf6c-60ad-5a08-8e5a-1a1bc5857caf | note | Test Frequency - Once
40f0cf8c-e98b-59b0-af98-975eaed1d1d6 | note | QA Record - MDS, Warranty Certificate
600f4f76-3303-54c9-8d9f-93502b5bec88 | textbox | InEight Approval
61c56c4a-5c08-5182-8f72-02926b3c0e66 | note | DNZ Engineer - I
d3b8485f-d80f-5ae6-9761-4c9d95cebffe | note | Designer Rep - R
bf60cae0-9419-4625-afe1-86df9aa8cc77 | checkpoint | 2.5 - Dali System
0569c7fc-7fe5-56fa-8f58-e35f6f3c67fb | note | Standard, Drawing or Specification Reference - 3235599-SP03-BE-1002
49c5bba9-2273-58fb-9683-97778109fe72 | note | Construction Activity Description, Test Type and Acceptance Criteria - Contractor to provide new Dali Control system in controls section of board, Dali to be controlled by Rotary Dimmer for commissioning and adjustment purposes
2a1beddb-dfda-5900-8bd3-4ff64cf6826a | note | Test Frequency - Once
95d7a8a3-5a2b-5327-b91b-408318462c7c | note | QA Record - MDS
c76b57ac-7b47-5752-8299-3b2be67441e5 | textbox | InEight Approval
ecf1f16e-ea3c-5662-b781-1a2bc58f6ecf | note | DNZ Engineer - R
7ac7cc70-0916-5c73-814a-e0e05f5f32e0 | note | Designer Rep - R
35701952-b105-4429-b335-2b9d929d0509 | section | 3 - CONSTRUCTION ACTIVITIES
91e13ddc-b878-48bb-a38e-ae9b3dcc21eb | checkpoint | 3.1 - Survey Setout
795fc4eb-f028-5d0e-87f2-be33c1f150ae | note | Standard, Drawing or Specification Reference - 3235599-SP03-BE-1000
c7ae978f-5bfb-57df-802d-19b7c45593d8 | note | ○ 3235599-SP03-BE-1001
7b4845cb-6d04-57fb-bf11-116977d7f958 | note | ○ 3235599-SP03-BE-1002
9ba9165d-ffe1-5e12-95bc-710a21861796 | note | ○ 3235599-SP03-BE-1011
0763bee4-b05b-5e9a-acee-ae1d4037d617 | note | ○ 3235599-SP03-BE-1012
62f63828-5605-5536-8a24-a42845400271 | note | ○ 3235599-SP03-BE-1013
6607382e-8bb3-55fb-87ec-30b9f5bb9d88 | note | Construction Activity Description, Test Type and Acceptance Criteria - Surveyor to Setout light pole locations as per the model.
090fb8da-fa65-5241-ad6c-af739cb1ab81 | note | ○ Where pole is within 2m of the dripline of the trees, assess whether the tree requires trimming to minimise shadowing, and notify the Engineer for further action if required.
ac5106c2-3a11-5183-811b-55ed01c49861 | note | ○ Permitted Location Tolerance:
8ec1fc64-4fc1-5d18-8d6d-8155c14b4002 | note | -0.5m Parallel to The Carriage Way
1cc50dff-6381-58d3-8281-477ee544ef37 | note | -0.2m Perpendicular to The Carriage Way
4fdc3607-2484-5331-8564-2f88c86af386 | note | -0.2m Vertically
074dc2f4-900a-5253-8dd8-52440e3a6458 | note | ○ If the final pole location exceeds the permitted tolerance further lighting design may be required.
70605e16-f279-5f04-bd2d-070fd6c1f5ac | note | Test Frequency - Every Light Pole
14478272-e831-5f61-b73b-431d81e03b83 | note | QA Record - As-Builts
8a68a397-d692-50c4-b734-404ae8cfca39 | note | DNZ Engineer - H
1c2916be-6bd3-5157-9bae-1872f9a0f514 | note | Designer Rep - R
f43a1f99-d8b0-47e8-8b53-7b9b78a191a9 | signoff | AUTHORITY HOLDPOINT
24173fd3-6dd0-47aa-88d2-b7dddb6b0d48 | checkpoint | 3.2 - Hydro-excavation
5a946ba2-83b9-5f72-a8d9-a51a9e1773b2 | note | Standard, Drawing or Specification Reference - 3235599-SP03-BE-1012
220d6aaa-4d30-5666-8487-740ace6eacff | note | Construction Activity Description, Test Type and Acceptance Criteria - Excavate down 1300mm (height) x 300mm wide (Diameter)
6b8873f9-8aeb-52bc-909d-69365a70d6a6 | note | Test Frequency - Every Light Pole
e9fef405-3707-563d-824f-0df71ddcb7cf | note | QA Record - As-Builts, Photos, Checksheet
bd75fa24-4be0-5f69-b169-c523c752d293 | note | DNZ Engineer - I
3954ee89-d8ed-4714-97e2-0b899bbb59fa | checkpoint | 3.3 - Pole Installation
31397900-2a43-5752-91bc-a805ad905b75 | note | Standard, Drawing or Specification Reference - 3235599-SP03-BE-1000: Note 13, 3235599-SP03-BE-1012
55ad1971-b5e7-53b7-94c1-7114e1f0e346 | note | Construction Activity Description, Test Type and Acceptance Criteria - Excavate down 1300mm (height) x 300mm wide (Diameter).
08be470c-7c12-55e5-9fa7-adb85fb1bacf | note | Test Frequency - Every Light Pole
03a52585-3f39-556b-8be5-32ce5f2f2e03 | note | QA Record - As-Builts, Photos, Checksheet
11035163-4afe-5d9f-8741-2db259c4e811 | note | DNZ Engineer - I
61669e5b-bfb7-4ba4-bb1e-857810f56198 | checkpoint | 3.4 - Cable Pulling
389e1752-73c3-5607-adcb-d984e9590532 | note | Standard, Drawing or Specification Reference - 3235599-SP03-BE-1012
c1394a35-8058-5137-896d-25aa587bec80 | note | Construction Activity Description, Test Type and Acceptance Criteria - Each light pole to be installed as per the requirements of the NZTA and AS/NZS 3000, wiring rules.
47d57223-2c58-549e-a874-756e2157b5e6 | note | Test Frequency - Every Light Pole
99eb5d96-55c0-5071-863e-2806bed24bb0 | note | QA Record - MDS
ff42577f-ec1d-5d53-8b8d-481af521eca4 | note | DNZ Engineer - I
443dba36-1f17-4375-9d55-516ed47a8309 | checkpoint | 3.5 - Luminaires Installation
102c36b5-ef4e-53c8-88b4-5b7745558e2d | note | Standard, Drawing or Specification Reference - 3235599-SP03-BE-1012
9fbae37b-4ce5-50e5-b008-e354b2f484f1 | note | Construction Activity Description, Test Type and Acceptance Criteria - As per IFC drawings and specification, approved luminaires installed.
9849285e-d04a-5cc2-918c-3e1ff1080e87 | note | Test Frequency - Every Installation
8077bdb5-c9f1-5835-8f40-661d0f2e0187 | note | QA Record - MDs Photos
8dd29cb3-37de-59d0-a5ec-f4683b7580a9 | note | DNZ Engineer - I
082059b4-d1b6-450a-90e1-fd141354925b | checkpoint | 3.6 - Testing & Commissioning
5c7f90fc-4287-5aa3-8364-8080bcc155a8 | note | Standard, Drawing or Specification Reference - AS/NZS 3000
8cf280ee-de10-524d-8e22-cfaf64f1ed8e | note | Construction Activity Description, Test Type and Acceptance Criteria - COC to be completed by the installer to confirm installation is safe and complies with the design and specifications.
dffde4fd-189f-57ef-9ece-3ddca063bcb8 | note | ○ ROI to be completed by an independent Electrical Inspector to confirm the above prior to livening.
cb6b2a16-7103-56ca-9eb9-88047ac66fc8 | note | ○ Demonstrate all specific commissioning functions/requirements detailed in electrical specifications are met.
9d06e5d0-544b-51e3-9847-b2fc8396b0ac | note | Test Frequency - Once
fb0cacc1-a4ee-54b4-92f4-91181fe8583d | note | QA Record - Certification of Compliance, COC/ESC by Installer, ROI By Independent Inspector
0aafa690-3ba5-59f3-b753-2a58d01ddf53 | note | DNZ Engineer - H
112fa2d5-152e-581d-bb6e-3a2a8dd93899 | note | Designer Rep - I
4753668a-b3ed-4ff9-8ed7-3690a5fc3641 | signoff | AUTHORITY HOLDPOINT
6c005a19-b01d-4938-8c85-bf823325ede1 | checkpoint | 3.7 - Earthing Test
27cfae12-7b7e-586a-8e42-6d826c59c015 | note | Standard, Drawing or Specification Reference - AS/NZS 3000, NZ Electrical Safety Regulations
b267b052-e0a8-50fe-a333-02ea924b73fd | note | Construction Activity Description, Test Type and Acceptance Criteria - Check of earthing of metal columns, outreach arms, and Luminaries.
74670dc9-262e-5a4e-bfff-587f9c0e9bc7 | note | Test Frequency - Every Light Pole
5f7bcade-281b-50d2-b974-e3fa043d7df9 | note | QA Record - COC/ESC
97bb9b1b-07e1-5961-8df9-e9bf875d75e6 | note | DNZ Engineer - H
2842586b-f8b0-542e-ab46-aa153174781c | note | Designer Rep - I
d16814de-1c69-456f-9ffd-4a30a329a78c | signoff | AUTHORITY HOLDPOINT
4dbb2fe7-7cb1-4957-9b3a-a02a5ed87e79 | section | 4 - FINAL RECORDS
0885c5f9-4976-4b9e-914f-bde5819697c4 | checkpoint | 4.1 - As-Built
9ecb0852-51cc-5018-8ac4-e649ecaf9b60 | note | Standard, Drawing or Specification Reference - N/A
7f72c9e2-931b-5c7a-bdd9-ddc4ad0c70dd | note | Construction Activity Description, Test Type and Acceptance Criteria - Installed as per design drawings. All compliance recorded CAD files
e8442f94-b873-5184-84d5-249800ebf09a | note | Test Frequency - Once
5145eb15-9b13-576c-8151-2b394836a540 | note | QA Record - As-Built
a40c5707-8ac9-5ba2-92fb-77caec82d0ce | note | DNZ Engineer - H
846b5b30-484e-5e22-be58-85fce899a7ec | note | Designer Rep - R
d5e1d030-965a-4f3a-ba90-be3b38520a3b | signoff | AUTHORITY HOLDPOINT
a0450b11-81fd-4176-acf0-9225b8d2beee | checkpoint | 4.2 - Redline Mark-Up
3f832b85-e6fb-541c-98ce-2b0acf38f813 | note | Standard, Drawing or Specification Reference - IFC Drawings
034ec5e7-c749-5980-9beb-c7f8c7d49839 | note | Construction Activity Description, Test Type and Acceptance Criteria - IFC Drawings mark-Up on ACC sheets dated and signed.
8dd22b6c-5174-5326-954c-46de5270d914 | note | Test Frequency - Once
e6ddcfa8-e816-5401-a500-b56baabe0f7c | note | QA Record - IFC Drawings Mark-Up on ACC
d11843bf-962c-5884-86d3-c5401ddb6b3d | note | DNZ Engineer - H
c1594925-b90c-53ca-a295-af9abf19c17d | note | Designer Rep - R
93b539a5-bbe7-4136-978d-7ae8e4683fe6 | signoff | AUTHORITY HOLDPOINT
b5e91d8d-be74-46e9-8f02-657d55016aed | checkpoint | 4.3 - Certificate of Compliance
705379aa-fa81-5bae-a865-dcca79f45b44 | note | Standard, Drawing or Specification Reference - Electrical Safety Regulations 2010
c7d51884-efa7-51d2-a267-618ae130cc69 | note | Construction Activity Description, Test Type and Acceptance Criteria - Compliance Certificates, COC, ESC & ROI
0e060941-edd6-5f00-a95b-78dd190da4fe | note | Test Frequency - Once
8a247530-2a82-57fb-85ae-ab85d09c84b2 | note | QA Record - Certification
09fcb432-54d1-56b4-a551-caf1fcbed463 | note | DNZ Engineer - H
a7cc83be-55da-5899-9336-0a425d61f603 | note | Designer Rep - R
0acbf4e3-4991-4963-8a9c-961ff5fbded8 | signoff | AUTHORITY HOLDPOINT
5a0253d7-19e7-47be-9824-0c02c346596f | checkpoint | 4.4 - Producer Statement
c56c5229-40c2-5fbb-991e-56e289e9b0ad | note | Standard, Drawing or Specification Reference - Schedule 6 3910
6cb34c74-1d0d-5b44-b344-a76103115635 | note | Construction Activity Description, Test Type and Acceptance Criteria - Signed PS3 confirming electrical works completed meets the requirements of the building code and consent plans.
06ab492e-8aeb-5923-8af2-bc51a69697a9 | note | Test Frequency - Once
8797aa71-2151-5f7d-ae18-28b5ac25a3d1 | note | QA Record - Signed PS3
cedaf65c-8638-52b8-9ac8-65a0edc1d423 | note | DNZ Engineer - H
d8d7400d-df80-5449-9800-844b7adc6ada | note | Designer Rep - R
59d1dbf2-d57f-4eb3-ac63-ea21cee7f1b6 | signoff | AUTHORITY HOLDPOINT
81159b72-2c9e-468d-bef3-f1bf451ec3bf | checkpoint | 4.5 - Non-conformances
44707944-de3b-5ec0-b813-68f57fe7327b | note | Standard, Drawing or Specification Reference - DN1212-DOW-PLA-PM-0005 QMP
1b6883f2-b268-551b-9986-d1dd21bfa392 | note | Construction Activity Description, Test Type and Acceptance Criteria - Non-conformances reports to be raised when specification not met. All non-conformances within the area under review need to be listed on the NCR report.
516c1b99-f994-5cbf-9ed2-ce11df077615 | textbox | NCR Reference
2c3fa9a7-595a-552d-8f15-b8c60f7c0ae3 | note | Test Frequency - Each NCR
4b13abae-fba3-5c74-8435-7dc7f9487ef3 | note | QA Record - NCR forms on InEight
e58e0d83-a899-5db6-94bc-21b66da274e0 | note | DNZ Engineer - H
bb73072b-1732-52df-8bb3-fa62099619c5 | note | Designer Rep - R
98d15f5b-6c2d-453c-ae30-d144c3c2c4a5 | signoff | AUTHORITY HOLDPOINT
1512eb77-6a3c-4a6c-bc91-8aa2a53cf890 | section | ITP APPROVAL PROCESS
53b9248b-ac56-4dfd-aff7-bb34f1f11605 | checkpoint-no-value | ITP APPROVAL PROCESS
52e32d91-210b-5509-8c1c-a2dbb98880a5 | note | Prepared By: Project Engineer - Grant Wallace
c85c04d0-7477-5802-b458-918b34717a54 | note | Reviewed By: Project Manager - Dan Trotman
611382d3-754d-5080-aae9-2673e26102bf | note | Reviewed by: Quality Mgr./Eng. - Cordelia Girdler-Brown
fbd11a77-99de-5e9f-b972-65f0d971c8e1 | note | Reviewed By: Design Engineer - Daniel Cvitanich
1b1fff46-bb9b-5452-9333-150ecc1f83ab | note | Reviewed By: AT Project Manager - Werner Nel
0679e862-403c-56fa-893b-7d8b1c85064d | note | Reviewed By: AT Engineer to Contract - Mike Robertson
40fb24d2-0f33-531a-94e0-5298c25318de | date | Date:
7ff1687e-4386-43a3-a6f5-ef38640ce62e | section | FINAL ITP CLOSE-OUT
d1c7c0d7-ee48-4a21-b7c4-cedd63e7b414 | checkpoint | FINAL ITP CLOSE-OUT
8f5fdcc9-be32-58fa-a276-42becd45753b | textbox | Downer Project/Site Engineer:
a8426a88-8d70-5274-b8dd-fd7c0cbf8911 | textbox | QA Mgr./Engineer:
bde8df4a-60c2-58d6-92f3-27b423d98691 | textbox | Designers Rep(Assistant):
09634134-c216-556a-af5c-5183bf30b55e | date | Date:
b95c894c-8840-4831-81e4-8a742ddcbc81 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
77690ab0-ea6e-5185-9231-d29d741ea610 | textbox | Contractor's Rep Name:
049621b5-c168-5fc4-b6de-3b3e06a0fc4d | textbox | Engineer's Rep. Name:
943b1bba-bd9a-529b-a59b-c55c60447aaf | date | Date:
dd2faced-a4b8-4079-83ae-08b65b4cd4ec | signoff | Add Signature
2835e5c4-d4c4-468c-b4a6-dd4afd6adf47 | checklist | DN1212-ITP-012 Pier 5 - Column and Headstock Construction Rev1 | itp | DN1212-ITP-012 Pier 5 - Column and Headstock Construction
7d79d5e2-f42c-4c84-aaf9-d00a5945854a | section | 1 - PRELIMINARY AND GENERAL
00a18d3a-e0cb-41a6-aee0-3fd9ea02695e | checkpoint | 1.1 - Method Statement Development & Safety Analysis
6d7618a8-536a-5162-be99-fa16d388cbf8 | note | Standard, Drawing or Specification Reference - The Downer Standards (TDS)
76e05948-598f-54ae-bfbe-14adebdae744 | note | Construction Activity Description, Test Type and Acceptance Criteria - Prior to Construction: Document Review
3bb60a4a-3503-508e-a3d6-45090c2d150b | note | ○ Method Statement & JSEA
7b2c8351-1560-5413-9e02-a5b0b213e850 | note | ○ Completed & signed by relevant authority
e60f4855-5ecd-53b3-949d-1742dcba67d7 | note | Test Frequency - Once
c5d00e89-ad92-56e4-9587-d1e1e81091dd | note | QA Record - Work pack (MS,JSEA,ITP)
f1e53d75-a7a6-5a60-ae9b-33c688792659 | note | DNZ Engineer - H
f2739ac7-99c8-5b07-aabc-7efe94f4ee0a | note | Engineer's Rep - R
baf44209-cf26-5ccc-823c-180012361470 | note | Designer Rep - R
7919f7b8-7a45-4a91-a287-b01660a35b7a | signoff | AUTHORITY HOLDPOINT
33d3487d-84d4-421a-9bf4-55b8af23941f | checkpoint | 1.2 - IFC Drawings and Specification
f45dd0e2-d8b7-5b34-9b85-3ba90c6c7027 | note | Standard, Drawing or Specification Reference - ACC
dbeafd8f-3c1b-5f8a-9ed4-388015118272 | note | Construction Activity Description, Test Type and Acceptance Criteria - A minimum of two weeks prior to construction: document review. DWG’s are for construction or as per instruction
e993ee8c-3c89-52ae-8f02-381f0afd8c55 | note | ○ Works done in accordance with KiwiRail specification
e62616ca-d096-57b4-ab69-4463d77988fa | note | Test Frequency - Once
2c1e8d9e-a40f-5390-afe1-998baa4f3e1b | note | QA Record - N/A
4d3f5db5-eb06-5856-93ac-1dd1f3064024 | note | DNZ Engineer - R
c229b717-fe13-48e6-ab24-1e0f4d424d63 | checkpoint | 1.3 - Permit to Dig
57ba55c3-3250-571f-8cfc-cf09cbfc0c48 | note | Standard, Drawing or Specification Reference - DG-ZH-ST004 Ground Disturbance
813afcc4-bd9a-563a-8553-fffdff3e90a5 | note | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction. Permit in work package
6388c287-d5c9-5836-8393-072d1cb9aa43 | note | Test Frequency - Permit issued each week
f018733f-2e73-538e-b11f-cd6dfebff766 | textbox | QA Record - FlowForm Permit Register/Permit Number
d8c6db21-01dd-52aa-9c09-8215998cdb56 | note | DNZ Engineer - H
4f937713-a272-4c66-b9fc-59b1cf501ae6 | signoff | AUTHORITY HOLDPOINT
a7c9c986-fbd9-4e84-aed2-1606bdf2df39 | checkpoint | 1.4 - Lifting Permit
b53c5a00-fc62-5419-92b5-1fe49e26cd71 | note | Standard, Drawing or Specification Reference - DG-ZH-ST047 Cranes and Lifting Equipment Loads
7ce2c830-b0c9-524d-a84c-7ae3dd940781 | note | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction. Permit in work package
44014c9f-11a0-5b99-86c2-6100faa29e1f | note | Test Frequency - Prior to Construction when required
1ab7f6f6-8364-5c1e-a845-e9f612fd6ae1 | textbox | QA Record - FlowForm Permit Register/Permit Number
9768e7f8-87ab-53e3-9780-b11ac24becbb | note | DNZ Engineer - H
1933495f-3ee3-4c50-b19c-d0bfdfd3ba57 | signoff | AUTHORITY HOLDPOINT
ea479860-af47-4ebc-88c9-ee714d29517f | checkpoint | 1.5 - Working at Heights Permit
b3a0dac5-e14d-54c2-8bc6-84a4c249013d | note | Standard, Drawing or Specification Reference - DG-ZH-ST042 Working at Height
8d2a1a7a-4910-5b62-aa5d-faccd262e898 | note | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction. Permit in work package
3b84e8a1-8b7d-5a8a-8e20-fd4d6a6ab07d | note | Test Frequency - Permit issued each week
7763f982-1d93-596a-8631-1777ba8cd304 | textbox | QA Record - FlowForm Permit Register/Permit Number
911843b6-b7a0-517a-8584-e677fb60c6d8 | note | DNZ Engineer - H
56766fc3-5908-4975-a508-ccf5c63d10eb | signoff | AUTHORITY HOLDPOINT
e2096ee1-670b-4b41-95f0-1da52f21cba5 | checkpoint | 1.6 - Permit to Load - Scaffolding
4a7596bc-8b5c-5ad9-b60b-812dc755bdfe | note | Standard, Drawing or Specification Reference - DG-DM-PR036 Temporary Works Procedure DG-DM-FM066
94f20964-aca0-5c9d-94a5-49ed100b4b28 | note | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction. Permit in work package
4889f39f-5968-5cc5-a616-9d2dad60309b | note | Test Frequency - Permit Issued prior to construction
81939828-5596-5c3c-a07a-0c01e2ea22f4 | note | QA Record - Temp Works Certification ITP
7942336c-2726-503e-bf07-cb30346d6ddc | textbox | Permit to Load - PtL
65fb343a-3083-5740-ba03-017ff4183b6c | note | DNZ Engineer - H
cd697656-47db-45f1-a51d-40b5044838c8 | signoff | AUTHORITY HOLDPOINT
ce8a5a68-97c0-4072-a2e1-5a476d9da625 | section | 2 - MATERIAL APPROVALS
c66c647d-867b-4ea9-8eee-a0d9519e8d68 | checkpoint | 2.1 - Concrete Mix Design
c7ec0d9c-ab81-580d-9862-2a592a971961 | note | Standard, Drawing or Specification Reference - NZS 3104, SP-NIMT-ST-AD-00001, Section 2.3.10
8d3ceeb6-01d0-5306-bc27-f47d672bf374 | note | Construction Activity Description, Test Type and Acceptance Criteria - Concrete mix details shall be provided to the Engineer for review and approval.
d1dd16eb-6709-5094-bd75-f4009ec57389 | note | ○ 40MPa @ 28 Day Compressive Strength.
12505214-0fe5-579e-9b3b-f8e7a387c5a7 | note | Test Frequency - Once
58924851-116e-5f42-a781-b196a90b1020 | textbox | QA Record - Mix Certification InEight Response
e3188ef9-32c3-5cf6-899c-24137f0fa962 | note | DNZ Engineer - R
7210fd85-10a1-5a19-a256-022f8ba68f30 | note | Designer Rep - H
a0dd17c6-bb6e-4170-90d6-a6c5a64bf666 | signoff | AUTHORITY HOLDPOINT
a0ea5cbd-51a6-415c-a5de-f566b4324893 | checkpoint | 2.2 - Reinforcing Cages
ea85cf37-61cc-5884-83ee-6df1eb71a315 | note | Standard, Drawing or Specification Reference - Reinforcing Cage Drawings - Pier 5 datail sheet
0041c0b5-0ee3-58d7-af68-7e1bf6c931b0 | note | Construction Activity Description, Test Type and Acceptance Criteria - As per Column Reinforcing IFC detail drawings.
cd17811c-40e0-50e7-b817-0a176b674b7c | note | ○ Shop Drawings shall be provided to the Engineer for review and approval.
bc8ddac0-c415-5e9d-89cf-9c1da6880df8 | note | ○ Note any changes undertaken to reinforcing to be captured as per item 4.2
d7d467f7-3cb7-555c-9025-c4f7d71cd1ff | note | Test Frequency - Every Reinforcement Cage
8f61ab89-a4e7-519b-bc82-6b5c4029171d | note | QA Record - Mill Test Certificates, Delivery Dockets
838a4b21-4b3a-5c29-a1c7-c5d45ff9c6cc | textbox | In Eight Response
e05ff107-2b55-5679-8eae-dbdbbffe533f | note | DNZ Engineer - I
c40e8b3b-5f04-58f0-858c-e2370d6c4391 | note | Designer Rep - H
2b15ba99-6779-4b60-a546-73891e11915e | signoff | AUTHORITY HOLDPOINT
e0fec339-e983-4159-9f4c-19b3eac330c6 | checkpoint | 2.3 - Formwork
bee18179-0f06-5474-8d78-d8d015f8be24 | note | Standard, Drawing or Specification Reference - Material Data Sheet
3d781bf7-cf07-50eb-b671-7531ff116145 | note | ○ Temporaray works drawings Piers 3 and 4.
dbdce0b9-a556-5e60-b63f-688e956fab21 | note | Construction Activity Description, Test Type and Acceptance Criteria - Formwork of choice from sub-contractor, Standard panels up to 900mm wide modules
a5885ce0-3997-5de7-acf7-83b5e50539a9 | note | ○ Rigid hollow-section steel frame
af45a10a-303a-524f-9cee-effaaf609046 | note | ○ High-grade hot dip galvinising for durability & long life
2a10483d-ee12-5be3-b230-8ae122e24eda | note | ○ Gang forms and lifting applications available
a20545d1-6985-54f1-b07a-1341c6059566 | note | ○ Full range of safety features
7254d9e6-e30e-5140-bf96-f7ae3856a937 | note | ○ High Quality plywood
35d10281-4976-55cd-8346-2615cd20a0e6 | note | ○ 60kN/m2 permissible fresh concrete pressure
fdae0133-5914-53d7-83b5-65c4c24a1d96 | note | ○ To be captured on temp works drawings.
98b5ecdd-38f3-588a-bcfa-2afaeea6c532 | note | ○ Inclusive of structural shore loading for super structure
c3f7ace1-5fed-5eec-a344-035a3245ba26 | note | Test Frequency - Once
fb41cf16-1fd3-5db8-b450-876d980e9cde | note | QA Record - MDS
84608fc8-2d79-5fbc-b135-d43fcea5d038 | note | DNZ Engineer - I
949bf2eb-c0b7-592c-b36b-4c3a90a5dc03 | note | Designer Rep - R
0043a561-7097-4be7-81bb-1e3b808065f3 | checkpoint | 2.4 - Formwork Curing Agent
f76dcd95-5d48-5bcb-83fb-c63938dbe3ff | note | Standard, Drawing or Specification Reference - Material Data Sheet
c9b3bc01-8ed6-5946-baed-68bd7b4112a5 | note | Construction Activity Description, Test Type and Acceptance Criteria - Chemical curing agent.
0ced51fd-935e-5008-b77c-24e38ae46b9a | note | Test Frequency - Once
2193c612-1445-50b3-a240-77931eed791b | note | QA Record - MDS
abb0d19f-431d-5d7a-8f2b-fed7da2bac7c | note | DNZ Engineer - R
a7b547b2-4b21-5f62-bde1-c0f79a4c9ebc | note | Designer Rep - R
85dd10ff-1848-4cf9-98a1-c201e65cf707 | checkpoint | 2.6 - Reid Bars Products
621d5909-389e-5ae1-bfa8-3d4082fe95af | note | Standard, Drawing or Specification Reference - Material Data Sheet, 3235599-SP03-ST-3002
240716c5-72a8-555e-a757-57075ba9239b | note | Construction Activity Description, Test Type and Acceptance Criteria - RB 25 Couplers & RB25FNS Reidbar Steel Flange nut, as per noted 8 & 9 on drawing 3235599-SP03-ST-3002. Proposed epoxy will be per manufacturers recommendations to use C8 extreme epoxy. Superstructural couplers will be covered under PFS installation methodology and ITP. This is only for column / headstock construction.
3d00a3b9-9c17-5fba-bf89-e25bdd2b4438 | note | Test Frequency - Once
a478ec14-5667-5141-98b0-ac915bfc7deb | textbox | QA Record - MDS, Delivery Dockets, mill certs
3378ff40-d37e-50d6-90a3-a926729cf45d | note | DNZ Engineer - R
9943a8c6-ce95-5da0-9fac-0589c68398c1 | note | Designer Rep - R
0af1dfa7-8816-42d8-b0ef-b565c9a8f184 | section | 3 - CONSTRUCTION ACTIVITIES
0bed37cd-d350-41d5-8fce-41830247c9ea | checkpoint | 3.1 - Column Set-Out
9621c2c2-c541-5e82-abd6-1d5678896df0 | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3100
e13df6a6-e301-58bd-91ad-7c290907233f | note | ○ 3235599-SP03-ST-3150
6f0bcbb1-7131-57bc-8eab-dd3dae0486a2 | note | ○ 3235599-SP03-ST-3202
c9e8cbaf-1dc5-5a11-869a-69e4c81db021 | note | Construction Activity Description, Test Type and Acceptance Criteria - Before commencing formwork installation, survey set out column position based on drawings with RL supplied. Set out to include; Column centre, height and offset. Tollerances for insitu concrete pour taken from NZS 3109 table 5.2
97861e7d-5464-558f-9a77-3df9d059d363 | note | Test Frequency - Once
7fd694be-3210-5b17-bf25-87c5781f8959 | note | QA Record - As-Built
ab6d4b37-0a25-54ba-b7fd-0b409140dab3 | note | DNZ Engineer - W
a98b8547-3727-43b8-a5eb-7a1f14b181fb | checkpoint | 3.2 - Formwork Installation
dd789614-31fd-578d-81bb-2175baac16a9 | note | Standard, Drawing or Specification Reference - Material Data Sheet, Temporaray works drawings Pier 5
411caf62-b3ac-52ec-b2b6-c4fdf2d0885a | note | Construction Activity Description, Test Type and Acceptance Criteria - As per Temporaray works drawings for Piers 5. Inclusive of shoreloading requirements for the support of the bridge superstructure around Pier 5.
88512fa3-17a2-57c3-ac4d-6f2f7f62275d | note | Test Frequency - Once
28ee0bd7-e00b-5b87-a1b0-61f26c464904 | note | QA Record - Photos plus signed off temporaray works inspection of shuttering and formwork.
8d69e891-8c38-5bd6-ae17-6bfedee8ca92 | note | DNZ Engineer - W
197fad1b-bdd0-47e8-9554-f474f50b964b | checkpoint | 3.3 - Steel Cage Installation
98908331-c84a-51ba-96f5-228e6c5fd7d4 | note | Standard, Drawing or Specification Reference - As per detail Sheets for Pier 5, 3235599-SP03-ST-3210
c165f147-ca1e-598b-9f09-3f695b662c0a | note | Construction Activity Description, Test Type and Acceptance Criteria - Cage installation will be checked prior to placement to ensure that cage inspection requirements identified by BECA and DNZ will install cage and secure with RB 25 couplers that will be installed between the pier and pile starter bars.
946a06ea-cfbc-57e8-b817-bdb944824e23 | note | ○ Couplers will be installed and epoxied in place using manufac turer recommended C8 extreme epoxy and photos of coupler will be supplied a spart of installation QA. Surveyors will also survey cage to ensure verticality and correct height of steel has been achieved prior to epoxying.
b315a1de-23cd-5e55-a748-e665161f0810 | note | Test Frequency - Once
a6bb222d-ae2a-5735-b62f-1a490614bbe6 | note | QA Record - Photos,
2b462003-56a3-51a6-ab70-e84e784d8807 | note | DNZ Engineer - H
27848ba5-e956-5561-ae92-00bca6a36463 | note | Designer Rep - R
eab8fe12-bad3-486b-8133-a99c80f9f0a2 | signoff | AUTHORITY HOLDPOINT
98606154-45ac-463d-b5a4-cc2c42603e6a | checkpoint | 3.4 - Concrete Pre-Pour Inspection
67a44503-3198-5e98-8dda-77f1a745637f | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3200 - PROPOSED ACCESS RAMP- EXISTING PIER 1 DETAILS
996af807-5723-50c8-bd52-408861fc056e | note | ○ 3235599-SP03-ST-3201 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS
afb70af4-0283-5795-8601-d5fdbaa83fcd | note | ○ 3235599-SP03-ST-3202 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS
78387c8c-f6c6-590d-9033-27d6d29f5a73 | note | ○ App 1C - 746-24-847-AC - Tech Spec - Geo & Struc
7c647c1a-3447-5ca1-a4af-87985ead83c2 | note | Construction Activity Description, Test Type and Acceptance Criteria - Reinforcing cage as per IFC and shop drawings.
07c10a53-f466-5294-8042-4f3f7655fa81 | note | ○ Correct number of bars and grade.
e3a6e468-c51b-5bd8-ac4c-cd67a7773540 | note | ○ Correct steel lapping.
c364469e-4811-5274-a66f-ad6d455f36fe | note | ○ Earthing and Earth terminal tested and inspected.
a4349daa-85f4-5a8c-bf20-1d811d744098 | note | ○ Formwork installed as per the temporaray works drawings.
d6be989c-87b8-52f7-a3d4-ac138a071ed9 | note | ○ Minimum 40mm cover achieved.
38975e3b-0241-5aef-96f8-d096aa0fd0a3 | note | ○ Test specimens to be supplied by plant for every 75m³ for each shift of conncrete ordered.
0df9cffb-9891-56e3-a0ff-003c4603387e | note | Test Frequency - Once
76c87d19-95c7-5587-9768-5dc7d3fd28f2 | note | QA Record - Survey Check, Structural Engineer Inspection, MSQA SVR, Pre-Pour Checklist, Photos
8cbe7206-b584-5e6a-b806-ca382e3f38db | note | DNZ Engineer - I
b1bb71a7-5565-5d75-adf4-4a7685e19174 | note | Designer Rep - H
86b5c260-faea-40cf-be4c-6b892ca69c8b | signoff | AUTHORITY HOLDPOINT
5b831e7a-4647-4b35-90ba-08a8352defc9 | checkpoint | 3.5 - Concrete Pour
409c4f1a-ac13-5781-829d-c78739292584 | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3200 - PROPOSED ACCESS RAMP- EXISTING PIER 1 DETAILS
a687df99-86b1-50e5-9833-3dca8ee69699 | note | ○ 3235599-SP03-ST-3201 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS
63bcfc87-45e2-5bda-bbc9-2d327ce34ebb | note | ○ 3235599-SP03-ST-3202 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS
9d6926a2-24c3-54d1-8219-611255df21c4 | note | ○ App 1C - 746-24-847-AC - Tech Spec - Geo & Struc
66510586-f3ff-5f77-8bdf-6f4afc67aa00 | note | Construction Activity Description, Test Type and Acceptance Criteria - Concrete: 40MPa - Self Compacting Concrete - WS4010FS
5c690d41-8aca-5412-a27b-682dd0b6abed | note | ○ Cylinder test taken at supply Yard only.
bb3f682a-a20c-56ed-842b-8dd53added17 | note | ○ Spread Test to be completed on site prior to concrete pour.
27c16773-21b9-5eb6-9473-ffe12b7301e1 | note | ○ Target Spread Test - 680mm +/- 60mm
8d6842b8-0c21-5df6-9ea9-4a05e4cda6a3 | note | Test Frequency - Once
7c44c645-569c-5bde-8a96-8549d1397cbb | note | QA Record - Delivery Dockets, Compressive Test Results, Photos
dfb0de8b-21e9-53eb-ae79-7a764c04ae7d | note | DNZ Engineer - H
28eaae77-039b-586b-a986-d29543047db0 | note | Designer Rep - W
8cf4a840-9284-49f7-8a48-6fd76c3ea9c7 | signoff | AUTHORITY HOLDPOINT
98d30c1c-8c8f-4028-927d-f1e2c1c5d3d6 | checkpoint | 3.6 - Structural Surface Finish
8362bb26-3aae-5efa-8db7-abb3cb6dfc75 | note | Standard, Drawing or Specification Reference - App 1C - 746-24-847-AC - Tech Spec - Geo & Struc 3235599-SP03-ST-3003, NZS 3114, NZS 3109
d6f1b1fd-ccca-5512-8d5a-79b9f352526a | note | Construction Activity Description, Test Type and Acceptance Criteria - F1 Surface Finish - Concealed Formed faces
32b704d1-67c8-5938-a147-e6163cb477d4 | note | ○ F5 Surface Finish - Exposed and Visible Faces
db908cf4-b8b1-5b52-b035-3d7bdb38a3b4 | note | Test Frequency - Each joint and surface.
ebf52c26-67e7-5901-97c6-2e4b8dec85c2 | note | QA Record - Visual Inspection, Photos, cylinders for blinding
f06ecf28-1be7-5dad-bfd2-ceff3fd7a743 | note | DNZ Engineer - H
1fe85f82-d11a-5bbe-8de5-2113c51c7dd1 | note | Designer Rep - I
11682091-4df3-4003-9357-ebfe0a8ef14b | signoff | AUTHORITY HOLDPOINT
5e67b5b7-fc8c-441e-8ecc-82004b64744e | checkpoint | 3.7 - Concrete Curing
59146fdd-c35b-5908-b09a-997e9f6cb634 | note | Standard, Drawing or Specification Reference - App 1C - 746-24-847-AC - Tech Spec - Geo & Struc 3235599-SP03-ST-3200
ac471625-cfa0-592d-a0b5-9569c19beead | note | Construction Activity Description, Test Type and Acceptance Criteria - Concrete to be cured for a minimum of 3 days as per drawing st-3200, curing methodology will be formwork curing. Cylinder to be taken at 3 days to verify strength of 30 Mpa has been achieved prior to stripping of formwork if required. Intention is to leave formwork on to 7 days max if possible.
d2ce586e-b8fb-5ff3-87f7-5aa6bb966406 | note | Test Frequency - Once
f08834e1-f1d2-509d-b743-81991305a4e2 | note | QA Record - Concrete strength results, concrete pour checksheet notifying date of formwork striking.
cdb3e4b3-6c34-5d9a-af6b-17f49103db37 | note | DNZ Engineer - H
cb13853c-63fd-55b5-a6c8-bdc59aaf1b01 | note | Designer Rep - R
0bd6c031-2d50-43f6-bd6b-d5b47a851148 | signoff | AUTHORITY HOLDPOINT
224765ca-68a9-4c0a-b2f4-b80bd37f15a6 | checkpoint | 3.8 - Post Pour Inspection
851ce035-db8c-5aa5-9302-f5e6d95b65fc | note | Standard, Drawing or Specification Reference - App 1C - 746-24-847-AC - Tech Spec - Geo & Struc 3235599-SP03-ST-3003, NZS 3114
f2d75a27-e55e-5d14-aeb7-925550615237 | note | Construction Activity Description, Test Type and Acceptance Criteria - Joint inspection be undertaken with designer to inspect shutters of structure following removal of shutters and survey/ check dimeniosn of structure have acieved stipulated tollarences stated in drawing suite and NZS 3109
288ab8ba-b39a-5caa-b480-c4058c0e40df | note | Test Frequency - Once
5493dd6b-ec10-551a-acd2-eb4345aca478 | note | QA Record - Visual Inspection, Photos
b5bf6ddf-ba16-51fe-9b8e-d2e868cf0390 | note | DNZ Engineer - H
9234c42a-933a-5820-b4e7-01ed5da0b861 | note | Designer Rep - W
ed7a713c-56c6-4f16-99f3-525aaea98d34 | signoff | AUTHORITY HOLDPOINT
d259614b-4f4d-4192-9164-64a9172bc251 | section | 4 - FINAL RECORDS
f79fcd82-425b-4d8c-b419-800f7eb0ea27 | checkpoint | 4.1 - As-Built
d7e66a58-70f1-54d9-b127-6d7fe421819a | note | Standard, Drawing or Specification Reference - N/A
925347f4-62c9-51ee-b53c-dbf6276057c4 | note | Construction Activity Description, Test Type and Acceptance Criteria - Installed as per design drawings. All compliance recorded CAD files
09af72a5-0dfa-5c56-b24c-1c820befa455 | note | Test Frequency - Once
85cb7c53-0de7-5ba2-bb43-74b6f0d16853 | note | QA Record - As-Built
1cf42bf0-0727-54a2-a1de-eae88e4cec28 | note | DNZ Engineer - H
f8cc2561-0082-592c-be5a-c4c5e9a1b6ab | note | Designer Rep - R
c31912cd-9275-41da-af66-11df407012df | signoff | AUTHORITY HOLDPOINT
46891132-e85b-4311-874a-ca10ddb1b387 | checkpoint | 4.2 - Redline Mark-Up
a6a89bf9-f8b9-55fd-bfed-35c7cdfc6c44 | note | Standard, Drawing or Specification Reference - IFC Drawings
ab197424-8ffc-5577-9b6a-4c5407893fc0 | note | Construction Activity Description, Test Type and Acceptance Criteria - IFC Drawings mark-Up on ACC sheets dated and signed.
eec24d1d-9948-5bf9-b74d-cb2d16cd6777 | note | Test Frequency - Once
e222b88e-f312-512f-be6b-80fd2e271e10 | note | QA Record - IFC Drawings Mark-Up on ACC
f4ec2d45-78f8-5b0d-b2c5-856f7aa54718 | note | DNZ Engineer - H
b78685f6-d164-5d34-bc57-6e9393f1a388 | note | Designer Rep - R
678e3de8-11fe-4257-900a-e14259329c7a | signoff | AUTHORITY HOLDPOINT
7b810877-848f-4f80-8ad2-bc3d0459c15c | checkpoint | 4.3 - Non-conformances
fe67c2cc-d819-587c-bc66-77890a6b826a | note | Standard, Drawing or Specification Reference - DN1212-DOW-PLA-PM-0005 QMP
1a202b8f-0ee5-5c86-b274-a45d15724c95 | note | Construction Activity Description, Test Type and Acceptance Criteria - Non-conformances reports to be raised when specification not met. All non-conformances within the area under review need to be listed on the NCR report.
76916e1d-e732-5300-9523-7e5ac4a1a619 | textbox | NCR Reference
400a6697-b7d2-51c6-a876-b226d185669a | note | Test Frequency - Each NCR
278d9984-fef7-5bd5-a2f9-f5a279f194e6 | note | QA Record - NCR forms on InEight
aeb54397-25bd-5a32-b73a-c5f54e985518 | note | DNZ Engineer - H
f557f298-22f3-44e3-945e-a6f9d96d8f93 | signoff | AUTHORITY HOLDPOINT
253b8195-5856-4308-88eb-0b8cd2e8067a | section | ITP APPROVAL PROCESS
632125b5-4af5-4738-8b3e-7ae1d0287690 | checkpoint-no-value | ITP APPROVAL PROCESS
8be90b35-9262-5664-96d6-8703a720d81d | note | Prepared By: Project Engineer - Grant Wallace
806c47e8-b6f4-54a8-aa2a-4f067248b13a | note | Reviewed By: Project Manager - Dan Trotman
a1841cbc-019e-5802-ac3b-5c3852011f4d | note | Reviewed by: Quality Manager - Cordelia Girdler-Brown
9c74cf25-876f-5722-904a-a8138e1ed8e3 | note | Reviewed By: Design Engineer - Daniel Cvitanich
e9a1e48e-f697-5868-9f81-0c336da2ee92 | note | Reviewed By: AT Project Manager - Werner Nel
43b63600-d995-5f4c-a16b-857d6805283b | note | Reviewed By: AT Engineer to Contract - Mike Robertson
1a78f2f6-dd29-54e9-aeb4-ef328076e8a9 | date | Date:
93f4142e-2bb8-498f-889c-1ce3e6e72de2 | section | FINAL ITP CLOSE-OUT
1fd8e92b-0ee4-484d-ad0d-5cd9ea21d338 | checkpoint | FINAL ITP CLOSE-OUT
2acb7077-9f7e-5d3a-a130-68ac0ceb6578 | textbox | Downer Project/Site Engineer:
756b125f-25b1-5dc1-8099-d23ea648094f | textbox | QA Mgr./Engineer:
9d48837c-b58c-5642-b90c-a8580949ee7d | textbox | Designers Rep(Assistant):
bb56d3a7-0d6e-52f0-8d1a-2ab18390e8cb | date | Date:
c52d1a22-7e6f-48b7-8d40-48dee8ca186e | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
3f3925db-7a02-56f5-af43-acf8c5c7b88f | textbox | Contractor's Rep Name:
c5425bf8-7814-573f-b1cf-0778c7ef317f | textbox | Engineer's Rep. Name:
9d02b223-2217-5d1d-b08e-b2acc0590738 | date | Date:
8c42a692-8812-4322-b7d8-8038fd7c2dd8 | signoff | Add Signature
df616841-e21b-4916-8d43-67855654a74d | checklist | DN1212-ITP-013 Pre Cast Cantilever Deck Fabrication Rev1 | itp | DN1212-ITP-013 Pre Cast Cantilever Deck Fabrication
7bb03407-e601-4c6c-ab6a-b5cd3cc7aa95 | section | 1 - PRELIMINARY AND GENERAL
13d86ba7-f9b1-47e9-ae6e-e66bed8c0bbb | checkpoint | 1.1 - IFC Drawings and Specification
f7ebc2df-cdd6-5355-88ad-030ac6e6a28e | note | Standard, Drawing or Specification Reference - IFC Drawings, Wilco Shop Drawings
916f4a7e-92a1-5970-9701-3ba973f1bdf9 | note | Construction Activity Description, Test Type and Acceptance Criteria - A minimum of two weeks prior to construction: document review. DWG’s are for construction or as per the instruction.
04032685-ff9a-515d-a33b-1e09092d08b7 | note | ○ Work is done in accordance with IFC design and specification.
a1d6e017-d6cf-5364-a05b-5f4989c593f0 | note | Test Frequency - Once
c8aebe19-ab4d-5fa1-8511-c5a5a76bd28e | textbox | QA Record - Reviewed Shop Drawings InEight Reference
9e7457c6-451c-5f45-a496-e6fd12bfed8f | note | DNZ Engineer - R
aed042a1-71e2-58a5-95b8-a75b036a016b | note | Wilco PM - R
35201a51-2d10-5f54-8efa-b9bac8ba5e02 | note | Designer Rep - R
237b0566-d684-4c37-bb45-0d751cffcac7 | section | 2 - MATERIAL APPROVALS
13ffc625-a267-4509-92a4-c4841c2d09f6 | checkpoint | 2.1 - Concrete Mix Design
03e46ac3-fcbf-5792-b042-68cfe49a6e0b | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3001 - PROPOSED ACCESS RAMP- GENERAL NOTES
f093ca40-4e5d-5f88-af53-b9197789a1e0 | note | ○ 3235599-SP03-ST-3002 - PROPOSED ACCESS RAMP- GENERAL NOTES- REINFORCED CONCRETE (SHEET1 OF 2)
efb9469c-1697-521e-ad03-a60e3d29b99b | note | ○ 3235599-SP03-ST-3003 - PROPOSED ACCESS RAMP- GENERAL NOTES- REINFORCED CONCRETE (SHEET2 OF 2)
50281642-295f-53df-8b37-a197630aedd8 | note | ○ App 1C - 746-24-847-AC - Tech Spec - Geo & Struc
9520deee-fe52-507d-9bf7-a87aad8f4dcb | note | Construction Activity Description, Test Type and Acceptance Criteria - Concrete mix details shall be provided to the Engineer for review and approval.
1c71963f-d44a-50ba-83af-a63c533fe32b | note | ○ 50MPa @ 28 Day Compressive Strength.
438e52cf-6fed-54d3-bdb2-d0de8ae2b111 | note | ○ Maximum Aggregate Size 20mm.
e6d4ad73-c175-53b7-af0a-fe918eb787bb | note | ○ Maximum Water/Cement Ratio 0.43 (drawing/ notes state 40 Mpa but concrete increased to 50 Mpa mix to reach target strength quicker for demoulding).
085a47fe-ce4c-515a-9584-8953f99f2c08 | note | Test Frequency - Once
c3bccae3-9f68-51ab-b042-9ef378ffd0ec | note | QA Record - Mix Certificate, Plant Certification
8a5d9fce-8c30-58f3-a6df-c24b3aadea9c | textbox | InEight Reference Approval
5461dbdb-3e53-5144-b9c3-52aad6bdfa80 | note | DNZ Engineer - R
118bfe48-e5f9-5f8a-af94-4a008f6817fc | note | Wilco PM - R
96b43c96-622b-5082-92c6-032bf94aed70 | note | Designer Rep - H
4a36cef5-e48d-414d-8946-0b50edaeaebc | signoff | AUTHORITY HOLDPOINT
38fc8fdb-01f0-4dcf-808c-19a7bbee606b | checkpoint | 2.2 - Reinforcement
7e120d6a-3bda-522b-ba8a-959e9bbcaa44 | note | Standard, Drawing or Specification Reference - IFC Reinforcement Detail Sheets
8a627e59-9c37-56bc-9753-9921cd741a67 | note | Construction Activity Description, Test Type and Acceptance Criteria - As per Cantilever Reinforcement shop drawing detail.
532beb6a-8d96-5afb-8bce-5c57338c87c3 | note | ○ Shop Drawings shall be provided to the Engineer for review.
5c7505de-bcd5-56ea-a660-ac686af0efc9 | note | ○ Grade 500.
8505944a-4ab5-5a44-bb73-abc453a6c298 | note | Test Frequency - Once
a6d02773-4f99-59bd-8f31-b0976fe9e386 | note | QA Record - Mill Test Certificates, Delivery Dockets, Wilco Shop Drawings
0e83093d-2477-5c2d-946b-1dad9b744459 | textbox | InEight Reference
4991ae3d-11c3-5c0d-ba0b-e7dbbd514574 | note | DNZ Engineer - R
eac9e103-3325-5692-b0e4-1e54a43d4350 | note | Wilco PM - R
855d8574-c0b7-5d76-b16c-3703252ae23a | note | Designer Rep - H
6a09f694-4738-44cd-b070-ee9f7a5cff2b | signoff | AUTHORITY HOLDPOINT
4e46ddef-49df-415b-ad4a-c139e88a063b | checkpoint | 2.3 - Lifting And Handling
37fe987b-929a-5977-9067-454452b1b683 | note | Standard, Drawing or Specification Reference - REIDS Lifting Manual
2384921a-ddb5-5828-bba1-3da7542aa61a | note | Construction Activity Description, Test Type and Acceptance Criteria - Lifting Design added to the shop drawings.
aeb41476-0a36-53ad-9ef9-d6eac403b2fe | note | Test Frequency - Once
7ae30467-73c4-5bd7-b07c-6ebe8430b2ad | note | QA Record - Lift Design Approval
63b28d4e-c240-5b7b-bbed-a403cfe1c07d | note | DNZ Engineer - R
057a9f21-37a3-5ae1-997c-02c3a183597c | note | Wilco PM - H
1cb90620-f747-4564-880d-1ff4cd733a6c | signoff | AUTHORITY HOLDPOINT
1525d9d2-e1f9-4401-ab2a-d87899e2dfa9 | checkpoint | 2.4 - Curing Method
86f15764-6a5e-5777-bba6-104c7b4eba2d | note | Standard, Drawing or Specification Reference - C0602.7, NZS 3109:1997 Section 7
d9d41242-903b-5212-ab8e-2e4d16437221 | note | Construction Activity Description, Test Type and Acceptance Criteria - Curing method shall be by wrapping of the precast concrete with shrink wrapping for a minimum of 7 days.
374cdaa1-6de9-54f3-b638-4af84e455c98 | note | Test Frequency - Once
ae6f9c75-00da-5d7a-8796-fb5d0f32f77c | note | QA Record - Photos
c00dad9e-c639-50a6-a47a-ce1f63c3465a | textbox | InEight Reference
6ecc1cb2-069e-56cd-8e85-2d6a98e2aea3 | note | DNZ Engineer - H
fe08397f-e1ca-500b-96b9-17a0bb7ee6cc | note | Wilco PM - R
a972abc5-907b-5257-b03e-fb1f50b14f4a | note | Designer Rep - R
bee82e78-b208-42c8-bacf-28bef77df2e0 | signoff | AUTHORITY HOLDPOINT
fa2a86eb-29f3-492a-9f02-7362943f2120 | checkpoint | 2.5 - Cast in Plate
cf9f654b-86ea-5221-a86a-1ae69e9595b4 | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3200 - PROPOSED ACCESS RAMP- EXISTING PIER 1 DETAILS
42e87f74-1a7b-5c19-ae16-f7b8bfdabf39 | note | Construction Activity Description, Test Type and Acceptance Criteria - Stainless Steel:
c311675f-aae8-5735-b526-cb984207a2bc | note | 1) M10 SS Grade 316 Bolts with Nylon Washers
44163867-4623-5998-a677-8ee246d54aac | note | 2) M10 SS Grade 316 TCM threaded inserts
1e2c65cf-60f0-5e9f-bd89-26960c476e1c | note | Hot Dipped Galvanised:
50769a69-ebbd-515c-8ddc-8e4549019846 | note | 1) 450 x 10mm thick HDG 600 plate with approved surface treatment. Colour matched to concrete.
a961d0af-2544-5184-b572-56811ca20234 | note | Test Frequency - Once
bfe63172-630f-5489-9030-6c80bbc7ebe8 | note | QA Record - Material Certificate & Photos
c7a75e77-eb97-5f6d-9240-65761201d96a | note | DNZ Engineer - R
51d6409d-18fb-578e-9fef-772649eba1f8 | note | Wilco PM - R
a8955604-4c52-43f8-a687-b25954b2a570 | section | 3 - PRE-CAST FABRICATION ACTIVITIES
1c41d3fb-28fa-47cf-bad0-fee95e740caf | checkpoint | 3.1 - Mould assembly / set-up
98dd2540-b7b9-55d4-8e93-82aef52da983 | note | Standard, Drawing or Specification Reference - Approved Shop Drawings
bb8ef94b-ab27-5a06-8e43-4a4c56d9b439 | note | Construction Activity Description, Test Type and Acceptance Criteria - Mould shall be set-up as per IFC Shop Drawings.
6e3e2318-986d-5950-b3eb-4df3bb672f61 | note | Test Frequency - Once
250853d0-3031-5349-85f9-dacaa0eb649c | note | QA Record - Wilco QA Report
1e4123aa-a84e-5e34-840b-c07350d1cc83 | note | DNZ Engineer - W
c73713d3-bfe7-5238-be31-32edd2cb482d | note | Wilco PM - I
27865d51-c5a8-55c4-8a8f-907174e0a3cc | note | Designer Rep - W
5341daa1-6dfc-4999-b0a5-699e7ff088b1 | checkpoint | 3.2 - Reo Assembly & Placement
06227289-1c31-53f7-8677-e54e99191d2c | note | Standard, Drawing or Specification Reference - Approved Shop Drawings
2d05d67c-4dde-553e-bc8f-5183ae74ffcc | note | Construction Activity Description, Test Type and Acceptance Criteria - Reinforcement cage assembled & installed as per IFC Shop Drawings.
d8102c23-95ac-56da-8369-fce4bb5f05a9 | note | ○ Threaded rods shall be wrapped with 2 layers of Denso tape at the interface.
d6ab810e-d14a-5f13-8028-dd13d1ddfff5 | note | ○ Stainless steel 50EA6 Studs to have 100mm embedment and to be flush with the surface of headstock.
ad668e6b-9b05-5d7f-a902-aa0b8bb92bc1 | note | Test Frequency - Once
3765d677-510f-571f-8cb8-bb12322af9ca | note | QA Record - Wilco QA Report
5ee1429b-cd0e-5ae6-8641-151915791830 | note | DNZ Engineer - W
e4adddcb-ea02-5bd5-a764-eb6fa45c5fd5 | note | Wilco PM - I
990221cd-df8c-5bfb-a336-50a22f8751ce | note | Designer Rep - W
f0d45cae-1bab-4278-a3dc-658e94b12dd6 | checkpoint | 3.3 - Corners and edges
a391ad8c-295c-5b85-b00f-aaa839eb01db | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3200
7abb0457-f028-53f4-89da-00c85eb2113f | note | ○ 3235599-SP03-ST-3001
b80b2849-9a03-58a9-b6d2-86caccb8abf9 | note | ○ 3235599-SP03-ST-3002
76804bb6-874f-51c3-aa45-03e21f0adeb0 | note | ○ 3235599-SP03-ST-3003
eedacc1c-cb81-5f02-a02c-73f044d1df23 | note | Construction Activity Description, Test Type and Acceptance Criteria - All external corners and edges to concrete surfaces shall have a 20x20mm CHAMFER unless shown otherwise on the drawings.
451adf09-0e77-5685-bb6c-1010a4b4d406 | note | Test Frequency - Once
120501e0-7751-51e9-895e-d44a4fb03c51 | note | QA Record - Wilco QA Report
68f5c587-d391-5dca-9894-03acf9b4ac17 | note | DNZ Engineer - W
b9564122-e78d-56fd-8959-0dfe7bd0597a | note | Wilco PM - I
38b35e9e-6802-557a-8aa5-496839a41deb | note | Designer Rep - I
7716d3a4-0c4d-4824-ab79-1ebb4bed6646 | checkpoint | 3.4 - Dimensional Tolerances
28b4de87-2e78-54db-acd1-a9e21f6c4bb1 | note | Standard, Drawing or Specification Reference - NZS 3109: 1997, Table 5.1
dc9bff6e-c078-55fb-898c-3c442a1e088b | note | Construction Activity Description, Test Type and Acceptance Criteria - As per Table 5.1 – Tolerance for precast components NZS 3109: 1997.
686ef838-72a2-503b-8a49-441e3cb16efd | note | Test Frequency - Once
3e6a07fd-5e7e-59b0-b887-b2b55e726caa | note | QA Record - Wilco QA Report
9c234c9f-d317-5318-9dad-c302d3be4181 | note | DNZ Engineer - W
5a99935c-8ce5-5b3b-a467-1a198c97b69f | note | Wilco PM - I
6120f766-9a33-5181-a0d0-43986b3c4689 | note | Designer Rep - W
6d7ed7b8-eb7d-4b04-a001-5123775df39a | checkpoint | 3.5 - Cast-in Installation & Inspection
c03c5d15-0ccf-592d-b498-2e50f7c0591a | note | Standard, Drawing or Specification Reference - Approved Shop Drawings
cef85233-1b22-5ba9-b261-d54359576b8d | note | Construction Activity Description, Test Type and Acceptance Criteria - Set-up as per IFC Shop Drawings.
88fccf61-ddf0-57e9-9d29-b49c4f4a13c7 | note | Test Frequency - Once
19412dec-97bf-5ff2-8d4f-73b6b0d2270b | note | QA Record - Wilco QA Report
1b560181-4706-51b7-a78a-f0dc7abe5c71 | note | DNZ Engineer - W
938ccc2b-7441-5bec-a67f-8f285c26368b | note | Wilco PM - I
b809584c-3cb0-5520-af39-f7eafe38097b | note | Designer Rep - W
db206a89-be92-4cb7-972b-8c6048f495e7 | checkpoint | 3.6 - Approval to cast (Pre-Pour)
9b0ce25c-09f4-50a8-b427-64ee9530d498 | note | Standard, Drawing or Specification Reference - Approved Shop Drawings
ee385d79-d15d-5701-ac2b-7ef33f81e66d | note | Construction Activity Description, Test Type and Acceptance Criteria - DNZ/Beca to be notified of the cast date for a Pre-pour inspection.
7839e6a9-76eb-5295-af35-64d665d2115f | note | ○ PS3 to be supplied by Wilson.
18e86814-9078-573f-8913-179e318d7abc | note | Test Frequency - Once
98e959d8-945c-5f2f-81aa-bced62fddd50 | note | QA Record - Wilco QA Report, DNZ/Beca Pre-Pour Inspection, Photos
44d18a08-693c-5fda-a207-73fa80489db9 | note | DNZ Engineer - I
b87a0fa8-3b3c-5c3f-a92f-80fff624ff87 | note | Wilco PM - H
fee552f3-3e8e-5e01-b8cf-7aea5b483332 | note | Designer Rep - I
685fe856-0c8b-41ab-a43a-70f5bcd7f1ab | signoff | AUTHORITY HOLDPOINT
e21d8dec-6254-4396-bd42-9b2337eccfb1 | checkpoint | 3.7 - Concrete Testing
ecc33b13-135b-5c68-a993-44686257dc73 | note | Standard, Drawing or Specification Reference - NZS3104:2021
640a0f48-0dcc-5f1e-a56f-a374505205dd | note | Construction Activity Description, Test Type and Acceptance Criteria - 3 x Cylinders for 28 Days Compressive Strength Testing.
f150f23a-fc85-5609-9951-ede59981e197 | note | Test Frequency - Once
53127be0-e87e-51e9-9a50-1e76d9fb2834 | note | QA Record - One set of samples, 28 Days Concrete Compressive Results
060a6dcd-537b-5c87-a620-8662535c4b7c | note | DNZ Engineer - R
e5ffa429-4ae4-5fea-ab29-89250df5ace3 | note | Wilco PM - H
6570ea35-2766-5734-b4af-272de91bc002 | note | Designer Rep - R
98d96802-28dc-4e88-a424-375b37701f37 | signoff | AUTHORITY HOLDPOINT
f57bbb7c-29ed-4d75-874a-366d286e2d9e | checkpoint | 3.8 - Concrete Placement and Finish
77d85482-11e2-58e9-bcf0-37ad99803c7f | note | Standard, Drawing or Specification Reference - NZS 3114:1987
5441968c-b562-55e9-a6a1-092f43be3f4a | note | Construction Activity Description, Test Type and Acceptance Criteria - 50Mpa Concrete.
805b799c-9798-50f2-b293-bc28a1580758 | note | ○ Finish as per Shop Drawings.
490b13a5-d47a-5350-bfd3-674ec94e3930 | note | ○ U3/F5 finish class.
290e576c-5d25-5d2c-a377-611c628d57aa | note | ○ Tolerance on Cover: -0, +5mm
86809542-d51d-5be0-a766-76ad658c7083 | note | Test Frequency - Once
bae1b925-7818-5891-a313-bb1a9823fe25 | note | QA Record - Wilco QA Report, Concrete Dockets
e8c3eb10-306b-5e9e-8e91-e817ca904754 | note | DNZ Engineer - W
2c2a030d-2dfa-5e7d-b88b-86d244d9f657 | note | Wilco PM - I
5e0a5809-49de-5404-a1d1-1f49917d37d9 | note | Designer Rep - W
a66b1d48-c3b6-41b7-a37a-39c8b40c9bce | checkpoint | 3.9 - Demoulding
c15cc61d-0d02-5705-9c81-b6d9a4cd36e7 | note | Standard, Drawing or Specification Reference - Reid Lifting Manual, Reid Lift Plan
bb049086-7944-5126-8756-566538df1d67 | note | Construction Activity Description, Test Type and Acceptance Criteria - Minimum demoulding strength achieved.
011f7635-1a8b-5dc8-9822-1942f4d4e041 | note | ○ Lift plan shall be followed.
a05503ef-234b-55e2-8052-87bd99e916e4 | note | Test Frequency - Once
a0659506-5ad0-56fe-9c2a-52624d6176fc | note | QA Record - Lift Plan, Compressive strength Test Results, Reid lifting manual, Reid Lift Plan
ca942c3b-4db8-51ca-829c-1cf349051401 | note | DNZ Engineer - R
2b19c9b5-0d6d-5357-9392-4f50bc66fb2b | note | Wilco PM - H
42635ae0-af15-53b1-ba75-dbe2548c0815 | note | Designer Rep - R
49281e74-d478-42f4-a8ee-33dd14ad90f1 | signoff | AUTHORITY HOLDPOINT
814f8161-4a1c-4941-9d79-1511e0ce22f3 | checkpoint | 3.10 - Post Pour Inspection
e2043505-39a2-52d5-9be7-5a59b780d798 | note | Standard, Drawing or Specification Reference - Approved Shop Drawings
1e95056f-baf1-5d8d-a939-d5b20255d8ee | note | Construction Activity Description, Test Type and Acceptance Criteria - Cantilever to be inspected to ensure are free of defects prior to site delivery.
31ab8de4-360a-5aa9-bc84-4da11f639f5e | note | ○ Confirmation that F5 finish has been acieved for the pre cast unit and the U5 broom finish has been applied to the top deck as per shop drawings.
a9fa8551-8e41-5dc7-81fa-16b5a8a67e6a | note | Test Frequency - Once
ae03a38e-c183-53e2-9d18-55a3e4f98d6d | note | QA Record - Wilco QA Report
8688cdd4-5110-595f-9263-8b9e8dc01edd | note | DNZ Engineer - I
4c480364-6ec7-5fc6-ab69-472b624444df | note | Wilco PM - I
6b3e7e2b-6149-5ad6-aca9-33def5117814 | note | Designer Rep - I
ccffe341-7f83-4a45-b289-ef160b0da0c7 | checkpoint | 3.11 - Unit Marking
19eb0a97-26a8-54aa-b6b5-e3490fb2972a | note | Standard, Drawing or Specification Reference - Approved Shop Drawings
2d7ef64e-04b4-5dc5-bf00-8ded24f97626 | note | Construction Activity Description, Test Type and Acceptance Criteria - Product marked with the correct information. (Date of cast, Unit ID, Weight)
48426e7b-25b9-59c6-9ca4-c67999eb5dff | note | Test Frequency - Once
98f1292c-733f-5285-85fc-c94a6a43b361 | note | QA Record - ID Label
3f133470-b4d0-5be8-9cb6-5519c556f6a8 | note | DNZ Engineer - R
5015d2eb-ca0b-5c32-a7d0-d62fbfe75a9b | note | Wilco PM - I
4add8590-ff2e-5ae2-8db2-174b30ad715a | note | Designer Rep - R
30cffcf8-0fee-45bb-afbb-3d3251b492f5 | checkpoint | 3.12 - Curing
33906a66-b52a-5c50-b56c-4de222309bcb | note | Standard, Drawing or Specification Reference - NZS 3101.1&2:2006
bcd851ea-1463-59a6-ab88-0e3bcbe32093 | note | Construction Activity Description, Test Type and Acceptance Criteria - Standard 7 days curing with concrete unit remaining shrink wrapped to provide membrane for curing.
3829ff4e-6268-575a-9019-eb7c65e51b6b | note | Test Frequency - Once
389f9ab1-28a9-5f32-aadb-58e5707fab35 | note | QA Record - N/A
9ed6b98c-47dc-5d94-8d67-ea834fea23a8 | note | DNZ Engineer - R
2aba79e3-86d4-5cd4-b1b6-3f8b2f55bd98 | note | Wilco PM - I
6f83e13c-b2f1-52c1-887e-70fe8d3635bb | note | Designer Rep - R
d2b62f56-8059-4e95-bc0c-51cc8114f1f9 | section | 4 - FINAL RECORDS
620e7470-458e-4009-92fc-90485356cd27 | checkpoint | 4.1 - Compiled QA
b5ed3221-3d37-57d6-bb09-6afc7a427eb8 | note | Standard, Drawing or Specification Reference - DN1212-DOW-PLA-PM-0005 QMP
bf775931-c251-5c58-adeb-df1ef5894a78 | note | Construction Activity Description, Test Type and Acceptance Criteria - Quality Assurance documents are compiled as per the ITP acceptance criteria.
76450fdd-2fc4-589d-98c9-bc387b6e0831 | note | Test Frequency - Once
a20a5fd6-9996-5fcb-8de8-2982611e0e5d | note | QA Record - Wilco QA Report
8e45c59f-42e4-5ff6-b344-a9640b0891d3 | note | DNZ Engineer - R
81097a84-c9ca-5543-a9e0-ce89b5d5fb29 | note | Wilco PM - H
b6d905b2-ef67-5481-9d91-d1021fd08a21 | note | Designer Rep - R
98ba8a45-fbcc-465b-82fa-293bd041b2ae | signoff | AUTHORITY HOLDPOINT
d3f8a553-fdd8-4083-8d49-0f2807d6cb95 | checkpoint | 4.2 - Producer Statement (PS3)
3db253ad-b860-553b-94de-f7110dcaff22 | note | Standard, Drawing or Specification Reference - NZS 3916:2013 Schedule 6
3cd3c7f1-e124-5ea1-b6d8-30b089675552 | note | Construction Activity Description, Test Type and Acceptance Criteria - Completed and signed PS3 by Wilco Confirming Compliance with the IFC drawings and specification for the fabrication of Cantilever Deck.
cc411793-ecfd-51ce-9a0f-b9667a197097 | note | Test Frequency - Once
2ae3cd76-1ed0-522a-828c-dceccc6861e5 | note | QA Record - Signed PS3
4f80e06e-a699-5a50-8872-bfb4464d80a7 | note | DNZ Engineer - R
a3cee6a7-fec5-50cb-ad4d-104386188431 | note | Wilco PM - H
ddf86045-3b29-5d24-9071-1c6b498ae759 | note | Designer Rep - R
4f535361-b2e0-421e-9150-518c95c17a61 | signoff | AUTHORITY HOLDPOINT
2d72d287-8a64-4d10-9bda-00252519a693 | checkpoint | 4.3 - Non-conformances
bf2fdc9e-0c2d-5e54-a4d1-af53deffd9fc | note | Standard, Drawing or Specification Reference - DN1212-DOW-PLA-PM-0005 QMP
ae6cf579-73b5-5cb7-8fa1-e5bd32631539 | note | Construction Activity Description, Test Type and Acceptance Criteria - Non-conformances reports to be raised when specification not met. All non-conformances within the area under review need to be listed on the NCR report.
3fb5ef1d-fe7c-58fc-bd0b-b43e73c52347 | textbox | NCR Reference
bc5e41db-d8cc-5e8d-96fe-334f33194657 | note | Test Frequency - Each NCR
791cb492-06da-598d-9ff9-e73162cdb246 | note | QA Record - NCR forms on InEight
34badfcd-d387-5b26-b241-f2176e1910c4 | note | DNZ Engineer - H
37b715fe-fcad-5598-82dc-58899d16d630 | note | Wilco PM - R
317279f9-522f-5009-b21d-aade0dbe5eae | note | Designer Rep - R
03797772-7922-49c5-ad2f-88b8410b316f | signoff | AUTHORITY HOLDPOINT
1abdca21-9c2d-4c50-a1d1-eecbc88c253c | section | ITP APPROVAL PROCESS
de5a1e78-807f-4b98-b8df-119fe9436598 | checkpoint-no-value | ITP APPROVAL PROCESS
c5a3a8aa-3e3e-5a8c-9321-1ce85a1d5571 | note | Prepared By: Project Engineer - Grant Wallace
4c3b7d89-5dbc-505e-b1ae-043f7678ca3a | note | Reviewed By: Project Manager - Dan Trotman
0026d901-8089-5884-92f7-6e433cdecbff | note | Reviewed by: Quality Eng./Mgr. - Nas Matar
52aca371-5cdc-5531-a687-11e0da867ca5 | note | Reviewed By: Design Engineer - Daniel Cvitanich
47578234-0779-51af-9f06-ef8dfe9bd1ee | note | Reviewed By: AT Project Manager - Werner Nel
46d6aa43-13a9-5365-86b0-036edbfb2a6c | note | Reviewed By: AT Engineer to Contract - Mike Robertson
bc5d2917-39c6-5f3a-95cb-c6ab78d0614e | date | Date:
c2e3479e-7377-44a5-9416-bd9785d6e809 | section | FINAL ITP CLOSE-OUT
f3d0982f-5661-4982-b9c6-ab76309598f4 | checkpoint | FINAL ITP CLOSE-OUT
941fa852-df3e-549f-a480-d0761718b1fd | textbox | Downer Project/Site Engineer:
8070e519-9592-59a1-9fb1-729264d9660f | textbox | QA Mgr./Engineer:
45304e90-65c6-5bb9-8153-0b0b8b17e38b | textbox | Designers Rep(Assistant):
eae99314-33a2-5f03-88d1-03bf352f3ef0 | date | Date:
b520fc47-082e-4b1f-8acf-0384661a8737 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
e79030ed-f54a-5720-97a7-04d9568e3ad4 | textbox | Contractor's Rep Name:
a521ff70-971f-50c9-8334-888945ee5062 | textbox | Engineer's Rep. Name:
ae825774-0a84-5404-b4e5-bb0bb4f95c98 | date | Date:
bfab3f44-db47-4d9e-9c85-818c96eb3a3e | signoff | Add Signature
4ecd0690-635e-4b91-b472-1a77b9179e44 | checklist | DN1212-ITP-014 Pier 1 Cantilever Deck Install & Stitch Rev1 | itp | DN1212-ITP-014 Pier 1 Cantilever Deck Install & Stitch
2acc6169-e9ce-43d9-851c-ff4d0210b2d6 | section | 1 - PRELIMINARY AND GENERAL
71fda87f-6898-459f-bdca-f042a44605aa | checkpoint | 1.1 - IFC Drawings and Specification
27d48b23-15f4-5766-a100-b688b986ee1f | note | Standard, Drawing or Specification Reference - IFC Drawings
80dd74ce-31ba-5e81-91e0-416d83d3b215 | note | Construction Activity Description, Test Type and Acceptance Criteria - Work is done in accordance with IFC design and specification.
be322b4d-0b4c-5509-ac88-745ffb4588f1 | note | Test Frequency - Once
27508223-cd0e-553e-b8d7-7ba8e631c4f2 | note | QA Record - DN1212-ITP-013
8f99466c-8291-54ee-b6ba-ba533d91f40a | note | DNZ Engineer - R
22989d32-6a3a-5ed0-a9fa-bb124f83b5dc | note | Engineers Rep - R
f0217ee2-5eb6-5211-964b-2bf6bfcd4964 | note | Designer Rep - R
2b7e8051-87d0-456c-b543-308d3a66c8a2 | checkpoint | 1.2 - Method Statement Development & Safety Analysis
cc12cf01-4d31-5721-bea9-4095cea51886 | note | Standard, Drawing or Specification Reference - The Downer Standards (TDS)
4cf78951-ee0b-599c-ae0e-e4b91a4d9099 | note | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction: document review.
ecfdb911-258c-51d3-b355-2437fb1e0779 | note | Test Frequency - Once
35154dd8-ddbb-58e4-8bb2-ecedba2b40cd | note | QA Record - Method Statement & JSEA Completed & signed by relevant authority
2841a395-b934-5c24-be7c-01d8c4438017 | note | DNZ Engineer - H
79a18d67-b55f-5e90-ac33-861bf41974f6 | note | Engineers Rep - R
5130a632-124c-5211-8049-ea98298eeb6f | note | Designer Rep - R
74b5a68b-cf60-43e2-a671-a17e1878b218 | signoff | AUTHORITY HOLDPOINT
9de87a8e-27ed-4d9c-915d-a0de2a24ca11 | checkpoint | 1.3 - Model
3c3e1cee-749b-5230-a585-f51343a4b68d | note | Standard, Drawing or Specification Reference - ACC
a3730cca-0f16-5722-b831-48e6702ae435 | note | Construction Activity Description, Test Type and Acceptance Criteria - Model reviewed and confirmed with correct location; depth, height and orientation
50fa3adb-d14d-50e5-827f-2431954fdb38 | note | Test Frequency - Once
d5122a31-392c-5ed4-92ca-8ce9db22f2a6 | note | QA Record - N/A
21f0ff53-6502-53cd-a401-fb14f611057f | note | DNZ Engineer - R
37c8dd50-4fd2-403e-9119-4795e9b6f269 | section | 2 - MATERIAL APPROVALS
1a33339f-5397-401d-a28d-6e5db91ce69b | checkpoint | 2.1 - Concrete Mix Design (Stitch)
ce41a01d-1d29-54a5-bd9e-7703fe90fc34 | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3001 - PROPOSED ACCESS RAMP- GENERAL NOTES 3235599-SP03-ST-3002 - PROPOSED ACCESS RAMP- GENERAL NOTES- REINFORCED CONCRETE (SHEET1 OF 2) 3235599-SP03-ST-3003 - PROPOSED ACCESS RAMP- GENERAL NOTES- REINFORCED CONCRETE (SHEET2 OF 2) App 1C - 746-24-847-AC - Tech Spec - Geo & Struc
fa2be19a-330f-5be5-9ff4-dd4bd0c15796 | note | Construction Activity Description, Test Type and Acceptance Criteria - Concrete mix details shall be provided to the Engineer for review and approval. 50MPa @ 28 Day Compressive Strength. Maximum Water/Cement Ratio 0.43 (drawing/ notes state 40 Mpa but concrete increased to 50 Mpa mix to reach target strength quicker). Samples to be taken at 1, 2,3, 7 and 28 day strengths.
2a85c5c3-d447-5334-b99d-52208ca8a497 | note | Test Frequency - Once
9d1ad4ca-1149-53ba-8bd3-27128e0215e6 | note | QA Record - Mix Certificate Plant Certification InEight Reference Approval ..................
ca843e61-81eb-5569-a909-a7827e6b91f1 | note | DNZ Engineer - R
3bb1aaab-0889-5c89-93be-98707a6d5c5b | note | Engineers Rep - R
438bdc66-41e8-5fe7-9cbd-cdc613edd766 | note | Designer Rep - H
e93209f3-82b7-4840-8285-6dfe441bb3bd | signoff | AUTHORITY HOLDPOINT
ef955cae-e933-4e6c-95a3-5b091ea9b335 | checkpoint | 2.2 - Reinforcement (corbel steel and Stitch pour Steel)
4227ee25-355b-55d0-aa8a-b26957504a10 | note | Standard, Drawing or Specification Reference - IFC Reinforcement Detail Sheets
cc4dfb73-80de-5655-a482-889ff30c7eb5 | note | Construction Activity Description, Test Type and Acceptance Criteria - As per NTC 058 Installation of DH12 bars on precast edges to create corbels.. Grade 500. Also includes the structural steel required for the stitch pour.
03cfeca8-c5f3-50d2-9b7a-02334e9251bc | note | Test Frequency - Once
309da08f-ea6d-5a76-8769-76754ba392cb | note | QA Record - Mill Test Certificates Delivery Dockets InEight Reference ...................
f07942aa-2f3e-5040-b291-1130dd624a88 | note | DNZ Engineer - R
2f039824-6944-50b4-9a52-0a1d2895174c | note | Engineers Rep - R
2d5c1e3a-50e6-5902-a606-d3e4da20e699 | note | Designer Rep - H
1c7a4811-981b-4aea-b2b0-6a777d39e5d7 | signoff | AUTHORITY HOLDPOINT
3fda90ad-3c87-4ee6-847f-7727a382b2df | checkpoint | 2.3 - Formwork
94179ac8-0458-56b3-95c1-192afc479ed3 | note | Standard, Drawing or Specification Reference - Material Data Sheet Temporary works drawings Piers 1 and 2.
0f913cdd-f95d-5fab-8cd8-08357b043153 | note | Construction Activity Description, Test Type and Acceptance Criteria - Formwork of choice from sub-contractor, Standard panels up to 900mm wide modules Rigid hollow-section steel frame High-grade hot dip galvanising for durability & long life Gang forms and lifting applications available Full range of safety features High Quality plywood 60kN/m2 permissible fresh concrete pressure To be captured on temp works drawings. Inclusive of structural shore loading for super structure
b4c83b0e-a5d5-59c1-a31b-da527fc7c7a3 | note | Test Frequency - Once
99b7b328-9993-59c6-9c38-d485cabc84e2 | note | QA Record - MDS
a67d284d-6a71-56af-acf2-1b771fba0490 | note | DNZ Engineer - H
658d8c93-1811-5ffe-85d0-033927d3cd50 | note | Engineers Rep - R
fb78b910-cc2a-5673-a69e-ee74e7a33c4a | note | Designer Rep - R
2f696197-0cbd-4579-be98-b48a220ea4ea | signoff | AUTHORITY HOLDPOINT
fa92990d-e240-478a-a47e-fe4060c97ae5 | checkpoint | 2.4 - Formwork Curing Agent
440ddc60-dfab-5fcb-8ed1-a1bd453de93d | note | Standard, Drawing or Specification Reference - Material Data Sheet
5e7fbef2-0fb0-5087-840e-35b823c2c824 | note | Construction Activity Description, Test Type and Acceptance Criteria - Chemical curing agent.
bd739937-0c70-58bc-bc17-e4d687ef7f7a | note | Test Frequency - Once
7f2f9afa-5b7d-5733-bc34-47b4ab505193 | note | QA Record - MDS
79a955fa-837e-5a37-b5d9-d3cc4a7ab637 | note | DNZ Engineer - R
0cf3d6b6-ab6c-5e6a-89ab-c6d299441c7c | note | Engineers Rep - R
4329cb25-698d-5a94-a2b4-9faf3a1768c8 | note | Designer Rep - R
4d9c47b8-0520-4aac-a993-0800fe76bb49 | checkpoint | 2.5 - Installation - Lift Plan
275a3812-87b3-5ecc-b8fc-b4fe67b55f31 | note | Standard, Drawing or Specification Reference - DNZ Lift Plan for GMK 300 L
a8ce9070-c5c2-5d9a-842a-a1beda3c8c8f | note | Construction Activity Description, Test Type and Acceptance Criteria - Lifting plan for the installation of the pre cast cantilever deck.
66f4448e-899a-5e17-9d35-d0cc296c3f2e | note | Test Frequency - Once
cf829517-3967-523f-b33e-9fd56d475fe3 | note | QA Record - Lift Design Approval
75f1f3fb-085e-5a6a-a349-03714dc12b5f | note | DNZ Engineer - H
4caf6a97-4ae9-5172-9768-a8a82431f6de | note | Engineers Rep - R
88462d04-9e91-57a8-ae99-38d8fa03e414 | note | Designer Rep - R
2ddd28a5-8e71-4860-bbbe-5319644feebd | signoff | AUTHORITY HOLDPOINT
2b8938a9-fc7c-4dad-9009-605853f508a6 | checkpoint | 2.6 - Epoxy for corbel Installation
05771cb3-bf40-5218-a853-dbad4ef68036 | note | Standard, Drawing or Specification Reference - As per NTC 058
e4b4c3da-c6b5-5dc7-980b-c936b9dd1510 | note | Construction Activity Description, Test Type and Acceptance Criteria - R12 bars to be installed and epoxied into place using C8 epoxy. Requires designer approval.
c10119a6-18fd-5528-ab16-73d2d5df3685 | note | Test Frequency - Once
a0a75e52-eb85-536a-ac47-161de4f332ec | note | QA Record - MDS In Eight Reference ….........
15c4c6a4-988e-5532-b24a-a279245e76c2 | note | DNZ Engineer - H
1a2c670d-54bb-53d1-b63c-09981e9239be | note | Engineers Rep - R
187324f4-cef6-5a03-affa-8c428db2372c | note | Designer Rep - R
7fb36fc3-32ea-437b-9ef1-d1d470710aa4 | signoff | AUTHORITY HOLDPOINT
a3536469-9197-4eb0-9cd8-cb8d6132e656 | checkpoint | 2.7 - Concrete Bags
4d193c25-dee5-5376-9889-8b2b5402dc1c | note | Standard, Drawing or Specification Reference - MDS
061b9561-f29a-55b4-a49f-0964b626b812 | note | Construction Activity Description, Test Type and Acceptance Criteria - 40Mpa Concrete Dricon High Strength Handicrete or similar approved product.
137bd6b9-7ff2-589a-a2bf-7616d076ff3d | note | Test Frequency - Once
f6d0e5c4-907d-5295-96f9-2689eb77a08e | note | QA Record - MDS
ed049e54-a30f-5f57-ab73-8199b6ea8c8a | note | DNZ Engineer - H
6765f1b9-c86d-5126-b297-cae81eab2def | note | Engineers Rep - R
a5200932-18d2-5edb-b67c-ce302c74a3a2 | note | Designer Rep - R
41e0661a-f044-4034-867d-f0ddcbd1af17 | signoff | AUTHORITY HOLDPOINT
1107c170-6062-43df-9f93-789184fd207d | checkpoint | 2.8 - Column and Headstock ITP Sign Off
4d67b637-8fdc-52f5-8d93-f57547d9bdba | note | Standard, Drawing or Specification Reference - Signed ITP
9878162d-f421-5946-b206-99b2fc155654 | note | Construction Activity Description, Test Type and Acceptance Criteria - Sign off of Column and headstock construction
41c19f02-1e85-5d1f-b56d-d0d3597431f8 | note | Test Frequency - Once
143382a5-29b1-5add-b2b8-eb66d991c841 | note | QA Record - Signed ITP
5065eb3b-0fad-5b47-8e76-9d57372f6384 | note | DNZ Engineer - H
cee00f7a-ae43-5d80-9964-d60920cc93d0 | note | Engineers Rep - R
3eb0bd4c-e777-5f09-b086-ee1d7f0b2f0c | note | Designer Rep - R
19cf7bfb-c0cb-4c4c-a2e3-4afce6cfd6f3 | signoff | AUTHORITY HOLDPOINT
8728d27d-20a5-4e8b-965b-7a5f654c4b2d | checkpoint | 2.9 - Structural Steel Deck Installation ITP Sign Off
5d51948e-c57f-5071-90b6-179003338210 | note | Standard, Drawing or Specification Reference - Signed ITP
e0da5703-c87f-5805-9feb-cd274922b54e | note | Construction Activity Description, Test Type and Acceptance Criteria - Required before pouring of concrete stitch pour.
b76b3292-70e1-5b78-b0ad-f4541608a16d | note | Test Frequency - Once
0e18fce5-f130-5626-9b54-c59683382fdf | note | QA Record - Signed ITP
6572dbaa-4d35-5868-bcdf-7b56016d5bd5 | note | DNZ Engineer - H
030ddef1-6abb-5399-8204-9b238114dd73 | note | Engineers Rep - R
674f8402-ddfe-58c2-85fc-d1561023e135 | note | Designer Rep - R
99377da1-ca22-434c-a35d-6dfdefea00ac | signoff | AUTHORITY HOLDPOINT
cbd8c142-ba68-4dfd-8366-aaaacad9a5e3 | section | 3 - CONSTRUCTION ACTIVITIES
d2b50b38-5f3c-461c-82ab-c41c6092e110 | checkpoint | 3.1 - Setout
a9c7eac3-a03e-5593-9672-0d94a6bbd1cc | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3100 3235599-SP03-ST-3150 3235599-SP03-ST-3202
236a776f-046b-5a38-97d7-d6fb38568cb5 | note | Construction Activity Description, Test Type and Acceptance Criteria - Before commencing formwork installation, survey set out top of cantilever position based on drawings with RL supplied. Tolerances for insitu concrete pour taken from NZS 3109 table 5.2. Required to check and confirm that the position of the slab has the correct clearance from the bridge structure of 160mm and that the Macalloy bars are installed per the correct place.
fbfe5b77-f1ea-5a57-85fc-caca5d9993cc | note | Test Frequency - Once
0b52eeed-cf16-59a2-bfd5-5df94f11f0f6 | note | QA Record - As-Built
5cff71fa-d846-5bd7-ac36-b6b00394e3ad | note | DNZ Engineer - H
8d01d09c-6191-5740-be40-e5a0ad2c4ad0 | note | Designer Rep - R
6bdce50e-194e-4e6f-885c-854a04de4e52 | signoff | AUTHORITY HOLDPOINT
c2495761-f720-43b9-b8d0-e19ea309b73c | checkpoint | 3.2 - Type B Construction Joint Corbels
d35a89e0-d002-56e2-8ccc-392d2eee0c12 | note | Standard, Drawing or Specification Reference - As per CAN 69
98ea79ad-328e-57b5-877f-57b8280d1480 | note | Construction Activity Description, Test Type and Acceptance Criteria - As per CAN 069 Type B construction joint to be formed on the vertical faces of the corbels to ensure connection when concrete poured.
ea5c86f7-e55b-5d0a-b7e1-a499c5ecf55c | note | Test Frequency - Each Corbel
8d180875-5243-5e13-aed8-72b55bf40daf | note | QA Record - Photos
4edb3cb9-fe7f-50d0-b89c-91d783dbb20c | note | DNZ Engineer - H
2cbdfcfd-1a4b-590d-8560-e31b5336eabb | note | Designer Rep - R
00e72c10-9268-4114-a4d8-dd4ba2031d86 | signoff | AUTHORITY HOLDPOINT
a7d44cdd-796f-4bcc-bb9c-bb002907c15e | checkpoint | 3.3 - Formwork Installation
d31cbc81-5423-5382-a489-552cb62d962d | note | Standard, Drawing or Specification Reference - Material Data Sheet Temporary works drawings Piers 1 and 2.
8635a380-a246-567a-9870-9e23e2d09835 | note | Construction Activity Description, Test Type and Acceptance Criteria - As per Temporary works drawings for Piers Stitch Pour.
45f6ed27-abca-5d6e-9473-24e256203642 | note | Test Frequency - Once
89282a6d-2b32-5292-9f17-4507c937fdcd | note | QA Record - Photos plus signed off temporary works inspection of shuttering and formwork.
ff6757bb-cb49-5222-9910-0c07efa39024 | note | DNZ Engineer - H
cb327aab-1b38-5000-8ed0-d5f0bfad0516 | note | Designer Rep - R
87aa8345-d5fd-42a4-8e0d-c5cfa70eda31 | signoff | AUTHORITY HOLDPOINT
c009748a-a601-40c3-bce6-399502ddcf74 | checkpoint | 3.4 - Steel Installation for Corbel
5cd532fa-d6f6-5f2b-a1ab-c648136908cb | note | Standard, Drawing or Specification Reference - As per NTC 058
c6657707-3ae2-5c2b-9310-ad103b528b49 | note | Construction Activity Description, Test Type and Acceptance Criteria - R12 U bars to be installed within concrete corbel as per NTC 058. 40mm cover to be obtained surrounding steel. All bars must be epoxied into place with visual evidence to support that approved epoxy has been installed. Epoxy to be installed as per manufacturers installation instructions. Refer to CAN 069
ec5a91c5-7867-5ef8-80ff-ebdb3fdedbda | note | Test Frequency - Once
384cb529-84bb-5a67-9124-9bd6647daa12 | note | QA Record - Photos
0a63e900-20a6-59c9-93d1-8be3aa5d9385 | note | DNZ Engineer - H
63240852-5d5c-51d4-afe2-1472f23ee1b8 | note | Designer Rep - R
fc7c440d-e65b-4e23-8abf-39a970783e48 | signoff | AUTHORITY HOLDPOINT
d489ce1d-78fc-42d2-93f2-cba087a6dc8f | checkpoint | 3.5 - Concrete Corbel Pre-Pour Inspection
eb7b8ddf-c347-5683-af71-dc5fa1d9500f | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3200 - PROPOSED ACCESS RAMP- EXISTING PIER 1 DETAILS 3235599-SP03-ST-3201 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS 3235599-SP03-ST-3202 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS App 1C - 746-24-847-AC - Tech Spec - Geo & Struc
c8ee515b-06d7-5b88-bf1c-114a4c79ddf2 | note | Construction Activity Description, Test Type and Acceptance Criteria - Reinforcing installed as per NTC 058. Correct number of bars and grade. Correct steel lapping. Minimum 40mm cover achieved. 40Mpa Bagged Concrete to achieve 28 Days Compressive Strength. Mixing as per manufactures guidelines. Refer to CAN 069
f60f6179-a45f-551f-917a-e2b44a65ab1e | note | Test Frequency - Once
1e157b6f-38b8-57ff-bda5-3660468c367d | note | QA Record - Survey Check Structural Engineer Inspection MSQA SVR Pre-Pour Checklist Photos
7c679f3d-2712-542c-a3e1-9ea2ce665987 | note | DNZ Engineer - I
6f6b62e8-a5b1-50cc-ad92-5f4e10afde3b | note | Designer Rep - H
4bf941d5-7101-4985-8a41-298ae9d2419f | signoff | AUTHORITY HOLDPOINT
d81cddcd-5b07-4317-8b32-f2742ad4505e | checkpoint | 3.6 - Corbel Concrete Pour
ce37f4ac-0012-5e60-be2d-818a8ddd334f | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3200 - PROPOSED ACCESS RAMP- EXISTING PIER 1 DETAILS 3235599-SP03-ST-3201 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS 3235599-SP03-ST-3202 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS App 1C - 746-24-847-AC - Tech Spec - Geo & Struc
a3b483c1-81b1-597e-96f5-11a8578ec775 | note | Construction Activity Description, Test Type and Acceptance Criteria - Minimum 40mm cover achieved. 40Mpa Bagged Concrete to achieve 28 Days Compressive Strength. Mixing as per manufactures guidelines.
7c8e95b6-280c-581b-b004-051d5ab1dadb | note | Test Frequency - Once
ff091e83-ae86-55fd-a893-c6a07f6b707a | note | QA Record - Survey Check Pre-Pour Checklist Photos
b94375bf-ddb2-55b6-b2ef-ac1bd89731c2 | note | DNZ Engineer - H
ff40492d-8c31-590e-8281-22ad5bf6d260 | note | Designer Rep - W
7b035416-3a34-4583-adeb-75a34c9bd523 | signoff | AUTHORITY HOLDPOINT
14c2d337-70f5-43f9-91c2-04d728f524a1 | checkpoint | 3.7 - Concrete Stitch Pre-Pour
b8b38831-0a9c-542a-8de7-19f4d57c4929 | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3200 - PROPOSED ACCESS RAMP- EXISTING PIER 1 DETAILS 3235599-SP03-ST-3201 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS 3235599-SP03-ST-3202 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS App 1C - 746-24-847-AC - Tech Spec - Geo & Struc
f17aee92-bde9-5fe9-affc-26d63879900b | note | Construction Activity Description, Test Type and Acceptance Criteria - Reinforcing installed as per IFC drawings. Minimum cover 50mm.
ecec0c67-5ea7-529d-ba2f-70f681c12ce6 | note | Test Frequency - Once
9b589c8e-66ca-5c14-9f0d-b581c200e7d3 | note | QA Record - Survey Check Structural Engineer Inspection MSQA SVR Pre-Pour Checklist Photos
7d189c7a-d746-5d13-a937-6b7cb580ebce | note | DNZ Engineer - I
4a617a3a-c5e5-565d-86f0-3063ea4da7dc | note | Designer Rep - H
669c841b-9fec-47cd-ae1d-5ea3108d0b64 | signoff | AUTHORITY HOLDPOINT
26b12a84-a70d-4c53-8082-bcf9a6494f66 | checkpoint | 3.8 - Concrete Stitch Pour
993c9f4e-3530-57a6-9d73-fc96811a586c | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3200 - PROPOSED ACCESS RAMP- EXISTING PIER 1 DETAILS 3235599-SP03-ST-3201 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS 3235599-SP03-ST-3202 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS App 1C - 746-24-847-AC - Tech Spec - Geo & Struc
7eaccbee-3d44-5da1-89eb-7cf022e50fe8 | note | Construction Activity Description, Test Type and Acceptance Criteria - Concrete: 50MPa - Self Compacting Concrete Cylinder test taken at supply Yard only. Spread Test to be completed on site prior to concrete pour. Target Spread Test - 680mm +/- 60mm
e672f2ef-dd89-5a08-9b32-3858da0a4cfa | note | Test Frequency - Once
deec5cd8-3cb5-5972-b19b-d94c0b1b6394 | note | QA Record - Delivery Dockets Compressive Test Results Photos
5146cc8d-c413-5946-8811-5d7480163ceb | note | DNZ Engineer - H
7106bba3-06ea-53fd-b163-0d1c2358bab6 | note | Designer Rep - W
bf89cd1a-7d19-4749-b9df-844f0ade89bd | signoff | AUTHORITY HOLDPOINT
db568c68-62a9-4420-b89d-d170938a7055 | checkpoint | 3.9 - Surface Finish/Construction Joint
3bfabd40-ef13-5501-a33f-0ebe4c5b7883 | note | Standard, Drawing or Specification Reference - App 1C - 746-24-847-AC - Tech Spec - Geo & Struc 3235599-SP03-ST-3003 NZS 3114
596d4612-3fd4-52a4-8c7a-3e3a176631e7 | note | Construction Activity Description, Test Type and Acceptance Criteria - F1 Surface Finish - Concealed Formed faces F5 Surface Finish - Exposed and Visible Faces Type B Construction Joint to be used between insitu and pre-cast deck placement, as well as headstock placement on existing column. Insitu Concrete Stich Pour on Pier 1 - surface to have U2 broomed finish for slip resistance in both rain and dry as per NZBC D1 requirements.
6e6d315a-a96d-52c1-afc4-b88eee63c22c | note | Test Frequency - Once
2358a793-55fb-58d7-93f0-30f6d7531ea2 | note | QA Record - Visual Inspection Photos
59676c1e-239f-5a85-b661-ec73d0f09028 | note | DNZ Engineer - H
d656116a-951a-5705-b000-aab8c1cf0424 | note | Designer Rep - I
aa8dd9b4-85dd-4168-be5d-5f5e0c38a08a | signoff | AUTHORITY HOLDPOINT
f79818af-5318-4de3-af45-cfb99544e2fe | checkpoint | 3.10 - Concrete Curing
a7dd6f17-fd44-5486-b9f4-071d92a1bd37 | note | Standard, Drawing or Specification Reference - App 1C - 746-24-847-AC - Tech Spec - Geo & Struc 3235599-SP03-ST-3200
d2e74d2a-2f9d-5a3e-b947-dd71ecd226d9 | note | Construction Activity Description, Test Type and Acceptance Criteria - Concrete to be cured for a minimum of 3 days as per drawing ST-3200, curing methodology will be formwork curing. Cylinder to be taken at 3 days to verify strength of 30 Mpa has been achieved prior to stripping of formwork.
55d0be14-e348-5632-b2c7-0a6ee40a1f79 | note | Test Frequency - Once
1eb86b63-8e0f-5414-9b19-ad368e9463a6 | note | QA Record - Concrete strength results, concrete pour checksheet notifying date of formwork striking.
e38ce7be-b2ea-5974-b5fd-5d20e5c2c0c3 | note | DNZ Engineer - H
8223f2a0-47f3-5df7-9ed9-1e792938a1fc | note | Designer Rep - R
88c92118-95c7-40e0-a259-fba53811f06d | signoff | AUTHORITY HOLDPOINT
b265e1a3-1d69-4089-bc2c-b18b148feeac | checkpoint | 3.11 - Post Pour Inspection
986a5eeb-4dde-5160-86cb-8afae2ff470d | note | Standard, Drawing or Specification Reference - App 1C - 746-24-847-AC - Tech Spec - Geo & Struc 3235599-SP03-ST-3003 NZS 3114
2b460127-8c30-5c7f-b6a4-47234171b6b8 | note | Construction Activity Description, Test Type and Acceptance Criteria - Joint inspection be undertaken with designer to inspect shutters of structure following removal of shutters and survey/ check dimension of structure have achieved stipulated tolerances stated in drawing suite and NZS 3109
bc34861f-3905-57bc-8b5b-83a241e88292 | note | Test Frequency - Once
6f8aef96-fda1-560f-8d4e-7bcc1b5647e2 | note | QA Record - Visual Inspection Photos
780e9cdd-a359-53aa-acf8-53d1f1e39df6 | note | DNZ Engineer - H
ff755470-a00a-5d1f-99b0-9335b01b60dd | note | Designer Rep - W
ca584731-9d93-478d-97ec-2ace25f292b8 | signoff | AUTHORITY HOLDPOINT
4016ea0d-8577-4381-ad5b-8cd34c3a3d02 | section | 4 - FINAL RECORDS
c06de116-fb24-425a-9c6a-cec0d7502da4 | checkpoint | 4.1 - As-Built
23a7fc63-1114-5ef0-8c9e-57e840ead81c | note | Standard, Drawing or Specification Reference - N/A
5ebdcb9f-318f-5ed0-8df2-81b138ab1750 | note | Construction Activity Description, Test Type and Acceptance Criteria - Installed as per design drawings. All compliance recorded CAD files
66cd7c40-620c-5511-b01a-1d2c4f5c707b | note | Test Frequency - Once
8187ac69-39df-5d73-b90b-f878df564ceb | note | QA Record - As-Built
2d47abc9-a9e5-53af-ad51-0528cc11ea0d | note | DNZ Engineer - H
1becbd7f-3ce3-529f-a528-2c4c6b511122 | note | Designer Rep - R
bbb26e4e-c6ca-49e3-aed4-459cdbd6fe4e | signoff | AUTHORITY HOLDPOINT
250e2c86-7ae1-4728-b2c9-d180de148ea8 | checkpoint | 4.2 - Redline Mark-Up
e33d22bf-b74c-5996-840a-03d36ed87ec9 | note | Standard, Drawing or Specification Reference - IFC Drawings
9fcc57d2-cfff-57a5-a6d9-623836828fa5 | note | Construction Activity Description, Test Type and Acceptance Criteria - IFC Drawings marked up and signed.
df3b4901-65e3-5265-8313-a1bc3fc8f3bf | note | Test Frequency - Once
167561e8-1924-5f50-9224-f69b54ac36c3 | note | QA Record - IFC Drawings Mark-Up
3a870be2-9df3-5eeb-9149-9f97a49922b3 | note | DNZ Engineer - H
9966e5d7-747c-5945-9d13-b2c4a8a02c81 | note | Designer Rep - R
2d4c214e-1dc8-4d92-92a8-44ee648a0c97 | signoff | AUTHORITY HOLDPOINT
f3dc0945-47b1-4884-a64a-9edc2fc180d8 | checkpoint | 4.3 - Non-conformances
8d46e358-551f-5539-8f00-1f77d61631d3 | note | Standard, Drawing or Specification Reference - DN1212-DOW-PLA-PM-0005 QMP
8b233f2d-5b59-54bb-8806-17c838bef192 | note | Construction Activity Description, Test Type and Acceptance Criteria - Non-conformances reports to be raised when specification not met. All non-conformances within the area under review need to be listed on the NCR report. NCR Reference …..................
3a737c51-ff5c-5212-9de5-12f76ae6707d | note | Test Frequency - Each NCR
044aaaa5-e46c-5cc0-bd90-ae3897010435 | note | QA Record - NCR forms on InEight
a50fd145-720b-5ccf-a3eb-9c493bdd0565 | note | DNZ Engineer - H
d157479f-38d7-5e37-9435-5b5a9306b8de | note | Engineers Rep - R
a31a677d-0c6d-5e54-8271-4f0b7136a894 | note | Designer Rep - R
557c6f09-9a47-499a-842d-759c4bb7c78a | signoff | AUTHORITY HOLDPOINT
2f048047-8e98-42d6-8464-ba59041ec98a | section | ITP APPROVAL PROCESS
10bb89ed-69c4-4b17-935e-52c3f4c3a577 | checkpoint-no-value | ITP APPROVAL PROCESS
631dfd76-85eb-5cc8-889c-58675c3f6016 | note | Prepared By: Project Engineer - Grant Wallace
25dac62f-a3a1-598c-aafb-8520dc6ae402 | note | Reviewed By: Project Manager - Dan Trotman
31898f78-c135-5d85-9241-21d28fbed18b | note | Reviewed by: Quality Eng./Mgr. - Nas Matar
c77634a8-7bbb-5428-a3fa-f5de76d4ee5a | note | Reviewed By: Design Engineer - Daniel Cvitanich
5135410b-eb6e-5c4a-9bb9-d94d301e2594 | note | Reviewed By: AT Project Manager - Werner Nel
4a0be5ab-5f5f-5b62-8b8b-9134868c3731 | note | Reviewed By: AT Engineer to Contract - Mike Robertson
9f78ff98-d69f-5c97-87c3-7c78033a4d35 | date | Date:
abf8ac0a-3870-48bb-a9ef-d103a4e4ad8f | section | FINAL ITP CLOSE-OUT
8d7401ef-ac11-4a21-8cb5-ca4cef183095 | checkpoint | FINAL ITP CLOSE-OUT
3f9308c8-2f00-5920-8913-ffed1641a4e7 | textbox | Downer Project/Site Engineer:
29776e0f-8e6b-57ae-9e46-47f5d45567fa | textbox | QA Mgr./Engineer:
380e2c58-e1ec-5b36-8334-3fe472c27e2f | textbox | Designers Rep(Assistant):
2c2ae3c3-9b90-561d-ae64-2fcf14fb5244 | date | Date:
bfd0c69b-a1ff-49ab-b0bb-6ff44353db78 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
7efba689-3741-529f-9c05-aabb999bcaf1 | textbox | Contractor's Rep Name:
6a1c4e1d-77ce-56a9-82d3-5353a4449df2 | textbox | Engineer's Rep. Name:
669c9a22-da42-5ad9-97bd-33f7681fa5d2 | date | Date:
aa2b5043-46e4-4dfa-b8a8-14b54892b03e | signoff | Add Signature
e2847dac-2e16-4b76-9739-fca394b5995d | checklist | DN1212-ITP-015 Bearing Pad Grouting Rev1 | itp | DN1212-ITP-015 Bearing Pad Grouting
00974ef8-82af-440a-a8b8-db3c4569dc22 | section | 1 - PRELIMINARY AND GENERAL
817ad10a-383c-4088-bbcf-05aef5741d2b | checkpoint | 1.1 - Method Statement Development & Safety Analysis
384fb9d7-b3a5-5794-96ec-832b47634489 | note | Standard, Drawing or Specification Reference - The Downer Standards (TDS)
0f7f1c80-00f6-5f16-98a7-b79f91bb580a | note | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction: document review.
20fb24ce-e8b9-581a-859b-c3506f4d8e5b | note | Test Frequency - Once
e7ff4040-9ed8-5811-8e07-5017c46878ce | note | QA Record - Method Statement & JSEA Completed & signed by relevant authority
add5f49a-d04a-525b-9575-b7f93aff7204 | note | DNZ Engineer - H
49c946ac-cffb-52f1-8e72-a10eac87a691 | note | Engineers Rep - R
42e10f22-6d75-5a9b-99e6-ee385eea81d5 | note | Designer Rep - R
a8d43266-00d7-4dc8-8776-0b56c3554a58 | signoff | AUTHORITY HOLDPOINT
52111b7f-01c2-4595-bf17-9e2baa78b0ed | checkpoint | 1.2 - Confirmation of superstructure position.
28d77441-ee64-54a7-b8e8-f4526ea35303 | note | Standard, Drawing or Specification Reference - Signed ITP
944ddb3a-6008-5c6e-a6cb-4bd5710b57aa | note | Construction Activity Description, Test Type and Acceptance Criteria - Signed ITP required for the position of the superstructure before grouting.
eb603e49-694a-5db4-aea9-3ee2470ff946 | note | Test Frequency - Once
67c5ac48-e2bf-5ff0-a661-7c00d3a33ca0 | note | QA Record - Signed ITP
a352a899-5159-537f-8599-5fd6eb196d27 | note | DNZ Engineer - I
bdc22b8a-f783-5d94-953e-0a0608cc9a47 | note | Engineers Rep - W
dccca2eb-340f-573f-8907-7fa1cfdade87 | note | Designer Rep - H
415469a0-adc1-4b58-9efb-56861268dfb4 | signoff | AUTHORITY HOLDPOINT
8795ea2d-5c1e-4548-8f57-9ccbaec566e6 | section | 2 - MATERIAL APPROVALS
661c70f3-8497-41b4-ae6c-018dd1a49a22 | checkpoint | 2.1 - Non Shrink Grout Approval
cec40710-ed6e-528d-b610-d1bfed2c25bf | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3200 - PROPOSED ACCESS RAMP- EXISTING PIER 1 DETAILS
1ab9e973-e873-546b-ae18-7a2c09574026 | note | ○ 3235599-SP03-ST-3201 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS
dbb12f1b-a514-576d-b079-4dce8314154b | note | ○ 3235599-SP03-ST-3202 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS
41b1228a-8446-5ea9-8ffc-f3c6b9609203 | note | ○ 3235599-SP03-ST-3250 - PROPOSED ACCESS RAMP- ABUTMENT DETAILS- SHEET1
4efc32f4-8a3b-521e-8267-41240b7056a7 | note | ○ 3235599-SP03-ST-3252 - PROPOSED ACCESS RAMP- ABUTMENT BEARING
eb75c1d0-f11d-598a-bc0c-1ca0d496b161 | note | ○ App 1C - 746-24-847-AC - Tech Spec - Geo & Struc
1bd61474-a140-539d-8c38-4be7d92fd6e0 | note | ○ Spec - C0602.10.04
f63bc403-df23-529e-8f8a-6d8cb8140ca0 | note | Construction Activity Description, Test Type and Acceptance Criteria - Non shrink grout - sika 212 HP to be submitted to designer for review and approval as it obtains 85 Mpa after 28 Days > 50 Mpa as per 3252 - Note 1.4
37b9276e-939b-5ad4-8d55-51e4872619d8 | note | Test Frequency - Once
5da8c3c0-04be-5461-a54d-d646c3c2af75 | textbox | QA Record - MDS, In Eight Ref
abdcc36d-8a31-5e26-a30e-4aaa2c232c74 | note | DNZ Engineer - R
250ddd30-f6be-537b-8714-57c969cf46ea | note | Engineers Rep - R
5c1fd2a8-a7a6-5867-a8e1-f01ec4b8963a | note | Designer Rep - H
578974fd-58e2-44b4-af8d-da31eddf35ae | signoff | AUTHORITY HOLDPOINT
69fd9993-b534-4b23-a9d6-b4e60f499905 | checkpoint | 2.2 - Glass Plate Trial
7ca436ad-85ad-568f-9393-084684300992 | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3252 - PROPOSED ACCESS RAMP- ABUTMENT BEARING - Note
e453cb08-d7f9-5ac9-ab16-532823bd9ec2 | note | Construction Activity Description, Test Type and Acceptance Criteria - As per 3235599-SP03-ST-3252 - PROPOSED ACCESS RAMP- ABUTMENT BEARING - Note 1.4. Glass Plate trial to be undertaken to replicate bearing pad footprint of 230mm x 230mm x 20mm. Area is to be poured prior to installation of bearing grout to confirm voiding is less than 10% of area. Undertaken with MSQA observations
7bb1fb67-6529-5504-96af-25501bcc3b88 | note | ○ Methodology to be submitted prior to commencement..
84ff1aab-ea97-5ff1-9f5f-fa9e0557bc98 | note | Test Frequency - Once
df06e7ae-743f-594b-b0f7-7d78e02a4594 | note | QA Record - Site Observation Report, Written acceptance of material following trial.
2eca6dd7-ddab-5002-820d-e947c5f8ea81 | note | DNZ Engineer - I
ae6605d1-5b4e-58c1-96ac-75aac1275271 | note | Engineers Rep - R
34115055-710f-5cb0-acb3-b7035704df18 | note | Designer Rep - H
ad77839c-1f4a-47de-81db-49dee4b1c3ff | signoff | AUTHORITY HOLDPOINT
b2d03253-3f9b-41dd-8168-7aaf484e5979 | checkpoint | 2.3 - Curing Method
f69dc58a-e122-548c-89f6-9d24825052a9 | note | Standard, Drawing or Specification Reference - App 1C - 746-24-847-AC - Tech Spec - Geo & Struc
6ffd759a-ca0a-538b-bf71-0d60dace8283 | note | Construction Activity Description, Test Type and Acceptance Criteria - According to MDS sheet for Sika 212 HP, See below, grout to be sealed with timber shutter, left to cure within small shutter and then treated with Sika Anti Sol as per data sheet attached..
65c3017b-5c99-59bf-b2ca-bbc2a0e92d40 | note | Curing Treatment
b40f408b-a78b-54cc-88c1-e8236129c768 | note | ○ Formwork should be left in place for at least 5 days if possible, to prevent moisture evaporation and provide restraint to early age hardened expansion. Once formwork is removed a suitable curing membrane such as Sika Antisol should be applied to any exposed faces. Refer to separate data sheet for further information.
12159ebd-5cf9-5a2c-ba69-0d0ab0fcd661 | note | Test Frequency - Once
07731380-4944-5299-aea5-918e3149112b | note | QA Record - MDS, Photos
5dd50b51-e2dd-5041-b063-0ca764c45496 | note | DNZ Engineer - R
f5707a3b-07e0-5465-b5c5-24226e22bfde | note | Engineers Rep - R
a5f2f1af-d320-5062-a57a-cc4f9e3ac9ab | note | Designer Rep - R
39969b40-0bd8-4eb5-8d30-a6175aa13b43 | section | 3 - CONSTRUCTION ACTIVITIES
4cd72482-e644-4041-b49a-61230604dbee | checkpoint | 3.1 - Construction Joint
8b43daca-67ac-5822-8e2c-66dbc30f2ec2 | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3252 - PROPOSED ACCESS RAMP- ABUTMENT BEARING
9660ab5d-0185-5858-a990-234c5d567a2c | note | Construction Activity Description, Test Type and Acceptance Criteria - Formation of construction joint required on top of pier / abutment to the construction joint must be visible.
148a4de6-f3e6-5ebc-86fd-d465686fef6c | note | Test Frequency - Once
aa93f3b6-6001-567c-8147-fd6101625449 | note | QA Record - Photos
a75fb62b-0f2b-5cbb-9485-7394455530aa | note | DNZ Engineer - H
387aa642-b6fe-5cd7-8713-3e986e279a67 | note | Engineers Rep - R
2a5d03ac-3049-5549-8aa0-e4c7ae09b18e | note | Designer Rep - I
079f3bd3-55d9-4c50-91b9-82cdb7a16ef0 | signoff | AUTHORITY HOLDPOINT
d65f5039-8ae9-40eb-84b5-dc9729217896 | checkpoint | 3.2 - Grouting Pre-Pour Inspection
0190b979-534e-5cf9-9d8e-47b34ecaf380 | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3202 - PROPOSED ACCESS RAMP- EXISTING PIER 2 DETAILS
fd4ee6f8-bf74-5ebe-90aa-5b0573c330f7 | note | ○ App 1C - 746-24-847-AC - Tech Spec - Geo & Struc
87dbcd58-41ab-5690-a6de-fa6cbe353280 | note | Construction Activity Description, Test Type and Acceptance Criteria - No reinforcing requirements.
6df35345-c13f-5070-8bbc-55499307ed8d | note | ○ Check to ensure that the surface is prepped, underside of bearing pad is in correct location prior to pouring. Nominal 20mm will be poured.
5fbb16c7-1bdb-5a4b-aa0d-aa36e8fa280b | note | Test Frequency - Each Structure
dea74761-a3d2-5167-8d00-8423a6c80ef5 | note | QA Record - MSQA SVR, Pre-Pour Checklist, Photos
02e38576-313d-584d-8219-51b7975a75be | note | DNZ Engineer - I
8cd12b32-9e0d-59e2-8e84-e934bb9ec2bc | note | Designer Rep - H
d3e49481-6269-40d3-82e6-98867a7777f0 | signoff | AUTHORITY HOLDPOINT
fa2dfe21-416e-4725-8465-464d3836c4f1 | checkpoint | 3.3 - Grouting Pour
f4bcf9e6-52e7-55db-b110-f42664d475fa | note | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3252 - PROPOSED ACCESS RAMP- ABUTMENT BEARING, NS 3109, AS1012, Spec - C0602.10.04
0ce8445b-a06a-522a-995c-3a0bb82f1c10 | note | Construction Activity Description, Test Type and Acceptance Criteria - Concrete to be poured as per manufacturers recommendations where 3.7 litres per bag.
6eb43f14-a4c8-5589-94dd-855a40107efb | note | ○ Samples to be taken from each batch using steel moulds where 1, 2, 3, 5, 14 and 28 day tests are to be taken to ensure that grout has reached necessary strength
24045e44-992f-58e4-9126-3d791f26481d | note | Mixing
badccc80-4c01-5c7e-bdd3-446ca7f5d283 | note | ○ Place about 70-80 % of the premeasured clean water (depending on consistency required - refer to "Mix Ratio") into a clean container and gradually add the whole bag of SikaGrout-212 HP into it while continuously mixing. Add the remaining water until the desired consistency is obtained. Mix for 3-5 minutes with a low speed drill (500 rpm max.). Allow to stand so any entrapped air can escape. Do not add more water to increase flow of the grout if a mix has stiffended due to time delays. If the ground is unworkable discard.
c825c92d-c14c-5723-be2b-57c2164a54a8 | note | Test Frequency - Once
99d7a7b0-3ecf-5499-8048-4dc7f307c030 | note | QA Record - Photos, Test Report for Compressive Strength
489f327c-9705-5508-bf88-9386989fec78 | note | DNZ Engineer - H
7898b6d9-aa98-5965-9fa6-af2828f33f00 | note | Engineers Rep - R
e6a972c8-e358-59df-8a2d-1f55cad50e41 | note | Designer Rep - R
e29a7755-1869-40b6-8875-44358d37165f | signoff | AUTHORITY HOLDPOINT
85ced097-0353-4c40-9a28-29a32152e8c6 | checkpoint | 3.4 - Post Pour Inspection
fe8bd781-bbe1-50b1-ac04-524f8478f9a3 | note | Standard, Drawing or Specification Reference - App 1C - 746-24-847-AC - Tech Spec - Geo & Struc 3235599-SP03-ST-3003, NZS 3114
661f3416-7b05-50ce-ac73-e8c8425ea49c | note | Construction Activity Description, Test Type and Acceptance Criteria - Joint inspection be undertaken with designer to inspect shutters of structure following removal of shutters and survey/ check dimension of structure have achieved stipulated tolerances stated in drawing suite and NZS 3109
d0d7b083-079b-5370-bb6e-d338b712f054 | note | Test Frequency - Once
7176ac58-2ef3-571c-9bde-cdceb2353c88 | note | QA Record - Visual Inspection, Photos
e7a059ff-32bf-5422-9318-dde7f6066546 | note | DNZ Engineer - H
7cf73002-416d-5677-8a66-d148d21237a1 | note | Engineers Rep - R
18f725ff-5af0-5428-8585-2c417e8428b3 | note | Designer Rep - W
ae509881-32b1-481d-b14b-b1f191131523 | signoff | AUTHORITY HOLDPOINT
564757de-a130-4199-9c9f-9663f6b9d922 | section | 4 - FINAL RECORDS
48b0efaf-4506-4daa-ad77-efd2e21006e8 | checkpoint | 4.1 - As-Built
b8479f3b-9871-5281-a26a-41353586caf0 | note | Standard, Drawing or Specification Reference - N/A
725d96b3-f340-52d3-8f4e-f0444a4d1de9 | note | Construction Activity Description, Test Type and Acceptance Criteria - Installed as per design drawings. All compliance recorded CAD files
743977cb-05a1-5077-85fd-845b06a603a5 | note | Test Frequency - Once
cda199fc-f2fe-50af-8946-4a79cb357048 | note | QA Record - As-Built
9b200996-d9ae-5a5b-98fc-8824eb81993b | note | DNZ Engineer - H
ca5c329d-7c09-5c5a-8c98-2de8a819f8e0 | note | Designer Rep - R
f3ad8a7a-490a-4fbe-9d05-27968eef9d41 | signoff | AUTHORITY HOLDPOINT
217fd13e-bea4-43e8-ae20-91c685d33f0a | checkpoint | 4.2 - Non-conformances
e3cfb5dc-7af1-5408-adda-1f46e2d4bab9 | note | Standard, Drawing or Specification Reference - DN1212-DOW-PLA-PM-0005 QMP
76d3f8dd-6b90-5a96-af78-6c57f3e48027 | note | Construction Activity Description, Test Type and Acceptance Criteria - Non-conformances reports to be raised when specification not met. All non-conformances within the area under review need to be listed on the NCR report.
0cf84f07-b4b3-5769-a58e-1b9bf337beb7 | textbox | NCR Reference
64275fd3-1833-5252-aa2d-d491c71b3b26 | note | Test Frequency - Each NCR
7459d00b-b63d-5430-a89a-e443e0ac00e1 | note | QA Record - NCR forms on InEight
979d6ddf-54a6-5e12-a2b1-493e43d27db9 | note | DNZ Engineer - H
fe97d31f-8adb-5f6c-ad6a-da938f33179f | note | Engineers Rep - R
160ffd50-166f-5487-8ac5-aeae81f466c1 | note | Designer Rep - R
aa52c2ba-fcd4-483e-ba18-d16a2c92fe43 | signoff | AUTHORITY HOLDPOINT
1a0460e3-5fd3-423d-b081-f421f43b8f85 | section | ITP APPROVAL PROCESS
c115ea9e-d95f-4cf9-ad62-94338aed0466 | checkpoint-no-value | ITP APPROVAL PROCESS
452168df-9ff7-571c-a76a-263c0a90206d | note | Prepared By: Project Engineer - Grant Wallace
1c9a0ce1-d32d-5998-94ac-88ab93459333 | note | Reviewed By: Project Manager - Dan Trotman
931cd12e-798a-5844-a272-8cf1632f30b9 | note | Reviewed by: Quality Eng./Mgr. - Nas Matar
2a8d2986-f004-535f-ac36-9d7b4ab17f8a | note | Reviewed By: Design Engineer - Daniel Cvitanich
19624113-34b4-5cc7-96ce-1c79007064a2 | note | Reviewed By: AT Project Manager - Werner Nel
3d76ffa8-4811-5f6b-9c63-c67ef2c14202 | note | Reviewed By: AT Engineer to Contract - Mike Robertson
4e1106cb-2857-5602-9313-3ceca52df675 | date | Date:
ce861bed-073b-4fbf-8cfd-dc78265eb14f | section | FINAL ITP CLOSE-OUT
d508cc09-13dc-4509-a8c4-b13a2915f0c5 | checkpoint | FINAL ITP CLOSE-OUT
da6415a1-d9e6-5a1c-a70f-77804a65be3b | textbox | Downer Project/Site Engineer:
0acc95df-0866-5204-bd9d-4c8a63414eef | textbox | QA Mgr./Engineer:
bd0898c3-c644-5a8d-b62d-97cb904c4d65 | textbox | Designers Rep(Assistant):
f8c97850-8f9e-5103-b5b7-8f9d1c19a9da | date | Date:
a1aef4f5-0388-413f-b6de-68dfb1c8265b | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
be09c2d8-89a1-572d-9677-ff2605fa9ba2 | textbox | Contractor's Rep Name:
75072ced-cc22-51f6-97a9-190564981caa | textbox | Engineer's Rep. Name:
f24d8cde-302b-52d4-8162-393ccde3c176 | date | Date:
67a958b3-c9ee-46a0-8b7d-b4020af268b0 | signoff | Add Signature
bc0b8541-2698-42b2-91a4-3960952cf8c2 | checklist | DN1212-ITP-016 Shop fabrication - Span 2 RevD | itp | DN1212-ITP-016 Shop fabrication - Span 2
0d8d19d7-abf1-489a-a705-3fa6b9d4edf8 | section | Engineering
b873b8cd-f988-4cd0-9dd2-47b338fbba98 | checkpoint | 1 - Inspection and Test Plan Reviewed and Approved by Customer
82f63c0f-03b5-571a-86c1-0ae2c41b2c4e | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
0de7f2d7-b4ee-527d-97c9-ffa3ab0b0680 | note | Acceptance Criteria - Inspection and Test plan shall be submitted to the Engineer for review and approval before fabrication is commenced.
45f1b03d-51b0-5cbe-88b7-daaf635fcfae | note | Certify Doc / Ref - IFC DWGs
96b2085d-1c02-58ef-9c23-da2a76d5a710 | note | PFS Engineering - PM/PE
d876ce8f-fc86-5616-b85e-c6d957c1fef9 | textbox | PFS Engineering: Sign - Initial: Sign:
40a91d16-0677-5af7-b33e-93a63942e68b | note | PFS Engineering: C - S
e32f63d0-6f03-506a-ba37-aeb9d440645c | note | Downer - Downer
03a1aafa-29d7-571b-8f87-fb975eaa664d | textbox | Downer: Sign - Initial: Sign:
155d2629-d84d-53ae-b67d-e72b60900a9e | note | Downer: C - H
04e3e312-a479-4507-abb4-8ccbfd15b25b | signoff | AUTHORITY HOLDPOINT
e197a0a2-a430-4381-a053-9ab38fc30bd2 | checkpoint | 2 - Shop Drawing approval
1c3cb241-173c-5cfe-a7b9-1efbdfd95e07 | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
06fc98fb-bccd-50f1-88e6-dfe36613685f | note | Acceptance Criteria - Shop Drawing shall be submitted to Engineer for review along with Shop Drawing Check form
cc81bd1b-afe4-5856-8a2a-930753465343 | note | Certify Doc / Ref - Shop Drawing Check form
3709cf98-2772-5e6f-873f-716d3b709819 | note | PFS Engineering - PM/PE
ba3534ae-d6e6-5109-9308-6aead51de04e | textbox | PFS Engineering: Sign - Initial: Sign:
241e124d-4d0a-520c-8ceb-95b141bd4109 | note | PFS Engineering: C - S
ba348bd1-211a-5684-a148-003087327dd7 | note | Downer - Downer
e8ce3a66-eca0-5167-90d2-53951831da08 | note | Downer: Sign - Initial: Sign:
ba8667f8-fd12-50df-a9e6-2bee49d749ed | note | Downer: C - H
c18e287a-7a40-4377-8145-7380e5a2e1ea | signoff | AUTHORITY HOLDPOINT
fd383576-9e5e-468a-90de-da7594943b63 | checkpoint | 3 - Submit Inspection personel competencies
1a4f0f37-2a4e-5460-b026-0adeab9ef596 | note | Specification Standard - Project Structure Specification C07 Rev. 01
d9a9b4d5-1ef3-50d6-89bd-5a2b2e64ef3b | note | Acceptance Criteria - Inspection personel (Independent inspectors) qualification and certificate shall be submitted to the Engineer for review and approval according to C0701.2.4
d732261c-e0f2-57d5-bb41-3bdf68a014ac | note | Certify Doc / Ref - NDT qualification
e4247490-030b-5b9f-b0ad-4e97214c77be | note | PFS Engineering - PM/PE
7935b888-7b3b-5bbc-982b-f2f149ad9992 | textbox | PFS Engineering: Sign - Initial: Sign:
ae659146-29d9-56c8-a036-2f7302963124 | note | PFS Engineering: C - S
52469621-39bb-5bda-9f69-750edd1ce866 | note | Downer - Downer
fcd7e602-8d73-5deb-8345-ccb02d777ffb | textbox | Downer: Sign - Initial: Sign:
b1b543ba-1bd9-5451-8b26-73854c556edf | note | Downer: C - H
a280f82c-c0f2-40cc-8d9d-90adff3a1a07 | signoff | AUTHORITY HOLDPOINT
3f97a8b9-3d78-4b36-a278-7b85cfcdbc38 | checkpoint | 4 - Welding Procedures - Structural
992f83fd-5ff6-5e6b-8a55-bb7021fe745d | note | Specification Standard - AS/NZS 1554.1:2014 Category SP
1e4d9a01-e932-5f59-b13e-9805f6edc1af | note | Acceptance Criteria - Details of the welding procedures to be used including details of the equipment and consumables before any welding is carried out. No welder shall carry out work for which he is not certified.
649115fa-1944-5192-afb3-bc90c46770c8 | note | Certify Doc / Ref - Welding Procedures HERA/CSWIP Stamp
b3d52771-772c-5ce3-bf8b-882f54bb8a24 | note | PFS Engineering - PM/PE
47b9bee7-46e7-5114-bae2-83d8c8f8c144 | textbox | PFS Engineering: Sign - Initial: Sign:
308fb22a-4571-52c0-b85a-57326496918c | note | PFS Engineering: C - S
a7f12340-8519-5e91-a5dd-3789cab7f9ec | note | Subcontracted scope - SQA
de815876-72ba-527e-93d0-a037e1726a74 | textbox | Subcontracted scope: Sign - Initial: Sign:
e2927499-2db3-5b3d-939b-a2619071ba7e | note | Subcontracted scope: C - RA
6da6ee9b-9e05-4d6e-a099-4e77824b2ba2 | checkpoint | 5 - Welder Qualifications - Structural
21e01a73-d6a0-5d12-ad2a-79d3fa78784e | note | Specification Standard - AS/NZS 1554.1:2014, ISO 9606-1:2017
64489f73-4308-5f77-b8bc-b2eb9a3da4ac | note | Acceptance Criteria - A list of proposed welders and their welding certificatesto be provided prior to any welding being carried out.
bfbf43cd-36cb-5ba1-9811-5551da025492 | note | ○ No welder shall carry out work for which he is not certified.
5577a9ec-b7bd-5d1f-af5b-bd044f7f4121 | note | Certify Doc / Ref - WQT by Authorised Person (Welding Supervisor)
32258e4a-13bf-515f-a899-d3c38be21a06 | note | PFS Engineering - PM/PE
73fd211d-140e-5000-b6f3-97ab4b9f63fd | textbox | PFS Engineering: Sign - Initial: Sign:
1799c0e4-7e57-5d47-b637-0b925cf826e4 | note | PFS Engineering: C - S
8a2f5140-4254-547e-996e-35c7aa7b1590 | note | Subcontracted scope - SQA
fe5a01b0-96c4-50f1-b944-da03e1ef26d5 | textbox | Subcontracted scope: Sign - Initial: Sign:
034c4810-b986-5020-87a3-f05d627a1da2 | note | Subcontracted scope: C - RA
a599034b-d036-4fec-be3d-6de708337e8c | checkpoint | 6 - Submit the required documents to Client for review
c2c1cfc1-4ff0-52aa-8af1-ab289d6aa59c | note | Specification Standard - Project Structure Specification C07 Rev. 01
866945cd-8588-5446-9351-bd9273d02dba | note | Acceptance Criteria - Following shall be submitted to the Engineer for review before fabrication is commenced:
c2988f30-9ae1-56ec-827a-00cf5fe10dc6 | note | 1 - Quality Management Plan
ab261eda-c0a1-50e5-81bd-a23ec3225859 | note | 2 - IMS Manual
e2f1aa92-b0df-55ea-b0a6-8fdc1c40ac3b | note | 3 - SFC Certificate
fd38283d-8240-5121-bbf7-95bf8d7fcee5 | note | 4 - ISO 9001 Certificate
54a13fc4-4fbc-5046-9139-ae62e46aafe1 | note | Certify Doc / Ref - Quality certificates, Quality Plan
ee111f5d-da5a-54a3-9674-4bfa12f64bc7 | note | PFS Engineering - PM/PE
07337deb-1499-5e83-9a88-5bc986ca3d1e | textbox | PFS Engineering: Sign - Initial: Sign:
bc40222b-9229-5f48-9640-464bccf35f11 | note | PFS Engineering: C - S
9bd923b0-434d-50be-a001-1ae78f4bc15a | note | Downer - Downer
737aacfd-6963-5e8a-94de-32593aae5fd7 | textbox | Downer: Sign - Initial: Sign:
7ecc5e6e-e92c-55a6-9dd4-6ee2c94ee5dd | note | Downer: C - R
43725b7c-98f2-414d-8aef-5378e50f1852 | section | Procurement
20a8529b-7944-4f1f-b3fd-35ac84f90316 | checkpoint | 7 - Procurement of materials in line with IFC drawings and Technical Specification
2ceb6a6f-0714-5042-bb93-8ea5252a0480 | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
378e39fa-ef17-55ad-a6f7-3607ec2611fa | note | Acceptance Criteria - Materials match that specified in Project IFC drawings and Technical Specification.
df72b997-8545-5f01-8570-b4ec0be39702 | note | ○ Structural steel Material shall be sourced from suppliers certified by ACRS
79eda9f1-82ef-5d4b-9eef-9c31ace22843 | note | ○ Material test certificates shall report all element required by AS/NZS relevant standard, plus total boron content (Manufacturer certificates shall from ILAC MRA laboratories)
3dc632a0-74d6-51ae-92c1-197d77f7d1a9 | note | Certify Doc / Ref - Supplier Material Certificate
d44a77d3-6efb-5b72-8d2b-ab86138e136c | note | PFS Engineering - PM/PE
3d6003c0-06e2-51b4-b81c-e8bce1a2f98b | textbox | PFS Engineering: Sign - Initial: Sign:
177da8de-52a9-5e9e-b72d-bf52cb77eeef | note | PFS Engineering: C - RA/S
b0830d52-693c-52ec-81ff-95d8b9106b37 | note | Downer - Downer
5a37a7e6-f82b-5889-b1e3-56b5f2907ff9 | textbox | Downer: Sign - Initial: Sign:
1b2d2589-5c12-5d6c-95d4-70ce3dae584b | note | Downer: C - H
7135a954-9975-4db6-acac-ecb83d519ea2 | signoff | AUTHORITY HOLDPOINT
a9d7bc92-cb1f-47d1-a7f3-324d0b0603d3 | checkpoint | 8 - Procurement of Welding consumable to match Weld procedure and parent materials.
343b20ad-a202-5433-9d4e-2d3d1530fcaa | note | Specification Standard - AS/NZS 1554.1
2fc37e14-ad0f-5280-959f-1a15e5d324db | note | Acceptance Criteria - Welding consumables and gas match what is specified on the appropriate welding procedures.
1ffad913-4561-5cf9-9d11-4031d911d599 | note | Certify Doc / Ref - Supplier Material Certificate, PFS Welding Procedures
0ead9100-c2b5-5dfe-b680-fc64828ccd8c | note | PFS Engineering - PM/PE
b22809a7-ccbb-513c-83bf-ad90ec82017a | textbox | PFS Engineering: Sign - Initial: Sign:
aece63d4-66b0-58e9-bda5-29b5a8c55c87 | note | PFS Engineering: C - RA
578eb06a-7d58-4d4f-b84c-730955fdf4f7 | checkpoint | 9 - Material inspection upon receiving (By supplier/sub-contractor/ Free issue material)
1b380850-685a-59c5-aaea-80525353fce1 | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
7c5094bf-0a24-5106-86e9-6897c3f0042b | note | Acceptance Criteria - All material shall be inspected against IFC drawing to make sure material grades, type, thickness, size are in compliance with IFC DWGs.
36e5db85-3540-5343-9076-9b0308abfb57 | note | Certify Doc / Ref - IFC DWGs
9d2e45ac-ba56-51bb-bbd9-39bcb547a200 | note | PFS Engineering - Team Leader
c1612bc5-23c6-5719-8bee-80a61f263499 | textbox | PFS Engineering: Sign - Initial: Sign:
50b63a39-4100-5274-9099-0ef89ab46760 | note | PFS Engineering: C - H
f9ee9f12-6ea9-4f0c-9208-8bb2626b6206 | signoff | AUTHORITY HOLDPOINT
35d3eed2-36b4-4a7b-8eab-80a98fe3d90e | section | Steel structure Fabrication
bc851999-5cab-4510-8562-dc76b7f5abfd | checkpoint | 10 - Manufacturing Work Pack Issued to Production Manager
986cfb81-ed69-54a0-bcb0-16d6bdf01856 | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
b1e14a9d-4a41-5922-84de-406588f73227 | note | Acceptance Criteria - Job barcodes, Inspection & Test Plan's, IFC Fabrication Drawings, Reference Drawings/Info, Welding Procedures, weld map, welding log info, traceability sheet
eaa50bcb-2bb7-5701-a573-c0731b4c66a9 | note | PFS Engineering - Production Manager
77b4e613-8761-5d21-8494-347d9a1f0425 | textbox | PFS Engineering: Sign - Initial: Sign:
43a22081-3c2b-51a8-bed6-4976f18c9892 | note | PFS Engineering: C - RA
31df18c2-be51-461f-ae31-d7d0d4b90d1b | checkpoint | 11 - Cutting the structural steel
75c29a31-3399-5f8c-bac6-a9ede46167bf | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG, SHEQ-01-02-0039
c66074cd-5c88-5ce5-bea9-d73a3a6fb511 | note | Acceptance Criteria - Dimensional survey of fabricated item's against IFC drawings.
b418d81c-4f58-53de-b40f-0ba788f4ce01 | note | ○ Measured dimensions shall be within Functional Tolerances class 2 as per AS/NZS 5131 Table F2.1 to F2.10
586a8d66-9d06-5f73-b0fc-b01a6f491e44 | note | Certify Doc / Ref - IFC DWGs
617b11ca-3d80-5282-bca1-3bc131a97960 | note | PFS Engineering - Team Leader
31941ddd-49a4-550f-9a32-410eccc91e13 | textbox | PFS Engineering: Sign - Initial: Sign:
7710c080-20e4-5fc7-8407-031412d68bf2 | note | PFS Engineering: C - D
2c0177a2-7fcb-43ae-819b-0a51dfcd8c1c | checkpoint | 12 - Holing
4999454c-3713-5199-a724-99995dccfcdc | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG, SHEQ-01-02-0040
78f27694-5d64-58a1-8705-f46281bf1b52 | note | Acceptance Criteria - Dimensional survey of fabricated item's against IFC drawings.
fd58b69e-f740-5188-9c06-0c2201202850 | note | ○ Measured dimensions shall be within Functional Tolerances class 2 as per AS/NZS 5131 Table F2.1 to F2.10
43d319b2-e8a5-5088-84a9-51b628563d49 | note | Certify Doc / Ref - IFC DWGs
df5488e0-5955-55ef-88eb-52badd0de94b | note | PFS Engineering - Team Leader
203d48d6-f7c9-5a19-bb49-06ba3c450531 | textbox | PFS Engineering: Sign - Initial: Sign:
42bd0cf8-4934-520c-8ee3-b3ead96400d1 | note | PFS Engineering: C - D
461e9f32-0ea8-45ef-8106-0e62fcecfb58 | checkpoint | 13 - Identification and traceability for main items
2fa999bd-fadb-5359-96d7-d592ad249148 | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG, AS/NZS 5131
7bd90614-8e7a-5761-baae-a03ad01147bb | note | Acceptance Criteria - Lot traceability shall be provided for main structural members, connections between main structural members and major plate components. Tracibility as per AS/NZS 5131:Amd 1:2020 5.2.3 (ii) for minor components including cleats, connecting brackets and the like.
909a859e-88a1-5af7-a9d1-c0253491469b | note | Certify Doc / Ref - IFC DWGs
8fc87048-e587-56e4-b27c-ef0da8748383 | note | PFS Engineering - PM/PE
e8a57eaf-1a25-502c-aa2e-55c2a92e277c | textbox | PFS Engineering: Sign - Initial: Sign:
8a2f0111-f610-50a8-95b9-4d9a5d838c7d | note | PFS Engineering: C - H
060a407c-d69c-49d4-b785-7502612b16db | signoff | AUTHORITY HOLDPOINT
e1873d60-e724-4c5d-9254-998b4a3ede22 | checkpoint | 14 - Manufacture of steel structure - Tack welded only
f1da5cb6-ec15-528f-937e-b958d935a2b8 | note | Specification Standard - IFC DWGs
35a3ae7c-f24d-5cac-acc1-c52c5db06d8a | note | Acceptance Criteria - Manufacture completed as per IFC Fabrication drawings.
b4e50994-e311-53c5-873f-f6b249f623e7 | note | ○ All tack welding shall be performed in accordance with PFS weld procedure.
8663b15d-3d4b-5eaa-b2be-74e92f293695 | note | ○ Welding consumables, process & any applicable pre/post heat requirements shall comply with approved welding procedure's.
2c579cca-30d9-536a-b00d-296c90c59a87 | note | Certify Doc / Ref - IFC DWGs
dc0faf2d-757a-5e4b-9db2-554e65a99c3d | note | PFS Engineering - Team Leader
8ed1a40b-e021-51ad-8706-a465c75e7fbd | textbox | PFS Engineering: Sign - Initial: Sign:
07278ff6-bba9-511b-a1d6-140143c8c843 | note | PFS Engineering: C - D
c50120e3-cbae-4b57-9995-d7ae773ec1a4 | checkpoint | 15 - Pre Weld Dimensional Check (Tack Check)
2dce80aa-1816-5440-83c9-80a90b36dfe1 | note | Specification Standard - IFC Drawings
9168b148-2147-5f35-a21d-60f4fd7ecfc8 | note | Acceptance Criteria - Dimensional survey of fabricated item's against IFC drawings.
1a017d04-5168-57ca-827d-8e1b6800ca2b | note | ○ Measured dimensions shall be within stated tolerances unless noted otherwise.
0f50b68e-bd17-5dd3-ba8a-8629092aaf9d | note | ○ Project specification clause C0702.1.3
739d3015-b8d4-5aad-8345-6bafc93e3d5e | note | ○ Functional Tolerances shall be class 2 as per AS/NZS 5131 Table F2.1 to F2.10
949ef5e8-12ec-58f2-a692-fddad3c11286 | note | ○ Inspections recorded in line with SHEQ-01-02-0035 Product Inspection Procedure
74316dd9-af1c-5373-a918-7d278315eb3e | note | Certify Doc / Ref - IFC DWGs
c30ab62f-3e70-511c-9380-cb33d9d12381 | note | PFS Engineering - Team Leader
85fb0e91-bc42-5645-9ecb-87d4f7d48ae6 | textbox | PFS Engineering: Sign - Initial: Sign:
97f9c90f-396d-574c-80c7-96872227c428 | note | PFS Engineering: C - D
d7489a93-0ce1-496e-9ca3-a67cb027ac52 | checkpoint | 16 - Welding
1bf3f7c6-c0e7-508a-a478-04c1bbf04f05 | note | Specification Standard - AS/NZS 1554.1, AS/NZS 9606.1
7affc4a7-4422-5766-941a-f964c20e4678 | note | Acceptance Criteria - All welding shall be performed in accordance with PFS weld procedures
18d73261-90db-5cd0-bc48-5307243ed84c | note | ○ Welding consumables, process & any applicable pre/post heat requirements shall comply with approved welding procedure's. Welder ID, weld date & consumable batch are recorded on traceability register.
369d04ac-f7b2-53e0-9404-2d9e078340aa | note | Certify Doc / Ref - Welding Procedure and Welder Qualification
eeda4cf3-9bdb-5ab2-8d7e-67ec9f1e4f8f | note | PFS Engineering - Team Leader
3e6952b8-1c75-557e-a64f-e9ce7e799867 | textbox | PFS Engineering: Sign - Initial: Sign:
765e8c10-7014-553e-816e-23a02eb7598d | note | PFS Engineering: C - V
ec463a81-b9da-4716-964b-6a1f248c948b | checkpoint | 17 - Post Weld Dimensional Check
3406d37b-c7f3-5c27-97ae-1a6f9de6b275 | note | Specification Standard - IFC DWGs
eac97362-1643-5705-8452-ba5a71243866 | note | Acceptance Criteria - Dimensional survey of fabricated item's against IFC drawings.
b3365adb-4427-5e20-b01d-a74e1532051f | note | ○ Measured dimensions shall be within stated tolerances unless noted otherwise.
3ccfa0d3-8553-5640-aee4-9c49c7fdca55 | note | ○ Project specification clause C0702.1.3
4a6c8de0-1d2f-53ce-9921-70506861b43b | note | ○ Functional Tolerances shall be class 2 as per AS/NZS 5131 Table F2.1 to F2.10
50dd6831-b3b4-5b87-a08d-5605a431e5a9 | note | ○ Inspections recorded in line with SHEQ-01-02-0035 Product Inspection Procedure
e3e173bf-fefe-524d-92be-5742f2b23e17 | note | Certify Doc / Ref - IFC DWGs & Workshop Pack.
31733993-3b24-59c0-8614-326b1e51be28 | note | PFS Engineering - Team Leader
a49f588a-8931-5dcc-84ba-bf33e56ee62d | textbox | PFS Engineering: Sign - Initial: Sign:
e1c8a8f6-d844-5ce8-87d0-c8e5f20570af | note | PFS Engineering: C - D
6e9a9b22-ee16-47be-a1cb-cff07e039314 | checkpoint | 18 - Weld Visual Scanning (PFS Internal Check)
bf64add1-ecfc-5b5e-8d49-e45e4ca401cc | note | Specification Standard - IFC Drawing
6c2c009e-65bf-551a-bc48-01257a81726a | note | Acceptance Criteria - 100% of all welds shall be subject to visual scanning
67a47d9a-4b0a-5469-afa2-55d60576b893 | note | Certify Doc / Ref - PFS NDT Register
72ac25ba-dc3b-53f5-882d-87aec9e3ced1 | note | PFS Engineering - Team Leader
e078171d-a783-55c7-b8b9-c9be77baf3f9 | textbox | PFS Engineering: Sign - Initial: Sign:
4238a205-6975-5dc4-919b-766c7beac55e | note | PFS Engineering: C - V
d321d0d5-c6ca-4191-ac25-fa2b27665d96 | checkpoint | 19 - NDT inspection
1c17df24-6600-5705-a29c-c7ca43395b27 | note | Specification Standard - Project Structure Specification C07 Rev. 01
1139ed84-382c-5cbf-9df4-31c8c37c84bb | note | Acceptance Criteria - NDE shall include as a minimum:
d88f22df-156d-573c-ad77-6e042e14f9a2 | note | ○ 100% Visual Scanning, 100% Visual examination, 100% UT examination of all butt weld, 10% MT examination for fillet weld
8c5307ef-8ff8-51c5-a7ea-478b9e40777e | note | ○ The Welding Compliance Inspector shall complete all inspections including any additional inspection, tests and reports necessary due to any welding or welding related workmanship defects.
154f3c2f-8196-55a0-9323-0c34ae161137 | note | Certify Doc / Ref - Stamped NDT report
6bfee8d2-e591-5535-a921-89d275cd0db1 | note | PFS Engineering - PM/PE
87f804d4-0828-5771-8a86-e8507aa6d6ae | textbox | PFS Engineering: Sign - Initial: Sign:
13ff6f5e-62f3-55ba-bc60-111828a18979 | note | PFS Engineering: C - RA
2c297f54-f9e7-570c-b04c-4d33354806be | note | Subcontracted scope - NDT subcontractor
de24f634-4114-50b6-a4fa-1489a41a6d95 | textbox | Subcontracted scope: Sign - Initial: Sign:
1a79d8cd-f9cb-5fdb-974e-9d1ae3b455af | note | Subcontracted scope: C - S
822b354d-1391-4402-b79a-2acf7f59fef7 | checkpoint | 20 - Protective Coatings Preparation
2631d7b0-6f7c-5b68-a7f0-a7fb9bd8ed54 | note | Specification Standard - Project Structure Specification C07 Rev. 01
8c6e2063-c9ce-5c2f-ba05-17fd9904a6e7 | note | Acceptance Criteria - Removal of all weld spatter and dressing of any weld to removed sharp edges / spatter.
6c590bf3-7968-5544-933b-718158ecb993 | note | ○ All sharp edges are ground to a smooth 2 mm radius.
bcd477d1-f860-5cc7-9c32-ff46e01d795d | note | Certify Doc / Ref - N/A
513d1a70-db21-5d38-98f7-2ac0532fc13c | note | PFS Engineering - Team Leader
f78c5c71-6ee8-50f1-97f4-f0ab5beefd6d | textbox | PFS Engineering: Sign - Initial: Sign:
20143dfb-eb9f-53ca-8ccb-ff25cc017334 | note | PFS Engineering: C - V
b725e3bb-551d-4244-ac90-8b13e038763c | checkpoint | 21 - Fabrication NCR (if any)
67e5daae-49ab-538b-92a9-c9e3d7291421 | note | Specification Standard - Project Structure Specification C07 Rev. 01
a0f23226-a7c7-52c0-9f30-81790f38a38c | note | Acceptance Criteria - All Non-conformities reported in PFS NCR system during manufacturing of steel structure need to be submitted to Client for approval
59903364-6f17-5ab3-8ad5-1058901d8f36 | note | PFS Engineering - PM/PE
83918ab5-1e01-59ae-8f93-9508c264838a | textbox | PFS Engineering: Sign - Initial: Sign:
0c95e380-01a1-5a1c-872a-b761544b39e8 | note | PFS Engineering: C - S
5f99bd05-97e1-5e94-b0d5-7d506e9ef076 | note | Downer - Downer
d4913437-c0e3-5c39-922c-78bb1d432718 | textbox | Downer: Sign - Initial: Sign:
62b9fb36-1870-5c56-bbe0-5d3337416efd | note | Downer: C - RA
f590a46d-0055-46a4-9135-cac3d112b282 | section | Shop Assembly - Pannels, Handrails and Balustrades
3b5ea43f-d22d-4ca3-be00-989dc4410902 | checkpoint | 22 - Inspection the free issue pannel uppon receipt at PFS work shop
c2c4f377-9b4a-57aa-a3c8-91b697da5588 | note | Specification Standard - Pannel DWGs
00c946c7-be50-528e-9ff7-95f0a4705f9e | note | Acceptance Criteria - Check pannel to make sure the quantity and/or dimension are based on approved DWGs.
30601e8e-da02-599d-a795-3f54963f03b5 | note | Certify Doc / Ref - Pannel DWGs
b5e2fa9c-1614-515e-b5c5-6c741b6fe3cc | note | PFS Engineering - Team Leader
5c6faa08-2f5e-5965-a2ae-8c6b114223e9 | textbox | PFS Engineering: Sign - Initial: Sign:
652f6bfc-f6c3-5c35-9b67-9c679de803cb | note | PFS Engineering: C - V
fa91d281-f2a2-4525-bab3-a356156d92fb | checkpoint | 23 - Panels Pre-assembly
4a124658-4e12-50ae-a168-2c4bf50f547c | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
fa5e3aaf-e3dd-5db3-973e-feadbbbd3bb0 | note | Acceptance Criteria - After painting, Client supplied pannels for decking and balastrades to be assembled.
1c39b3ad-75c3-51c0-91e5-733d02baf631 | note | ○ Handrails need to be assembled in the shop
58724b88-63ea-5019-af7b-d7b861e86e96 | note | Certify Doc / Ref - IFC DWGs
21ee6b93-2cdc-51e3-8d6a-dfafd73a0a41 | note | PFS Engineering - Team Leader
ebbbbc90-5656-51a2-b7b9-130db922d133 | textbox | PFS Engineering: Sign - Initial: Sign:
161a6f8b-498a-585d-915c-01fd43b9ee86 | note | PFS Engineering: C - V/D
59a36c8f-691c-422e-9e8b-a72aa719ee5b | checkpoint | 24 - Dimension check
c4d9dc60-dba6-5fc2-b82b-97797413f1c0 | note | Specification Standard - IFC DWG
32381974-4b7d-5c0f-b46d-08a29481677c | note | Acceptance Criteria - Compliance with IFC DWGs
55873318-63ab-562b-a9fa-3869b7a98b28 | note | PFS Engineering - Team Leader
e29ece9b-4eb9-5a7c-a070-dc15880d7198 | textbox | PFS Engineering: Sign - Initial: Sign:
834c655e-eb6e-52f5-bf99-52c96bc67670 | note | PFS Engineering: C - D
857fa970-9032-4cf3-8d94-88155dd0cdad | checkpoint | 25 - Visual inspection of Fasteners (Free issue)
a3778113-1767-5132-ada8-f21949f2ff62 | note | Specification Standard - IFC Drawing
4aea159d-e503-5f89-af01-7fb5a9927266 | note | Acceptance Criteria - All fasteners (bolts, nuts, washers) are to be in complied with the Porject requirement (Grade, Size and Length)
8714f756-f6d7-565b-bdb0-5be05ae05976 | note | Certify Doc / Ref - IFC Drawing
01b985d5-ae54-5762-9641-29e72c3fdf61 | note | PFS Engineering - Team Leader
447aec41-3168-58a1-a9fc-b274392da9c0 | textbox | PFS Engineering: Sign - Initial: Sign:
eaaabbf8-134e-5643-ab23-c215ff767c5a | note | PFS Engineering: C - V
0625b2f3-f8f3-43db-a9dc-14ab54dfda01 | checkpoint | 26 - Snug tightening of conposite component fixings
841a9aae-965e-54af-bd79-bb75f06fb332 | note | Specification Standard - Standard operation procedure for steel structure bolt tightening, SHEQ-01-02-0038
68ff90f9-8dc3-5e2d-8e87-5de3d1196668 | note | Acceptance Criteria - 100% of fixings securing composite material to structure are to be inspected for snug tight condition and marked with coloured paint pen to confirm fixing condtion has been checked and verified.
8b9c52e9-5b84-58b2-8594-f20fb7490a48 | note | PFS Engineering - Team Leader
cdf67a43-5740-5ec0-9ab4-f3ec586dd390 | textbox | PFS Engineering: Sign - Initial: Sign:
7c5966c2-a402-510c-a6e3-857630827a22 | note | PFS Engineering: C - V
b208c033-de29-49af-8f6f-07787fdfff5f | checkpoint | 27 - Final Inspection
751c2232-fdbf-528c-aec3-b57890349def | note | Specification Standard - IFC Drawings, AS/NZS 1554.1:2014 Category SP
335a624d-ed96-531f-bffd-502f4a8cb5db | note | Acceptance Criteria - Visual and Dimensional inspections completed by PFS Project Manager to confirm manufactured items have been manufactured to acceptable standard & tolerance and approved to progress to protective coatings.
53d4f4ee-1468-5ff1-b597-5ec3f964e30d | note | ○ >Confirmation that dimensional inspections have been completed in line with SHEQ-01-02-0035 Product Inspection Procedure
ecaf2fe1-4307-5df1-b631-48d6f683d9aa | note | ○ >Confirmation that required quantity and type's of NDE has been completed and any identified defects have been remediated.
8af74b2f-ed36-5ead-921c-3ac352073ba9 | note | Certify Doc / Ref - IFC DWGs
0bc98d5c-9ab9-5df3-aa09-5c7c1606d914 | note | PFS Engineering - PM/PE
0150c9ba-6294-5309-a94d-d0aed1ff9929 | textbox | PFS Engineering: Sign - Initial: Sign:
5c4c6a9b-b59e-5e38-b606-95f326310b9e | note | PFS Engineering: C - RA
93b85edd-ff79-41fb-8336-4e81209642c8 | section | Quality Review
af9edd6d-34ae-40e4-996e-e1e16af07f71 | checkpoint | 28 - Compile, review and submit documentation
1b31de54-7cfe-5244-8bdd-6c00a8589f78 | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
9543f668-fe25-5086-8732-8479c9671142 | note | Acceptance Criteria - Documentation, Certificates and reports to support manufacture of steel structure and subcontracted items compiled into PFS Manufactures Data Report
867c5eca-6927-5a17-8a60-92faa97093c7 | note | Certify Doc / Ref - PFS Manufactures Data Report
7a71edb2-21ac-53f3-ab78-73d683d4f5cb | note | PFS Engineering - PM/PE
03d48c23-0b6a-599c-a142-0498bf584607 | textbox | PFS Engineering: Sign - Initial: Sign:
258c2e8e-5fc6-50e1-8d40-3fbe759ec46d | note | PFS Engineering: C - RA
c47d89c6-3c1a-5193-ae02-65cf4148f347 | note | Downer - Downer
d284c1b9-82ec-5070-8a6c-c913685d3592 | textbox | Downer: Sign - Initial: Sign:
465d2beb-f34c-5213-8025-7e87fd28fe2a | note | Downer: C - RA
de58a375-5c0b-493c-965f-8a8a1aebd712 | section | ITP APPROVAL PROCESS
b3868273-5b9f-46cc-8b73-2cef5149ccfa | checkpoint-no-value | ITP APPROVAL PROCESS
75a69643-f835-5596-a71a-d7b94da2aba6 | textbox | Approved by [Engineer/Client]:
729bcdd4-958a-5ba6-af5c-3923e653ea35 | textbox | Issued for Construction:
c7974c53-4269-4a92-99eb-fbf941d129b5 | signoff | Sign:
df8ed6f9-7241-4987-834c-93b2b755c09c | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
53062b30-c6be-5756-a3a3-79177aeb2439 | textbox | Contractor's Rep Name:
6146f5e4-a802-56c0-b7fa-1e5435a9fb25 | textbox | Engineer's Rep. Name:
73ff3f4f-f949-5ed2-b204-a69a322d54e3 | date | Date:
b24aa8c6-054a-4b59-bdf9-79608f6c6e93 | signoff | Add Signature
b3dcc23d-e7c9-4062-8833-b150c7d64297 | checklist | DN1212-ITP-017 Shop fabrication - Span 3 RevD | itp | DN1212-ITP-017 Shop fabrication - Span 3
70c37746-ace6-4aa4-9782-177585dac612 | section | Engineering
7cb3f7f0-de2a-450e-8a90-3fca4e794fb5 | checkpoint | 1 - Inspection and Test Plan Reviewed and Approved by Customer
fa62cf90-556a-5af2-8ba8-c08cf246cff7 | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
d9001ef2-a28e-5fd5-befa-c5ab2fab430b | note | Acceptance Criteria - Inspection and Test plan shall be submitted to the Engineer for review and approval before fabrication is commenced.
d00dda6c-4b5e-5bf4-80b2-3120a24e4b57 | note | Certify Doc / Ref - IFC DWGs
8fe05071-59c2-5905-af61-b20ef6d11ef3 | note | PFS Engineering - PM/PE
403787cf-c814-54e1-84ae-ea06cb38d575 | textbox | PFS Engineering: Sign - Initial: Sign:
10ba32a1-ffcf-54cb-8691-37acef1449d0 | note | PFS Engineering: C - S
0c33d61e-1020-5be8-9fed-4edfb840d335 | note | Downer - Downer
ddd552cd-1250-53bb-abfd-5c0ae8b7cef5 | textbox | Downer: Sign - Initial: Sign:
8937a992-aa74-5ed0-b832-8b5fde825918 | note | Downer: C - H
a8482c36-c466-4ab4-8394-b3fc2de7369e | signoff | AUTHORITY HOLDPOINT
b4d51796-8551-4897-8ee7-f6009b6f34d5 | checkpoint | 2 - Shop Drawing approval
77114c50-70de-51dc-a530-624ece70ba63 | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
878aba1d-6608-525e-aa8b-17522377283d | note | Acceptance Criteria - Shop Drawing shall be submitted to Engineer for review along with Shop Drawing Check form
afc7736c-46e5-524b-844a-33c1c2889ddf | note | Certify Doc / Ref - Shop Drawing Check form
fa796473-5ce5-5c75-89ef-c7816614e6f7 | note | PFS Engineering - PM/PE
72921233-a466-531a-ab39-1d427d42d032 | textbox | PFS Engineering: Sign - Initial: Sign:
65bb61e9-5c62-57bd-8dad-a62c5f97f731 | note | PFS Engineering: C - S
e3e5bf1d-b267-561b-b644-efda27165957 | note | Downer - Downer
b3f07058-d9cd-56d7-ba0c-cb6df89b68af | textbox | Downer: Sign - Initial: Sign:
ea9a7c1f-42dd-50b0-b9a7-177e00a5ff57 | note | Downer: C - H
dbc018b2-2409-47c5-b168-5b6fb8848ee6 | signoff | AUTHORITY HOLDPOINT
b7cd936b-9950-4d7f-ae1e-550f6e12a6e7 | checkpoint | 3 - Submit Inspection personel competencies
52aab6e3-f250-5db1-ad5c-1c55e2d36182 | note | Specification Standard - Project Structure Specification C07 Rev. 01
fe959000-652b-5b07-964d-a5ebde3a1753 | note | Acceptance Criteria - Inspection personel (Independent inspectors) qualification and certificate shall be submitted to the Engineer for review and approval according to C0701.2.4
675294e6-695b-53ff-b0f1-b2f42039ae24 | note | Certify Doc / Ref - NDT qualification
066a49c4-5ae9-55f4-a9af-7487beb6ada9 | note | PFS Engineering - PM/PE
c24984ff-f740-5cc7-b041-cda0cf59c4de | textbox | PFS Engineering: Sign - Initial: Sign:
9a590eeb-c4f2-5a33-ac69-b7dd9e9428c3 | note | PFS Engineering: C - S
a07f4856-dafd-54d5-94cc-b11a9e3b7788 | note | Downer - Downer
0446c410-7af3-533c-8380-78c3863dd552 | textbox | Downer: Sign - Initial: Sign:
151269c0-b9a9-5add-92e6-040d566262f8 | note | Downer: C - H
601daed9-8596-446e-bbe6-fb1d2a202327 | signoff | AUTHORITY HOLDPOINT
b32a99a6-c675-4333-921c-223e640c1d52 | checkpoint | 4 - Welding Procedures - Structural
dc6362f3-e76c-561d-8057-eca62579fd33 | note | Specification Standard - AS/NZS 1554.1:2014 Category SP
23af22d4-b2e7-5d2d-8a6a-f5117b59c91f | note | Acceptance Criteria - Details of the welding procedures to be used including details of the equipment and consumables before any welding is carried out. No welder shall carry out work for which he is not certified.
acbe8b7a-d148-530c-8b01-517fbac831eb | note | Certify Doc / Ref - Welding Procedures, HERA/CSWIP Stamp
985fa813-5747-5dd6-9cb7-4f771c8afc6c | note | PFS Engineering - PM/PE
240995d9-2710-5d03-b3e7-c6a82fbe78aa | textbox | PFS Engineering: Sign - Initial: Sign:
6f1d3601-1691-58d7-80dc-0c8849c45333 | note | PFS Engineering: C - S
7497126e-ecc8-5436-b839-5c93722846cc | note | Subcontracted scope - SQA
7f3b8a01-a95a-5960-aa52-129f762e5ce2 | textbox | Subcontracted scope: Sign - Initial: Sign:
42085356-0e28-507f-a2c6-285dae8c7abf | note | Subcontracted scope: C - RA
3538a429-917c-4002-a811-ade0ed525b5e | checkpoint | 5 - Welder Qualifications - Structural
1a6c6f22-9163-56de-89c3-edddc0c2dd82 | note | Specification Standard - AS/NZS 1554.1:2014, ISO 9606-1:2017
0905d527-eb26-50ad-b55c-0b3c7d8bdd4b | note | Acceptance Criteria - A list of proposed welders and their welding certificatesto be provided prior to any welding being carried out.
052728b1-cfed-5a0f-9f72-36643342147b | note | ○ No welder shall carry out work for which he is not certified.
18246938-0933-56d9-95c8-b93af2fc52fd | note | Certify Doc / Ref - WQT by Authorised Person (Welding Supervisor)
d5d301d9-1931-58c5-9390-88d800c306b8 | note | PFS Engineering - PM/PE
de1ea55f-a5d5-5d82-972b-c025b5f5b422 | textbox | PFS Engineering: Sign - Initial: Sign:
91ef4a2a-1b6f-5f7b-b39e-fb3d5ed07a05 | note | PFS Engineering: C - S
5fac8152-851c-5b30-b851-2680474cbf83 | note | Subcontracted scope - SQA
28d093a9-52a6-568f-ae77-f20accd71fba | textbox | Subcontracted scope: Sign - Initial: Sign:
02a5b588-88b1-52ed-86c0-273c4c11723e | note | Subcontracted scope: C - RA
98fc697f-c642-4761-8b73-2c97b01cd33d | checkpoint | 6 - Submit the required documents to Client for review
fb01ab05-9e23-5c78-b052-80039d2d50fd | note | Specification Standard - Project Structure Specification C07 Rev. 01
4b5d360c-0037-5348-ad81-04e8ff2bf18b | note | Acceptance Criteria - Following shall be submitted to the Engineer for review before fabrication is commenced:
704b3936-0a48-5618-acfb-72b7f61b4826 | note | 1 - Quality Management Plan
c2fdc251-c55e-5a99-a72b-09c44d14686a | note | 2 - IMS Manual
6961a311-eb9d-5985-81ea-bb8e79666283 | note | 3 - SFC Certificate
96c59a17-27df-54c7-8c4a-c28ef445c105 | note | 4 - ISO 9001 Certificate
0fcb1ea1-dd68-52de-a1ef-1400b8657ab5 | note | Certify Doc / Ref - Quality certificates, Quality Plan
1653cc3d-2a14-5b49-a501-8db8ab90c03c | note | PFS Engineering - PM/PE
9d3df1ea-e8a5-5be2-a613-0a27f19bf667 | textbox | PFS Engineering: Sign - Initial: Sign:
c7fc0b2a-32fa-57dc-b3e1-a590cceabf4c | note | PFS Engineering: C - S
0c758c32-3b85-5e2c-8ce4-4af60eadde3e | note | Downer - Downer
07fd966e-f01f-5df3-97c2-1b27583f0127 | textbox | Downer: Sign - Initial: Sign:
af842385-b5dc-5646-a972-1de64d7d00f0 | note | Downer: C - R
661d37d2-19ba-4328-822d-d413c08f7c01 | section | Procurement
b3563509-2080-403b-b8b2-113c17452ee4 | checkpoint | 7 - Procurement of materials in line with IFC drawings and Technical Specification
eaf6c8e2-cddd-5aa3-9623-35ae8191f793 | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
97b46710-dfdd-57ba-bd73-88bc80db8178 | note | Acceptance Criteria - Materials match that specified in Project IFC drawings and Technical Specification.
3a0facdb-6919-5001-95c5-13c95b93991d | note | ○ Structural steel Material shall be sourced from suppliers certified by ACRS
25d1b62b-81a8-5f02-a9f0-53b0c0b00ee0 | note | ○ Material test certificates shall report all element required by AS/NZS relevant standard, plus total boron content (Manufacturer certificates shall from ILAC MRA laboratories)
27ce6833-a31b-51dc-b2cb-9361859d6d4e | note | Certify Doc / Ref - Supplier Material Certificate
f189c95d-d2a3-511e-abf9-6f0753351ecd | note | PFS Engineering - PM/PE
18324823-197a-5f84-9839-02b079813b38 | textbox | PFS Engineering: Sign - Initial: Sign:
419d1f22-d098-589d-87a5-08495fb0e8d0 | note | PFS Engineering: C - RA/S
438dfe69-86c3-59e8-9da8-54f86c81d6c1 | note | Downer - Downer
9227b19c-b8a1-5497-83e4-911657ad384f | textbox | Downer: Sign - Initial: Sign:
eb7fba03-8872-5e5a-85c7-3ba016f84c6b | note | Downer: C - H
dc6ea5a8-3e9d-4a60-9eeb-455e85c38d53 | signoff | AUTHORITY HOLDPOINT
215748c2-849f-4692-be94-2deddb5a9344 | checkpoint | 8 - Procurement of Welding consumable to match Weld procedure and parent materials.
fc1a235b-d85f-5b57-a26c-e56cec5e039f | note | Specification Standard - AS/NZS 1554.1
f9c9ad33-3092-5bff-a429-ab5d27984abd | note | Acceptance Criteria - Welding consumables and gas match what is specified on the appropriate welding procedures.
1e3406ad-3688-5da3-9f40-a7dc98495306 | note | Certify Doc / Ref - Supplier Material Certificate, PFS Welding Procedures
fc23aee9-a41b-573e-a879-15b7e1177249 | note | PFS Engineering - PM/PE
365726a7-a15e-5b54-920d-f5b34395db13 | textbox | PFS Engineering: Sign - Initial: Sign:
f311632a-a15c-54d4-a761-68c63ed62bb5 | note | PFS Engineering: C - RA
deffd1f7-b57e-4317-ad06-8c780b16cbc0 | checkpoint | 9 - Material inspection upon receiving (By supplier/sub-contractor/ Free issue material)
b912cb7f-98ae-56bb-9611-82ccaca20512 | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
9a89705d-116b-5158-bd1b-8edb634dc558 | note | Acceptance Criteria - All material shall be inspected against IFC drawing to make sure material grades, type, thickness, size are in compliance with IFC DWGs.
25d31e07-6bcd-5dc1-8138-186e3b3ab872 | note | Certify Doc / Ref - IFC DWGs
e97913c1-b23e-5ef3-a868-8748dad1f6e5 | note | PFS Engineering - Team Leader
fded04b3-3fec-5fa9-875d-7667ee6e0a0c | textbox | PFS Engineering: Sign - Initial: Sign:
a4479c56-ffba-534a-8ee3-f3a896b525a6 | note | PFS Engineering: C - H
5b60ae2c-028a-4fba-b981-11bf1e140344 | signoff | AUTHORITY HOLDPOINT
b15208d9-8328-4a41-b8dd-3606adef5ad4 | section | Steel structure Fabrication
856619a6-3a6d-40b9-a06f-1b921607f8f5 | checkpoint | 10 - Manufacturing Work Pack Issued to Production Manager
315a6f63-cc2c-5b10-8ba4-a98634bb9f5d | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
4fc616c0-b397-5ef4-9b6b-c59c7f14e2de | note | Acceptance Criteria - Job barcodes, Inspection & Test Plan's, IFC Fabrication Drawings, Reference Drawings/Info, Welding Procedures, weld map, welding log info, traceability sheet
6e233e02-c449-555e-abce-e9b75495df4d | note | PFS Engineering - Production Manager
c39a95f0-4ad1-527c-a145-f039f0760a39 | textbox | PFS Engineering: Sign - Initial: Sign:
d69165fc-7425-5628-b6bd-83bb9e4d7af3 | note | PFS Engineering: C - RA
7d2e7897-9c82-4548-8f49-c5e7aaed160d | checkpoint | 11 - Cutting the structural steel
68038b87-f664-555f-9f82-56fb4e725b40 | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG, SHEQ-01-02-0039
e4bd70c3-a8fa-5d8e-9346-2019cc474d23 | note | Acceptance Criteria - Dimensional survey of fabricated item's against IFC drawings.
a9307e32-f9f6-5182-87bf-6026196e7b0b | note | ○ Measured dimensions shall be within Functional Tolerances class 2 as per AS/NZS 5131 Table F2.1 to F2.10
881b0468-ea8b-5811-b849-47ceba4326d2 | note | Certify Doc / Ref - IFC DWGs
df7d6d47-84e7-5231-aca4-801a99217c26 | note | PFS Engineering - Team Leader
1503a313-87c7-594e-9158-fdd2d0453868 | textbox | PFS Engineering: Sign - Initial: Sign:
5f47c154-c75f-59e6-9ff7-74d25f5918f9 | note | PFS Engineering: C - D
3c49f31a-6a1e-401f-8c6d-63a375eda264 | checkpoint | 12 - Holing
2a360ac2-5c2c-50f2-adbb-b6f3f0dddb5e | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG, SHEQ-01-02-0040
56ffd9fa-310a-593f-a6d3-620671594c56 | note | Acceptance Criteria - Dimensional survey of fabricated item's against IFC drawings.
7c6446f9-e769-5d10-82e0-db602366f21a | note | ○ Measured dimensions shall be within Functional Tolerances class 2 as per AS/NZS 5131 Table F2.1 to F2.10
a42d4755-65b4-5e50-9d0e-3448a507d908 | note | Certify Doc / Ref - IFC DWGs
1dbfdb6d-0467-55d2-ac46-24b2dc9b6e77 | note | PFS Engineering - Team Leader
414db93b-a484-54d3-8582-2e5a219539b3 | textbox | PFS Engineering: Sign - Initial: Sign:
25c8c1a4-8f26-532b-ba7e-bc807778e23a | note | PFS Engineering: C - D
c6d1600f-9c10-4303-999b-2640bd5cbc1f | checkpoint | 13 - Identification and traceability for main items
76b1074a-db2b-500c-9c44-884a6aa4af92 | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG, AS/NZS 5131
255f7819-7499-565a-b6bf-4f627b467d98 | note | Acceptance Criteria - Lot traceability shall be provided for main structural members, connections between main structural members and major plate components. Tracibility as per AS/NZS 5131:Amd 1:2020 5.2.3 (ii) for minor components including cleats, connecting brackets and the like.
87b850c7-e0a3-5ba3-ab48-c00703186226 | note | Certify Doc / Ref - IFC DWGs
3371bc00-ef37-5b94-9848-38df81007bf3 | note | PFS Engineering - PM/PE
bf7e9770-e3f3-55c7-9bc5-05248cfe87d7 | textbox | PFS Engineering: Sign - Initial: Sign:
cf4cf0d0-56eb-5d51-88af-b4133b3c0b33 | note | PFS Engineering: C - H
20517f09-eb58-4147-94ed-494a6e5b149f | signoff | AUTHORITY HOLDPOINT
a81d3c10-4f9c-4724-a22f-d2791ea5bdf6 | checkpoint | 14 - Manufacture of steel structure - Tack welded only
b4858df8-854e-5858-b97e-d4903c61c2cc | note | Specification Standard - IFC DWGs
7b313894-5b6d-57b2-ae36-94d273492c2a | note | Acceptance Criteria - Manufacture completed as per IFC Fabrication drawings.
9a704322-a259-5204-83d8-c47c00069450 | note | ○ All tack welding shall be performed in accordance with PFS weld procedure.
884e8013-e0f4-5471-9540-9e10cb3c3284 | note | ○ Welding consumables, process & any applicable pre/post heat requirements shall comply with approved welding procedure's.
e1ce8a72-1f89-5d20-aeca-25e18c8d62e3 | note | Certify Doc / Ref - IFC DWGs
4b79a470-2357-5e2a-af86-d21fcea789e6 | note | PFS Engineering - Team Leader
9a191e5f-85c6-511a-9d07-4e51de50939d | textbox | PFS Engineering: Sign - Initial: Sign:
d1fe192f-e8fb-517a-bbaf-ab72f4036631 | note | PFS Engineering: C - D
4b684e9b-dc8d-4ed2-8715-b0f744e4771b | checkpoint | 15 - Pre Weld Dimensional Check (Tack Check)
4123ab07-ede1-57d2-9943-2c5021fc7491 | note | Specification Standard - IFC Drawings
ce49a2ff-5d1f-5498-8a91-687d228a3b4f | note | Acceptance Criteria - Dimensional survey of fabricated item's against IFC drawings.
c29dc529-4797-5bbb-b9b2-a4fba536930a | note | ○ Measured dimensions shall be within stated tolerances unless noted otherwise.
5f6cc0e3-92cb-5354-a353-f49dc020a3d0 | note | ○ Project specification clause C0702.1.3
6fdd7a99-522a-5ada-aee1-706921ff902e | note | ○ Functional Tolerances shall be class 2 as per AS/NZS 5131 Table F2.1 to F2.10
9195a88d-3fcd-571a-ad00-7704bda40df7 | note | ○ Inspections recorded in line with SHEQ-01-02-0035 Product Inspection Procedure
45a881de-9b2d-54b9-b478-ca224954d04e | note | Certify Doc / Ref - IFC DWGs
d4b4a80a-97e7-5d14-b572-3e7b4e489891 | note | PFS Engineering - Team Leader
932b5398-8ad8-5fa0-ae9a-e32e8e9db443 | textbox | PFS Engineering: Sign - Initial: Sign:
6aea6da3-9d73-5273-92f9-c207b6025252 | note | PFS Engineering: C - D
f942ba5e-d824-4872-b192-77cff48d13b2 | checkpoint | 16 - Welding
be06a7a8-e6a0-5003-ab3c-29c8ce82fdbd | note | Specification Standard - AS/NZS 1554.1, AS/NZS 9606.1
95c4ab6e-f45f-57df-85e3-e64a7506b1ae | note | Acceptance Criteria - All welding shall be performed in accordance with PFS weld procedures
fe81e613-8bde-512b-8d12-54b003409c9e | note | ○ Welding consumables, process & any applicable pre/post heat requirements shall comply with approved welding procedure's. Welder ID, weld date & consumable batch are recorded on traceability register.
9917dd15-47e6-5c49-b651-8b2401125767 | note | Certify Doc / Ref - Welding Procedure and Welder Qualification
48ac23dc-3465-57a5-8947-6fc35eb95e21 | note | PFS Engineering - Team Leader
dddb6bc8-54df-5ab5-b09d-810c7d2aa852 | textbox | PFS Engineering: Sign - Initial: Sign:
c152da56-4980-56aa-a203-b14a9d48970e | note | PFS Engineering: C - V
29a9b4b7-953d-446b-9498-da7a9e6d8f84 | checkpoint | 17 - Post Weld Dimensional Check
fbcd8cc7-9634-5df7-ab94-157126746ba4 | note | Specification Standard - IFC DWGs
926deb22-a78c-525a-9f7a-2beb4842341e | note | Acceptance Criteria - Dimensional survey of fabricated item's against IFC drawings.
d932c9d3-3bd6-5c88-87fc-fb84d65ce251 | note | ○ Measured dimensions shall be within stated tolerances unless noted otherwise.
0f226fef-8b5d-59c0-a254-c4f4988fa84f | note | ○ Project specification clause C0702.1.3
b8782641-8964-57d1-875e-02c1eb851139 | note | ○ Functional Tolerances shall be class 2 as per AS/NZS 5131 Table F2.1 to F2.10
b44ae2a6-857e-5be2-8d75-7ad36e9f4634 | note | ○ Inspections recorded in line with SHEQ-01-02-0035 Product Inspection Procedure
209fa2b4-8b42-5c1a-a574-d7bbfad52c1e | note | Certify Doc / Ref - IFC DWGs & Workshop Pack.
d90730d9-5ee0-57e6-a88d-1f99b89538b5 | note | PFS Engineering - Team Leader
956c06e1-64d3-5d58-8bb3-b7136356f70a | textbox | PFS Engineering: Sign - Initial: Sign:
0880e07c-40cc-55ca-8d49-64012c2d5cc0 | note | PFS Engineering: C - D
1bfedb4d-24a6-4c6d-9ddd-aed6db47c7e6 | checkpoint | 18 - Weld Visual Scanning (PFS Internal Check)
e8d4e777-1315-58e8-a8c5-f046e7b7954e | note | Specification Standard - IFC Drawing
c53b9136-3070-5dca-829c-71e3f4d637fe | note | Acceptance Criteria - 100% of all welds shall be subject to visual scanning
5e33c3e7-d574-537c-8fb2-dadf575e10ce | note | Certify Doc / Ref - PFS NDT Register
7044c8c4-b43d-5a34-95c0-7a78cfe8f1cf | note | PFS Engineering - Team Leader
6884f91c-58fd-50ca-98f6-76b01c0d09cb | textbox | PFS Engineering: Sign - Initial: Sign:
c292bcfe-91b1-50d4-95ee-1328bd489419 | note | PFS Engineering: C - V
c26f953e-2517-4a35-a4e2-53d43d401f8f | checkpoint | 19 - NDT inspection
d95f092e-cebd-5a20-ae77-d1e8b3bf08dd | note | Specification Standard - Project Structure Specification C07 Rev. 01
06b6564c-07eb-5843-ad79-fb2c6f7b34ec | note | Acceptance Criteria - NDE shall include as a minimum:
4e4f7b8c-fe55-5026-9afa-d525b1384cfc | note | ○ 100% Visual Scanning, 100% Visual examination, 100% UT examination of all butt weld, 10% MT examination for fillet weld
468666c3-5897-5f16-a786-00d6a343c1b7 | note | ○ The Welding Compliance Inspector shall complete all inspections including any additional inspection, tests and reports necessary due to any welding or welding related workmanship defects.
6319a16b-2e7f-5297-984d-f77972986a5c | note | Certify Doc / Ref - Stamped NDT report
3af8f5e9-f5b1-5ef0-a194-fa415ea2aa3b | note | PFS Engineering - PM/PE
9d06b138-9180-5708-8c98-b1090462a87e | textbox | PFS Engineering: Sign - Initial: Sign:
06549222-01ff-574c-895b-e919af7b752e | note | PFS Engineering: C - RA
f3929341-3390-5c7b-afff-2462ccc94d58 | note | Subcontracted scope - NDT subcontractor
1e9184f3-c0a0-59cd-acc4-ed0412df781c | textbox | Subcontracted scope: Sign - Initial: Sign:
fbf60bae-4833-5b10-9226-ec63c9dc8839 | note | Subcontracted scope: C - S
29036fb6-d476-46d9-9a32-c5b490e6a29b | checkpoint | 20 - Protective Coatings Preparation
c8017608-e578-5ad1-9574-74206bcb0efd | note | Specification Standard - Project Structure Specification C07 Rev. 01
3d4266fd-c7ae-510b-886a-366316544c06 | note | Acceptance Criteria - Removal of all weld spatter and dressing of any weld to removed sharp edges / spatter.
4f647dd8-ffc3-5063-b0e2-597921e557cb | note | ○ All sharp edges are ground to a smooth 2 mm radius.
db540857-b791-55b8-918c-c09fec651dd9 | note | Certify Doc / Ref - N/A
6b623190-d374-5bd8-aaf4-d71a3751fe16 | note | PFS Engineering - Team Leader
b63a3c64-cc2c-5104-9d33-a012b14c69da | textbox | PFS Engineering: Sign - Initial: Sign:
c6096a05-4b17-5495-8d4f-baac234d3c20 | note | PFS Engineering: C - V
857c6237-03a7-4e38-b555-d7121576b359 | checkpoint | 21 - Fabrication NCR (if any)
a321c982-e905-59a6-a357-98b830f572e9 | note | Specification Standard - Project Structure Specification C07 Rev. 01
915d0de0-637a-5b1d-859a-d86d6c294f84 | note | Acceptance Criteria - All Non-conformities reported in PFS NCR system during manufacturing of steel structure need to be submitted to Client for approval
6ffedd34-d674-5565-9acd-64ff978772d7 | note | PFS Engineering - PM/PE
5459952d-50d1-522d-ad24-ae15696ba31f | textbox | PFS Engineering: Sign - Initial: Sign:
74b5bf22-f31f-5854-b87d-a66e8d2bf191 | note | PFS Engineering: C - S
dc2be97d-74f3-5202-b200-c1366ca5026f | note | Downer - Downer
2adb27cf-0476-584f-9b31-cbecea1a8580 | textbox | Downer: Sign - Initial: Sign:
efb353b1-220a-543b-ac29-c280ece946ba | note | Downer: C - RA
fa1e53bd-42b6-45b1-812c-640332eb6cb3 | section | Shop Assembly - Pannels, Handrails and Balustrades
9e9091f7-0bb3-4446-950d-b4293a855d92 | checkpoint | 22 - Inspection the free issue pannel uppon receipt at PFS work shop
be2dd62d-b3f0-50db-9c62-059eedb266c4 | note | Specification Standard - Pannel DWGs
580d7f81-5bb8-5731-97e3-66846cafc817 | note | Acceptance Criteria - Check pannel to make sure the quantity and/or dimension are based on approved DWGs.
f75da9f4-b3bf-5175-8522-d0d7729a6b63 | note | Certify Doc / Ref - Pannel DWGs
bb5aa5ff-5a26-563f-8390-56e159b72426 | note | PFS Engineering - Team Leader
3bb032ab-7cc2-5f70-8358-da201f3d2734 | textbox | PFS Engineering: Sign - Initial: Sign:
d290dc51-48e9-5c84-9d54-cd1e4b0b1c66 | note | PFS Engineering: C - V
1c78f1ba-7d8d-4014-81cb-c4241b30aafb | checkpoint | 23 - Panels Pre-assembly
fd9486b1-c111-56f0-90cb-ed14958d9dbe | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
ad153589-85e4-5ecb-8f0e-c63089648d34 | note | Acceptance Criteria - After painting, Client supplied pannels for decking and balastrades to be assembled.
42e31441-3454-52be-8100-34aba8bf956c | note | ○ Handrails need to be assembled in the shop
4577a12d-4870-5660-8556-7b4f05e1c354 | note | Certify Doc / Ref - IFC DWGs
85188df2-535b-59ae-9f1b-ebb0be67e6b4 | note | PFS Engineering - Team Leader
a2624df2-a387-54e7-8664-c3a07c077d4e | textbox | PFS Engineering: Sign - Initial: Sign:
39b4e23c-1af2-5d2c-bb70-04670ab2dac3 | note | PFS Engineering: C - V/D
227df8f1-b06b-41b2-b21a-e06205285c77 | checkpoint | 24 - Dimension check
2cd434b2-5277-5af4-920d-ce60991c998b | note | Specification Standard - IFC DWG
6ff5af8e-71c8-5590-bff1-4c4018dbbbf5 | note | Acceptance Criteria - Compliance with IFC DWGs
1f1ff052-39dd-5461-9715-e1a1fe35702b | note | PFS Engineering - Team Leader
e3f0ca12-ea98-57a9-9b6e-68f8ad23d66d | textbox | PFS Engineering: Sign - Initial: Sign:
7a5866bc-1220-50b5-ad15-3ac8b484d15f | note | PFS Engineering: C - D
0c40914e-173b-425e-b7a9-ebe91df4cf1f | checkpoint | 25 - Visual inspection of Fasteners (Free issue)
d5b8c06f-464e-5d3c-bb04-1be0e6e84ea6 | note | Specification Standard - IFC Drawing
ae2061f3-f3a4-537d-963e-3a55327781e6 | note | Acceptance Criteria - All fasteners (bolts, nuts, washers) are to be in complied with the Porject requirement (Grade, Size and Length)
d21bc913-bdf4-5217-91c6-0c8956575d4f | note | Certify Doc / Ref - IFC Drawing
5a3d4a14-2215-532e-af24-4804267d77a5 | note | PFS Engineering - Team Leader
39cbd608-fb84-583d-aa40-992e9527ea73 | textbox | PFS Engineering: Sign - Initial: Sign:
f2901bd2-456b-5a79-9050-2ae1a9243750 | note | PFS Engineering: C - V
97bc9699-8ba7-43a2-8a24-42992e8de927 | checkpoint | 26 - Snug tightening of conposite component fixings
4214486f-a4fe-5f17-bd86-f9d8309318c4 | note | Specification Standard - Standard operation procedure for steel structure bolt tightening, SHEQ-01-02-0038
f390d3ca-7fbb-5005-b523-0c233e01407f | note | Acceptance Criteria - 100% of fixings securing composite material to structure are to be inspected for snug tight condition and marked with coloured paint pen to confirm fixing condtion has been checked and verified.
dcbe8313-8033-571c-9b2e-19236d54a033 | note | PFS Engineering - Team Leader
4bdf45fe-75a4-54d8-8346-a0acc2b9ad89 | textbox | PFS Engineering: Sign - Initial: Sign:
df8ab45c-af8a-587e-b754-fb443a8b712a | note | PFS Engineering: C - V
ec3d7950-d35f-446b-9787-32d4eb08d057 | checkpoint | 27 - Final Inspection
e0715e85-6096-5188-a4e7-b74b82dc88fe | note | Specification Standard - IFC Drawings, AS/NZS 1554.1:2014 Category SP
af2093c7-da37-5083-937b-468ebeab56ae | note | Acceptance Criteria - Visual and Dimensional inspections completed by PFS Project Manager to confirm manufactured items have been manufactured to acceptable standard & tolerance and approved to progress to protective coatings.
ef723bac-eaa0-5b0a-98ec-7fdece1b737d | note | ○ >Confirmation that dimensional inspections have been completed in line with SHEQ-01-02-0035 Product Inspection Procedure
5c0415a8-24c4-5727-be6e-e74de10f0837 | note | ○ >Confirmation that required quantity and type's of NDE has been completed and any identified defects have been remediated.
1161bf71-7c83-5f98-a272-35d8f9c0aeef | note | Certify Doc / Ref - IFC DWGs
aa9d1cd5-54cc-52fd-8138-35942821d03d | note | PFS Engineering - PM/PE
fce3a980-437b-5276-bb37-2a9902cde726 | textbox | PFS Engineering: Sign - Initial: Sign:
ee0e2aa5-6714-5c7a-a2b5-4c92cd4aca2b | note | PFS Engineering: C - RA
dd9c9698-6c8c-4410-91ee-821b6c091f39 | section | Quality Review
a21be4ec-91c2-4cae-8b80-a65325a45cb1 | checkpoint | 28 - Compile, review and submit documentation
45c1d2ff-0345-5b21-8582-652781de523e | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
29296cb4-d467-5245-9845-cfff25273fc5 | note | Acceptance Criteria - Documentation, Certificates and reports to support manufacture of steel structure and subcontracted items compiled into PFS Manufactures Data Report
a7087cd2-08d5-574c-af2a-be6112aa3114 | note | Certify Doc / Ref - PFS Manufactures Data Report
5a8445c8-1039-56af-94d4-c81c0da30249 | note | PFS Engineering - PM/PE
11548525-71fa-550a-bc4e-cbc748a60c74 | textbox | PFS Engineering: Sign - Initial: Sign:
35f47abc-3f15-560f-b8a5-9a47db2fe118 | note | PFS Engineering: C - RA
ff1986d0-8857-5497-9cc6-1929491fd8db | note | Downer - Downer
589c554c-84ea-53b8-92a4-da13ce011c0b | textbox | Downer: Sign - Initial: Sign:
86eaf558-6c86-5cbd-a9dd-f2e2eb2d6f43 | note | Downer: C - RA
f617e6a8-d329-4ee8-945a-0c6b4fa4bd19 | section | ITP APPROVAL PROCESS
aa7a2c87-d5f6-484b-8532-d65f9b5947f3 | checkpoint-no-value | ITP APPROVAL PROCESS
b3068aa6-fa05-58af-888e-478a4ca03b52 | textbox | Approved by [Engineer/Client]:
82596f37-46e1-57d5-8203-f01263465f13 | textbox | Issued for Construction:
851dfbca-51cc-4e9b-9daf-15a4953b9583 | signoff | Sign:
5c9b2f45-1f47-4b60-a7b4-6f040dd9fc58 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
9947f51b-7603-509c-9da4-0c3af5fc690a | textbox | Contractor's Rep Name:
a0e33ef8-e111-5a73-888d-cf9a8b046c98 | textbox | Engineer's Rep. Name:
740dc1ca-cced-5ab6-a106-3f25c2e1fd0b | date | Date:
375638bf-1a0f-4711-b9ee-0040d4270433 | signoff | Add Signature
2b973694-f56f-4e6e-858a-1a5889d61d79 | checklist | DN1212-ITP-018 Shop fabrication - Span 4 RevD | itp | DN1212-ITP-018 Shop fabrication - Span 4
3bddc7ba-a9f8-4d13-b599-2a3fef139236 | section | Engineering
9c00d74c-35db-43d5-bda4-aec1aa8b2220 | checkpoint | 1 - Inspection and Test Plan Reviewed and Approved by Customer
f8b95a5c-5bca-5e9b-bfe5-f66ba91ac01e | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
104b34a3-e642-5be7-bd43-51f4780750cf | note | Acceptance Criteria - Inspection and Test plan shall be submitted to the Engineer for review and approval before fabrication is commenced.
ba5f4da6-32c7-56d6-aef8-bb39b3280162 | note | Certify Doc / Ref - IFC DWGs
026168b9-cdcd-5213-9864-6a611b09905c | note | PFS Engineering - PM/PE
3ed54f80-3585-5924-95e6-298df07aa820 | textbox | PFS Engineering: Sign - Initial: Sign:
20be5df4-e6b6-5822-b1c2-5e2a6e5172b9 | note | PFS Engineering: C - S
c0b197f8-e637-526a-9cc8-4864d24e7b78 | note | Downer - Downer
f3f8e306-9a0f-5c0c-9bb2-1028e4cd0711 | textbox | Downer: Sign - Initial: Sign:
dc3ba4ce-52d8-5a80-b80f-3f7087f3e03a | note | Downer: C - H
5065a2b3-6ae8-4907-8e53-04b389ff8785 | signoff | AUTHORITY HOLDPOINT
535fe5aa-0050-4c45-86fa-c63aa327652c | checkpoint | 2 - Shop Drawing approval
10300b2f-ef9a-51f4-9d59-2d2e1282bbfe | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
fe8e7b29-ca6a-528c-81c2-5b1b4991db60 | note | Acceptance Criteria - Shop Drawing shall be submitted to Engineer for review along with Shop Drawing Check form
7a50f129-5ce7-53bb-95bf-3647ef68b837 | note | Certify Doc / Ref - Shop Drawing Check form
3f78762c-697c-5c25-a3c8-7d09b3f6453d | note | PFS Engineering - PM/PE
a8248366-8e3e-5ce7-95b0-7dc6d50f34d4 | textbox | PFS Engineering: Sign - Initial: Sign:
7eb8474c-63b8-51c4-bbb2-22262731bb70 | note | PFS Engineering: C - S
b80f0726-1c81-5fb1-9139-57bd871bb5c2 | note | Downer - Downer
1076fac0-3c42-523f-abb7-8c3fc664bb75 | note | Downer: Sign - Initial: Sign:
7b2d933f-f47a-5eb5-89f3-50253d4a61cb | note | Downer: C - H
3250427d-d1e9-4ddd-bc46-74c762effd01 | signoff | AUTHORITY HOLDPOINT
c75788b1-2ea1-4fe6-8122-7f1e76c325a8 | checkpoint | 3 - Submit Inspection personel competencies
328278f1-ce7d-5963-91e0-c63d78e53479 | note | Specification Standard - Project Structure Specification C07 Rev. 01
e367c3d5-def2-5b1b-a683-3d9d3e7266f8 | note | Acceptance Criteria - Inspection personel (Independent inspectors) qualification and certificate shall be submitted to the Engineer for review and approval according to C0701.2.4
7c323315-1831-5d96-9ed1-2a2df8579179 | note | Certify Doc / Ref - NDT qualification
eb91f546-1054-59d3-93c9-05a1b1994cec | note | PFS Engineering - PM/PE
7725c8e7-a0d2-5b22-85ce-dc8116894286 | textbox | PFS Engineering: Sign - Initial: Sign:
b31837d5-1fbb-56db-ab9b-b622f4297870 | note | PFS Engineering: C - S
34000ade-facf-5430-8cfa-f3e681309b9f | note | Downer - Downer
0661ebba-a2c5-5f0e-a710-bf1c6b7771db | textbox | Downer: Sign - Initial: Sign:
381a1028-15f3-5db3-870c-7cbcaf80b93a | note | Downer: C - H
f233c070-9c28-4b5d-97fd-ca72f2d32c14 | signoff | AUTHORITY HOLDPOINT
19ce168c-100c-4fdf-b28f-a9d8fa229c18 | checkpoint | 4 - Welding Procedures - Structural
c6dc1ff6-e6b7-510d-bb25-aaf67c68a1ff | note | Specification Standard - AS/NZS 1554.1:2014 Category SP
34450a77-591a-5f97-a46c-f43799f1cd1d | note | Acceptance Criteria - Details of the welding procedures to be used including details of the equipment and consumables before any welding is carried out. No welder shall carry out work for which he is not certified.
d4ab093f-5775-5daa-9367-225b313c53de | note | Certify Doc / Ref - Welding Procedures HERA/CSWIP Stamp
7599d57e-d9e1-5535-9d09-de2276c85d9a | note | PFS Engineering - PM/PE
326e964e-55d2-5611-bd3e-a91c61f9e707 | textbox | PFS Engineering: Sign - Initial: Sign:
7e0be633-c89a-5aab-8388-ecc6a80db5a9 | note | PFS Engineering: C - S
4001def7-27c5-5553-9d2e-fdb0e2bef5a9 | note | Subcontracted scope - SQA
44ab5458-3039-5dd6-b7dc-02885e9aabc5 | textbox | Subcontracted scope: Sign - Initial: Sign:
76406ac9-d681-557d-b16e-f135790e618e | note | Subcontracted scope: C - RA
3c470301-fd02-48b3-8194-43a9f6a4af72 | checkpoint | 5 - Welder Qualifications - Structural
6dd69c39-37db-58d8-a8cf-b574481c770f | note | Specification Standard - AS/NZS 1554.1:2014, ISO 9606-1:2017
933fb1a3-8d8e-5fd6-a2ef-6faeb7b088f9 | note | Acceptance Criteria - A list of proposed welders and their welding certificatesto be provided prior to any welding being carried out.
c7077698-4a39-5c9d-b6cc-add1381c95b2 | note | ○ No welder shall carry out work for which he is not certified.
d44e6fc3-a0b4-5094-9e2b-3f68e06e26f5 | note | Certify Doc / Ref - WQT by Authorised Person (Welding Supervisor)
6ccc4a7b-33e5-5b7b-b578-98b5fda611fa | note | PFS Engineering - PM/PE
8ab1b1ba-7f80-5187-83e7-80157063a13e | textbox | PFS Engineering: Sign - Initial: Sign:
7eedd602-6ed1-5b6f-93f5-fff6c3d7f7f8 | note | PFS Engineering: C - S
51de156b-01b6-5d30-95ff-5518fd00c737 | note | Subcontracted scope - SQA
6888a95f-529c-5402-b694-f140a503cf15 | textbox | Subcontracted scope: Sign - Initial: Sign:
7150612d-e79b-565d-9342-53384a218047 | note | Subcontracted scope: C - RA
7a97812c-46fd-4c16-8b10-f18b5a12c1c0 | checkpoint | 6 - Submit the required documents to Client for review
3fbcfcab-27c2-5269-aa0f-b226805c00ce | note | Specification Standard - Project Structure Specification C07 Rev. 01
eb98432a-619b-5ee1-a759-2c977040d022 | note | Acceptance Criteria - Following shall be submitted to the Engineer for review before fabrication is commenced:
4318a0e2-b062-5576-ab72-f69e42665dbf | note | 1 - Quality Management Plan
0ded98df-2918-527f-bee8-a109bbbe16bb | note | 2 - IMS Manual
223eb062-48fe-59c5-aa8c-b00a1c394f12 | note | 3 - SFC Certificate
984e221c-577d-5241-9255-5229ff5e34c6 | note | 4 - ISO 9001 Certificate
c0692e6d-d48c-5fe8-a15c-2ce11e486d34 | note | Certify Doc / Ref - Quality certificates, Quality Plan
f29e5e4f-83ab-5330-8784-b7edf12894c4 | note | PFS Engineering - PM/PE
93e8a8b6-8221-5484-ad57-bca587442e80 | textbox | PFS Engineering: Sign - Initial: Sign:
7dc81f69-cb14-5233-9fcc-e4dbbeec04f2 | note | PFS Engineering: C - S
da5c9745-9c26-5ab8-b21e-889b086b3998 | note | Downer - Downer
98d6cb00-e381-594e-9a7a-29c0ce15042c | textbox | Downer: Sign - Initial: Sign:
2215059b-5218-556a-b78e-4ed8a0998e2d | note | Downer: C - R
c4af6429-d759-436e-9db3-c01915d31552 | section | Procurement
a5a1c10d-e310-4451-97f8-f16885fbb1f0 | checkpoint | 7 - Procurement of materials in line with IFC drawings and Technical Specification
975f0df2-67cd-5bbe-b2dc-43d192caf0e9 | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
421c7489-e26f-5d6b-ac30-8de5288f1abe | note | Acceptance Criteria - Materials match that specified in Project IFC drawings and Technical Specification.
2f92b4b9-4127-55ae-b64a-9aa1fafda414 | note | ○ Structural steel Material shall be sourced from suppliers certified by ACRS
b33a5db3-98ad-5f43-8029-773eb396dbe7 | note | ○ Material test certificates shall report all element required by AS/NZS relevant standard, plus total boron content (Manufacturer certificates shall from ILAC MRA laboratories)
46caff8d-aa3b-57e2-bb10-dbeeaf40fdc5 | note | Certify Doc / Ref - Supplier Material Certificate
1f781c03-1884-50a1-b9aa-35632fbe8565 | note | PFS Engineering - PM/PE
d1505b8f-b3de-5654-9c88-ab659e40805a | textbox | PFS Engineering: Sign - Initial: Sign:
28038d04-cb10-5cc7-9752-3b736b349e84 | note | PFS Engineering: C - RA/S
be4a0027-7d8f-5a52-a963-ca634467d439 | note | Downer - Downer
a3d5566d-d0c6-5bf8-894e-670ea46eca34 | textbox | Downer: Sign - Initial: Sign:
a8558202-8ebe-5a44-ad0b-2f354f41ea60 | note | Downer: C - H
cc6ff9d2-ff6e-489a-bef3-ecb7bb829d33 | signoff | AUTHORITY HOLDPOINT
0d983f1f-4c92-4f26-a0c2-6fb9bcaa21ee | checkpoint | 8 - Procurement of Welding consumable to match Weld procedure and parent materials.
ed8e36b4-fd54-5ac9-8198-c2fdac4b6098 | note | Specification Standard - AS/NZS 1554.1
140d28c4-4bf2-5a0f-9513-10474e7b464d | note | Acceptance Criteria - Welding consumables and gas match what is specified on the appropriate welding procedures.
092d44a6-1fe3-5ea0-b107-6101414ebed8 | note | Certify Doc / Ref - Supplier Material Certificate, PFS Welding Procedures
0064b658-ff9a-5882-b969-02c2a46b9fd5 | note | PFS Engineering - PM/PE
6ee0702d-f435-5acc-b477-7f710f097f5f | textbox | PFS Engineering: Sign - Initial: Sign:
30c89309-9143-5681-ad28-9f90a5457327 | note | PFS Engineering: C - RA
a52c57d0-ef16-45ac-a93f-1055864e0689 | checkpoint | 9 - Material inspection upon receiving (By supplier/sub-contractor/ Free issue material)
14facdf0-9232-54a9-a9dc-c78697ca8d66 | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
14a84a4e-f3bf-523c-b9a5-b32b4f8edcc7 | note | Acceptance Criteria - All material shall be inspected against IFC drawing to make sure material grades, type, thickness, size are in compliance with IFC DWGs.
fec8a5b4-10b7-5e44-80c0-1376bb8fe543 | note | Certify Doc / Ref - IFC DWGs
2c575d0c-7e1c-5a8c-b0f7-db726ea38afe | note | PFS Engineering - Team Leader
5980036a-1eec-59d1-b6f3-c897f8e6f6f0 | textbox | PFS Engineering: Sign - Initial: Sign:
cd375367-5f33-5245-a2cf-648876493bdb | note | PFS Engineering: C - H
502b12c7-178f-460b-b72d-17ea1638f27f | signoff | AUTHORITY HOLDPOINT
6b7ba1ff-64f1-45fd-9a01-40936e2af8de | section | Steel structure Fabrication
d3a3eb36-6b8f-4cd3-9cdd-abc70a59991a | checkpoint | 10 - Manufacturing Work Pack Issued to Production Manager
93e8866c-6682-553e-8f13-8e2deafe4a90 | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
3b6f9bbd-bce7-50be-b4c2-e238e4447ca4 | note | Acceptance Criteria - Job barcodes, Inspection & Test Plan's, IFC Fabrication Drawings, Reference Drawings/Info, Welding Procedures, weld map, welding log info, traceability sheet
575ed633-ab2d-5d44-8bb6-99b364d41bc9 | note | PFS Engineering - Production Manager
3b909e24-e4b2-53f3-bcdf-7ffa0224e9ee | textbox | PFS Engineering: Sign - Initial: Sign:
5fca5b9d-cd4a-5734-9a99-f1b55130492d | note | PFS Engineering: C - RA
eda20a35-9ea9-4ff5-992c-2de2bbc15ba7 | checkpoint | 11 - Cutting the structural steel
d900d7f0-fa73-5559-9c51-4b3e2f329439 | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG, SHEQ-01-02-0039
7e68dc8c-00b6-5a34-8f1d-db43c19c4ec9 | note | Acceptance Criteria - Dimensional survey of fabricated item's against IFC drawings.
357c7623-34df-5a66-a914-a49bcc8d222f | note | ○ Measured dimensions shall be within Functional Tolerances class 2 as per AS/NZS 5131 Table F2.1 to F2.10
19100649-ebb1-5e9b-aeb7-4a2e2dba6702 | note | Certify Doc / Ref - IFC DWGs
cb6dca29-6db4-54ce-a61a-451b2f62c1ad | note | PFS Engineering - Team Leader
5b36afe7-c950-57f1-b80a-6c2bddfdbfb8 | textbox | PFS Engineering: Sign - Initial: Sign:
fc7ea945-1956-5bfc-83a3-9278dba7908a | note | PFS Engineering: C - D
1a0c4e46-7309-403f-bd4e-cfa4728eae43 | checkpoint | 12 - Holing
3e7c8741-195e-5e30-8fcb-c7bdbd16ee56 | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG, SHEQ-01-02-0040
0a2aaaaa-abeb-51c1-a681-1318721f2191 | note | Acceptance Criteria - Dimensional survey of fabricated item's against IFC drawings.
24c1e3d9-beeb-5391-9663-306a562a6a29 | note | ○ Measured dimensions shall be within Functional Tolerances class 2 as per AS/NZS 5131 Table F2.1 to F2.10
8f6453a8-2f7e-5e3b-9dc8-c6daf57164c8 | note | Certify Doc / Ref - IFC DWGs
210648fe-3905-5487-9fe9-572540edb8b6 | note | PFS Engineering - Team Leader
f18ae122-1c1d-5da0-a0ed-bca6ab16c857 | textbox | PFS Engineering: Sign - Initial: Sign:
68381cd5-1009-513a-b4bd-fe96f1bcd713 | note | PFS Engineering: C - D
65a825b7-8081-4185-b291-51b3f6d69f36 | checkpoint | 13 - Identification and traceability for main items
50e2d1f5-4d85-5f0e-9a99-b7e8b617b710 | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG, AS/NZS 5131
0b60bb45-5957-5fd9-be10-63e5b289cae3 | note | Acceptance Criteria - Lot traceability shall be provided for main structural members, connections between main structural members and major plate components. Tracibility as per AS/NZS 5131:Amd 1:2020 5.2.3 (ii) for minor components including cleats, connecting brackets and the like.
3e9a93eb-cede-531a-a243-154e76c2432a | note | Certify Doc / Ref - IFC DWGs
428cc82a-7909-58b7-93d8-c38e00da3344 | note | PFS Engineering - PM/PE
64a62fe7-12e6-55ae-b193-8ed44769e1e0 | textbox | PFS Engineering: Sign - Initial: Sign:
f49072f9-4899-548f-801f-e7924816f25e | note | PFS Engineering: C - H
cf20d15f-18d5-432c-ba3f-7f3bd81a4507 | signoff | AUTHORITY HOLDPOINT
35d35506-ee80-4271-8c25-661d40369c43 | checkpoint | 14 - Manufacture of steel structure - Tack welded only
371aa29b-2b29-5fbc-ab64-ea2531ce9c10 | note | Specification Standard - IFC DWGs
71f0fb86-f981-5e0d-b780-c485869b05d0 | note | Acceptance Criteria - Manufacture completed as per IFC Fabrication drawings.
099189e4-82c7-5117-bd63-aa9bee477c5f | note | ○ All tack welding shall be performed in accordance with PFS weld procedure.
1a7ef3b4-3698-5001-97c7-a94e72d35bf4 | note | ○ Welding consumables, process & any applicable pre/post heat requirements shall comply with approved welding procedure's.
e20312c3-3825-550f-9d68-887e79f2367a | note | Certify Doc / Ref - IFC DWGs
f6ced7a4-67a9-5291-9376-78c3d086c7fa | note | PFS Engineering - Team Leader
9dac969f-868d-5730-bb15-6218b7a1b162 | textbox | PFS Engineering: Sign - Initial: Sign:
525819cf-a24c-55a4-a45d-6e7ebb66448e | note | PFS Engineering: C - D
dc42536f-54b5-40a2-b82f-859823e6f092 | checkpoint | 15 - Pre Weld Dimensional Check (Tack Check)
21a34d6c-fddd-5a96-8fa6-3842e7ebe004 | note | Specification Standard - IFC Drawings
168b83e1-5e46-5a23-a2fc-17ef8e54ceba | note | Acceptance Criteria - Dimensional survey of fabricated item's against IFC drawings.
8727946d-fff0-560c-ad94-e2392e459c23 | note | ○ Measured dimensions shall be within stated tolerances unless noted otherwise.
92a5ad67-5a75-53f4-8aa1-9a510ef871c5 | note | ○ Project specification clause C0702.1.3
4bd99aa0-665f-5b34-8ded-ac6b136fe98c | note | ○ Functional Tolerances shall be class 2 as per AS/NZS 5131 Table F2.1 to F2.10
407b2219-9885-5fa2-9e87-7156f6516846 | note | ○ Inspections recorded in line with SHEQ-01-02-0035 Product Inspection Procedure
9a1ccced-2c0f-5065-a792-26656cb0df53 | note | Certify Doc / Ref - IFC DWGs
62f5ab8a-f5d3-5e1e-8f57-ec93076c9d80 | note | PFS Engineering - Team Leader
b038f2f1-7b75-5102-a6a8-2b46a1d3b508 | textbox | PFS Engineering: Sign - Initial: Sign:
e445a356-a151-5055-958f-2948ec09d4f7 | note | PFS Engineering: C - D
4e08d0e8-86ff-4996-8f14-6ff43cb7da23 | checkpoint | 16 - Welding
45b68132-fa95-51cf-b80c-5b3c460351e0 | note | Specification Standard - AS/NZS 1554.1, AS/NZS 9606.1
2a9ab8d8-d36b-552a-8373-a665720e0bbe | note | Acceptance Criteria - All welding shall be performed in accordance with PFS weld procedures
e56138aa-0180-5c20-98c8-d6443dd30f1c | note | ○ Welding consumables, process & any applicable pre/post heat requirements shall comply with approved welding procedure's. Welder ID, weld date & consumable batch are recorded on traceability register.
479a1566-e503-5f43-98a5-083845b54a00 | note | Certify Doc / Ref - Welding Procedure and Welder Qualification
54d4055c-ab5c-5ce0-aec8-8d208da2e825 | note | PFS Engineering - Team Leader
3a1d7bb6-f9fa-5499-8080-51f237376cc7 | textbox | PFS Engineering: Sign - Initial: Sign:
133cc2cc-d59e-596c-b264-9c0d7fbd56af | note | PFS Engineering: C - V
af9336b9-0477-4799-be17-8793816fbcf9 | checkpoint | 17 - Post Weld Dimensional Check
760b4e33-0493-5ae4-82e0-6aad75af8d5b | note | Specification Standard - IFC DWGs
6e2eb0b5-2127-5b10-8db5-018c90df6364 | note | Acceptance Criteria - Dimensional survey of fabricated item's against IFC drawings.
44c5926a-0d44-5c07-a56c-eb423c7ad6a7 | note | ○ Measured dimensions shall be within stated tolerances unless noted otherwise.
62335b5c-fefe-50a3-b26d-8eb2358b4e33 | note | ○ Project specification clause C0702.1.3
b47ab510-b5e8-5c40-96f1-a96b90d80cb2 | note | ○ Functional Tolerances shall be class 2 as per AS/NZS 5131 Table F2.1 to F2.10
3c43c57e-ec91-5530-abed-e10212a19b4d | note | ○ Inspections recorded in line with SHEQ-01-02-0035 Product Inspection Procedure
b43b113b-d1a3-58a9-ba72-941980d97d41 | note | Certify Doc / Ref - IFC DWGs & Workshop Pack.
ee78db30-c62f-5993-a258-1e52a3e11ef2 | note | PFS Engineering - Team Leader
51285178-79f0-5ec4-bd21-794d577a1db5 | textbox | PFS Engineering: Sign - Initial: Sign:
315c21a7-e96d-5e82-b0fc-fbfe300dd48e | note | PFS Engineering: C - D
fac55762-96a4-48a8-bb85-d715595cf9b7 | checkpoint | 18 - Weld Visual Scanning (PFS Internal Check)
08fa743d-1be8-5bb6-bdcd-a6ef84dd7223 | note | Specification Standard - IFC Drawing
41c66f2c-1c21-5006-9d2d-bd2a4f02d6f9 | note | Acceptance Criteria - 100% of all welds shall be subject to visual scanning
3a5aab0e-b445-55e1-98b0-b92e77235288 | note | Certify Doc / Ref - PFS NDT Register
ff5eba78-5241-57f5-bac9-d7c66a21373f | note | PFS Engineering - Team Leader
0296ab7a-bacc-5c90-9087-0a401aaecb9a | textbox | PFS Engineering: Sign - Initial: Sign:
82bab3bf-7fee-5f7f-acd1-142084a17c27 | note | PFS Engineering: C - V
3a30f0e9-6838-46cd-9abb-dd58fbace191 | checkpoint | 19 - NDT inspection
0dd376b5-aef5-5531-8c2d-edfb8a8d3234 | note | Specification Standard - Project Structure Specification C07 Rev. 01
786e7368-0c05-567b-a9e8-c4dfe0c2fc48 | note | Acceptance Criteria - NDE shall include as a minimum:
e9d9cce1-8fc2-582e-aede-9338fe90966d | note | ○ 100% Visual Scanning, 100% Visual examination, 100% UT examination of all butt weld, 10% MT examination for fillet weld
3aca3b8c-4741-5a23-9ac5-1c4266b4ae3a | note | ○ The Welding Compliance Inspector shall complete all inspections including any additional inspection, tests and reports necessary due to any welding or welding related workmanship defects.
e499719a-ced6-5927-8013-72f7abffe87f | note | Certify Doc / Ref - Stamped NDT report
bd20e176-c692-5de8-bd3d-d21d118885c9 | note | PFS Engineering - PM/PE
eb2483e2-5e8b-5ff6-9350-5546ccb87312 | textbox | PFS Engineering: Sign - Initial: Sign:
d6ddde5d-cc78-5d07-81f5-96417bfa52e2 | note | PFS Engineering: C - RA
c334f6ca-0756-5fdc-82da-fcff0885c274 | note | Subcontracted scope - NDT subcontractor
a451bf0d-32bd-5c7c-b839-f32003cebed3 | textbox | Subcontracted scope: Sign - Initial: Sign:
5ada20d6-ad7e-5b43-82f6-261b5bc9f31f | note | Subcontracted scope: C - S
5f8b9ce8-0c2a-4712-8a5a-2da8f9ac9298 | checkpoint | 20 - Protective Coatings Preparation
98c72a1e-fd7e-5649-af7d-a117bcdd05dd | note | Specification Standard - Project Structure Specification C07 Rev. 01
c6b36927-6944-5324-8ff8-85f3155cf4c4 | note | Acceptance Criteria - Removal of all weld spatter and dressing of any weld to removed sharp edges / spatter.
f15b1544-d478-5d01-b94c-2f212e3c05d0 | note | ○ All sharp edges are ground to a smooth 2 mm radius.
de6f90e9-62da-5e99-bad6-ee0df5513cf6 | note | Certify Doc / Ref - N/A
c2a9a5df-b690-518b-9f67-a48a17985529 | note | PFS Engineering - Team Leader
efae0035-0f0e-5974-800a-a16b4ab3034a | textbox | PFS Engineering: Sign - Initial: Sign:
ab928d2b-e786-5890-a525-96f2cb761945 | note | PFS Engineering: C - V
02fe3298-e59c-4c42-9191-9f0931456bf8 | checkpoint | 21 - Fabrication NCR (if any)
1ec7775c-152f-5bf3-adff-907e57db6bec | note | Specification Standard - Project Structure Specification C07 Rev. 01
580eb21f-ecd2-564a-bd6c-9091815faa7f | note | Acceptance Criteria - All Non-conformities reported in PFS NCR system during manufacturing of steel structure need to be submitted to Client for approval
bfe1ff61-e9ce-576c-a92e-730bae9ed5ce | note | PFS Engineering - PM/PE
bcf54a8d-e60e-5d05-bdcc-1126b80ba595 | textbox | PFS Engineering: Sign - Initial: Sign:
f9b86567-e52e-5872-b28f-a3f33761ee64 | note | PFS Engineering: C - S
4bb7682a-e469-595b-8c10-9417a57b4a7d | note | Downer - Downer
9210ac24-8ab2-5142-8f66-8017f4a9dcc5 | textbox | Downer: Sign - Initial: Sign:
167287df-c434-5bb3-93f5-b725ebd43d44 | note | Downer: C - RA
9d7dbf2b-5172-49e2-8cbf-cb0e68e5b7d7 | section | Shop Assembly - Pannels, Handrails and Balustrades
f84e5f58-3528-4ef9-98a6-245f078fca72 | checkpoint | 22 - Inspection the free issue pannel uppon receipt at PFS work shop
349df295-5676-5128-b1bc-fb36a1a9b365 | note | Specification Standard - Pannel DWGs
04789261-6352-5010-b6ff-629174bcfc41 | note | Acceptance Criteria - Check pannel to make sure the quantity and/or dimension are based on approved DWGs.
8b7c0977-e5cb-5dbd-92e3-0a04d75bac6c | note | Certify Doc / Ref - Pannel DWGs
f956610e-e8e0-5942-ac9c-50aaeb37d074 | note | PFS Engineering - Team Leader
fbc58378-ed4e-55f5-8262-0e109909f5e5 | textbox | PFS Engineering: Sign - Initial: Sign:
18e59d33-9390-59c3-b1e8-9c1b6c1a2d76 | note | PFS Engineering: C - V
f261aa55-6baa-4437-b041-61ce6ced7264 | checkpoint | 23 - Panels Pre-assembly
78032b89-ba33-512d-a57e-15d54e660886 | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
419b1c72-933c-53d1-ae8c-233ae0b32dd5 | note | Acceptance Criteria - After painting, Client supplied pannels for decking and balastrades to be assembled.
a19bfb30-8eaf-5be3-a025-17bfa9a0096e | note | ○ Handrails need to be assembled in the shop
b4f3dc91-abab-5e2e-8df8-b1bc83fbecc7 | note | Certify Doc / Ref - IFC DWGs
6404c89e-e30e-5847-a907-d0cd884475a6 | note | PFS Engineering - Team Leader
9121428d-7f57-561f-8e55-8d77a7408040 | textbox | PFS Engineering: Sign - Initial: Sign:
6c9c0df8-1d59-57e5-aecd-cd5f707d4627 | note | PFS Engineering: C - V/D
306822d9-7644-41b8-b754-4537bc7f05e7 | checkpoint | 24 - Dimension check
78c3a4a0-588f-52cb-acad-9bd1209bc185 | note | Specification Standard - IFC DWG
2fe1516c-549d-5e44-b3dd-b8cef8fc86f9 | note | Acceptance Criteria - Compliance with IFC DWGs
7fc40eee-5929-51fb-817c-0d26b2b832ae | note | PFS Engineering - Team Leader
b847a047-72c9-5df6-9865-9f9295a47f99 | textbox | PFS Engineering: Sign - Initial: Sign:
2bc4ec46-166c-51b4-bf3d-2a55b66998c5 | note | PFS Engineering: C - D
15fc740c-d4f0-42ca-b297-504c8276b045 | checkpoint | 25 - Visual inspection of Fasteners (Free issue)
a40b3bd0-d7b5-59f6-94cc-76677aa56cd1 | note | Specification Standard - IFC Drawing
a4efb6e3-9c52-554b-93a0-2d65a79367bb | note | Acceptance Criteria - All fasteners (bolts, nuts, washers) are to be in complied with the Porject requirement (Grade, Size and Length)
55734643-5249-5d7b-b0a8-b7847842a586 | note | Certify Doc / Ref - IFC Drawing
fea621e7-b95b-57ce-a95f-11252782571a | note | PFS Engineering - Team Leader
007c37a9-b9f0-5742-a4be-8c5fefaf96f3 | textbox | PFS Engineering: Sign - Initial: Sign:
fc692ee4-682e-54a1-b53b-997eeacbfda4 | note | PFS Engineering: C - V
b347cb95-bf90-4131-b4bd-38a0bb5f297e | checkpoint | 26 - Snug tightening of conposite component fixings
44bbd86a-e468-54c6-a4bd-4c701500e256 | note | Specification Standard - Standard operation procedure for steel structure bolt tightening, SHEQ-01-02-0038
d4610e38-0151-5f61-b11f-bac654e9f647 | note | Acceptance Criteria - 100% of fixings securing composite material to structure are to be inspected for snug tight condition and marked with coloured paint pen to confirm fixing condtion has been checked and verified.
440aa9ec-6f54-5737-91bf-8204c931d959 | note | PFS Engineering - Team Leader
f19d810d-708b-5d4d-b839-7e9cd5d8eaa1 | textbox | PFS Engineering: Sign - Initial: Sign:
a9d31090-3043-5f02-8442-d93f7d30c35a | note | PFS Engineering: C - V
a406474d-64af-44a4-aac8-4a7094c65a70 | checkpoint | 27 - Final Inspection
bdfce0d1-33f6-5d3a-8a4c-f24b8bdfb295 | note | Specification Standard - IFC Drawings, AS/NZS 1554.1:2014 Category SP
f2e3b7a0-5e9d-5269-8144-1a5d2b5b1235 | note | Acceptance Criteria - Visual and Dimensional inspections completed by PFS Project Manager to confirm manufactured items have been manufactured to acceptable standard & tolerance and approved to progress to protective coatings.
8884dac7-b17c-5efd-a039-ad6fd311805f | note | ○ >Confirmation that dimensional inspections have been completed in line with SHEQ-01-02-0035 Product Inspection Procedure
1ae39610-fbd9-536b-b5c6-8d363b336208 | note | ○ >Confirmation that required quantity and type's of NDE has been completed and any identified defects have been remediated.
de5e2aaa-7450-5896-b898-84b24d20e4f1 | note | Certify Doc / Ref - IFC DWGs
960c76da-c3cc-5497-a841-5e5c3665476f | note | PFS Engineering - PM/PE
6f966a68-833e-5ec7-8a66-65ef51a594e4 | textbox | PFS Engineering: Sign - Initial: Sign:
3f19183b-2288-56a6-9188-482226d41bce | note | PFS Engineering: C - RA
c2c35233-641b-4062-b73d-d300114d1f1a | section | Quality Review
c5f47bc3-f951-4277-8417-8921ff667212 | checkpoint | 28 - Compile, review and submit documentation
c09cf9c6-aa1c-5bff-aed0-d188e791441b | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
6a3daae5-28cd-583c-95c0-4a5ca4c6475b | note | Acceptance Criteria - Documentation, Certificates and reports to support manufacture of steel structure and subcontracted items compiled into PFS Manufactures Data Report
4fc48d4c-6d71-535f-8f27-4bec555edbaa | note | Certify Doc / Ref - PFS Manufactures Data Report
f2a40ab1-1886-5610-bbcf-86b19a3b4fce | note | PFS Engineering - PM/PE
5edac39b-4d25-5c4c-a3e3-9a88df51ddb0 | textbox | PFS Engineering: Sign - Initial: Sign:
77e3db58-c4e6-513a-9701-793139d98812 | note | PFS Engineering: C - RA
5826c74f-b835-5f26-b4b1-b56562eb1c85 | note | Downer - Downer
b49478e7-ad55-5a5d-8fca-b708716583f1 | textbox | Downer: Sign - Initial: Sign:
cf7f9247-3650-54bd-ae73-527a34de2aa2 | note | Downer: C - RA
4473d366-f65e-4a59-9f10-c62dbefe3e4b | section | ITP APPROVAL PROCESS
6ca90dda-bf9f-4d0c-a066-fdb5cc5740a1 | checkpoint-no-value | ITP APPROVAL PROCESS
0dd3be3d-c9db-505a-ab5e-fbd7d47fa38b | textbox | Approved by [Engineer/Client]:
21bb152f-7f30-529e-a97d-8693725f19ba | textbox | Issued for Construction:
91040c1b-4fcf-4a89-82b6-055a0f087d39 | signoff | Sign:
ce034d49-958c-418e-94ff-2efe234cc4b7 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
5c30c1cc-11b5-58ac-842c-ca1d2adcd819 | textbox | Contractor's Rep Name:
40c74469-e5a2-50e3-8eb2-b3636726680c | textbox | Engineer's Rep. Name:
67036896-5151-5546-9b4e-d91986443bcd | date | Date:
b04c10fd-bcd8-4ec9-bc3d-931cd55e2db7 | signoff | Add Signature
5402261b-2ab7-4498-a20b-738be492a72f | checklist | DN1212-ITP-019 Shop fabrication - Span 5 RevD | itp | DN1212-ITP-019 Shop fabrication - Span 5
e6c1f28a-6c17-4120-8a36-3ccc5f7e55ff | section | Engineering
9bf41516-f91d-43cd-bb19-c366a9841e6a | checkpoint | 1 - Inspection and Test Plan Reviewed and Approved by Customer
1d3f4864-1870-5513-8b9d-9bfc686cf6fe | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
37027913-918f-5886-9b05-c0bf5efe9f2f | note | Acceptance Criteria - Inspection and Test plan shall be submitted to the Engineer for review and approval before fabrication is commenced.
5e36f389-d540-5f84-9771-5bd8daf45f9a | note | Certify Doc / Ref - IFC DWGs
a7c8d238-3fd4-5c98-b401-f30d2ef04024 | note | PFS Engineering - PM/PE
a63573c1-c9c5-5692-b245-65f8074be12f | textbox | PFS Engineering: Sign - Initial: Sign:
73def0c2-f113-5548-bde0-cfbafeec26c0 | note | PFS Engineering: C - S
2e4d0142-ccb4-504a-963d-611b32583fc8 | note | Downer - Downer
05eb741a-6f4f-5096-959d-b60bf6f76040 | textbox | Downer: Sign - Initial: Sign:
75c1fc4a-bff6-51cc-af3e-0ab7e3681825 | note | Downer: C - H
658413d5-df9e-49ed-9d78-13827b437cb3 | signoff | AUTHORITY HOLDPOINT
f150aa1f-6cbe-42de-833b-02b8a0081baf | checkpoint | 2 - Shop Drawing approval
94d3b5a7-ead0-5bd9-8ba5-1c7bc54dc74c | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
f1ddccf7-e4af-5cf9-89f8-abca0f95b693 | note | Acceptance Criteria - Shop Drawing shall be submitted to Engineer for review along with Shop Drawing Check form
c1929701-0280-56f9-87b0-bd7bf3b63d07 | note | Certify Doc / Ref - Shop Drawing Check form
6cfc0723-ae0e-5c06-8d9d-e40602cdd3cc | note | PFS Engineering - PM/PE
5002ffe2-f4f1-59f9-b047-757e39f899e3 | textbox | PFS Engineering: Sign - Initial: Sign:
e355d6eb-b3c2-5061-a730-2845801b69ef | note | PFS Engineering: C - S
d7d978e3-369f-5971-be4d-2cdbc1b07a84 | note | Downer - Downer
57f54fc5-2358-5345-bea1-52c25e00d244 | note | Downer: Sign - Initial: Sign:
b9e294cd-1697-511e-bd59-374ae24e3d30 | note | Downer: C - H
96dff7d6-d180-4eb4-86b7-14df5be0afad | signoff | AUTHORITY HOLDPOINT
195873e7-0015-4d6f-afcb-886f4c038c14 | checkpoint | 3 - Submit Inspection personel competencies
ab8b7b4b-e18e-5a0f-a283-c94d25281faf | note | Specification Standard - Project Structure Specification C07 Rev. 01
54ff479a-26c1-552c-9beb-b25fdc82985d | note | Acceptance Criteria - Inspection personel (Independent inspectors) qualification and certificate shall be submitted to the Engineer for review and approval according to C0701.2.4
6e7cc4b7-1edd-594a-9534-d1b36aa41089 | note | Certify Doc / Ref - NDT qualification
d845481f-595f-5e5d-92ec-55f12941578c | note | PFS Engineering - PM/PE
f80a8d31-8c8c-5c9d-9e05-2f61253b8ebf | textbox | PFS Engineering: Sign - Initial: Sign:
c0123473-849b-56a6-ae4b-015737445c02 | note | PFS Engineering: C - S
7c7c0fff-a67e-5552-aebb-2ec65128e609 | note | Downer - Downer
92085964-8163-56c8-88cf-604f1966ad8f | textbox | Downer: Sign - Initial: Sign:
281afcc9-6475-5a73-ac15-47fd783c968d | note | Downer: C - H
e7cbd42c-da5f-4291-9358-8970a6b0b1b9 | signoff | AUTHORITY HOLDPOINT
93b79814-2285-483a-b1eb-b5eb3ec2cfdc | checkpoint | 4 - Welding Procedures - Structural
1f2bb26b-d347-528d-ac1c-a3bdccc65cdb | note | Specification Standard - AS/NZS 1554.1:2014 Category SP
313551ac-020c-54da-af72-678b62e7bd17 | note | Acceptance Criteria - Details of the welding procedures to be used including details of the equipment and consumables before any welding is carried out. No welder shall carry out work for which he is not certified.
86b871f4-4808-57d8-bdcb-cd32ac0bc273 | note | Certify Doc / Ref - Welding Procedures HERA/CSWIP Stamp
1b4d1872-d7eb-52f3-9ffc-b33dc3f5524d | note | PFS Engineering - PM/PE
2f9d6ffe-63a5-5ad9-87b4-14684b4bfb7c | textbox | PFS Engineering: Sign - Initial: Sign:
a2b99865-f472-57c3-81b9-9d61a633eacd | note | PFS Engineering: C - S
aac523f0-c889-5763-bf25-0fcd176c52f4 | note | Subcontracted scope - SQA
0ec8143a-93a3-5cfa-8bd1-6826cbc830ff | textbox | Subcontracted scope: Sign - Initial: Sign:
43ec85bb-4eb0-5375-9e1d-50c431136873 | note | Subcontracted scope: C - RA
8961924b-1af5-43b2-82e6-cf94074d2c15 | checkpoint | 5 - Welder Qualifications - Structural
ebed6be8-507d-5693-adca-87386ac3d1c6 | note | Specification Standard - AS/NZS 1554.1:2014, ISO 9606-1:2017
c2c23434-ef7c-5e2d-bd12-600e0ae6d3fa | note | Acceptance Criteria - A list of proposed welders and their welding certificatesto be provided prior to any welding being carried out.
74cac586-23fd-5f9a-8f21-2c1c31c3114a | note | ○ No welder shall carry out work for which he is not certified.
775b450f-6088-5210-bfef-7bdc976e71bd | note | Certify Doc / Ref - WQT by Authorised Person (Welding Supervisor)
27f61682-c225-5293-a9a9-aa54f7f75044 | note | PFS Engineering - PM/PE
d8994c62-a6c6-5631-af9c-0d4fc18fa929 | textbox | PFS Engineering: Sign - Initial: Sign:
d7fae3f9-394f-50e5-9e36-05fac4df93a7 | note | PFS Engineering: C - S
a20d56bf-6e19-5ad5-b908-c2735b32b36b | note | Subcontracted scope - SQA
5f67d64b-7096-502c-9a37-e6352a8455d6 | textbox | Subcontracted scope: Sign - Initial: Sign:
959f38be-d6aa-5bba-976b-cc6062bed19f | note | Subcontracted scope: C - RA
def60d86-5e3e-4839-ae2a-7a9eeec9242f | checkpoint | 6 - Submit the required documents to Client for review
c8479f70-1cbf-5ab3-9950-271a81e59641 | note | Specification Standard - Project Structure Specification C07 Rev. 01
e6cae513-f870-5cbf-a6ca-f40f4e95f602 | note | Acceptance Criteria - Following shall be submitted to the Engineer for review before fabrication is commenced:
a872d3ce-6743-5687-8b37-ee167c4c4d22 | note | 1 - Quality Management Plan
d3f6e56b-97ee-5600-b41b-4606169e1bb6 | note | 2 - IMS Manual
576dc225-2de6-5504-b86e-5ce47f924724 | note | 3 - SFC Certificate
a2234eed-01c1-54b0-9070-b6e695d5a3fc | note | 4 - ISO 9001 Certificate
6af1b5b9-b0d5-5c33-9072-54951e33c379 | note | Certify Doc / Ref - Quality certificates, Quality Plan
ae70775b-396f-5965-b5d1-7b8ac05908cf | note | PFS Engineering - PM/PE
4ec20414-8de9-587b-bc72-5f1e19a393ae | textbox | PFS Engineering: Sign - Initial: Sign:
b9cbaaa4-2d12-50b3-87bf-9b4cf32c0808 | note | PFS Engineering: C - S
606fafb6-b55f-5dda-a8f0-7389a14ecaac | note | Downer - Downer
ec2325b1-8136-55cb-8405-60aee0ec80bc | textbox | Downer: Sign - Initial: Sign:
39954aae-f04e-5077-a5f0-8864572bf3ed | note | Downer: C - R
67891b5e-34ba-463a-8efc-109186841325 | section | Procurement
b20f5723-01cf-48b5-99b9-fe3452643155 | checkpoint | 7 - Procurement of materials in line with IFC drawings and Technical Specification
2c917d33-268b-52d3-94be-c9d2556ae5f3 | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
6d7a4331-1176-5afe-8da6-09516aef82ec | note | Acceptance Criteria - Materials match that specified in Project IFC drawings and Technical Specification.
2e91154e-e783-5cd6-8ea9-6f92b018ac01 | note | ○ Structural steel Material shall be sourced from suppliers certified by ACRS
11abd6a9-2d59-5f90-a1c1-4d46d0b14085 | note | ○ Material test certificates shall report all element required by AS/NZS relevant standard, plus total boron content (Manufacturer certificates shall from ILAC MRA laboratories)
aa5e53a9-5cf3-5b59-894a-6ec0a19779bf | note | Certify Doc / Ref - Supplier Material Certificate
b0195648-6587-558d-960d-44630d314ae1 | note | PFS Engineering - PM/PE
3d7649f5-2571-5a62-98f0-e83d9acfdf12 | textbox | PFS Engineering: Sign - Initial: Sign:
ed721a53-f493-5a35-962f-197fff735c75 | note | PFS Engineering: C - RA/S
6ed047bc-2e74-588d-b189-a5db4de47de1 | note | Downer - Downer
ed357c3c-7987-5cff-b3f8-f6454d69f3be | textbox | Downer: Sign - Initial: Sign:
47d97e18-74b8-5347-9737-fa2ebb16a034 | note | Downer: C - H
4fc370cf-2ace-45d9-87f0-1a3105460aa4 | signoff | AUTHORITY HOLDPOINT
3282c2ea-0394-4087-ada5-902e130c3cde | checkpoint | 8 - Procurement of Welding consumable to match Weld procedure and parent materials.
793e80a1-82e6-53b7-b217-77c6ff81c8de | note | Specification Standard - AS/NZS 1554.1
644ef58d-cd73-5866-90be-71d95c6a8666 | note | Acceptance Criteria - Welding consumables and gas match what is specified on the appropriate welding procedures.
b94d4d19-170a-573f-9392-fa984ca1df4d | note | Certify Doc / Ref - Supplier Material Certificate, PFS Welding Procedures
8dea1c25-bae4-57c8-bdd8-188b9608721a | note | PFS Engineering - PM/PE
8807ba84-6cda-58e7-b669-3670e5aaff14 | textbox | PFS Engineering: Sign - Initial: Sign:
749f1e89-d077-5a6c-8b85-4ff4459bde03 | note | PFS Engineering: C - RA
ebc2d496-7b2d-4ec5-ac99-029905cfef36 | checkpoint | 9 - Material inspection upon receiving (By supplier/sub-contractor/ Free issue material)
90547b37-2af7-5de8-9410-891ccbb2fa8e | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
a5cc5916-32ca-5c6b-b47d-3a4d3dc8455c | note | Acceptance Criteria - All material shall be inspected against IFC drawing to make sure material grades, type, thickness, size are in compliance with IFC DWGs.
7cd8cab1-55b7-5844-a62e-2d67aee0a6eb | note | Certify Doc / Ref - IFC DWGs
59efd39b-ae7f-5191-9378-78b93eadcbc5 | note | PFS Engineering - Team Leader
290b9535-7317-5045-a937-7af17a4f863a | textbox | PFS Engineering: Sign - Initial: Sign:
691162d1-674f-5811-9d7d-50dada01cd15 | note | PFS Engineering: C - H
ec70e2af-a750-4115-94a8-9f666f3a646c | signoff | AUTHORITY HOLDPOINT
f9c7fc23-a7d9-4406-8b55-ab086b648d6d | section | Steel structure Fabrication
4dda3d88-2061-4c9c-a785-69edccc86e24 | checkpoint | 10 - Manufacturing Work Pack Issued to Production Manager
84b0a63b-da73-50f9-a437-d8dc9ee43a70 | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
48fcf33f-2b85-5cfd-9665-23f02d210535 | note | Acceptance Criteria - Job barcodes, Inspection & Test Plan's, IFC Fabrication Drawings, Reference Drawings/Info, Welding Procedures, weld map, welding log info, traceability sheet
e1cbeaf9-5936-5a6a-bed9-f1146d52cdf6 | note | PFS Engineering - Production Manager
004fb282-40a3-5ddd-a21a-b554ec6eebee | textbox | PFS Engineering: Sign - Initial: Sign:
5eb2252b-f164-5616-9e72-9a6d48dd4e64 | note | PFS Engineering: C - RA
8acea2a5-889e-4fda-99c2-7ac92e9a48a9 | checkpoint | 11 - Cutting the structural steel
04d09414-fd18-57a2-9e67-2f2f6c348afd | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG, SHEQ-01-02-0039
3860eec2-2783-5f59-beb1-681c32aaef78 | note | Acceptance Criteria - Dimensional survey of fabricated item's against IFC drawings.
4365b2cf-0f7e-5ef1-a976-2d17060a4066 | note | ○ Measured dimensions shall be within Functional Tolerances class 2 as per AS/NZS 5131 Table F2.1 to F2.10
56333cae-6b4c-564e-b5a2-11df0bb6ab72 | note | Certify Doc / Ref - IFC DWGs
5985141f-8426-5480-8dc1-62091d072110 | note | PFS Engineering - Team Leader
0a1e27e5-2b9a-5b80-8a2b-a32f71a6c25b | textbox | PFS Engineering: Sign - Initial: Sign:
5544b905-34fb-50f2-bce5-068b5dd56a14 | note | PFS Engineering: C - D
0f0dceba-b960-40cf-bdbd-2fcd6ffc3011 | checkpoint | 12 - Holing
902a5e3f-fa5c-5335-a0d2-b268f4fc350f | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG, SHEQ-01-02-0040
2e994291-7ca6-5066-851b-11de35cf7890 | note | Acceptance Criteria - Dimensional survey of fabricated item's against IFC drawings.
149c4b21-bf17-55c5-b420-3315f35b287c | note | ○ Measured dimensions shall be within Functional Tolerances class 2 as per AS/NZS 5131 Table F2.1 to F2.10
bc70a675-0ba0-5296-91bd-dd5736e114b8 | note | Certify Doc / Ref - IFC DWGs
c30f2353-d504-5a49-833a-bd3655bb0c7a | note | PFS Engineering - Team Leader
2e9cbb84-46ef-5552-b57e-ea236da4a803 | textbox | PFS Engineering: Sign - Initial: Sign:
34a15d3a-c643-54d0-88f8-7813519f5cc0 | note | PFS Engineering: C - D
5f74d2e8-8d57-4ff6-bdb6-7281f08dbcb2 | checkpoint | 13 - Identification and traceability for main items
dfcb5cf6-2af5-52d7-8bd2-f39d88e0417b | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG, AS/NZS 5131
4a739d47-8651-5443-b270-7b0aaf39cd58 | note | Acceptance Criteria - Lot traceability shall be provided for main structural members, connections between main structural members and major plate components. Tracibility as per AS/NZS 5131:Amd 1:2020 5.2.3 (ii) for minor components including cleats, connecting brackets and the like.
79af5562-bcd7-5d45-b9d1-2385ab09d5cb | note | Certify Doc / Ref - IFC DWGs
5dff05ef-4fd8-573f-90d1-1cfd516749a0 | note | PFS Engineering - PM/PE
ca9c89ba-a2c4-5a62-85ee-033712eefe40 | textbox | PFS Engineering: Sign - Initial: Sign:
4f44aca6-b155-557f-83a1-8396b68b00f5 | note | PFS Engineering: C - H
21d0e6d2-bc9b-42f2-bb30-342f378aff8a | signoff | AUTHORITY HOLDPOINT
2fed962a-c832-4b4f-bd3d-10371a5266e8 | checkpoint | 14 - Manufacture of steel structure - Tack welded only
6f789654-9984-57cb-ab16-5f1d39773e2d | note | Specification Standard - IFC DWGs
d48bddb7-2147-5e3b-8a18-58cd0383bfc9 | note | Acceptance Criteria - Manufacture completed as per IFC Fabrication drawings.
d759f13b-b2cf-5faf-8fa5-e2b47f365ded | note | ○ All tack welding shall be performed in accordance with PFS weld procedure.
c65caf89-9a6f-55b9-a0e7-5ad1214cfe69 | note | ○ Welding consumables, process & any applicable pre/post heat requirements shall comply with approved welding procedure's.
3e1cbe5b-bb28-5524-943f-8379e17bf608 | note | Certify Doc / Ref - IFC DWGs
5c802856-05c5-5cb6-8549-5738f6cd4e83 | note | PFS Engineering - Team Leader
9fb956f0-ab47-5ff6-91a8-b6c3df40972b | textbox | PFS Engineering: Sign - Initial: Sign:
387e4554-1c5a-56ed-afea-7c63d56f26bf | note | PFS Engineering: C - D
f7f3437d-2e6f-48dd-aa77-ffb932d5a71d | checkpoint | 15 - Pre Weld Dimensional Check (Tack Check)
fb5a8de7-6f68-594b-b341-08d3c7d56a04 | note | Specification Standard - IFC Drawings
97ef8cfd-e130-5ff9-8518-bd86a8d08486 | note | Acceptance Criteria - Dimensional survey of fabricated item's against IFC drawings.
6430ed1e-c10e-51c7-9cfb-d2d9a93ba75c | note | ○ Measured dimensions shall be within stated tolerances unless noted otherwise.
11fcda99-675d-52d9-ac5a-9cce2b95d9bb | note | ○ Project specification clause C0702.1.3
ec6f253b-f072-5d92-b738-756094d86db5 | note | ○ Functional Tolerances shall be class 2 as per AS/NZS 5131 Table F2.1 to F2.10
b2343ee8-d95e-5c22-8fd0-5a57d42eb728 | note | ○ Inspections recorded in line with SHEQ-01-02-0035 Product Inspection Procedure
47621613-a2be-5ad2-93af-c8f39efafca2 | note | Certify Doc / Ref - IFC DWGs
9979e250-66b4-514f-9acd-08fb5b36acdd | note | PFS Engineering - Team Leader
205012b7-a8b0-5e6d-b142-c886e266221c | textbox | PFS Engineering: Sign - Initial: Sign:
b78d6eca-2714-5121-9489-a8a5d9c79935 | note | PFS Engineering: C - D
f7c07dd5-7270-4772-a4cb-e4a8fd331fdf | checkpoint | 16 - Welding
0ab673cd-db3d-546c-afe4-c34a1ef5d22d | note | Specification Standard - AS/NZS 1554.1, AS/NZS 9606.1
018b56b1-19a6-5504-90e6-ea014e316b08 | note | Acceptance Criteria - All welding shall be performed in accordance with PFS weld procedures
a59aca09-ece3-54ec-b85c-c70bed978ed0 | note | ○ Welding consumables, process & any applicable pre/post heat requirements shall comply with approved welding procedure's. Welder ID, weld date & consumable batch are recorded on traceability register.
40e17344-65ee-593c-8221-f810fed2d5b8 | note | Certify Doc / Ref - Welding Procedure and Welder Qualification
58faa9bf-fb7d-5765-83a4-be8a78248ca3 | note | PFS Engineering - Team Leader
9bcf14e4-41f1-5330-8dc8-f7adcf3bd1b0 | textbox | PFS Engineering: Sign - Initial: Sign:
482d1971-6530-51b8-9b89-35c44f507dd6 | note | PFS Engineering: C - V
88a8c9e6-d006-4489-b758-9f92629557aa | checkpoint | 17 - Post Weld Dimensional Check
f377529b-8459-5e10-a700-b4563ad9de61 | note | Specification Standard - IFC DWGs
9b2fde74-2b69-5ddc-896c-87944af908e0 | note | Acceptance Criteria - Dimensional survey of fabricated item's against IFC drawings.
813019db-e2ea-5efb-bc94-a6dc0e652cd9 | note | ○ Measured dimensions shall be within stated tolerances unless noted otherwise.
dcf56a0c-77d2-5739-b85e-d07034e17262 | note | ○ Project specification clause C0702.1.3
09a68555-ccea-5a54-9f54-0895f07377e2 | note | ○ Functional Tolerances shall be class 2 as per AS/NZS 5131 Table F2.1 to F2.10
d19efc29-871f-59ce-8d1f-2c55034641e4 | note | ○ Inspections recorded in line with SHEQ-01-02-0035 Product Inspection Procedure
63da37b8-1659-50ab-a98a-4f1052c65b69 | note | Certify Doc / Ref - IFC DWGs & Workshop Pack.
74b6d963-0a4c-537b-8a49-5efb5c2341fc | note | PFS Engineering - Team Leader
ef8efd93-1b45-5c75-8147-898f3ee54c82 | textbox | PFS Engineering: Sign - Initial: Sign:
e163c450-7445-5d6c-b385-0eeabcd730c4 | note | PFS Engineering: C - D
ea42ed5a-d279-4b0a-8936-d5880df49b2f | checkpoint | 18 - Weld Visual Scanning (PFS Internal Check)
ebb213e8-6e71-5afc-bb43-e58662e6bc9f | note | Specification Standard - IFC Drawing
c1de6db4-b53f-5e1c-99fa-4ed55f4a9b0e | note | Acceptance Criteria - 100% of all welds shall be subject to visual scanning
c08f5443-492f-5aed-a8ab-73820c845eb8 | note | Certify Doc / Ref - PFS NDT Register
3bb24c73-b0d7-5b9b-9fc6-85cc5c849c07 | note | PFS Engineering - Team Leader
f35e45cf-fcfd-5489-8245-c421eaa42beb | textbox | PFS Engineering: Sign - Initial: Sign:
bb153bbf-ca33-525d-a104-c24e3af2395a | note | PFS Engineering: C - V
cf04e812-5fe6-42c1-9f38-3b4e4efe1398 | checkpoint | 19 - NDT inspection
80925fd7-50ec-58e8-931c-f6e7f587573a | note | Specification Standard - Project Structure Specification C07 Rev. 01
26cb592b-d36b-5d1f-8552-bacd150465b2 | note | Acceptance Criteria - NDE shall include as a minimum:
48cd782a-0aea-5aff-9011-6e5155ba4fc4 | note | ○ 100% Visual Scanning, 100% Visual examination, 100% UT examination of all butt weld, 10% MT examination for fillet weld
539c128a-cf70-5dd2-80c8-9381692e98c5 | note | ○ The Welding Compliance Inspector shall complete all inspections including any additional inspection, tests and reports necessary due to any welding or welding related workmanship defects.
f8415b4c-dd48-5419-8cb1-236242630895 | note | Certify Doc / Ref - Stamped NDT report
bbc71509-21d3-5748-bd30-6bfc788e00d0 | note | PFS Engineering - PM/PE
0d0aff1e-34d9-5418-bec0-98eb74517f4a | textbox | PFS Engineering: Sign - Initial: Sign:
390fa214-f85f-5a47-8c6c-0f2fd999a0d6 | note | PFS Engineering: C - RA
16390dca-40d5-5c92-ad0a-1660b7273be6 | note | Subcontracted scope - NDT subcontractor
5a4dc81b-22f2-5bf1-9287-5bd39d1ccf87 | textbox | Subcontracted scope: Sign - Initial: Sign:
d58b2842-32b0-5772-93f8-9455253ba4eb | note | Subcontracted scope: C - S
0907e263-93cb-45ff-90b8-a95493071880 | checkpoint | 20 - Protective Coatings Preparation
03eca22f-986f-5bcb-80c5-97d112e8c1d6 | note | Specification Standard - Project Structure Specification C07 Rev. 01
0a689de1-ba78-5d7c-8b0d-c7d5bb495fb4 | note | Acceptance Criteria - Removal of all weld spatter and dressing of any weld to removed sharp edges / spatter.
33d452a6-f07f-5fe4-886d-46a77d741e38 | note | ○ All sharp edges are ground to a smooth 2 mm radius.
880f392f-b56a-5d5b-9fd5-399915251d31 | note | Certify Doc / Ref - N/A
88f57d9b-3033-5553-8d2b-e2f19fde2210 | note | PFS Engineering - Team Leader
daa425ec-f72c-5959-a0db-f54e06fd037c | textbox | PFS Engineering: Sign - Initial: Sign:
37196709-9687-50e7-bf34-b071bd0a4b98 | note | PFS Engineering: C - V
e80446cf-907c-4f74-a035-064256d3b7c4 | checkpoint | 21 - Fabrication NCR (if any)
e4315bac-7045-59ca-8bb0-69d78add587e | note | Specification Standard - Project Structure Specification C07 Rev. 01
769e7b93-1ca3-51fb-b112-4d58c6ebf534 | note | Acceptance Criteria - All Non-conformities reported in PFS NCR system during manufacturing of steel structure need to be submitted to Client for approval
6eea148e-7e50-5c61-bfc0-3a4d2b3f4ffc | note | PFS Engineering - PM/PE
b03391a7-4968-5c3c-a40f-5d0c9fb91da6 | textbox | PFS Engineering: Sign - Initial: Sign:
bdea325a-db17-5259-a7c3-ba45a45c0433 | note | PFS Engineering: C - S
5717e4c9-18f0-54ef-8fbd-462851b904d4 | note | Downer - Downer
1346be25-4c97-57c0-841c-e6a55d0a1871 | textbox | Downer: Sign - Initial: Sign:
2a459f8a-4a0e-55c6-bf4f-5166321517fd | note | Downer: C - RA
7abba1e9-d3b2-4fbd-8bda-6678f404d751 | section | Shop Assembly - Pannels, Handrails and Balustrades
957092bd-32b9-48b7-a2c7-d76760a93372 | checkpoint | 22 - Inspection the free issue pannel uppon receipt at PFS work shop
5e008939-de06-57f9-9b8b-4ccb6bae5202 | note | Specification Standard - Pannel DWGs
afa98170-a1e6-543e-862c-5e6bcd8d4e0f | note | Acceptance Criteria - Check pannel to make sure the quantity and/or dimension are based on approved DWGs.
2ac77b0b-1739-5b45-9c5e-bac42d83448b | note | Certify Doc / Ref - Pannel DWGs
93913fb7-1c6e-54dc-9781-8704764824ec | note | PFS Engineering - Team Leader
3d7485b8-b562-5069-8f4b-b4c8a4c0909a | textbox | PFS Engineering: Sign - Initial: Sign:
cd62e6f4-3172-5f9d-88ac-1efb5aa7e118 | note | PFS Engineering: C - V
b76bf930-69b6-4d14-9067-3b0ce6ae2636 | checkpoint | 23 - Panels Pre-assembly
2d4403d1-c50f-5a11-8183-df701ff72803 | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
be8c4ee3-37e4-5b70-8af1-1afb11b9bdae | note | Acceptance Criteria - After painting, Client supplied pannels for decking and balastrades to be assembled.
fe6accd5-ee90-591e-acbe-4b3208c81a2d | note | ○ Handrails need to be assembled in the shop
cc88ce7a-9496-5854-8b22-a1a8a9efbd31 | note | Certify Doc / Ref - IFC DWGs
e2f5b951-0212-5909-bb4c-60ef294a5169 | note | PFS Engineering - Team Leader
5fd36e48-f2e6-54d2-be96-d1b942f2d199 | textbox | PFS Engineering: Sign - Initial: Sign:
fb849d2d-d8c7-5a34-aa9c-85cf68c3825e | note | PFS Engineering: C - V/D
109994f2-edd9-49b3-a066-79b6f816d985 | checkpoint | 24 - Dimension check
3e958098-f36c-556e-b54b-fc9ecda93136 | note | Specification Standard - IFC DWG
1d08e0aa-9941-529a-b791-ed4265f9ee45 | note | Acceptance Criteria - Compliance with IFC DWGs
04d99209-55fc-587a-b239-abb060c0866d | note | PFS Engineering - Team Leader
338bf2ed-69b0-595a-b563-021dedd5dfe7 | textbox | PFS Engineering: Sign - Initial: Sign:
2c3a2888-8771-5207-a8e3-0e4286be403c | note | PFS Engineering: C - D
ef328147-ec11-4862-aa32-1feee6f6c52a | checkpoint | 25 - Visual inspection of Fasteners (Free issue)
9a2eb504-4cec-53cc-9b3b-1eca2515bd1c | note | Specification Standard - IFC Drawing
cef2dc7a-fbf2-5828-aa45-9e4bbc712b26 | note | Acceptance Criteria - All fasteners (bolts, nuts, washers) are to be in complied with the Porject requirement (Grade, Size and Length)
8db55ad9-c9cd-56df-8de8-7429df63e82f | note | Certify Doc / Ref - IFC Drawing
5d22edbd-7253-53cd-b8ec-dc15b60e1807 | note | PFS Engineering - Team Leader
758bc637-4786-585a-9c20-d3ead2fa1bd7 | textbox | PFS Engineering: Sign - Initial: Sign:
ba0f8daf-4907-53b2-88ae-2fa12a8945c1 | note | PFS Engineering: C - V
1959b7ef-5d04-4b0b-a6df-8e473bb4f761 | checkpoint | 26 - Snug tightening of conposite component fixings
43080b85-a1cd-506e-b564-5379440d5fdd | note | Specification Standard - Standard operation procedure for steel structure bolt tightening, SHEQ-01-02-0038
b876e43c-2c15-5fad-add0-fbb3c2b074f9 | note | Acceptance Criteria - 100% of fixings securing composite material to structure are to be inspected for snug tight condition and marked with coloured paint pen to confirm fixing condtion has been checked and verified.
97d84b6d-2d47-59c9-abd3-c60c3d7d1941 | note | PFS Engineering - Team Leader
da2fc97a-718f-5ae5-8e92-bd4ebde0f35a | textbox | PFS Engineering: Sign - Initial: Sign:
4805ce7d-313e-557b-a9c2-c869de3529c5 | note | PFS Engineering: C - V
f854f502-65d0-4564-bcdf-9594abf6b4b4 | checkpoint | 27 - Final Inspection
9f6dd224-031f-53a8-a5d0-168a8e14fefc | note | Specification Standard - IFC Drawings, AS/NZS 1554.1:2014 Category SP
d16279e3-5f33-57c1-acd0-cd611a2a82b9 | note | Acceptance Criteria - Visual and Dimensional inspections completed by PFS Project Manager to confirm manufactured items have been manufactured to acceptable standard & tolerance and approved to progress to protective coatings.
49e4cce1-05fc-58a4-8b3e-c9dceabc9a6e | note | ○ >Confirmation that dimensional inspections have been completed in line with SHEQ-01-02-0035 Product Inspection Procedure
368d3a90-2e1f-5676-a8d6-8a7576264ea8 | note | ○ >Confirmation that required quantity and type's of NDE has been completed and any identified defects have been remediated.
b26d0af5-4eb4-50ff-801a-7597d5c5e79a | note | Certify Doc / Ref - IFC DWGs
e8db9c42-e069-596f-b342-a332b5a49b0d | note | PFS Engineering - PM/PE
a073f3da-9ea4-5adb-b8e9-9a75b9397a18 | textbox | PFS Engineering: Sign - Initial: Sign:
c3e86e2c-69cc-51b2-8624-8f42c773a640 | note | PFS Engineering: C - RA
61059a31-36c5-4ebb-9de4-223cf84ac4be | section | Quality Review
f47742a3-2ccf-4330-95e3-d393c4b23cce | checkpoint | 28 - Compile, review and submit documentation
ae7a2502-80e3-5af6-ae1b-b27e81eea6f1 | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
dd9fb946-4efa-5a35-9422-1b6ede15ad0c | note | Acceptance Criteria - Documentation, Certificates and reports to support manufacture of steel structure and subcontracted items compiled into PFS Manufactures Data Report
73b5e168-9421-574f-961d-12f68dc5bdae | note | Certify Doc / Ref - PFS Manufactures Data Report
cc83d1da-5238-5c8c-b602-520fc3c3b3f2 | note | PFS Engineering - PM/PE
78b97b6e-bf0d-513f-a3d8-9798711ac0c3 | textbox | PFS Engineering: Sign - Initial: Sign:
baeb71e3-a0e1-515e-a117-a34ed8b216f3 | note | PFS Engineering: C - RA
de2ebd18-e1b2-5ea2-872c-0ce1d06fe26e | note | Downer - Downer
bb5ae6ad-48af-5fa0-937a-e26df25798df | textbox | Downer: Sign - Initial: Sign:
66d61cc7-0483-54d7-b797-192bb0f58d88 | note | Downer: C - RA
96725fdf-b151-41c6-b0a4-4376df19e83c | section | ITP APPROVAL PROCESS
1aa7bb16-c29a-4513-b656-eba683ea6991 | checkpoint-no-value | ITP APPROVAL PROCESS
cae923db-3b41-5443-beb9-b1f465561e90 | textbox | Approved by [Engineer/Client]:
c7a0efab-ceaa-5ff7-945e-7b7a064460bf | textbox | Issued for Construction:
aeeb0bd9-1cb4-4033-85b3-68aa145531f3 | signoff | Sign:
1f16a3ef-e312-4a00-b0c2-b1e566d1afe9 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
b488abf7-b2f0-5d34-9ae6-b805619e90d7 | textbox | Contractor's Rep Name:
0fc9d3e8-2129-5bf5-bb08-701569611576 | textbox | Engineer's Rep. Name:
c1085f43-edf0-5796-83c6-5b776573bfad | date | Date:
654f46b5-c8d1-4434-997b-66e99fbc43fb | signoff | Add Signature
6b11aa8f-5ad7-4df2-ac0a-cd86c66b8ac9 | checklist | DN1212-ITP-020 Shop fabrication - Span 6 RevD | itp | DN1212-ITP-020 Shop fabrication - Span 6
b2147743-a0f9-4d95-bac2-1c2140392692 | section | Engineering
59c9768c-9bfc-4136-ac3b-bf49f0169f15 | checkpoint | 1 - Inspection and Test Plan Reviewed and Approved by Customer
646385ce-6714-5880-9a46-f4bd3d96aa25 | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
6ae1ef10-d3e5-5268-946e-a15e9f734edc | note | Acceptance Criteria - Inspection and Test plan shall be submitted to the Engineer for review and approval before fabrication is commenced.
79f759c6-4555-5e16-a550-5099c7d2dd73 | note | Certify Doc / Ref - IFC DWGs
79560f53-2690-567a-9194-384794f4cbd6 | note | PFS Engineering - PM/PE
988ed9c3-ff17-5157-bbdf-494edcec6fc2 | textbox | PFS Engineering: Sign - Initial: Sign:
9af40e01-5104-5db9-a1d4-77f7a68b89a3 | note | PFS Engineering: C - S
5b10a60a-a8bf-5852-a5dc-15e9f081581c | note | Downer - Downer
433bf8a1-1c82-508e-b3d5-f6e8cc2b5e51 | textbox | Downer: Sign - Initial: Sign:
858a7a28-16c1-56a2-9500-3ad454f3dbea | note | Downer: C - H
434f2d2a-780a-480d-a7f6-c1ce37c45d8f | signoff | AUTHORITY HOLDPOINT
535dcc02-c58a-4021-a5c9-4276cfe1a7c2 | checkpoint | 2 - Shop Drawing approval
de4c0c29-306c-59d8-9e47-e4f809739607 | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
f4d0958d-9b57-5583-a670-5feec496f5f8 | note | Acceptance Criteria - Shop Drawing shall be submitted to Engineer for review along with Shop Drawing Check form
76a84faa-8f19-5423-a7c9-ad1881ad97b4 | note | Certify Doc / Ref - Shop Drawing Check form
36385e55-1323-5c7e-a15e-d52485ebb98b | note | PFS Engineering - PM/PE
d140ee36-5952-55bf-bbba-b278f9338404 | textbox | PFS Engineering: Sign - Initial: Sign:
97e40c64-b2a1-54f0-82f4-73530ccccd29 | note | PFS Engineering: C - S
d63a4a42-ddc9-5518-ab7f-444da34a8750 | note | Downer - Downer
639ccc36-4dd8-5d94-8da5-b264120f764d | note | Downer: Sign - Initial: Sign:
e1839aac-eb70-55c2-8417-685c9a11db4b | note | Downer: C - H
55d0d59f-ba14-47ab-909b-5edecac41e68 | signoff | AUTHORITY HOLDPOINT
0886fbd9-f2da-4975-90e4-b1d71f823bd4 | checkpoint | 3 - Submit Inspection personel competencies
ef4c6b95-d3f0-52e9-a570-ce22e0b36772 | note | Specification Standard - Project Structure Specification C07 Rev. 01
9fd324ae-1b2b-5476-ad99-06590888988e | note | Acceptance Criteria - Inspection personel (Independent inspectors) qualification and certificate shall be submitted to the Engineer for review and approval according to C0701.2.4
fff95582-a84f-5658-8b2d-877b677058fc | note | Certify Doc / Ref - NDT qualification
e74434c2-656f-53e0-b99b-d2fee9d3f84f | note | PFS Engineering - PM/PE
c4c55230-426b-5e8f-b425-2d46496387b0 | textbox | PFS Engineering: Sign - Initial: Sign:
3bce1d2d-f00f-5f5b-b7e6-a87ac2b80de1 | note | PFS Engineering: C - S
45dc02c1-b17a-5e53-837e-c8529e0a70bf | note | Downer - Downer
3214421a-2f1c-502f-b2c4-a021b3025ac4 | textbox | Downer: Sign - Initial: Sign:
c2b600fb-70bd-5cd7-9384-34929a6e1716 | note | Downer: C - H
23cf6ae6-4964-4911-9f85-9cb66aed27f3 | signoff | AUTHORITY HOLDPOINT
a7b77cbc-c77f-4414-8c86-7e10dfbe5f96 | checkpoint | 4 - Welding Procedures - Structural
f20e9782-8d0b-5fca-ab02-1c54f991fe64 | note | Specification Standard - AS/NZS 1554.1:2014 Category SP
be5f78ad-a237-556a-8f5d-37407eff4c09 | note | Acceptance Criteria - Details of the welding procedures to be used including details of the equipment and consumables before any welding is carried out. No welder shall carry out work for which he is not certified.
d91fb96b-33f4-5204-b492-97083ce4d4ad | note | Certify Doc / Ref - Welding Procedures HERA/CSWIP Stamp
a202d735-0019-5223-8fac-985abd5d04fd | note | PFS Engineering - PM/PE
67fb3844-d2d6-52ce-af11-b59d07471f32 | textbox | PFS Engineering: Sign - Initial: Sign:
a7dd8ce0-3da7-5b43-8d0f-b102bbf773f2 | note | PFS Engineering: C - S
62c71b2d-9065-57e2-826b-9135899f7a8f | note | Subcontracted scope - SQA
855af788-318b-5b89-bd44-1da352308432 | textbox | Subcontracted scope: Sign - Initial: Sign:
9c8fc299-cbdc-547a-83f9-860e88e95c29 | note | Subcontracted scope: C - RA
a3b72487-712c-4f47-842f-4d3eb5310fac | checkpoint | 5 - Welder Qualifications - Structural
2061144e-bf19-5a9f-be5d-715737489b95 | note | Specification Standard - AS/NZS 1554.1:2014, ISO 9606-1:2017
cba9f976-5629-5b54-b881-585c0e45648e | note | Acceptance Criteria - A list of proposed welders and their welding certificatesto be provided prior to any welding being carried out.
05d8f243-0abc-5165-b31d-5254d3840174 | note | ○ No welder shall carry out work for which he is not certified.
0babf7c3-b71b-51d5-a1cc-ebff874fe1ae | note | Certify Doc / Ref - WQT by Authorised Person (Welding Supervisor)
0a310c8f-99c3-5e33-bc58-04a81c57042e | note | PFS Engineering - PM/PE
6788957f-ff22-5f29-b3c0-3ee937d993a5 | textbox | PFS Engineering: Sign - Initial: Sign:
a7bae2da-2c3b-5b84-8b6a-601ec9cc7489 | note | PFS Engineering: C - S
e7af81ba-212d-577f-8a79-891e29a6fecf | note | Subcontracted scope - SQA
441f9da2-b2e2-5ebb-95e0-f07d9078e4f0 | textbox | Subcontracted scope: Sign - Initial: Sign:
d19d3047-2d4f-54a3-81be-ffa17becef44 | note | Subcontracted scope: C - RA
df5636bb-7be1-40bd-9db1-20a07f56eee0 | checkpoint | 6 - Submit the required documents to Client for review
bcc2d8de-4d63-50d6-b047-da80434cc129 | note | Specification Standard - Project Structure Specification C07 Rev. 01
d2fa85e6-cd7d-5e75-a547-9f8f293c017c | note | Acceptance Criteria - Following shall be submitted to the Engineer for review before fabrication is commenced:
632b454a-f0e6-5c1e-8e22-3ff0e7ba8878 | note | 1 - Quality Management Plan
38b4132f-0541-588c-9fc1-99bf2b276f47 | note | 2 - IMS Manual
af9985ac-6a03-5121-a16f-a8ed71bf34b9 | note | 3 - SFC Certificate
37baeaad-e13f-57e7-a4c7-34390dd2670f | note | 4 - ISO 9001 Certificate
b8f81e0f-6cae-5877-aae9-612eff08012a | note | Certify Doc / Ref - Quality certificates, Quality Plan
7e641ed0-aa91-53e8-a519-a6ff3bab22f4 | note | PFS Engineering - PM/PE
55dcdb22-ce87-5544-8265-058da9bf8c05 | textbox | PFS Engineering: Sign - Initial: Sign:
fa221f4b-af94-5ccb-8df8-bd77379178ac | note | PFS Engineering: C - S
e5f5a349-d6f3-5816-82de-271caebab571 | note | Downer - Downer
d685ec31-46c7-5ee3-9f58-a48e2287e542 | textbox | Downer: Sign - Initial: Sign:
1a7d31f9-fd73-563a-9c29-9e4399fe8de7 | note | Downer: C - R
e99ca8a2-98bb-487b-ae04-843170dc6429 | section | Procurement
5f429108-d6aa-4849-9af4-45e3eab3d63e | checkpoint | 7 - Procurement of materials in line with IFC drawings and Technical Specification
66358d18-6ee3-5f6c-bfc2-c8ee95030102 | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
31ec03ff-1b1b-5057-88ed-0c405ad31a90 | note | Acceptance Criteria - Materials match that specified in Project IFC drawings and Technical Specification.
d3e3aced-719c-5186-b7b6-2a534a7a90f2 | note | ○ Structural steel Material shall be sourced from suppliers certified by ACRS
ae5edb06-8c71-533a-90ad-c9f037da2233 | note | ○ Material test certificates shall report all element required by AS/NZS relevant standard, plus total boron content (Manufacturer certificates shall from ILAC MRA laboratories)
fd7d2f98-4113-521c-8df0-2cbef3e1b4ca | note | Certify Doc / Ref - Supplier Material Certificate
0b31c322-15a5-5eb8-8275-c88f126b0d3d | note | PFS Engineering - PM/PE
1cd52e9f-c167-5632-aad9-61e7a8e16180 | textbox | PFS Engineering: Sign - Initial: Sign:
c1b1bf92-5902-5374-b51e-85aea72c3b5e | note | PFS Engineering: C - RA/S
a087187e-c208-51ac-91a7-52200c0acd2e | note | Downer - Downer
c7e06940-13ab-5180-bd9b-f31b6e3fd582 | textbox | Downer: Sign - Initial: Sign:
f1fe22dc-a60f-51fb-bb01-90dcda1e63f5 | note | Downer: C - H
3c839224-3020-4bb8-8da2-9bad540c3e6c | signoff | AUTHORITY HOLDPOINT
d5b00414-be44-4ebf-a3ee-93c6c36d05f4 | checkpoint | 8 - Procurement of Welding consumable to match Weld procedure and parent materials.
ec3063b4-086a-51f0-8eac-788743b72235 | note | Specification Standard - AS/NZS 1554.1
1c79d8af-26e6-5cfa-8b94-89eacdb1e7e4 | note | Acceptance Criteria - Welding consumables and gas match what is specified on the appropriate welding procedures.
6afe9130-20ce-52cb-a6b4-a6bfd49ff949 | note | Certify Doc / Ref - Supplier Material Certificate, PFS Welding Procedures
5d798ed9-ba65-5435-ab6c-8a1400742aa3 | note | PFS Engineering - PM/PE
d7e2059f-6d70-5608-bd00-1f7848f6d02f | textbox | PFS Engineering: Sign - Initial: Sign:
44d21f9d-4aad-569c-b5eb-5605afcdd198 | note | PFS Engineering: C - RA
6c24ad2c-17c9-4e54-9dc5-853e50cd479f | checkpoint | 9 - Material inspection upon receiving (By supplier/sub-contractor/ Free issue material)
d20eef13-182c-5cad-81dd-57da3f8597fd | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
efc3043f-857c-5898-808a-a0a504e8e76d | note | Acceptance Criteria - All material shall be inspected against IFC drawing to make sure material grades, type, thickness, size are in compliance with IFC DWGs.
ddf1ab1d-b0d9-5ce4-9675-0f7cef8c99c1 | note | Certify Doc / Ref - IFC DWGs
d48fd5ef-0837-5cab-b494-e2703affa495 | note | PFS Engineering - Team Leader
263f67b3-79fb-5480-90b6-8d7544eb3d99 | textbox | PFS Engineering: Sign - Initial: Sign:
2c4bed99-c0e1-5a6e-834c-597b2a73d0c1 | note | PFS Engineering: C - H
65757062-6ad4-476d-91f8-b7dd8d63d5a6 | signoff | AUTHORITY HOLDPOINT
a2d1e7a6-63ca-4d9f-b192-c310ff113920 | section | Steel structure Fabrication
d588039a-c10a-4c94-8fb4-da65a86b2f60 | checkpoint | 10 - Manufacturing Work Pack Issued to Production Manager
a2b24dea-961e-5d33-9046-cab62384bf48 | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
3ba7262c-7468-5651-82b5-27e1258d1b19 | note | Acceptance Criteria - Job barcodes, Inspection & Test Plan's, IFC Fabrication Drawings, Reference Drawings/Info, Welding Procedures, weld map, welding log info, traceability sheet
f06aeca0-c5df-5970-bad3-0f03d1bd2228 | note | PFS Engineering - Production Manager
9a671092-0bfb-5928-8a94-57c5f1f3cef7 | textbox | PFS Engineering: Sign - Initial: Sign:
74399776-9e5a-5b07-97fa-55caa2dee9f0 | note | PFS Engineering: C - RA
8d3481bc-299c-4d74-bbf4-18bc1da5679d | checkpoint | 11 - Cutting the structural steel
f21b485f-c209-5792-b9f7-63975f98f513 | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG, SHEQ-01-02-0039
b41746b3-981d-53ab-8d77-f623ad529f51 | note | Acceptance Criteria - Dimensional survey of fabricated item's against IFC drawings.
6ee05428-dad5-5613-a6bd-349d553304cd | note | ○ Measured dimensions shall be within Functional Tolerances class 2 as per AS/NZS 5131 Table F2.1 to F2.10
8bc3f90f-ad74-5928-921f-98d670397929 | note | Certify Doc / Ref - IFC DWGs
bcbec8ba-8f3f-5b5c-83ec-80e382e606b0 | note | PFS Engineering - Team Leader
219dcad6-770f-5f2b-9952-4f1ab933ade3 | textbox | PFS Engineering: Sign - Initial: Sign:
efc787fb-ad19-504b-a4a6-ef55e403ff24 | note | PFS Engineering: C - D
4d15fbc2-066e-4721-93cf-00b08d243434 | checkpoint | 12 - Holing
5211f659-03c0-541c-8faa-27c5ce35c66c | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG, SHEQ-01-02-0040
65db1e79-daef-557c-9cdc-99dd9fe9e58b | note | Acceptance Criteria - Dimensional survey of fabricated item's against IFC drawings.
390ad2af-ec1c-5d6d-b5b2-4a288ac97317 | note | ○ Measured dimensions shall be within Functional Tolerances class 2 as per AS/NZS 5131 Table F2.1 to F2.10
a0224b17-e9dc-59e6-9940-0fd31b42efa2 | note | Certify Doc / Ref - IFC DWGs
88881d07-afbf-5c72-a44b-23d47fcaefaa | note | PFS Engineering - Team Leader
3038e8f4-7c3c-5845-b9a9-cfb412a35ce0 | textbox | PFS Engineering: Sign - Initial: Sign:
83ff586c-31f3-58f1-be9d-bc135bbfaa23 | note | PFS Engineering: C - D
2f1cbc1c-e9ca-4927-a8a3-e7ee0e696e59 | checkpoint | 13 - Identification and traceability for main items
7fc5fe23-61c5-514b-a011-310806da7967 | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG, AS/NZS 5131
02e24f23-68dd-5e32-8510-5808d9fb0544 | note | Acceptance Criteria - Lot traceability shall be provided for main structural members, connections between main structural members and major plate components. Tracibility as per AS/NZS 5131:Amd 1:2020 5.2.3 (ii) for minor components including cleats, connecting brackets and the like.
f481e360-b56f-58b7-a787-6803161bcea3 | note | Certify Doc / Ref - IFC DWGs
535bc6b3-ee75-5736-8314-8fb0b391d78a | note | PFS Engineering - PM/PE
b4260513-92cc-5887-8ea1-1d62e080eed9 | textbox | PFS Engineering: Sign - Initial: Sign:
b97bb79a-5eff-5821-9b6d-4140e1fc1144 | note | PFS Engineering: C - H
6949ec98-96ac-46ab-b47c-225a2e35c6d4 | signoff | AUTHORITY HOLDPOINT
209b7e0c-2346-4182-8b05-c90412dc023d | checkpoint | 14 - Manufacture of steel structure - Tack welded only
d3bc4dec-f4ff-5e06-843a-4dc1ac50fb52 | note | Specification Standard - IFC DWGs
087a762e-47d3-5233-ba6d-7f94116b2502 | note | Acceptance Criteria - Manufacture completed as per IFC Fabrication drawings.
eb2a118a-fe6f-5bcf-90e9-7fb8260c3b97 | note | ○ All tack welding shall be performed in accordance with PFS weld procedure.
bcd45cf9-770d-56ed-b61d-0c9740e3e474 | note | ○ Welding consumables, process & any applicable pre/post heat requirements shall comply with approved welding procedure's.
2d4fd4b8-a48b-5b87-a51c-7ffffa7c3634 | note | Certify Doc / Ref - IFC DWGs
2b554d8b-c502-52d6-8aa1-8ac055670dd4 | note | PFS Engineering - Team Leader
eeb70364-bd20-5fe3-a513-11b59153d45e | textbox | PFS Engineering: Sign - Initial: Sign:
a8e68c9b-0c31-55ae-b15f-5343efc6cc87 | note | PFS Engineering: C - D
c758e291-8511-4424-985a-f951474e4ef8 | checkpoint | 15 - Pre Weld Dimensional Check (Tack Check)
0d38926e-63c3-5bdb-a752-b8cd4b42577b | note | Specification Standard - IFC Drawings
4fc98219-2943-5d31-9bdc-8dcb69a355b5 | note | Acceptance Criteria - Dimensional survey of fabricated item's against IFC drawings.
86f9a156-0df6-5f48-9853-d48ba6a149c6 | note | ○ Measured dimensions shall be within stated tolerances unless noted otherwise.
c97e3b84-0b8b-5e88-a060-6789998283e2 | note | ○ Project specification clause C0702.1.3
41b9f56a-af8c-55fb-97f0-8058aad6e47d | note | ○ Functional Tolerances shall be class 2 as per AS/NZS 5131 Table F2.1 to F2.10
d8caa94d-3583-5cee-a86c-dcbd9f5711a3 | note | ○ Inspections recorded in line with SHEQ-01-02-0035 Product Inspection Procedure
d4ba9df9-8dbf-5278-ae5c-25f2ac19de76 | note | Certify Doc / Ref - IFC DWGs
5aa236bf-f115-5b18-8902-acdb4230c228 | note | PFS Engineering - Team Leader
100a37b2-9dde-5a5d-86ec-695f56c40a6f | textbox | PFS Engineering: Sign - Initial: Sign:
6fde7d52-9f75-5ee8-8752-4b79080dc731 | note | PFS Engineering: C - D
8e717923-8fd2-46df-b3b3-c0108de60ff1 | checkpoint | 16 - Welding
9bef3122-7811-536a-b47d-9825adcafb19 | note | Specification Standard - AS/NZS 1554.1, AS/NZS 9606.1
5f02bb55-c577-55b5-9e5a-32e2acce4952 | note | Acceptance Criteria - All welding shall be performed in accordance with PFS weld procedures
69e8c877-b0de-510c-a4a2-d0878c5acc4b | note | ○ Welding consumables, process & any applicable pre/post heat requirements shall comply with approved welding procedure's. Welder ID, weld date & consumable batch are recorded on traceability register.
1de8e630-65da-50bc-b092-9356bfb8e55e | note | Certify Doc / Ref - Welding Procedure and Welder Qualification
047ad631-4a0c-5f31-890c-9c423ce45f64 | note | PFS Engineering - Team Leader
b1579951-f89e-54a3-9d8d-4d3650ff5939 | textbox | PFS Engineering: Sign - Initial: Sign:
3d959832-d129-5645-94d9-76e6806aef39 | note | PFS Engineering: C - V
b309323a-a29e-4110-b511-7ad543df3d60 | checkpoint | 17 - Post Weld Dimensional Check
e7b5e931-cf40-5fa3-8344-2fd60bb10e80 | note | Specification Standard - IFC DWGs
e65b6a6f-59da-53b2-a540-b22e98f3795a | note | Acceptance Criteria - Dimensional survey of fabricated item's against IFC drawings.
5d6a2e72-cc67-5ec8-9c23-df0b28e1c0a7 | note | ○ Measured dimensions shall be within stated tolerances unless noted otherwise.
62ac74d9-4d33-545b-85fe-206465ffd509 | note | ○ Project specification clause C0702.1.3
62c2bf1b-e69f-581b-a7c4-deb8835b4f68 | note | ○ Functional Tolerances shall be class 2 as per AS/NZS 5131 Table F2.1 to F2.10
facd7700-9855-5d25-b5c4-c017ce8d7411 | note | ○ Inspections recorded in line with SHEQ-01-02-0035 Product Inspection Procedure
6eb683fa-394e-55f4-b6f4-6ccebb34ba22 | note | Certify Doc / Ref - IFC DWGs & Workshop Pack.
112ab489-4b3b-5bb2-af28-5c2f798af87f | note | PFS Engineering - Team Leader
c81e1234-31d5-5c1c-9515-75358b334ce9 | textbox | PFS Engineering: Sign - Initial: Sign:
aa104bcb-231e-515d-a400-894d96306797 | note | PFS Engineering: C - D
b710fd07-a617-4f79-bcd9-b028cc68c3af | checkpoint | 18 - Weld Visual Scanning (PFS Internal Check)
b9ff339b-52fd-5491-bdc8-5697454db202 | note | Specification Standard - IFC Drawing
23f5e040-2fe5-5b12-816c-f6ce5bd7730a | note | Acceptance Criteria - 100% of all welds shall be subject to visual scanning
4ff7ae9d-a2f9-58b4-8a44-2c25ca4b52f7 | note | Certify Doc / Ref - PFS NDT Register
08584dee-2a10-5187-8f35-04cfe7d40eb4 | note | PFS Engineering - Team Leader
0632cf4c-c47a-5997-8247-50beeca7b83c | textbox | PFS Engineering: Sign - Initial: Sign:
67664bea-f514-5d28-aff6-715b668fb8d5 | note | PFS Engineering: C - V
7f355b0a-c3d3-4d79-a945-e0896efcf875 | checkpoint | 19 - NDT inspection
b8a735be-1d50-5e04-9f4b-31a3d95d2165 | note | Specification Standard - Project Structure Specification C07 Rev. 01
dd82b032-97c5-59e1-902d-70a81c7ceb6e | note | Acceptance Criteria - NDE shall include as a minimum:
57f1efff-cb40-5cc6-b3ff-c5554ea707c0 | note | ○ 100% Visual Scanning, 100% Visual examination, 100% UT examination of all butt weld, 10% MT examination for fillet weld
43d26058-998b-5d07-9825-a3b5c03f0614 | note | ○ The Welding Compliance Inspector shall complete all inspections including any additional inspection, tests and reports necessary due to any welding or welding related workmanship defects.
b31e048b-5194-5741-b4b6-9b93168f9c49 | note | Certify Doc / Ref - Stamped NDT report
897e323b-5748-54dc-a9b1-f51fce3023bb | note | PFS Engineering - PM/PE
77fd5c2f-9460-55c7-8ac6-eb46dbec3ab5 | textbox | PFS Engineering: Sign - Initial: Sign:
e9a037d2-3e31-5ef4-b7b0-c917284387eb | note | PFS Engineering: C - RA
76a369e7-6b49-5d01-ad32-116095ead55a | note | Subcontracted scope - NDT subcontractor
95e1df72-9116-5deb-a10d-b3fe65640fa7 | textbox | Subcontracted scope: Sign - Initial: Sign:
2b97e3bc-1835-5955-8640-2e02e9e55437 | note | Subcontracted scope: C - S
134398b7-56ff-43b0-bd80-e08e16e76159 | checkpoint | 20 - Protective Coatings Preparation
fe14a92e-cf15-50f5-aae1-ef5482544147 | note | Specification Standard - Project Structure Specification C07 Rev. 01
55619495-de07-5c9b-8ec7-9d9b157558cc | note | Acceptance Criteria - Removal of all weld spatter and dressing of any weld to removed sharp edges / spatter.
ab47cccb-857e-5131-bbe6-7365b156dca6 | note | ○ All sharp edges are ground to a smooth 2 mm radius.
15ce6863-df84-5095-a154-66dde1b60edc | note | Certify Doc / Ref - N/A
1924c312-2cff-5cb9-8647-2b04a7dab636 | note | PFS Engineering - Team Leader
238f0a38-e10d-5812-9923-2f7c9c99ccc4 | textbox | PFS Engineering: Sign - Initial: Sign:
e282a5de-fde2-5045-8536-0b3107abb476 | note | PFS Engineering: C - V
7149c489-6d20-4670-b900-991a54ae3f19 | checkpoint | 21 - Fabrication NCR (if any)
365e7a35-ae94-5041-a621-63cd900dcc4b | note | Specification Standard - Project Structure Specification C07 Rev. 01
6d284010-41e5-5ea6-a3f7-b9de5ac9bbbb | note | Acceptance Criteria - All Non-conformities reported in PFS NCR system during manufacturing of steel structure need to be submitted to Client for approval
76bd3492-8606-5542-a1e1-cde7bd2626bf | note | PFS Engineering - PM/PE
7d552a09-3a1b-5481-9d28-99c66abd8f6c | textbox | PFS Engineering: Sign - Initial: Sign:
470a0e42-74d3-5414-906a-9152d4ada581 | note | PFS Engineering: C - S
e2426540-f9de-5a41-a55b-e3d77ef13c59 | note | Downer - Downer
ba370de8-cc93-53b5-9ac8-0fca1fcc0e84 | textbox | Downer: Sign - Initial: Sign:
1f1d9d50-d0e0-58b9-a529-2726e5978a31 | note | Downer: C - RA
a71c8ada-b1eb-4705-8f2f-276deb4e8ba4 | section | Shop Assembly - Pannels, Handrails and Balustrades
1a765af0-bb95-4328-b8ec-57414e272b63 | checkpoint | 22 - Inspection the free issue pannel uppon receipt at PFS work shop
786ef891-7963-5283-8194-fce8f9151d03 | note | Specification Standard - Pannel DWGs
57996894-3be4-54da-8b28-f6e80b01acfe | note | Acceptance Criteria - Check pannel to make sure the quantity and/or dimension are based on approved DWGs.
457984a4-60e4-5c12-b028-d282687a81c0 | note | Certify Doc / Ref - Pannel DWGs
cfb8b61c-1e0d-5efc-956b-0d21f5daef86 | note | PFS Engineering - Team Leader
f9b2dd82-15fc-5571-88d6-fc10a3897111 | textbox | PFS Engineering: Sign - Initial: Sign:
dec4d8ee-dae9-517a-8490-f240d4eec803 | note | PFS Engineering: C - V
713080e1-54d4-440b-bda9-e23e3ddf7441 | checkpoint | 23 - Panels Pre-assembly
b2eac31b-85c8-511a-945b-bb21e65a3684 | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
3ac295a4-0ff7-56be-a772-19e53a721086 | note | Acceptance Criteria - After painting, Client supplied pannels for decking and balastrades to be assembled.
93c2447b-a9ef-54ad-8997-5949d748421d | note | ○ Handrails need to be assembled in the shop
8b875fb2-0898-5d25-adf0-cd9a0948228a | note | Certify Doc / Ref - IFC DWGs
7c47e43d-2b36-5f83-ad62-20c297ef8935 | note | PFS Engineering - Team Leader
452f4f4f-98e2-5f94-8a85-8459b8c3adf9 | textbox | PFS Engineering: Sign - Initial: Sign:
46400634-c9dc-5a29-b443-84e5fa2293a8 | note | PFS Engineering: C - V/D
58304b03-b4ee-43a4-8234-7ddb621812d7 | checkpoint | 24 - Dimension check
be3ae31a-2525-5478-a172-19ad831da953 | note | Specification Standard - IFC DWG
2d3804a1-29dc-5c70-9bef-9be0cb5268ae | note | Acceptance Criteria - Compliance with IFC DWGs
74b2055e-fff3-5dd5-8c59-8d9af7a1ad7f | note | PFS Engineering - Team Leader
0d088080-3b31-5aa6-9860-fd775e9cc6ac | textbox | PFS Engineering: Sign - Initial: Sign:
0f9be08e-8913-55c7-9df5-f1a20f720200 | note | PFS Engineering: C - D
e692a7cc-5e2f-482d-847f-bbe0f2071e4f | checkpoint | 25 - Visual inspection of Fasteners (Free issue)
3d63529c-d90f-56a4-ab7d-0398f3cd65b3 | note | Specification Standard - IFC Drawing
e4d0066d-8aa1-5080-aaf8-3b7935007519 | note | Acceptance Criteria - All fasteners (bolts, nuts, washers) are to be in complied with the Porject requirement (Grade, Size and Length)
9d8e6107-655a-5947-80fd-b4b5d4c380c8 | note | Certify Doc / Ref - IFC Drawing
0d353617-b55a-5e44-b520-395c887d50d9 | note | PFS Engineering - Team Leader
43cd80d0-2fa0-5391-aefa-22382ed4d1e4 | textbox | PFS Engineering: Sign - Initial: Sign:
c45ed4d5-ee97-50fe-8a1c-32fa4c2f1147 | note | PFS Engineering: C - V
fcccef9d-2e98-4d94-8d54-77ac853260ca | checkpoint | 26 - Snug tightening of conposite component fixings
9a7c683f-3b89-5a05-9bbe-64f53f5207de | note | Specification Standard - Standard operation procedure for steel structure bolt tightening, SHEQ-01-02-0038
afb642a9-9119-53c4-9c44-af7401bec5b9 | note | Acceptance Criteria - 100% of fixings securing composite material to structure are to be inspected for snug tight condition and marked with coloured paint pen to confirm fixing condtion has been checked and verified.
4f90c29a-1aaf-51c6-9455-c70d37758b90 | note | PFS Engineering - Team Leader
92149be6-fb83-547c-8f36-9287f65e9fda | textbox | PFS Engineering: Sign - Initial: Sign:
17b9e0b7-9e17-5934-a2bb-28f190042aa7 | note | PFS Engineering: C - V
d373bd7a-5313-4a35-a947-e7681773e972 | checkpoint | 27 - Final Inspection
d8d448cc-3a38-5f85-961d-9ccf42786d07 | note | Specification Standard - IFC Drawings, AS/NZS 1554.1:2014 Category SP
b91bc4e4-26ae-55a4-8de8-e5beafe00e5e | note | Acceptance Criteria - Visual and Dimensional inspections completed by PFS Project Manager to confirm manufactured items have been manufactured to acceptable standard & tolerance and approved to progress to protective coatings.
6e7acc45-2b73-546d-ab8f-dc7d4a334d11 | note | ○ >Confirmation that dimensional inspections have been completed in line with SHEQ-01-02-0035 Product Inspection Procedure
584f3031-87da-54dc-bb4f-05a4f971222a | note | ○ >Confirmation that required quantity and type's of NDE has been completed and any identified defects have been remediated.
2d133455-4fcf-58e1-a0d8-d3cbd6542d14 | note | Certify Doc / Ref - IFC DWGs
d9b323d7-4a6e-5b06-92e6-fdd35118e26b | note | PFS Engineering - PM/PE
2157ebc4-99c9-5146-83ec-0dbf4da8565a | textbox | PFS Engineering: Sign - Initial: Sign:
2a3598b8-bfd8-52b8-a128-9d91eaf6b83f | note | PFS Engineering: C - RA
e956537a-8c0f-4b34-9b55-614a386c3d38 | section | Quality Review
e85d362b-beef-4eb9-ad0d-9a16a2443825 | checkpoint | 28 - Compile, review and submit documentation
3f4823be-cab3-5d9d-ac2f-57b780376b63 | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
93548892-db2a-5451-956f-322677c6e8b4 | note | Acceptance Criteria - Documentation, Certificates and reports to support manufacture of steel structure and subcontracted items compiled into PFS Manufactures Data Report
545a6032-ad5c-54f3-add1-83a4c9a04264 | note | Certify Doc / Ref - PFS Manufactures Data Report
985d0914-0aef-54fa-a1de-1625dc3f8841 | note | PFS Engineering - PM/PE
cd36dcef-8209-5174-bf93-8c6cef51447d | textbox | PFS Engineering: Sign - Initial: Sign:
4dcdeafc-7efd-50b1-8e09-b7c735093015 | note | PFS Engineering: C - RA
06a9959e-cea3-5ff5-95b8-4b7c9be28728 | note | Downer - Downer
f85bbe90-5f13-5c32-a00b-2dd54c30ee23 | textbox | Downer: Sign - Initial: Sign:
80b697ff-00b0-51b6-bd79-b42e1f370cc3 | note | Downer: C - RA
93e29709-14e9-4021-8a70-ee12306f9124 | section | ITP APPROVAL PROCESS
38eacf22-bd6f-43bf-983a-2e7dc367c07e | checkpoint-no-value | ITP APPROVAL PROCESS
838650a1-e2f3-50fc-ad52-450531f6244c | textbox | Approved by [Engineer/Client]:
94356fda-10dd-5a87-bfd3-6543c8193134 | textbox | Issued for Construction:
ec2fc6d4-a6ba-405b-a905-dfb63b899fea | signoff | Sign:
394c32fd-3e26-4960-bd8f-ae3e92d046b0 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
d58e802e-9ad6-5747-a162-5f6f8fa7185f | textbox | Contractor's Rep Name:
2256d2e0-c5e1-5e4f-b7d8-437dd103280e | textbox | Engineer's Rep. Name:
7f533951-8895-5573-ab3b-9e138fabb7a7 | date | Date:
0f9fb80d-b5a1-4e6b-95d2-633fe122ed8f | signoff | Add Signature
01941237-2a38-4ff6-aaeb-7ae25f0bdc99 | checklist | DN1212-ITP-021 Shop fabrication - Lighting and conduit Brackets RevA | itp | DN1212-ITP-021 Shop fabrication - Lighting and conduit Brackets
39b3ef0f-7505-454d-8363-c3faade4b8ba | section | Engineering
30e1e92d-9244-4beb-b503-949027bfe1f5 | checkpoint | 1 - Inspection and Test Plan Reviewed and Approved by Customer
64946b8d-9901-5bc1-84cc-5ed80a5ff3bb | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
83dc10ee-1b35-568a-abbf-91b7ef9c91a9 | note | Acceptance Criteria - Inspection and Test plan shall be submitted to the Engineer for review and approval before fabrication is commenced.
b6295aeb-9706-5e11-a430-3bee2b9cda89 | note | Certify Doc / Ref - IFC DWGs
48520f21-7869-58dd-8411-5f31edf9602c | note | PFS Engineering - PM/PE
4f6ee219-37ff-5599-9767-6ff16a94f2df | textbox | PFS Engineering: Sign - Initial: Sign:
5f2a7aeb-1cc0-5232-add3-8d619c75f156 | note | PFS Engineering: C - S
0c9a7366-1ac6-500f-a7b1-57120039b293 | note | Downer - Downer
2999dd67-280d-5e77-82d5-e71de1653c37 | textbox | Downer: Sign - Initial: Sign:
8cf5a118-7185-534d-a1dd-354f7b2299c2 | note | Downer: C - H
d3e90fd8-a610-4dbb-aa0e-236b639c6750 | signoff | AUTHORITY HOLDPOINT
653dfd7c-34c7-467e-b698-11cf6f2ebe5b | checkpoint | 2 - Shop Drawing approval
02c6969b-bcc3-566b-9baf-1967d3f512ab | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
9c52c6e2-425d-5dd7-93f4-9756d1514f12 | note | Acceptance Criteria - Shop Drawing shall be submitted to Engineer for review along with Shop Drawing Check form
45ad3413-ca36-53f2-a987-08c02879eaef | note | Certify Doc / Ref - Shop Drawing Check form
e6cec895-0788-570f-a6f9-299ff9a12c04 | note | PFS Engineering - PM/PE
8bb576b6-6180-5d52-93b3-ed09c0adbd76 | textbox | PFS Engineering: Sign - Initial: Sign:
91ff6287-d69c-5dfa-9da2-8356a63f2973 | note | PFS Engineering: C - S
96ed2526-a01e-5366-be5d-97d507c13392 | note | Downer - Downer
9629d524-7a9e-54d5-b3fb-b96b673ef05f | textbox | Downer: Sign - Initial: Sign:
6650598f-136c-5dff-93cb-f5b7acc916d0 | note | Downer: C - H
4e9dc8d6-12a2-4952-b675-c6a295d6e89a | signoff | AUTHORITY HOLDPOINT
95862015-8c29-4649-a90e-7141a0b8d9ec | checkpoint | 3 - Welding Procedures - Structural
70cd19c5-f2d5-5fd7-bff0-b7dac5cee963 | note | Specification Standard - AS/NZS 1554.1:2014 Category SP
41eccc94-75d1-5b51-9edb-8121215d9063 | note | Acceptance Criteria - Details of the welding procedures to be used including details of the equipment and consumables before any welding is carried out. No welder shall carry out work for which he is not certified.
ff52d84c-cd6b-5d9d-8fb5-9bddc07ff1e9 | note | Certify Doc / Ref - Welding Procedures, HERA/CSWIP Stamp
42228c40-09a4-5da8-afde-1d6451561aac | note | PFS Engineering - PM/PE
65c7dc98-80a3-538f-9250-683def278f0d | textbox | PFS Engineering: Sign - Initial: Sign:
6db86c94-9a7b-5ff6-bc2e-277e2a4097b4 | note | PFS Engineering: C - S
24decaee-e9f1-5363-812b-8769c63ca664 | note | Subcontracted scope - SQA
7e79a9c4-2188-5381-9e8f-caa4c6569828 | textbox | Subcontracted scope: Sign - Initial: Sign:
2336365d-8c3d-51cc-b61a-1b12b56586f2 | note | Subcontracted scope: C - RA
8ef809a1-de95-4e06-8998-e6728c86f76c | checkpoint | 4 - Welder Qualifications - Structural
2fab06e0-8d86-5d84-92d2-3d5350eb8726 | note | Specification Standard - AS/NZS 1554.1:2014, ISO 9606-1:2017
b81366cd-0b4d-57c3-b5c8-1e4ee9a8b607 | note | Acceptance Criteria - A list of proposed welders and their welding certificatesto be provided prior to any welding being carried out.
d3bbea0b-a812-5b4d-986c-828eb19202d4 | note | ○ No welder shall carry out work for which he is not certified.
9de58bc3-f287-555f-a4c4-a87434b37316 | note | Certify Doc / Ref - WQT by Authorised Person (Welding Supervisor)
bd45d891-8ace-5b39-bf80-71cfb0d45efb | note | PFS Engineering - PM/PE
753f8a49-d1f1-5c88-9b60-c45f03ca110b | textbox | PFS Engineering: Sign - Initial: Sign:
0d993eab-393c-528e-b52a-1bc5263a83f6 | note | PFS Engineering: C - S
b58c29a3-262c-52c2-a024-52086fe6d3be | note | Subcontracted scope - SQA
22f0931c-2db3-5e53-a823-15ae768fe6ec | textbox | Subcontracted scope: Sign - Initial: Sign:
fef2a48c-ed15-5c5a-b0a1-0a7247c8beca | note | Subcontracted scope: C - RA
3ed093c4-79a5-4f28-a2a2-85f96b8ef175 | section | Procurement
363691d7-c0e0-4715-80e9-6ce6021836a6 | checkpoint | 5 - Procurement of materials in line with IFC drawings and Technical Specification
11551df7-73aa-51db-989d-602ce207316c | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
d6294719-6b60-57f2-8411-f6d0de6b8821 | note | Acceptance Criteria - Materials match that specified in Project IFC drawings and Technical Specification.
bcd55e2f-156f-5d2e-b0ad-ea0f9b797cc3 | note | ○ Structural steel Material shall be sourced from suppliers certified by ACRS
9422e86b-39ab-5bfc-a219-7599ebdc4fbb | note | ○ Material test certificates shall report all element required by AS/NZS relevant standard, plus total boron content (Manufacturer certificates shall from ILAC MRA laboratories)
c44625f4-1d5e-5a14-81a0-217d5d066956 | note | Certify Doc / Ref - Supplier Material Certificate
d1571957-419c-5069-b56b-475393bd3def | note | PFS Engineering - PM/PE
b71d3b74-6cc8-548d-8b87-7d9db580654b | textbox | PFS Engineering: Sign - Initial: Sign:
97670508-ecb8-5cb0-95f0-b0cb9efc1be5 | note | PFS Engineering: C - RA/S
3f09684d-131b-5926-8859-271f8610336c | note | Downer - Downer
db76a11b-be75-5128-9f80-80e3393831ea | textbox | Downer: Sign - Initial: Sign:
1cade3cd-4280-58bf-8990-8de16ea45384 | note | Downer: C - H
183ed5b2-4dfe-4e91-9639-6da403e68d73 | signoff | AUTHORITY HOLDPOINT
037f98b3-1f66-4402-8707-11f5c0623102 | checkpoint | 6 - Procurement of Welding consumable to match Weld procedure and parent materials.
57f4caf5-aadd-595b-921c-7ab65d681181 | note | Specification Standard - AS/NZS 1554.1
efeda1d1-9696-553a-8498-91e5808845df | note | Acceptance Criteria - Welding consumables and gas match what is specified on the appropriate welding procedures.
3955d192-94ba-5203-ac1b-a6d6036fc2bd | note | Certify Doc / Ref - Supplier Material Certificate, PFS Welding Procedures
962d5fc8-7c38-5b43-a380-cb7aad0dae81 | note | PFS Engineering - PM/PE
c6e34a54-83dd-57e6-bc26-af0beec754d4 | textbox | PFS Engineering: Sign - Initial: Sign:
671ebe34-b495-5d09-a0d0-f3966dceea43 | note | PFS Engineering: C - RA
0d54adaf-4906-48d5-aad0-671ffa203550 | checkpoint | 7 - Material inspection upon receiving
c94ecc8f-8bc1-54c2-bdd2-4950799b1035 | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
5cc22d98-84fd-54f4-b23b-d32a619bb2b4 | note | Acceptance Criteria - All material shall be inspected against IFC drawing to make sure material grades, type, thickness, size are in compliance with IFC DWGs.
e8af6e7c-7534-5cbf-a88c-605371db15e5 | note | Certify Doc / Ref - IFC DWGs
a25152f1-506c-5cee-871a-a1f81862ed0c | note | PFS Engineering - Team Leader
3fce2f37-8aa6-5d0d-a9f1-6de72b3a205d | textbox | PFS Engineering: Sign - Initial: Sign:
1f92e28f-9db7-5375-bb85-b80e3c5b167f | note | PFS Engineering: C - H
2d4984e5-6034-48ac-ae12-754380281e0f | signoff | AUTHORITY HOLDPOINT
532da174-5fd3-4702-aa6e-76da9b0b767a | section | Steel structure Fabrication
85c44261-0493-4a62-b9d4-fa9ef59d81c4 | checkpoint | 8 - Manufacturing Work Pack Issued to Production Manager
f4594021-9ab4-57af-b46c-28e17b1f16f1 | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
2596d700-f463-565f-aa5a-435b4a7422f8 | note | Acceptance Criteria - Job barcodes, Inspection & Test Plan's, IFC Fabrication Drawings, Reference Drawings/Info, Welding Procedures, weld map, welding log info, traceability sheet
d1ca69fc-0094-528b-9041-5837d4a8d3ed | note | PFS Engineering - Production Manager
60a8aaff-9418-5b87-a52b-81d21fc95735 | textbox | PFS Engineering: Sign - Initial: Sign:
debe601d-83ee-5e47-a651-b706d1fe8290 | note | PFS Engineering: C - RA
dba0148d-8b94-42f4-a4ba-8b06c8adf23b | checkpoint | 9 - Identification and traceability for main items
1ae53bc6-bf2c-5c4a-9a2b-52ac7271e6e4 | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG, AS/NZS 5131
391ba583-80e4-5916-b59d-e32049c14c6b | note | Acceptance Criteria - Lot traceability shall be provided for main structural members, connections between main structural members and major plate components. Tracibility as per AS/NZS 5131:Amd 1:2020 5.2.3 (ii) for minor components including cleats, connecting brackets and the like.
440630ec-480a-5ae9-a838-943c24deaf45 | note | Certify Doc / Ref - IFC DWGs
2fb0002c-57df-5de4-ab44-6cb6135c8d69 | note | PFS Engineering - PM/PE
58b111ca-b7da-583c-b742-b2bf759fb87f | textbox | PFS Engineering: Sign - Initial: Sign:
c43e9fce-b626-5d71-8ac6-7a9a649239a9 | note | PFS Engineering: C - H
e0fd6590-7c99-4124-9c2e-f4b622574cba | signoff | AUTHORITY HOLDPOINT
9f0e8422-e11f-4acd-a435-0d6e154ea8fb | checkpoint | 10 - Manufacture of steel structure - Tack welded only
fbaed24b-0967-520b-ad78-15117584852d | note | Specification Standard - IFC DWGs
667d9a87-9fdc-5902-93e8-035957148f33 | note | Acceptance Criteria - Manufacture completed as per IFC Fabrication drawings.
c766938b-fe1f-5bef-89b2-48b915026ac8 | note | ○ All tack welding shall be performed in accordance with PFS weld procedure.
0c103dcb-6c9c-5b8b-8de2-faf616cb567f | note | ○ Welding consumables, process & any applicable pre/post heat requirements shall comply with approved welding procedure's.
75889088-b664-5d61-8a68-ccc38ae17931 | note | Certify Doc / Ref - IFC DWGs
dd332c1c-4215-59be-afef-4b4bad67a5f9 | note | PFS Engineering - Team Leader
1c4f8d00-940a-5ff9-b31c-725f2640f03e | textbox | PFS Engineering: Sign - Initial: Sign:
7d545158-b2f2-55a6-8196-81b2517be800 | note | PFS Engineering: C - D
43af5c8d-6363-4f47-8321-7a0b36ecc92d | checkpoint | 11 - Pre Weld Dimensional Check (Tack Check)
f696183f-6d94-5ea7-ae9e-30ef8355a9b9 | note | Specification Standard - IFC Drawings
ecc57f41-31d1-5734-9552-f2af70414477 | note | Acceptance Criteria - Dimensional survey of fabricated item's against IFC drawings.
ec08de5c-38ca-5e5a-b64b-73b7df00d95f | note | ○ Measured dimensions shall be within stated tolerances unless noted otherwise.
94b9f2d3-a874-5c94-888d-cb31b1fc3d0a | note | ○ Project specification clause C0702.1.3
39421cca-32d2-53db-8043-da9d0ed8f214 | note | ○ Functional Tolerances shall be class 2 as per AS/NZS 5131 Table F2.1 to F2.10
934bdad7-92d6-5c75-a251-12055f2d39ad | note | ○ Inspections recorded in line with SHEQ-01-02-0035 Product Inspection Procedure
bcb2bc28-1fd3-54c2-a9e9-2cad7dc8963a | note | Certify Doc / Ref - IFC DWGs
2837ac2e-95f1-5e0a-983c-64190fa6f30f | note | PFS Engineering - Team Leader
37b97682-6966-5cdd-8a12-4b8f59aaf69c | textbox | PFS Engineering: Sign - Initial: Sign:
fb948893-ac41-553a-92f3-9e6b451d203d | note | PFS Engineering: C - D
0db48879-4b45-462d-be09-bfae0416087a | checkpoint | 12 - Welding
028ec12c-3d5c-57f5-af3d-49c1b020cf3d | note | Specification Standard - AS/NZS 1554.1, AS/NZS 9606.1
23dec235-d63c-5dd1-8386-70668483cd3c | note | Acceptance Criteria - All welding shall be performed in accordance with PFS weld procedures
c7c620e3-495a-52d8-876a-443e7d25e9d5 | note | ○ Welding consumables, process & any applicable pre/post heat requirements shall comply with approved welding procedure's. Welder ID, weld date & consumable batch are recorded on traceability register.
edc42916-4f31-5e1f-a3f4-574c0bb7571d | note | Certify Doc / Ref - Welding Procedure and Welder Qualification
bd82376b-4f84-5aad-9fba-8e3de3fec597 | note | PFS Engineering - Team Leader
b808b7f6-d0f3-59cc-bf29-36b6db985688 | textbox | PFS Engineering: Sign - Initial: Sign:
879eace7-0eda-5441-99d6-da5d196563ea | note | PFS Engineering: C - V
01bcb94f-1b36-49c9-a463-8a77cae7aa64 | checkpoint | 13 - Post Weld Dimensional Check
0914705d-0311-560b-a33b-fed80d5703fe | note | Specification Standard - IFC DWGs
687802cb-d861-5630-a7c6-9329aae6db71 | note | Acceptance Criteria - Dimensional survey of fabricated item's against IFC drawings.
200977f9-79a7-5b2e-92b6-8222083e80b7 | note | ○ Measured dimensions shall be within stated tolerances unless noted otherwise.
1bea0c92-9ac5-55d5-9a58-c85d41a37f05 | note | ○ Project specification clause C0702.1.3
cfe2e3d7-b131-5645-97d7-39a685802753 | note | ○ Functional Tolerances shall be class 2 as per AS/NZS 5131 Table F2.1 to F2.10
b26ead96-9979-5cbc-9c97-83f551888275 | note | ○ Inspections recorded in line with SHEQ-01-02-0035 Product Inspection Procedure
71ef9185-65c2-5740-b03e-2c91e69c5447 | note | Certify Doc / Ref - IFC DWGs & Workshop Pack.
eceb5e27-05dc-5bd2-85eb-27928ba7bb5b | note | PFS Engineering - Team Leader
1112a7a4-ec55-5019-a916-62ca6f05b77e | textbox | PFS Engineering: Sign - Initial: Sign:
bf9d23a2-9e58-5c9c-b363-0eba3a9e7129 | note | PFS Engineering: C - D
7f8abd07-f692-46e2-b4f2-1c162e7221cb | checkpoint | 14 - Weld Visual Scanning (PFS Internal Check)
bb01f430-c03f-5451-be30-627ac391fdb8 | note | Specification Standard - IFC Drawing
947c224b-0aa3-5cb0-a99b-c022f016c47e | note | Acceptance Criteria - 100% of all welds shall be subject to visual scanning
8a2d5cfd-56bf-55f5-a31f-16f15bf841f1 | note | Certify Doc / Ref - PFS NDT Register
84ba6d5a-84bc-5736-95f4-55883b84da18 | note | PFS Engineering - Team Leader
cb7a785d-7b27-5ec2-9bc6-a83dca1e3ad8 | textbox | PFS Engineering: Sign - Initial: Sign:
433bdbc8-0eb2-5873-bea7-95596ce47444 | note | PFS Engineering: C - V
7049fa2a-39e5-4cef-aebe-7048c9e8dc00 | checkpoint | 15 - NDT inspection
9c736f2b-1b40-5bb9-9877-fa9f654bc958 | note | Specification Standard - Project Structure Specification C07 Rev. 01
a5f1f376-b680-50bb-b7e2-7c06c4b24563 | note | Acceptance Criteria - NDE shall include as a minimum:
84a99559-bfe5-529b-a12a-77f3460aa2d5 | note | ○ 100% Visual Scanning, 100% Visual examination
092303ef-91bc-55d1-8a48-d54fd9fd614c | note | ○ The Welding Compliance Inspector shall complete all inspections including any additional inspection, tests and reports necessary due to any welding or welding related workmanship defects.
17c4d5c6-c26c-5325-ac1f-a3fda00c6b0f | note | Certify Doc / Ref - Stamped NDT report
4ce8f599-ba6c-5f0f-9df8-bed8b7cb56c7 | note | PFS Engineering - PM/PE
300bf01e-9ea7-5545-a210-a9354704e483 | textbox | PFS Engineering: Sign - Initial: Sign:
ec4a70c3-8c1c-5bc7-9217-adf586e8ae9e | note | PFS Engineering: C - RA
cc937efa-f5d7-5ebf-a6c7-407b2cc6087c | note | Subcontracted scope - NDT subcontractor
d8b251e2-9f17-5100-a3ad-314d3c5a6dd4 | textbox | Subcontracted scope: Sign - Initial: Sign:
f4d66bd4-32c2-55a3-a228-663df5cabe53 | note | Subcontracted scope: C - S
68363c5d-2640-44c8-8116-b20adafd2aa9 | checkpoint | 16 - Protective Coatings Preparation
352bfa31-e0d4-5025-9330-935f9d14c0e1 | note | Specification Standard - Project Structure Specification C07 Rev. 01
4d7f90a6-979f-5791-8706-3e4d6d79979f | note | Acceptance Criteria - Removal of all weld spatter and dressing of any weld to removed sharp edges / spatter.
7e8090a6-e37c-53c9-9ff1-2995b956643a | note | ○ All sharp edges are ground to a smooth 2 mm radius.
80b419f3-2857-5934-9809-472ae53589e3 | note | Certify Doc / Ref - N/A
aa642f5b-528f-5623-a72d-ce4356c08f71 | note | PFS Engineering - Team Leader
c24d5ed7-e3d3-5833-baf9-93adc8fd5af6 | textbox | PFS Engineering: Sign - Initial: Sign:
e002c130-e89c-5732-8a7f-d46936222457 | note | PFS Engineering: C - V
02bf6f53-51b0-49ce-a1f6-e4cfecfd05bc | checkpoint | 17 - Fabrication NCR (if any)
7bfcc82c-bb4b-5de4-a83a-7c793500b963 | note | Specification Standard - Project Structure Specification C07 Rev. 01
1a96d980-6bb5-508a-9b45-7906b801d3f8 | note | Acceptance Criteria - All Non-conformities reported in PFS NCR system during manufacturing of steel structure need to be submitted to Client for approval
260b44e0-ed01-5631-ac4a-345eaeca5b23 | note | PFS Engineering - PM/PE
cb87bd92-ac13-5cee-93a5-dc31d35dcdea | textbox | PFS Engineering: Sign - Initial: Sign:
c915c9b5-8265-5524-9d20-7eab0b9d0c7e | note | PFS Engineering: C - S
27673b6e-ce7d-5095-9fb2-bbce3a09a839 | note | Downer - Downer
f1e2b011-f0c8-598e-8a0f-e6ecfcee6241 | textbox | Downer: Sign - Initial: Sign:
a9eae005-ef86-5dc9-8ba5-169a5b72ff20 | note | Downer: C - RA
fd036418-6f47-47c1-be90-d3d3c5e37cc1 | section | Assembly - Lightning and Conduit Bracket
ff0a6e32-b56d-4972-b37b-b303996339fd | checkpoint | 18 - Lighting and conduit bracket- assembly
6576d8e4-e23d-56f5-87be-11d269b8b31e | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
1cef68ac-9f38-5d8a-b887-f77088018653 | note | Acceptance Criteria - After coating, the bracketes to be assembled on GRP material
8aa31aa1-4ab9-58a0-9041-a6f62ae1c538 | note | Certify Doc / Ref - IFC DWGs
bacd5852-44fc-5e40-bba0-470919d8c7f2 | note | PFS Engineering - Team Leader
7c6d91bd-ea9a-5b60-9ea1-9ff81686e56e | textbox | PFS Engineering: Sign - Initial: Sign:
c4f64e75-a8c3-5b57-a98d-a3906a5f499e | note | PFS Engineering: C - V/D
8eb92026-da8a-4742-8842-a064a330ae16 | checkpoint | 19 - Holing
8a5d4112-15f9-5a21-9ef5-bc473e81a03b | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG, SHEQ-01-02-0040
414ee955-a1eb-568a-aec8-c4cad9458786 | note | Acceptance Criteria - Manual holing shall be performed on GRP material.
12d7be4e-cbbf-5487-9107-7477f719c43f | note | Certify Doc / Ref - IFC DWGs
1ea21e02-2e3b-547a-a2bf-d9ff857c34fd | note | PFS Engineering - Team Leader
4da0cc1e-3b80-5106-a487-df606e854221 | textbox | PFS Engineering: Sign - Initial: Sign:
353da2cc-b49e-5bbf-91d6-b321c5db6e3d | note | PFS Engineering: C - D
221dcf75-afc4-4122-9547-2f7f4143fca4 | checkpoint | 20 - Dimension check
1a6f6bac-1f6b-5144-98b3-45c9c49c78b6 | note | Specification Standard - IFC DWG
142d054d-45a3-51f8-9b97-25f771f39076 | note | Acceptance Criteria - Compliance with IFC DWGs
29850f99-b7c6-573b-9041-ab8b06a60236 | note | PFS Engineering - Team Leader
789bb0fd-ea7f-536e-87a9-ff5edc8cab8a | textbox | PFS Engineering: Sign - Initial: Sign:
46318ee2-2e45-5251-a267-c63d4841bfd0 | note | PFS Engineering: C - D
5a4a681e-ba74-4cf9-9949-0e728dc69364 | checkpoint | 21 - Visual inspection of Fasteners
ddf66f9c-7b8d-557c-8899-0443b3a3e5cb | note | Specification Standard - IFC Drawing
d1bdc939-fe5e-557d-b379-4f947e869d32 | note | Acceptance Criteria - All fasteners (bolts, nuts, washers) are to be in complied with the Project requirement (Grade, Size and Length)
81ab3298-8e7e-5d32-823a-39c0ca52f3f6 | note | Certify Doc / Ref - IFC Drawing
bfa136f6-3dd3-5e3f-87e3-e092ae56efbf | note | PFS Engineering - Team Leader
474c4b08-ace1-5b19-aead-8f2eadddf713 | textbox | PFS Engineering: Sign - Initial: Sign:
aa2ba4c7-cdf8-5e00-99cb-ba7ac2d09235 | note | PFS Engineering: C - V
597a8f2b-158d-4455-bf64-0f625c1df8a8 | checkpoint | 22 - Snug tightening of fastener to fasten the brackets to the GRP material
b37fabf5-54e8-5bd0-9581-0741b63b11e5 | note | Specification Standard - Standard operation procedure for steel structure bolt tightening, SHEQ-01-02-0038
d541484d-048e-524b-afd0-afa9a93cfe3f | note | Acceptance Criteria - 100% of fixings securing brackets to be inspected for snug tight condition and marked with coloured paint pen to confirm fixing condtion has been checked and verified.
5e9354dc-5c80-57be-acbd-e2554c0c3947 | note | PFS Engineering - Team Leader
b872842f-7823-5646-954d-1b09487fe7cb | textbox | PFS Engineering: Sign - Initial: Sign:
25135b85-8749-5e81-9c8c-f890f3973cd0 | note | PFS Engineering: C - V
caada7a6-3b4f-4141-aee9-ffb01d0bbd56 | checkpoint | 23 - Assembly of the angles between brackets
4ed37bfc-a3a5-55b9-8d68-ebec73cdcbcb | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
d8175de2-4d59-56bc-9b3e-37aa2341070b | note | Acceptance Criteria - The angles to be assembled between bracket with fasteners
31c41c89-3a13-5770-a315-623b1199aa2e | note | Certify Doc / Ref - IFC DWGs
48de6e0b-cc01-52ad-81ab-2c3a0f2cb3b5 | note | PFS Engineering - Team Leader
780d0e41-5a4b-532f-b8a2-704fba3c590b | textbox | PFS Engineering: Sign - Initial: Sign:
19f15810-ebdd-5e1e-be99-672369b21e1e | note | PFS Engineering: C - V/D
8fe348be-020d-46fc-8233-6c0aed676050 | checkpoint | 24 - Snug tightening of fastener to fasten angles to the brackets
5200c566-6fc7-5bb1-ac21-cccd7a36809a | note | Specification Standard - Standard operation procedure for steel structure bolt tightening, SHEQ-01-02-0038
1fca140d-88a3-54dd-806b-74eefc64755e | note | Acceptance Criteria - 100% of fixings securing brackets and angles to be inspected for snug tight condition and marked with coloured paint pen to confirm fixing condtion has been checked and verified.
49828ce5-0843-5202-9213-0a4cce32e33c | note | PFS Engineering - Team Leader
e5130306-6267-5f98-bfe3-e57d67a186aa | textbox | PFS Engineering: Sign - Initial: Sign:
43827cab-3718-544d-96dc-ddfee5ae0c5d | note | PFS Engineering: C - V
79b9a63b-10ba-4774-9dcd-19db7277ced5 | checkpoint | 25 - Final Inspection
43600675-a066-5823-9271-a9a5cb89911e | note | Specification Standard - IFC Drawings, AS/NZS 1554.1:2014 Category SP
9e148a72-243f-52eb-ac3f-5f256488ed10 | note | Acceptance Criteria - Visual and Dimensional inspections completed by PFS Project Manager to confirm manufactured items have been manufactured to acceptable standard & tolerance and approved to progress to protective coatings.
bd145fd2-cb28-58d3-8fc5-3ef3f04266d4 | note | ○ >Confirmation that dimensional inspections have been completed in line with SHEQ-01-02-0035 Product Inspection Procedure
6d352743-ca9e-5aa0-95ec-89ccfc32f04e | note | ○ >Confirmation that required quantity and type's of NDE has been completed and any identified defects have been remediated.
b1d3d74c-278e-5dd8-91d9-1c69a918a779 | note | Certify Doc / Ref - IFC DWGs
5469459f-8381-5dd7-a92d-95734e37e248 | note | PFS Engineering - PM/PE
58b806d6-3c4c-5a92-921a-2d1b9779b5db | textbox | PFS Engineering: Sign - Initial: Sign:
4872fd8b-ee35-5518-afe2-325a92278e39 | note | PFS Engineering: C - RA
a9f2854d-8b56-478e-9577-99fa387a85a7 | section | Quality Review
d5f3ecd6-ec94-40a7-b59c-a11f96830828 | checkpoint | 26 - Compile, review and submit documentation
e38cc9d1-2bbc-5e72-8cf3-24f33f90cffa | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
392c8917-ec7b-5de6-8682-b95d374634aa | note | Acceptance Criteria - Documentation, Certificates and reports to support manufacture of steel structure and subcontracted items compiled into PFS Manufactures Data Report
41ce463a-ebd0-5fa9-9043-02c40daffbc0 | note | Certify Doc / Ref - PFS Manufactures Data Report
5d6ba414-415b-552e-8a9e-efd3a167da9d | note | PFS Engineering - PM/PE
6d778913-fee0-5e47-b043-eda08342aa16 | textbox | PFS Engineering: Sign - Initial: Sign:
b91df520-1569-5096-a5b9-7ab510cc7244 | note | PFS Engineering: C - RA
5f05da21-08b8-5ca8-8193-335e5b328426 | note | Downer - Downer
2104f719-ee78-5202-a199-e0212f20486f | textbox | Downer: Sign - Initial: Sign:
ce869a51-2a92-5f72-ae5b-3da49628382b | note | Downer: C - RA
79e745bb-aa06-4352-b3a1-f963defc11b4 | section | ITP APPROVAL PROCESS
15e04520-7e11-43ac-96ac-3edb2fe7d2f7 | checkpoint-no-value | ITP APPROVAL PROCESS
afeac28f-18d6-5c9d-8ca9-7ce51dce0b1e | textbox | Approved by [Engineer/Client]:
f86461c5-9d73-53a4-aa04-6a7c41f19eac | textbox | Issued for Construction:
452b1204-fe3e-4a0f-93bb-0a3204fe760b | signoff | Sign:
df9b0ec2-853d-4dc2-bc96-045578f411b1 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
362e2dea-cbeb-5f18-a8dd-87944374d99e | textbox | Contractor's Rep Name:
0c91afb7-e8d6-5bf7-98c5-8f5c46bd745e | textbox | Engineer's Rep. Name:
5a915530-1d12-59e8-986b-9c599e345d27 | date | Date:
b4dda904-12aa-4030-9a92-59150b04c4e8 | signoff | Add Signature
784c51f8-7f9f-4e88-beae-5c9b2395b41e | checklist | DN1212-ITP-022 Steel structure and panels - Installation RevC | itp | DN1212-ITP-022 Steel structure and panels - Installation
4f6a0959-a3ac-4366-854f-6bb629ffd885 | section | Engineering
9481e12b-864a-4473-a421-0edb8a3417c6 | checkpoint | 1 - Inspection and Test Plan Reviewed and Approved by Customer
237b99b2-3b92-5ebd-a69e-6229b63071b5 | note | Specification Standard - Project Structure Specification C0702 Rev. 01, IFC structure DWG
5eace0d8-a77d-582a-a11a-923685db39b5 | note | Acceptance Criteria - Inspection and Test plan shall be submitted to the Engineer for review and approval before fabrication is commenced.
0f1e9255-84ca-5fe3-ab93-94a5141fce6b | note | Certify Doc / Ref - IFC DWGs
28361c20-5ad1-592c-952b-f817ce984144 | note | PFS Engineering - PM/PE
f372252e-c58c-57ba-a5dd-450634a1cd9d | textbox | PFS Engineering: Sign - Initial: Sign:
13437787-8361-5fba-87f4-ec1b87f44d5a | note | PFS Engineering: C - S
47cf4aac-f23e-550c-8f6e-798ddb20e239 | note | Downer - Downer
d8d77be3-a71d-5aab-9ac5-5649aeb9b697 | textbox | Downer: Sign - Initial: Sign:
11bd517d-5264-524a-a1c5-70820cac51a3 | note | Downer: C - H
c07ba943-e550-4f8e-85b6-39c269cba878 | signoff | AUTHORITY HOLDPOINT
9247e119-fc8f-49ce-bcd4-584a024fb97f | checkpoint | 2 - Submit the required documents to Client for review
985801d1-10fd-53e2-9c41-28faed840f13 | note | Specification Standard - Project Structure Specification C0702 Rev. 01
1c753419-1b12-5de4-b389-4f25994c0a28 | note | Acceptance Criteria - Site installation methodology shall be submitted to the Engineer for review
ba7bf7a3-564f-5760-b022-d5d5a139993b | note | Certify Doc / Ref - Erection Sequence Methodology
bae6b4b4-ff99-5694-b1bc-7f27dcc614d0 | note | PFS Engineering - PM/PE
a49b643a-3b56-5f79-8c86-e2e5fee6fdd6 | textbox | PFS Engineering: Sign - Initial: Sign:
642c47c5-593c-5081-b7d4-6f7b0acea65a | note | PFS Engineering: C - S
fbac3c86-70a2-5bbb-8090-03d820f33729 | note | Downer - Downer
11731ba6-a816-5260-95fb-ceeb3bd424fc | textbox | Downer: Sign - Initial: Sign:
132145c4-7438-51da-b278-fb7e68b01554 | note | Downer: C - R
7b2a1dfe-5846-4145-9362-eac06901b84e | checkpoint | 3 - Installation Procurement - Cast in items
76c5ec8c-c132-5376-8dae-2ec0bad913e0 | note | Specification Standard - Project Structure Specification C0702 Rev. 01, IFC structure DWG
d76c8b4d-1425-54e1-ad1c-3b29d0cb4347 | note | Acceptance Criteria - Confirm Procurement and delivery of all Cast in Items:
72eb0902-aa14-58c0-a30b-2c3ddb1f591b | note | i. shear keys.
4e09552e-f50b-5950-ae2d-c15c9bc846b8 | note | ii. uplift restraints and associated nuts
8dbe9e5e-5b07-5558-bfd1-08590777195c | note | iii. plate washers.
2f4c3030-21ca-5733-974e-9a7b9b6a3ec5 | note | iv. Maccaloy bars (ETA 06/01/25) and couplers with denso tape.
84a14162-eab3-5e4b-91ea-ebdb46297308 | note | v. Reidbar and couplers + touch up protective coating.
3615e27a-84b2-5283-a0f1-7c9f140f54da | note | vi. Nylon washers and rubber sleeves.
d401b49f-e4b7-5c70-827e-1d1d078d214f | note | vii. Temporary bearing components.
21429df6-6fef-58a4-994b-17871acd835a | note | Certify Doc / Ref - IFC DWG
098d4c9c-ca86-52d4-a36d-d1b6248716e4 | note | ○ PFS: 39028-3202-000-FABRC
462fdf36-aa87-55d0-8cbc-cecff76d9e17 | note | ○ PFS: 39028-3201-000-FABRC
c6834532-f268-5ef2-9e05-3aa6ed4ad1f3 | note | ○ Mill Certs
8c3e49db-1c9f-5dcb-a788-6503a97d5995 | note | ○ Compliance Documentation
5027fbb5-5b86-5d12-81ae-5f7c96ee2ac4 | note | PFS Engineering - PM/PE
2ba1f1f0-e38a-516c-b339-3c4586b290dd | textbox | PFS Engineering: Sign - Initial: Sign:
c590fa71-fbe8-5931-aead-77ca6f4c5383 | note | PFS Engineering: C - V
2d4a1c6e-726d-430b-8160-4b8e1d96652f | section | Good Receipt on site
14e467d6-cd27-42e9-a06a-dcda695e0c39 | checkpoint | 4 - Inspection upon receipt at site
7f023d79-87c0-572f-99f6-3bff65dc61bb | note | Specification Standard - Project Structure Specification C0702 Rev. 01, IFC structure DWG
75d488be-245d-52ba-ae76-72d7c4a6414f | note | Acceptance Criteria - The material receipt at site need to be visually inspected for quantity and make sure no damage occurred during transport
03bf4c05-25c4-5d3a-a6cf-8f125c92335d | note | Certify Doc / Ref - IFC DWG
0665f9ab-07c7-59bd-bfd7-5ed7c98b3e33 | note | PFS Engineering - PM/PE
f30773c8-733b-5868-8e1a-a0fcae6ade4e | textbox | PFS Engineering: Sign - Initial: Sign:
b4637c64-3cd3-5f44-bcf2-968e0563f049 | note | PFS Engineering: C - V
279034ac-5952-5e9d-9f05-6f69b43d8e17 | note | Downer - Downer
2cb7867b-960c-5f0f-87e3-52370ce46823 | textbox | Downer: Sign - Initial: Sign:
5ddf0919-1bd4-553d-b33a-3596c2508e20 | note | Downer: C - R
c10f7982-a6a4-4c28-abec-6df9c9e31e09 | checkpoint | 5 - Inspection upon receipt at site - Cast in Items.
e5f55c58-36b1-5f13-ae0b-9b4cb87992e1 | note | Specification Standard - Project Structure Specification C0702 Rev. 01, IFC structure DWG
db5cdf1d-ec00-5c10-aad5-19fb93bfe7c1 | note | Acceptance Criteria - The material receipt at site need to be visually inspected for quantity, make sure no damage occurred during transport. All related documents have been received.
10877554-778b-513d-87b4-fb86cc8ba9c7 | note | Certify Doc / Ref - IFC DWG
96dbca08-4329-524d-bfb7-49323fe67844 | note | PFS Engineering - PM/PE
9e679a88-a750-5058-a797-acad8765750f | textbox | PFS Engineering: Sign - Initial: Sign:
f7fa3a92-0ef2-5cc1-9def-fb91384e6a71 | note | PFS Engineering: C - V
839bcacc-6486-58fc-8573-b16698128f37 | note | Downer - Downer
472ee175-4a29-53a0-be9c-f109a150de55 | textbox | Downer: Sign - Initial: Sign:
cd4bdb27-8b57-50c0-80f6-18dae17e542a | note | Downer: C - R
47d56d97-92dd-49c9-b701-b66d1b380d12 | section | Steel structure Erection
bae4007e-af1c-4ccb-82fc-cbe195fa6bf2 | checkpoint | 6 - Preparation work - prior to Span Lifting for All Spans
8af520fc-324d-5f06-b72a-dbd861d9bd35 | note | Specification Standard - Site installation methodology, Project Structure Specification C0702 Rev. 01, IFC structure DWG
bfb96200-518c-5ed4-88df-839da6506994 | note | Acceptance Criteria - Make sure survey has been done and center marks on the framework as a reference have been provided by Downer
a938de32-f085-5b4d-a866-3214d13e1bf3 | note | ○ Installation of 100x100 EA as a lifting aid on temporary structure
536a75ec-95d8-58f2-8f81-1fbaea44e49e | note | ○ Span unloaded from truck and placed on Dunnage on ground prior to rigging adjustment
c27ef1af-0885-5438-b9e2-dbce5a3969f2 | note | ○ Attaching the tag lines to Spans to prevent rotation during installation
5f70be5d-41d6-5794-af47-feefa334cbc4 | note | Certify Doc / Ref - Lift plan
aa87bc5d-002e-5dab-9cb1-1556047b5161 | note | PFS Engineering - Site project Manager
1c323367-34d2-5420-a9d6-a20c905f5a62 | textbox | PFS Engineering: Sign - Initial: Sign:
25dbc4f7-ccb1-520a-98cf-9b7aeaf6e31f | note | PFS Engineering: C - H
cbda45da-29a6-58af-87ed-6a602139d2f2 | note | Downer - Downer
f79260ee-5140-51fb-9e1c-0c62f7bcad77 | textbox | Downer: Sign - Initial: Sign:
a8576729-a744-5487-9d9e-14c05526ae41 | note | Downer: C - R
147141ec-f9ce-4382-a438-f255089a3430 | signoff | AUTHORITY HOLDPOINT
6271996d-3ba4-4b3f-973d-d6724ce90632 | checkpoint | 7 - Confirm all Manufacture documentation has been completed for Span #2
e5a12bbd-7523-50ea-8a5b-97e8c2a6626e | note | Specification Standard - Project Structure Specification C0702 Rev. 01
1232d3f2-e8b7-509c-ad1e-c89e688a3196 | note | Acceptance Criteria - Confirming that the fabrication, coating, and factory erection (including balustrade and deck panel bolting) works have been signed off.
dcbba5af-b25a-5314-82a6-85a4c8c31cc0 | note | Certify Doc / Ref - QA Documentation
92a17ffb-2927-50fe-a8b9-83b4a6345f48 | note | PFS Engineering - PM/PE
f2bab5d4-c93d-5f8c-a72c-60b12eef27ea | textbox | PFS Engineering: Sign - Initial: Sign:
07949b4f-fe3d-5bab-bc4c-40f4c904d971 | note | PFS Engineering: C - V
1cecabee-627f-414e-adbf-a33aab9ac6b6 | checkpoint | 8 - Installation of Span #2
0e5a6b3a-f518-534d-a51d-8335b2504c10 | note | Specification Standard - Site installation methodology, Project Structure Specification C0702 Rev. 01, IFC structure DWG
2e64f218-ed14-5b5c-975c-a0351bcc47a6 | note | Acceptance Criteria - Verify that the structural component is securely rigged according to the rigging plan
1eced699-6524-5298-949b-e0c47dc595aa | note | ○ To lift Span #2 and Position the component precisely over the pile and lower it slowly into its final placement on temporary girder support structure
fe7e0d13-ead8-5e1b-9dd0-8c1c81d510eb | note | ○ Chain block will be connected to the West end to adjust level.
73efe2ab-0afa-5926-a265-d0598a4fed20 | note | ○ When location is confirmed by surveyor and PFS staff, span to be secured in place to the slim soldiers.
1a4fa0d0-f5fb-5612-be35-5eefa99898f8 | note | Certify Doc / Ref - Lift plan
576dad9f-72e7-59c3-9f7a-47560504de32 | note | PFS Engineering - Site project Manager
907f0679-e857-58ef-b7b3-66ac470af293 | textbox | PFS Engineering: Sign - Initial: Sign:
d1daadc4-a876-5379-ae58-f754f7da522e | note | PFS Engineering: C - H
31976f55-4dbf-5290-b6a5-be7dca13bde9 | note | Downer - Downer
b7a66b07-93f0-59e1-ae7d-ee250d9d2af6 | textbox | Downer: Sign - Initial: Sign:
964a8010-fda6-5cdd-979a-5e3fc2ccd1c0 | note | Downer: C - R
4d9bf1d3-e69a-4487-aa76-0d5b2308109b | signoff | AUTHORITY HOLDPOINT
d1256e19-dfa3-4f78-8497-7915371a4081 | checkpoint | 9 - Macalloy Bars installation for Span #2
af99bc33-9c3d-52d4-bb22-84530ae9cfa9 | note | Specification Standard - Site installation methodology, Project Structure Specification C0702 Rev. 01, IFC structure DWG
2a2104bf-79ef-519e-84f3-a8799d6d911e | note | Acceptance Criteria - To keep Macalloy bar aligned, a coupler to be tightened to extend the Macalloy bar and Tempory nut will be added to the rod on the Span 2 high end. The nuts will be tightened to hold the Macalloy bars in correct position.
38e6125c-4fb5-5c93-9a3a-059e1921a171 | note | Certify Doc / Ref - IFC Drawing
aea35435-94a5-5704-9fcc-fa57971a5cf3 | note | PFS Engineering - Site project Manager
e8519518-8f25-5331-b516-98ab77c855fe | textbox | PFS Engineering: Sign - Initial: Sign:
c44f5214-7c2d-5d19-9de9-8beb6f8d4050 | note | PFS Engineering: C - H
a694e195-c28d-494f-bae4-7feccd0622cd | signoff | AUTHORITY HOLDPOINT
9afd1b23-014e-4af9-bd56-d1e400498045 | checkpoint | 10 - Confirm all Manufacture documentation has been completed for Span #3
f86cc23c-3b3a-5178-8630-cf436d983ee7 | note | Specification Standard - Project Structure Specification C0702 Rev. 01
5c0930b2-2c24-56cb-bda5-e575474928d2 | note | Acceptance Criteria - Confirming that the fabrication, coating, and factory erection (including balustrade and deck panel bolting) works have been signed off.
bc64f1d8-abf1-5d1c-858a-0093f3e458c6 | note | Certify Doc / Ref - QA Documentation
069185bb-95bf-5337-8620-16256b1afa12 | note | PFS Engineering - PM/PE
41097e44-d25d-5db0-9de1-0acd58e8c5e7 | textbox | PFS Engineering: Sign - Initial: Sign:
14d143cf-fa56-5dba-a449-6c05dd10d689 | note | PFS Engineering: C - V
a7c5f527-b882-529e-bfc1-0a0d3a4e7c63 | note | Downer - Downer
3f51939b-7c3d-5a8d-a962-d14cb5ef460e | textbox | Downer: Sign - Initial: Sign:
72f2f8e8-cdcf-5bf6-8391-639ba2dbc557 | note | Downer: C - R
ea987a79-b7c1-47e9-80d4-ccd1c5c24ec8 | checkpoint | 11 - Installation of Span#3
129b69cb-582b-547d-bfb1-4a6ff6bebaf9 | note | Specification Standard - Site installation methodology, Project Structure Specification C0702 Rev. 01, IFC structure DWG
47c56e98-1ffb-52c5-a5fe-04ddff53ffa0 | note | Acceptance Criteria - Verify that the structural component is securely rigged according to the lift plan
26201418-595c-52e1-aeed-607d691a43ea | note | ○ To lift Span #3 and Position the component precisely over the pile and lower it slowly into its final placement on temporary girder support structure when location is confirmed by surveyor and PFS staff, span to be secured in place to the slim soldiers.
9110b681-b6c3-5ffc-96f7-189ff4a01afc | note | Certify Doc / Ref - Lift plan
defea15e-f9c1-53f6-8ad6-3638ee8a6519 | note | PFS Engineering - Site project Manager
458f1ecd-9ed0-58c4-8805-550024f01e59 | textbox | PFS Engineering: Sign - Initial: Sign:
b75443d1-3697-5964-8218-4129d59d590d | note | PFS Engineering: C - H
1f0674a1-ff5b-5ac0-81e7-a4fb3a6271a6 | note | Downer - Downer
0bd1fe50-0675-59b1-995e-ebb55a44f427 | textbox | Downer: Sign - Initial: Sign:
a66539ec-8565-5213-9cab-e7345e46f874 | note | Downer: C - R
99c0864b-f867-4cfc-9717-0d4b7d773ad8 | signoff | AUTHORITY HOLDPOINT
e63712e9-50f9-4c41-8361-47f0a672dbea | checkpoint | 12 - Shear Keys, Hold Down Bolt and Reidbars Installation for Span #3
215512a2-8d53-526d-8bdf-f3be75e53195 | note | Specification Standard - Site installation methodology, Project Structure Specification C0702 Rev. 01, IFC structure DWG
12f09dd2-7707-5ebd-a58d-8a9835439a7a | note | Acceptance Criteria - The longitudinal and latitudinal Shear keys are to be installed to secure the position of span from movement during Head stock Pouring
0416b059-f06e-5918-9138-f421eea22093 | note | ○ Hold Down Bolt to be Installed
9cf70f55-a8be-5b09-bab1-06f5fc3b3be9 | note | ○ Nuts on Reidbar to be snug tightened to help minimal lateral movement.
3afda904-e4eb-569e-8134-1a3e631ba25a | note | Certify Doc / Ref - Shear keys, Hold Down bolts and Reidbars Drawing
ae53bc8c-2cbb-5643-ac53-6ee7d4a345d7 | note | PFS Engineering - Site project Manager
b286ff7c-52f2-573b-9a1e-7375f737d27b | textbox | PFS Engineering: Sign - Initial: Sign:
134c7614-10ce-53bd-8801-2706737e60bb | note | PFS Engineering: C - H
35150d6f-c3c2-5248-96bf-b2373ee52fd2 | note | Downer - Downer
a2a2d6f4-b81b-55c2-8371-901b597f274b | textbox | Downer: Sign - Initial: Sign:
25cf8062-ce93-5548-b67b-04788908a5f8 | note | Downer: C - R
56f8c7e8-ac49-4022-b1e3-a66a6f20dbd4 | signoff | AUTHORITY HOLDPOINT
eb14b217-7517-4a6f-a748-201445f954e4 | checkpoint | 13 - Confirm all Manufacture documentation has been completed for Span #4
bcd001a2-cfe1-56e2-938f-99f37aca87ea | note | Specification Standard - Project Structure Specification C0702 Rev. 01
ddc565a7-dbd4-5859-ad93-b824e289f8df | note | Acceptance Criteria - Confirming that the fabrication, coating, and factory erection (including balustrade and deck panel bolting) works have been signed off.
0b38d8fa-0752-5d4a-8cba-c58c45012250 | note | Certify Doc / Ref - QA Documentation
b0781d20-f0e7-510d-9c87-ad63bd1f31a6 | note | PFS Engineering - PM/PE
002cc7ed-fd34-5a2f-a631-1d98c0e6af14 | textbox | PFS Engineering: Sign - Initial: Sign:
51352733-6543-531d-a5fc-407a39873bb0 | note | PFS Engineering: C - V
41b52038-b76f-42e2-8975-8f29b75e720b | checkpoint | 14 - Installation of Span#4
ba6b5c08-630a-50dd-9a05-a6a72213a004 | note | Specification Standard - Site installation methodology, Project Structure Specification C0702 Rev. 01, IFC structure DWG
d8bb36b3-be64-5756-bb6c-22009dcfe8a6 | note | Acceptance Criteria - Verify that the structural component is securely rigged according to the lift plan
1a6ecd35-7a39-5ee7-bb28-061299fe8a69 | note | ○ To lift Span #4 and Position the component precisely over the pile and lower it slowly into its final placement on temporary girder support structure
2538c402-e3fe-5f73-9f90-434522d5010e | note | ○ When location is confirmed by surveyor and PFS staff, span to be secured in place to the slim soldiers.
c7df3162-cd41-5e90-8fe3-6a31ab03b71d | note | Certify Doc / Ref - Lift plan
0a621101-1199-5a27-8686-b3d1e1058b3c | note | PFS Engineering - Site project Manager
bde8690e-3da7-5ec0-a4e9-f03ef2e7c8e1 | textbox | PFS Engineering: Sign - Initial: Sign:
79ad2102-c686-5461-a11a-55b24e25966c | note | PFS Engineering: C - H
8f643c8b-8730-581d-8051-5793e639e057 | note | Downer - Downer
a9c5fba3-f3fe-5899-a455-ae4150fe97dc | textbox | Downer: Sign - Initial: Sign:
8e6df505-65dd-5003-a883-40ff7a44f7b3 | note | Downer: C - R
121a751c-2d3b-4682-a8b5-768e4e38031c | signoff | AUTHORITY HOLDPOINT
915a192d-b09d-4b27-8d11-f6203496ed48 | checkpoint | 15 - Shear Keys, Hold Down Bolt and Reidbars Installation for Span #4
eebdcecb-5d11-5c51-b2bd-74af1ef9f7bc | note | Specification Standard - Site installation methodology, Project Structure Specification C0702 Rev. 01, IFC structure DWG
5109b55b-8e93-5351-acf5-7da80a46406e | note | Acceptance Criteria - The longitudinal and latitudinal Shear keys are to be installed to secure the position of span from movement during Head stock Pouring
ca3a7f34-a7df-5571-8fe7-0e55600f3daa | note | ○ Hold Down Bolt to be Installed
ff54072d-273a-5394-ba66-f95ccd6ab2cd | note | ○ Nuts on Reidbar to be snug tightened to help minimal lateral movement.
4b78426d-c17e-5bbd-b79c-ff1901b543bc | note | Certify Doc / Ref - Shear keys, Hold Down bolts and Reidbars Drawing
82ea4cd6-9cff-5f6b-b93c-dd67712c4b84 | note | PFS Engineering - Site project Manager
b747ac31-3e84-5dc8-a144-c8623463c4ce | textbox | PFS Engineering: Sign - Initial: Sign:
46b3f8ca-80de-56ee-9310-9cf80a750153 | note | PFS Engineering: C - H
e889a543-7e77-54f2-8211-0eb4f40f4dad | note | Downer - Downer
868cb4eb-0c6a-5e7d-bb23-7c7ddc080b31 | textbox | Downer: Sign - Initial: Sign:
c4c33a67-c95e-5d80-8449-44474060e0f3 | note | Downer: C - R
87257ced-9e78-4915-ad0f-2d74554c9bb5 | signoff | AUTHORITY HOLDPOINT
fd67ea01-171a-4317-98e3-416aa613f463 | checkpoint | 16 - Confirm all Manufacture documentation has been completed for Span #5
7c863901-e6df-55af-bae9-a0db30017b73 | note | Specification Standard - Project Structure Specification C0702 Rev. 01
070bb3db-be43-58a4-8070-066e5a827dfc | note | Acceptance Criteria - Confirming that the fabrication, coating, and factory erection (including balustrade and deck panel bolting) works have been signed off.
7822d3f6-0076-5fd3-b3d0-d307e93369f8 | note | Certify Doc / Ref - QA Documentation
6106e571-0e22-5f4c-acf8-97984f7be0af | note | PFS Engineering - PM/PE
0a6a3337-8a32-556e-9650-d3e0c2561839 | textbox | PFS Engineering: Sign - Initial: Sign:
fe62a5a2-264f-5939-b611-d8abee41fd28 | note | PFS Engineering: C - V
33b2d8d0-a85b-4f0d-acf1-69b9ef6a0022 | checkpoint | 17 - Installation of Span#5
d485cf4a-c693-561c-ab67-076dc994b454 | note | Specification Standard - Site installation methodology, Project Structure Specification C0702 Rev. 01, IFC structure DWG
dd2e5f3f-93c2-5ad3-85a1-2b7f9abe0f38 | note | Acceptance Criteria - Verify that the structural component is securely rigged according to the lift plan
02e07c80-7126-5e5d-823e-c5ecdb62df1e | note | ○ To lift Span #5 and Position the component precisely over the pile and lower it slowly into its final placement on temporary girder support structure
e0118305-a0f3-547d-bf1e-5af4a5374c1e | note | ○ When location is confirmed by surveyor and PFS staff, span to be secured in place to the slim soldiers.
a3a1a854-5d59-51a2-bd9c-a819a657f5f9 | note | Certify Doc / Ref - Lift plan
f751f815-017f-5ea6-9a50-c78633193a81 | note | PFS Engineering - Site project Manager
c58cb33f-d1f4-5c09-a68a-f1bc91e3dcd9 | textbox | PFS Engineering: Sign - Initial: Sign:
0e3fcfd3-6b7b-5c4b-b61c-4071a50a28b2 | note | PFS Engineering: C - H
b7136b04-edbc-5dbb-bd8e-91c0279630c8 | note | Downer - Downer
153322eb-7383-56fd-9c27-8adbcb7dda32 | textbox | Downer: Sign - Initial: Sign:
03869c92-c010-54c1-a69e-cf6c336f7ebf | note | Downer: C - R
393f8f26-89f4-4a40-9dc8-d9872f13063e | signoff | AUTHORITY HOLDPOINT
18dba4ef-2a5c-4289-98fd-f5f79dcd45ed | checkpoint | 18 - Shear Keys, Hold Down Bolt and Reidbars Installation for Span #5
0575be4b-2161-529b-ac70-3097e6b45cb0 | note | Specification Standard - Site installation methodology, Project Structure Specification C0702 Rev. 01, IFC structure DWG
8f5d5f2f-d1e6-5cdc-85d4-eedb099fa876 | note | Acceptance Criteria - The longitudinal and latitudinal Shear keys are to be installed to secure the position of span from movement during Head stock Pouring
617a5c34-3cc1-5e06-88fd-69fba5ef39db | note | ○ Hold Down Bolt to be Installed
5608ea18-6f63-5136-90f8-eb8a4a0cc98f | note | ○ Nuts on Reidbar to be snug tightened to help minimal lateral movement.
7c9bdce5-d978-5b48-9ed2-4c7b7246dd08 | note | Certify Doc / Ref - Shear keys, Hold Down bolts and Reidbars Drawing
4d8d2bda-9761-5955-b6b9-70eb6c6b82d5 | note | PFS Engineering - Site project Manager
b22195d2-d5fd-5651-9caf-515825722ed6 | textbox | PFS Engineering: Sign - Initial: Sign:
86aeb64d-a706-5299-8a43-fb9f989f2e0f | note | PFS Engineering: C - H
8cfaa5a6-d277-5c81-9d81-4b04c373ff5b | note | Downer - Downer
192369ac-ece2-59fa-af87-19a72e68067e | textbox | Downer: Sign - Initial: Sign:
d5f24482-8b88-55ae-80e5-18f169df8cf1 | note | Downer: C - R
3e2b2179-c3a5-49f4-828c-a4d432e193de | signoff | AUTHORITY HOLDPOINT
e6971981-be31-4e78-b577-16da269d96ec | checkpoint | 19 - Confirm all Manufacture documentation has been completed for Span #6
75a555b4-f014-5b3d-bb4a-91a783438931 | note | Specification Standard - Project Structure Specification C0702 Rev. 01
eafe1c5c-088a-563d-a9f6-5d9e702f6e5a | note | Acceptance Criteria - Confirming that the fabrication, coating, and factory erection (including balustrade and deck panel bolting) works have been signed off.
45a4c1eb-79a3-5c52-85af-9f8e9b4af21d | note | Certify Doc / Ref - QA Documentation
9d19e18d-16ca-588a-b21d-c5de9eca0968 | note | PFS Engineering - PM/PE
fa937a22-cd2c-5a02-bbbf-8eecf5da0956 | textbox | PFS Engineering: Sign - Initial: Sign:
fd98208c-53e0-5307-a55c-fad485ef481c | note | PFS Engineering: C - V
076377b8-8b76-4b47-bd58-f6c9f9401cc2 | checkpoint | 20 - Installation of Span#6
668093c9-ccd6-5cb5-8c6a-46d04bf12b10 | note | Specification Standard - Site installation methodology, Project Structure Specification C0702 Rev. 01, IFC structure DWG
eb76558e-eb91-57b1-87c6-87f23322e45c | note | Acceptance Criteria - Verify that the structural component is securely rigged according to the lift plan
ebea5d16-f8f2-50f5-833e-cb5ee89bf4a7 | note | ○ To lift Span #6 and Position the component precisely over the pile and lower it slowly into its final placement on temporary girder support structure
7cb7446e-7b97-54fa-a09d-5ad69e014d6a | note | ○ When location is confirmed by surveyor and PFS staff, span to be secured in place to the slim soldiers.
69454393-9248-5ef4-b0b3-42aa7011ec15 | note | Certify Doc / Ref - Lift plan
b31ba3d7-604c-5432-ae0c-322cad6e91ec | note | PFS Engineering - Site project Manager
b6da4699-f7bc-5863-94c3-37d56437b24c | textbox | PFS Engineering: Sign - Initial: Sign:
7b7d15b0-8719-53bc-b2e7-e33abfa7161c | note | PFS Engineering: C - H
0d820797-7fb3-5d72-8cb2-6b94ad5aec3a | note | Downer - Downer
d2786847-a881-5381-ae3e-e5df16e97e6b | textbox | Downer: Sign - Initial: Sign:
54433477-9219-5396-b196-622c092a56cc | note | Downer: C - R
bf4c59a1-9d5b-4765-a799-4f707fb475cd | signoff | AUTHORITY HOLDPOINT
35c315e8-e462-4c54-be24-c46d8c4af8ec | checkpoint | 21 - Shear Keys, Hold Down Bolt and Reidbars Installation for Span #6
5c040a0a-8886-58e9-99bd-b80b2c07eb42 | note | Specification Standard - Site installation methodology, Project Structure Specification C0702 Rev. 01, IFC structure DWG
838cb4cc-a56a-5619-b5d3-395a5238ca7c | note | Acceptance Criteria - The longitudinal and latitudinal Shear keys are to be installed to secure the position of span from movement during Head stock Pouring
200d0162-ab52-5039-9819-2d44285e0c11 | note | ○ Hold Down Bolt to be Installed
7fe36471-625a-58fd-b14e-5280cc397d64 | note | ○ Temporary Bearing installation under lower end
a3d5d3b4-f9c2-509e-8cb2-fbdd78819b8d | note | ○ Nuts on Reidbar to be snug tightened to help minimal lateral movement.
02e49be5-4be6-5df8-8c0b-9d63fe8b4005 | note | Certify Doc / Ref - Shear keys, Hold Down bolts and Reidbars Drawing
d656e53c-b2a6-52a9-987c-5f1ac85b7c39 | note | PFS Engineering - Site project Manager
8d47bfbb-2eaf-5c63-ab41-c94662f2fa17 | textbox | PFS Engineering: Sign - Initial: Sign:
d1ce8447-93a0-5568-8a93-db12fd6e7ad6 | note | PFS Engineering: C - H
8e34f7f5-0f5b-5935-96c4-845ce30058c6 | note | Downer - Downer
19dc4482-4e77-5f41-9531-e9e2079cc7e0 | textbox | Downer: Sign - Initial: Sign:
d0350445-fbdb-569c-970a-1cec715d88f2 | note | Downer: C - R
bd59ced1-1934-4190-ac2c-f3ff5d9e0ca9 | signoff | AUTHORITY HOLDPOINT
3c6de246-f2c2-4dcf-a8ce-66b126fb7fb9 | checkpoint | 22 - Dimensional survey By Downer
3851b8be-60cd-5e97-9783-83115320c176 | note | Specification Standard - Site installation methodology, IFC Drawings
bcba6601-ec6a-5c39-885d-5f0c5ad3e045 | note | Acceptance Criteria - Conduct a thorough dimensinal survay inspection to confirm that the component is correctly positioned and secured based on IFC Drawing.
b9692610-d6a5-507e-8f12-8070a761939e | note | ○ Measured dimensions shall be within stated tolerances unless noted otherwise.
4e8ac286-8d4d-5764-b4da-20d4b85a2a8b | note | ○ Project specification clause C0702.1.3
e21ebc53-2c7a-5e1c-80ed-24578f0a1636 | note | ○ Functional Tolerances shall be class 2 as per AS/NZS 5131 Table F2.1 to F2.10
04842881-991f-5d92-8293-7bdb1de6ac3e | note | ○ Record the lifting operation in the project log, including any deviations or required adjustments to be made.
9647c072-b99e-5284-8424-999173803162 | note | Certify Doc / Ref - Marked up and Signed IFC DWGs
f8ba4c98-8ad0-5bef-a4ef-5c0ecf534efe | note | PFS Engineering - Site project Manager
ea0fcebe-5972-5975-90e4-7930f5bb3917 | textbox | PFS Engineering: Sign - Initial: Sign:
81d07b44-f26e-5dc0-bfa6-c872451ffe6a | note | PFS Engineering: C - H
c6ad8f9d-44e3-586e-bd76-b6e5dbeed334 | note | Downer - Downer
0fd838e9-4773-5f90-aa21-dd9e17520c58 | textbox | Downer: Sign - Initial: Sign:
b9891f6b-9403-502d-918c-72d3676adb7b | note | Downer: C - H
1228e28a-1e16-4f9e-bda4-8bc91cc3b239 | signoff | AUTHORITY HOLDPOINT
532e9923-ab8f-471d-a442-5db3a0f216a9 | checkpoint | 23 - Remove Reid bar tension.
0920bed3-3708-5fe6-b2bd-a3ffc8047e13 | note | Specification Standard - Site installation methodology, IFC Drawings
6908b2c1-658e-59d4-8f8d-dfcd7918b2cd | note | Acceptance Criteria - Lossen Reidbars to match IFC drawing detail at all peirs before any headstock pours.
30df79dd-4a3d-50f4-918b-d9a5d8ff091f | note | Certify Doc / Ref - IFC DWGs
a1f8075a-98fd-560e-ae7a-f210a407afe2 | note | PFS Engineering - Site project Manager
4a2bc256-f3e9-597a-ba81-087b62d7c9d1 | textbox | PFS Engineering: Sign - Initial: Sign:
91592bc6-92a1-5f1c-86d4-45325abf2829 | note | PFS Engineering: C - H
129dcf0b-a0ca-5038-b79a-153f20073c44 | note | Downer - Downer
c62a8d27-7bd0-5a35-8234-57a8e912a15d | textbox | Downer: Sign - Initial: Sign:
adc01450-9aac-5258-a10f-0166073b7526 | note | Downer: C - H
8cb3e4ad-8d9b-43f2-91f2-6454e0f43b4d | signoff | AUTHORITY HOLDPOINT
cbaac2a2-bfa6-4a1b-9bec-7fb8eef7e53b | checkpoint | 24 - Reid bar touch up painting (if required)
e51dba3e-7264-569f-81d3-0da5647af4c8 | note | Acceptance Criteria - Any coatings damage to Reidbars touched up as per paint specification, Coatings to comply with note 1.2 on drawing ST-3202.
ba873c5e-5d7c-518f-b38e-4774d88c01e9 | note | Certify Doc / Ref - Project Paint Specification
93a5a54d-8bb6-541f-968e-3608b3780091 | note | PFS Engineering - Site project Manager
852ac648-e4e3-595d-a50c-4bd46f22979c | textbox | PFS Engineering: Sign - Initial: Sign:
5c2b9b8a-c7cc-570f-b31a-d3113e330ea2 | note | PFS Engineering: C - V
fcdb59d2-2e5f-5c62-8ac5-d2e838deafa6 | note | Downer - Downer
6a926d15-c657-5b8b-82c8-84b250112ce7 | textbox | Downer: Sign - Initial: Sign:
351b90e7-47eb-5d27-85f2-3c3b17a01f8a | note | Downer: C - V
ba075146-639a-4eef-a7b0-5a5310b8e715 | section | Post Head stock Pouring activities
92613b22-1012-420d-8817-f45e4df54c04 | checkpoint | 25 - Hold Down Bolts tightening
fb03f32d-3807-5a9e-bbf1-ff84935ec497 | note | Specification Standard - Site installation methodology, IFC Drawings, Standard operation procedure for steel structure bolt tightening, SHEQ-01-02-0038
7d9de17d-8f30-5c84-9306-8a65c14a1362 | note | Acceptance Criteria - Remove additional nuts, tape (masking and double sided) used for alignment. Apply rubber sleeves to the exposed threads. Reinstall oversized washers, apply instulating washers and tighten nuts down to achive a 1mm gap between washer and nut, lock nut to be installed as per detail C & Section 5 on ST-3202, Detail D on ST-3200.
9760473c-731f-58f5-be50-0756e7592fe4 | note | Certify Doc / Ref - Bolt Tightening report
26dbc011-43b1-5820-8ab5-eaf5dca50793 | note | PFS Engineering - Site project Manager
83e083df-86b9-5c7a-a1b2-398aba976eab | textbox | PFS Engineering: Sign - Initial: Sign:
ec9cd500-c3e7-5be0-ae0f-0d73913bbbff | note | PFS Engineering: C - H
de62c3bd-c9c2-489e-86b0-d1e3fcdfc532 | signoff | AUTHORITY HOLDPOINT
2a2d3845-4ad5-4f32-b466-477a14e7112b | checkpoint | 26 - Macalloy Bolts tightening
7e73b457-fdd6-5601-b818-43ba3bffb59f | note | Specification Standard - Site installation methodology, IFC Drawings, Standard operation procedure for steel structure bolt tightening, SHEQ-01-02-0038
2a6ca62c-ca5e-59e6-9077-08d7c2cf7065 | note | Acceptance Criteria - to Undo the coupler, remove temporary alignment nut, install the rubber sleeves to the exposed rod, install the washers, nuts and snug tighten the nuts (as there are compressible components in contanc area)
d8d73c03-4fba-5f86-9c10-70c6139b345b | note | Certify Doc / Ref - Bolt Tightening report
6a6a6e51-ba62-5084-88cf-6687f55c7e37 | note | PFS Engineering - Site project Manager
693e8eeb-85ac-5144-8a74-d47869f4877b | textbox | PFS Engineering: Sign - Initial: Sign:
76f9b045-5b2a-51e6-871e-378dd4c2b4ac | note | PFS Engineering: C - H
ca8b8f4f-35f5-44b1-8035-718f92a664d8 | signoff | AUTHORITY HOLDPOINT
df00d291-e289-4543-9d93-5c2b90c4ba43 | checkpoint | 27 - Temporary restraints removal
6cb290a1-9b2b-5d81-aef1-b9a67ae51b51 | note | Specification Standard - Site installation methodology, IFC Drawings
d3087805-be3f-58f4-83e3-82e44b01942a | note | Acceptance Criteria - All temporary restraints to the temporary shoring to be removed
5876014e-70db-5ac1-8484-92290c30abfb | note | ○ All positioning Jigs and screws applied to PTFE on Shear Keys to be removed
deb46341-0998-5708-8c59-a1a187f14d8c | note | PFS Engineering - Team Leader
9d366857-3bba-5587-8594-fa02524f87ed | textbox | PFS Engineering: Sign - Initial: Sign:
86887647-121e-5117-b654-51bcde9a41fd | note | PFS Engineering: C - V
e25bc11d-b6fc-460d-a3e0-4343e2ff8dd4 | checkpoint | 28 - Installation of Granor Bearing
c5da8199-9b47-59cc-9675-a3fb03cac877 | note | Specification Standard - Site installation methodology, IFC Drawings, Standard operation procedure for steel structure bolt tightening, SHEQ-01-02-0038
0c6f6149-0f51-5c19-9212-2159930dbf3a | note | Acceptance Criteria - The Temporary Bearing to be removed and Granor Bearing to be installed in the position
a7fec47d-33b1-5153-9168-98a30720dc0b | note | ○ The Bolts need to be snug tightened to the girders (top) and screws need to be snug tightened into the base plate.
c6884580-8287-5624-ba0c-b5a47289501e | note | ○ The keeper plates' bolts (M20) for uplift restraint to be tightened (full Tensioned).
072c693c-0d74-5c60-99a9-0e0458054f1b | note | Certify Doc / Ref - Bolt Tightening report
db0f3cf0-559e-5fae-9c72-c62f843dce13 | note | PFS Engineering - Site project Manager
ea6ef2ab-8af5-5d89-a2a5-aa99d74cd19b | textbox | PFS Engineering: Sign - Initial: Sign:
8335b7d4-7c18-51fc-9215-800242473d56 | note | PFS Engineering: C - H
a6920d70-c799-46de-81ff-17399ccba9c0 | signoff | AUTHORITY HOLDPOINT
855549fe-19fd-47b0-ab9c-24414467f04c | checkpoint | 29 - Installation of remaining Decking panels and wall panels
66ef901e-e4da-5bd3-9187-d0cfad0133ed | note | Specification Standard - Site installation methodology, IFC Drawings
7366f1f6-ec6c-50eb-9d87-11e434e3833e | note | Acceptance Criteria - Carefully position the Decking and wall panels in the conjunction area according to the approved drawings.
fd37b53c-e829-517e-b1b5-b51fb6bbf0fa | note | Certify Doc / Ref - IFC DWGs
0d9aba85-881e-5fb6-b31e-6b8582c14f0a | note | PFS Engineering - Team Leader
86c6f15b-c1ed-5fc4-a2a2-4d1cc162ddd4 | textbox | PFS Engineering: Sign - Initial: Sign:
e8a0a436-8a0d-50a6-9cc4-3b58d63b4a37 | note | PFS Engineering: C - D
aaf254b2-8173-48c7-8061-74061c8fd23e | checkpoint | 30 - Snug tightening of Decking panels and wall panels
d135a39a-4263-54db-9bd9-a43b32da68e4 | note | Specification Standard - Standard operation procedure for steel structure bolt tightening, SHEQ-01-02-0038
9235fafe-85b5-57a3-868b-d8aa35218312 | note | Acceptance Criteria - Fasteners of Decking and wall panels to be inspected for snug tight condition and marked with coloured paint pen to confirm fixing condtion has been checked and verified.
70cfa766-933e-5f39-add7-55e94af02f13 | note | Certify Doc / Ref - Bolt Tightening report
536b2ae6-22a6-5682-9301-5d529d07860b | note | PFS Engineering - Site project Manager
5a5d3383-9e81-5cea-bfb1-aa06f72fe0dc | textbox | PFS Engineering: Sign - Initial: Sign:
b6d30b40-5930-5599-98b3-01be2ba68369 | note | PFS Engineering: C - H
a818962d-2122-4187-86a9-f1f6f82c11de | signoff | AUTHORITY HOLDPOINT
7b499fa5-b11f-402a-9f23-49069fc25058 | checkpoint | 31 - Installation of remaining handrails between the spans
d0e0ede5-e20e-580c-b393-c494338dcb46 | note | Specification Standard - Site installation methodology, IFC Drawings
5eb56516-afff-58b1-b3d7-7b06e0aa3c4a | note | Acceptance Criteria - Carefully position the handrails in the conjunction area according to the approved drawings.
0990feab-735a-58f8-896b-69517ecff975 | note | Certify Doc / Ref - IFC DWGs
e70346d3-496e-503b-8d29-77a18f320952 | note | PFS Engineering - Team Leader
017a5312-33fc-5312-97a0-7e8e08383680 | textbox | PFS Engineering: Sign - Initial: Sign:
e2fdfdf4-33af-573f-9afc-2a5450afa6b7 | note | PFS Engineering: C - D
42523856-4655-416c-8dcc-3c7459a74bd6 | checkpoint | 32 - Snug tightening of Conduti Brackets
2b4c4b3d-5eea-5e37-8d65-3790bc9c39ee | note | Specification Standard - Standard operation procedure for steel structure bolt tightening, SHEQ-01-02-0038
b60fd9da-9cfd-5768-9a30-83033887b9c6 | note | Acceptance Criteria - Fasteners of handrails to be inspected for snug tight condition with addition of Loctite or Locknut to prevent loosening and marked with coloured paint pen to confirm fixing condtion has been checked and verified.
4e1a86a1-9a61-518d-8440-8543c93483a0 | note | ○ Note: The connections for the EA's spanning the pier movement joints shall be hand tightened, Ref CAN 063.
f5740e39-cb5e-515f-affc-7975ac330b50 | note | Certify Doc / Ref - Bolt Tightening report
4bbe7e20-f258-5634-9e8f-700bb7a672af | note | PFS Engineering - Site project Manager
a409b69d-b78a-5301-923d-61cf62385d7d | textbox | PFS Engineering: Sign - Initial: Sign:
38dc9720-0853-51b6-93f4-136cbe657543 | note | PFS Engineering: C - H
536e7023-6557-400b-af32-f461a02fa4a8 | signoff | AUTHORITY HOLDPOINT
2d13cce2-20a1-4070-aee6-ada0bc29996e | checkpoint | 33 - Installation of Expansion plates
2f0fc60c-59e5-5baf-9334-47ce48ca061f | note | Specification Standard - Site installation methodology, IFC Drawings
70e42eb1-f152-543b-96ff-e312d0571052 | note | Acceptance Criteria - The expansion plates to be installed between Span 1 and 2 and between span 6 and 7
79f2995e-dcf6-5664-8e38-484f45868563 | note | Certify Doc / Ref - IFC DWGs
fc742f9a-4012-5436-a3cc-168a7d49cce5 | note | PFS Engineering - Team Leader
9e9a397a-0126-5bd5-8c84-2f6de6779563 | textbox | PFS Engineering: Sign - Initial: Sign:
6ab543cd-d4d6-574f-a6db-8bd11fa49084 | note | PFS Engineering: C - D
3551d58c-9702-4a3b-88b1-6d71cb900861 | checkpoint | 34 - Inspection to identify any damage to painted surfaceses requiring touchup
aba369d2-dd72-5a94-a9e3-5e92c51a65c0 | note | Acceptance Criteria - Inspect paint for any required repair and touch up of paint works (bolted connections and any damage paint to steelwork). Repair method proposed shall be approved by the independent coating inspector. Areas repaired shall be reinspected by the coating applicator and independent inspector.
038013a5-f4cc-5d92-a28c-60665a786b35 | note | Certify Doc / Ref - Note 1.2, Drawing ST-3202
4ed098eb-444a-5dad-9444-c75519cac801 | note | PFS Engineering - Site project Manager
f778d674-ef41-516b-a732-ff06c1b2f761 | textbox | PFS Engineering: Sign - Initial: Sign:
4664ae02-ec15-557d-80e4-7ee0cbda70a4 | note | PFS Engineering: C - H
82323631-f8c7-51a7-897e-57689ea4494b | note | Downer - Downer
b7d2e5e3-b45f-5f1d-b6ac-c1ed6fe22a32 | textbox | Downer: Sign - Initial: Sign:
9d2ca93a-1f2a-54fa-9c62-b2fa0aef01db | note | Downer: C - H
0c85e475-76b9-4a1a-89f2-e754d3a43c4a | signoff | AUTHORITY HOLDPOINT
9811e5ae-2d4e-4eb3-aa9f-a22f113482e7 | checkpoint | 35 - Site Installation and Sign-off.
b9019bfa-e3c2-5b5f-b287-31a40032df85 | note | Specification Standard - Erection sequence methodology (EMS), IFC Drawings
dd446b4e-a85f-5e80-b595-70f2ec6161c3 | note | Acceptance Criteria - Visual and Dimensional inspections completed by PFS Project Manager to confirm manufactured items have been completely installed.
bf86437a-ffce-5273-9ffc-83d4f4e6ae37 | note | ○ Inspection of erected steelwork in accordance with AS/NZS 5131 Section 13.11 as per specification C0702.1.10.
060876e6-e1aa-54cb-a6e7-0454d913953a | note | ○ Inspections shall cover all relevant items listed in clause 13.11.1.
392974fc-8b99-561a-a049-84c8ba4751cd | note | ○ Inspections shall be documented in inspection reports as per clause 13.11.3 of AS/NZS5131, and included in the QA documentation.
a9d7ed1f-6c9c-505a-b99b-48b9c74c4805 | note | ○ Inspections shall be conducted by competent personnel. Evidence of experience or qualifications for nominated individual(s) shall be provided for review. An example of qualification of competent personnel is a relevant trade qualification and over 10 years experience in structural steel erection.
a15ca5e0-9756-509a-adc6-23141368560c | note | ○ Following inspection on site, should any modification or repairs be required a written procedure shall be submitted to the Engineer prior to any work proceeding as per C0702.3.
5212ebb5-c92d-5a90-a9c3-9c7d343a7208 | note | Certify Doc / Ref - IFC DWGs
0e0cc501-f0fb-5d5f-a910-c789e9514659 | note | PFS Engineering - Site project Manager
6fd3cee8-f1a8-5eee-bbea-4ca62bd1f92d | textbox | PFS Engineering: Sign - Initial: Sign:
c05bd558-f45f-5a7e-9685-b6c00ae908a8 | note | PFS Engineering: C - H
5eea263b-a1c4-515d-b8a1-05e179bafe83 | note | Downer - Downer
2f4be045-565c-5284-af99-3501997f3fe4 | textbox | Downer: Sign - Initial: Sign:
fb942655-fa90-5bbe-892f-a463b3a39503 | note | Downer: C - H
0d635619-1cf9-4e12-8ecf-d1e00dfc427c | signoff | AUTHORITY HOLDPOINT
bcb2a49f-264c-41e2-b013-929c42c184b7 | section | Quality Review
2c6b38f2-9d18-4b07-8dcb-37e50e229044 | checkpoint | 36 - Compile, review and submit documentation
f7a4985d-6ef4-5d54-855b-9b4cdba521a4 | note | Specification Standard - Project Structure Specification C07 Rev. 01, IFC structure DWG
d04dd0d8-55ed-50af-8bf6-8285f8b2cefe | note | Acceptance Criteria - Documentation and reports to support installation of steel structure items compiled into PFS Manufactures Data Report
b4ef77e9-f886-564d-b576-e5e01901458c | note | Certify Doc / Ref - PFS Manufactures Data Report
8ff4ea88-d334-56aa-83e3-ba7bc0ad8dbe | note | PFS Engineering - Site project Manager
504b6e24-721b-5df8-98cf-8e33b0852a52 | textbox | PFS Engineering: Sign - Initial: Sign:
2a8bde63-200e-53a8-a280-f4a571f82fb8 | note | PFS Engineering: C - S
7029babb-7749-5f96-ac0b-ed02f9db73dc | note | Downer - Downer
fe40d06b-1557-5946-bc5d-5bfb91bac42a | textbox | Downer: Sign - Initial: Sign:
5f0f07e2-3382-505f-8419-0abb2ec6ed0b | note | Downer: C - RA
dcd42985-79ee-42f2-aa9a-3e29e9ea2b55 | section | ITP APPROVAL PROCESS
615d31a3-b509-486e-ba0d-97c01abfc4e1 | checkpoint-no-value | ITP APPROVAL PROCESS
6f35b94b-9345-50ee-be16-bb2260788398 | textbox | Approved by [Engineer/Client]:
d502425e-e193-5887-8647-1fb707e35892 | textbox | Issued for Construction:
61e1e3ca-1af4-41a5-bd47-ab8874bb6975 | signoff | Sign:
1b41e7fa-d4cb-455f-9207-51e96045f75e | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
4b66fa01-73b7-58d1-8527-e271861d699d | textbox | Contractor's Rep Name:
4c10a94a-4dc6-53ca-9dca-76c212d9441d | textbox | Engineer's Rep. Name:
4bbe5e39-aca6-5ea6-bbad-c6dbf4c8622a | date | Date:
44c009bb-510a-4b5a-8483-645c541a6b62 | signoff | Add Signature
a96ac2f6-ee7c-44b3-8278-3abf7a5e0a2c | checklist | DN1212-ITP-023 Earthing & Bonding | itp | DN1212-ITP-023 Earthing & Bonding
53a41d8b-d7d9-453b-b80d-3799c51b6528 | section | 1.0 - OH &S
3f091324-7be7-4678-a133-ddf53374aaeb | checkpoint | 1.1 - The following document is to be submitted for review/approval: Safe Work Method Statement (SWMS)
9cf5839e-2a80-5f8b-8074-4d2403169879 | note | Application Std. & Acceptance Criteria - AS/NZS ISO 480-1-2001 & project OH&S Management Plan
2fb39e3b-06ba-5cf8-bded-cc519b94159e | note | Timing or Frequency - Prior to commencement
0ccc6998-64ba-5ab6-a047-d5051af3ba29 | note | Records & Remarks: Downer - R
46729371-1105-5521-a4a2-f5787cc352c1 | note | Records & Remarks: Alpha Rail - R
89c8e88b-1350-47c8-89db-f2553377895c | section | 2.0 - ENVIRONMENTAL
17c9c8dd-29ae-4ac1-8581-72a03229dc68 | checkpoint | 2.1 - Environmental: Environmental Control Plan
a67edef8-bd0e-5d51-bbe7-cd075c58f0cb | note | Application Std. & Acceptance Criteria - AS/NZS ISO 14001-2000. Project Environmental Management Plan & Associated Sub-Plans.
d1ace274-bd06-541f-a01c-7f1c177e28e6 | note | Timing or Frequency - Continuous
7b83a5df-184f-550e-a6d9-380aaf793fbd | note | Records & Remarks: Downer - R
b47bee3b-e909-5c5a-b789-ebb7b62df21c | note | Records & Remarks: Alpha Rail - R
ca164304-00ff-4210-a5ac-7afb3b230eba | section | 3.0 - MATERIAL RECEIPT
a5f07bd1-241f-465b-a657-e96650e79413 | checkpoint | 3.1 - All major product items delivered to site shall be : Inspected on receipt then stored in designated area(s)
34d8d33e-b61d-5a24-8078-e518ec84fca4 | note | Application Std. & Acceptance Criteria - Construction Management Plan.
0399e0c7-3e76-5c72-b6ff-18c85c099171 | note | Timing or Frequency - On receipt & Continuous
3047b030-0ed6-5c08-8af8-f1c0dbce9798 | note | Records & Remarks: Downer - R
629f4f12-1adc-535b-92c1-e7c2166f0cfa | note | Records & Remarks: Alpha Rail - W
96de6f88-ad05-447f-8bac-4e8d887b3e85 | section | 4.0 - BONDING INSTALLATION
cfb4045b-2b6f-4e75-be9f-45bc153f5e40 | checkpoint | 4.1 - Balustrade Guard Conductor to PET Equpotential Earth Bar 35 mm2 Cu cable bonds
6e076b11-329a-5eb2-b0fe-babf0da1b7ca | note | Application Std. & Acceptance Criteria - IFC Bonding Plans; AKL Basic Design Drawings; Extraneous Bonding Layouts
260930eb-3013-5031-b9d1-6eb8c096e1b1 | note | Timing or Frequency - PET Cabinet Bonds
aafc2fd6-432c-58aa-a7d9-b969ddfacec4 | note | Records & Remarks: Downer - R
09a6a376-2697-539f-af23-a3e44cbff1cc | note | Records & Remarks: Alpha Rail - X
86f2e8a8-e4bb-4876-8f30-43a3bf74eaea | checkpoint | 4.2 - Girder to Girder Bonds 50 mm2 Cu cable bonds
f2a3a23b-64b6-5b9c-ad10-59948457a404 | note | Application Std. & Acceptance Criteria - IFC Bonding Plans; AKL Basic Design Drawings; Extraneous Bonding Layouts
56df15af-7f2b-5304-88e1-6a2a91c362a1 | note | Timing or Frequency - Girder Bonds
abc4f154-92f3-5209-b104-0ed1ccf06860 | note | Records & Remarks: Downer - R
b44548fb-32d3-54e5-af00-08a96137eaff | note | Records & Remarks: Alpha Rail - X
e412ffdd-e0b1-4a7d-9714-0c81e3fcdce9 | checkpoint | 4.3 - Balustrade Guard Conductor to Balustrade Guard Conductor Bond 35 mm2 Cu cable bonds
1e1580bf-cd51-5379-8b69-9971443dbcef | note | Application Std. & Acceptance Criteria - IFC Bonding Plans; AKL Basic Design Drawings; Extraneous Bonding Layouts
d2a17d52-54cd-5527-94f9-bbcb9a4b9b91 | note | Timing or Frequency - Ballustrades Guard Conductor Bonds
92de21ff-c4ac-5af3-9902-ecf555f21d08 | note | Records & Remarks: Downer - R
e9cca648-e4b9-59a7-9ef7-9e20d38d1da0 | note | Records & Remarks: Alpha Rail - X
0db3ac37-98f0-4e91-bb11-a534a376c092 | checkpoint | 4.4 - Connections & Terminations
b78b44c8-e1a7-5abc-b957-ba52eaf47bbb | note | Application Std. & Acceptance Criteria - AKL Basic Design Drawings
43f808ab-e390-5a40-b444-d179453a3f1a | note | Timing or Frequency - At Procurement
d1950cd8-2fd5-583f-b37a-6242c6d6123c | note | Records & Remarks: Downer - R
c11e8e53-f192-52fa-8316-87ca3d41a638 | note | Records & Remarks: Alpha Rail - X
abf0cadd-b561-48ef-9257-e8b876e3f80f | section | 5.0 - BONDING CONTINUITY TESTS
92b145b9-afc7-42b3-bc1f-bbd8ca6a73ce | checkpoint | 5.1 - Ensure correct Contnuity tester is used. DLRO (Digital Low Resistance Ohmmeter).
594b90e5-4814-595d-9dae-92d2e8879422 | note | Application Std. & Acceptance Criteria - E-SP-AE-61318 AEA Earthing and Bonding
b139046d-792e-5124-ace6-3d7d0aa3bffc | note | ○ E-ST-AE-0101 AEA Earthing and Bonding Design Standards
d35308e6-e2ff-5306-9f1e-e4d06ac0fe99 | note | Timing or Frequency - Prior to test
2eada86a-4f61-5261-9aff-cb247d7df6ad | note | Records & Remarks: Downer - R
3d20691a-36ca-5774-82d9-b5d7366fd52c | note | Records & Remarks: Alpha Rail - R
04ced7b4-9c45-4934-a435-8ecc4cc97949 | checkpoint | 5.2 - Ensure testing equipment is calibrated for use with photo evidence.
0e3817d5-51e4-54fc-9d4d-f40f33f0791e | note | Application Std. & Acceptance Criteria - E-SP-AE-61318 AEA Earthing and Bonding
db7d1dfe-0e58-5aee-9d36-41f2469c1181 | note | ○ E-ST-AE-0101 AEA Earthing and Bonding Design Standards
f8824e67-7efd-5cd2-ae43-7b38febaaa3b | note | Timing or Frequency - Prior to test
e0d078b3-0c18-5e63-bde5-18282b97b984 | note | Records & Remarks: Downer - R
a025a43b-96da-5755-a877-d93488ac205e | note | Records & Remarks: Alpha Rail - R
bba75d67-6687-4c8a-afdf-beee521df285 | checkpoint | 5.3 - Tests shall be conduted at 10 amps and readings should be less than 0.5 ohms.
4b6df07d-c57b-57f1-8330-19beda48503a | note | Application Std. & Acceptance Criteria - ≤ 0.5 ohms, AS/NZS 3000:2007
8cd067e9-6cbd-5691-8028-7e72b55a8ea9 | note | Timing or Frequency - After Bonding
1844b3c2-64d5-5dce-85ea-efc0d1a060cb | note | Records & Remarks: Downer - R
fc58bf03-e5d9-56a3-b3e0-4fcd38635f58 | note | Records & Remarks: Alpha Rail - R
ed591a96-0baf-4ad6-a664-7f532a4e1d1d | checkpoint | 5.4 - Record Test results on ITR Bonding testing sheet.
44c899cd-25a4-5873-82f6-e5db7c14e11f | note | Application Std. & Acceptance Criteria - DNR-43032-NIMT-CHK-001-Rev0 - Homai Bonding Check Sheet
dd56dca0-ff4b-5439-8c7f-af539fbe1dfb | note | Timing or Frequency - After Bonding
40a43da9-513d-5e33-b735-9ae11d34158b | note | Records & Remarks: Downer - R
6fb6f5d1-b8c5-55a3-879b-9f53098fb788 | note | Records & Remarks: Alpha Rail - R
95e27985-79d4-5763-9c1c-74cd39e47ff3 | note | Comments - Test Failed.
aa4c455c-4218-56cc-8869-be9180f9a6ff | note | ○ Need to retest once mortar has cured
fc287f42-f623-48b4-9879-2d16c7f7b902 | section | 6.0 - Insulation Resistance Tests
e7a42ca8-c3be-4cc4-b348-fd761714c6fe | checkpoint | 6.1 - Insulation Resistance test between bridge screen and concrete barrier at 1000V DC to provied result greater than 1M ohm.
d87b548c-e55e-5637-9db4-bd624939ac19 | note | Application Std. & Acceptance Criteria - BECA-4323-10-HOMAI-RPT-001
886c92e5-1a35-5c0d-b6c2-fdefd8484ce9 | note | Timing or Frequency - After Installation
2607a3c9-c897-59c9-ae48-5452c834ea06 | note | Records & Remarks: Downer - W
2fcb8b97-502e-5dfb-b283-63620b69ac64 | note | Records & Remarks: Alpha Rail - R
77915abd-eeaa-40d5-b99b-5554e12db869 | checkpoint | 6.2 - Ensure testing equipment is calibrated for use with photo evidence.
53d94ea6-cb6e-5dff-8eef-1501aca4b116 | note | Application Std. & Acceptance Criteria - E-SP-AE-61318 AEA Earthing and Bonding
42b4171f-83a7-560c-85a8-f33bdb097fd3 | note | ○ E-ST-AE-0101 AEA Earthing and Bonding Design Standards
8a7556d0-b4f7-5238-a200-2bcc47502bdc | note | Timing or Frequency - Prior to test
ec3725a4-e5eb-54f7-94c2-3b7959f17236 | note | Records & Remarks: Downer - W
30137e51-aaca-58d8-9ab9-4a34447a36b9 | note | Records & Remarks: Alpha Rail - R
e59f75ad-2a66-42aa-bd84-cf8f5b166476 | checkpoint | 6.3 - Record Test results on ITR Bonding testing sheet.
7ed7cbfb-79b5-5e40-8c77-f2e4d9f2408c | note | Application Std. & Acceptance Criteria - KR-43029-NAL-ITR-005-Rev0 - OLE Bonding Test Sheet
a71985d3-9365-5ae3-a627-d2c39bfa7a09 | note | ○ KR-43029-NAL-ITR-028-Rev0 - OLE Bonding Check Sheet
8e45589c-69bf-57f1-82d2-d9e0c879d16a | note | Timing or Frequency - After Bonding
67c0ad04-6b67-5985-bb53-c63b27668fb6 | note | Records & Remarks: Downer - R
1965d37b-89ee-5396-a9ff-65991d8a3d20 | note | Records & Remarks: Alpha Rail - R
6d15b3b9-eeaa-407b-b046-88e956802e13 | checkpoint | 6.4 - Record Test results on ITR Bonding testing sheet.
3fe897ab-1a1e-5a5e-9ba7-5109f9ac307a | note | Application Std. & Acceptance Criteria - DNR-43032-NIMT-CHK-002-Rev0 - Homai IR Check Sheet
a8e2c80f-55b8-5be8-9b7f-9da953238b5e | note | Timing or Frequency - After Bonding
b044673b-6817-5d4c-9f93-bee8e35fa8cc | note | Records & Remarks: Downer - R
7ecec807-c001-5c1e-963a-19f9ab095ffa | note | Records & Remarks: Alpha Rail - R
739e62fc-b378-4baf-891a-4961aa5367e3 | section | 7.0 - AS CONSTRUCTED RECORDS
e3668f4a-1ce0-448a-97a0-7ae052c21648 | checkpoint | 7.1 - Relevant RFI(s).
139b35b7-c4ff-5c66-919f-597e1fb6a695 | note | Application Std. & Acceptance Criteria - All RFIs closed
3ce90007-acac-5a5a-afe9-3b15a7d78328 | note | Records & Remarks: Downer - R
9cbcbd9e-3cb4-5992-9765-3cdcbd86d922 | note | Records & Remarks: Alpha Rail - H
e8b1534e-0b2b-4e78-856d-c0af3db76c52 | signoff | AUTHORITY HOLDPOINT
816925ef-5722-4c1c-8a24-cfdc209f1873 | checkpoint | 7.2 - Snags
dd9d89b1-0be3-57e6-8222-345829c32f6f | note | Application Std. & Acceptance Criteria - Snags to be rectified/addressed with evidence to be sent to engineer for confirmation to allow for close out
a062e5dd-eded-48c0-9736-b4bad296d706 | checkpoint | 7.3 - Record on Bonding Plans.
b93adee9-61ee-56f7-b03e-762aa6c8eebc | note | Application Std. & Acceptance Criteria - IFC Bonding Plans
7ae63f9e-13f6-56de-9a06-9f2af5767876 | note | Timing or Frequency - After Installation
239a3f70-5e52-5c29-89fb-f7ddaecf5750 | note | Records & Remarks: Downer - W
cc34092a-0c50-56f1-ac00-8ea6298ee76e | note | Records & Remarks: Alpha Rail - W
7864f093-f73d-404e-81ea-68794a580e81 | checkpoint | 7.4 - COC issued no more than 20 days after works are completed.
022f12b9-49c6-5ba4-9b2a-9c57cdb408a4 | note | Application Std. & Acceptance Criteria - AS/NZS 3000:2007
71a0fd58-cee6-5d2e-ab91-ba60f0d6a317 | note | Timing or Frequency - After Installation
6316a744-fd66-5137-9541-c12d0903939e | note | Records & Remarks: Downer - H
a5b11160-1b87-5a58-a15b-6f744fe5eb92 | note | Records & Remarks: Alpha Rail - H
bbcb1022-6ae6-46fd-82f4-222000402873 | signoff | AUTHORITY HOLDPOINT
0695af30-2c15-4d6a-8127-943ceee05103 | checkpoint | 7.5 - ROI Issued no more than 20 working days after works completed.
38743e19-f207-5275-92c5-3b2b155ce836 | note | Application Std. & Acceptance Criteria - AS/NZS 3000:2007
9e81e8ec-ea40-5698-8904-782bb3b4488e | note | Timing or Frequency - After Installation
b3de71b7-ab68-4113-a045-0b647c3c484c | checkpoint | 7.6 - EAC part 1&2 signed 20 working days after works completed.
7501d18d-db60-59e3-80f1-20279a500eee | note | Application Std. & Acceptance Criteria - E-ST-AL-0183-FO EAC Certificate
a18eccfe-865a-58b9-ac43-2ebd861d3b46 | note | Timing or Frequency - After Installation
a36b6697-2851-4ac9-ae3f-11ce8779a19c | section | ITP APPROVAL PROCESS
74f151a7-6b91-45de-a38e-19ebe795e709 | checkpoint-no-value | Works completed satisfactorily in accordance with relevant Sandards & Specifications as indicated above
0bef5289-64ad-5818-a32f-925a32e28d64 | note | Prepared by: Alan Twine
22caea6f-2e9d-5e2e-95b3-f6548842b784 | note | Approved by: Tab Kilisimasi
b66d0866-d9f7-5118-8e08-ad569851aee7 | note | Distributed: Danny Cox
3d426d73-532c-4a45-ae10-a0f90d70e762 | signoff | Signed on behalf of Installer : Alpha Rail
59b938db-22c8-458f-893a-4ea8579a38ef | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
515a6527-3233-5bbf-ab1b-bfd670db7896 | textbox | Contractor's Rep Name:
2107395d-0808-5fc2-b0eb-73e9ccc46dab | textbox | Engineer's Rep. Name:
b14a9d27-abc6-51aa-b1dc-98021fcfff3b | date | Date:
f1ac128b-2eed-4a8e-ab60-dd8f03a7625c | signoff | Add Signature