## Table 1
a PFS Engineering Lid 175 RIYO<lea Rd Hamitton. New Zealand Ph: +&17 856 6225 fx; +64 7 856 6226 |  |  | INSPECTION AND TEST PLAN | [7 empty] | Downer
Inspection & Test Plan Description: Downer ITP for site balustrade installation - Homai pedestrian bridge
Downer- Homai pedestrian bridge |  |  |  | Location: Hamilton | [8 empty] | ITP Doc No; ITP-004-39028.VO04
Customer: Downer |  |  |  | Customer Job Reference: 746-24-847-AC | [8 empty] | Revision: A
Prepared by: Bashir Heidarian |  |  |  | PFS Job Reference 39028.V004
Date: 12/12/2024 |  |  |  | Review by: Regan Hose
Construction Category |  | CC3 | Service Category | Date: 12/12/2024 SC2 |  | Fabrication Category FC1 |  | Weld Category SP |  |  |  |  | Tolerance Class 2
Seq | Task/ QA Activity | Specification Standard | Acceptance Criteria |  | Certify Doc I Ref |  | PFS Engineering |  | Sign | C | Subcontracted scope | Sign | C | Downer | algn | C | Remark
Engineering
1 | Inspection and Test Plan Reviewed and Approved by Customer | Project Structure Specification C0702 Rev. 01 IFC structure OWG | Inspection and Test plan shall be submitted to the Engineer for review and approval before fabrication is commenced. |  | IFC DWGs |  | PM/PE |  | lnltlal: l\\ Sig | s |  |  |  | Downer | Initial: Digitally signed by Nas Matar Nas DN: cn=Nas Matar gn=Nas Matar c=NZ SigMnat : Zealand o=T&I New Zealand l=NZ New ou=Downer e=nas.matar@downer.c o.nz ar Reason: I have reviewed this document Location: Date: 2025-02-21 11:28+13:00 | H
Good Receipt on site
2 | Inspection upon receipt at site | Project Structure Specification C0702 Rev. 01 IFC structure OWG | The material receipt at site need to be visually inspected for quantity and make sure no damage occurred during transport |  | IFC DWG |  | PM/PE |  | Initial: Sign: | V |  |  |  | Downer | Initial: Digitally signed by Nas Matar Nas DN: cn=Nas Matar gn=Nas Matar c=NZ New Zealand l=NZ New Sign: Reason: I have Zealand o=T&I Mat ou=Downer e=nas.matar@downer.c o.nz ar reviewed this document Location: Date: 2025-02-21 11:28+13:00 | R
Installation of Studs
3 | Installation of Templates to identify the Hole locations | Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG | Anchors Hole locations should be in complied with IFC Drawing |  | IFC Drawing |  | Team Leader |  | Initial: ii' /' Slgn:1 | ._o
4 | Drilling the holes based in concrete | Project Structure Specification C0702 Rev. 01 | Studs' Holes location should be in compliance with IFC Drawing 22 mm Hole Diameter for M20 Studs Hole depth >210 mm |  | IFC Drawing Hilti HIT-RE 500 V4 Technical Data sheet |  | Team Leader |  | lnitlal:/11/' • Slgn,Y | D
5 | Blow out all holes | Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG | Blow out all hole to make sure all holes are free from dust |  | IFC Drawing Hilli HIT-RE 500 V4 Technical Data sheet |  | Team Leader |  | lnitial:"'1/' Sign:¥ | K
6 | Chemical Anchoring | Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure OWG | Epoxy Studs using Hilti HIT-RE 500 V4 Make sure minimum 210 mm the embedment to achive Wait for epoxy to cure |  | IFC Drawing Hilti HIT-RE 500 V4 Technical Data sheet |  | Team Leader |  | Initial Sign:
Seq | Task/ QA Activity | Spectticatlon Standard | Acceptance Criteria |  | Certffy Doc/ Ref |  | PFS Engineering |  | Sign | C | Subcontracted scope | Sign | C | Downer | elgn | C | Remark
7 | Land Base plates on studs level base plates with Jacking nuts | Project Structure Specification C0702 Rev. 01 | Make sure the base plates are leveled and confirm their elevation |  | IFC Drawing |  | Team Leader |  | lnlUal:/J?J) Slgn:14"r | V,D
8 | Final alignment Bolt wide flange beams to base plate | Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG Standard operation procedure for steel structure bolt tightening SHEQ-01-02-0038 | Verify that the structural component are aligned based on IFC Drawing Bolts to be Installed and snug tightened |  | IFC Drawing |  | Team Leader |  | lnitial: p Slgn:J#r | H
9 | Installation of Dura wall panels and cam covers | Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG | Carefully position wall panels" and cam covers according to the approved drawings. |  | IFC DWGs |  | Team Leader |  | Initial: Sign:)I'/ | D
Assembly -Lightning and Conduit Bracket
10 | Holing | Project Structure Specification C07 Rev. 01 IFC structure DWG SHEQ-01-02-0040 | Manual holing shall be performed on GRP material. |  | IFC DWGs |  | Team Leader |  | lnitial:/t'I? Sign: | _. D
11 | Dimension check | IFC DWG | Compliance with IFC DWGs |  |  |  | Team Leader |  | lnitial:/Z1p Sign:¥ p | D
12 | Visual inspection of Fasteners | IFC Drawing | All fasteners (bolts, nuts, washers) are to be in compliance with the Project requirement (Grade, Size and Length) |  | IFC Drawing |  | Team Leader |  | lnltlal:,/?1 Sign:p1_pC | V
13 | Snug tightening of fastener to fasten the brackets to the GRP material | Standard operation procedure for steel structure bolt lightening SHEQ-01-02-0038 | 100% of fixings securing brackets to be inspected for snug tight condition and marked with coloured paint pen to confirm fixing condtion has been checked and verified. |  |  |  | Team Leader |  | Initial: Sign:
14 | Assembly of the angles between bracke!s | Project Structure Specification C07 Rev. 01 IFC structure DWG | The angles to be assembled between bracket with fasteners |  | IFC DWGs |  | Team Leader |  | Initial Sign | V V/D
15 | Snug tightening of fastener to fasten angles to the brackets | Standard operation procedure for steel structure bolt tightening SHE0-01-02-0038 | 100% of fixings securing brackets and angles to be inspected for snug tight condition and marked with coloured paint pen to confirm fixing condtion has been checked and verified |  |  |  | Team Leader |  | lnit1a1,/?J/t:7 Sign: | v
16 | Final Inspection | IFC Drawings, AS/NZS 1554.1:2014 Category SP | Visual and Dimensional inspections completed by PFS Project Manager to confirm manufactured items have been manufactured to acceptable standard & tolerance and approved to progress to protective coatings. >Confim1ation that dimensional inspections have been completed in line with SHEQ-01-02-0035 Product Inspection Procedure >Confirmation that required quantity and type's of NOE has been completed and any identified defects have been remediated |  | IFC OWGs |  | Site project Manager |  | Initial: I?.\.\ Sig | RA
Quality Review
Seq | Task/ QA Activity | Specification Standard | Acceptance Criteria |  | Certify Doc I Ref |  | PFS Engineering |  | Sign | C | Subcontracted, scope, | Sign | C | Downer | sign | C | Remark
17 | Compile, review and submit documentation | Project Structure Specification C07 Rev. 01 IFC structure DWG | Documentation and reports to support installation of steel structure items compiled into PFS Manufactures Data Report |  | PFS Manufactures Data Report |  | Site project Manager |  | Initial: R\\ Sig | s |  | ' ' |  | Downer | Initial: Sign: Digitally signed by Nas Matar Nas DN: cn=Nas Matar gn=Nas Matar c=NZ New Zealand l=NZ New Zealand o=T&I Mat ou=Downer e=nas.matar@downer. co.nz Reason: I have ar reviewed this document | RA
Date: 2025-02-21 11:27+13:00
PFS Revision Record: 39028.VO04-ITP-004-39028.VO04 RevA
| Approved by [Engineer/Client] |  | Name· |  | Date: |  | Sign:Nas Mat ar | Digitally signed by Nas Matar DN: cn=Nas Matar gn=Nas Matar c=NZ New Zealand l=NZ New Zealand o=T&I ou=Downer e=nas.matar@downer.c o.nz Reason: I have reviewed this document Location: Date: 2025-02-21 11:28+13:00
| Issued for Construction |  | Name: °""""" Ut.se... |  | Date 12/11/ ;).f.1 |  | Sign: rt..11'1-.A
Comments{Notes:
-..,